## Sheet1
Unnamed: 0 | Date | 2024-06-19 | Unnamed: 3 | Unnamed: 4 | Unnamed: 5 | Unnamed: 6 | Unnamed: 7 | Unnamed: 8 | Unnamed: 9 | Unnamed: 10 | Unnamed: 11
| Cumulative Totals across all orders |  |  | Count current status | [5 empty] | Count of missing dates
| Number of orders raised |  | 2913 | 1. Provisioning - In progress with OLO |  |  | 1. Provisioning = fixed line ordered – initial status when order in progress with OR. |  |  | Initial OLO requested date
|  |  |  | 2. Commissioning - Router install is progressing |  |  | 2. Commissioning = Awaiting Router install and in progress |  |  | Forecasted OLO install Date
| OLO circuits completed |  |  | 3. In life Router installed (flat file info provided) |  |  | 3. In life = Router installed (flat file info provided)
| Router installs completed by Allwyn | 1 |  | 4. On hold – Allwyn |  |  | 4. On hold from Allwyn = Order will be reraised in a future batch
Sites within CSL acceptance testing
| Completed - Sites in support |  |  | 5. On hold - Supplier |  |  | 5. On hold – Supplier
|  |  |  | 6. CSL - Failures during acceptance testing |  |  | 6. Failed router install (router does not pass 3d acceptance period)
| Abortive Visit - Customer Access (A1) |  |  | 7. Order cancelled ( terminated ) |  |  | 7. Order cancellation = Allwyn requested to terminated the site as they are no longer selling lottery.
| Abortive Visit - OLO no-show/ scheduling issue (A2) |  |  | 8. Order change |  |  | 8. Order change from Allwyn
| Abortive Visit - OLO installation issue (A3) |  |  | 9. Completed - CSL have taken site into support |  |  | 9. Completed - note these will be removed from the CSL report once taken into support and passed 3d acceptance.
| Premium Upgrade (A4) |  |  | 10. OR line test failures prior to router install |  |  | 10. Line test failures : total number of the sites that failed in line test priot to rtr install.
Advanced Upgrade (A4)
ECC other (A4)
| Cancelled Order Request |  |  | Count current actions
| Order Change Request |  |  | 1.Allwyn to approve additional charges
| High Gain Antenna Upgrade request |  |  | 2.Allwyn to arrange access
| Type 4 upgrade to VSAT |  |  | 3.Allwyn to arrange rtr install
| Failed router acceptance from CSL |  |  | 4.Vodafone
| Failed Allwyn router installation |  |  | 5.CSL
6.No action
C10 figure from CSL report
C9 figure from CSL report
| 6. CSL - Failures during acceptance testing | take figure CSL report
| Sites within CSL acceptance testing | take figure CSL report |  | Ask CSL if they can provide report for this figure
| Completed - Sites in support | take figure CSL report
| 10. OR line test failures prior to router install | take figure from line test tracker shared with CSL
| Number of orders raised | Figure does not include on holds, cancelled/terminated. But does include completed sites
figure comes from Martin's master file