## Sheet1
| Retailer ID | SR No. | Order batch date | Allwyn Site Type (ie Type 1 or 2) | SOGEA / FTTP | Store Name | City | Postcode | Date of comment | Updates / Comments | Concat | OR reach updates | CSL #update | Action required raised date | Action required | Action response from Allwyn date | Action response from Allwyn | Action owner | Access Service Id (VF Access Service Id) | Connection ID (CSL Service) | Site Status | Appointment Slot - AM (9am-1pm) / PM (1pm - 5pm) | Site Survey Date | Initial OLO requested date | Forecasted OLO install Date | Actual completion date OLO First Poll Date | OLO Service Activated | Line test (Fault) | Forecasted Allwyn Router install date | Actual Allwyn Router install date | Scheduled Router Install Date | Appointment Slot - AM (9am-1pm) / PM (1pm - 5pm)2 | SG Installer / Engineer Name | SG Installer / Engineer Contact Number | Completed Router Install Date & Time | CSL Router - S/N | New2 | S/N notification date to CSL | Valiation | New | Same
0 | 632626 | 2 | Batch 1 Feb24 | Type 1 | SOGEA | Harveen Convenience Store | Melton Mowbray | LE13 0QW | 2024-05-08 | 16/02/24: Order Completed | 16/02/24: Order Completed | [7 empty] | VFS1097771 | 30012233 | 6.Failed router install | AM |  | 2024-02-14 | 2024-02-14 | 2024-02-14 | TRUE |  | 2024-03-12 | 2024-03-12 | 2024-03-11 |  | Mike Jones | 07957 175416 | 2024-03-11 | 236004882547 | 236004882547 |  | 1
1 | 444068 | 4 | Batch 1 Feb24 | Type 1 | SOGEA | The Village Store | High Peak | SK22 2JE | 2024-05-02 | 22/02/2024: Order completed | 22/02/2024: Order completed |  |  | 2024-03-14 | 14/03/24 - Allwyn to reschedule rtr install. 12/03/24: Allwyn to arrange access for OR on the 14/03. - 13/03 dependent on hearing back from retailer by 1200 on the 13/03. - closed |  |  | 3.Allwyn to arrange rtr install | VFS977932 | 30012239 | 2.Commissioning | AM |  | 2024-02-16 | 2024-02-16 | 2024-02-16 | TRUE |  | 2024-03-13 | 2024-03-13 | 2024-07-26 | AM | Liam Curtain Marion Aitken | [5 empty] | 0
2 | 468904 | 25 | Batch 1 Feb24 | Type 1 |  | One Stop | Hull | HU9 2EU | 2024-05-30 | 6/9/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_5/9/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_4/9/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_3/9/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_2/9/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_29/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_28/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_27/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_23/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_22/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_21/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_20/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_19/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_19/8/2024:01294677 _x000D_16/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_15/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_14/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_13/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_12/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_9/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_8/8/2024:01/03/2024 _x000D_6/8/2024:01/03/2024 _x000D_5/8/2024:01/03/2024 _x000D_2/8/2024:01/03/2024 _x000D_1/8/2024:01/03/2024 _x000D_31/7/2024:01/03/2024 _x000D_31/7/2024:01/03/2024 _x000D_30/7/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_29/7/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_29/7/2024:01294677 _x000D_26/7/2024:01294677 _x000D_24/7/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_23/7/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_22/7/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_22/7/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_08/03/24: Order completed 14/02/24: Order Re-raised and recommitted for 26/02 09/02/24: Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. | 9/9/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_6/9/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_5/9/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_4/9/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_3/9/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_2/9/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_29/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_28/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_27/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_23/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_22/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_21/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_20/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_19/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_19/8/2024:01294677 _x000D_16/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_15/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_14/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_13/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_12/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_9/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_8/8/2024:01/03/2024 _x000D_6/8/2024:01/03/2024 _x000D_5/8/2024:01/03/2024 _x000D_2/8/2024:01/03/2024 _x000D_1/8/2024:01/03/2024 _x000D_31/7/2024:01/03/2024 _x000D_31/7/2024:01/03/2024 _x000D_30/7/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_29/7/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_29/7/2024:01294677 _x000D_26/7/2024:01294677 _x000D_24/7/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_23/7/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_22/7/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_22/7/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_08/03/24: Order completed 14/02/24: Order Re-raised and recommitted for 26/02 09/02/24: Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. | 0 | #Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. |  | 3/28/2024: Allwyn to reach out to the store and make sure there is available power socket to install the line. 22/02/24: Allwyn advised that engineer tried to attend site today 22/02 to install cct, engineer was turned away. Action CSL to provide more detail re the visit and to advise on the dependencies from KCOM to complete. Retailer stated that KCOM advised that store needs to be closed in order to complete the order, exact requirements tbc before access can be arranged. 27/02/24: KCOM have advised that there is no need to complete any out of hours work as all work can be completed in store hours. Appointment scheduled for the 06/03/24. Action Allwyn to arrange site access with end user for the 06/03. - closed 01/03 |  | 01/03/24; Allwyn have confirmed access for the 06/03 | 3.Allwyn to arrange rtr install | BUS0003530 | 30012256 | 2.Commissioning | AM | [6 empty] | 2024-03-20 |  | 2024-07-22 | [7 empty] | 0
3 | 627387 | 16 | Batch 1 Feb24 | Type 1 | SOGEA | Ovingdean Village Stores | Brighton | BN2 7BD | 2024-04-18 | 6/9/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_5/9/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_4/9/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_3/9/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_2/9/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_29/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_28/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_27/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_23/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_22/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_21/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_20/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_19/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_19/8/2024:01294677 _x000D_16/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_15/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_14/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_13/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_12/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_9/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_8/8/2024:01/03/2024 _x000D_6/8/2024:01/03/2024 _x000D_5/8/2024:01/03/2024 _x000D_2/8/2024:01/03/2024 _x000D_1/8/2024:01/03/2024 _x000D_31/7/2024:01/03/2024 _x000D_31/7/2024:01/03/2024 _x000D_30/7/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_29/7/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_29/7/2024:01294677 _x000D_26/7/2024:01294677 _x000D_24/7/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_23/7/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_22/7/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_22/7/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_08/03/24: Order completed 14/02/24: Order Re-raised and recommitted for 26/02 09/02/24: Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. | 6/9/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_5/9/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_4/9/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_3/9/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_2/9/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_29/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_28/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_27/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_23/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_22/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_21/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_20/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_19/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_19/8/2024:01294677 _x000D_16/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_15/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_14/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_13/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_12/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_9/8/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_8/8/2024:01/03/2024 _x000D_6/8/2024:01/03/2024 _x000D_5/8/2024:01/03/2024 _x000D_2/8/2024:01/03/2024 _x000D_1/8/2024:01/03/2024 _x000D_31/7/2024:01/03/2024 _x000D_31/7/2024:01/03/2024 _x000D_30/7/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_29/7/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_29/7/2024:01294677 _x000D_26/7/2024:01294677 _x000D_24/7/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_23/7/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_22/7/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_22/7/2024:#Update - Engineering team have advised that there is no need to complete any out of hour work. All work can be completed in store hours. Install booked for 06/03. _x000D_08/03/24: Order completed 14/02/24: Order Re-raised and recommitted for 26/02 09/02/24: Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. |  |  | 2024-04-18 | 18/04/2024: Allwyn to check with the retailer 07/03 - Action Allwyn to arrange access for the 19/03/24. - closed 26/02/2024: Supplier requires access to site. Action Allwyn to arrange access with customer and advise date. 29/02 - closed access not required. 23/02/24: Supplier system delay which is holding up order order progressing. Our Suppliers have given us a review date of 27/02/2024. 16/02/24: Action CSL to provide update from OR W/C19/02. 19/02/24: Supplier to provide update 22/02/24. |  | 14/03/24 - Allwyn 13/03/24 -Spoken to Retailer (Michelle) confirmed visit for the 19th March JP 13/03 - 19/03 action closed | 6.No action | VFS977908 | 30012232 | 6.Failed router install | AM |  | 2024-02-14 | 2024-03-20 | 2024-03-20 | TRUE |  | 2024-04-09 | 2024-04-09 | 2024-04-09 |  | Barry Rajoo | 07957 175420 | 2024-04-12 | 236004882479 |  |  | 1
4 | 470023 | 22 | Batch 1 Feb24 | Type 1 | SOGEA | One Stop | Boston | PE21 8QN | 2024-04-11 | 11/04/2024: Failed due to an average RSSI of -91.2 (Poor) and RSRP is also poor. We have also seen the router moving repeatedly other providers which supports poor signal. Recommend that a high gain aerial is installed to improve signal strength and quality 26/03/2024: Engineer installed new socket for sogea services. Router now online on the DSL on CSL network. 22/03/2024: Openreach engineer has been booked for 26/03 AM slot 21/03/24 - OR did not complete as there are external that need to completed. OR to provide update. 13/03/24 - Store was closed when OR attended to complete provision. Appointment rebooked for the 20/03. CSL seeking more info from OR. CSL to confirm if there is a abortive visit charge. 09/02/2024: Engineer has advised 'Customer owns shop with lotto machine, lotto booked in for FTTP. Shop owner unhappy with this and will not allow job due to drilling through walls.' Please let us know how you wish to proceed with this, we need to reappoint in 15 days otherwise this order will be cancelled. VF to raise Abortive visit charge - closed 05/03 charge approved by Allwyn. 06/03/24 - Allwyn stated that this order might be downgraded to type 3 due to difficulties in trying to arrange works - 07/03 will not be downgraded, app to go ahead on the 12/03. | 11/04/2024: Failed due to an average RSSI of -91.2 (Poor) and RSRP is also poor. We have also seen the router moving repeatedly other providers which supports poor signal. Recommend that a high gain aerial is installed to improve signal strength and quality 26/03/2024: Engineer installed new socket for sogea services. Router now online on the DSL on CSL network. 22/03/2024: Openreach engineer has been booked for 26/03 AM slot 21/03/24 - OR did not complete as there are external that need to completed. OR to provide update. 13/03/24 - Store was closed when OR attended to complete provision. Appointment rebooked for the 20/03. CSL seeking more info from OR. CSL to confirm if there is a abortive visit charge. 09/02/2024: Engineer has advised 'Customer owns shop with lotto machine, lotto booked in for FTTP. Shop owner unhappy with this and will not allow job due to drilling through walls.' Please let us know how you wish to proceed with this, we need to reappoint in 15 days otherwise this order will be cancelled. VF to raise Abortive visit charge - closed 05/03 charge approved by Allwyn. 06/03/24 - Allwyn stated that this order might be downgraded to type 3 due to difficulties in trying to arrange works - 07/03 will not be downgraded, app to go ahead on the 12/03. |  |  |  | 08/03/24: Allwyn to arrange access for the 20/03 - closed Allwyn have confirmed access for 20/03. 28/02/24: CSL to push completion date out to begining March 24. Order will be cancelled if upgrade is not approved by this date. - closed. 22/02/24 - Order also needs to upgraded to a premium as 20M of cabling is required. Action Allwyn to provide approval to proceed. 21/02/24: Action Allwyn to discuss with retailer on how to proceed, new install date to be agreed. |  |  | 6.No action | VFS929513 | 30012254 | 6.Failed router install | AM |  | 2024-02-20 | 2024-03-21 | 2024-03-21 | TRUE |  | 2024-02-05 | 2024-02-05 | 2024-04-02 |  |  |  | 2024-04-02 | 236004882500 |  |  | 1
5 | 665554 | 20 | Batch 1 Feb24 | Type 1 | SOGEA | Steeple Aston Stores | Bicester | OX25 4RR | 2024-04-11 | 03/04/2024: order completed 19/03/24: New order added to report | 03/04/2024: order completed 19/03/24: New order added to report |  |  | 2024-03-26 | 26/03/2024: Closed 26/03/2024 22/03/2024: Allwyn's action, is to make the retailer awar that the retailer aware of the visit on 26/03 AM (anytime between 8am - 1pm) to arrange access. 19/03/24 - Action Allwyn to arrange access with retialer for OR to fix fault. 20/02/04: Action Allwyn to discuss with retailer on how to proceed. OR requesting revisit on the 06/03 if Allwyn can arrange site access. - closed 01/03 |  | 01/03/24; Allwyn have confirmed access for the 07/03 - closed 08/03 |  | VFS977926 | 30012252 | 6.Failed router install | AM |  | 2024-02-19 | 2024-03-27 | 2024-03-27 | TRUE |  | 2024-03-23 | 2024-03-24 | 2024-03-22 |  | Barry Rajoo | 07957 175420 | 2024-03-22 | 236004882482 |  |  | 1
6 | 462199 | 41 | Batch 2 Apr24 | Type 1 | FTTP | Blair Convenience Store | Dalry | KA24 4DT | 2024-04-04 | 03/04/2024: order completed 19/03/24: New order added to report | 03/04/2024: order completed 19/03/24: New order added to report |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFP2300485 | 30013113 | 2.Commissioning | AM |  | 2024-04-02 | 2024-04-02 | 2024-04-02 | TRUE |  | 2024-04-17 |  | 2024-05-15 |  | Jan Mitchell | 7392452470 |  |  |  |  | 0
7 | 443417 | 43 | Batch 2 Apr24 | Type 1 | SOGEA | Spar Stores | Ayr | KA6 6PH | 2024-04-04 | 03/04/2024: order completed 9/03/24: New order added to report | 03/04/2024: order completed 9/03/24: New order added to report |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS939479 | 30013116 | 2.Commissioning | AM |  | 2024-04-02 | 2024-04-02 | 2024-04-02 | TRUE |  | 2024-04-17 |  | 2024-05-15 |  | Jan Mitchell | 7392452470 |  |  |  |  | 0
8 | 435871 | 37 | Batch 2 Apr24 | Type 1 | FTTP | Rushden Mini Market | RUSHDEN. | NN10 0QE | 2024-04-09 | 04/04/2024: Order completed 19/03/24: New order added to report | 04/04/2024: Order completed 19/03/24: New order added to report |  |  | 2024-04-09 | 09/04/2024: CSL to provide updates. Closed 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS1096837 | 30013098 | 6.Failed router install | AM |  | 2024-04-02 | 2024-04-03 | 2024-04-03 | TRUE |  | 2024-04-17 |  | 2024-04-29 |  | Barry Rajoo | 07957 175420 | 2024-06-13 | 23A004945241 |  | 2024-07-01 | 1
9 | 470551 | 58 | Batch 2 Apr24 | Type 1 | FTTP | Nisa Local | Manchester | M13 9AB | 2024-04-05 | 04/04/2024: Order completed 19/03/24: New order added to report | 04/04/2024: Order completed 19/03/24: New order added to report |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 6.No action | VFP2300490 | 30013126 | 6.Failed router install | AM |  | 2024-04-03 | 2024-04-03 | 2024-04-03 | TRUE |  | 2024-04-19 | 2024-04-29 | 2024-04-29 |  | RED TEAM 1 | TBC | 2024-04-29 | 238004917259 |  |  | 1
10 | 660339 | 70 | Batch 2 Apr24 | Type 1 | SOGEA | Redmonds Convenient Store | Sunderland | SR5 5PJ | 2024-05-14 | 03/04/2024: order completed 19/03/24: New order added to report | 03/04/2024: order completed 19/03/24: New order added to report |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS939493 | 30013128 | 6.Failed router install | AM |  | 2024-04-03 | 2024-04-03 | 2024-04-03 | TRUE |  | 2024-04-19 | 2024-05-09 | 2024-05-09 |  | RED TEAM 1 | TBC | 2024-05-09 | 238004917220 |  |  | 1
11 | 466796 | 82 | Batch 2 Apr24 | Type 1 | FTTP | Pitchforth News | Liverpool | L23 3AT | 2024-05-09 | 05/04/2024: Order completed. 19/03/24: New order added to report | 05/04/2024: Order completed. 19/03/24: New order added to report |  |  | 2024-04-04 | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 6.No action | VFP2300406 | 30013163 | 6.Failed router install | AM |  | 2024-04-03 | 2024-04-03 | 2024-04-03 | TRUE |  | 2024-04-19 | 2024-04-25 | 2024-04-25 |  | RED TEAM 1 | TBC | 2024-04-25 | 238004917254 |  |  | 1
12 | 468423 | 87 | Batch 2 Apr24 | Type 1 | SOGEA | A A News | MANCHESTER | M14 7LT | 2024-04-06 | 01/05/2024: OR reported a fault- waiting CSL to provide date to fix 05/04/2024: Order completed. 19/03/24: New order added to report | 01/05/2024: OR reported a fault- waiting CSL to provide date to fix 05/04/2024: Order completed. 19/03/24: New order added to report |  |  | 2024-04-04 | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS939394 | 30013183 | 2.Commissioning | AM |  | 2024-04-04 | 2024-04-04 | 2024-04-04 | TRUE |  | 2024-04-19 |  | 2024-04-29 |  | RED TEAM 1 | TBC |  |  |  |  | 0
13 | 667554 | 88 | Batch 2 Apr24 | Type 1 | SOGEA | Ponty Convenience Store | Pontypridd | CF37 4TR | 2024-05-01 | 05/04/2024: Order completed 19/03/24: New order added to report | 05/04/2024: Order completed 19/03/24: New order added to report |  |  | 2024-04-04 | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 6.No action | VFS939397 | 30013154 | 6.Failed router install | AM |  | 2024-04-04 | 2024-04-04 | 2024-04-04 | TRUE |  | 2024-04-17 | 2024-04-18 | 2024-04-18 |  |  |  | 2024-04-18 | 236004882514 |  |  | 1
14 | 617772 | 96 | Batch 2 Apr24 | Type 1 | SOGEA | Town Shop | Ilford | IG3 8LA | 2024-04-06 | 6/9/2024:#Update Fault identified between internal DP and NTE. This was shown by a damaged / missing socket. The source of the damage was identified as unknown third party. Engineer replaced. Engineer has not done anything with star wiring / bridge taps . No star wiring / bridge taps / VRI / power line technology issue found. Engineer has provided / replaced NTE because upgradation of NTE is required. Engineer has provided / replaced SSFP because upgradation of SSFP is required. Engineer hasn't found any issue with modem / router. Engineer hasn't found any issue with extension wiring. _x000D_5/9/2024:#Update Fault identified between internal DP and NTE. This was shown by a damaged / missing socket. The source of the damage was identified as unknown third party. Engineer replaced. Engineer has not done anything with star wiring / bridge taps . No star wiring / bridge taps / VRI / power line technology issue found. Engineer has provided / replaced NTE because upgradation of NTE is required. Engineer has provided / replaced SSFP because upgradation of SSFP is required. Engineer hasn't found any issue with modem / router. Engineer hasn't found any issue with extension wiring. _x000D_4/9/2024:#Update Fault identified between internal DP and NTE. This was shown by a damaged / missing socket. The source of the damage was identified as unknown third party. Engineer replaced. Engineer has not done anything with star wiring / bridge taps . No star wiring / bridge taps / VRI / power line technology issue found. Engineer has provided / replaced NTE because upgradation of NTE is required. Engineer has provided / replaced SSFP because upgradation of SSFP is required. Engineer hasn't found any issue with modem / router. Engineer hasn't found any issue with extension wiring. _x000D_3/9/2024:#Update Fault identified between internal DP and NTE. This was shown by a damaged / missing socket. The source of the damage was identified as unknown third party. Engineer replaced. Engineer has not done anything with star wiring / bridge taps . No star wiring / bridge taps / VRI / power line technology issue found. Engineer has provided / replaced NTE because upgradation of NTE is required. Engineer has provided / replaced SSFP because upgradation of SSFP is required. Engineer hasn't found any issue with modem / router. Engineer hasn't found any issue with extension wiring. _x000D_2/9/2024:#Update Fault identified between internal DP and NTE. This was shown by a damaged / missing socket. The source of the damage was identified as unknown third party. Engineer replaced. Engineer has not done anything with star wiring / bridge taps . No star wiring / bridge taps / VRI / power line technology issue found. Engineer has provided / replaced NTE because upgradation of NTE is required. Engineer has provided / replaced SSFP because upgradation of SSFP is required. Engineer hasn't found any issue with modem / router. Engineer hasn't found any issue with extension wiring. _x000D_29/8/2024:#Update Fault identified between internal DP and NTE. This was shown by a damaged / missing socket. The source of the damage was identified as unknown third party. Engineer replaced. Engineer has not done anything with star wiring / bridge taps . No star wiring / bridge taps / VRI / power line technology issue found. Engineer has provided / replaced NTE because upgradation of NTE is required. Engineer has provided / replaced SSFP because upgradation of SSFP is required. Engineer hasn't found any issue with modem / router. Engineer hasn't found any issue with extension wiring. _x000D_28/8/2024:#Update Fault identified between internal DP and NTE. This was shown by a damaged / missing socket. The source of the damage was identified as unknown third party. Engineer replaced. Engineer has not done anything with star wiring / bridge taps . No star wiring / bridge taps / VRI / power line technology issue found. Engineer has provided / replaced NTE because upgradation of NTE is required. Engineer has provided / replaced SSFP because upgradation of SSFP is required. Engineer hasn't found any issue with modem / router. Engineer hasn't found any issue with extension wiring. _x000D_27/8/2024:#Update Fault identified between internal DP and NTE. This was shown by a damaged / missing socket. The source of the damage was identified as unknown third party. Engineer replaced. Engineer has not done anything with star wiring / bridge taps . No star wiring / bridge taps / VRI / power line technology issue found. Engineer has provided / replaced NTE because upgradation of NTE is required. Engineer has provided / replaced SSFP because upgradation of SSFP is required. Engineer hasn't found any issue with modem / router. Engineer hasn't found any issue with extension wiring. _x000D_23/8/2024:#Update Fault identified between internal DP and NTE. This was shown by a damaged / missing socket. The source of the damage was identified as unknown third party. Engineer replaced. Engineer has not done anything with star wiring / bridge taps . No star wiring / bridge taps / VRI / power line technology issue found. Engineer has provided / replaced NTE because upgradation of NTE is required. Engineer has provided / replaced SSFP because upgradation of SSFP is required. Engineer hasn't found any issue with modem / router. Engineer hasn't found any issue with extension wiring. _x000D_22/8/2024:#Update Fault identified between internal DP and NTE. This was shown by a damaged / missing socket. The source of the damage was identified as unknown third party. Engineer replaced. Engineer has not done anything with star wiring / bridge taps . No star wiring / bridge taps / VRI / power line technology issue found. Engineer has provided / replaced NTE because upgradation of NTE is required. Engineer has provided / replaced SSFP because upgradation of SSFP is required. Engineer hasn't found any issue with modem / router. Engineer hasn't found any issue with extension wiring. _x000D_21/8/2024:#Update Fault identified between internal DP and NTE. This was shown by a damaged / missing socket. The source of the damage was identified as unknown third party. Engineer replaced. Engineer has not done anything with star wiring / bridge taps . No star wiring / bridge taps / VRI / power line technology issue found. Engineer has provided / replaced NTE because upgradation of NTE is required. Engineer has provided / replaced SSFP because upgradation of SSFP is required. Engineer hasn't found any issue with modem / router. Engineer hasn't found any issue with extension wiring. _x000D_05/04/2024: Order completed. 19/03/24: New order added to report | 9/9/2024:#Update Fault identified between internal DP and NTE. This was shown by a damaged / missing socket. The source of the damage was identified as unknown third party. Engineer replaced. Engineer has not done anything with star wiring / bridge taps . No star wiring / bridge taps / VRI / power line technology issue found. Engineer has provided / replaced NTE because upgradation of NTE is required. Engineer has provided / replaced SSFP because upgradation of SSFP is required. Engineer hasn't found any issue with modem / router. Engineer hasn't found any issue with extension wiring. _x000D_6/9/2024:#Update Fault identified between internal DP and NTE. This was shown by a damaged / missing socket. The source of the damage was identified as unknown third party. Engineer replaced. Engineer has not done anything with star wiring / bridge taps . No star wiring / bridge taps / VRI / power line technology issue found. Engineer has provided / replaced NTE because upgradation of NTE is required. Engineer has provided / replaced SSFP because upgradation of SSFP is required. Engineer hasn't found any issue with modem / router. Engineer hasn't found any issue with extension wiring. _x000D_5/9/2024:#Update Fault identified between internal DP and NTE. This was shown by a damaged / missing socket. The source of the damage was identified as unknown third party. Engineer replaced. Engineer has not done anything with star wiring / bridge taps . No star wiring / bridge taps / VRI / power line technology issue found. Engineer has provided / replaced NTE because upgradation of NTE is required. Engineer has provided / replaced SSFP because upgradation of SSFP is required. Engineer hasn't found any issue with modem / router. Engineer hasn't found any issue with extension wiring. _x000D_4/9/2024:#Update Fault identified between internal DP and NTE. This was shown by a damaged / missing socket. The source of the damage was identified as unknown third party. Engineer replaced. Engineer has not done anything with star wiring / bridge taps . No star wiring / bridge taps / VRI / power line technology issue found. Engineer has provided / replaced NTE because upgradation of NTE is required. Engineer has provided / replaced SSFP because upgradation of SSFP is required. Engineer hasn't found any issue with modem / router. Engineer hasn't found any issue with extension wiring. _x000D_3/9/2024:#Update Fault identified between internal DP and NTE. This was shown by a damaged / missing socket. The source of the damage was identified as unknown third party. Engineer replaced. Engineer has not done anything with star wiring / bridge taps . No star wiring / bridge taps / VRI / power line technology issue found. Engineer has provided / replaced NTE because upgradation of NTE is required. Engineer has provided / replaced SSFP because upgradation of SSFP is required. Engineer hasn't found any issue with modem / router. Engineer hasn't found any issue with extension wiring. _x000D_2/9/2024:#Update Fault identified between internal DP and NTE. This was shown by a damaged / missing socket. The source of the damage was identified as unknown third party. Engineer replaced. Engineer has not done anything with star wiring / bridge taps . No star wiring / bridge taps / VRI / power line technology issue found. Engineer has provided / replaced NTE because upgradation of NTE is required. Engineer has provided / replaced SSFP because upgradation of SSFP is required. Engineer hasn't found any issue with modem / router. Engineer hasn't found any issue with extension wiring. _x000D_29/8/2024:#Update Fault identified between internal DP and NTE. This was shown by a damaged / missing socket. The source of the damage was identified as unknown third party. Engineer replaced. Engineer has not done anything with star wiring / bridge taps . No star wiring / bridge taps / VRI / power line technology issue found. Engineer has provided / replaced NTE because upgradation of NTE is required. Engineer has provided / replaced SSFP because upgradation of SSFP is required. Engineer hasn't found any issue with modem / router. Engineer hasn't found any issue with extension wiring. _x000D_28/8/2024:#Update Fault identified between internal DP and NTE. This was shown by a damaged / missing socket. The source of the damage was identified as unknown third party. Engineer replaced. Engineer has not done anything with star wiring / bridge taps . No star wiring / bridge taps / VRI / power line technology issue found. Engineer has provided / replaced NTE because upgradation of NTE is required. Engineer has provided / replaced SSFP because upgradation of SSFP is required. Engineer hasn't found any issue with modem / router. Engineer hasn't found any issue with extension wiring. _x000D_27/8/2024:#Update Fault identified between internal DP and NTE. This was shown by a damaged / missing socket. The source of the damage was identified as unknown third party. Engineer replaced. Engineer has not done anything with star wiring / bridge taps . No star wiring / bridge taps / VRI / power line technology issue found. Engineer has provided / replaced NTE because upgradation of NTE is required. Engineer has provided / replaced SSFP because upgradation of SSFP is required. Engineer hasn't found any issue with modem / router. Engineer hasn't found any issue with extension wiring. _x000D_23/8/2024:#Update Fault identified between internal DP and NTE. This was shown by a damaged / missing socket. The source of the damage was identified as unknown third party. Engineer replaced. Engineer has not done anything with star wiring / bridge taps . No star wiring / bridge taps / VRI / power line technology issue found. Engineer has provided / replaced NTE because upgradation of NTE is required. Engineer has provided / replaced SSFP because upgradation of SSFP is required. Engineer hasn't found any issue with modem / router. Engineer hasn't found any issue with extension wiring. _x000D_22/8/2024:#Update Fault identified between internal DP and NTE. This was shown by a damaged / missing socket. The source of the damage was identified as unknown third party. Engineer replaced. Engineer has not done anything with star wiring / bridge taps . No star wiring / bridge taps / VRI / power line technology issue found. Engineer has provided / replaced NTE because upgradation of NTE is required. Engineer has provided / replaced SSFP because upgradation of SSFP is required. Engineer hasn't found any issue with modem / router. Engineer hasn't found any issue with extension wiring. _x000D_21/8/2024:#Update Fault identified between internal DP and NTE. This was shown by a damaged / missing socket. The source of the damage was identified as unknown third party. Engineer replaced. Engineer has not done anything with star wiring / bridge taps . No star wiring / bridge taps / VRI / power line technology issue found. Engineer has provided / replaced NTE because upgradation of NTE is required. Engineer has provided / replaced SSFP because upgradation of SSFP is required. Engineer hasn't found any issue with modem / router. Engineer hasn't found any issue with extension wiring. _x000D_05/04/2024: Order completed. 19/03/24: New order added to report | 0 | #Update Fault identified between internal DP and NTE. This was shown by a damaged / missing socket. The source of the damage was identified as unknown third party. Engineer replaced. Engineer has not done anything with star wiring / bridge taps . No star wiring / bridge taps / VRI / power line technology issue found. Engineer has provided / replaced NTE because upgradation of NTE is required. Engineer has provided / replaced SSFP because upgradation of SSFP is required. Engineer hasn't found any issue with modem / router. Engineer hasn't found any issue with extension wiring. | 2024-04-04 | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS939400 | 30013176 | 2.Commissioning | AM |  | 2024-04-04 | 2024-04-04 | 2024-04-12 | TRUE |  | 2024-04-17 |  | 2024-07-31 |  | Barry Rajoo | 07957 175420 |  |  |  |  | 0
15 | 485858 | 101 | Batch 2 Apr24 | Type 1 | FTTP | Gifto Mini Market | Nottingham | NG5 6AS | 2024-04-05 | 05/04/2024: Order completed. 19/03/24: New order added to report | 05/04/2024: Order completed. 19/03/24: New order added to report |  |  | 2024-04-04 | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFP2300442 | 30013147 | 6.Failed router install | AM |  | 2024-04-04 | 2024-04-04 | 2024-04-12 | TRUE |  | 2024-04-19 | 2024-05-01 | 2024-05-01 |  | RED TEAM 1 | TBC | 2024-05-01 | 238004917161 |  |  | 1
16 | 478829 | 115 | Batch 2 Apr24 | Type 1 | FTTP | The Stumble Inn | Manchester | M38 9RQ | 2024-04-05 | 08/04/2024: Order completed on 05/04/2024 - . The Engineer managed to work around the scaffolding issue 03/04/2024:Openreach engineer faced obstacles: scaffolding, internal fixtures, cable entry point not found. CSL in talks with Openreach for solutions. 19/03/24: New order added to report | 08/04/2024: Order completed on 05/04/2024 - . The Engineer managed to work around the scaffolding issue 03/04/2024:Openreach engineer faced obstacles: scaffolding, internal fixtures, cable entry point not found. CSL in talks with Openreach for solutions. 19/03/24: New order added to report |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 6.No action | VFP2300388 | 30013078 | 6.Failed router install | AM |  | 2024-04-04 | 2024-04-04 | 2024-04-04 | TRUE |  | 2024-04-19 | 2024-04-29 | 2024-04-29 |  | RED TEAM 1 | tbc | 2024-04-29 | 236004882511 |  |  | 1
17 | 652197 | 38 | Batch 2 Apr24 | Type 1 | FTTP | Scott Drive Superstore | Ormskirk | L39 1PP | 2024-04-08 | 08/04/2024: Openreach have investigated and determined a multiskilled engineer is required- engineerreturned to the site on 05/04/2024 and order is now completed. 04/04/2024: engineer advised they did not have the equipment to complete to installation- CSL to provide updates. 19/03/24: New order added to report | 08/04/2024: Openreach have investigated and determined a multiskilled engineer is required- engineerreturned to the site on 05/04/2024 and order is now completed. 04/04/2024: engineer advised they did not have the equipment to complete to installation- CSL to provide updates. 19/03/24: New order added to report |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 6.No action | VFP2303073 | 30013120 | 6.Failed router install | AM |  | 2024-04-02 | 2024-04-05 | 2024-04-05 | TRUE |  | 2024-04-19 | 2024-04-25 | 2024-04-25 |  | RED TEAM 1 | TBC | 2024-04-25 | 238004917252 |  |  | 1
18 | 480371 | 116 | Batch 2 Apr24 | Type 1 | SOGEA | Premier Central Convenience Store | Sheffield | S5 0EP | 2024-04-05 | 08/04/2024: Order completed 19/03/24: New order added to report | 08/04/2024: Order completed 19/03/24: New order added to report |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 6.No action | VFS1097722 | 30013065 | 6.Failed router install | AM |  | 2024-04-05 | 2024-04-05 | 2024-04-05 | TRUE |  | 2024-04-17 | 2024-05-02 | 2024-04-22 |  | RED TEAM 1 |  | 2024-05-02 | 238004917170 |  |  | 1
19 | 480952 | 128 | Batch 2 Apr24 | Type 1 | FTTP | Super Shop | Killyleagh | BT30 9QG | 2024-04-08 | 05/04/2024: Order completed 19/03/24: New order added to report | 05/04/2024: Order completed 19/03/24: New order added to report |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFP2300376 | 30013091 | 6.Failed router install | AM |  | 2024-04-05 | 2024-04-05 | 2024-04-05 | TRUE |  | 2024-04-17 | 2024-05-01 | 2024-04-29 |  | Georgina Douglas | 7989259596 | 2024-04-30 | 236004882350 |  |  | 1
20 | 608023 | 133 | Batch 2 Apr24 | Type 1 | FTTP | Mace | Omagh | BT79 7HX | 2024-04-08 | 10/06/2024: Line fault resolved 08/04/2024: Order completed | 10/06/2024: Line fault resolved 08/04/2024: Order completed |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 6.No action | VFP2300378 | 30013063 | 6.Failed router install | AM |  | 2024-04-05 | 2024-04-05 | 2024-04-05 | TRUE |  | 2024-04-19 | 2024-04-26 | 2024-04-26 |  | Tony Foat | 7748641086 | 2024-04-29 | 236004882352 |  |  | 1
21 | 617425 | 136 | Batch 2 Apr24 | Type 1 | SOGEA | Pershore Stores | Pershore | WR10 1LN | 2024-04-08 | 08/04/2024: Order completed 19/03/24: New order added to report | 08/04/2024: Order completed 19/03/24: New order added to report |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS939377 | 30013089 | 6.Failed router install | AM |  | 2024-04-05 | 2024-04-05 | 2024-04-05 | TRUE |  | 2024-04-17 |  | 2024-05-16 |  | Adam Boyce | 7391054256 | 2024-06-24 | 238004917354 |  | 2024-07-01 | 1
22 | 629557 | 151 | Batch 2 Apr24 | Type 1 | SOGEA | All in 1 Food & Wine | Hammersmith | SW6 1NL | 2024-04-09 | 09/04/2024: order completed 19/03/24: New order added to report | 09/04/2024: order completed 19/03/24: New order added to report |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS939373 | 30013062 | 2.Commissioning | AM |  | 2024-04-08 | 2024-04-08 | 2024-04-08 | TRUE |  | 2024-04-17 |  | 2024-04-29 |  | Hassan Shariff | 7932267557 |  |  |  |  | 0
23 | 656437 | 155 | Batch 2 Apr24 | Type 1 | SOGEA | Wigan Centre News | Wigan | WN1 1QH | 2024-05-01 | 09/04/2024: order completed 19/03/24: New order added to report | 09/04/2024: order completed 19/03/24: New order added to report |  |  | 2024-04-23 | 23/04/2024: CSL to provide updates. 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS1008098 | 30013096 | 2.Commissioning | AM |  | 2024-04-08 | 2024-04-08 | 2024-02-05 | TRUE |  | 2024-04-19 |  | 2024-07-29 |  | RED TEAM 1 | TBC |  |  |  |  | 0
24 | 631092 | 161 | Batch 2 Apr24 | Type 1 | FTTP | General Store | BRISTOL | BS4 1JL | 2024-05-30 | 09/04/2024: order completed 19/03/24: New order added to report | 09/04/2024: order completed 19/03/24: New order added to report |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFP2344990 | 30013015 | 6.Failed router install | AM |  | 2024-05-17 | 2024-06-14 | 2024-06-14 | TRUE |  | 2024-04-17 |  | 2024-04-19 |  | Adam Boyce | 07391 054256 | 2024-07-25 | 239004929552 |  | 2024-07-26 | 1
25 | 619688 | 163 | Batch 2 Apr24 | Type 1 | SOGEA | Mace Clandeboye | Bangor | BT19 1AA | 2024-04-29 | 08/04/2024: Order completed | 08/04/2024: Order completed |  |  | 2024-04-29 | 29/04/2024: Allwyn to make retailer aware of visit as per the date in column T 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS939440 | 30013029 | 6.Failed router install | AM |  | 2024-04-08 | 2024-04-08 | 2024-04-08 | TRUE |  | 2024-04-17 |  | 2024-04-29 |  | Georgina Douglas | 7989259596 | 2024-06-11 | 23A004952883 |  | 2024-07-01 | 1
26 | 654642 | 164 | Batch 2 Apr24 | Type 1 | FTTP | Nearbuy | Belfast | BT17 0FA | 2024-04-09 | 02/05/2024: OR resolved the fault. 01/05/2024: OR reported a fault- waiting CSL to provide date to fix 09/04/2024: order completed 19/03/24: New order added to report | 02/05/2024: OR resolved the fault. 01/05/2024: OR reported a fault- waiting CSL to provide date to fix 09/04/2024: order completed 19/03/24: New order added to report |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFP2300453 | 30013019 | 6.Failed router install | AM |  | 2024-04-08 | 2024-04-08 | 2024-04-08 | TRUE |  | 2024-04-17 | 2024-05-14 | 2024-04-29 |  | Georgina Douglas | 7989259596 | 2024-04-26 | 236004882355 |  |  | 1
27 | 655398 | 170 | Batch 2 Apr24 | Type 1 | SOGEA | G Y News | Great Yarmouth | NR30 2BA | 2024-05-09 | 30/04/2024: OR raised an issue on this site after rtr installation- booked a visit on 02/05 to fix 09/04/2024: order completed 19/03/24: New order added to report | 30/04/2024: OR raised an issue on this site after rtr installation- booked a visit on 02/05 to fix 09/04/2024: order completed 19/03/24: New order added to report |  |  | 2024-04-09 | 09/04/2024: CSL to provide update. 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS939446 | 30013037 | 2.Commissioning | AM |  | 2024-04-08 | 2024-04-08 | 2024-04-09 | TRUE |  | 2024-04-26 |  | 2024-05-13 | [7 empty] | 0
28 | 624974 | 171 | Batch 2 Apr24 | Type 1 | SOGEA | Premier Stores | Southampton | SO16 9GA | 2024-04-30 | 09/04/2024: order completed 19/03/24: New order added to report | 09/04/2024: order completed 19/03/24: New order added to report |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS939445 | 30013025 | 2.Commissioning | AM |  | 2024-04-08 | 2024-04-08 | 2024-04-08 | TRUE |  | 2024-04-19 |  | 2024-04-30 |  | Barry Rajoo | 07957 175420 |  |  |  |  | 0
29 | 650911 | 165 | Batch 2 Apr24 | Type 1 | SOGEA | Manor Top Store Go Local Extra | Sheffield | S2 1GQ | 2024-04-10 | 03/06/24: S/N updated with the correct one, old S/N 238004917175 10/04/2024: Order completed 19/03/24: New order added to report | 03/06/24: S/N updated with the correct one, old S/N 238004917175 10/04/2024: Order completed 19/03/24: New order added to report |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFP2300458 | 30013034 | 6.Failed router install | AM |  | 2024-04-08 | 2024-04-09 | 2024-04-09 | TRUE |  | 2024-04-26 |  | 2024-05-22 |  |  |  | 2024-05-22 | 238004917181 |  |  | 1
30 | 627480 | 176 | Batch 2 Apr24 | Type 1 | SOGEA | Oldfield Local | Northolt | UB5 4RR | 2024-04-25 | 03/06/24: S/N updated with the correct one, old S/N 238004917312 25/04/2024: Order completed 10/04/2024: Your order has been delayed by our Suppliers due to Multiskilled Engineer required to complete the installation. Please check with end user and re-appoint order for earliest date. 19/03/24: New order added to report | 03/06/24: S/N updated with the correct one, old S/N 238004917312 25/04/2024: Order completed 10/04/2024: Your order has been delayed by our Suppliers due to Multiskilled Engineer required to complete the installation. Please check with end user and re-appoint order for earliest date. 19/03/24: New order added to report |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS939453 | 30013054 | 2.Commissioning | AM |  | 2024-04-09 | 2024-04-09 | 2024-04-09 | TRUE |  | 2024-04-26 |  | 2024-05-20 | [7 empty] | 0
31 | 645274 | 180 | Batch 2 Apr24 | Type 1 | SOGEA | Deansbrook Supermarket | Edgware | HA8 9BU | 2024-04-10 | 10/04/2024: Order completed 19/03/24: New order added to report | 10/04/2024: Order completed 19/03/24: New order added to report |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS939458 | 30013043 | 6.Failed router install | AM |  | 2024-04-09 | 2024-04-09 | 2024-04-09 | TRUE |  | 2024-04-26 |  | 2024-08-07 |  |  |  | 2024-08-21 | 242005010985 | 242005010985 | 2024-08-22 | 1
32 | 636516 | 189 | Batch 2 Apr24 | Type 1 | FTTP | Tooting Mini Market | LONDON | SW17 0RG | 2024-04-10 | 10/04/2024: Order completed 19/03/24: New order added to report | 10/04/2024: Order completed 19/03/24: New order added to report |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 6.No action | VFP2300463 | 30013047 | 6.Failed router install | AM |  | 2024-04-09 | 2024-04-09 | 2024-04-09 | TRUE |  | 2024-04-26 |  | 2024-05-20 |  |  |  | 2024-05-21 | 237004906994 |  |  | 1
33 | 632971 | 195 | Batch 2 Apr24 | Type 1 | FTTP | Mace | Dungannon | BT71 4LG | 2024-05-01 | 10/04/2024: Order completed 19/03/24: New order added to report | 10/04/2024: Order completed 19/03/24: New order added to report |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFP2300465 | 30013048 | 2.Commissioning | AM |  | 2024-04-09 | 2024-04-09 | 2024-04-09 | TRUE |  | 2024-04-26 |  | 2024-04-29 | [7 empty] | 0
34 | 632844 | 197 | Batch 2 Apr24 | Type 1 | SOGEA | Sugar & Spice Mini Market | Edgware | HA8 5NP | 2024-04-10 | 10/04/2024: Order completed 19/03/24: New order added to report | 10/04/2024: Order completed 19/03/24: New order added to report |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 5.CSL | VFS939465 | 30013028 | 6.Failed router install | AM |  | 2024-04-09 | 2024-04-09 | 2024-04-09 | TRUE |  | 2024-04-26 |  | 2024-05-21 |  |  |  | 2024-07-17 | 242005008606 |  | 2024-07-19 | 1
35 | 632882 | 201 | Batch 2 Apr24 | Type 1 | SOGEA | Premier Church Warsop Convenience S | MANSFIELD | NG20 0TG | 2024-04-10 | 10/04/2024: Order completed 19/03/24: New order added to report | 10/04/2024: Order completed 19/03/24: New order added to report |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS939566 | 30013486 | 2.Commissioning | AM |  | 2024-04-09 | 2024-04-09 | 2024-04-09 | TRUE |  | 2024-04-26 |  | 2024-07-31 | [7 empty] | 0
36 | 481222 | 124 | Batch 2 Apr24 | Type 1 | FTTP | Ahmad Bros | Leven | KY8 1BZ | 2024-04-11 | 11/04/2024: Order completed. 19/03/24: New order added to report | 11/04/2024: Order completed. 19/03/24: New order added to report |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFP2300382 | 30013085 | 6.Failed router install | AM |  | 2024-04-05 | 2024-04-10 | 2024-04-10 | TRUE |  | 2024-04-26 |  | 2024-05-24 |  |  |  | 2024-05-24 | 237004907121 |  |  | 1
37 | 648612 | 206 | Batch 2 Apr24 | Type 1 | SOGEA | Smart Food & Wine | Aldershot | GU11 1JE | 2024-04-11 | 11/04/2024: Order completed. 19/03/24: New order added to report | 11/04/2024: Order completed. 19/03/24: New order added to report |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS939569 | 30013488 | 2.Commissioning | AM |  | 2024-04-10 | 2024-04-10 | 2024-04-10 | TRUE |  | 2024-04-26 |  | 2024-05-23 | [7 empty] | 0
38 | 632554 | 210 | Batch 2 Apr24 | Type 1 | FTTP | Hazels Newsagents | Carrickfergus | BT38 7DP | 2024-04-11 | 11/04/2024: Order completed. 19/03/24: New order added to report | 11/04/2024: Order completed. 19/03/24: New order added to report |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 6.No action | VFP2300553 | 30013512 | 6.Failed router install | AM |  | 2024-04-10 | 2024-04-10 | 2024-04-10 | TRUE |  | 2024-04-26 | 2024-04-29 | 2024-04-26 |  |  |  | 2024-04-29 | 236004882534 |  |  | 1
39 | 633526 | 214 | Batch 2 Apr24 | Type 1 | SOGEA | Lifestyle Express | London | N11 2JA | 2024-04-16 | 01/05/2024: OR reported a fault- waiting CSL to provide date to fix 11/04/2024: Order completed. 19/03/24: New order added to report | 01/05/2024: OR reported a fault- waiting CSL to provide date to fix 11/04/2024: Order completed. 19/03/24: New order added to report |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS939573 | 30013509 | 2.Commissioning | AM |  | 2024-04-10 | 2024-04-10 | 2024-04-11 | TRUE |  |  |  | 2024-06-11 | [7 empty] | 0
40 | 634487 | 224 | Batch 2 Apr24 | Type 1 | SOGEA | Londis | EPSOM | KT19 9HG | 2024-04-11 | 19/7/2024:#Update - Action for Allwyn - Installation has now been amended to 19/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 19/07 is a suitable date. _x000D_18/7/2024:#Update - Action for Allwyn - Installation has now been amended to 19/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 19/07 is a suitable date. _x000D_17/7/2024:#Update - Action for Allwyn - Installation has now been amended to 19/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 19/07 is a suitable date. _x000D_16/7/2024:#Update - Action for Allwyn - Installation has now been amended to 19/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 19/07 is a suitable date. _x000D_15/7/2024:#Update - Action for Allwyn - Installation has now been amended to 19/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 19/07 is a suitable date. _x000D_12/7/2024:#Update - Action for Allwyn - Installation has now been amended to 19/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 19/07 is a suitable date. _x000D_11/7/2024:#Update - Action for Allwyn - Installation has now been amended to 19/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 19/07 is a suitable date. _x000D_10/7/2024:#Update - Action for Allwyn - Installation has now been amended to 19/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 19/07 is a suitable date. _x000D_9/7/2024:#Update - Action for Allwyn - Installation has now been amended to 19/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 19/07 is a suitable date. _x000D_4/7/2024:#Update - Action for Allwyn - Installation has now been amended to 19/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 19/07 is a suitable date. _x000D_3/7/2024:#Update - Action for Allwyn - Installation has now been amended to 19/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 19/07 is a suitable date. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Action for Allwyn - Installation has now been amended to 19/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 19/07 is a suitable date. _x000D_27/6/2024:#Update - Missed Appointment - The retailer refused to allow engineer to complete job. CSL to reappoint the installation and update with a committed date. _x000D_11/04/2024: Order completed. 19/03/24: New order added to report | 19/7/2024:#Update - Action for Allwyn - Installation has now been amended to 19/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 19/07 is a suitable date. _x000D_18/7/2024:#Update - Action for Allwyn - Installation has now been amended to 19/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 19/07 is a suitable date. _x000D_17/7/2024:#Update - Action for Allwyn - Installation has now been amended to 19/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 19/07 is a suitable date. _x000D_16/7/2024:#Update - Action for Allwyn - Installation has now been amended to 19/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 19/07 is a suitable date. _x000D_15/7/2024:#Update - Action for Allwyn - Installation has now been amended to 19/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 19/07 is a suitable date. _x000D_12/7/2024:#Update - Action for Allwyn - Installation has now been amended to 19/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 19/07 is a suitable date. _x000D_11/7/2024:#Update - Action for Allwyn - Installation has now been amended to 19/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 19/07 is a suitable date. _x000D_10/7/2024:#Update - Action for Allwyn - Installation has now been amended to 19/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 19/07 is a suitable date. _x000D_9/7/2024:#Update - Action for Allwyn - Installation has now been amended to 19/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 19/07 is a suitable date. _x000D_4/7/2024:#Update - Action for Allwyn - Installation has now been amended to 19/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 19/07 is a suitable date. _x000D_3/7/2024:#Update - Action for Allwyn - Installation has now been amended to 19/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 19/07 is a suitable date. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Action for Allwyn - Installation has now been amended to 19/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 19/07 is a suitable date. _x000D_27/6/2024:#Update - Missed Appointment - The retailer refused to allow engineer to complete job. CSL to reappoint the installation and update with a committed date. _x000D_11/04/2024: Order completed. 19/03/24: New order added to report |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS939578 | 30013492 | 6.Failed router install | AM |  | 2024-04-10 | 2024-04-10 | 2024-04-10 | TRUE |  | 2024-04-26 |  | 2024-05-17 |  |  |  | 2024-06-06 | 23A004949235 |  | 2024-07-01 | 1
41 | 634587 | 226 | Batch 2 Apr24 | Type 1 | SoGEA/Mobile | Fair Price | MANSFIELD | NG20 0AB | 2024-04-11 | 6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 16/09 PM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 16/09 PM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 16/09 PM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 16/09 PM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 16/09 PM _x000D_29/8/2024:#Update - Missed Appointment - The retailer stated that an engineer has retuned three times and they don't want a new line and to not send an engineer out again. _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_23/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_19/8/2024:01454937 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_13/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_12/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_9/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_8/8/2024:06/08/2024 _x000D_6/8/2024:31/07/2024 _x000D_5/8/2024:31/07/2024 _x000D_2/8/2024:31/07/2024 _x000D_1/8/2024:31/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_30/7/2024:#Update - Retailer unaware of appointment. Reappointed for 23/08 - Action for allwyn: Please confirm appointment date. _x000D_29/7/2024:#Update - Retailer unaware of appointment. Reappointed for 23/08 - Action for allwyn: Please confirm appointment date. _x000D_29/7/2024:01434723 _x000D_26/7/2024:01434723 _x000D_24/7/2024:#Update - Retailer unaware of appointment. Reappointed for 23/08 - Action for allwyn: Please confirm appointment date. _x000D_23/7/2024:#Update - Retailer unaware of appointment. Reappointed for 23/08 - Action for allwyn: Please confirm appointment date. _x000D_22/7/2024:#Update - Action for Allwyn - Installation has now been amended to 19/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 19/07 is a suitable date. _x000D_22/7/2024:#Update - Action for Allwyn - Installation has now been amended to 19/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 19/07 is a suitable date. _x000D_11/04/2024: Order completed. 19/03/24: New order added to report | 9/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 16/09 PM _x000D_6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 16/09 PM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 16/09 PM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 16/09 PM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 16/09 PM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 16/09 PM _x000D_29/8/2024:#Update - Missed Appointment - The retailer stated that an engineer has retuned three times and they don't want a new line and to not send an engineer out again. _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_23/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_19/8/2024:01454937 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_13/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_12/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_9/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_8/8/2024:06/08/2024 _x000D_6/8/2024:31/07/2024 _x000D_5/8/2024:31/07/2024 _x000D_2/8/2024:31/07/2024 _x000D_1/8/2024:31/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_30/7/2024:#Update - Retailer unaware of appointment. Reappointed for 23/08 - Action for allwyn: Please confirm appointment date. _x000D_29/7/2024:#Update - Retailer unaware of appointment. Reappointed for 23/08 - Action for allwyn: Please confirm appointment date. _x000D_29/7/2024:01434723 _x000D_26/7/2024:01434723 _x000D_24/7/2024:#Update - Retailer unaware of appointment. Reappointed for 23/08 - Action for allwyn: Please confirm appointment date. _x000D_23/7/2024:#Update - Retailer unaware of appointment. Reappointed for 23/08 - Action for allwyn: Please confirm appointment date. _x000D_22/7/2024:#Update - Action for Allwyn - Installation has now been amended to 19/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 19/07 is a suitable date. _x000D_22/7/2024:#Update - Action for Allwyn - Installation has now been amended to 19/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 19/07 is a suitable date. _x000D_11/04/2024: Order completed. 19/03/24: New order added to report | 0 | #Update - Allwyn confirmed Retailer has agreed to installation on 16/09 PM |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS1027078 | 30013502 | 2.Commissioning | AM |  | 2024-06-26 | 2024-08-23 |  | 0 |  | 2024-04-26 |  | 2024-05-23 | [7 empty] | 0
42 | 641285 | 229 | Batch 2 Apr24 | Type 1 | SOGEA | Norris News & Off Licence | PIMLICO | SW1V 3EN | 2024-04-11 | 11/04/2024: Order completed. 19/03/24: New order added to report | 11/04/2024: Order completed. 19/03/24: New order added to report |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS939584 | 30013480 | 6.Failed router install | AM |  | 2024-04-10 | 2024-04-10 | 2024-04-10 | TRUE |  | 2024-04-26 |  | 2024-05-20 |  |  |  | 2024-05-21 | 237004906949 |  |  | 1
43 | 635589 | 243 | Batch 2 Apr24 | Type 1 | SOGEA | McAloanans Service Station | Ballycastle | BT54 6DX | 2024-04-12 | 12/04/2024: Order completed 19/03/24: New order added to report | 12/04/2024: Order completed 19/03/24: New order added to report |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS943323 | 30013305 | 2.Commissioning | AM |  | 2024-04-11 | 2024-04-11 | 2024-04-11 | TRUE |  | 2024-04-26 |  | 2024-08-13 | [7 empty] | 0
44 | 635790 | 251 | Batch 2 Apr24 | Type 1 | FTTP | Dorans | Londonderry | BT47 2DL | 2024-04-12 | 15/2024: Order completed 12/04/2024: Abortive visit- Retailer manager was not available so did not allow engineer access. Reappointing new install date 19/03/24: New order added to report | 15/2024: Order completed 12/04/2024: Abortive visit- Retailer manager was not available so did not allow engineer access. Reappointing new install date 19/03/24: New order added to report |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFP2300527 | 30013272 | 6.Failed router install | AM |  | 2024-04-11 | 2024-04-11 | 2024-04-11 | TRUE |  | 2024-04-26 |  | 2024-05-21 |  |  |  | 2024-05-23 | 236004882537 |  |  | 1
45 | 638159 | 259 | Batch 2 Apr24 | Type 1 | FTTP | The Boulevard | Belfast | BT4 2EX | 2024-05-01 | 12/04/2024: Order completed 19/03/24: New order added to report | 12/04/2024: Order completed 19/03/24: New order added to report |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFP2300532 | 30013292 | 6.Failed router install | AM |  | 2024-04-11 | 2024-04-11 | 2024-04-11 | TRUE |  | 2024-04-26 |  | 2024-05-21 |  |  |  | 2024-05-24 | 236004882497 |  |  | 1
46 | 651310 | 262 | Batch 2 Apr24 | Type 1 | SOGEA | Best Supermarket | Maidstone | ME15 7AU | 2024-04-12 | 12/04/2024: Order completed 19/03/24: New order added to report | 12/04/2024: Order completed 19/03/24: New order added to report |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS939550 | 30013278 | 2.Commissioning | AM |  | 2024-04-11 | 2024-04-11 | 2024-04-11 | TRUE |  | 2024-04-26 |  | 2024-05-24 | [7 empty] | 0
47 | 646447 | 273 | Batch 2 Apr24 | Type 1 | SOGEA | Western Road Store | Bexhill | TN40 1DU | 2024-04-15 | 01/05/2024: OR reported a fault- waiting CSL to provide date to fix 15/04/2024: Order completed 19/03/24: New order added to report | 01/05/2024: OR reported a fault- waiting CSL to provide date to fix 15/04/2024: Order completed 19/03/24: New order added to report |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS939556 | 30013282 | 6.Failed router install | AM |  | 2024-04-12 | 2024-04-12 | 2024-05-13 | TRUE |  | 2024-04-26 |  | 2024-05-20 |  |  |  | 2024-06-05 | 23A004948810 |  |  | 1
48 | 647488 | 275 | Batch 2 Apr24 | Type 1 | FTTP | Nisa Local | South Oxhey | WD19 7EU | 2024-04-15 | 03/06/24: Reason for fail: Device only up on LTE, no data being transmitted on FTTP. Line test came back with following results. "Service is working - problem with ONT connection to the router. Please ensure the connecting cable is using the WAN port on the router". 15/04/2024: Order completed 19/03/24: New order added to report | 03/06/24: Reason for fail: Device only up on LTE, no data being transmitted on FTTP. Line test came back with following results. "Service is working - problem with ONT connection to the router. Please ensure the connecting cable is using the WAN port on the router". 15/04/2024: Order completed 19/03/24: New order added to report |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFP2300540 | 30013287 | 2.Commissioning | AM |  | 2024-04-12 | 2024-04-12 | 2024-04-12 | TRUE |  | 2024-04-26 |  | 2024-05-20 | [7 empty] | 0
49 | 651892 | 279 | Batch 2 Apr24 | Type 1 | SOGEA | Price Chopper Supermarket | London | NW11 8DY | 2024-05-01 | 15/04/2024: Order completed 19/03/24: New order added to report | 15/04/2024: Order completed 19/03/24: New order added to report |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS939559 | 30013279 | 2.Commissioning | AM |  | 2024-04-12 | 2024-04-12 | 2024-04-12 | TRUE |  | 2024-04-26 |  | 2024-05-17 | [7 empty] | 0
50 | 656045 | 284 | Batch 2 Apr24 | Type 1 | SOGEA | Premier Cherry Lane Convenience | Liverpool | L4 8SG | 2024-04-15 | 15/04/2024: Order completed 19/03/24: New order added to report | 15/04/2024: Order completed 19/03/24: New order added to report |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS939497 | 30013193 | 2.Commissioning | AM |  | 2024-04-12 | 2024-04-12 | 2024-04-12 | TRUE |  | 2024-04-26 |  | 2024-07-25 | [7 empty] | 0
51 | 645482 | 291 | Batch 2 Apr24 | Type 1 | SOGEA | Rains Newsagents | London | NW10 8NU | 2024-04-15 | 15/04/2024: Order completed 19/03/24: New order added to report | 15/04/2024: Order completed 19/03/24: New order added to report |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS939505 | 30013196 | 6.Failed router install | AM |  | 2024-04-12 | 2024-04-12 | 2024-04-12 | TRUE |  |  |  | 2024-05-17 |  |  |  | 2024-05-17 | 237004906956 |  |  | 1
52 | 657126 | 293 | Batch 2 Apr24 | Type 1 | FTTP | Costcutter Supermarket | Heywood | OL10 4RF | 2024-05-01 | 01/05/2024: OR reported a fault- waiting CSL to provide date to fix 15/04/2024: Order completed 19/03/24: New order added to report | 01/05/2024: OR reported a fault- waiting CSL to provide date to fix 15/04/2024: Order completed 19/03/24: New order added to report |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS939506 | 30013220 | 6.Failed router install | AM |  | 2024-04-12 | 2024-04-12 | 2024-04-12 | TRUE |  | 2024-04-26 |  | 2024-05-14 |  |  |  | 2024-05-14 | 238004917175 |  |  | 1
53 | 647010 | 298 | Batch 2 Apr24 | Type 1 | SOGEA | Jays Convenience Express | Leicester | LE3 6LW | 2024-04-16 | 16/04/2024: Order completed 19/03/24: New order added to report | 16/04/2024: Order completed 19/03/24: New order added to report |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS939510 | 30013199 | 6.Failed router install | AM |  | 2024-04-15 | 2024-04-15 | 2024-04-15 | TRUE |  | 2024-04-30 | 2024-05-14 | 2024-05-07 |  |  |  | 2024-05-07 | 238004917389 |  |  | 1
54 | 484352 | 303 | Batch 2 Apr24 | Type 1 | FTTP | Bywaters News Ltd | Dudley | DY3 2DA | 2024-04-16 | 16/04/2024: Order completed 19/03/24: New order added to report | 16/04/2024: Order completed 19/03/24: New order added to report |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFP2303017 | 30013522 | 6.Failed router install | AM |  | 2024-04-15 | 2024-04-15 | 2024-04-15 | TRUE |  | 2024-04-26 |  | 2024-05-16 |  |  |  | 2024-05-13 | 238004917316 |  |  | 1
55 | 671760 | 306 | Batch 2 Apr24 | Type 1 | SOGEA | Quinton Supermarket | Quinton | B32 1SL | 2024-04-16 | 16/04/2024: Order completed 19/03/24: New order added to report | 16/04/2024: Order completed 19/03/24: New order added to report |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFP2300515 | 30013211 | 2.Commissioning | AM |  | 2024-04-15 | 2024-04-15 | 2024-04-15 | TRUE |  | 2024-04-30 |  | 2024-08-09 | [7 empty] | 0 | 671760
56 | 446726 | 308 | Batch 2 Apr24 | Type 1 | SOGEA | THE PAPER PLACE | BIRMINGHAM | B24 0NU | 2024-05-15 | 16/04/2024: Order completed 19/03/24: New order added to report | 16/04/2024: Order completed 19/03/24: New order added to report |  |  | 2024-05-15 | 15/05/2024: Allwyn to check the rtr power with the retailer 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS939513 | 30013198 | 6.Failed router install | AM |  | 2024-04-15 | 2024-04-15 | 2024-04-15 | TRUE |  | 2024-04-30 | 2024-05-14 | 2024-05-02 |  |  |  | 2024-05-02 | 238004917315 |  |  | 1
57 | 642195 | 311 | Batch 2 Apr24 | Type 1 | SOGEA | News Rack | NEWCASTLE | ST5 8HX | 2024-04-23 | 16/04/2024: Order completed 19/03/24: New order added to report | 16/04/2024: Order completed 19/03/24: New order added to report |  |  | 2024-04-16 | 16/04/2024: CSL to provide updates. 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS939516 | 30013184 | 6.Failed router install | AM |  | 2024-04-15 | 2024-04-15 | 2024-04-19 | TRUE |  | 2024-05-09 |  | 2024-05-13 |  |  |  | 2024-06-13 | 23A004948584 |  | 2024-07-01 | 1
58 | 647725 | 313 | Batch 2 Apr24 | Type 1 | SOGEA | Premier Convenience Store | Coventry | CV6 7AZ | 2024-04-23 | 16/04/2024: Order completed 19/03/24: New order added to report | 16/04/2024: Order completed 19/03/24: New order added to report |  |  | 2024-04-16 | 16/04/2024: CSL to provide updates. 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS939517 | 30013195 | 2.Commissioning | AM |  | 2024-04-15 | 2024-04-15 | 2024-04-17 | TRUE |  | 2024-05-09 |  | 2024-05-15 | [7 empty] | 0
59 | 614969 | 317 | Batch 2 Apr24 | Type 1 | SOGEA | R & D Stores | Harrow | HA3 9HU | 2024-04-16 | 16/04/2024: Order completed 19/03/24: New order added to report | 16/04/2024: Order completed 19/03/24: New order added to report |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS939522 | 30013203 | 6.Failed router install | AM |  | 2024-04-15 | 2024-04-15 | 2024-04-15 | TRUE |  | 2024-04-26 |  | 2024-08-07 |  |  |  | 2024-08-07 | 242005011159 |  | 2024-08-08 | 1
60 | 411402 | 318 | Batch 2 Apr24 | Type 1 | FTTP | D M C Newsplus Ltd | HOUGHTON LE SPRING | DH4 5DR | 2024-04-16 | 10/06/2024: Line fault resolved 08/05/2024: Fault visit on 10/05 01/05/2024: OR reported a fault- waiting CSL to provide date to fix 16/04/2024: Order completed 19/03/24: New order added to report | 10/06/2024: Line fault resolved 08/05/2024: Fault visit on 10/05 01/05/2024: OR reported a fault- waiting CSL to provide date to fix 16/04/2024: Order completed 19/03/24: New order added to report |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFP2300520 | 30013204 | 6.Failed router install | AM |  | 2024-04-15 | 2024-04-15 | 2024-04-15 | TRUE |  | 2024-04-26 |  | 2024-05-15 |  |  |  | 2024-05-15 | 238004917178 |  |  | 1
61 | 661508 | 319 | Batch 2 Apr24 | Type 1 | SOGEA | JJ Convenience Store | Ashington | NE63 8RN | 2024-05-08 | 16/04/2024: Order completed 19/03/24: New order added to report | 16/04/2024: Order completed 19/03/24: New order added to report |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS939523 | 30013224 | 2.Commissioning | AM |  | 2024-04-15 | 2024-04-15 | 2024-04-15 | TRUE |  | 2024-04-26 |  | 2024-08-23 | [7 empty] | 0
62 | 467692 | 320 | Batch 2 Apr24 | Type 1 | SOGEA | RNP Convenience Store | HATFIELD | AL9 7DY | 2024-04-16 | 16/04/2024: Order completed 19/03/24: New order added to report | 16/04/2024: Order completed 19/03/24: New order added to report |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS939524 | 30013190 | 6.Failed router install | AM |  | 2024-04-15 | 2024-04-15 | 2024-04-15 | TRUE |  | 2024-04-26 |  | 2024-05-10 |  |  |  | 2024-05-10 | 237004907102 |  |  | 1
63 | 612573 | 48 | Batch 2 Apr24 | Type 1 | FTTP | Thurnby Express | Leicester | LE5 2EH | 2024-04-19 | 19/04/2024: Order completed 05/04/2024: rescheduled on 18th-April- This site requires an upgrade - Cbt is located on wall of flat near front door cable would have to run across mutiple properties to get into customers shop 04/04/2024: incomplete work- survey will be required. CSL to provide updates. 19/03/24: New order added to report | 19/04/2024: Order completed 05/04/2024: rescheduled on 18th-April- This site requires an upgrade - Cbt is located on wall of flat near front door cable would have to run across mutiple properties to get into customers shop 04/04/2024: incomplete work- survey will be required. CSL to provide updates. 19/03/24: New order added to report |  |  | 2024-04-08 | 08/04/2024: Alwwyn to make the retaile awar of the rebooked visit on 18th-April 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 6.No action | VFP2303086 | 30013117 | 6.Failed router install | AM |  | 2024-04-03 | 2024-04-18 | 2024-04-18 | TRUE |  | 2024-04-25 | 2024-04-26 | 2024-04-26 |  |  |  | 2024-04-26 | 238004917387 |  |  | 1
64 | 632906 | 203 | Batch 2 Apr24 | Type 1 | SOGEA | Kingsbury Newsbox | London | NW9 8JU | 2024-04-23 | 19/04/2024: Rebooked on 24/04 12/04/2024: Expected date for completion of external work is 22/04. Further updates to follow 05/04/2024: Dig work required. Our Suppliers have given us a review date of 15/04/2024. 19/03/24: New order added to report | 19/04/2024: Rebooked on 24/04 12/04/2024: Expected date for completion of external work is 22/04. Further updates to follow 05/04/2024: Dig work required. Our Suppliers have given us a review date of 15/04/2024. 19/03/24: New order added to report |  |  | 2024-04-11 | 09/04/2024: Allwyn to make the retailer awar of the new date 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS939567 | 30013499 | 6.Failed router install | AM |  | 2024-04-09 | 2024-04-22 | 2024-04-22 | TRUE |  | 2024-05-09 |  | 2024-05-17 |  |  |  | 2024-05-17 | 237004906957 |  |  | 1
65 | 632977 | 196 | Batch 2 Apr24 | Type 1 | FTTP | Woods Newsagents | Deal | CT14 7AA | 2024-04-05 | 26/7/2024:23/07/2024 10:36 _x000D_24/7/2024:Order Completed _x000D_23/7/2024:Order Completed _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_25/04/2024: Order completed 24/04/2024: Abortive visit- Customer requested to reschedule appt as was unaware of this installation.- installation incomplete; on 23/04 remaining work is required, will return to the site 24/04 with additional engineer support. 11/04/2024: Abortive visit- retailer unaware of the visit and requested to rebook the visit- rebooked on 23/04/2024 19/03/24: New order added to report | 26/7/2024:23/07/2024 10:36 _x000D_24/7/2024:Order Completed _x000D_23/7/2024:Order Completed _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_25/04/2024: Order completed 24/04/2024: Abortive visit- Customer requested to reschedule appt as was unaware of this installation.- installation incomplete; on 23/04 remaining work is required, will return to the site 24/04 with additional engineer support. 11/04/2024: Abortive visit- retailer unaware of the visit and requested to rebook the visit- rebooked on 23/04/2024 19/03/24: New order added to report |  |  | 2024-04-05 | 05/04/2024: CSL to Reschedule the visit Closed 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFP2300467 | 30013053 | 2.Commissioning | AM |  | 2024-04-09 | 2024-04-23 | 2024-05-13 | TRUE |  |  |  | 2024-06-03 | [7 empty] | 0
66 | 635341 | 235 | Batch 2 Apr24 | Type 1 | SOGEA | Holme Stores | Bradford | BD4 0AH | 2024-04-26 | 29/04/2024: Order completed. 12/04/2024: Abortive visit- Rebooked 26/04/2024- Retailer was not aware of the visit. 19/03/24: New order added to report | 29/04/2024: Order completed. 12/04/2024: Abortive visit- Rebooked 26/04/2024- Retailer was not aware of the visit. 19/03/24: New order added to report |  |  | 2024-04-11 | 11/04/2024: Allwyn to let the retailer aware of new visit. 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS939587 | 30013496 | 6.Failed router install | AM |  | 2024-04-10 | 2024-04-26 | 2024-04-26 | TRUE |  |  |  | 2024-05-28 |  |  |  | 2024-05-28 | 238004917249 |  |  | 1
67 | 461372 | 68 | Batch 2 Apr24 | Type 1 | FTTP | Dunnes Stores | Belfast | BT7 3AE | 2024-04-30 | 30/04/2024: Order completed 16/04/2024: Order forcasted date on 29/04/2024 ( confirmed ) 05/04/2024: Pair divert required, to be completed by the 08/04. Awaiting committed date 27/03/2024: Order delay, next updated will be provided on 2nd April 25/03/2024 Order is experiencing contractor delay- next review date on 26/03/2024 19/03/24: New order added to report | 30/04/2024: Order completed 16/04/2024: Order forcasted date on 29/04/2024 ( confirmed ) 05/04/2024: Pair divert required, to be completed by the 08/04. Awaiting committed date 27/03/2024: Order delay, next updated will be provided on 2nd April 25/03/2024 Order is experiencing contractor delay- next review date on 26/03/2024 19/03/24: New order added to report |  |  | 2024-04-26 | 26/04/2024: Allwyn to make the retaer awar. 23/04/2024: Allwyn to make the retailer aware of the new visit 04/04/2024: Allwyn to approve upgrade Approved 9/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFP2300498 | 30013099 | 6.Failed router install | AM |  | 2024-04-03 | 2024-04-28 | 2024-04-28 | TRUE |  |  |  | 2024-05-22 |  |  |  | 2024-05-24 | 236004882498 |  |  | 1
68 | 659579 | 282 | Batch 2 Apr24 | Type 1 | SOGEA | Premier Stores | Alloa | FK10 1JX | 2024-04-30 | 30/04/2024: Order completed 15/04/2024: Abortive visit - Spoke to the store manager and she knows nothing about it- Order moved on 29/04 19/03/24: New order added to report | 30/04/2024: Order completed 15/04/2024: Abortive visit - Spoke to the store manager and she knows nothing about it- Order moved on 29/04 19/03/24: New order added to report |  |  |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS939498 | 30013221 | 2.Commissioning | AM |  | 2024-04-12 | 2024-04-29 | 2024-04-29 | TRUE |  |  |  | 2024-06-03 | [7 empty] | 0
69 | 461933 | 39 | Batch 2 Apr24 | Type 1 | SOGEA | Rujal News | CLACTON-ON-SEA | CO15 1TB | 2024-05-02 | 02/05/2024: Order completed 18/04/2024: forecated date on 01/05 16/04/2024: there are currently no further updates regarding the completion of the outstanding external work. We will continue to monitor the order every 2-3 working days and update you accordingly. 08/04/2024: Supplier Delay: Delay due to Frames Complications, further updates to follow 19/03/24: New order added to report | 02/05/2024: Order completed 18/04/2024: forecated date on 01/05 16/04/2024: there are currently no further updates regarding the completion of the outstanding external work. We will continue to monitor the order every 2-3 working days and update you accordingly. 08/04/2024: Supplier Delay: Delay due to Frames Complications, further updates to follow 19/03/24: New order added to report |  |  | 2024-04-18 | 18/04/2024: Allwyn to rebook RTR install date as the scheduled visit based on the error completion date 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS964421 | 30013122 | 2.Commissioning | AM |  | 2024-04-02 | 2024-05-01 | 2024-05-01 | TRUE |  | 2024-04-17 |  | 2024-08-02 |  | Geoff Brosse | 7727673515 |  |  |  |  | 0
70 | 112331 | 329 | Batch 3 May24 | Type 1 | SOGEA | Milco Supersaver Off Licence | DEWSBURY | WF13 3HL | 2024-05-02 | 02/05/2024: Order completed 08/04/2024: New order added to report | 02/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300526 | 30013219 | 2.Commissioning |  |  | 2024-05-01 | 2024-05-01 | 2024-05-01 | TRUE |  |  |  | 2024-05-28 | [7 empty] | 0
71 | 651406 | 333 | Batch 3 May24 | Type 1 | SOGEA | Briardale Road G & S Ltd | Blyth | NE24 5LB | 2024-05-02 | 01/05/2024: Order completed 08/04/2024: New order added to report | 01/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300530 | 30013223 | 6.Failed router install |  |  | 2024-05-01 | 2024-05-01 | 2024-05-01 | TRUE |  |  |  | 2024-06-05 |  |  |  | 2024-06-05 | 238004917207 |  |  | 1
72 | 447883 | 341 | Batch 3 May24 | Type 1 | SOGEA | Davids Newsagents | LONDON | NW4 2DY | 2024-05-02 | 02/05/2024: Order completed 08/04/2024: New order added to report | 02/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300538 | 30013231 | 2.Commissioning |  |  | 2024-05-01 | 2024-05-01 | 2024-05-01 | TRUE |  |  |  | 2024-05-30 | [7 empty] | 0
73 | 654225 | 342 | Batch 3 May24 | Type 1 | SOGEA | The Chocolate Box | Whitstable | CT5 1RB | 2024-05-02 | 02/05/2024: Order completed 08/04/2024: New order added to report | 02/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300539 | 30013232 | 2.Commissioning |  |  | 2024-05-01 | 2024-05-01 | 2024-05-01 | TRUE |  |  |  | 2024-05-23 | [7 empty] | 0
74 | 668638 | 343 | Batch 3 May24 | Type 1 | FTTP | Jos Newsagent and Off Licence | TONBRIDGE | TN9 2HR | 2024-05-02 | 02/05/2024: Order completed 08/04/2024: New order added to report | 02/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300540 | 30013233 | 6.Failed router install |  |  | 2024-05-01 | 2024-05-01 | 2024-05-01 | TRUE |  |  |  | 2024-05-24 |  |  |  | 2024-05-24 | 237004906967 |  |  | 1 | 668638
75 | 105158 | 347 | Batch 3 May24 | Type 1 | SOGEA | R & R Retail | CWMBRAN | NP44 8HS | 2024-05-02 | 02/05/2024: Order completed 08/04/2024: New order added to report | 02/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 6.No action | VFP2300544 | 30013237 | 6.Failed router install |  |  | 2024-05-01 | 2024-05-01 | 2024-05-01 | TRUE |  |  |  | 2024-05-24 |  |  |  | 2024-05-24 | 237004907224 |  |  | 1
76 | 417602 | 351 | Batch 3 May24 | Type 1 | SOGEA | Pick N Mix Sweet Shop The Newsagent | LONDON | E15 3ET | 2024-05-02 | 02/05/2024: Order completed 08/04/2024: New order added to report | 02/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300548 | 30013241 | 6.Failed router install |  |  | 2024-05-01 | 2024-05-01 | 2024-05-01 | TRUE |  |  |  | 2024-05-29 |  |  |  | 2024-05-29 | 237004907082 |  |  | 1
77 | 409677 | 352 | Batch 3 May24 | Type 1 | SOGEA | BUTLERS | LONDON | N19 5QU | 2024-05-02 | 02/05/2024: Order completed 08/04/2024: New order added to report | 02/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300549 | 30013242 | 2.Commissioning |  |  | 2024-05-01 | 2024-05-01 | 2024-05-02 | TRUE |  |  |  | 2024-05-30 | [7 empty] | 0
78 | 657006 | 357 | Batch 3 May24 | Type 1 | SOGEA | Arkay's Ltd | Thornton Heath | CR7 7ND | 2024-05-02 | 23/8/2024:#Update End customer advised engineer that Internet was not working. After investigation engineer has found no issues in Openreach network Engineer has visited end customer premises. No action is required. _x000D_22/8/2024:#Update End customer advised engineer that Internet was not working. After investigation engineer has found no issues in Openreach network Engineer has visited end customer premises. No action is required. _x000D_21/8/2024:#Update End customer advised engineer that Internet was not working. After investigation engineer has found no issues in Openreach network Engineer has visited end customer premises. No action is required. _x000D_02/05/2024: Order completed 08/04/2024: New order added to report | 23/8/2024:#Update End customer advised engineer that Internet was not working. After investigation engineer has found no issues in Openreach network Engineer has visited end customer premises. No action is required. _x000D_22/8/2024:#Update End customer advised engineer that Internet was not working. After investigation engineer has found no issues in Openreach network Engineer has visited end customer premises. No action is required. _x000D_21/8/2024:#Update End customer advised engineer that Internet was not working. After investigation engineer has found no issues in Openreach network Engineer has visited end customer premises. No action is required. _x000D_02/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300554 | 30013247 | 2.Commissioning |  |  | 2024-05-01 | 2024-05-01 | 2024-05-01 | TRUE |  |  |  | 2024-07-18 | [7 empty] | 0
79 | 641966 | 367 | Batch 3 May24 | Type 1 | SOGEA | Newington Park Express | LONDON | N1 4RA | 2024-05-02 | 10/06/2024: Line fault resolved 08/05/2024: Line fault -m Openreach has deemed this to be a non-appointment task 02/05/2024: Order completed 08/04/2024: New order added to report | 10/06/2024: Line fault resolved 08/05/2024: Line fault -m Openreach has deemed this to be a non-appointment task 02/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300564 | 30013257 | 6.Failed router install |  |  | 2024-05-01 | 2024-05-01 | 2024-05-02 | TRUE |  |  |  | 2024-05-31 |  |  |  | 2024-05-30 | 237004907083 |  |  | 1
80 | 477469 | 368 | Batch 3 May24 | Type 1 | SOGEA | Asha Puri Store | LONDON | N1 5AH | 2024-05-08 | 02/05/2024: Order completed 08/04/2024: New order added to report | 02/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300565 | 30013258 | 2.Commissioning |  |  | 2024-05-01 | 2024-05-01 | 2024-05-01 | TRUE |  |  |  | 2024-05-31 | [7 empty] | 0
81 | 644039 | 369 | Batch 3 May24 | Type 1 | SOGEA | Londis | London | N9 0TN | 2024-05-02 | 02/05/2024: Order completed 08/04/2024: New order added to report | 02/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300566 | 30013259 | 6.Failed router install |  |  | 2024-05-01 | 2024-05-01 | 2024-05-01 | TRUE |  |  |  | 2024-06-11 |  |  |  | 2024-06-11 | 237004907085 |  | 2024-07-01 | 1
82 | 412992 | 374 | Batch 3 May24 | Type 1 | SOGEA | Clapton Newsagents | LONDON | E5 8EQ | 2024-05-02 | 02/05/2024: Order completed 08/04/2024: New order added to report | 02/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300571 | 30013264 | 2.Commissioning |  |  | 2024-05-01 | 2024-05-01 | 2024-05-03 | TRUE |  |  |  | 2024-05-29 | [7 empty] | 0
83 | 420902 | 17 | Batch 1 Feb24 | Type 1 | SOGEA | The Co-Operative | Telford | TF2 8EF | 2024-05-24 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_23/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_23/5/2024:Order completed 10/5/2024:#Update - Network solution is required to complete the job - this has been escalated to Survey team to investigate and review what sort of network build work / identify the alternative routing for this site - review date of 13/05 03/05/24: Job has been sent to survey as alternate routing is required, OR will provide update this by 08/05 17/05/2024.We will continue to provide update as they become available. 09/04/2024: Abortive visit- retailer was not awar of the visit - rebooked on 02/05/2024. 19/03/24: New order added to report | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_23/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_23/5/2024:Order completed 10/5/2024:#Update - Network solution is required to complete the job - this has been escalated to Survey team to investigate and review what sort of network build work / identify the alternative routing for this site - review date of 13/05 03/05/24: Job has been sent to survey as alternate routing is required, OR will provide update this by 08/05 17/05/2024.We will continue to provide update as they become available. 09/04/2024: Abortive visit- retailer was not awar of the visit - rebooked on 02/05/2024. 19/03/24: New order added to report | 0 | 0 | 2024-03-26 | 26/03/2024: Allywn to arrange notify the retailer with the new date for compeleting the remaining work 13/03/24: Allwyn to discuss & confirm alternate NTE location with store. - closed 15/03 retailer advised that safe can be moved. 12/03/24: Allwyn to provide access on the 21/03. - closed access confirmed 15/03. 28/02/24: From meeting agreed that appointment will be scheduled for the 12/03. Action CSL to provide cost and confirm OOH slot required. - closed OoH work no longer required. 28/02/2024: Order to be upgraded, CSL to provide ECC charges and will push date out by a couple of wks to give timescale for approval. 16/02/2024: Action Allwyn to discuss with retailer on how to proceed and advise on out of hrs availability in order to rebook visit. |  |  | 3.Allwyn to arrange rtr install | VFS874908 | 30012240 | 2.Commissioning | AM | [8 empty] | 2024-03-27 | [7 empty] | 0
84 | 672703 | 57 | Batch 2 Apr24 | Type 1 | FTTP | Booze Master | Scunthorpe | DN15 7JR | 2024-05-03 | 03/05/24: Order completed 23/04/2024: Installation visit on 02/05 22/04/2024: Advanced upgrade approved 16/04/2024: Proposal went over to Vodafone on 04/04 - Awaiting update on upgrade to advance. 04/04/2024:Engineer has advised survey is required and additional network. Further updates to follow. 19/03/24: New order added to report | 03/05/24: Order completed 23/04/2024: Installation visit on 02/05 22/04/2024: Advanced upgrade approved 16/04/2024: Proposal went over to Vodafone on 04/04 - Awaiting update on upgrade to advance. 04/04/2024:Engineer has advised survey is required and additional network. Further updates to follow. 19/03/24: New order added to report |  |  | 2024-04-09 | 09/04/2024: Allwyn to make the retailer awar of the new date 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFP2300488 | 30013130 | 6.Failed router install | AM |  | 2024-05-02 | 2024-05-02 | 2024-05-21 | TRUE | [7 empty] | 2024-06-13 | 23A004948535 |  |  | 1
85 | 482851 | 132 | Batch 2 Apr24 | Type 1 | SOGEA | Supervalue | Craigavon | BT62 1EH | 2024-05-03 | 03/05/24: Order completed 02/05/24: Order completed on the second of May 17/04/2024: In order to complete the work it need a premium UPGRADE as there are no spare pairs available, awaiting Allwyn to approve 10/04/2024:OR completed the order by taking an existing line line services. DSO team back to the site and corected the work. 19/03/24: New order added to report | 03/05/24: Order completed 02/05/24: Order completed on the second of May 17/04/2024: In order to complete the work it need a premium UPGRADE as there are no spare pairs available, awaiting Allwyn to approve 10/04/2024:OR completed the order by taking an existing line line services. DSO team back to the site and corected the work. 19/03/24: New order added to report |  |  | 2024-04-16 | 16/04/2024: Allwyn to make the retailer aware. Confirmed 08/04/2024: CSL to provide update 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS938878 | 30013058 | 2.Commissioning | AM |  | 2024-04-05 | 2024-05-02 | 2024-05-02 | TRUE |  |  |  | 2024-06-12 | [7 empty] | 0
86 | 630728 | 183 | Batch 2 Apr24 | Type 1 | SOGEA | McBees | CRAIGAVON | BT66 6AQ | 2024-05-03 | 10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_03/05/24: Order completed 11/04/2024: Abortive visit - retailer was not awar of the visit - rebooked on 01/05/2024 19/03/24: New order added to report | 10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_03/05/24: Order completed 11/04/2024: Abortive visit - retailer was not awar of the visit - rebooked on 01/05/2024 19/03/24: New order added to report |  |  | 2024-04-17 | 17/04/2024: Allwyn to approve upgrade 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS939460 | 30013039 | 6.Failed router install | AM |  | 2024-04-09 | 2024-05-02 | 2024-05-02 | TRUE |  |  |  | 2024-04-29 |  |  |  | 2024-06-12 | 23A004952862 |  | 2024-07-01 | 1
87 | 638759 | 266 | Batch 2 Apr24 | Type 1 | FTTP | Premier The Corner Shop | Watford | WD18 0PX | 2024-05-03 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_23/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_03/05/24: Order completed 08/04/2024: New order added to report | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_23/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_03/05/24: Order completed 08/04/2024: New order added to report | 0 | 0 | 2024-04-15 | 15/04/2024:Allwyn to make retailer aware of visit as per the date in column T 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFP2300536 | 30013300 | 2.Commissioning | AM | [8 empty] | 2024-06-13 | [7 empty] | 0
88 | 104677 | 377 | Batch 3 May24 | Type 1 | SOGEA | Spring Box Newsagents | LONDON | E12 6RA | 2024-05-03 | 27/6/2024:#Update Delayed due to Line plant planning. We will provide updates when they become available. _x000D_25/6/2024:#Update Delayed due to Line plant planning. We will provide updates when they become available. _x000D_24/6/2024:#Update Delayed due to Line plant planning. We will provide updates when they become available. _x000D_20/6/2024:#Update Delayed due to Line plant planning. We will provide updates when they become available. _x000D_19/6/2024:#Update Delayed due to Line plant planning. We will provide updates when they become available. _x000D_18/6/2024:#Update Delayed due to Line plant planning. We will provide updates when they become available. _x000D_17/6/2024:#Update Retailer confirmed new appointment. _x000D_14/6/2024:#Update Retailer confirmed new appointment. _x000D_13/6/2024:#Update Retailer confirmed new appointment. _x000D_12/6/2024:#Update Retailer confirmed new appointment. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 27/6/2024:#Update Delayed due to Line plant planning. We will provide updates when they become available. _x000D_25/6/2024:#Update Delayed due to Line plant planning. We will provide updates when they become available. _x000D_24/6/2024:#Update Delayed due to Line plant planning. We will provide updates when they become available. _x000D_20/6/2024:#Update Delayed due to Line plant planning. We will provide updates when they become available. _x000D_19/6/2024:#Update Delayed due to Line plant planning. We will provide updates when they become available. _x000D_18/6/2024:#Update Delayed due to Line plant planning. We will provide updates when they become available. _x000D_17/6/2024:#Update Retailer confirmed new appointment. _x000D_14/6/2024:#Update Retailer confirmed new appointment. _x000D_13/6/2024:#Update Retailer confirmed new appointment. _x000D_12/6/2024:#Update Retailer confirmed new appointment. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300574 | 30013267 | 6.Failed router install |  |  | 2024-05-02 | 2024-05-02 | 2024-05-02 | TRUE |  |  |  | 2024-06-10 |  |  |  | 2024-06-10 | 237004907001 |  |  | 1
89 | 641538 | 378 | Batch 3 May24 | Type 1 | SOGEA | Maniakka Food and Wine | Ilford | IG2 6JZ | 2024-05-30 | 03/05/24: Order completed 08/04/2024: New order added to report | 03/05/24: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300575 | 30013268 | 2.Commissioning | AM |  | 2024-05-02 | 2024-05-02 | 2024-06-24 | TRUE |  |  |  | 2024-07-22 | [7 empty] | 0
90 | 486886 | 379 | Batch 3 May24 | Type 1 | SOGEA | Whitchurch Newsagents | Romford | RM3 9AA | 2024-05-03 | 03/05/24: Order completed 08/04/2024: New order added to report | 03/05/24: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300576 | 30013269 | 6.Failed router install |  |  | 2024-05-02 | 2024-05-02 | 2024-05-02 | TRUE |  |  |  | 2024-06-07 |  |  |  | 2024-08-22 | 242005010987 | 242005010987 | 2024-08-23 | 1
91 | 458164 | 380 | Batch 3 May24 | Type 1 | SOGEA | News Plus | ROMFORD | RM5 3SS | 2024-05-03 | 26/06/2024: OR fixed fault by installing missing socket 19/7/2024:#Update - A premium upgrade is required to progress the order. Proposal sent to Vodafone on 10/06 18/7/2024:#Update - A premium upgrade is required to progress the order. Proposal sent to Vodafone on 10/06 17/7/2024:#Update - A premium upgrade is required to progress the order. Proposal sent to Vodafone on 10/06 16/7/2024:#Update – Openreach have determined that further work is required to complete the installation. CSL are liaising with Openreach to understand what is necessary and will then send the ECC proposal. 15/7/2024:#Update – Openreach have determined that further work is required to complete the installation. CSL are liaising with Openreach to understand what is necessary and will then send the ECC proposal. 12/7/2024:#Update – Openreach have determined that further work is required to complete the installation. CSL are liaising with Openreach to understand what is necessary and will then send the ECC proposal. 11/7/2024:#Update – Openreach have determined that further work is required to complete the installation. CSL are liaising with Openreach to understand what is necessary and will then send the ECC proposal. 10/7/2024:#Update – Openreach have determined that further work is required to complete the installation. CSL are liaising with Openreach to understand what is necessary and will then send the ECC proposal. 9/7/2024:#Update – Openreach have determined that further work is required to complete the installation. CSL are liaising with Openreach to understand what is necessary and will then send the ECC proposal. 4/7/2024:#Update – Openreach have determined that further work is required to complete the installation. CSL are liaising with Openreach to understand what is necessary and will then send the ECC proposal. 3/7/2024:#Update – Openreach have determined that further work is required to complete the installation. CSL are liaising with Openreach to understand what is necessary and will then send the ECC proposal. 2/7/2024:0 1/7/2024:#Update – Openreach have determined that further work is required to complete the installation. CSL are liaising with Openreach to understand what is necessary and will then send the ECC proposal. 27/6/2024:#Update – Openreach have determined that further work is required to complete the installation. CSL are liaising with Openreach to understand what is necessary and will then send the ECC proposal. 25/6/2024:#Update – Openreach have determined that further work is required to complete the installation. CSL are liaising with Openreach to understand what is necessary and will then send the ECC proposal. 24/6/2024:#Update – Openreach have determined that further work is required to complete the installation. CSL are liaising with Openreach to understand what is necessary and will then send the ECC proposal. 20/6/2024:#Update – Openreach have determined that further work is required to complete the installation. CSL are liaising with Openreach to understand what is necessary and will then send the ECC proposal. 19/6/2024:#Update – Openreach have determined that further work is required to complete the installation. CSL are liaising with Openreach to understand what is necessary and will then send the ECC proposal. 18/6/2024:#Update – Openreach have determined that further work is required to complete the installation. CSL are liaising with Openreach to understand what is necessary and will then send the ECC proposal. 17/6/2024:#Update – Openreach have determined that further work is required to complete the installation. CSL are liaising with Openreach to understand what is necessary and will then send the ECC proposal. 14/6/2024:#Update – Openreach have determined that further work is required to complete the installation. CSL are liaising with Openreach to understand what is necessary and will then send the ECC proposal. 13/6/2024:#Update – Openreach have determined that further work is required to complete the installation. CSL are liaising with Openreach to understand what is necessary and will then send the ECC proposal. 12/6/2024:#Update – Openreach have determined that further work is required to complete the installation. CSL are liaising with Openreach to understand what is necessary and will then send the ECC proposal. 11/6/2024:0 10/6/2024:0 7/6/2024:0 6/6/2024:0 5/6/2024:0 4/6/2024:0 31/5/2024:0 30/5/2024:0 29/5/2024:0 28/5/2024:0 10/5/2024:0 02/05/2024: New order added to report | 26/06/2024: OR fixed fault by installing missing socket 19/7/2024:#Update - A premium upgrade is required to progress the order. Proposal sent to Vodafone on 10/06 18/7/2024:#Update - A premium upgrade is required to progress the order. Proposal sent to Vodafone on 10/06 17/7/2024:#Update - A premium upgrade is required to progress the order. Proposal sent to Vodafone on 10/06 16/7/2024:#Update – Openreach have determined that further work is required to complete the installation. CSL are liaising with Openreach to understand what is necessary and will then send the ECC proposal. 15/7/2024:#Update – Openreach have determined that further work is required to complete the installation. CSL are liaising with Openreach to understand what is necessary and will then send the ECC proposal. 12/7/2024:#Update – Openreach have determined that further work is required to complete the installation. CSL are liaising with Openreach to understand what is necessary and will then send the ECC proposal. 11/7/2024:#Update – Openreach have determined that further work is required to complete the installation. CSL are liaising with Openreach to understand what is necessary and will then send the ECC proposal. 10/7/2024:#Update – Openreach have determined that further work is required to complete the installation. CSL are liaising with Openreach to understand what is necessary and will then send the ECC proposal. 9/7/2024:#Update – Openreach have determined that further work is required to complete the installation. CSL are liaising with Openreach to understand what is necessary and will then send the ECC proposal. 4/7/2024:#Update – Openreach have determined that further work is required to complete the installation. CSL are liaising with Openreach to understand what is necessary and will then send the ECC proposal. 3/7/2024:#Update – Openreach have determined that further work is required to complete the installation. CSL are liaising with Openreach to understand what is necessary and will then send the ECC proposal. 2/7/2024:0 1/7/2024:#Update – Openreach have determined that further work is required to complete the installation. CSL are liaising with Openreach to understand what is necessary and will then send the ECC proposal. 27/6/2024:#Update – Openreach have determined that further work is required to complete the installation. CSL are liaising with Openreach to understand what is necessary and will then send the ECC proposal. 25/6/2024:#Update – Openreach have determined that further work is required to complete the installation. CSL are liaising with Openreach to understand what is necessary and will then send the ECC proposal. 24/6/2024:#Update – Openreach have determined that further work is required to complete the installation. CSL are liaising with Openreach to understand what is necessary and will then send the ECC proposal. 20/6/2024:#Update – Openreach have determined that further work is required to complete the installation. CSL are liaising with Openreach to understand what is necessary and will then send the ECC proposal. 19/6/2024:#Update – Openreach have determined that further work is required to complete the installation. CSL are liaising with Openreach to understand what is necessary and will then send the ECC proposal. 18/6/2024:#Update – Openreach have determined that further work is required to complete the installation. CSL are liaising with Openreach to understand what is necessary and will then send the ECC proposal. 17/6/2024:#Update – Openreach have determined that further work is required to complete the installation. CSL are liaising with Openreach to understand what is necessary and will then send the ECC proposal. 14/6/2024:#Update – Openreach have determined that further work is required to complete the installation. CSL are liaising with Openreach to understand what is necessary and will then send the ECC proposal. 13/6/2024:#Update – Openreach have determined that further work is required to complete the installation. CSL are liaising with Openreach to understand what is necessary and will then send the ECC proposal. 12/6/2024:#Update – Openreach have determined that further work is required to complete the installation. CSL are liaising with Openreach to understand what is necessary and will then send the ECC proposal. 11/6/2024:0 10/6/2024:0 7/6/2024:0 6/6/2024:0 5/6/2024:0 4/6/2024:0 31/5/2024:0 30/5/2024:0 29/5/2024:0 28/5/2024:0 10/5/2024:0 02/05/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300577 | 30013270 | 2.Commissioning |  |  | 2024-05-02 | 2024-05-02 | 2024-05-02 | TRUE |  |  |  | 2024-06-07 | [7 empty] | 0
92 | 649549 | 382 | Batch 3 May24 | Type 1 | FTTP/Mobile | Rakhs Peckham Newsagents Ltd | London | SE15 5SL | 2024-05-30 | 6/9/2024:#Update - Still awaiting approval on ECC's _x000D_5/9/2024:#Update - Still awaiting approval on ECC's _x000D_4/9/2024:#Update - Still awaiting approval on ECC's _x000D_3/9/2024:#Update - Still awaiting approval on ECC's _x000D_2/9/2024:#Update - Still awaiting approval on ECC's _x000D_29/8/2024:#Update - Still awaiting approval on ECC's _x000D_28/8/2024:#Update - Still awaiting approval on ECC's _x000D_27/8/2024:#Update - Still awaiting approval on ECC's _x000D_23/8/2024:#Update - Still awaiting approval on ECC's _x000D_22/8/2024:#Update - Still awaiting approval on ECC's _x000D_21/8/2024:#Update - Still awaiting approval on ECC's _x000D_20/8/2024:#Update - A premium upgrade is required to progress the order. Proposal sent to Vodafone on 10/06 _x000D_19/8/2024:#Update - A premium upgrade is required to progress the order. Proposal sent to Vodafone on 10/06 _x000D_19/8/2024:01381204 _x000D_16/8/2024:#Update - A premium upgrade is required to progress the order. Proposal sent to Vodafone on 10/06 _x000D_15/8/2024:#Update - A premium upgrade is required to progress the order. Proposal sent to Vodafone on 10/06 _x000D_14/8/2024:#Update - A premium upgrade is required to progress the order. Proposal sent to Vodafone on 10/06 _x000D_13/8/2024:#Update - A premium upgrade is required to progress the order. Proposal sent to Vodafone on 10/06 _x000D_12/8/2024:#Update - A premium upgrade is required to progress the order. Proposal sent to Vodafone on 10/06 _x000D_9/8/2024:#Update - A premium upgrade is required to progress the order. Proposal sent to Vodafone on 10/06 _x000D_8/8/2024:16/07/2024 _x000D_6/8/2024:16/07/2024 _x000D_5/8/2024:16/07/2024 _x000D_2/8/2024:16/07/2024 _x000D_1/8/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_30/7/2024:#Update - A premium upgrade is required to progress the order. Proposal sent to Vodafone on 10/06 _x000D_29/7/2024:#Update - A premium upgrade is required to progress the order. Proposal sent to Vodafone on 10/06 _x000D_29/7/2024:01381204 _x000D_26/7/2024:01381204 _x000D_24/7/2024:#Update - A premium upgrade is required to progress the order. Proposal sent to Vodafone on 10/06 _x000D_23/7/2024:#Update - A premium upgrade is required to progress the order. Proposal sent to Vodafone on 10/06 _x000D_22/7/2024:#Update - A premium upgrade is required to progress the order. Proposal sent to Vodafone on 10/06 _x000D_22/7/2024:#Update - A premium upgrade is required to progress the order. Proposal sent to Vodafone on 10/06 _x000D_03/05/24: Order completed 08/04/2024: New order added to report | 9/9/2024:#Update - Still awaiting approval on ECC's _x000D_6/9/2024:#Update - Still awaiting approval on ECC's _x000D_5/9/2024:#Update - Still awaiting approval on ECC's _x000D_4/9/2024:#Update - Still awaiting approval on ECC's _x000D_3/9/2024:#Update - Still awaiting approval on ECC's _x000D_2/9/2024:#Update - Still awaiting approval on ECC's _x000D_29/8/2024:#Update - Still awaiting approval on ECC's _x000D_28/8/2024:#Update - Still awaiting approval on ECC's _x000D_27/8/2024:#Update - Still awaiting approval on ECC's _x000D_23/8/2024:#Update - Still awaiting approval on ECC's _x000D_22/8/2024:#Update - Still awaiting approval on ECC's _x000D_21/8/2024:#Update - Still awaiting approval on ECC's _x000D_20/8/2024:#Update - A premium upgrade is required to progress the order. Proposal sent to Vodafone on 10/06 _x000D_19/8/2024:#Update - A premium upgrade is required to progress the order. Proposal sent to Vodafone on 10/06 _x000D_19/8/2024:01381204 _x000D_16/8/2024:#Update - A premium upgrade is required to progress the order. Proposal sent to Vodafone on 10/06 _x000D_15/8/2024:#Update - A premium upgrade is required to progress the order. Proposal sent to Vodafone on 10/06 _x000D_14/8/2024:#Update - A premium upgrade is required to progress the order. Proposal sent to Vodafone on 10/06 _x000D_13/8/2024:#Update - A premium upgrade is required to progress the order. Proposal sent to Vodafone on 10/06 _x000D_12/8/2024:#Update - A premium upgrade is required to progress the order. Proposal sent to Vodafone on 10/06 _x000D_9/8/2024:#Update - A premium upgrade is required to progress the order. Proposal sent to Vodafone on 10/06 _x000D_8/8/2024:16/07/2024 _x000D_6/8/2024:16/07/2024 _x000D_5/8/2024:16/07/2024 _x000D_2/8/2024:16/07/2024 _x000D_1/8/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_30/7/2024:#Update - A premium upgrade is required to progress the order. Proposal sent to Vodafone on 10/06 _x000D_29/7/2024:#Update - A premium upgrade is required to progress the order. Proposal sent to Vodafone on 10/06 _x000D_29/7/2024:01381204 _x000D_26/7/2024:01381204 _x000D_24/7/2024:#Update - A premium upgrade is required to progress the order. Proposal sent to Vodafone on 10/06 _x000D_23/7/2024:#Update - A premium upgrade is required to progress the order. Proposal sent to Vodafone on 10/06 _x000D_22/7/2024:#Update - A premium upgrade is required to progress the order. Proposal sent to Vodafone on 10/06 _x000D_22/7/2024:#Update - A premium upgrade is required to progress the order. Proposal sent to Vodafone on 10/06 _x000D_03/05/24: Order completed 08/04/2024: New order added to report | 0 | #Update - Still awaiting approval on ECC's |  |  |  |  | 2.Allwyn to arrange access | VFP2325017 | 30013272 | 1.Provisioning | AM |  | 2024-05-02 | 2024-05-02 |  | 0 | [11 empty] | 0
93 | 448048 | 385 | Batch 3 May24 | Type 1 | SOGEA | The Week Rococo News Magazines and | LONDON | W11 2HX | 2024-05-03 | 03/05/24: Order completed 08/04/2024: New order added to report | 03/05/24: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300582 | 30013275 | 2.Commissioning |  |  | 2024-05-02 | 2024-05-02 | 2024-05-02 | TRUE |  |  |  | 2024-07-17 | [7 empty] | 0
94 | 103888 | 392 | Batch 3 May24 | Type 1 | SOGEA | Tally Ho News | LONDON | N12 0EH | 2024-05-03 | 03/05/24: Order completed 08/04/2024: New order added to report | 03/05/24: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300589 | 30013282 | 2.Commissioning |  |  | 2024-05-02 | 2024-05-02 | 2024-05-02 | TRUE |  |  |  | 2024-06-11 | [7 empty] | 0
95 | 640328 | 394 | Batch 3 May24 | Type 1 | SOGEA | Pooles | Middlesex | HA7 4DU | 2024-05-03 | 03/05/24: Order completed 08/04/2024: New order added to report | 03/05/24: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300591 | 30013284 | 2.Commissioning |  |  | 2024-05-02 | 2024-05-02 | 2024-05-02 | TRUE |  |  |  | 2024-06-13 | [7 empty] | 0
96 | 466300 | 414 | Batch 3 May24 | Type 1 | FTTP | Premier | GLASGOW | G78 3JX | 2024-05-03 | 03/05/24: Order completed 08/04/2024: New order added to report | 03/05/24: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300611 | 30013304 | 6.Failed router install |  |  | 2024-05-02 | 2024-05-02 | 2024-05-02 | TRUE |  |  |  | 2024-06-05 |  |  |  | 2024-06-05 | 237004907061 |  |  | 1
97 | 631678 | 422 | Batch 3 May24 | Type 1 | FTTP | Premier Express Pencester Convenien | Dover | CT16 1BW | 2024-05-03 | 03/05/24: Order completed 08/04/2024: New order added to report | 03/05/24: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300619 | 30013312 | 6.Failed router install |  |  | 2024-05-02 | 2024-05-02 | 2024-05-02 | TRUE | [7 empty] | 2024-06-26 | 23A004945603 |  | 2024-07-01 | 1
98 | 637959 | 424 | Batch 3 May24 | Type 1 | SOGEA | Angies Newsagent | SEAFORD | BN25 2PF | 2024-05-03 | 10/5/2024:#Update - order completed by Openreach, Vodafone system not showing as completed yet _x000D_08/04/2024: New order added to report | 10/5/2024:#Update - order completed by Openreach, Vodafone system not showing as completed yet _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300621 | 30013314 | 6.Failed router install |  |  | 2024-05-02 | 2024-05-02 | 2024-05-02 | TRUE |  |  |  | 2024-06-07 |  |  |  | 2024-07-25 | 23A004945605 |  | 2024-07-29 | 1
99 | 642796 | 425 | Batch 3 May24 | Type 1 | SOGEA | Akshar News | ALDERSHOT | GU11 3PS | 2024-05-10 | 03/05/24: Order completed 08/04/2024: New order added to report | 03/05/24: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300622 | 30013315 | 2.Commissioning |  |  | 2024-05-02 | 2024-05-02 | 2024-05-08 | TRUE |  |  |  | 2024-06-28 | [7 empty] | 0
100 | 659775 | 834 | Batch 3 May24 | Type 1 | SOGEA | Bennetts Castle | Dagenham | RM8 3XP | 2024-06-07 | 10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_07/05/2024: Order completed 24/04/2024: Abortive visit - rebook on 03/05 retailer was not aware of the vist 23/04/2024: reappointment still pending, CSL will confirm new install date asap 15/04/2024: (Order Completed) Delayed in Processing. 04/04/2024: Engineer denied access - end user unaware of any installation 19/03/24: New order added to report | 10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_07/05/2024: Order completed 24/04/2024: Abortive visit - rebook on 03/05 retailer was not aware of the vist 23/04/2024: reappointment still pending, CSL will confirm new install date asap 15/04/2024: (Order Completed) Delayed in Processing. 04/04/2024: Engineer denied access - end user unaware of any installation 19/03/24: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301031 | 30013724 | 6.Failed router install |  |  | 2024-05-02 | 2024-05-02 | 2024-05-02 | TRUE |  |  |  | 2024-06-14 |  |  |  | 2024-06-14 | 23A004949281 |  | 2024-07-01 | 1
101 | 463413 | 440 | Batch 3 May24 | Type 1 | SOGEA | Sarswati News and Off Licence | LONDON | E16 4HP | 2024-05-07 | 07/05/2024: Order completed 08/04/2024: New order added to report | 07/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300637 | 30013330 | 2.Commissioning |  |  | 2024-05-03 | 2024-05-03 | 2024-05-03 | TRUE |  |  |  | 2024-06-10 | [7 empty] | 0
102 | 657409 | 443 | Batch 3 May24 | Type 1 | SOGEA | 1st Stop 2 Shop | Dundee | DD4 9PB | 2024-05-07 | 07/05/2024: Order completed 08/04/2024: New order added to report | 07/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300640 | 30013333 | 2.Commissioning |  |  | 2024-05-03 | 2024-05-03 | 2024-05-03 | TRUE |  |  |  | 2024-06-04 | [7 empty] | 0
103 | 648265 | 444 | Batch 3 May24 | Type 1 | FTTP | Top Spot | Newtownards | BT23 4JA | 2024-05-07 | 07/05/2024: Order completed 08/04/2024: New order added to report | 07/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300641 | 30013334 | 6.Failed router install |  |  | 2024-05-03 | 2024-05-03 | 2024-05-03 | TRUE | [7 empty] | 2024-06-11 | 23A004952878 |  | 2024-07-01 | 1
104 | 616503 | 448 | Batch 3 May24 | Type 1 | SOGEA | Hatch Lane News | London | E4 6LQ | 2024-05-07 | 07/05/2024: Order completed 08/04/2024: New order added to report | 07/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300645 | 30013338 | 2.Commissioning |  |  | 2024-05-03 | 2024-05-03 | 2024-05-03 | TRUE |  |  |  | 2024-06-10 | [7 empty] | 0
105 | 462214 | 451 | Batch 3 May24 | Type 1 | SOGEA | New Addington Food & Wine | CROYDON | CR0 0JD | 2024-05-07 | 07/05/2024: Order completed 08/04/2024: New order added to report | 07/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300648 | 30013341 | 2.Commissioning |  |  | 2024-05-03 | 2024-05-03 | 2024-05-03 | TRUE |  |  |  | 2024-06-07 | [7 empty] | 0
106 | 456333 | 459 | Batch 3 May24 | Type 1 | FTTP | T N S News Premier | MARGATE | CT9 2LZ | 2024-05-07 | 07/05/2024: Order completed 08/04/2024: New order added to report | 07/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300656 | 30013349 | 6.Failed router install |  |  | 2024-05-03 | 2024-05-03 | 2024-05-03 | TRUE | [7 empty] | 2024-06-26 | 23A004945607 |  | 2024-07-01 | 1
107 | 615289 | 465 | Batch 3 May24 | Type 1 | SOGEA | Island Newsagent | London | E3 3PN | 2024-05-07 | 07/05/2024: Order completed 08/04/2024: New order added to report | 07/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300662 | 30013355 | 2.Commissioning |  |  | 2024-05-03 | 2024-05-03 | 2024-05-03 | TRUE |  |  |  | 2024-06-10 | [7 empty] | 0
108 | 425901 | 466 | Batch 3 May24 | Type 1 | FTTP | Mo Munchies | LIVERPOOL | L7 8XD | 2024-05-07 | 07/05/2024: Order completed 08/04/2024: New order added to report | 07/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300663 | 30013356 | 6.Failed router install |  |  | 2024-05-03 | 2024-05-03 | 2024-05-03 | TRUE | [7 empty] | 2024-06-11 | 23A004952844 |  | 2024-07-01 | 1
109 | 111097 | 471 | Batch 3 May24 | Type 1 | FTTP | Normas Newsagents | DAGENHAM | RM8 3NT | 2024-05-07 | 07/05/2024: Order completed 08/04/2024: New order added to report | 07/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300668 | 30013361 | 6.Failed router install |  |  | 2024-05-03 | 2024-05-03 | 2024-05-03 | TRUE |  |  |  | 2024-06-07 |  |  |  | 2024-06-07 | 237004907095 |  |  | 1
110 | 662588 | 475 | Batch 3 May24 | Type 1 | SOGEA | College Service Station | Downpatrick | BT30 6LZ | 2024-05-07 | 07/05/2024: Order completed 08/04/2024: New order added to report | 07/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300672 | 30013365 | 6.Failed router install |  |  | 2024-05-03 | 2024-05-03 | 2024-05-03 | TRUE | [7 empty] | 2024-06-11 | 23A004952859 |  | 2024-07-01 | 1
111 | 659119 | 477 | Batch 3 May24 | Type 1 | FTTP | Oval Newsagents | Sidcup | DA15 9ER | 2024-05-07 | 10/5/2024:#Update - Engineer advised that retailer already has broadband and doesnt need another line. CSL to reappoint and allwyn to speak to end user and explain. _x000D_08/05/2024: Order completed 15/04/2024: Allwyn have advised that the retailer will be off on 01/05, Waiting CSL to provide new visit date 15/04/2024: order was delayed due to a mix-up with the engineer (specifically the retailer stated he already has broadband). rebooed on 01/05/2024 09/04/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing 19/03/24: New order added to report | 10/5/2024:#Update - Engineer advised that retailer already has broadband and doesnt need another line. CSL to reappoint and allwyn to speak to end user and explain. _x000D_08/05/2024: Order completed 15/04/2024: Allwyn have advised that the retailer will be off on 01/05, Waiting CSL to provide new visit date 15/04/2024: order was delayed due to a mix-up with the engineer (specifically the retailer stated he already has broadband). rebooed on 01/05/2024 09/04/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing 19/03/24: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300674 | 30013367 | 3.In life |  |  | 2024-05-03 | 2024-05-03 | 2024-05-03 | TRUE | [7 empty] | 2024-09-02 | 242005011147 | 242005011147 |  | 1
112 | 243062 | 494 | Batch 3 May24 | Type 3 | SoGEA/Mobile | Kwality Stores | LONDON | E13 9BA | 2024-05-10 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_23/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_10/5/2024:Order Completed _x000D_08/05/2024: Order completed 08/04/2024: New order added to report | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_23/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_10/5/2024:Order Completed _x000D_08/05/2024: Order completed 08/04/2024: New order added to report | 0 | 0 |  |  |  |  | 3.Allwyn to arrange rtr install | VFS970638 | 30013384 | 2.Commissioning | AM |  |  |  |  | 0 |  |  |  | 2024-06-17 | [7 empty] | 0
113 | 649242 | 509 | Batch 3 May24 | Type 1 | SOGEA | Welcome Westhoughton | Bolton | BL5 3AN | 2024-05-10 | 10/5/2024:Order Completed _x000D_08/05/2024: Order completed 08/04/2024: New order added to report | 10/5/2024:Order Completed _x000D_08/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300706 | 30013399 | 2.Commissioning |  |  | 2024-05-07 | 2024-05-07 | 2024-05-07 | TRUE |  |  |  | 2024-06-08 | [7 empty] | 0
114 | 639225 | 526 | Batch 3 May24 | Type 1 | FTTP | Kennedys Convenience Store | Burnley | BB10 4DH | 2024-05-10 | 10/5/2024:Order Completed _x000D_08/05/2024: Order completed 08/04/2024: New order added to report | 10/5/2024:Order Completed _x000D_08/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300723 | 30013416 | 6.Failed router install |  |  | 2024-05-07 | 2024-05-07 | 2024-05-07 | TRUE | [7 empty] | 2024-06-10 | 23A004948353 |  |  | 1
115 | 471612 | 560 | Batch 3 May24 | Type 1 | SOGEA | Supersaver | Merseyside | L20 6AH | 2024-06-07 | 10/5/2024:Order Completed _x000D_08/05/2024: Order completed 08/04/2024: New order added to report | 10/5/2024:Order Completed _x000D_08/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300757 | 30013450 | 6.Failed router install |  |  | 2024-05-07 | 2024-05-07 | 2024-05-07 | TRUE | [7 empty] | 2024-06-14 | 23A004948582 |  | 2024-07-01 | 1
116 | 468850 | 576 | Batch 3 May24 | Type 1 | SOGEA | Nisa Local | LEICESTER | LE4 2ED | 2024-06-07 | 10/5/2024:Order Completed _x000D_08/05/2024: Order completed 08/04/2024: New order added to report | 10/5/2024:Order Completed _x000D_08/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300773 | 30013466 | 6.Failed router install |  |  | 2024-05-07 | 2024-05-07 | 2024-05-07 | TRUE | [7 empty] | 2024-06-19 | 23A004945830 |  | 2024-07-01 | 1
117 | 472081 | 586 | Batch 3 May24 | Type 1 | SOGEA | All In One | Liverpool | L11 1EW | 2024-06-07 | 19/7/2024:Order Completed _x000D_18/7/2024:Order Completed _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_10/5/2024:Order Completed _x000D_08/05/2024: Order completed 08/04/2024: New order added to report | 19/7/2024:Order Completed _x000D_18/7/2024:Order Completed _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_10/5/2024:Order Completed _x000D_08/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300783 | 30013476 | 6.Failed router install |  |  | 2024-05-07 | 2024-05-07 | 2024-05-07 | TRUE | [7 empty] | 2024-06-20 | 242005013390 |  | 2024-07-01 | 1
118 | 622648 | 587 | Batch 3 May24 | Type 1 | SOGEA | Collindale Food Centre | London | NW9 6RR | 2024-06-07 | 22/7/2024:Order Completed _x000D_22/7/2024:Order Completed _x000D_10/5/2024:Update: Order Completed by Supplier _x000D_08/05/2024: Order completed 08/04/2024: New order added to report | 22/7/2024:Order Completed _x000D_22/7/2024:Order Completed _x000D_10/5/2024:Update: Order Completed by Supplier _x000D_08/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300784 | 30013477 | 2.Commissioning |  |  | 2024-05-07 | 2024-05-07 | 2024-05-07 | TRUE |  |  |  | 2024-06-20 | [7 empty] | 0
119 | 482193 | 589 | Batch 3 May24 | Type 1 | FTTP | Tels Confectionery | Down Patrick | BT30 6DW | 2024-06-07 | 10/5/2024:Order Completed _x000D_08/05/2024: Order completed 08/04/2024: New order added to report | 10/5/2024:Order Completed _x000D_08/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300786 | 30013479 | 6.Failed router install |  |  | 2024-05-07 | 2024-05-07 | 2024-05-07 | TRUE | [7 empty] | 2024-06-18 | 23A004952873 |  | 2024-07-01 | 1
120 | 614863 | 592 | Batch 3 May24 | Type 1 | FTTP | Alaxs Convenience Store Hednesford | Cannock | WS12 4DH | 2024-06-07 | 10/5/2024:Order Completed _x000D_08/05/2024: Order completed 08/04/2024: New order added to report | 10/5/2024:Order Completed _x000D_08/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300789 | 30013482 | 6.Failed router install |  |  | 2024-05-07 | 2024-05-07 | 2024-05-07 | TRUE | [7 empty] | 2024-06-10 | 238004917323 |  |  | 1
121 | 617723 | 595 | Batch 3 May24 | Type 1 | SOGEA | Meon Vale Londis | Straford Upon Avon | CV37 8YE | 2024-06-07 | 10/5/2024:Order Completed _x000D_08/05/2024: Order completed 08/04/2024: New order added to report | 10/5/2024:Order Completed _x000D_08/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300792 | 30013485 | 2.Commissioning |  |  | 2024-05-07 | 2024-05-07 | 2024-05-07 | TRUE |  |  |  | 2024-06-25 | [7 empty] | 0
122 | 648955 | 626 | Batch 3 May24 | Type 1 | SOGEA | Nisa Local | Birmingham | B36 0BU | 2024-06-07 | 10/5/2024:Order Completed _x000D_08/05/2024: Order completed 08/04/2024: New order added to report | 10/5/2024:Order Completed _x000D_08/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300823 | 30013516 | 2.Commissioning |  |  | 2024-05-07 | 2024-05-07 | 2024-05-07 | TRUE |  |  |  | 2024-06-13 | [7 empty] | 0
123 | 647995 | 628 | Batch 3 May24 | Type 1 | FTTP | Grange Convenience | Coventry | CV2 1RH | 2024-06-07 | 10/5/2024:Order Completed _x000D_08/05/2024: Order completed 08/04/2024: New order added to report | 10/5/2024:Order Completed _x000D_08/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300825 | 30013518 | 6.Failed router install |  |  | 2024-05-07 | 2024-05-07 | 2024-05-07 | TRUE | [7 empty] | 2024-06-17 | 23A004945896 |  | 2024-07-01 | 1
124 | 445454 | 629 | Batch 3 May24 | Type 1 | SOGEA | Premier Pauls Store | BEDFORD | MK42 7HR | 2024-06-07 | 10/5/2024:Order Completed _x000D_08/05/2024: Order completed 08/04/2024: New order added to report | 10/5/2024:Order Completed _x000D_08/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300826 | 30013519 | 2.Commissioning |  |  | 2024-05-07 | 2024-05-07 | 2024-05-07 | TRUE |  |  |  | 2024-06-13 | [7 empty] | 0
125 | 645799 | 641 | Batch 3 May24 | Type 1 | SOGEA | J.Walsh Newsagents | Holmer Green | HP15 6RW | 2024-06-07 | 10/5/2024:Order Completed _x000D_08/05/2024: Order completed 08/04/2024: New order added to report | 10/5/2024:Order Completed _x000D_08/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300838 | 30013531 | 6.Failed router install |  |  | 2024-05-07 | 2024-05-07 | 2024-05-07 | TRUE |  |  |  | 2024-06-07 |  |  |  | 2024-08-22 | 242005011156 | 242005011156 | 2024-08-23 | 1
126 | 111704 | 642 | Batch 3 May24 | Type 1 | SOGEA | Nisa Local | SOUTHEND-ON-SEA | SS1 2SG | 2024-06-07 | 10/5/2024:Order Completed _x000D_08/05/2024: Order completed 08/04/2024: New order added to report | 10/5/2024:Order Completed _x000D_08/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300839 | 30013532 | 2.Commissioning |  |  | 2024-05-07 | 2024-05-07 | 2024-05-07 | TRUE |  |  |  | 2024-06-20 | [7 empty] | 0
127 | 627526 | 692 | Batch 3 May24 | Type 1 | SOGEA | Vimals News | Croydon | CR0 1RB | 2024-06-07 | 6/9/2024:#Update - Allwyn confirmed socket is onsite. SG to reattempt install. _x000D_5/9/2024:#Update - Allwyn confirmed socket is onsite. SG to reattempt install. _x000D_4/9/2024:#Update - Allwyn confirmed socket is onsite. SG to reattempt install. _x000D_3/9/2024:#Update - Allwyn confirmed socket is onsite. SG to reattempt install. _x000D_2/9/2024:#Update - Allwyn confirmed socket is onsite. SG to reattempt install. _x000D_29/8/2024:#Update - Allwyn confirmed socket is onsite. SG to reattempt install. _x000D_28/8/2024:#Update - Allwyn confirmed socket is onsite. SG to reattempt install. _x000D_27/8/2024:#Update - Allwyn confirmed socket is onsite. SG to reattempt install. _x000D_10/5/2024:Order Completed _x000D_09/05/2024: Order completed 08/04/2024: New order added to report | 9/9/2024:#Update - Allwyn confirmed socket is onsite. SG to reattempt install. _x000D_6/9/2024:#Update - Allwyn confirmed socket is onsite. SG to reattempt install. _x000D_5/9/2024:#Update - Allwyn confirmed socket is onsite. SG to reattempt install. _x000D_4/9/2024:#Update - Allwyn confirmed socket is onsite. SG to reattempt install. _x000D_3/9/2024:#Update - Allwyn confirmed socket is onsite. SG to reattempt install. _x000D_2/9/2024:#Update - Allwyn confirmed socket is onsite. SG to reattempt install. _x000D_29/8/2024:#Update - Allwyn confirmed socket is onsite. SG to reattempt install. _x000D_28/8/2024:#Update - Allwyn confirmed socket is onsite. SG to reattempt install. _x000D_27/8/2024:#Update - Allwyn confirmed socket is onsite. SG to reattempt install. _x000D_10/5/2024:Order Completed _x000D_09/05/2024: Order completed 08/04/2024: New order added to report | 0 | #Update - Allwyn confirmed socket is onsite. SG to reattempt install. |  |  |  |  | 3.Allwyn to arrange rtr install | VFP2300889 | 30013582 | 2.Commissioning |  |  | 2024-05-08 | 2024-05-08 | 2024-05-08 | TRUE |  |  |  | 2024-07-18 | [7 empty] | 0
128 | 240938 | 693 | Batch 3 May24 | Type 1 | SOGEA | J Evans Newsagents & Post Office | Bridgend | CF32 0AW | 2024-06-07 | 10/5/2024:Openreach Delay : Automated testing has identified a potential fault _x000D_09/05/2024: Order completed 08/04/2024: New order added to report | 10/5/2024:Openreach Delay : Automated testing has identified a potential fault _x000D_09/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300890 | 30013583 | 2.Commissioning |  |  | 2024-05-08 | 2024-05-08 | 2024-05-08 | TRUE |  |  |  | 2024-06-12 | [7 empty] | 0
129 | 426205 | 705 | Batch 3 May24 | Type 1 | FTTP | Chirag News and Groceries | HORSHAM | RH12 4ET | 2024-06-07 | 10/5/2024:Order Completed _x000D_09/05/2024: Order completed 08/04/2024: New order added to report | 10/5/2024:Order Completed _x000D_09/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300902 | 30013595 | 6.Failed router install |  |  | 2024-05-08 | 2024-05-08 | 2024-05-08 | TRUE | [7 empty] | 2024-06-06 | 23A004948807 |  |  | 1
130 | 457779 | 706 | Batch 3 May24 | Type 1 | SOGEA | P and J News | SANDOWN | PO36 8AF | 2024-06-07 | 10/5/2024:Order Completed _x000D_09/05/2024: Order completed 08/04/2024: New order added to report | 10/5/2024:Order Completed _x000D_09/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 6.No action | VFP2300903 | 30013596 | 6.Failed router install |  |  | 2024-05-08 | 2024-05-08 | 2024-05-08 | TRUE | [7 empty] | 2024-07-18 | 242005008527 |  | 2024-07-19 | 1
131 | 643404 | 711 | Batch 3 May24 | Type 1 | SOGEA | Premier | Edinburgh | EH14 3BG | 2024-06-07 | 10/5/2024:Order Completed _x000D_09/05/2024: Order completed 08/04/2024: New order added to report | 10/5/2024:Order Completed _x000D_09/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300908 | 30013601 | 2.Commissioning |  |  | 2024-05-08 | 2024-05-08 | 2024-05-08 | TRUE |  |  |  | 2024-06-03 | [7 empty] | 0
132 | 444117 | 715 | Batch 3 May24 | Type 1 | FTTP | Newsham Convenience Store | BLYTH | NE24 4AG | 2024-06-07 | 10/5/2024:Order Completed _x000D_09/05/2024: Order completed 08/04/2024: New order added to report | 10/5/2024:Order Completed _x000D_09/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300912 | 30013605 | 2.Commissioning |  |  | 2024-05-08 | 2024-05-08 | 2024-05-08 | TRUE |  |  |  | 2024-05-30 | [7 empty] | 0
133 | 428811 | 716 | Batch 3 May24 | Type 1 | SOGEA | Nisa Ss Food and Wine | HIGH WYCOMBE | HP13 7HA | 2024-06-07 | 10/5/2024:Order Completed _x000D_09/05/2024: Order completed 08/04/2024: New order added to report | 10/5/2024:Order Completed _x000D_09/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300913 | 30013606 | 2.Commissioning |  |  | 2024-05-08 | 2024-05-08 | 2024-05-08 | TRUE |  |  |  | 2024-06-05 | [7 empty] | 0
134 | 664052 | 720 | Batch 3 May24 | Type 1 | SOGEA | Gays Newsagents | HERTFORD | SG14 1BY | 2024-06-07 | 10/5/2024:Order Completed _x000D_09/05/2024: Order completed 08/04/2024: New order added to report | 10/5/2024:Order Completed _x000D_09/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300917 | 30013610 | 6.Failed router install |  |  | 2024-05-08 | 2024-05-08 | 2024-05-08 | TRUE |  |  |  | 2024-06-13 |  |  |  | 2024-06-13 | 237004906981 |  | 2024-07-01 | 1
135 | 658918 | 723 | Batch 3 May24 | Type 1 | FTTP | Aum News | London | N3 1TR | 2024-06-07 | 10/5/2024:Order Completed _x000D_09/05/2024: Order completed 08/04/2024: New order added to report | 10/5/2024:Order Completed _x000D_09/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300920 | 30013613 | 6.Failed router install |  |  | 2024-05-08 | 2024-05-08 | 2024-05-08 | TRUE |  |  |  | 2024-06-11 |  |  |  | 2024-06-11 | 237004907088 |  | 2024-07-01 | 1
136 | 445920 | 730 | Batch 3 May24 | Type 1 | FTTP/Mobile | IMPERIAL NEWSAGENTS | FELTHAM | TW14 8BP | 2024-06-07 | 6/9/2024:#Update - order requires a (step-1) survey. We will continue to provide update as they become available. _x000D_5/9/2024:#Update - order requires a (step-1) survey. We will continue to provide update as they become available. _x000D_4/9/2024:#Update - order requires a (step-1) survey. We will continue to provide update as they become available. _x000D_3/9/2024:#Update - order requires a (step-1) survey. We will continue to provide update as they become available. _x000D_2/9/2024:#Update - order requires a (step-1) survey. We will continue to provide update as they become available. _x000D_29/8/2024:#Update - there is no available network/capacity issues therefore this order is cancelled and will be reraised when fibre is available in the area, CSL to monitor and update progress accordingly _x000D_28/8/2024:#Update - order has been delayed. Civil work required. We will continue to provide update as they become available. _x000D_27/8/2024:#Update - order has been delayed. Civil work required. We will continue to provide update as they become available. _x000D_22/8/2024:#Update - order has been delayed. Civil work required. We will continue to provide update as they become available. _x000D_21/8/2024:#Update - order has been delayed. Civil work required. We will continue to provide update as they become available. _x000D_20/8/2024:#Update - order has been delayed. Civil work required. We will continue to provide update as they become available. _x000D_19/8/2024:#Update - order has been delayed. Civil work required. We will continue to provide update as they become available. _x000D_19/8/2024:01413678 _x000D_16/8/2024:#Update - order has been delayed. Civil work required. We will continue to provide update as they become available. _x000D_15/8/2024:#Update - order has been delayed. Civil work required. We will continue to provide update as they become available. _x000D_14/8/2024:#Update - order has been delayed. Civil work required. We will continue to provide update as they become available. _x000D_13/8/2024:#Update - order has been delayed. Civil work required. We will continue to provide update as they become available. _x000D_12/8/2024:#Update - order has been delayed. Civil work required. We will continue to provide update as they become available. _x000D_9/8/2024:#Update - order has been delayed. Civil work required. We will continue to provide update as they become available. _x000D_8/8/2024:02/08/2024 _x000D_6/8/2024:02/08/2024 _x000D_5/8/2024:02/08/2024 _x000D_2/8/2024:22/07/2024 _x000D_1/8/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_30/7/2024:#Update - continued delays due to civil work required. Our Suppliers have given us a review date of 29/07. We will continue to provide update as they become available. _x000D_29/7/2024:#Update - continued delays due to civil work required. Our Suppliers have given us a review date of 29/07. We will continue to provide update as they become available. _x000D_29/7/2024:01413678 _x000D_26/7/2024:01413678 _x000D_24/7/2024:#Update - continued delays due to civil work required. Our Suppliers have given us a review date of 29/07. We will continue to provide update as they become available. _x000D_23/7/2024:#Update - continued delays due to civil work required. Our Suppliers have given us a review date of 29/07. We will continue to provide update as they become available. _x000D_22/7/2024:#Update - continued delays due to Civil work required. Our Suppliers have given us a review date of 22/07 and we will continue to provide update as they become available. _x000D_22/7/2024:#Update - continued delays due to Civil work required. Our Suppliers have given us a review date of 22/07 and we will continue to provide update as they become available. _x000D_10/5/2024:Update: Order Completed by Supplier _x000D_09/05/2024: Order completed 08/04/2024: New order added to report | 9/9/2024:#Update - order requires a (step-1) survey. We will continue to provide update as they become available. _x000D_6/9/2024:#Update - order requires a (step-1) survey. We will continue to provide update as they become available. _x000D_5/9/2024:#Update - order requires a (step-1) survey. We will continue to provide update as they become available. _x000D_4/9/2024:#Update - order requires a (step-1) survey. We will continue to provide update as they become available. _x000D_3/9/2024:#Update - order requires a (step-1) survey. We will continue to provide update as they become available. _x000D_2/9/2024:#Update - order requires a (step-1) survey. We will continue to provide update as they become available. _x000D_29/8/2024:#Update - there is no available network/capacity issues therefore this order is cancelled and will be reraised when fibre is available in the area, CSL to monitor and update progress accordingly _x000D_28/8/2024:#Update - order has been delayed. Civil work required. We will continue to provide update as they become available. _x000D_27/8/2024:#Update - order has been delayed. Civil work required. We will continue to provide update as they become available. _x000D_22/8/2024:#Update - order has been delayed. Civil work required. We will continue to provide update as they become available. _x000D_21/8/2024:#Update - order has been delayed. Civil work required. We will continue to provide update as they become available. _x000D_20/8/2024:#Update - order has been delayed. Civil work required. We will continue to provide update as they become available. _x000D_19/8/2024:#Update - order has been delayed. Civil work required. We will continue to provide update as they become available. _x000D_19/8/2024:01413678 _x000D_16/8/2024:#Update - order has been delayed. Civil work required. We will continue to provide update as they become available. _x000D_15/8/2024:#Update - order has been delayed. Civil work required. We will continue to provide update as they become available. _x000D_14/8/2024:#Update - order has been delayed. Civil work required. We will continue to provide update as they become available. _x000D_13/8/2024:#Update - order has been delayed. Civil work required. We will continue to provide update as they become available. _x000D_12/8/2024:#Update - order has been delayed. Civil work required. We will continue to provide update as they become available. _x000D_9/8/2024:#Update - order has been delayed. Civil work required. We will continue to provide update as they become available. _x000D_8/8/2024:02/08/2024 _x000D_6/8/2024:02/08/2024 _x000D_5/8/2024:02/08/2024 _x000D_2/8/2024:22/07/2024 _x000D_1/8/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_30/7/2024:#Update - continued delays due to civil work required. Our Suppliers have given us a review date of 29/07. We will continue to provide update as they become available. _x000D_29/7/2024:#Update - continued delays due to civil work required. Our Suppliers have given us a review date of 29/07. We will continue to provide update as they become available. _x000D_29/7/2024:01413678 _x000D_26/7/2024:01413678 _x000D_24/7/2024:#Update - continued delays due to civil work required. Our Suppliers have given us a review date of 29/07. We will continue to provide update as they become available. _x000D_23/7/2024:#Update - continued delays due to civil work required. Our Suppliers have given us a review date of 29/07. We will continue to provide update as they become available. _x000D_22/7/2024:#Update - continued delays due to Civil work required. Our Suppliers have given us a review date of 22/07 and we will continue to provide update as they become available. _x000D_22/7/2024:#Update - continued delays due to Civil work required. Our Suppliers have given us a review date of 22/07 and we will continue to provide update as they become available. _x000D_10/5/2024:Update: Order Completed by Supplier _x000D_09/05/2024: Order completed 08/04/2024: New order added to report | 0 | #Update - order requires a (step-1) survey. We will continue to provide update as they become available. | 2024-05-09 | 09/05/2024: CSL to provide an update |  |  | 2.Allwyn to arrange access | VFP2325395 | 30013620 | 1.Provisioning | AM |  | 2024-05-08 | 2024-05-08 |  | 0 | [11 empty] | 0
137 | 657868 | 738 | Batch 3 May24 | Type 1 | FTTP | Winnies | Craigavon | BT62 1JL | 2024-06-07 | 10/5/2024:Order Completed _x000D_09/05/2024: Order completed 08/04/2024: New order added to report | 10/5/2024:Order Completed _x000D_09/05/2024: Order completed 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300935 | 30013628 | 6.Failed router install |  |  | 2024-05-08 | 2024-05-08 | 2024-05-08 | TRUE | [7 empty] | 2024-06-12 | 23A004952863 |  | 2024-07-01 | 1
138 | 471078 | 578 | Batch 3 May24 | Type 1 | FTTP | Nearby Candy Bar | Ballymena | BT42 2BD | 2024-06-07 | 10/5/2024:Order Completed _x000D_08/04/2024: New order added to report | 10/5/2024:Order Completed _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300775 | 30013468 | 6.Failed router install |  |  | 2024-05-09 | 2024-05-09 | 2024-05-09 | TRUE | [7 empty] | 2024-06-10 | 23A004952881 |  | 2024-07-01 | 1
139 | 470352 | 684 | Batch 3 May24 | Type 1 | FTTP | Nisa Extra | SOUTHEND-ON-SEA | SS1 3EU | 2024-06-07 | 10/5/2024:Order Completed _x000D_08/04/2024: New order added to report | 10/5/2024:Order Completed _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300881 | 30013574 | 2.Commissioning |  |  | 2024-05-07 | 2024-05-09 | 2024-05-09 | TRUE |  |  |  | 2024-06-06 | [7 empty] | 0
140 | 460203 | 750 | Batch 3 May24 | Type 3 | SOGEA | Pop In Shop Newsagents | ERITH | DA8 3EZ | 2024-06-07 | 10/5/2024:Order Completed _x000D_08/04/2024: New order added to report | 10/5/2024:Order Completed _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300947 | 30013640 | 2.Commissioning |  |  | 2024-05-09 | 2024-05-09 | 2024-05-09 | Not Applicable |  |  |  | 2024-08-02 | [7 empty] | 0
141 | 645959 | 751 | Batch 3 May24 | Type 1 | FTTP | The Wee Shop | Comber | BT23 5BX | 2024-06-07 | 10/5/2024:Order Completed _x000D_08/04/2024: New order added to report | 10/5/2024:Order Completed _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300948 | 30013641 | 2.Commissioning |  |  | 2024-05-09 | 2024-05-09 | 2024-05-09 | TRUE |  |  |  | 2024-06-11 | [7 empty] | 0
142 | 434639 | 752 | Batch 3 May24 | Type 1 | SOGEA | ARCADE NEWS | NEWTON-LE-WILLOWS | WA12 9BQ | 2024-06-07 | 10/5/2024:Order Completed _x000D_08/04/2024: New order added to report | 10/5/2024:Order Completed _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300949 | 30013642 | 6.Failed router install |  |  | 2024-05-09 | 2024-05-09 | 2024-05-09 | TRUE | [7 empty] | 2024-06-12 | 23A004952851 |  | 2024-07-01 | 1
143 | 201624 | 763 | Batch 3 May24 | Type 1 | SOGEA | Premier Prabins Convenience Store | BRADFORD | BD5 7ES | 2024-06-07 | 10/5/2024:Order Completed _x000D_08/04/2024: New order added to report | 10/5/2024:Order Completed _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300960 | 30013653 | 2.Commissioning |  |  | 2024-05-09 | 2024-05-09 | 2024-05-09 | TRUE |  |  |  | 2024-06-07 | [7 empty] | 0
144 | 648640 | 765 | Batch 3 May24 | Type 1 | SOGEA | Taylor News | London | N1 1EF | 2024-06-07 | 10/5/2024:Order Completed _x000D_08/04/2024: New order added to report | 10/5/2024:Order Completed _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300962 | 30013655 | 2.Commissioning |  |  | 2024-05-09 | 2024-05-09 | 2024-05-09 | TRUE |  |  |  | 2024-06-11 | [7 empty] | 0
145 | 612130 | 769 | Batch 3 May24 | Type 1 | SOGEA | Sanghas | Liverpool | L11 2SF | 2024-06-07 | 10/5/2024:Order Completed _x000D_08/04/2024: New order added to report | 10/5/2024:Order Completed _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300966 | 30013659 | 6.Failed router install |  |  | 2024-05-09 | 2024-05-09 | 2024-05-09 | TRUE | [7 empty] | 2024-06-12 | 23A004952849 |  | 2024-07-01 | 1
146 | 486527 | 773 | Batch 3 May24 | Type 1 | SoGEA/Mobile | Station Express | London | NW10 4UX | 2024-06-07 | 16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/08 AM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/08 AM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/08 AM _x000D_13/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/08 AM _x000D_12/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/08 AM _x000D_9/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/08 AM _x000D_8/8/2024:01/08/2024 _x000D_6/8/2024:01/08/2024 _x000D_5/8/2024:01/08/2024 _x000D_2/8/2024:01/08/2024 _x000D_1/8/2024:01/08/2024 _x000D_31/7/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_30/7/2024:#Update - This has been sent to the engineers and they have given us a review date of 26/07/2024.We will continue to provide update as they become available. _x000D_29/7/2024:#Update - This has been sent to the engineers and they have given us a review date of 26/07/2024.We will continue to provide update as they become available. _x000D_29/7/2024:01482885 _x000D_26/7/2024:01482885 _x000D_24/7/2024:#Update - This has been sent to the engineers and they have given us a review date of 26/07/2024.We will continue to provide update as they become available. _x000D_23/7/2024:#Update - This has been sent to the engineers and they have given us a review date of 26/07/2024.We will continue to provide update as they become available. _x000D_22/7/2024:#Update - Order has been delayed as line plant work is required. CSL will update as more information become available. _x000D_22/7/2024:#Update - Order has been delayed as line plant work is required. CSL will update as more information become available. _x000D_10/5/2024:Update: Order Completed by Supplier _x000D_08/04/2024: New order added to report | 16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/08 AM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/08 AM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/08 AM _x000D_13/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/08 AM _x000D_12/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/08 AM _x000D_9/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/08 AM _x000D_8/8/2024:01/08/2024 _x000D_6/8/2024:01/08/2024 _x000D_5/8/2024:01/08/2024 _x000D_2/8/2024:01/08/2024 _x000D_1/8/2024:01/08/2024 _x000D_31/7/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_30/7/2024:#Update - This has been sent to the engineers and they have given us a review date of 26/07/2024.We will continue to provide update as they become available. _x000D_29/7/2024:#Update - This has been sent to the engineers and they have given us a review date of 26/07/2024.We will continue to provide update as they become available. _x000D_29/7/2024:01482885 _x000D_26/7/2024:01482885 _x000D_24/7/2024:#Update - This has been sent to the engineers and they have given us a review date of 26/07/2024.We will continue to provide update as they become available. _x000D_23/7/2024:#Update - This has been sent to the engineers and they have given us a review date of 26/07/2024.We will continue to provide update as they become available. _x000D_22/7/2024:#Update - Order has been delayed as line plant work is required. CSL will update as more information become available. _x000D_22/7/2024:#Update - Order has been delayed as line plant work is required. CSL will update as more information become available. _x000D_10/5/2024:Update: Order Completed by Supplier _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300970 | 30013663 | 2.Commissioning | AM |  | 2024-08-12 | 2024-08-12 | 2024-08-12 12:00 | 1 | 1 |  |  | 2024-06-12 | [7 empty] | 0
147 | 636083 | 783 | Batch 3 May24 | Type 1 | SOGEA | Pramukh New Ltd | Leicester | LE4 6AS | 2024-06-07 | 10/5/2024:Order Completed _x000D_08/04/2024: New order added to report | 10/5/2024:Order Completed _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300980 | 30013673 | 2.Commissioning |  |  | 2024-05-09 | 2024-05-09 | 2024-05-09 | TRUE |  |  |  | 2024-06-06 | [7 empty] | 0
148 | 240975 | 795 | Batch 3 May24 | Type 1 | SOGEA | Naisbitt News | North Shields | NE29 6QZ | 2024-06-07 | 10/5/2024:Order Completed _x000D_02/05/2024: New order added to report | 10/5/2024:Order Completed _x000D_02/05/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300992 | 30013685 | 6.Failed router install |  |  | 2024-05-09 | 2024-05-09 | 2024-05-09 | TRUE |  |  |  | 2024-05-31 |  |  |  | 2024-05-31 | 238004917209 |  |  | 1
149 | 669697 | 1535 | Batch 4 Jun24 | Type 1 | SOGEA | Spar Stores | Peterhead | AB42 1PL | 2024-06-07 | 19/7/2024:#Update Approval for an upgrade with VF. _x000D_18/7/2024:#Update Approval for an upgrade with VF. _x000D_17/7/2024:#Update Approval for an upgrade with VF. _x000D_16/7/2024:#Update Approval for an upgrade with VF. _x000D_15/7/2024:#Update Approval for an upgrade with VF. _x000D_12/7/2024:#Update Approval for an upgrade with VF. _x000D_11/7/2024:#Update Approval for an upgrade with VF. _x000D_10/7/2024:#Update Approval for an upgrade with VF. _x000D_9/7/2024:#Update Approval for an upgrade with VF. _x000D_4/7/2024:#Update Approval for an upgrade with VF. _x000D_3/7/2024:#Update Approval for an upgrade with VF. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update Approval for an upgrade with VF. _x000D_27/6/2024:#Update Approval for an upgrade with VF. _x000D_25/6/2024:#Update Chased Openreach regarding OOH, updates to follow. _x000D_24/6/2024:#Update Chased Openreach regarding OOH, updates to follow. _x000D_20/6/2024:#Update Chased Openreach regarding OOH, updates to follow. _x000D_19/6/2024:#Update Chased Openreach regarding OOH, updates to follow. _x000D_18/6/2024:#Update Chased Openreach regarding OOH, updates to follow. _x000D_17/6/2024:#Update Chased Openreach regarding OOH, updates to follow. _x000D_14/6/2024:#Update Chased Openreach regarding OOH, updates to follow. _x000D_13/6/2024:#Update Chased Openreach regarding OOH, updates to follow. _x000D_12/6/2024:#Update Chased Openreach regarding OOH, updates to follow. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 19/7/2024:#Update Approval for an upgrade with VF. _x000D_18/7/2024:#Update Approval for an upgrade with VF. _x000D_17/7/2024:#Update Approval for an upgrade with VF. _x000D_16/7/2024:#Update Approval for an upgrade with VF. _x000D_15/7/2024:#Update Approval for an upgrade with VF. _x000D_12/7/2024:#Update Approval for an upgrade with VF. _x000D_11/7/2024:#Update Approval for an upgrade with VF. _x000D_10/7/2024:#Update Approval for an upgrade with VF. _x000D_9/7/2024:#Update Approval for an upgrade with VF. _x000D_4/7/2024:#Update Approval for an upgrade with VF. _x000D_3/7/2024:#Update Approval for an upgrade with VF. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update Approval for an upgrade with VF. _x000D_27/6/2024:#Update Approval for an upgrade with VF. _x000D_25/6/2024:#Update Chased Openreach regarding OOH, updates to follow. _x000D_24/6/2024:#Update Chased Openreach regarding OOH, updates to follow. _x000D_20/6/2024:#Update Chased Openreach regarding OOH, updates to follow. _x000D_19/6/2024:#Update Chased Openreach regarding OOH, updates to follow. _x000D_18/6/2024:#Update Chased Openreach regarding OOH, updates to follow. _x000D_17/6/2024:#Update Chased Openreach regarding OOH, updates to follow. _x000D_14/6/2024:#Update Chased Openreach regarding OOH, updates to follow. _x000D_13/6/2024:#Update Chased Openreach regarding OOH, updates to follow. _x000D_12/6/2024:#Update Chased Openreach regarding OOH, updates to follow. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2338535 | 30015391 | 2.Commissioning | AM |  | 2024-05-24 | 2024-05-09 | 2024-05-09 | TRUE |  |  |  | 2024-06-04 | [7 empty] | 0
150 | 658912 | 370 | Batch 3 May24 | Type 1 | SoGEA/Mobile | News Express | London | N9 0EQ | 2024-05-30 | 6/9/2024:#Update Sent chaser to VF on upgrade / OOH _x000D_5/9/2024:#Update Sent chaser to VF on upgrade / OOH _x000D_4/9/2024:#Update Sent chaser to VF on upgrade / OOH _x000D_3/9/2024:#Update Sent chaser to VF on upgrade / OOH _x000D_2/9/2024:#Update Sent chaser to VF on upgrade / OOH _x000D_29/8/2024:#Update Sent chaser to VF on upgrade / OOH _x000D_28/8/2024:#Update Sent chaser to VF on upgrade / OOH _x000D_27/8/2024:#Update Sent chaser to VF on upgrade / OOH _x000D_22/8/2024:#Update Sent chaser to VF on upgrade / OOH _x000D_21/8/2024:#Update Sent chaser to VF on upgrade / OOH _x000D_20/8/2024:#Update Sent chaser to VF on upgrade / OOH _x000D_19/8/2024:#Update Sent chaser to VF on upgrade / OOH _x000D_19/8/2024:01349301 _x000D_16/8/2024:#Update Sent chaser to VF on upgrade / OOH _x000D_15/8/2024:#Update Sent chaser to VF on upgrade / OOH _x000D_14/8/2024:#Update Sent chaser to VF on upgrade / OOH _x000D_13/8/2024:#Update Sent chaser to VF on upgrade / OOH _x000D_12/8/2024:#Update Sent chaser to VF on upgrade / OOH _x000D_9/8/2024:#Update Sent chaser to VF on upgrade / OOH _x000D_8/8/2024:25/07/2024 _x000D_6/8/2024:25/07/2024 _x000D_5/8/2024:25/07/2024 _x000D_2/8/2024:25/07/2024 _x000D_1/8/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_30/7/2024:#Update Sent chaser to VF on upgrade / OOH _x000D_29/7/2024:#Update Sent chaser to VF on upgrade / OOH _x000D_29/7/2024:01349301 _x000D_26/7/2024:01349301 _x000D_24/7/2024:#Update Approval for an upgrade with VF. _x000D_23/7/2024:#Update Approval for an upgrade with VF. _x000D_22/7/2024:#Update Approval for an upgrade with VF. _x000D_22/7/2024:#Update Approval for an upgrade with VF. _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 9/9/2024:#Update Sent chaser to VF on upgrade / OOH _x000D_6/9/2024:#Update Sent chaser to VF on upgrade / OOH _x000D_5/9/2024:#Update Sent chaser to VF on upgrade / OOH _x000D_4/9/2024:#Update Sent chaser to VF on upgrade / OOH _x000D_3/9/2024:#Update Sent chaser to VF on upgrade / OOH _x000D_2/9/2024:#Update Sent chaser to VF on upgrade / OOH _x000D_29/8/2024:#Update Sent chaser to VF on upgrade / OOH _x000D_28/8/2024:#Update Sent chaser to VF on upgrade / OOH _x000D_27/8/2024:#Update Sent chaser to VF on upgrade / OOH _x000D_22/8/2024:#Update Sent chaser to VF on upgrade / OOH _x000D_21/8/2024:#Update Sent chaser to VF on upgrade / OOH _x000D_20/8/2024:#Update Sent chaser to VF on upgrade / OOH _x000D_19/8/2024:#Update Sent chaser to VF on upgrade / OOH _x000D_19/8/2024:01349301 _x000D_16/8/2024:#Update Sent chaser to VF on upgrade / OOH _x000D_15/8/2024:#Update Sent chaser to VF on upgrade / OOH _x000D_14/8/2024:#Update Sent chaser to VF on upgrade / OOH _x000D_13/8/2024:#Update Sent chaser to VF on upgrade / OOH _x000D_12/8/2024:#Update Sent chaser to VF on upgrade / OOH _x000D_9/8/2024:#Update Sent chaser to VF on upgrade / OOH _x000D_8/8/2024:25/07/2024 _x000D_6/8/2024:25/07/2024 _x000D_5/8/2024:25/07/2024 _x000D_2/8/2024:25/07/2024 _x000D_1/8/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_30/7/2024:#Update Sent chaser to VF on upgrade / OOH _x000D_29/7/2024:#Update Sent chaser to VF on upgrade / OOH _x000D_29/7/2024:01349301 _x000D_26/7/2024:01349301 _x000D_24/7/2024:#Update Approval for an upgrade with VF. _x000D_23/7/2024:#Update Approval for an upgrade with VF. _x000D_22/7/2024:#Update Approval for an upgrade with VF. _x000D_22/7/2024:#Update Approval for an upgrade with VF. _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 0 | #Update Sent chaser to VF on upgrade / OOH | 2024-05-13 | 13/05/2024: CSL to provide an update 02/05/2024: CSL to provide update. |  |  | 2.Allwyn to arrange access | VFS970447 | 30013260 | 1.Provisioning | AM |  | 2024-05-10 | 2024-09-04 |  | 0 | [11 empty] | 0
151 | 481826 | 481 | Batch 3 May24 | Type 1 | FTTP | Premier Store Delce | Rochester | ME1 2DH | 2024-04-08 | 10/5/2024:Order Completed _x000D_08/04/2024: New order added to report | 10/5/2024:Order Completed _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300678 | 30013371 | 6.Failed router install |  |  | 2024-05-10 | 2024-05-10 | 2024-05-10 | TRUE | [7 empty] | 2024-06-05 | 23A004948811 |  |  | 1
152 | 252696 | 619 | Batch 3 May24 | Type 1 | FTTP | Joes News and Supermarket | LIVERPOOL | L32 0TU | 2024-06-07 | 10/5/2024:0 _x000D_08/04/2024: New order added to report | 10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300816 | 30013509 | 6.Failed router install |  |  | 2024-05-10 | 2024-05-10 | 2024-05-10 | TRUE | [7 empty] | 2024-06-12 | 23A004952847 |  | 2024-07-01 | 1
153 | 654533 | 798 | Batch 3 May24 | Type 1 | SOGEA | Londis | Rochdale | OL16 3QF | 2024-06-07 | 10/5/2024:0 _x000D_08/04/2024: New order added to report | 10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300995 | 30013688 | 2.Commissioning |  |  | 2024-05-10 | 2024-05-10 | 2024-05-10 | TRUE |  |  |  | 2024-06-06 | [7 empty] | 0
154 | 467532 | 808 | Batch 3 May24 | Type 1 | SOGEA | Supervalu | BALLYMONEY | BT53 7AB | 2024-06-07 | 10/5/2024:0 _x000D_08/04/2024: New order added to report | 10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301005 | 30013698 | 6.Failed router install |  |  | 2024-05-10 | 2024-05-10 | 2024-05-10 | TRUE | [7 empty] | 2024-06-10 | 23A004952879 |  |  | 1
155 | 659686 | 816 | Batch 3 May24 | Type 1 | SOGEA | Nisa Local | ROTHERHAM | S62 5DY | 2024-06-07 | 10/5/2024:0 _x000D_08/04/2024: New order added to report | 10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301013 | 30013706 | 6.Failed router install |  |  | 2024-05-10 | 2024-05-10 | 2024-05-10 | TRUE | [7 empty] | 2024-06-12 | 23A004948537 |  | 2024-07-01 | 1
156 | 428026 | 821 | Batch 3 May24 | Type 1 | SOGEA | CENTRA | COLERAINE | BT51 3QJ | 2024-06-07 | 6/9/2024:#Update re-raised order internally to resolve routing issues. Installation has been committed for 16/09. Allwyn made aware. _x000D_5/9/2024:#Update re-raised order internally to resolve routing issues. Installation has been committed for 16/09. Allwyn made aware. _x000D_4/9/2024:#Update re-raised order internally to resolve routing issues. Installation has been committed for 16/09. Allwyn made aware. _x000D_3/9/2024:#Update re-raised order internally to resolve routing issues. Installation has been committed for 16/09. Allwyn made aware. _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 9/9/2024:#Update re-raised order internally to resolve routing issues. Installation has been committed for 16/09. Allwyn made aware. _x000D_6/9/2024:#Update re-raised order internally to resolve routing issues. Installation has been committed for 16/09. Allwyn made aware. _x000D_5/9/2024:#Update re-raised order internally to resolve routing issues. Installation has been committed for 16/09. Allwyn made aware. _x000D_4/9/2024:#Update re-raised order internally to resolve routing issues. Installation has been committed for 16/09. Allwyn made aware. _x000D_3/9/2024:#Update re-raised order internally to resolve routing issues. Installation has been committed for 16/09. Allwyn made aware. _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 0 | #Update re-raised order internally to resolve routing issues. Installation has been committed for 16/09. Allwyn made aware. |  |  |  |  | 3.Allwyn to arrange rtr install | VFP2301018 | 30013711 | 2.Commissioning |  |  | 2024-05-10 | 2024-05-10 | 2024-05-10 | TRUE |  |  |  | 2024-06-07 | [7 empty] | 0
157 | 631390 | 184 | Batch 2 Apr24 | Type 1 | SOGEA | Manor Stores | Slough | SL2 1NW | 2024-04-25 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:Update: Order Amended _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:Update: Order Amended _x000D_ | 0 | 0 | 2024-04-11 | 11/04/2024: Allwyn to let the retailer aware of the visit. Closed 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS939462 | 30013038 | 2.Commissioning | PM | [8 empty] | 2024-06-18 | [7 empty] | 0
158 | 632816 | 194 | Batch 2 Apr24 | Type 1 | FTTP | Smart Choices | Huyton | L36 3RG | 2024-04-23 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_ | 0 | 0 |  | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFP2300460 | 30013051 | 2.Commissioning | AM | [8 empty] | 2024-06-21 | [7 empty] | 0
159 | 651240 | 537 | Batch 3 May24 | Type 1 | SOGEA | P & H News | LONDON | E15 3EU | 2024-04-08 | 10/5/2024:0 _x000D_08/04/2024: New order added to report | 10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300734 | 30013427 | 2.Commissioning |  |  | 2024-05-13 | 2024-05-13 | 2024-05-13 | TRUE |  |  |  | 2024-06-19 | [7 empty] | 0
160 | 460649 | 719 | Batch 3 May24 | Type 1 | SOGEA | Woodgrange News | LONDON | E7 8BA | 2024-06-07 | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024: _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:#Update - Allwyn confirmed appointment with Retailer, required adjustment to 18/06 as per retailers req. Got permission for Sharing contact details with OR. _x000D_ | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024: _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:#Update - Allwyn confirmed appointment with Retailer, required adjustment to 18/06 as per retailers req. Got permission for Sharing contact details with OR. _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300916 | 30013609 | 6.Failed router install |  |  | 2024-05-13 | 2024-05-13 | 2024-05-13 | TRUE | [7 empty] | 2024-06-19 | 23A004945745 |  | 2024-07-01 | 1
161 | 670429 | 84 | Batch 2 Apr24 | Type 1 | SOGEA | Todays Extra | Grimsby | DN33 2LY | 2024-05-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:Order Completed _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:Order Completed _x000D_ | 0 | 0 | 2024-05-14 | 14/05/2024: Allwyn to arrange access 23/04/2024: Vodafone to send the proposal to Allwyn- Allwyn to approve up 65676 SOGEA Advanced upgrade 19/04/2024: Allwyn have spoken with the retailer and he is happy to install the cable near to CCTV. 08/04/2024: Allwyn to check with the retailer regarding the shop glass front and advised how they wish to proceed. With the Advanced order or change to Site Type 3, if Signal permits. 04/04/2024: Allwyn to check with the retailer when can the installation happen CSL to provide updates once recived after 21/3/2024 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS939392 | 30013173 | 2.Commissioning | AM | [8 empty] | 2024-06-13 | [7 empty] | 0 | 670429
162 | 471816 | 682 | Batch 3 May24 | Type 1 | SOGEA | Circle 8 | Newton Abbot | TQ12 2EY | 2024-06-07 | 2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_ | 2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300879 | 30013572 | 2.Commissioning |  |  | 2024-05-07 | 2024-05-14 | 2024-05-14 | TRUE |  |  |  | 2024-06-25 | [7 empty] | 0
163 | 610317 | 354 | Batch 3 May24 | Type 1 | SoGEA/Mobile | News Box Super Store | Hounslow | TW3 1NP | 2024-05-30 | 6/9/2024:#Update Retailer confirmed 27/09, AM. _x000D_5/9/2024:#Update Retailer confirmed 27/09, AM. _x000D_4/9/2024:#Update Retailer confirmed 27/09, AM. _x000D_3/9/2024:#Update Retailer confirmed 27/09, AM. _x000D_2/9/2024:#Update Retailer confirmed 27/09, AM. _x000D_29/8/2024:#Update Retailer confirmed 27/09, AM. _x000D_28/8/2024:#Update Retailer confirmed 27/09, AM. _x000D_27/8/2024:#Update Chased VF for cost approval _x000D_22/8/2024:#Update Chased VF for cost approval _x000D_21/8/2024:#Update Chased VF for cost approval _x000D_20/8/2024:#Update Chased VF for cost approval _x000D_19/8/2024:#Update Chased VF for cost approval _x000D_19/8/2024:01349352 _x000D_16/8/2024:#Update Chased VF for cost approval _x000D_15/8/2024:#Update Chased VF for cost approval _x000D_14/8/2024:#Update Chased VF for cost approval _x000D_13/8/2024:#Update Chased VF for cost approval _x000D_12/8/2024:#Update Chased VF for cost approval _x000D_9/8/2024:#Update Chased VF for cost approval _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update Chased VF for cost approval _x000D_29/7/2024:#Update Chased VF for cost approval _x000D_29/7/2024:01349352 _x000D_26/7/2024:01349352 _x000D_24/7/2024:#Update Awaiting for charges to be approved. _x000D_23/7/2024:#Update Awaiting for charges to be approved. _x000D_22/7/2024:#Update Awaiting for charges to be approved. _x000D_22/7/2024:#Update Awaiting for charges to be approved. _x000D_10/5/2024: #Update - Order is delayed as external work is required. CSL to liaise with Openreach and update as necessary. _x000D_08/04/2024: New order added to report | 9/9/2024:#Update Retailer confirmed 27/09, AM. _x000D_6/9/2024:#Update Retailer confirmed 27/09, AM. _x000D_5/9/2024:#Update Retailer confirmed 27/09, AM. _x000D_4/9/2024:#Update Retailer confirmed 27/09, AM. _x000D_3/9/2024:#Update Retailer confirmed 27/09, AM. _x000D_2/9/2024:#Update Retailer confirmed 27/09, AM. _x000D_29/8/2024:#Update Retailer confirmed 27/09, AM. _x000D_28/8/2024:#Update Retailer confirmed 27/09, AM. _x000D_27/8/2024:#Update Chased VF for cost approval _x000D_22/8/2024:#Update Chased VF for cost approval _x000D_21/8/2024:#Update Chased VF for cost approval _x000D_20/8/2024:#Update Chased VF for cost approval _x000D_19/8/2024:#Update Chased VF for cost approval _x000D_19/8/2024:01349352 _x000D_16/8/2024:#Update Chased VF for cost approval _x000D_15/8/2024:#Update Chased VF for cost approval _x000D_14/8/2024:#Update Chased VF for cost approval _x000D_13/8/2024:#Update Chased VF for cost approval _x000D_12/8/2024:#Update Chased VF for cost approval _x000D_9/8/2024:#Update Chased VF for cost approval _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update Chased VF for cost approval _x000D_29/7/2024:#Update Chased VF for cost approval _x000D_29/7/2024:01349352 _x000D_26/7/2024:01349352 _x000D_24/7/2024:#Update Awaiting for charges to be approved. _x000D_23/7/2024:#Update Awaiting for charges to be approved. _x000D_22/7/2024:#Update Awaiting for charges to be approved. _x000D_22/7/2024:#Update Awaiting for charges to be approved. _x000D_10/5/2024: #Update - Order is delayed as external work is required. CSL to liaise with Openreach and update as necessary. _x000D_08/04/2024: New order added to report | 0 | #Update Retailer confirmed 27/09, AM. |  | 02/05/2024: CSL to provide update. |  |  | 2.Allwyn to arrange access | VFS970434 | 30013244 | 1.Provisioning | AM |  | 2024-05-01 | 2024-09-04 |  | 0 | [11 empty] | 0
164 | 100365 | 415 | Batch 3 May24 | Type 1 | SOGEA | Fairhill Store | HAMILTON | ML3 8JY | 2024-05-16 | 10/5/2024:0 _x000D_08/04/2024: New order added to report | 10/5/2024:0 _x000D_08/04/2024: New order added to report |  |  | 2024-05-16 | 16/05/2024: Allwyn to make the retailer aware of the new date 03/05/2024: CSL to provide update |  |  | 3.Allwyn to arrange rtr install | VFP2300612 | 30013305 | 6.Failed router install |  |  | 2024-05-15 | 2024-05-15 | 2024-05-21 | TRUE | [7 empty] | 2024-06-12 | 23A004945404 |  | 2024-07-01 | 1
165 | 449396 | 564 | Batch 3 May24 | Type 1 | SOGEA | Mace | Belfast | BT12 6HN | 2024-06-07 | 10/5/2024:03/05/2024: Unfortunately your order has been delayed due to insufficient capacity at our suppliers cabinets. Our suppliers have given us a review date of 21/05/2024 when we expect to know if this is a temporary or permanent issue. We will continue to pro _x000D_08/04/2024: New order added to report | 10/5/2024:03/05/2024: Unfortunately your order has been delayed due to insufficient capacity at our suppliers cabinets. Our suppliers have given us a review date of 21/05/2024 when we expect to know if this is a temporary or permanent issue. We will continue to pro _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300761 | 30013454 | 6.Failed router install |  |  | 2024-05-07 | 2024-05-15 | 2024-05-15 | TRUE | [7 empty] | 2024-06-20 | 23A004952971 |  | 2024-07-01 | 1
166 | 471832 | 581 | Batch 3 May24 | Type 1 | SOGEA | Taughmonagh Convenience Store | Belfast | BT9 6QR | 2024-06-07 | 10/5/2024:0 _x000D_08/04/2024: New order added to report | 10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300778 | 30013471 | 6.Failed router install |  |  | 2024-05-05 | 2024-05-15 | 2024-05-15 | TRUE | [7 empty] | 2024-06-20 | 23A004952973 |  | 2024-07-01 | 1
167 | 648976 | 679 | Batch 3 May24 | Type 1 | SOGEA | Centra | BELFAST | BT14 6LA | 2024-06-07 | 10/5/2024:0 _x000D_08/04/2024: New order added to report | 10/5/2024:0 _x000D_08/04/2024: New order added to report |  |  | 2024-05-08 | 08/05/2024: CSL to provide an update |  |  | 3.Allwyn to arrange rtr install | VFP2300876 | 30013569 | 6.Failed router install |  |  | 2024-05-07 | 2024-05-15 | 2024-05-15 | TRUE | [7 empty] | 2024-06-20 | 23A004952970 |  | 2024-07-01 | 1
168 | 432518 | 714 | Batch 3 May24 | Type 1 | SOGEA | NEWS FOR YOU | CANVEY ISLAND | SS8 7AE | 2024-06-07 | 19/7/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_18/7/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_17/7/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_16/7/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_15/7/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_12/7/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_11/7/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_10/7/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_9/7/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_4/7/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_3/7/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_2/7/2024:0 _x000D_1/7/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_27/6/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_25/6/2024:#Update order delay due to wayleave being required. Update due 24/06 AM. _x000D_24/6/2024:#Update order delay due to wayleave being required. Update due 24/06 AM. _x000D_20/6/2024:#Update order delay due to wayleave being required. Update due 24/06 AM. _x000D_19/6/2024:#Update order delay due to wayleave being required. Update due 24/06 AM. _x000D_18/6/2024:#Update This order has been delayed as site survey is required. This has been sent to the survey engineers and they have given us a review date of 31/05/2024.We will continue to provide update as they become available _x000D_17/6/2024:#Update This order has been delayed as site survey is required. This has been sent to the survey engineers and they have given us a review date of 31/05/2024.We will continue to provide update as they become available _x000D_14/6/2024:#Update This order has been delayed as site survey is required. This has been sent to the survey engineers and they have given us a review date of 31/05/2024.We will continue to provide update as they become available _x000D_13/6/2024:#Update This order has been delayed as site survey is required. This has been sent to the survey engineers and they have given us a review date of 31/05/2024.We will continue to provide update as they become available _x000D_12/6/2024:#Update This order has been delayed as site survey is required. This has been sent to the survey engineers and they have given us a review date of 31/05/2024.We will continue to provide update as they become available _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 19/7/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_18/7/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_17/7/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_16/7/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_15/7/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_12/7/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_11/7/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_10/7/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_9/7/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_4/7/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_3/7/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_2/7/2024:0 _x000D_1/7/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_27/6/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_25/6/2024:#Update order delay due to wayleave being required. Update due 24/06 AM. _x000D_24/6/2024:#Update order delay due to wayleave being required. Update due 24/06 AM. _x000D_20/6/2024:#Update order delay due to wayleave being required. Update due 24/06 AM. _x000D_19/6/2024:#Update order delay due to wayleave being required. Update due 24/06 AM. _x000D_18/6/2024:#Update This order has been delayed as site survey is required. This has been sent to the survey engineers and they have given us a review date of 31/05/2024.We will continue to provide update as they become available _x000D_17/6/2024:#Update This order has been delayed as site survey is required. This has been sent to the survey engineers and they have given us a review date of 31/05/2024.We will continue to provide update as they become available _x000D_14/6/2024:#Update This order has been delayed as site survey is required. This has been sent to the survey engineers and they have given us a review date of 31/05/2024.We will continue to provide update as they become available _x000D_13/6/2024:#Update This order has been delayed as site survey is required. This has been sent to the survey engineers and they have given us a review date of 31/05/2024.We will continue to provide update as they become available _x000D_12/6/2024:#Update This order has been delayed as site survey is required. This has been sent to the survey engineers and they have given us a review date of 31/05/2024.We will continue to provide update as they become available _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-05-09 | 09/05/2024: CSL to provide an update |  |  | 3.Allwyn to arrange rtr install | VFP2300911 | 30013604 | 6.Failed router install |  |  | 2024-05-08 | 2024-05-15 | 2024-05-15 | TRUE | [7 empty] | 2024-06-20 | 23A004945744 |  | 2024-07-01 | 1
169 | 432102 | 727 | Batch 3 May24 | Type 1 | FTTP/Mobile | NEWSFARE | LONDON | NW10 8SE | 2024-06-07 | 6/9/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_5/9/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_4/9/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_3/9/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_2/9/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_29/8/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_28/8/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_27/8/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_22/8/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_21/8/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_20/8/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_19/8/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_19/8/2024:01392987 _x000D_16/8/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_15/8/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_14/8/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_13/8/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_12/8/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_9/8/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_8/8/2024:26/06/2024 _x000D_6/8/2024:26/06/2024 _x000D_5/8/2024:26/06/2024 _x000D_2/8/2024:26/06/2024 _x000D_1/8/2024:26/06/2024 _x000D_31/7/2024:26/06/2024 _x000D_31/7/2024:26/06/2024 _x000D_30/7/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_29/7/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_29/7/2024:01392987 _x000D_26/7/2024:01392987 _x000D_24/7/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_23/7/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_22/7/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_22/7/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 9/9/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_6/9/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_5/9/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_4/9/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_3/9/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_2/9/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_29/8/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_28/8/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_27/8/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_22/8/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_21/8/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_20/8/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_19/8/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_19/8/2024:01392987 _x000D_16/8/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_15/8/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_14/8/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_13/8/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_12/8/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_9/8/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_8/8/2024:26/06/2024 _x000D_6/8/2024:26/06/2024 _x000D_5/8/2024:26/06/2024 _x000D_2/8/2024:26/06/2024 _x000D_1/8/2024:26/06/2024 _x000D_31/7/2024:26/06/2024 _x000D_31/7/2024:26/06/2024 _x000D_30/7/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_29/7/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_29/7/2024:01392987 _x000D_26/7/2024:01392987 _x000D_24/7/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_23/7/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_22/7/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_22/7/2024:#Update Still waiting for wayleave - no response. Update 2/07 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 0 | #Update Still waiting for wayleave - no response. Update 2/07 | 2024-05-16 | 09/05/2024: CSL to provide an update |  |  | 2.Allwyn to arrange access | VFP2300924 | 30013617 | 1.Provisioning | AM | [16 empty] | 0
170 | 470127 | 1299 | Batch 3 May24 | Type 1 | SOGEA | Keystore | KILMARNOCK | KA2 9HF | 2024-06-07 | 10/5/2024:0 08/04/2024: New order added to report | 10/5/2024:0 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301496 | 30014189 | 2.Commissioning |  |  | 2024-05-30 | 2024-05-15 | 2024-05-15 | TRUE |  |  |  | 2024-06-12 | [7 empty] | 0
171 | 205171 | 1313 | Batch 3 May24 | Type 1 | SOGEA | Nisa Local | PETERBOROUGH | PE4 6HN | 2024-06-07 | 29/8/2024:#Update - Update from engineer - -Installed above existing socket behind counter. Tested and proved working as NO ROUTER PROVIDED AT SITE. Staff made aware of location of socket which has been tagged with date, service ID and intended use (lotto) _x000D_28/8/2024:#Update - Update from engineer - -Installed above existing socket behind counter. Tested and proved working as NO ROUTER PROVIDED AT SITE. Staff made aware of location of socket which has been tagged with date, service ID and intended use (lotto) _x000D_27/8/2024:#Update - Update from engineer - -Installed above existing socket behind counter. Tested and proved working as NO ROUTER PROVIDED AT SITE. Staff made aware of location of socket which has been tagged with date, service ID and intended use (lotto) _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024: _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:#Update - Please be informed the engineer was unable to complete the task as Complex DIG work is required. To progress this further, a DIG activity has been raised. Please allow 7 working days for an update. Review date 07/06/24 _x000D_ | 29/8/2024:#Update - Update from engineer - -Installed above existing socket behind counter. Tested and proved working as NO ROUTER PROVIDED AT SITE. Staff made aware of location of socket which has been tagged with date, service ID and intended use (lotto) _x000D_28/8/2024:#Update - Update from engineer - -Installed above existing socket behind counter. Tested and proved working as NO ROUTER PROVIDED AT SITE. Staff made aware of location of socket which has been tagged with date, service ID and intended use (lotto) _x000D_27/8/2024:#Update - Update from engineer - -Installed above existing socket behind counter. Tested and proved working as NO ROUTER PROVIDED AT SITE. Staff made aware of location of socket which has been tagged with date, service ID and intended use (lotto) _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024: _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:#Update - Please be informed the engineer was unable to complete the task as Complex DIG work is required. To progress this further, a DIG activity has been raised. Please allow 7 working days for an update. Review date 07/06/24 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301510 | 30014203 | 2.Commissioning |  |  | 2024-05-09 | 2024-05-15 | 2024-05-15 | TRUE |  |  |  | 2024-06-12 | [7 empty] | 0
172 | 467716 | 85 | Batch 2 Apr24 | Type 1 | FTTP | Chimes News | LONDON | SW16 5SX | 2024-05-17 | 16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_17/05/2024: Olo order completed 26/04/2024:Abortive visit on 26/04/2024 - retailer was not aware of the visit - order was marked as completed by mistake, and marked as comissioning. 08/04/2024: Order completed 05/04/2024: No updates on CSL report on 05/04/2024. 19/03/24: New order added to report | 16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_17/05/2024: Olo order completed 26/04/2024:Abortive visit on 26/04/2024 - retailer was not aware of the visit - order was marked as completed by mistake, and marked as comissioning. 08/04/2024: Order completed 05/04/2024: No updates on CSL report on 05/04/2024. 19/03/24: New order added to report |  |  | 2024-04-26 | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS943699 | 30013143 | 6.Failed router install | AM | [6 empty] | 2024-04-17 |  | 2024-04-29 |  | Hassan Shariff | 7932267557 | 2024-08-14 | 242005011170 | 242005011170 | 2024-08-16 | 1
173 | 632547 | 603 | Batch 3 May24 | Type 1 | FTTP | Premier Gurnos Stores | Merthyr Tydfil | CF47 9SB | 2024-06-07 | 17/05/2024: Olo order completed 26/04/2024:Abortive visit on 26/04/2024 - retailer was not aware of the visit - order was marked as completed by mistake, and marked as comissioning. 08/04/2024: Order completed 05/04/2024: No updates on CSL report on 05/04/2024. 19/03/24: New order added to report | 17/05/2024: Olo order completed 26/04/2024:Abortive visit on 26/04/2024 - retailer was not aware of the visit - order was marked as completed by mistake, and marked as comissioning. 08/04/2024: Order completed 05/04/2024: No updates on CSL report on 05/04/2024. 19/03/24: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300800 | 30013493 | 6.Failed router install |  |  | 2024-05-16 | 2024-05-16 | 2024-05-16 | TRUE | [7 empty] | 2024-06-17 | 23A004945377 |  | 2024-07-01 | 1
174 | 651325 | 826 | Batch 3 May24 | Type 1 | SOGEA | Best One Yoden Road | Peterlee | SR8 5DY | 2024-06-07 | 17/05/2024: Olo order completed 26/04/2024:Abortive visit on 26/04/2024 - retailer was not aware of the visit - order was marked as completed by mistake, and marked as comissioning. 08/04/2024: Order completed 05/04/2024: No updates on CSL report on 05/04/2024. 19/03/24: New order added to report | 17/05/2024: Olo order completed 26/04/2024:Abortive visit on 26/04/2024 - retailer was not aware of the visit - order was marked as completed by mistake, and marked as comissioning. 08/04/2024: Order completed 05/04/2024: No updates on CSL report on 05/04/2024. 19/03/24: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301023 | 30013716 | 6.Failed router install |  |  | 2024-05-16 | 2024-05-16 | 2024-05-16 | TRUE | [7 empty] | 2024-06-14 | 237004907020 |  | 2024-07-01 | 1
175 | 460358 | 828 | Batch 3 May24 | Type 1 | SOGEA | Shop 4 U | CANNOCK | WS11 5RL | 2024-06-07 | 17/05/2024: Olo order completed 26/04/2024:Abortive visit on 26/04/2024 - retailer was not aware of the visit - order was marked as completed by mistake, and marked as comissioning. 08/04/2024: Order completed 05/04/2024: No updates on CSL report on 05/04/2024. 19/03/24: New order added to report | 17/05/2024: Olo order completed 26/04/2024:Abortive visit on 26/04/2024 - retailer was not aware of the visit - order was marked as completed by mistake, and marked as comissioning. 08/04/2024: Order completed 05/04/2024: No updates on CSL report on 05/04/2024. 19/03/24: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301025 | 30013718 | 6.Failed router install |  |  | 2024-05-16 | 2024-05-16 | 2024-05-16 | TRUE | [7 empty] | 2024-06-10 | 238004917321 |  |  | 1
176 | 461452 | 843 | Batch 3 May24 | Type 1 | SOGEA | West End Store | NORTHOLT | UB5 4JP | 2024-06-07 | 17/05/2024: Olo order completed 26/04/2024:Abortive visit on 26/04/2024 - retailer was not aware of the visit - order was marked as completed by mistake, and marked as comissioning. 08/04/2024: Order completed 05/04/2024: No updates on CSL report on 05/04/2024. 19/03/24: New order added to report | 17/05/2024: Olo order completed 26/04/2024:Abortive visit on 26/04/2024 - retailer was not aware of the visit - order was marked as completed by mistake, and marked as comissioning. 08/04/2024: Order completed 05/04/2024: No updates on CSL report on 05/04/2024. 19/03/24: New order added to report |  |  | 2024-05-17 | 17/05/2024: CSL to provide an update |  |  | 3.Allwyn to arrange rtr install | VFP2301040 | 30013733 | 2.Commissioning |  |  | 2024-05-16 | 2024-05-16 | 2024-05-20 | TRUE |  |  |  | 2024-06-18 | [7 empty] | 0
177 | 648595 | 845 | Batch 3 May24 | Type 1 | SOGEA | Erne's | PLYMOUTH | PL5 2TG | 2024-06-07 | 17/05/2024: Olo order completed 26/04/2024:Abortive visit on 26/04/2024 - retailer was not aware of the visit - order was marked as completed by mistake, and marked as comissioning. 08/04/2024: Order completed 05/04/2024: No updates on CSL report on 05/04/2024. 19/03/24: New order added to report | 17/05/2024: Olo order completed 26/04/2024:Abortive visit on 26/04/2024 - retailer was not aware of the visit - order was marked as completed by mistake, and marked as comissioning. 08/04/2024: Order completed 05/04/2024: No updates on CSL report on 05/04/2024. 19/03/24: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301042 | 30013735 | 2.Commissioning |  |  | 2024-05-16 | 2024-05-16 | 2024-05-16 | TRUE |  |  |  | 2024-06-25 | [7 empty] | 0
178 | 645262 | 868 | Batch 3 May24 | Type 1 | SOGEA | Arden News | Sutton in Ashfield | NG17 1BN | 2024-06-07 | 17/05/2024: Olo order completed 26/04/2024:Abortive visit on 26/04/2024 - retailer was not aware of the visit - order was marked as completed by mistake, and marked as comissioning. 08/04/2024: Order completed 05/04/2024: No updates on CSL report on 05/04/2024. 19/03/24: New order added to report | 17/05/2024: Olo order completed 26/04/2024:Abortive visit on 26/04/2024 - retailer was not aware of the visit - order was marked as completed by mistake, and marked as comissioning. 08/04/2024: Order completed 05/04/2024: No updates on CSL report on 05/04/2024. 19/03/24: New order added to report | [6 empty] | 6.No action | VFP2301065 | 30013758 | 6.Failed router install |  |  | 2024-05-16 | 2024-05-16 | 2024-05-16 | TRUE |  |  |  | 2024-06-06 |  |  |  | 2024-08-13 | 242005008836 | 242005008836 | 2024-08-14 | 1
179 | 657905 | 870 | Batch 3 May24 | Type 1 | SOGEA | Belgrave General Stores | Leicester | LE4 5LG | 2024-06-07 | 17/05/2024: Olo order completed 26/04/2024:Abortive visit on 26/04/2024 - retailer was not aware of the visit - order was marked as completed by mistake, and marked as comissioning. 08/04/2024: Order completed 05/04/2024: No updates on CSL report on 05/04/2024. 19/03/24: New order added to report | 17/05/2024: Olo order completed 26/04/2024:Abortive visit on 26/04/2024 - retailer was not aware of the visit - order was marked as completed by mistake, and marked as comissioning. 08/04/2024: Order completed 05/04/2024: No updates on CSL report on 05/04/2024. 19/03/24: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301067 | 30013760 | 6.Failed router install |  |  | 2024-05-16 | 2024-05-16 | 2024-05-16 | TRUE | [7 empty] | 2024-06-19 | 23A004945967 |  | 2024-07-01 | 1
180 | 620268 | 871 | Batch 3 May24 | Type 1 | SOGEA | Late Shopper | Birmingham | B18 7QX | 2024-06-07 | 17/05/2024: Olo order completed 26/04/2024:Abortive visit on 26/04/2024 - retailer was not aware of the visit - order was marked as completed by mistake, and marked as comissioning. 08/04/2024: Order completed 05/04/2024: No updates on CSL report on 05/04/2024. 19/03/24: New order added to report | 17/05/2024: Olo order completed 26/04/2024:Abortive visit on 26/04/2024 - retailer was not aware of the visit - order was marked as completed by mistake, and marked as comissioning. 08/04/2024: Order completed 05/04/2024: No updates on CSL report on 05/04/2024. 19/03/24: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301068 | 30013761 | 6.Failed router install |  |  | 2024-05-16 | 2024-05-16 | 2024-05-16 | TRUE | [7 empty] | 2024-06-12 | 238004917328 |  | 2024-07-01 | 1
181 | 438276 | 1669 | Batch 4 Jun24 | Type 1 | FTTP | SPAR | ORMSKIRK | L40 5TN | 2024-06-07 | 2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_4/6/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_31/5/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_30/5/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_29/5/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_4/6/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_31/5/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_30/5/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_29/5/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2338583 | 30015571 | 2.Commissioning | AM |  | 2024-05-29 | 2024-05-16 | 2024-05-16 | TRUE |  |  |  | 2024-06-13 | [7 empty] | 0
182 | 653618 | 606 | Batch 3 May24 | Type 1 | SOGEA | LOCO | Clydebank | G81 4HD | 2024-06-07 | 20/05/2024: OLO order completed 10/5/2024:0 08/04/2024: New order added to report | 20/05/2024: OLO order completed 10/5/2024:0 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300803 | 30013496 | 2.Commissioning |  |  | 2024-05-07 | 2024-05-17 | 2024-05-17 | TRUE |  |  |  | 2024-06-11 | [7 empty] | 0
183 | 654096 | 876 | Batch 3 May24 | Type 1 | SOGEA | Arbourthorne Londis | Sheffield | S2 2EJ | 2024-06-07 | 20/05/2024: OLO order completed 10/5/2024:0 08/04/2024: New order added to report | 20/05/2024: OLO order completed 10/5/2024:0 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301073 | 30013766 | 6.Failed router install |  |  | 2024-05-17 | 2024-05-17 | 2024-05-17 | TRUE | [7 empty] | 2024-06-17 | 23A004948707 |  | 2024-07-01 | 1
184 | 621551 | 882 | Batch 3 May24 | Type 1 | SOGEA | Bus Stop Stores | Londonderry | BT48 6AL | 2024-06-07 | 20/05/2024: OLO order completed 10/5/2024:0 08/04/2024: New order added to report | 20/05/2024: OLO order completed 10/5/2024:0 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301079 | 30013772 | 6.Failed router install |  |  | 2024-05-17 | 2024-05-17 | 2024-05-17 | TRUE | [7 empty] | 2024-06-19 | 23A004952867 |  | 2024-07-01 | 1
185 | 619733 | 883 | Batch 3 May24 | Type 1 | SOGEA | Cally News | London | N7 9RP | 2024-06-07 | 20/05/2024: OLO order completed 10/5/2024:0 08/04/2024: New order added to report | 20/05/2024: OLO order completed 10/5/2024:0 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301080 | 30013773 | 2.Commissioning |  |  | 2024-05-17 | 2024-05-17 | 2024-05-17 | TRUE |  |  |  | 2024-06-19 | [7 empty] | 0
186 | 646653 | 890 | Batch 3 May24 | Type 1 | SOGEA | Ardgowan Convenience Store | London | SE6 1UU | 2024-06-07 | 20/05/2024: OLO order completed 10/5/2024:0 08/04/2024: New order added to report | 20/05/2024: OLO order completed 10/5/2024:0 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301087 | 30013780 | 6.Failed router install |  |  | 2024-05-17 | 2024-05-17 | 2024-05-17 | TRUE | [7 empty] | 2024-06-11 | 23A004948634 |  | 2024-07-01 | 1
187 | 625413 | 896 | Batch 3 May24 | Type 1 | SOGEA | Hadston Newsagency | Morpeth | NE65 9YF | 2024-06-07 | 20/05/2024: OLO order completed 10/5/2024:0 08/04/2024: New order added to report | 20/05/2024: OLO order completed 10/5/2024:0 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301093 | 30013786 | 6.Failed router install |  |  | 2024-05-17 | 2024-05-17 | 2024-05-17 | TRUE | [7 empty] | 2024-06-24 | 242005008781 |  | 2024-07-01 | 1
188 | 634760 | 898 | Batch 3 May24 | Type 1 | SOGEA | Finlays Newsagents | London | SW7 2NA | 2024-06-07 | 20/05/2024: OLO order completed 10/5/2024:0 08/04/2024: New order added to report | 20/05/2024: OLO order completed 10/5/2024:0 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301095 | 30013788 | 2.Commissioning |  |  | 2024-05-17 | 2024-05-17 | 2024-05-17 | TRUE |  |  |  | 2024-06-13 | [7 empty] | 0
189 | 450476 | 902 | Batch 3 May24 | Type 1 | SOGEA | NEWS 4 U | BRISTOL | BS35 2AZ | 2024-06-07 | 20/05/2024: OLO order completed 10/5/2024:0 08/04/2024: New order added to report | 20/05/2024: OLO order completed 10/5/2024:0 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301099 | 30013792 | 3.In life |  |  | 2024-05-17 | 2024-05-17 | 2024-05-17 | TRUE |  |  |  | 2024-06-20 |  |  |  | 2024-09-02 | 242005010457 | 242005010457 | 2024-09-03 | 1
190 | 671860 | 905 | Batch 3 May24 | Type 1 | SOGEA | Jackson Street Post Office | GATESHEAD | NE8 1EE | 2024-06-07 | 20/05/2024: OLO order completed 10/5/2024:0 08/04/2024: New order added to report | 20/05/2024: OLO order completed 10/5/2024:0 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301102 | 30013795 | 2.Commissioning |  |  | 2024-05-17 | 2024-05-17 | 2024-05-17 | TRUE |  |  |  | 2024-06-21 | [7 empty] | 0 | 671860
191 | 668693 | 906 | Batch 3 May24 | Type 1 | SOGEA | Budgens | BASILDON | SS15 6LF | 2024-06-07 | 20/05/2024: OLO order completed 10/5/2024:0 08/04/2024: New order added to report | 20/05/2024: OLO order completed 10/5/2024:0 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301103 | 30013796 | 2.Commissioning |  |  | 2024-05-17 | 2024-05-17 | 2024-05-17 | TRUE |  |  |  | 2024-06-20 | [7 empty] | 0 | 668693
192 | 615043 | 909 | Batch 3 May24 | Type 1 | SOGEA | Chintu News | Enfield | EN2 7HW | 2024-06-07 | 20/05/2024: OLO order completed 10/5/2024:0 08/04/2024: New order added to report | 20/05/2024: OLO order completed 10/5/2024:0 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301106 | 30013799 | 6.Failed router install |  |  | 2024-05-17 | 2024-05-17 | 2024-05-17 | TRUE | [7 empty] | 2024-06-14 | 23A004945738 |  | 2024-07-01 | 1
193 | 435424 | 915 | Batch 3 May24 | Type 1 | SOGEA | Gosals Supermarket | STOURPORT-ON-SEVERN | DY13 8XL | 2024-07-18 | 20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:#Update Retailer happy with new appointment - 17/07, AM. _x000D_20/05/2024: OLO order completed 10/5/2024:0 08/04/2024: New order added to report | 20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:#Update Retailer happy with new appointment - 17/07, AM. _x000D_20/05/2024: OLO order completed 10/5/2024:0 08/04/2024: New order added to report |  |  | 2024-05-20 | 20/05/24: CSL to provide update |  |  | 5.CSL | VFP2301112 | 30013805 | 6.Failed router install | AM | [8 empty] | 2024-08-16 |  |  |  | 2024-08-19 | 23A004945867 | 23A004945867 | 2024-08-20 | 1
194 | 629750 | 917 | Batch 3 May24 | Type 1 | SOGEA | Market News | Walthamstow | E17 7BH | 2024-06-07 | 20/05/2024: OLO order completed 10/5/2024:0 08/04/2024: New order added to report | 20/05/2024: OLO order completed 10/5/2024:0 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301114 | 30013807 | 6.Failed router install |  |  | 2024-05-17 | 2024-05-17 | 2024-05-17 | TRUE | [7 empty] | 2024-06-19 | 23A004945748 |  | 2024-07-01 | 1
195 | 461406 | 922 | Batch 3 May24 | Type 1 | SoGEA/Mobile | Sekar's Extra | MORDEN | SM4 5RT | 2024-06-07 | 6/9/2024:#Update Retailer confirmed 12/09,AM. _x000D_5/9/2024:#Update Retailer confirmed 12/09,AM. _x000D_4/9/2024:#Update Retailer confirmed 12/09,AM. _x000D_3/9/2024:#Update Retailer confirmed 12/09,AM. _x000D_2/9/2024:#Update Retailer confirmed 12/09,AM. _x000D_29/8/2024:#Update Retailer confirmed 12/09,AM. _x000D_28/8/2024:#Update Retailer confirmed 12/09,AM. _x000D_27/8/2024:#Update Retailer confirmed 12/09,AM. _x000D_22/8/2024:#Update Scaffolding around the DP. The retailer advised Allwyn to contact them at the end of July / beginning of Aug to reschedule when scaffolding is down. _x000D_21/8/2024:#Update Scaffolding around the DP. The retailer advised Allwyn to contact them at the end of July / beginning of Aug to reschedule when scaffolding is down. _x000D_20/8/2024:#Update Scaffolding around the DP. The retailer advised Allwyn to contact them at the end of July / beginning of Aug to reschedule when scaffolding is down. _x000D_19/8/2024:#Update Scaffolding around the DP. The retailer advised Allwyn to contact them at the end of July / beginning of Aug to reschedule when scaffolding is down. _x000D_19/8/2024:01403214 _x000D_16/8/2024:#Update Scaffolding around the DP. The retailer advised Allwyn to contact them at the end of July / beginning of Aug to reschedule when scaffolding is down. _x000D_15/8/2024:#Update Scaffolding around the DP. The retailer advised Allwyn to contact them at the end of July / beginning of Aug to reschedule when scaffolding is down. _x000D_14/8/2024:#Update Scaffolding around the DP. The retailer advised Allwyn to contact them at the end of July / beginning of Aug to reschedule when scaffolding is down. _x000D_13/8/2024:#Update Scaffolding around the DP. The retailer advised Allwyn to contact them at the end of July / beginning of Aug to reschedule when scaffolding is down. _x000D_12/8/2024:#Update Scaffolding around the DP. The retailer advised Allwyn to contact them at the end of July / beginning of Aug to reschedule when scaffolding is down. _x000D_9/8/2024:#Update Scaffolding around the DP. The retailer advised Allwyn to contact them at the end of July / beginning of Aug to reschedule when scaffolding is down. _x000D_8/8/2024:01/07/2024 _x000D_6/8/2024:01/07/2024 _x000D_5/8/2024:01/07/2024 _x000D_2/8/2024:01/07/2024 _x000D_1/8/2024:01/07/2024 _x000D_31/7/2024:01/07/2024 _x000D_31/7/2024:01/07/2024 _x000D_30/7/2024:#Update Scaffolding around the DP. The retailer advised Allwyn to contact them at the end of July / beginning of Aug to reschedule when scaffolding is down. _x000D_29/7/2024:#Update Scaffolding around the DP. The retailer advised Allwyn to contact them at the end of July / beginning of Aug to reschedule when scaffolding is down. _x000D_29/7/2024:01403214 _x000D_26/7/2024:01403214 _x000D_24/7/2024:#Update Scaffolding around the DP. The retailer advised Allwyn to contact them at the end of July / beginning of Aug to reschedule when scaffolding is down. _x000D_23/7/2024:#Update Scaffolding around the DP. The retailer advised Allwyn to contact them at the end of July / beginning of Aug to reschedule when scaffolding is down. _x000D_22/7/2024:#Update Scaffolding around the DP. The retailer advised Allwyn to contact them at the end of July / beginning of Aug to reschedule when scaffolding is down. _x000D_22/7/2024:#Update Scaffolding around the DP. The retailer advised Allwyn to contact them at the end of July / beginning of Aug to reschedule when scaffolding is down. _x000D_20/05/2024: OLO order completed 10/5/2024:0 08/04/2024: New order added to report | 9/9/2024:#Update Retailer confirmed 12/09,AM. _x000D_6/9/2024:#Update Retailer confirmed 12/09,AM. _x000D_5/9/2024:#Update Retailer confirmed 12/09,AM. _x000D_4/9/2024:#Update Retailer confirmed 12/09,AM. _x000D_3/9/2024:#Update Retailer confirmed 12/09,AM. _x000D_2/9/2024:#Update Retailer confirmed 12/09,AM. _x000D_29/8/2024:#Update Retailer confirmed 12/09,AM. _x000D_28/8/2024:#Update Retailer confirmed 12/09,AM. _x000D_27/8/2024:#Update Retailer confirmed 12/09,AM. _x000D_22/8/2024:#Update Scaffolding around the DP. The retailer advised Allwyn to contact them at the end of July / beginning of Aug to reschedule when scaffolding is down. _x000D_21/8/2024:#Update Scaffolding around the DP. The retailer advised Allwyn to contact them at the end of July / beginning of Aug to reschedule when scaffolding is down. _x000D_20/8/2024:#Update Scaffolding around the DP. The retailer advised Allwyn to contact them at the end of July / beginning of Aug to reschedule when scaffolding is down. _x000D_19/8/2024:#Update Scaffolding around the DP. The retailer advised Allwyn to contact them at the end of July / beginning of Aug to reschedule when scaffolding is down. _x000D_19/8/2024:01403214 _x000D_16/8/2024:#Update Scaffolding around the DP. The retailer advised Allwyn to contact them at the end of July / beginning of Aug to reschedule when scaffolding is down. _x000D_15/8/2024:#Update Scaffolding around the DP. The retailer advised Allwyn to contact them at the end of July / beginning of Aug to reschedule when scaffolding is down. _x000D_14/8/2024:#Update Scaffolding around the DP. The retailer advised Allwyn to contact them at the end of July / beginning of Aug to reschedule when scaffolding is down. _x000D_13/8/2024:#Update Scaffolding around the DP. The retailer advised Allwyn to contact them at the end of July / beginning of Aug to reschedule when scaffolding is down. _x000D_12/8/2024:#Update Scaffolding around the DP. The retailer advised Allwyn to contact them at the end of July / beginning of Aug to reschedule when scaffolding is down. _x000D_9/8/2024:#Update Scaffolding around the DP. The retailer advised Allwyn to contact them at the end of July / beginning of Aug to reschedule when scaffolding is down. _x000D_8/8/2024:01/07/2024 _x000D_6/8/2024:01/07/2024 _x000D_5/8/2024:01/07/2024 _x000D_2/8/2024:01/07/2024 _x000D_1/8/2024:01/07/2024 _x000D_31/7/2024:01/07/2024 _x000D_31/7/2024:01/07/2024 _x000D_30/7/2024:#Update Scaffolding around the DP. The retailer advised Allwyn to contact them at the end of July / beginning of Aug to reschedule when scaffolding is down. _x000D_29/7/2024:#Update Scaffolding around the DP. The retailer advised Allwyn to contact them at the end of July / beginning of Aug to reschedule when scaffolding is down. _x000D_29/7/2024:01403214 _x000D_26/7/2024:01403214 _x000D_24/7/2024:#Update Scaffolding around the DP. The retailer advised Allwyn to contact them at the end of July / beginning of Aug to reschedule when scaffolding is down. _x000D_23/7/2024:#Update Scaffolding around the DP. The retailer advised Allwyn to contact them at the end of July / beginning of Aug to reschedule when scaffolding is down. _x000D_22/7/2024:#Update Scaffolding around the DP. The retailer advised Allwyn to contact them at the end of July / beginning of Aug to reschedule when scaffolding is down. _x000D_22/7/2024:#Update Scaffolding around the DP. The retailer advised Allwyn to contact them at the end of July / beginning of Aug to reschedule when scaffolding is down. _x000D_20/05/2024: OLO order completed 10/5/2024:0 08/04/2024: New order added to report | 0 | #Update Retailer confirmed 12/09,AM. | 2024-05-20 | 20/05/2024: Allwyn to confirm the new date |  |  | 2.Allwyn to arrange access | VFP2461489 | 30013812 | 1.Provisioning | AM |  |  |  |  | 0 | [11 empty] | 0
196 | 647034 | 346 | Batch 3 May24 | Type 1 | FTTP | East Street News | Bristol | BS3 4EY | 2024-05-10 | 10/5/2024:0 _x000D_08/04/2024: New order added to report | 10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300543 | 30013236 | 3.In life |  |  | 2024-05-20 | 2024-05-20 | 2024-05-20 | TRUE |  |  |  | 2024-06-24 |  |  |  | 2024-09-02 | 242005010460 | 242005010460 | 2024-09-03 | 1
197 | 417825 | 433 | Batch 3 May24 | Type 1 | FTTP | G and R News | DEESIDE | CH5 4DP | 2024-05-10 | 21/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 21/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300630 | 30013323 | 6.Failed router install |  |  | 2024-05-03 | 2024-05-20 | 2024-05-20 | TRUE | [7 empty] | 2024-06-28 | 242005008903 |  | 2024-07-02 | 1
198 | 621021 | 480 | Batch 3 May24 | Type 1 | FTTP | Go Local Extra and Post Office | Tipton | DY4 0RL | 2024-05-21 | 10/5/2024:0 _x000D_08/04/2024: New order added to report | 10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300677 | 30013370 | 6.Failed router install |  |  | 2024-05-20 | 2024-05-20 | 2024-05-20 | TRUE | [7 empty] | 2024-06-11 | 238004917326 |  | 2024-07-01 | 1
199 | 486819 | 482 | Batch 3 May24 | Type 1 | FTTP | Savers News | Ashford | TN24 9DD | 2024-04-08 | 10/5/2024:0 _x000D_08/04/2024: New order added to report | 10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300679 | 30013372 | 6.Failed router install |  |  | 2024-05-20 | 2024-05-20 | 2024-05-20 | TRUE | [7 empty] | 2024-06-12 | 23A004945740 |  | 2024-07-01 | 1
200 | 468679 | 489 | Batch 3 May24 | Type 1 | SOGEA | News Rack | Ballymena | BT43 6AL | 2024-04-08 | 10/5/2024:0 _x000D_08/04/2024: New order added to report | 10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300686 | 30013379 | 6.Failed router install |  |  | 2024-05-20 | 2024-05-20 | 2024-05-20 | TRUE | [7 empty] | 2024-06-19 | 23A004952868 |  | 2024-07-01 | 1
201 | 486628 | 672 | Batch 3 May24 | Type 1 | SOGEA | Liquor World | Wiltshire | SN2 1TR | 2024-06-07 | 10/5/2024:0 _x000D_08/04/2024: New order added to report | 10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300869 | 30013562 | 2.Commissioning |  |  | 2024-05-20 | 2024-05-20 | 2024-05-20 | TRUE |  |  |  | 2024-06-26 | [7 empty] | 0
202 | 671811 | 686 | Batch 3 May24 | Type 1 | SOGEA | SPAR | St. Andrews | KY16 0HE | 2024-06-07 | 6/9/2024:#Update - Retailer would have authorised location of installation during handover. Socket relocation During socket relocation socket faceplate should be changed. _x000D_5/9/2024:#Update - Retailer would have authorised location of installation during handover. Socket relocation During socket relocation socket faceplate should be changed. _x000D_4/9/2024:#Update - Retailer would have authorised location of installation during handover. Socket relocation During socket relocation socket faceplate should be changed. _x000D_3/9/2024:#Update - Retailer would have authorised location of installation during handover. Socket relocation During socket relocation socket faceplate should be changed. _x000D_2/9/2024:#Update - Retailer would have authorised location of installation during handover. Socket relocation During socket relocation socket faceplate should be changed. _x000D_29/8/2024:#Update - Retailer would have authorised location of installation during handover. Socket relocation During socket relocation socket faceplate should be changed. _x000D_28/8/2024:#Update - Retailer would have authorised location of installation during handover. Socket relocation During socket relocation socket faceplate should be changed. _x000D_27/8/2024:#Update - Retailer would have authorised location of installation during handover. Socket relocation During socket relocation socket faceplate should be changed. _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 9/9/2024:#Update - Retailer would have authorised location of installation during handover. Socket relocation During socket relocation socket faceplate should be changed. _x000D_6/9/2024:#Update - Retailer would have authorised location of installation during handover. Socket relocation During socket relocation socket faceplate should be changed. _x000D_5/9/2024:#Update - Retailer would have authorised location of installation during handover. Socket relocation During socket relocation socket faceplate should be changed. _x000D_4/9/2024:#Update - Retailer would have authorised location of installation during handover. Socket relocation During socket relocation socket faceplate should be changed. _x000D_3/9/2024:#Update - Retailer would have authorised location of installation during handover. Socket relocation During socket relocation socket faceplate should be changed. _x000D_2/9/2024:#Update - Retailer would have authorised location of installation during handover. Socket relocation During socket relocation socket faceplate should be changed. _x000D_29/8/2024:#Update - Retailer would have authorised location of installation during handover. Socket relocation During socket relocation socket faceplate should be changed. _x000D_28/8/2024:#Update - Retailer would have authorised location of installation during handover. Socket relocation During socket relocation socket faceplate should be changed. _x000D_27/8/2024:#Update - Retailer would have authorised location of installation during handover. Socket relocation During socket relocation socket faceplate should be changed. _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 0 | #Update - Retailer would have authorised location of installation during handover. Socket relocation During socket relocation socket faceplate should be changed. |  |  |  |  | 3.Allwyn to arrange rtr install | VFP2300883 | 30013576 | 2.Commissioning |  |  | 2024-05-20 | 2024-05-20 | 2024-05-20 | TRUE |  |  |  | 2024-06-10 | [7 empty] | 0 | 671811
203 | 418594 | 842 | Batch 3 May24 | Type 1 | SoGEA/Mobile | Costcutter | BELFAST | BT15 3PW | 2024-06-07 | 6/9/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_5/9/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_4/9/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_3/9/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_2/9/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_29/8/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_28/8/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_27/8/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_22/8/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_21/8/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_20/8/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_19/8/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_19/8/2024:01403187 _x000D_16/8/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_15/8/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_14/8/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_13/8/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_12/8/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_9/8/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_8/8/2024:09/07/2024 _x000D_6/8/2024:09/07/2024 _x000D_5/8/2024:09/07/2024 _x000D_2/8/2024:09/07/2024 _x000D_1/8/2024:09/07/2024 _x000D_31/7/2024:09/07/2024 _x000D_31/7/2024:09/07/2024 _x000D_30/7/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_29/7/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_29/7/2024:01403187 _x000D_26/7/2024:01403187 _x000D_24/7/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_23/7/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_22/7/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_22/7/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 9/9/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_6/9/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_5/9/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_4/9/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_3/9/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_2/9/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_29/8/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_28/8/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_27/8/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_22/8/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_21/8/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_20/8/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_19/8/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_19/8/2024:01403187 _x000D_16/8/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_15/8/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_14/8/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_13/8/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_12/8/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_9/8/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_8/8/2024:09/07/2024 _x000D_6/8/2024:09/07/2024 _x000D_5/8/2024:09/07/2024 _x000D_2/8/2024:09/07/2024 _x000D_1/8/2024:09/07/2024 _x000D_31/7/2024:09/07/2024 _x000D_31/7/2024:09/07/2024 _x000D_30/7/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_29/7/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_29/7/2024:01403187 _x000D_26/7/2024:01403187 _x000D_24/7/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_23/7/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_22/7/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_22/7/2024:#Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 0 | #Update - order delayed - this has been sent to the survey engineers - further updates to follow accordingly | 2024-05-21 | 21/05/24: CSL to confirm the new date |  |  | 5.CSL | VFS1027746 | 30013732 | 1.Provisioning | AM |  | 2024-07-08 | 2024-07-18 |  | 0 | [11 empty] | 0
204 | 621024 | 855 | Batch 3 May24 | Type 1 | SOGEA | Centra | Antrim | BT41 4HR | 2024-06-07 | 10/5/2024:0 _x000D_08/04/2024: New order added to report | 10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301052 | 30013745 | 6.Failed router install |  |  | 2024-05-20 | 2024-05-20 | 2024-05-20 | TRUE | [7 empty] | 2024-06-19 | 23A004952864 |  | 2024-07-01 | 1
205 | 487638 | 928 | Batch 3 May24 | Type 1 | SOGEA | Savemore | Hillingdon | UB10 0NY | 2024-06-07 | 10/5/2024:0 _x000D_08/04/2024: New order added to report | 10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301125 | 30013818 | 2.Commissioning |  |  | 2024-05-20 | 2024-05-20 | 2024-05-20 | TRUE |  |  |  | 2024-07-30 | [7 empty] | 0
206 | 659679 | 936 | Batch 3 May24 | Type 1 | SOGEA | Old Mans Premier | Oxford | OX4 4JA | 2024-06-07 | 10/5/2024:0 _x000D_08/04/2024: New order added to report | 10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301133 | 30013826 | 6.Failed router install |  |  | 2024-05-20 | 2024-05-20 | 2024-05-20 | TRUE | [7 empty] | 2024-06-26 | 242005008631 |  | 2024-07-01 | 1
207 | 668539 | 938 | Batch 3 May24 | Type 1 | SOGEA | PARK ROAD NEWSAGENTS | LIVERPOOL | L8 6SH | 2024-06-07 | 10/5/2024:0 _x000D_08/04/2024: New order added to report | 10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301135 | 30013828 | 2.Commissioning |  |  | 2024-05-20 | 2024-05-20 | 2024-05-20 | TRUE |  |  |  | 2024-06-20 | [7 empty] | 0 | 668539
208 | 645339 | 951 | Batch 3 May24 | Type 1 | SOGEA | Thandis Premier | Mansfield | NG19 0JT | 2024-06-07 | 10/5/2024:0 _x000D_08/04/2024: New order added to report | 10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301148 | 30013841 | 6.Failed router install |  |  | 2024-05-20 | 2024-05-20 | 2024-05-20 | TRUE | [7 empty] | 2024-06-07 | 238004917360 |  | 2024-07-01 | 1
209 | 658982 | 966 | Batch 3 May24 | Type 1 | SOGEA | Londis | Fleet | GU52 0YE | 2024-06-07 | 10/5/2024:0 _x000D_08/04/2024: New order added to report | 10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301163 | 30013856 | 2.Commissioning |  |  | 2024-05-20 | 2024-05-20 | 2024-05-20 | TRUE |  |  |  | 2024-06-17 | [7 empty] | 0
210 | 657908 | 969 | Batch 3 May24 | Type 1 | SOGEA | Bedmond Store Premier | Abbots Langley | WD5 0QP | 2024-06-07 | 10/5/2024:0 _x000D_08/04/2024: New order added to report | 10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301166 | 30013859 | 6.Failed router install |  |  | 2024-05-20 | 2024-05-20 | 2024-05-20 | TRUE | [7 empty] | 2024-06-10 | 23A004948798 |  |  | 1
211 | 625265 | 970 | Batch 3 May24 | Type 1 | SOGEA | Arndale News | Luton | LU1 2TE | 2024-06-07 | 10/5/2024:0 _x000D_08/04/2024: New order added to report | 10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301167 | 30013860 | 2.Commissioning |  |  | 2024-05-20 | 2024-05-20 | 2024-05-20 | TRUE |  |  |  | 2024-06-10 | [7 empty] | 0
212 | 642051 | 975 | Batch 3 May24 | Type 1 | SOGEA | Spl70 News and Convenience Store | DAGENHAM | RM10 8DP | 2024-06-07 | 14/6/2024:#Update - Engineer could not access DP. Action for Allwyn: Contact retailer and ask them to arrange access for engineer to install at DP which is located in a flat. Re-appointed for 10/06 am, Allwyn to confirm with retailer that this date suits. _x000D_13/6/2024:#Update - Engineer could not access DP. Action for Allwyn: Contact retailer and ask them to arrange access for engineer to install at DP which is located in a flat. Re-appointed for 10/06 am, Allwyn to confirm with retailer that this date suits. _x000D_12/6/2024:#Update - Engineer could not access DP. Action for Allwyn: Contact retailer and ask them to arrange access for engineer to install at DP which is located in a flat. Re-appointed for 10/06 am, Allwyn to confirm with retailer that this date suits. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 14/6/2024:#Update - Engineer could not access DP. Action for Allwyn: Contact retailer and ask them to arrange access for engineer to install at DP which is located in a flat. Re-appointed for 10/06 am, Allwyn to confirm with retailer that this date suits. _x000D_13/6/2024:#Update - Engineer could not access DP. Action for Allwyn: Contact retailer and ask them to arrange access for engineer to install at DP which is located in a flat. Re-appointed for 10/06 am, Allwyn to confirm with retailer that this date suits. _x000D_12/6/2024:#Update - Engineer could not access DP. Action for Allwyn: Contact retailer and ask them to arrange access for engineer to install at DP which is located in a flat. Re-appointed for 10/06 am, Allwyn to confirm with retailer that this date suits. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301172 | 30013865 | 6.Failed router install |  |  | 2024-05-20 | 2024-05-20 | 2024-05-20 | TRUE | [7 empty] | 2024-06-21 | 23A004945630 |  | 2024-07-01 | 1
213 | 447967 | 1366 | Batch 4 Jun24 | Type 1 | SOGEA | CENTRA | LISBURN | BT28 2EU | 2024-06-07 | 26/7/2024:23/07/2024 14:38 _x000D_24/7/2024:Order Completed _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_22/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 26/7/2024:23/07/2024 14:38 _x000D_24/7/2024:Order Completed _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_22/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report |  |  | 2024-05-22 | 22/05/24: CSL to provide update |  |  | 3.Allwyn to arrange rtr install | VFS984916 | 30015499 | 6.Failed router install | AM |  | 2024-07-23 | 2024-07-23 | 2024-07-23 | TRUE |  |  |  | 2024-08-19 |  |  |  | 2024-08-19 | 23A004953012 | 23A004953012 | 2024-08-20 | 1
214 | 429193 | 506 | Batch 3 May24 | Type 1 | SOGEA | Walsh Newsagents | BANBRIDGE | BT32 3DA | 2024-05-22 | 22/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 22/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300703 | 30013396 | 6.Failed router install |  |  | 2024-05-21 | 2024-05-21 | 2024-05-21 | TRUE | [7 empty] | 2024-06-18 | 23A004952869 |  | 2024-07-01 | 1
215 | 668637 | 633 | Batch 3 May24 | Type 1 | SOGEA | PMK SUPERMARKET | Reading | RG2 8NY | 2024-06-07 | 22/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 22/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300830 | 30013523 | 6.Failed router install |  |  | 2024-05-21 | 2024-05-21 | 2024-05-21 | TRUE | [7 empty] | 2024-06-18 | 23A004948936 |  |  | 1 | 668637
216 | 424995 | 640 | Batch 3 May24 | Type 1 | FTTP | Clarence Convenience Store | LONDON | E5 8HB | 2024-06-07 | 22/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 22/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300837 | 30013530 | 6.Failed router install |  |  | 2024-05-21 | 2024-05-21 | 2024-05-21 | TRUE | [7 empty] | 2024-06-19 | 23A004949247 |  | 2024-07-01 | 1
217 | 603535 | 648 | Batch 3 May24 | Type 1 | SOGEA | Matthias Supermarket | London | N16 8NT | 2024-06-07 | 22/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 22/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300845 | 30013538 | 6.Failed router install |  |  | 2024-05-21 | 2024-05-21 | 2024-05-21 | TRUE | [7 empty] | 2024-06-19 | 23A004945326 |  | 2024-07-01 | 1
218 | 447851 | 650 | Batch 3 May24 | Type 1 | SOGEA | THE KIOSK | Magherafelt | BT45 6PR | 2024-06-07 | 22/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 22/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300847 | 30013540 | 6.Failed router install |  |  | 2024-05-21 | 2024-05-21 | 2024-05-21 | TRUE | [7 empty] | 2024-06-17 | 236004882493 |  | 2024-07-01 | 1
219 | 445479 | 651 | Batch 3 May24 | Type 1 | SOGEA | COSTCUTTER | LONDON | SW9 9AE | 2024-06-07 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_22/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_22/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 0 | 0 |  |  |  |  | 3.Allwyn to arrange rtr install | VFP2300848 | 30013541 | 2.Commissioning |  |  | 2024-05-21 | 2024-05-21 | 2024-05-21 | TRUE |  |  |  | 2024-06-13 | [7 empty] | 0
220 | 424434 | 653 | Batch 3 May24 | Type 1 | SOGEA | BP Londis Silverhill Service Stati | ST. LEONARDS-ON-SEA | TN37 7DA | 2024-06-07 | 22/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 22/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300850 | 30013543 | 6.Failed router install |  |  | 2024-05-21 | 2024-05-21 | 2024-05-21 | TRUE | [7 empty] | 2024-06-14 | 23A004948641 |  | 2024-07-01 | 1
221 | 240521 | 664 | Batch 3 May24 | Type 1 | SOGEA | Green Street Post Office | SOUTH SHIELDS | NE33 5DY | 2024-06-07 | 22/5/2024:#Update Third party supplier delay: Network Planning issues. Please await for further updates to follow. _x000D_10/5/2024:#Update Third party supplier delay: Network Planning issues. Please await for further updates to follow. _x000D_08/04/2024: New order added to report | 22/5/2024:#Update Third party supplier delay: Network Planning issues. Please await for further updates to follow. _x000D_10/5/2024:#Update Third party supplier delay: Network Planning issues. Please await for further updates to follow. _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300861 | 30013554 | 6.Failed router install |  |  | 2024-05-21 | 2024-05-21 | 2024-05-21 | TRUE | [7 empty] | 2024-06-21 | 23A004952678 |  | 2024-07-01 | 1
222 | 651863 | 984 | Batch 3 May24 | Type 1 | SOGEA | Londis | Welwyn Garden City | AL8 6AP | 2024-06-07 | 22/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 22/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301181 | 30013874 | 2.Commissioning |  |  | 2024-05-21 | 2024-05-21 | 2024-05-21 | TRUE |  |  |  | 2024-06-13 | [7 empty] | 0
223 | 659613 | 992 | Batch 3 May24 | Type 1 | SOGEA | Nisa Local | Ilkeston | DE7 4NU | 2024-06-07 | 22/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 22/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301189 | 30013882 | 2.Commissioning |  |  | 2024-05-21 | 2024-05-21 | 2024-05-21 | TRUE |  |  |  | 2024-06-20 | [7 empty] | 0
224 | 657650 | 996 | Batch 3 May24 | Type 1 | SOGEA | Greens of Shettleston | Glasgow | G32 7PQ | 2024-06-07 | 22/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 22/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301193 | 30013886 | 2.Commissioning |  |  | 2024-05-21 | 2024-05-21 | 2024-05-21 | TRUE |  |  |  | 2024-06-11 | [7 empty] | 0
225 | 667692 | 997 | Batch 3 May24 | Type 1 | SOGEA | Gills News | Rubery | B45 9JW | 2024-06-07 | 22/5/2024:#Update Third party supplier Networking issues. Further updates to follow. _x000D_10/5/2024:#Update Third party supplier Networking issues. Further updates to follow. _x000D_08/04/2024: New order added to report | 22/5/2024:#Update Third party supplier Networking issues. Further updates to follow. _x000D_10/5/2024:#Update Third party supplier Networking issues. Further updates to follow. _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301194 | 30013887 | 6.Failed router install |  |  | 2024-05-21 | 2024-05-21 | 2024-05-21 | TRUE | [7 empty] | 2024-06-12 | 23A004945979 |  |  | 1 | 667692
226 | 661240 | 998 | Batch 3 May24 | Type 1 | SOGEA | Morrisons Daily | Dorking | RH5 4HH | 2024-06-07 | 22/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 22/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301195 | 30013888 | 2.Commissioning |  |  | 2024-05-21 | 2024-05-21 | 2024-05-21 | TRUE |  |  |  | 2024-06-17 | [7 empty] | 0
227 | 484630 | 1000 | Batch 3 May24 | Type 1 | SOGEA | Londis | Chesham | HP5 2DA | 2024-06-07 | 22/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 22/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301197 | 30013890 | 6.Failed router install |  |  | 2024-05-21 | 2024-05-21 | 2024-05-21 | TRUE | [7 empty] | 2024-06-07 | 23A004948793 |  | 2024-07-01 | 1
228 | 670820 | 1002 | Batch 3 May24 | Type 1 | SOGEA | Ashs News & Off Licence | Harrow Weald | HA3 6LE | 2024-06-07 | 22/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 22/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301199 | 30013892 | 2.Commissioning |  |  | 2024-05-21 | 2024-05-21 | 2024-05-21 | TRUE |  |  |  | 2024-06-18 | [7 empty] | 0 | 670820
229 | 469565 | 1006 | Batch 3 May24 | Type 1 | SOGEA | Twins News | LEICESTER | LE8 4DJ | 2024-06-07 | 22/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 22/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301203 | 30013896 | 6.Failed router install |  |  | 2024-05-21 | 2024-05-21 | 2024-05-21 | TRUE | [7 empty] | 2024-06-18 | 23A004945856 |  | 2024-07-01 | 1
230 | 104900 | 1009 | Batch 3 May24 | Type 1 | SOGEA | GOSDENS | LONDON | N20 0BA | 2024-06-07 | 22/5/2024:Update: Order Completed by Supplier _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 22/5/2024:Update: Order Completed by Supplier _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301206 | 30013899 | 2.Commissioning |  |  | 2024-05-21 | 2024-05-21 | 2024-05-21 | TRUE |  |  |  | 2024-06-17 | [7 empty] | 0
231 | 662398 | 1021 | Batch 3 May24 | Type 1 | SOGEA | Anerley News Food & Wine | London | SE20 8AJ | 2024-06-07 | 22/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 22/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report |  |  | 2024-05-22 | 22/05/24: CSL to provide an update |  |  | 3.Allwyn to arrange rtr install | VFP2301218 | 30013911 | 6.Failed router install |  |  | 2024-05-21 | 2024-05-21 | 2024-05-22 | TRUE | [7 empty] | 2024-06-11 | 23A004949262 |  | 2024-07-01 | 1
232 | 664372 | 1084 | Batch 3 May24 | Type 1 | SOGEA | J N Charles Newsagents | BALLYNAHINCH | BT24 8DN | 2024-06-07 | 22/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 22/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301281 | 30013974 | 2.Commissioning |  |  | 2024-05-21 | 2024-05-21 | 2024-05-21 | TRUE |  |  |  | 2024-06-18 | [7 empty] | 0
233 | 665350 | 1090 | Batch 3 May24 | Type 1 | FTTP | The Newsagent | BANGOR | BT20 5NG | 2024-06-07 | 19/7/2024:#Update - Awaiting ECC's approval. _x000D_18/7/2024:#Update - Awaiting ECC's approval. _x000D_17/7/2024:#Update - Awaiting ECC's approval. _x000D_16/7/2024:#Update - Awaiting ECC's approval. _x000D_15/7/2024:#Update - Awaiting ECC's approval. _x000D_12/7/2024:#Update - Awaiting ECC's approval. _x000D_11/7/2024:#Update - Awaiting ECC's approval. _x000D_10/7/2024:#Update - Awaiting ECC's approval. _x000D_9/7/2024:#Update - Supplier delay - Duct work required. Our Suppliers have given us a review date of 12/07/2024. We will continue to provide update as they become available. _x000D_4/7/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_3/7/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_27/6/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_25/6/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_24/6/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_20/6/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_19/6/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_18/6/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_17/6/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_14/6/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_13/6/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_12/6/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:#Update - Awaiting ECC's approval. _x000D_18/7/2024:#Update - Awaiting ECC's approval. _x000D_17/7/2024:#Update - Awaiting ECC's approval. _x000D_16/7/2024:#Update - Awaiting ECC's approval. _x000D_15/7/2024:#Update - Awaiting ECC's approval. _x000D_12/7/2024:#Update - Awaiting ECC's approval. _x000D_11/7/2024:#Update - Awaiting ECC's approval. _x000D_10/7/2024:#Update - Awaiting ECC's approval. _x000D_9/7/2024:#Update - Supplier delay - Duct work required. Our Suppliers have given us a review date of 12/07/2024. We will continue to provide update as they become available. _x000D_4/7/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_3/7/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_27/6/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_25/6/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_24/6/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_20/6/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_19/6/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_18/6/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_17/6/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_14/6/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_13/6/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_12/6/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301287 | 30013980 | 6.Failed router install |  |  | 2024-05-21 | 2024-05-21 | 2024-05-21 | TRUE | [7 empty] | 2024-06-20 | 23A004952967 |  | 2024-07-01 | 1
234 | 664838 | 1092 | Batch 3 May24 | Type 1 | FTTP/Mobile | Moira Po & Store | Craigavon | BT67 0LE | 2024-06-07 | 6/9/2024:#Update - Awaiting ECC's approval. _x000D_5/9/2024:#Update - Awaiting ECC's approval. _x000D_4/9/2024:#Update - Awaiting ECC's approval. _x000D_3/9/2024:#Update - Awaiting ECC's approval. _x000D_2/9/2024:#Update - Awaiting ECC's approval. _x000D_29/8/2024:#Update - Awaiting ECC's approval. _x000D_28/8/2024:#Update - Awaiting ECC's approval. _x000D_27/8/2024:#Update - Awaiting ECC's approval. _x000D_22/8/2024:#Update - Awaiting ECC's approval. _x000D_21/8/2024:#Update - Awaiting ECC's approval. _x000D_20/8/2024:#Update - Awaiting ECC's approval. _x000D_19/8/2024:#Update - Awaiting ECC's approval. _x000D_19/8/2024:01466699 _x000D_16/8/2024:#Update - Awaiting ECC's approval. _x000D_15/8/2024:#Update - Awaiting ECC's approval. _x000D_14/8/2024:#Update - Awaiting ECC's approval. _x000D_13/8/2024:#Update - Awaiting ECC's approval. _x000D_12/8/2024:#Update - Awaiting ECC's approval. _x000D_9/8/2024:#Update - Awaiting ECC's approval. _x000D_8/8/2024:10/07/2024 _x000D_6/8/2024:10/07/2024 _x000D_5/8/2024:10/07/2024 _x000D_2/8/2024:10/07/2024 _x000D_1/8/2024:10/07/2024 _x000D_31/7/2024:10/07/2024 _x000D_31/7/2024:10/07/2024 _x000D_30/7/2024:#Update - Awaiting ECC's approval. _x000D_29/7/2024:#Update - Awaiting ECC's approval. _x000D_29/7/2024:01466699 _x000D_26/7/2024:01466699 _x000D_24/7/2024:#Update - Awaiting ECC's approval. _x000D_23/7/2024:#Update - Awaiting ECC's approval. _x000D_22/7/2024:#Update - Awaiting ECC's approval. _x000D_22/7/2024:#Update - Awaiting ECC's approval. _x000D_22/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 9/9/2024:#Update - Awaiting ECC's approval. _x000D_6/9/2024:#Update - Awaiting ECC's approval. _x000D_5/9/2024:#Update - Awaiting ECC's approval. _x000D_4/9/2024:#Update - Awaiting ECC's approval. _x000D_3/9/2024:#Update - Awaiting ECC's approval. _x000D_2/9/2024:#Update - Awaiting ECC's approval. _x000D_29/8/2024:#Update - Awaiting ECC's approval. _x000D_28/8/2024:#Update - Awaiting ECC's approval. _x000D_27/8/2024:#Update - Awaiting ECC's approval. _x000D_22/8/2024:#Update - Awaiting ECC's approval. _x000D_21/8/2024:#Update - Awaiting ECC's approval. _x000D_20/8/2024:#Update - Awaiting ECC's approval. _x000D_19/8/2024:#Update - Awaiting ECC's approval. _x000D_19/8/2024:01466699 _x000D_16/8/2024:#Update - Awaiting ECC's approval. _x000D_15/8/2024:#Update - Awaiting ECC's approval. _x000D_14/8/2024:#Update - Awaiting ECC's approval. _x000D_13/8/2024:#Update - Awaiting ECC's approval. _x000D_12/8/2024:#Update - Awaiting ECC's approval. _x000D_9/8/2024:#Update - Awaiting ECC's approval. _x000D_8/8/2024:10/07/2024 _x000D_6/8/2024:10/07/2024 _x000D_5/8/2024:10/07/2024 _x000D_2/8/2024:10/07/2024 _x000D_1/8/2024:10/07/2024 _x000D_31/7/2024:10/07/2024 _x000D_31/7/2024:10/07/2024 _x000D_30/7/2024:#Update - Awaiting ECC's approval. _x000D_29/7/2024:#Update - Awaiting ECC's approval. _x000D_29/7/2024:01466699 _x000D_26/7/2024:01466699 _x000D_24/7/2024:#Update - Awaiting ECC's approval. _x000D_23/7/2024:#Update - Awaiting ECC's approval. _x000D_22/7/2024:#Update - Awaiting ECC's approval. _x000D_22/7/2024:#Update - Awaiting ECC's approval. _x000D_22/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 0 | #Update - Awaiting ECC's approval. | 2024-05-22 | 22/05/24: CSL to provide an update |  |  | 5.CSL | VFP2332756 | 30013982 | 1.Provisioning | AM |  | 2024-05-21 | 2024-05-21 |  | 0 | [11 empty] | 0
235 | 666108 | 1141 | Batch 3 May24 | Type 1 | FTTP | Post Office | LIVERPOOL | L14 6TT | 2024-06-07 | 22/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 22/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301338 | 30014031 | 6.Failed router install |  |  | 2024-05-21 | 2024-05-21 | 2024-05-21 | TRUE | [7 empty] | 2024-06-21 | 242005013391 |  | 2024-07-01 | 1
236 | 405235 | 324 | Batch 2 Apr24 | Type 1 | SOGEA | Kitsons | BRIGHOUSE | HD6 1AF | 2024-05-23 | 10/5/2024:Your order has been delayed due to a customer missed appointment as the Customer is not ready. Now the order got re-appointed for 22/05/2024. _x000D_07/05/2024: rebooked 0n 22/05/2024- unsuccessful installation as the engineer requires additional time for the install & there was stock in the way. 08/04/2024: New order added to report | 10/5/2024:Your order has been delayed due to a customer missed appointment as the Customer is not ready. Now the order got re-appointed for 22/05/2024. _x000D_07/05/2024: rebooked 0n 22/05/2024- unsuccessful installation as the engineer requires additional time for the install & there was stock in the way. 08/04/2024: New order added to report |  |  | 2024-04-23 | 23/04/2023: CSL to provide Update 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS939526 | 30013210 | 2.Commissioning | AM |  | 2024-05-22 | 2024-05-22 | 2024-05-22 | TRUE |  |  |  | 2024-06-21 | [7 empty] | 0
237 | 424688 | 436 | Batch 3 May24 | Type 1 | SOGEA | Citrus News & Wine | HOUNSLOW | TW3 1RS | 2024-05-23 | 10/5/2024:0 _x000D_08/04/2024: New order added to report | 10/5/2024:0 _x000D_08/04/2024: New order added to report |  |  | 2024-05-07 | 07/05/2024:Allwyn to make the retailer aware |  |  | 3.Allwyn to arrange rtr install | VFP2300633 | 30013326 | 6.Failed router install |  |  | 2024-05-03 | 2024-05-22 | 2024-05-22 | TRUE | [7 empty] | 2024-06-21 | 23A004945281 |  | 2024-07-01 | 1
238 | 615549 | 593 | Batch 3 May24 | Type 1 | SOGEA | New Town Stores | Luton | LU1 3EB | 2024-06-07 | 10/5/2024:0 _x000D_08/04/2024: New order added to report | 10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 6.No action | VFP2300790 | 30013483 | 6.Failed router install |  |  | 2024-05-22 | 2024-05-22 | 2024-05-22 | TRUE | [7 empty] | 2024-06-10 | 23A004948789 |  |  | 1
239 | 656849 | 609 | Batch 3 May24 | Type 1 | SOGEA | Centra | Limavady | BT49 9EY | 2024-06-07 | 10/5/2024:0 _x000D_08/04/2024: New order added to report | 10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300806 | 30013499 | 6.Failed router install |  |  | 2024-05-22 | 2024-05-22 | 2024-05-22 | TRUE | [7 empty] | 2024-06-19 | 23A004952865 |  | 2024-07-01 | 1
240 | 646960 | 614 | Batch 3 May24 | Type 1 | SOGEA | Good News | Burton Upon Trent | DE14 1AN | 2024-06-07 | 10/5/2024:#Update - Third Party Supplier delay, Re-appointed to 22nd May AM. Action for Allwyn, Please confirm with the retailer for new appointment of 22nd May, AM. _x000D_08/05/2024: Third Party Supplier delay, Re-appointed to 22nd May AM. Action for Allwyn, Please confirm with the retailer for new appointment of 22nd May, AM. 08/04/2024: New order added to report | 10/5/2024:#Update - Third Party Supplier delay, Re-appointed to 22nd May AM. Action for Allwyn, Please confirm with the retailer for new appointment of 22nd May, AM. _x000D_08/05/2024: Third Party Supplier delay, Re-appointed to 22nd May AM. Action for Allwyn, Please confirm with the retailer for new appointment of 22nd May, AM. 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300811 | 30013504 | 6.Failed router install |  |  | 2024-05-22 | 2024-05-22 | 2024-05-22 | TRUE | [7 empty] | 2024-06-20 | 23A004945825 |  | 2024-07-01 | 1
241 | 109961 | 1030 | Batch 3 May24 | Type 1 | SOGEA | Proudfoot | SCARBOROUGH | YO11 3LJ | 2024-06-07 | 10/5/2024:0 _x000D_08/04/2024: New order added to report | 10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301227 | 30013920 | 2.Commissioning |  |  | 2024-05-22 | 2024-05-22 | 2024-05-22 | TRUE |  |  |  | 2024-06-21 | [7 empty] | 0
242 | 651675 | 1031 | Batch 3 May24 | Type 1 | SOGEA | Mourneview Service Station | Newry | BT34 4DT | 2024-06-07 | 10/5/2024:0 _x000D_08/04/2024: New order added to report | 10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301228 | 30013921 | 2.Commissioning |  |  | 2024-05-22 | 2024-05-22 | 2024-05-22 | TRUE |  |  |  | 2024-06-18 | [7 empty] | 0
243 | 650100 | 1039 | Batch 3 May24 | Type 1 | SOGEA | Londis | St Marys Bay ROMNEY MARSH | TN29 0SA | 2024-06-07 | 10/5/2024:0 _x000D_08/04/2024: New order added to report | 10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301236 | 30013929 | 6.Failed router install |  |  | 2024-05-22 | 2024-05-22 | 2024-05-22 | TRUE | [7 empty] | 2024-06-12 | 23A004945244 |  | 2024-07-01 | 1
244 | 664447 | 1045 | Batch 3 May24 | Type 1 | SOGEA | Premier Stores | WESTON-SUPER-MARE | BS23 3SS | 2024-06-07 | 10/5/2024:0 _x000D_08/04/2024: New order added to report | 10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301242 | 30013935 | 2.Commissioning |  |  | 2024-05-22 | 2024-05-22 | 2024-05-22 | TRUE |  |  |  | 2024-06-20 | [7 empty] | 0
245 | 666577 | 1056 | Batch 3 May24 | Type 1 | SOGEA | Bestone | Bristol | BS4 1LZ | 2024-06-07 | 10/5/2024:#Update - Supplier Delay: Network Planning issues. Please await for further updates _x000D_08/04/2024: New order added to report | 10/5/2024:#Update - Supplier Delay: Network Planning issues. Please await for further updates _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301253 | 30013946 | 2.Commissioning |  |  | 2024-05-22 | 2024-05-22 | 2024-05-22 | TRUE |  |  |  | 2024-06-26 | [7 empty] | 0
246 | 665559 | 1057 | Batch 3 May24 | Type 1 | FTTP | Premier Speke Town Convenience | Speke | L24 3TD | 2024-06-07 | 10/5/2024:0 _x000D_08/04/2024: New order added to report | 10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301254 | 30013947 | 2.Commissioning |  |  | 2024-05-22 | 2024-05-22 | 2024-05-22 | TRUE |  |  |  | 2024-06-21 | [7 empty] | 0
247 | 665277 | 1064 | Batch 3 May24 | Type 1 | SOGEA | Harzin News & Po | BIRMINGHAM | B7 5PY | 2024-06-07 | 10/5/2024:0 _x000D_08/04/2024: New order added to report | 10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301261 | 30013954 | 6.Failed router install |  |  | 2024-05-22 | 2024-05-22 | 2024-05-22 | TRUE | [7 empty] | 2024-06-13 | 23A004945857 |  | 2024-07-01 | 1
248 | 664785 | 1065 | Batch 3 May24 | Type 1 | FTTP | Moorside Stores | Huddersfield | HD5 0LU | 2024-06-07 | 10/5/2024:0 _x000D_08/04/2024: New order added to report | 10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301262 | 30013955 | 6.Failed router install |  |  | 2024-05-22 | 2024-05-22 | 2024-05-22 | TRUE | [7 empty] | 2024-06-21 | 23A004948340 |  | 2024-07-01 | 1
249 | 664803 | 1075 | Batch 3 May24 | Type 1 | FTTP | Post Office | CHISLEHURST | BR7 5NP | 2024-06-07 | 10/5/2024:0 _x000D_07/05/2024: Order rescheduled 08/04/2024: New order added to report | 10/5/2024:0 _x000D_07/05/2024: Order rescheduled 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301272 | 30013965 | 6.Failed router install |  |  | 2024-05-22 | 2024-05-22 | 2024-05-22 | TRUE | [7 empty] | 2024-06-20 | 23A004949272 |  | 2024-07-01 | 1
250 | 412257 | 1236 | Batch 3 May24 | Type 1 | SOGEA | Quality Foods | SOUTHALL | UB1 1SQ | 2024-06-07 | 10/5/2024:0 _x000D_08/04/2024: New order added to report | 10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301433 | 30014126 | 2.Commissioning |  |  | 2024-05-22 | 2024-05-22 | 2024-05-22 | TRUE |  |  |  | 2024-06-24 | [7 empty] | 0
251 | 641279 | 1267 | Batch 3 May24 | Type 1 | SOGEA | Nisa | Warwickshire | CV1 1JB | 2024-06-07 | 10/5/2024:0 _x000D_08/04/2024: New order added to report | 10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301464 | 30014157 | 2.Commissioning |  |  | 2024-05-22 | 2024-05-22 | 2024-05-22 | TRUE |  |  |  | 2024-06-14 | [7 empty] | 0
252 | 432580 | 552 | Batch 3 May24 | Type 1 | FTTP | Key Stores Newsagents | NOTTINGHAM | NG16 3AN | 2024-06-07 | 10/5/2024:0 _x000D_08/04/2024: New order added to report | 10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300749 | 30013442 | 6.Failed router install |  |  | 2024-05-23 | 2024-05-23 | 2024-05-23 | TRUE | [7 empty] | 2024-06-25 | 23A004945848 |  | 2024-07-04 | 1
253 | 625710 | 559 | Batch 3 May24 | Type 1 | SOGEA | Centra | Antrim | BT41 4LL | 2024-06-07 | 10/5/2024:0 _x000D_08/04/2024: New order added to report | 10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300756 | 30013449 | 6.Failed router install |  |  | 2024-05-23 | 2024-05-23 | 2024-05-23 | TRUE | [7 empty] | 2024-06-24 | 23A004952968 |  | 2024-07-01 | 1
254 | 661089 | 565 | Batch 3 May24 | Type 1 | SOGEA | Pavillion News | Crawley | RH10 1DE | 2024-06-07 | 2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_11/6/2024:#Update Retailer confirmed new appointment, 21/06, AM. _x000D_10/6/2024:Supplier Delay: New Appointment might be required _x000D_7/6/2024:Supplier Delay: New Appointment might be required _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_11/6/2024:#Update Retailer confirmed new appointment, 21/06, AM. _x000D_10/6/2024:Supplier Delay: New Appointment might be required _x000D_7/6/2024:Supplier Delay: New Appointment might be required _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300762 | 30013455 | 6.Failed router install |  |  | 2024-05-23 | 2024-05-23 | 2024-05-23 | TRUE | [7 empty] | 2024-06-27 | 242005011048 |  | 2024-07-02 | 1
255 | 230696 | 710 | Batch 3 May24 | Type 1 | SOGEA | NEWSMART | WEMBLEY | HA0 2DH | 2024-06-07 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_10/5/2024:#Update - Action for Allwyn- To confirm date with retailer when a quiet period in opening hours for engineer to remove ceiling panels for installation. Small shop and needs space to work when shop is not busy. _x000D_08/04/2024: New order added to report | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_10/5/2024:#Update - Action for Allwyn- To confirm date with retailer when a quiet period in opening hours for engineer to remove ceiling panels for installation. Small shop and needs space to work when shop is not busy. _x000D_08/04/2024: New order added to report | 0 | 0 | 2024-05-09 | 09/05/2024: Allwyn to make the retailer aware in the date in column U |  |  | 3.Allwyn to arrange rtr install | VFP2300907 | 30013600 | 2.Commissioning | [9 empty] | 2024-06-21 | [7 empty] | 0
256 | 665343 | 1087 | Batch 3 May24 | Type 1 | FTTP/Mobile | Reynolds News and | HARWICH | CO12 3AJ | 2024-06-07 | 6/9/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_5/9/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_4/9/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_3/9/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_2/9/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_29/8/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_28/8/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_27/8/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_22/8/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_21/8/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_20/8/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_19/8/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_19/8/2024:01407777 _x000D_16/8/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_15/8/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_14/8/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_13/8/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_12/8/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_9/8/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_8/8/2024:19/06/2024 _x000D_6/8/2024:19/06/2024 _x000D_5/8/2024:19/06/2024 _x000D_2/8/2024:19/06/2024 _x000D_1/8/2024:19/06/2024 _x000D_31/7/2024:19/06/2024 _x000D_31/7/2024:19/06/2024 _x000D_30/7/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_29/7/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_29/7/2024:01407777 _x000D_26/7/2024:01407777 _x000D_24/7/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_23/7/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_22/7/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_22/7/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 9/9/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_6/9/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_5/9/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_4/9/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_3/9/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_2/9/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_29/8/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_28/8/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_27/8/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_22/8/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_21/8/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_20/8/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_19/8/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_19/8/2024:01407777 _x000D_16/8/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_15/8/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_14/8/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_13/8/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_12/8/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_9/8/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_8/8/2024:19/06/2024 _x000D_6/8/2024:19/06/2024 _x000D_5/8/2024:19/06/2024 _x000D_2/8/2024:19/06/2024 _x000D_1/8/2024:19/06/2024 _x000D_31/7/2024:19/06/2024 _x000D_31/7/2024:19/06/2024 _x000D_30/7/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_29/7/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_29/7/2024:01407777 _x000D_26/7/2024:01407777 _x000D_24/7/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_23/7/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_22/7/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_22/7/2024:#Update - An OOH is required - Proposal sent to Vodafone on 07/06 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 0 | #Update - An OOH is required - Proposal sent to Vodafone on 07/06 |  |  |  |  | 2.Allwyn to arrange access | VFP2338334 | 30013977 | 1.Provisioning | AM |  | 2024-05-23 | 2024-05-23 |  | 0 | [11 empty] | 0
257 | 664834 | 1089 | Batch 3 May24 | Type 1 | SOGEA | Nisa Local | PETERBOROUGH | PE7 1HA | 2024-06-07 | 10/5/2024:0 _x000D_08/04/2024: New order added to report | 10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301286 | 30013979 | 2.Commissioning |  |  | 2024-05-23 | 2024-05-23 | 2024-05-23 | TRUE |  |  |  | 2024-06-17 | [7 empty] | 0
258 | 665351 | 1091 | Batch 3 May24 | Type 1 | SOGEA | The Book Nook | Larne | BT40 1RE | 2024-06-07 | 10/5/2024:0 _x000D_08/04/2024: New order added to report | 10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301288 | 30013981 | 6.Failed router install |  |  | 2024-05-23 | 2024-05-23 | 2024-05-23 | TRUE | [7 empty] | 2024-06-24 | 23A004952870 |  | 2024-07-01 | 1
259 | 665997 | 1101 | Batch 3 May24 | Type 1 | SOGEA | F P Mellish | RYDE | PO33 2RE | 2024-06-07 | 19/7/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_18/7/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_17/7/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_16/7/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_15/7/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_12/7/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_11/7/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_10/7/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 19/7/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_18/7/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_17/7/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_16/7/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_15/7/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_12/7/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_11/7/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_10/7/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301298 | 30013991 | 2.Commissioning |  |  | 2024-05-23 | 2024-05-23 | 2024-05-24 | TRUE |  |  |  | 2024-07-18 | [7 empty] | 0
260 | 664870 | 1102 | Batch 3 May24 | Type 1 | SoGEA/Mobile | Hertford Road Post Office | LONDON | N9 7ET | 2024-08-07 | 6/9/2024:#Update Following fault new order has been raised and committed for 2024-09-13. _x000D_5/9/2024:#Update Following fault new order has been raised and committed for 2024-09-13. _x000D_4/9/2024:#Update Following fault new order has been raised and committed for 2024-09-13. _x000D_3/9/2024:#Update Following fault new order has been raised and committed for 2024-09-13. _x000D_2/9/2024:#Update Following fault new order has been raised and committed for 2024-09-13. _x000D_29/8/2024:#Update Following fault new order has been raised and committed for 2024-09-13. _x000D_28/8/2024:#Update Following fault new order has been raised and committed for 2024-09-13. _x000D_27/8/2024:#Update Following fault new order has been raised and committed for 2024-09-13. _x000D_22/8/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_21/8/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_20/8/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_19/8/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_19/8/2024:01463472 _x000D_16/8/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_15/8/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_14/8/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_13/8/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_12/8/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_9/8/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_8/8/2024:02/07/2024 _x000D_6/8/2024:02/07/2024 _x000D_5/8/2024:02/07/2024 _x000D_2/8/2024:02/07/2024 _x000D_1/8/2024:02/07/2024 _x000D_31/7/2024:02/07/2024 _x000D_31/7/2024:02/07/2024 _x000D_30/7/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_29/7/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_29/7/2024:01463472 _x000D_26/7/2024:01463472 _x000D_24/7/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_23/7/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_22/7/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_22/7/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 9/9/2024:#Update Following fault new order has been raised and committed for 2024-09-13. _x000D_6/9/2024:#Update Following fault new order has been raised and committed for 2024-09-13. _x000D_5/9/2024:#Update Following fault new order has been raised and committed for 2024-09-13. _x000D_4/9/2024:#Update Following fault new order has been raised and committed for 2024-09-13. _x000D_3/9/2024:#Update Following fault new order has been raised and committed for 2024-09-13. _x000D_2/9/2024:#Update Following fault new order has been raised and committed for 2024-09-13. _x000D_29/8/2024:#Update Following fault new order has been raised and committed for 2024-09-13. _x000D_28/8/2024:#Update Following fault new order has been raised and committed for 2024-09-13. _x000D_27/8/2024:#Update Following fault new order has been raised and committed for 2024-09-13. _x000D_22/8/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_21/8/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_20/8/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_19/8/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_19/8/2024:01463472 _x000D_16/8/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_15/8/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_14/8/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_13/8/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_12/8/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_9/8/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_8/8/2024:02/07/2024 _x000D_6/8/2024:02/07/2024 _x000D_5/8/2024:02/07/2024 _x000D_2/8/2024:02/07/2024 _x000D_1/8/2024:02/07/2024 _x000D_31/7/2024:02/07/2024 _x000D_31/7/2024:02/07/2024 _x000D_30/7/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_29/7/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_29/7/2024:01463472 _x000D_26/7/2024:01463472 _x000D_24/7/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_23/7/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_22/7/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_22/7/2024:#Update - Proposal sent to Vodafone 02/07 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | Update: Order Amended | #Update Following fault new order has been raised and committed for 2024-09-13. |  |  |  |  | 3.Allwyn to arrange rtr install | VFS1050828 | 30013992 | 1.Provisioning | AM |  | 2024-05-23 | 2024-09-13 |  | 0 | [11 empty] | 0
261 | 666017 | 1104 | Batch 3 May24 | Type 1 | SOGEA | Post Office | PAISLEY | PA2 6LZ | 2024-06-07 | 10/5/2024:0 _x000D_08/04/2024: New order added to report | 10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301301 | 30013994 | 2.Commissioning |  |  | 2024-05-23 | 2024-05-23 | 2024-05-23 | TRUE |  |  |  | 2024-06-26 | [7 empty] | 0
262 | 666975 | 1114 | Batch 3 May24 | Type 1 | SOGEA | Trevelyan Drive PO | Newcastle Upon Tyne | NE5 4BR | 2024-06-07 | 10/5/2024:0 _x000D_08/04/2024: New order added to report | 10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301311 | 30014004 | 2.Commissioning |  |  | 2024-05-23 | 2024-05-23 | 2024-05-23 | TRUE |  |  |  | 2024-06-26 | [7 empty] | 0
263 | 666992 | 1119 | Batch 3 May24 | Type 1 | FTTP | Premier Dixon Lane Convenience Stor | LEEDS | LS12 4AD | 2024-06-07 | 28/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 28/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301316 | 30014009 | 2.Commissioning |  |  | 2024-05-23 | 2024-05-23 | 2024-05-23 | TRUE |  |  |  | 2024-07-02 | [7 empty] | 0
264 | 665326 | 1122 | Batch 3 May24 | Type 1 | SoGEA/Mobile | MALVERN GROVE SPSO | NORTHAMPTON | NN5 6AY | 2024-06-07 | 8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301319 | 30014012 | 2.Commissioning |  |  | 2024-05-23 | 2024-05-23 | 2024-05-23 | TRUE |  |  |  | 2024-06-18 | [7 empty] | 0
265 | 665352 | 1123 | Batch 3 May24 | Type 1 | SOGEA | SUPERVALU | Londonderry | BT48 8NN | 2024-06-07 | 10/5/2024:0 _x000D_08/04/2024: New order added to report | 10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301320 | 30014013 | 6.Failed router install |  |  | 2024-05-23 | 2024-05-23 | 2024-05-23 | TRUE | [7 empty] | 2024-06-26 | 242005010324 |  | 2024-07-01 | 1
266 | 666002 | 1124 | Batch 3 May24 | Type 1 | FTTP | Amen Corner News | LONDON | SW17 9JE | 2024-06-07 | 31/5/2024:Update: Order Completed by Supplier _x000D_30/5/2024:Update: Order Completed by Supplier _x000D_29/5/2024:Update: Order Completed by Supplier _x000D_28/5/2024:Update: Order Completed by Supplier _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 31/5/2024:Update: Order Completed by Supplier _x000D_30/5/2024:Update: Order Completed by Supplier _x000D_29/5/2024:Update: Order Completed by Supplier _x000D_28/5/2024:Update: Order Completed by Supplier _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301321 | 30014014 | 3.In life |  |  | 2024-05-23 | 2024-05-23 | 2024-05-23 | TRUE | [7 empty] | 2024-07-01 | 242005011021 |  | 2024-07-04 | 1
267 | 661291 | 495 | Batch 3 May24 | Type 1 | SOGEA | C J & R News | London | E12 6TJ | 2024-05-28 | 28/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 28/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300692 | 30013385 | 6.Failed router install |  |  | 2024-05-24 | 2024-05-24 | 2024-05-24 | TRUE | [7 empty] | 2024-06-27 | 242005011126 |  | 2024-07-02 | 1
268 | 659379 | 497 | Batch 3 May24 | Type 1 | SOGEA | Select & Save News | Derby | DE24 9BQ | 2024-05-28 | 28/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 28/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300694 | 30013387 | 6.Failed router install |  |  | 2024-05-24 | 2024-05-24 | 2024-05-24 | TRUE | [7 empty] | 2024-06-25 | 23A004945871 |  | 2024-07-01 | 1
269 | 607391 | 502 | Batch 3 May24 | Type 1 | SOGEA | Brooks | Pudsey | LS28 7LD | 2024-05-30 | 28/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 28/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300699 | 30013392 | 2.Commissioning |  |  | 2024-05-24 | 2024-05-24 | 2024-05-28 | TRUE |  |  |  | 2024-07-01 | [7 empty] | 0
270 | 483611 | 520 | Batch 3 May24 | Type 1 | SOGEA | Costcutter | Blyth | NE24 5RF | 2024-05-28 | 28/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 28/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300717 | 30013410 | 2.Commissioning |  |  | 2024-05-24 | 2024-05-24 | 2024-05-24 | TRUE |  |  |  | 2024-06-24 | [7 empty] | 0
271 | 265255 | 541 | Batch 3 May24 | Type 1 | SOGEA | Gwens Newsagents | LISBURN | BT28 3TP | 2024-05-30 | 28/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/05 at 8 AM - Parking restrictions are between 10-6. _x000D_10/5/2024:#Update – Missed Appointment – Openreach were unable to complete the job as a permit is required to access Trinity Street. A permit request needs to be raised by the retailer for a visitor. This needs to be done prior to the visit as the engineer was made aware by Coventry city council and not on the day. Action for Allwyn: Please speak with the retailer regarding obtaining a permit for the engineer and dates which would be suitable. _x000D_08/05/2024: Abortive visit - Openreach were unable to complete the job as a permit is required to access Trinity Street. A permit request needs to be raised by the retailer for a visitor. This needs to be done prior to the visit as the engineer was made aware by Coventry city council and not on the day. Action for Allwyn: Please speak with the retailer regarding obtaining a permit for the engineer and dates which would be suitable. 08/04/2024: New order added to report | 28/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/05 at 8 AM - Parking restrictions are between 10-6. _x000D_10/5/2024:#Update – Missed Appointment – Openreach were unable to complete the job as a permit is required to access Trinity Street. A permit request needs to be raised by the retailer for a visitor. This needs to be done prior to the visit as the engineer was made aware by Coventry city council and not on the day. Action for Allwyn: Please speak with the retailer regarding obtaining a permit for the engineer and dates which would be suitable. _x000D_08/05/2024: Abortive visit - Openreach were unable to complete the job as a permit is required to access Trinity Street. A permit request needs to be raised by the retailer for a visitor. This needs to be done prior to the visit as the engineer was made aware by Coventry city council and not on the day. Action for Allwyn: Please speak with the retailer regarding obtaining a permit for the engineer and dates which would be suitable. 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300738 | 30013431 | 6.Failed router install |  |  | 2024-05-24 | 2024-05-24 | 2024-05-28 | TRUE | [7 empty] | 2024-06-25 | 242005010322 |  | 2024-07-01 | 1
272 | 666056 | 1126 | Batch 3 May24 | Type 1 | SOGEA | Costless Express | EDINBURGH | EH4 4TD | 2024-06-07 | 31/5/2024:Update: Order Completed by Supplier _x000D_30/5/2024:Update: Order Completed by Supplier _x000D_29/5/2024:Update: Order Completed by Supplier _x000D_28/5/2024:Update: Order Completed by Supplier _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 31/5/2024:Update: Order Completed by Supplier _x000D_30/5/2024:Update: Order Completed by Supplier _x000D_29/5/2024:Update: Order Completed by Supplier _x000D_28/5/2024:Update: Order Completed by Supplier _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301323 | 30014016 | 6.Failed router install |  |  | 2024-05-24 | 2024-05-24 | 2024-05-24 | TRUE |  |  |  | 2024-06-27 |  |  |  | 2024-08-20 | 239004929651 | 239004929651 | 2024-08-21 | 1
273 | 666079 | 1134 | Batch 3 May24 | Type 1 | SOGEA | Londis Regents Park Post Office | SOUTHAMPTON | SO15 8PE | 2024-06-07 | 28/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 28/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301331 | 30014024 | 6.Failed router install |  |  | 2024-05-24 | 2024-05-24 | 2024-05-24 | TRUE | [7 empty] | 2024-06-18 | 23A004948803 |  | 2024-07-01 | 1
274 | 666097 | 1138 | Batch 3 May24 | Type 1 | SOGEA | Post Office | STOCKTON-ON-TEES | TS19 7LB | 2024-06-07 | 31/5/2024:Order Completed _x000D_30/5/2024:Order Completed _x000D_29/5/2024:Order Completed _x000D_28/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 31/5/2024:Order Completed _x000D_30/5/2024:Order Completed _x000D_29/5/2024:Order Completed _x000D_28/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301335 | 30014028 | 6.Failed router install |  |  | 2024-05-24 | 2024-05-24 | 2024-05-24 | TRUE | [7 empty] | 2024-06-27 | 23A004952675 |  | 2024-07-02 | 1
275 | 666748 | 1144 | Batch 3 May24 | Type 1 | FTTP | Thornbridge Avenue Post Office | BIRMINGHAM | B42 2AB | 2024-06-07 | 31/5/2024:Update: Order Completed by Supplier _x000D_30/5/2024:Update: Order Completed by Supplier _x000D_29/5/2024:Update: Order Completed by Supplier _x000D_28/5/2024:Update: Order Completed by Supplier _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 31/5/2024:Update: Order Completed by Supplier _x000D_30/5/2024:Update: Order Completed by Supplier _x000D_29/5/2024:Update: Order Completed by Supplier _x000D_28/5/2024:Update: Order Completed by Supplier _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301341 | 30014034 | 6.Failed router install |  |  | 2024-05-24 | 2024-05-24 | 2024-05-24 | TRUE | [7 empty] | 2024-06-24 | 238004917293 |  | 2024-07-01 | 1
276 | 665367 | 1145 | Batch 3 May24 | Type 1 | FTTP | Post Office | BOOTLE | L30 1QG | 2024-06-07 | 28/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 28/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301342 | 30014035 | 6.Failed router install |  |  | 2024-05-24 | 2024-05-24 | 2024-05-28 | TRUE | [7 empty] | 2024-06-20 | 242005008888 |  | 2024-07-01 | 1
277 | 663449 | 1147 | Batch 3 May24 | Type 1 | SOGEA | CAULFIELDS | BISHOP'S STORTFORD | CM23 5EP | 2024-06-07 | 28/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 28/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301344 | 30014037 | 2.Commissioning |  |  | 2024-05-24 | 2024-05-24 | 2024-05-24 | TRUE |  |  |  | 2024-06-18 | [7 empty] | 0
278 | 672623 | 1149 | Batch 3 May24 | Type 1 | SOGEA | SPAR | ST. AUSTELL | PL25 3DW | 2024-06-07 | 28/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 28/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301346 | 30014039 | 2.Commissioning |  |  | 2024-05-24 | 2024-05-24 | 2024-05-24 | TRUE |  |  |  | 2024-06-20 | [7 empty] | 0
279 | 666391 | 1156 | Batch 3 May24 | Type 1 | SOGEA | Londis | Mitcham | CR4 3BF | 2024-06-07 | 28/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 28/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301353 | 30014046 | 2.Commissioning |  |  | 2024-05-24 | 2024-05-24 | 2024-05-24 | TRUE |  |  |  | 2024-06-19 | [7 empty] | 0
280 | 665504 | 1161 | Batch 3 May24 | Type 1 | SOGEA | Best One Post Office | BLACKPOOL | FY1 6PU | 2024-06-07 | 28/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 28/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301358 | 30014051 | 6.Failed router install |  |  | 2024-05-24 | 2024-05-24 | 2024-05-24 | TRUE |  |  |  | 2024-07-29 |  |  |  | 2024-07-29 | 23A004948492 |  | 2024-07-30 | 1
281 | 665069 | 1166 | Batch 3 May24 | Type 1 | SOGEA | Londis Eastholme Drive | YORK | YO30 5SW | 2024-06-07 | 31/5/2024:Order Completed _x000D_30/5/2024:Order Completed _x000D_29/5/2024:Order Completed _x000D_28/5/2024:Supplier Delay: KCI-3 (Order Completed) Delayed in Processing. _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 31/5/2024:Order Completed _x000D_30/5/2024:Order Completed _x000D_29/5/2024:Order Completed _x000D_28/5/2024:Supplier Delay: KCI-3 (Order Completed) Delayed in Processing. _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301363 | 30014056 | 6.Failed router install |  |  | 2024-05-24 | 2024-05-24 | 2024-05-24 | TRUE | [7 empty] | 2024-06-27 | 242005008864 |  | 2024-07-01 | 1
282 | 665103 | 1171 | Batch 3 May24 | Type 1 | SOGEA | Kent Mart | SITTINGBOURNE | ME10 2AR | 2024-06-07 | 28/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 28/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301368 | 30014061 | 6.Failed router install |  |  | 2024-05-24 | 2024-05-24 | 2024-05-24 | TRUE |  |  |  | 2024-06-25 |  |  |  | 2024-08-22 | 242005011112 | 242005011112 | 2024-08-23 | 1
283 | 666404 | 1173 | Batch 3 May24 | Type 1 | SOGEA | WOODVALE PO | BELFAST | BT13 3BT | 2024-06-07 | 28/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 28/5/2024:Order Completed _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301370 | 30014063 | 6.Failed router install |  |  | 2024-05-24 | 2024-05-24 | 2024-05-24 | TRUE | [7 empty] | 2024-06-24 | 23A004952966 |  | 2024-07-01 | 1
284 | 665117 | 1175 | Batch 3 May24 | Type 1 | SOGEA | Hornsey Road Post Office | LONDON | N19 3QL | 2024-06-07 | 28/5/2024:#Update Network planning, we will provide further updates when they become available. _x000D_10/5/2024:#Update Network planning, we will provide further updates when they become available. _x000D_02/05/2024: New order added to report | 28/5/2024:#Update Network planning, we will provide further updates when they become available. _x000D_10/5/2024:#Update Network planning, we will provide further updates when they become available. _x000D_02/05/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301372 | 30014065 | 6.Failed router install |  |  | 2024-05-24 | 2024-05-24 | 2024-05-24 | TRUE |  |  |  | 2024-06-28 |  |  |  | 2024-08-23 | 242005011160 | 242005011160 | 2024-08-27 | 1
285 | 482187 | 1571 | Batch 4 Jun24 | Type 1 | FTTP | Spar | Portestewart | BT55 7HP | 2024-06-07 | 31/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/05 AM _x000D_30/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/05 AM _x000D_29/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/05 AM _x000D_28/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/05 AM _x000D_10/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/05 AM _x000D_26/04/2024: Upgrade has been approved rebooked on 28/05/2024 23/04/2024: proposal gone to Vodafone on 17/04 - awaiting update on next actions based on charges that are required. 11/04/2024: Allwyn to speak to the customer and get access advise access to the flat above so we can access the DP. Due to the shutters blocking the access to run a new into the property. Additionally as the DP in located in the flat upstairs. CSL checking with Openreach to see what is required in order to complete the installation due to shutter issue. 08/04/2024:: Awaiting further information from Openreach 19/03/24: New order added to report | 31/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/05 AM _x000D_30/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/05 AM _x000D_29/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/05 AM _x000D_28/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/05 AM _x000D_10/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/05 AM _x000D_26/04/2024: Upgrade has been approved rebooked on 28/05/2024 23/04/2024: proposal gone to Vodafone on 17/04 - awaiting update on next actions based on charges that are required. 11/04/2024: Allwyn to speak to the customer and get access advise access to the flat above so we can access the DP. Due to the shutters blocking the access to run a new into the property. Additionally as the DP in located in the flat upstairs. CSL checking with Openreach to see what is required in order to complete the installation due to shutter issue. 08/04/2024:: Awaiting further information from Openreach 19/03/24: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2338546 | 30015462 | 6.Failed router install | AM |  | 2024-05-24 | 2024-05-24 | 2024-05-24 | TRUE |  |  |  | 2024-06-26 |  |  |  | 2024-08-27 | 23A004952963 | 23A004952963 | 2024-08-28 | 1
286 | 437729 | 791 | Batch 3 May24 | Type 1 | SOGEA | EUROS | LONDON | W5 4QJ | 2024-06-07 | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_0 | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_0 | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300988 | 30013681 | 6.Failed router install |  |  | 2024-05-09 | 2024-05-28 | 2024-05-28 | TRUE | [7 empty] | 2024-06-20 | 23A004948651 |  | 2024-07-01 | 1
287 | 665161 | 1186 | Batch 3 May24 | Type 1 | SOGEA | Bains Post Office | BIRMINGHAM | B33 0ND | 2024-06-07 | 22/8/2024:#Update - Notes on order detail 'Service provided to nte5 under counter and labelled up for lottery machine. No router onsite yet'. Chasing with Openreach to see if we have any photos for NTE. _x000D_21/8/2024:#Update - Notes on order detail 'Service provided to nte5 under counter and labelled up for lottery machine. No router onsite yet'. Chasing with Openreach to see if we have any photos for NTE. _x000D_31/5/2024:Order Completed _x000D_30/5/2024:Order Completed _x000D_29/5/2024:Order Completed _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 22/8/2024:#Update - Notes on order detail 'Service provided to nte5 under counter and labelled up for lottery machine. No router onsite yet'. Chasing with Openreach to see if we have any photos for NTE. _x000D_21/8/2024:#Update - Notes on order detail 'Service provided to nte5 under counter and labelled up for lottery machine. No router onsite yet'. Chasing with Openreach to see if we have any photos for NTE. _x000D_31/5/2024:Order Completed _x000D_30/5/2024:Order Completed _x000D_29/5/2024:Order Completed _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report |  |  | 2024-05-29 | 29/05/24: CSL to provide an update |  |  | 3.Allwyn to arrange rtr install | VFP2301383 | 30014076 | 2.Commissioning |  |  | 2024-05-28 | 2024-05-28 | 2024-05-29 | TRUE |  |  |  | 2024-06-24 | [7 empty] | 0
288 | 665909 | 1187 | Batch 3 May24 | Type 1 | SOGEA | Londis | WEYMOUTH | DT4 0LX | 2024-06-07 | 31/5/2024:Order Completed _x000D_30/5/2024:Order Completed _x000D_29/5/2024:Order Completed _x000D_28/5/2024:Update: Order Completed by Supplier _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 31/5/2024:Order Completed _x000D_30/5/2024:Order Completed _x000D_29/5/2024:Order Completed _x000D_28/5/2024:Update: Order Completed by Supplier _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301384 | 30014077 | 3.In life |  |  | 2024-05-28 | 2024-05-28 | 2024-05-28 | TRUE |  |  |  | 2024-06-20 |  |  |  | 2024-09-03 | 239004929403 | 239004929403 | 2024-09-04 | 1
289 | 665200 | 1195 | Batch 3 May24 | Type 1 | SOGEA | Central | HOLYWOOD | BT18 9SA | 2024-06-07 | 31/5/2024:Order Completed _x000D_30/5/2024:Order Completed _x000D_29/5/2024:Order Completed _x000D_28/5/2024:Update: Order Completed by Supplier _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 31/5/2024:Order Completed _x000D_30/5/2024:Order Completed _x000D_29/5/2024:Order Completed _x000D_28/5/2024:Update: Order Completed by Supplier _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301392 | 30014085 | 6.Failed router install |  |  | 2024-05-28 | 2024-05-28 | 2024-05-28 | TRUE | [7 empty] | 2024-06-24 | 242005010321 |  | 2024-07-01 | 1
290 | 481697 | 1200 | Batch 3 May24 | Type 1 | FTTP | Londis Supermarket | Grays | RM17 6BU | 2024-06-07 | 31/5/2024:Order Completed _x000D_30/5/2024:Order Completed _x000D_29/5/2024:Order Completed _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 31/5/2024:Order Completed _x000D_30/5/2024:Order Completed _x000D_29/5/2024:Order Completed _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301397 | 30014090 | 6.Failed router install |  |  | 2024-05-28 | 2024-05-28 | 2024-05-28 | TRUE | [7 empty] | 2024-06-24 | 23A004948643 |  | 2024-07-01 | 1
291 | 485440 | 1204 | Batch 3 May24 | Type 1 | SOGEA | Co Op | Bedford | MK42 6AE | 2024-06-07 | 31/5/2024:#Update Order has been delayed due to multiskilled engineer work is required, updates to follow. _x000D_30/5/2024:#Update Order has been delayed due to multiskilled engineer work is required, updates to follow. _x000D_29/5/2024:Your order has been delayed due to multiskilled engineer work is required, order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 04/06/2024. _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 31/5/2024:#Update Order has been delayed due to multiskilled engineer work is required, updates to follow. _x000D_30/5/2024:#Update Order has been delayed due to multiskilled engineer work is required, updates to follow. _x000D_29/5/2024:Your order has been delayed due to multiskilled engineer work is required, order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 04/06/2024. _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301401 | 30014094 | 6.Failed router install |  |  | 2024-05-28 | 2024-05-28 | 2024-05-28 | TRUE | [7 empty] | 2024-06-26 | 23A004948813 |  | 2024-07-01 | 1
292 | 108581 | 1208 | Batch 3 May24 | Type 1 | SOGEA | Londis Supermarket | LONDON | SW3 5EJ | 2024-06-07 | 31/5/2024:Order Completed _x000D_30/5/2024:Order Completed _x000D_29/5/2024:Order Completed _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 31/5/2024:Order Completed _x000D_30/5/2024:Order Completed _x000D_29/5/2024:Order Completed _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301405 | 30014098 | 6.Failed router install |  |  | 2024-05-28 | 2024-05-28 | 2024-05-28 | TRUE | [7 empty] | 2024-07-01 | 242005008651 |  | 2024-07-04 | 1
293 | 603968 | 1218 | Batch 3 May24 | Type 1 | SOGEA | Budgens | Elmstead Market | CO7 7AA | 2024-06-07 | 6/9/2024:#Update - Order raised - committed for 12/09 - AM, Allwyn & VF aware. _x000D_5/9/2024:#Update - Order raised - committed for 12/09 - AM, Allwyn & VF aware. _x000D_4/9/2024:#Update - Order raised - committed for 12/09 - AM, Allwyn & VF aware. _x000D_3/9/2024:#Update - Order raised - committed for 12/09 - AM, Allwyn & VF aware. _x000D_2/9/2024:#Update - Order raised - committed for 12/09 - AM, Allwyn & VF aware. _x000D_29/8/2024:#Update - Order raised - committed for 12/09 - AM, Allwyn & VF aware. _x000D_31/5/2024:Order Completed _x000D_30/5/2024:Order Completed _x000D_29/5/2024:Order Completed _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 9/9/2024:#Update - Order raised - committed for 12/09 - AM, Allwyn & VF aware. _x000D_6/9/2024:#Update - Order raised - committed for 12/09 - AM, Allwyn & VF aware. _x000D_5/9/2024:#Update - Order raised - committed for 12/09 - AM, Allwyn & VF aware. _x000D_4/9/2024:#Update - Order raised - committed for 12/09 - AM, Allwyn & VF aware. _x000D_3/9/2024:#Update - Order raised - committed for 12/09 - AM, Allwyn & VF aware. _x000D_2/9/2024:#Update - Order raised - committed for 12/09 - AM, Allwyn & VF aware. _x000D_29/8/2024:#Update - Order raised - committed for 12/09 - AM, Allwyn & VF aware. _x000D_31/5/2024:Order Completed _x000D_30/5/2024:Order Completed _x000D_29/5/2024:Order Completed _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 0 | #Update - Order raised - committed for 12/09 - AM, Allwyn & VF aware. |  |  |  |  | 3.Allwyn to arrange rtr install | VFP2301415 | 30014108 | 2.Commissioning |  |  | 2024-05-28 | 2024-05-28 | 2024-05-28 | TRUE |  |  |  | 2024-06-19 | [7 empty] | 0
294 | 665292 | 1220 | Batch 3 May24 | Type 1 | SOGEA | LONDIS | FARNBOROUGH | GU14 8PX | 2024-06-07 | 31/5/2024:#Update Order delayed due as engineer unable to access DP. order is now with controls team to get the engineer reassigned. Further updates to follow _x000D_30/5/2024:#Update Order delayed due as engineer unable to access DP. order is now with controls team to get the engineer reassigned. Further updates to follow _x000D_29/5/2024:Your order has been delayed due as engineer unable to access DP. order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 04/06/2024 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 31/5/2024:#Update Order delayed due as engineer unable to access DP. order is now with controls team to get the engineer reassigned. Further updates to follow _x000D_30/5/2024:#Update Order delayed due as engineer unable to access DP. order is now with controls team to get the engineer reassigned. Further updates to follow _x000D_29/5/2024:Your order has been delayed due as engineer unable to access DP. order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 04/06/2024 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301417 | 30014110 | 6.Failed router install |  |  | 2024-05-28 | 2024-05-28 | 2024-05-28 | TRUE | [7 empty] | 2024-06-28 | 242005011067 |  | 2024-07-02 | 1
295 | 408679 | 1225 | Batch 3 May24 | Type 1 | SOGEA | Acton Central Londis | LONDON | W3 6EG | 2024-06-07 | 31/5/2024:#update - Order was cancelled by Openreach due to capacity in the cabinet for a new provide. Openreach advice to CSL is to re-try raising the order in 4-6 weeks. _x000D_30/5/2024:#update - Order was cancelled by Openreach due to capacity in the cabinet for a new provide. Openreach advice to CSL is to re-try raising the order in 4-6 weeks. _x000D_29/5/2024:#update - Order was cancelled by Openreach due to capacity in the cabinet for a new provide. Openreach advice to CSL is to re-try raising the order in 4-6 weeks. _x000D_28/5/2024:#update - Order was cancelled by Openreach due to capacity in the cabinet for a new provide. Openreach advice to CSL is to re-try raising the order in 4-6 weeks. _x000D_10/5/2024:#update - Order was cancelled by Openreach due to capacity in the cabinet for a new provide. Openreach advice to CSL is to re-try raising the order in 4-6 weeks. _x000D_02/05/2024: Order was cancelled by Openreach due to capacity in the cabinet for a new provide. Openreach advice to CSL is to re-try raising the order in 4-6 weeks. 23/04/2024: New Forecasted date on 1/5 16/04/2024: Service has been re-raised with supplier with a requested install date 26/04/2024 AM Slot (8am-1pm). Will confirm with customer once this has been agreed. 05/04/2024: CSL order delay. 19/03/24: New order added to report | 31/5/2024:#update - Order was cancelled by Openreach due to capacity in the cabinet for a new provide. Openreach advice to CSL is to re-try raising the order in 4-6 weeks. _x000D_30/5/2024:#update - Order was cancelled by Openreach due to capacity in the cabinet for a new provide. Openreach advice to CSL is to re-try raising the order in 4-6 weeks. _x000D_29/5/2024:#update - Order was cancelled by Openreach due to capacity in the cabinet for a new provide. Openreach advice to CSL is to re-try raising the order in 4-6 weeks. _x000D_28/5/2024:#update - Order was cancelled by Openreach due to capacity in the cabinet for a new provide. Openreach advice to CSL is to re-try raising the order in 4-6 weeks. _x000D_10/5/2024:#update - Order was cancelled by Openreach due to capacity in the cabinet for a new provide. Openreach advice to CSL is to re-try raising the order in 4-6 weeks. _x000D_02/05/2024: Order was cancelled by Openreach due to capacity in the cabinet for a new provide. Openreach advice to CSL is to re-try raising the order in 4-6 weeks. 23/04/2024: New Forecasted date on 1/5 16/04/2024: Service has been re-raised with supplier with a requested install date 26/04/2024 AM Slot (8am-1pm). Will confirm with customer once this has been agreed. 05/04/2024: CSL order delay. 19/03/24: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301422 | 30014115 | 2.Commissioning |  |  | 2024-05-23 | 2024-05-28 | 2024-05-28 | TRUE |  |  |  | 2024-06-19 | [7 empty] | 0
296 | 632804 | 193 | Batch 2 Apr24 | Type 1 | FTTP | Premier Mylees Convenience Store | Manchester | M22 8UE | 2024-05-30 | 31/5/2024:#Update - Dig work required. Third party suppliers have given us a review date of 07/05 _x000D_30/5/2024:#Update - Dig work required. Third party suppliers have given us a review date of 07/05 _x000D_29/5/2024:#Update - Dig work required. Third party suppliers have given us a review date of 07/05 _x000D_28/5/2024:#Update - Dig work required. Third party suppliers have given us a review date of 07/05 _x000D_10/5/2024:#Update - Dig work required. Third party suppliers have given us a review date of 07/05 _x000D_08/05/2024: 02/05/2024: Allwyn Approved Advanced upgrade. 26/04/2024: order has been delayed. Dig work required. Our Suppliers have given us a review date of 07/05/2024. We will continue to provide update as they become available 11/04/2024:Openreach would need to get access at 6AM in the morning when shop is not trading to take up floor boards to see if there is a duct. We will send this over to Allwyn and see if that are wanting to carry out these works with the retailer. 06/04/2024: Openreach completed external works but found the copper feed extends to an inaccessible area under the raised till. They propose accessing it at 6 AM, incurring extra costs. Allwyn must decide if they'll proceed. 19/03/24: New order added to report | 31/5/2024:#Update - Dig work required. Third party suppliers have given us a review date of 07/05 _x000D_30/5/2024:#Update - Dig work required. Third party suppliers have given us a review date of 07/05 _x000D_29/5/2024:#Update - Dig work required. Third party suppliers have given us a review date of 07/05 _x000D_28/5/2024:#Update - Dig work required. Third party suppliers have given us a review date of 07/05 _x000D_10/5/2024:#Update - Dig work required. Third party suppliers have given us a review date of 07/05 _x000D_08/05/2024: 02/05/2024: Allwyn Approved Advanced upgrade. 26/04/2024: order has been delayed. Dig work required. Our Suppliers have given us a review date of 07/05/2024. We will continue to provide update as they become available 11/04/2024:Openreach would need to get access at 6AM in the morning when shop is not trading to take up floor boards to see if there is a duct. We will send this over to Allwyn and see if that are wanting to carry out these works with the retailer. 06/04/2024: Openreach completed external works but found the copper feed extends to an inaccessible area under the raised till. They propose accessing it at 6 AM, incurring extra costs. Allwyn must decide if they'll proceed. 19/03/24: New order added to report |  |  | 2024-05-02 | 02/05/2024: CSL to re-raise the order with OR 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFP2300462 | 30013020 | 6.Failed router install | AM |  | 2024-05-29 | 2024-05-29 | 2024-05-29 | TRUE | [7 empty] | 2024-06-27 | 242005008908 |  | 2024-07-02 | 1
297 | 632893 | 202 | Batch 2 Apr24 | Type 1 | FTTP | Grovehill Express | Hemel Hempstead | HP2 6BJ | 2024-05-30 | 31/5/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_30/5/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_29/5/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_28/5/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_10/5/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_02/04/2024: installation unsuccessful due to third party supplier issues - reappointed for 29/05 - AM, 08/04/2024: New order added to report | 31/5/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_30/5/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_29/5/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_28/5/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_10/5/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_02/04/2024: installation unsuccessful due to third party supplier issues - reappointed for 29/05 - AM, 08/04/2024: New order added to report |  |  | 2024-05-02 | 02/05/2024: CSL to provide Forecasted date. 08/04/2024: Allwyn to advise if they will approve the upgrade or not. 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFP2300550 | 30013489 | 6.Failed router install | AM |  | 2024-05-29 | 2024-05-29 | 2024-05-29 | TRUE | [7 empty] | 2024-06-25 | 242005011061 |  | 2024-07-01 | 1
298 | 659548 | 339 | Batch 3 May24 | Type 1 | SOGEA | Barneys News | Sheringham | NR26 8RE | 2024-05-30 | 31/5/2024:Order Completed _x000D_30/5/2024:Order Completed _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 31/5/2024:Order Completed _x000D_30/5/2024:Order Completed _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report |  |  | 2024-05-02 | 20/05/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFP2300536 | 30013229 | 2.Commissioning |  |  | 2024-05-01 | 2024-05-29 | 2024-05-29 | TRUE |  |  |  | 2024-06-17 | [7 empty] | 0
299 | 462855 | 931 | Batch 3 May24 | Type 1 | SOGEA | ANNEXE STORES | PEACEHAVEN | BN10 8BT | 2024-06-07 | 9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:#Update - Order Completed _x000D_13/6/2024:#Update - Order Completed _x000D_12/6/2024:#Update - Order Completed _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:#Update - Order Completed _x000D_13/6/2024:#Update - Order Completed _x000D_12/6/2024:#Update - Order Completed _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301128 | 30013821 | 2.Commissioning |  |  | 2024-05-29 | 2024-05-29 | 2024-05-29 | TRUE |  |  |  | 2024-06-27 | [7 empty] | 0
300 | 665849 | 1231 | Batch 3 May24 | Type 1 | SOGEA | Londis | MARKET HARBOROUGH | LE16 9PL | 2024-06-07 | 31/5/2024:Order Completed _x000D_30/5/2024:Order Completed _x000D_29/5/2024:Order Completed _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 31/5/2024:Order Completed _x000D_30/5/2024:Order Completed _x000D_29/5/2024:Order Completed _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301428 | 30014121 | 2.Commissioning |  |  | 2024-05-29 | 2024-05-29 | 2024-05-29 | TRUE |  |  |  | 2024-06-26 | [7 empty] | 0 | 665849
301 | 433035 | 1238 | Batch 3 May24 | Type 1 | SOGEA | Milestone Rathfriland Ltd | NEWRY | BT34 5PZ | 2024-06-07 | 31/5/2024:Order Completed _x000D_30/5/2024:Order Completed _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 31/5/2024:Order Completed _x000D_30/5/2024:Order Completed _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301435 | 30014128 | 6.Failed router install |  |  | 2024-05-29 | 2024-05-29 | 2024-05-29 | TRUE | [7 empty] | 2024-06-25 | 242005010328 |  | 2024-07-01 | 1
302 | 436846 | 1239 | Batch 3 May24 | Type 1 | FTTP | Roys (Wroxham) Ltd | THETFORD | IP24 2DT | 2024-06-07 | 31/5/2024:Order Completed _x000D_30/5/2024:Order Completed _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 31/5/2024:Order Completed _x000D_30/5/2024:Order Completed _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301436 | 30014129 | 2.Commissioning |  |  | 2024-05-29 | 2024-05-29 | 2024-05-29 | TRUE |  |  |  | 2024-06-19 | [7 empty] | 0
303 | 441462 | 1240 | Batch 3 May24 | Type 1 | SOGEA | Fresh Food Centres Ltd | CASTLEWELLAN | BT31 9AQ | 2024-06-07 | 31/5/2024:#Update Retailer happy with new appointment. _x000D_30/5/2024:#Update Retailer happy with new appointment. _x000D_29/5/2024:#Update Retailer happy with new appointment. _x000D_28/5/2024:#Update Retailer happy with new appointment. _x000D_10/5/2024:#Update Scheduled for 29/05. Action on Allwyn - ensure the retailer is aware. _x000D_08/04/2024: New order added to report | 31/5/2024:#Update Retailer happy with new appointment. _x000D_30/5/2024:#Update Retailer happy with new appointment. _x000D_29/5/2024:#Update Retailer happy with new appointment. _x000D_28/5/2024:#Update Retailer happy with new appointment. _x000D_10/5/2024:#Update Scheduled for 29/05. Action on Allwyn - ensure the retailer is aware. _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301437 | 30014130 | 6.Failed router install |  |  | 2024-05-29 | 2024-05-29 | 2024-05-29 | TRUE | [7 empty] | 2024-06-25 | 242005010323 |  | 2024-07-01 | 1
304 | 471443 | 1242 | Batch 3 May24 | Type 1 | FTTP | C K's Supermarket | LLANELLI | SA15 5HU | 2024-06-07 | 31/5/2024:Order Completed _x000D_30/5/2024:Order Completed _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 31/5/2024:Order Completed _x000D_30/5/2024:Order Completed _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 6.No action | VFP2301439 | 30014132 | 6.Failed router install |  |  | 2024-05-29 | 2024-05-29 | 2024-05-29 | TRUE | [7 empty] | 2024-06-27 | 242005010337 |  | 2024-07-01 | 1
305 | 465541 | 1247 | Batch 3 May24 | Type 1 | SOGEA | Nisa Extra | Chigwell | IG7 4DN | 2024-06-07 | 31/5/2024:Order Completed _x000D_30/5/2024:Order Completed _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 31/5/2024:Order Completed _x000D_30/5/2024:Order Completed _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301444 | 30014137 | 2.Commissioning |  |  | 2024-05-29 | 2024-05-29 | 2024-05-29 | TRUE |  |  |  | 2024-06-18 | [7 empty] | 0
306 | 634624 | 1252 | Batch 3 May24 | Type 1 | SOGEA | Nisa Local Central Avenue | Grangemouth | FK3 8SD | 2024-06-07 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_31/5/2024:Order Completed _x000D_30/5/2024:Supplier Delay: Missed CCD and may require further work as the engineer has retained the job for next day _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_31/5/2024:Order Completed _x000D_30/5/2024:Supplier Delay: Missed CCD and may require further work as the engineer has retained the job for next day _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 0 | 0 |  |  |  |  | 3.Allwyn to arrange rtr install | VFP2301449 | 30014142 | 2.Commissioning |  |  | 2024-05-29 | 2024-05-29 | 2024-05-29 | TRUE |  |  |  | 2024-06-27 | [7 empty] | 0
307 | 632871 | 1262 | Batch 3 May24 | Type 1 | SOGEA | Nisa Local | Dartford | DA1 1XE | 2024-06-07 | 31/5/2024:Update: Order Completed by Supplier _x000D_30/5/2024:Order Completed _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 31/5/2024:Update: Order Completed by Supplier _x000D_30/5/2024:Order Completed _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301459 | 30014152 | 2.Commissioning |  |  | 2024-05-29 | 2024-05-29 | 2024-05-29 | TRUE |  |  |  | 2024-06-28 | [7 empty] | 0
308 | 633970 | 1264 | Batch 3 May24 | Type 1 | SOGEA | Post Office | SUNDERLAND | SR2 8RP | 2024-06-07 | 31/5/2024:Order Completed _x000D_30/5/2024:Order Completed _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 31/5/2024:Order Completed _x000D_30/5/2024:Order Completed _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301461 | 30014154 | 2.Commissioning |  |  | 2024-05-29 | 2024-05-29 | 2024-05-29 | TRUE |  |  |  | 2024-07-01 | [7 empty] | 0
309 | 637184 | 1266 | Batch 3 May24 | Type 1 | FTTP | Nisa Local | Hitchin | SG4 0AU | 2024-06-07 | 31/5/2024:Order Completed 30/5/2024:Order Completed 29/5/2024:Order Completed 28/5/2024:0 10/5/2024:0 08/04/2024: New order added to report | 31/5/2024:Order Completed 30/5/2024:Order Completed 29/5/2024:Order Completed 28/5/2024:0 10/5/2024:0 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301463 | 30014156 | 2.Commissioning |  |  | 2024-05-29 | 2024-05-29 | 2024-05-29 | TRUE |  |  |  | 2024-06-26 | [7 empty] | 0
310 | 670795 | 1269 | Batch 3 May24 | Type 1 | SOGEA | Local 4 U | SUTTON-IN-ASHFIELD | NG17 2FU | 2024-06-07 | 31/5/2024:Order Completed 30/5/2024:Order Completed 14/05/2024: Retailer changed ( old Id : 455871 ) 29/5/2024:0 28/5/2024:0 10/5/2024:0 08/04/2024: New order added to report | 31/5/2024:Order Completed 30/5/2024:Order Completed 14/05/2024: Retailer changed ( old Id : 455871 ) 29/5/2024:0 28/5/2024:0 10/5/2024:0 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301466 | 30014159 | 6.Failed router install |  |  | 2024-05-29 | 2024-05-29 | 2024-05-29 | TRUE | [7 empty] | 2024-06-28 | 23A004945850 |  | 2024-07-02 | 1
311 | 644277 | 1628 | Batch 4 Jun24 | Type 1 | FTTP/Mobile | Spar | Dungannon | BT71 4QB | 2024-06-07 | 6/9/2024:#Update - Openreach determined that Spar - Dungannon (Moor Road) requires a site survey to progress and this has now been carried out by the survey group. A 9 meters long D56 duct is required to be built in the footway (Sidewalk). A survey pack which outlines this further has been sent. This will be automatically cancelled on the 11th of September if the charges have not been approved, therefore please let us know how you wish to proceed as soon as possible. _x000D_5/9/2024:#Update - Openreach determined that Spar - Dungannon (Moor Road) requires a site survey to progress and this has now been carried out by the survey group. A 9 meters long D56 duct is required to be built in the footway (Sidewalk). A survey pack which outlines this further has been sent. This will be automatically cancelled on the 11th of September if the charges have not been approved, therefore please let us know how you wish to proceed as soon as possible. _x000D_4/9/2024:#Update - Openreach determined that Spar - Dungannon (Moor Road) requires a site survey to progress and this has now been carried out by the survey group. A 9 meters long D56 duct is required to be built in the footway (Sidewalk). A survey pack which outlines this further has been sent. This will be automatically cancelled on the 11th of September if the charges have not been approved, therefore please let us know how you wish to proceed as soon as possible. _x000D_3/9/2024:#Update - Openreach determined that Spar - Dungannon (Moor Road) requires a site survey to progress and this has now been carried out by the survey group. A 9 meters long D56 duct is required to be built in the footway (Sidewalk). A survey pack which outlines this further has been sent. This will be automatically cancelled on the 11th of September if the charges have not been approved, therefore please let us know how you wish to proceed as soon as possible. _x000D_2/9/2024:#Update - Openreach determined that Spar - Dungannon (Moor Road) requires a site survey to progress and this has now been carried out by the survey group. A 9 meters long D56 duct is required to be built in the footway (Sidewalk). A survey pack which outlines this further has been sent. This will be automatically cancelled on the 11th of September if the charges have not been approved, therefore please let us know how you wish to proceed as soon as possible. _x000D_29/8/2024:#Update - Openreach determined that Spar - Dungannon (Moor Road) requires a site survey to progress and this has now been carried out by the survey group. A 9 meters long D56 duct is required to be built in the footway (Sidewalk). A survey pack which outlines this further has been sent. This will be automatically cancelled on the 11th of September if the charges have not been approved, therefore please let us know how you wish to proceed as soon as possible. _x000D_28/8/2024:#Update - Openreach determined that Spar - Dungannon (Moor Road) requires a site survey to progress and this has now been carried out by the survey group. A 9 meters long D56 duct is required to be built in the footway (Sidewalk). A survey pack which outlines this further has been sent. This will be automatically cancelled on the 11th of September if the charges have not been approved, therefore please let us know how you wish to proceed as soon as possible. _x000D_27/8/2024:#Update - Openreach determined that Spar - Dungannon (Moor Road) requires a site survey to progress and this has now been carried out by the survey group. A 9 meters long D56 duct is required to be built in the footway (Sidewalk). A survey pack which outlines this further has been sent. This will be automatically cancelled on the 11th of September if the charges have not been approved, therefore please let us know how you wish to proceed as soon as possible. _x000D_22/8/2024:#Update - Openreach determined that Spar - Dungannon (Moor Road) requires a site survey to progress and this has now been carried out by the survey group. A 9 meters long D56 duct is required to be built in the footway (Sidewalk). A survey pack which outlines this further has been sent. This will be automatically cancelled on the 11th of September if the charges have not been approved, therefore please let us know how you wish to proceed as soon as possible. _x000D_21/8/2024:#Update - Openreach determined that Spar - Dungannon (Moor Road) requires a site survey to progress and this has now been carried out by the survey group. A 9 meters long D56 duct is required to be built in the footway (Sidewalk). A survey pack which outlines this further has been sent. This will be automatically cancelled on the 11th of September if the charges have not been approved, therefore please let us know how you wish to proceed as soon as possible. _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 08/08 AM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 08/08 AM _x000D_19/8/2024:01393564 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 08/08 AM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 08/08 AM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 08/08 AM _x000D_13/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 08/08 AM _x000D_12/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 08/08 AM _x000D_9/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 08/08 AM _x000D_8/8/2024:17/07/2024 _x000D_6/8/2024:17/07/2024 _x000D_5/8/2024:17/07/2024 _x000D_2/8/2024:17/07/2024 _x000D_1/8/2024:17/07/2024 _x000D_31/7/2024:17/07/2024 _x000D_31/7/2024:17/07/2024 _x000D_30/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 08/08 AM _x000D_29/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 08/08 AM _x000D_29/7/2024:01393564 _x000D_26/7/2024:01393564 _x000D_24/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 08/08 AM _x000D_23/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 08/08 AM _x000D_22/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 08/08 AM _x000D_22/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 08/08 AM _x000D_31/5/2024:#Update - NFA - Allwyn confirmed reappointed install date with retailer _x000D_30/5/2024:#Update - NFA - Allwyn confirmed reappointed install date with retailer _x000D_29/5/2024:#Update - NFA - Allwyn confirmed reappointed install date with retailer _x000D_28/5/2024:#Update - NFA - Allwyn confirmed reappointed install date with retailer _x000D_10/5/2024:#Update Pair divert work required. Our Suppliers have given us a review date of 08/05/2024. We will continue to provide update as they become available. _x000D_02/05/2024: New order added to report | 9/9/2024:#Update - Openreach determined that Spar - Dungannon (Moor Road) requires a site survey to progress and this has now been carried out by the survey group. A 9 meters long D56 duct is required to be built in the footway (Sidewalk). A survey pack which outlines this further has been sent. This will be automatically cancelled on the 11th of September if the charges have not been approved, therefore please let us know how you wish to proceed as soon as possible. _x000D_6/9/2024:#Update - Openreach determined that Spar - Dungannon (Moor Road) requires a site survey to progress and this has now been carried out by the survey group. A 9 meters long D56 duct is required to be built in the footway (Sidewalk). A survey pack which outlines this further has been sent. This will be automatically cancelled on the 11th of September if the charges have not been approved, therefore please let us know how you wish to proceed as soon as possible. _x000D_5/9/2024:#Update - Openreach determined that Spar - Dungannon (Moor Road) requires a site survey to progress and this has now been carried out by the survey group. A 9 meters long D56 duct is required to be built in the footway (Sidewalk). A survey pack which outlines this further has been sent. This will be automatically cancelled on the 11th of September if the charges have not been approved, therefore please let us know how you wish to proceed as soon as possible. _x000D_4/9/2024:#Update - Openreach determined that Spar - Dungannon (Moor Road) requires a site survey to progress and this has now been carried out by the survey group. A 9 meters long D56 duct is required to be built in the footway (Sidewalk). A survey pack which outlines this further has been sent. This will be automatically cancelled on the 11th of September if the charges have not been approved, therefore please let us know how you wish to proceed as soon as possible. _x000D_3/9/2024:#Update - Openreach determined that Spar - Dungannon (Moor Road) requires a site survey to progress and this has now been carried out by the survey group. A 9 meters long D56 duct is required to be built in the footway (Sidewalk). A survey pack which outlines this further has been sent. This will be automatically cancelled on the 11th of September if the charges have not been approved, therefore please let us know how you wish to proceed as soon as possible. _x000D_2/9/2024:#Update - Openreach determined that Spar - Dungannon (Moor Road) requires a site survey to progress and this has now been carried out by the survey group. A 9 meters long D56 duct is required to be built in the footway (Sidewalk). A survey pack which outlines this further has been sent. This will be automatically cancelled on the 11th of September if the charges have not been approved, therefore please let us know how you wish to proceed as soon as possible. _x000D_29/8/2024:#Update - Openreach determined that Spar - Dungannon (Moor Road) requires a site survey to progress and this has now been carried out by the survey group. A 9 meters long D56 duct is required to be built in the footway (Sidewalk). A survey pack which outlines this further has been sent. This will be automatically cancelled on the 11th of September if the charges have not been approved, therefore please let us know how you wish to proceed as soon as possible. _x000D_28/8/2024:#Update - Openreach determined that Spar - Dungannon (Moor Road) requires a site survey to progress and this has now been carried out by the survey group. A 9 meters long D56 duct is required to be built in the footway (Sidewalk). A survey pack which outlines this further has been sent. This will be automatically cancelled on the 11th of September if the charges have not been approved, therefore please let us know how you wish to proceed as soon as possible. _x000D_27/8/2024:#Update - Openreach determined that Spar - Dungannon (Moor Road) requires a site survey to progress and this has now been carried out by the survey group. A 9 meters long D56 duct is required to be built in the footway (Sidewalk). A survey pack which outlines this further has been sent. This will be automatically cancelled on the 11th of September if the charges have not been approved, therefore please let us know how you wish to proceed as soon as possible. _x000D_22/8/2024:#Update - Openreach determined that Spar - Dungannon (Moor Road) requires a site survey to progress and this has now been carried out by the survey group. A 9 meters long D56 duct is required to be built in the footway (Sidewalk). A survey pack which outlines this further has been sent. This will be automatically cancelled on the 11th of September if the charges have not been approved, therefore please let us know how you wish to proceed as soon as possible. _x000D_21/8/2024:#Update - Openreach determined that Spar - Dungannon (Moor Road) requires a site survey to progress and this has now been carried out by the survey group. A 9 meters long D56 duct is required to be built in the footway (Sidewalk). A survey pack which outlines this further has been sent. This will be automatically cancelled on the 11th of September if the charges have not been approved, therefore please let us know how you wish to proceed as soon as possible. _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 08/08 AM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 08/08 AM _x000D_19/8/2024:01393564 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 08/08 AM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 08/08 AM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 08/08 AM _x000D_13/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 08/08 AM _x000D_12/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 08/08 AM _x000D_9/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 08/08 AM _x000D_8/8/2024:17/07/2024 _x000D_6/8/2024:17/07/2024 _x000D_5/8/2024:17/07/2024 _x000D_2/8/2024:17/07/2024 _x000D_1/8/2024:17/07/2024 _x000D_31/7/2024:17/07/2024 _x000D_31/7/2024:17/07/2024 _x000D_30/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 08/08 AM _x000D_29/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 08/08 AM _x000D_29/7/2024:01393564 _x000D_26/7/2024:01393564 _x000D_24/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 08/08 AM _x000D_23/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 08/08 AM _x000D_22/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 08/08 AM _x000D_22/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 08/08 AM _x000D_31/5/2024:#Update - NFA - Allwyn confirmed reappointed install date with retailer _x000D_30/5/2024:#Update - NFA - Allwyn confirmed reappointed install date with retailer _x000D_29/5/2024:#Update - NFA - Allwyn confirmed reappointed install date with retailer _x000D_28/5/2024:#Update - NFA - Allwyn confirmed reappointed install date with retailer _x000D_10/5/2024:#Update Pair divert work required. Our Suppliers have given us a review date of 08/05/2024. We will continue to provide update as they become available. _x000D_02/05/2024: New order added to report | 0 | #Update - Openreach determined that Spar - Dungannon (Moor Road) requires a site survey to progress and this has now been carried out by the survey group. A 9 meters long D56 duct is required to be built in the footway (Sidewalk). A survey pack which outlines this further has been sent. This will be automatically cancelled on the 11th of September if the charges have not been approved, therefore please let us know how you wish to proceed as soon as possible. | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFP2338574 | 30015467 | 1.Provisioning | AM |  | 2024-05-29 | 2024-08-08 |  | 0 | [11 empty] | 0
312 | 656603 | 420 | Batch 3 May24 | Type 1 | SOGEA | M Kumaran | Enfield | EN3 5EP | 2024-05-31 | 31/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/05 AM _x000D_30/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/05 AM _x000D_29/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/05 AM _x000D_28/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/05 AM _x000D_10/5/2024:#Update - Installation has now been re-appointment for 30/05 AM. Action for Allwyn: Please speak with the retailer regarding installation details and confirm to CSL if 30/05 is a suitable date. _x000D_09/05/2024: #Update - Installation has now been re-appointment for 30/05 AM. Action for Allwyn: Please speak with the retailer regarding installation details and confirm to CSL if 30/05 is a suitable date. 08/04/2024: New order added to report | 31/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/05 AM _x000D_30/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/05 AM _x000D_29/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/05 AM _x000D_28/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/05 AM _x000D_10/5/2024:#Update - Installation has now been re-appointment for 30/05 AM. Action for Allwyn: Please speak with the retailer regarding installation details and confirm to CSL if 30/05 is a suitable date. _x000D_09/05/2024: #Update - Installation has now been re-appointment for 30/05 AM. Action for Allwyn: Please speak with the retailer regarding installation details and confirm to CSL if 30/05 is a suitable date. 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300617 | 30013310 | 2.Commissioning |  |  | 2024-05-02 | 2024-05-30 | 2024-05-31 | TRUE |  |  |  | 2024-06-18 | [7 empty] | 0
313 | 645335 | 728 | Batch 3 May24 | Type 1 | FTTP | Addington Stores | Cornwall | PL14 3JY | 2024-06-07 | 2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-05-09 | 09/05/2024: Allwyn to make the retailer aware in the date in column U |  |  | 3.Allwyn to arrange rtr install | VFP2300925 | 30013618 | 6.Failed router install |  |  | 2024-05-08 | 2024-05-30 | 2024-05-30 | TRUE | [7 empty] | 2024-06-20 | 242005013683 |  | 2024-07-01 | 1
314 | 664430 | 1043 | Batch 3 May24 | Type 1 | FTTP/Mobile | Costcutter Supermarket | LONDON | SW19 2NX | 2024-06-07 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_27/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_22/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_21/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 20/08/2024. We will continue to provide update as they become available. _x000D_20/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 20/08/2024. We will continue to provide update as they become available. _x000D_19/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 20/08/2024. We will continue to provide update as they become available. _x000D_19/8/2024:14/08/2024 16:23 _x000D_16/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 20/08/2024. We will continue to provide update as they become available. _x000D_15/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 20/08/2024. We will continue to provide update as they become available. _x000D_14/8/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_13/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 15/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 15/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_9/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 15/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_8/8/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/8/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 09/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_2/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 09/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_1/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 09/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 09/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:37701 _x000D_30/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 09/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_23/7/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_22/7/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_22/7/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_31/5/2024:Order Completed _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_27/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_22/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_21/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 20/08/2024. We will continue to provide update as they become available. _x000D_20/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 20/08/2024. We will continue to provide update as they become available. _x000D_19/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 20/08/2024. We will continue to provide update as they become available. _x000D_19/8/2024:14/08/2024 16:23 _x000D_16/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 20/08/2024. We will continue to provide update as they become available. _x000D_15/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 20/08/2024. We will continue to provide update as they become available. _x000D_14/8/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_13/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 15/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 15/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_9/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 15/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_8/8/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/8/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 09/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_2/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 09/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_1/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 09/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 09/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:37701 _x000D_30/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 09/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_23/7/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_22/7/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_22/7/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_31/5/2024:Order Completed _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | Update: Order Amended | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2399165 | 30013933 | 1.Provisioning | AM |  | 2024-05-30 | 2024-08-20 |  | 0 | [11 empty] | 0
315 | 447047 | 1302 | Batch 3 May24 | Type 1 | SOGEA | BELLFIELDS STORES | GUILDFORD | GU1 1QD | 2024-06-07 | 31/5/2024:Order Completed _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 31/5/2024:Order Completed _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301499 | 30014192 | 6.Failed router install |  |  | 2024-05-30 | 2024-05-30 | 2024-05-30 | TRUE | [7 empty] | 2024-06-27 | 242005008636 |  | 2024-07-02 | 1
316 | 668903 | 1310 | Batch 3 May24 | Type 1 | SOGEA | West 9 Wembley Central News & Wine | Wembley | HA9 7AY | 2024-06-07 | 31/5/2024:Order Completed 14/05/2024: Retailer changed ( old Id : 483082 ) 30/5/2024:0 29/5/2024:0 28/5/2024:0 10/5/2024:0 08/04/2024: New order added to report | 31/5/2024:Order Completed 14/05/2024: Retailer changed ( old Id : 483082 ) 30/5/2024:0 29/5/2024:0 28/5/2024:0 10/5/2024:0 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301507 | 30014200 | 6.Failed router install |  |  | 2024-05-30 | 2024-05-30 | 2024-05-30 | TRUE | [7 empty] | 2024-06-24 | 242005008632 |  | 2024-07-01 | 1
317 | 487176 | 1315 | Batch 3 May24 | Type 1 | SOGEA | Nisa Local Thistle Drive | Peterborough | PE2 8JA | 2024-06-07 | 31/5/2024:Order Completed _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 31/5/2024:Order Completed _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301512 | 30014205 | 6.Failed router install |  |  | 2024-05-30 | 2024-05-30 | 2024-05-30 | TRUE | [7 empty] | 2024-06-17 | 23A004948924 |  | 2024-07-01 | 1
318 | 614203 | 1316 | Batch 3 May24 | Type 1 | SOGEA | Woodhall Road | Chelmsford | CM1 4BA | 2024-06-07 | 31/5/2024:Order Completed _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 31/5/2024:Order Completed _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301513 | 30014206 | 2.Commissioning |  |  | 2024-05-30 | 2024-05-30 | 2024-05-30 | TRUE |  |  |  | 2024-06-24 | [7 empty] | 0
319 | 458862 | 1320 | Batch 3 May24 | Type 1 | SOGEA | Nisa | ENNISKILLEN | BT94 4EZ | 2024-06-07 | 19/7/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_18/7/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_17/7/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_16/7/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_15/7/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_12/7/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_11/7/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_10/6/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_7/6/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_6/6/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_5/6/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_4/6/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_31/5/2024:Supplier Delay: Network Planning issue, please await for further details. _x000D_30/5/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 19/7/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_18/7/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_17/7/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_16/7/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_15/7/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_12/7/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_11/7/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_10/6/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_7/6/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_6/6/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_5/6/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_4/6/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_31/5/2024:Supplier Delay: Network Planning issue, please await for further details. _x000D_30/5/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301517 | 30014210 | 6.Failed router install |  |  | 2024-05-30 | 2024-05-30 | 2024-05-30 | TRUE | [7 empty] | 2024-06-27 | 242005010330 |  | 2024-07-02 | 1
320 | 467309 | 1323 | Batch 3 May24 | Type 1 | SoGEA/Mobile | Nisa | Stockport | SK7 3AB | 2024-06-07 | 6/9/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_5/9/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_4/9/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_3/9/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_2/9/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_29/8/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_28/8/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_27/8/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_22/8/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_21/8/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_20/8/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_19/8/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_19/8/2024:01418594 _x000D_16/8/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_15/8/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_14/8/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_13/8/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_12/8/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_9/8/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_8/8/2024:31/05/2024 _x000D_6/8/2024:31/05/2024 _x000D_5/8/2024:31/05/2024 _x000D_2/8/2024:31/05/2024 _x000D_1/8/2024:31/05/2024 _x000D_31/7/2024:31/05/2024 _x000D_31/7/2024:31/05/2024 _x000D_30/7/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_29/7/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_29/7/2024:01418594 _x000D_26/7/2024:01418594 _x000D_24/7/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_23/7/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_22/7/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_22/7/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_31/5/2024:Order Completed _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 9/9/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_6/9/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_5/9/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_4/9/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_3/9/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_2/9/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_29/8/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_28/8/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_27/8/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_22/8/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_21/8/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_20/8/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_19/8/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_19/8/2024:01418594 _x000D_16/8/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_15/8/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_14/8/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_13/8/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_12/8/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_9/8/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_8/8/2024:31/05/2024 _x000D_6/8/2024:31/05/2024 _x000D_5/8/2024:31/05/2024 _x000D_2/8/2024:31/05/2024 _x000D_1/8/2024:31/05/2024 _x000D_31/7/2024:31/05/2024 _x000D_31/7/2024:31/05/2024 _x000D_30/7/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_29/7/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_29/7/2024:01418594 _x000D_26/7/2024:01418594 _x000D_24/7/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_23/7/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_22/7/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_22/7/2024:#Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. _x000D_31/5/2024:Order Completed _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 0 | #Update - order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 05/06/2024. We will continue to provide update as they become available. |  |  |  |  | 3.Allwyn to arrange rtr install | VFS1051739 | 30014213 | 2.Commissioning | AM |  | 2024-08-05 | 2024-08-05 |  | 0 |  |  |  | 2024-07-10 | [7 empty] | 0
321 | 666441 | 1536 | Batch 4 Jun24 | Type 1 | FTTP | Londis | Dagenham | RM9 6UX | 2024-06-07 | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2353436 | 30015961 | 6.Failed router install |  |  | 2024-06-06 | 2024-05-30 | 2024-05-30 | TRUE | [7 empty] | 2024-06-24 | 23A004948642 |  | 2024-07-01 | 1
322 | 672335 | 353 | Batch 3 May24 | Type 1 | FTTP | Better Choice Food and Wine LTD | LONDON | SW19 1AY | 2024-05-30 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:Your order requires planning validation. We may contact your customer if we need to. You will receive a further update by 17-06-2024. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:Your order requires planning validation. We may contact your customer if we need to. You will receive a further update by 17-06-2024. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 0 | 0 |  |  |  |  | 3.Allwyn to arrange rtr install | VFP2300550 | 30013243 | 2.Commissioning | [9 empty] | 2024-07-01 | [7 empty] | 0
323 | 633532 | 215 | Batch 2 Apr24 | Type 1 | SOGEA | Atkins Way Store | Hinckley | LE10 2PH | 2024-06-05 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_ | 0 | 0 | 2024-04-11 | 11/04/2024: Allwyn make the retailer aware ( confirmed ) 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS939575 | 30013514 | 2.Commissioning | AM | [8 empty] | 2024-07-10 | [7 empty] | 0
324 | 625695 | 336 | Batch 3 May24 | Type 3 | FTTP/Mobile | Remilton Store | Durham | TS26 8EE | 2024-05-30 | 6/9/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_5/9/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_4/9/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_3/9/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_2/9/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_29/8/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_28/8/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_27/8/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_22/8/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_21/8/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_20/8/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_19/8/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_19/8/2024:01378546 _x000D_16/8/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_15/8/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_14/8/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_13/8/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_12/8/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_9/8/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_8/8/2024:28/05/2024 _x000D_6/8/2024:28/05/2024 _x000D_5/8/2024:28/05/2024 _x000D_2/8/2024:28/05/2024 _x000D_1/8/2024:28/05/2024 _x000D_31/7/2024:28/05/2024 _x000D_31/7/2024:28/05/2024 _x000D_30/7/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_29/7/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_29/7/2024:01378546 _x000D_26/7/2024:01378546 _x000D_24/7/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_23/7/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_22/7/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_22/7/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_7/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 between 8-10 AM _x000D_6/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 between 8-10 AM _x000D_5/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 between 8-10 AM _x000D_4/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 between 8-10 AM _x000D_31/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 between 8-10 AM _x000D_30/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 between 8-10 AM _x000D_29/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 between 8-10 AM _x000D_28/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 between 8-10 AM _x000D_10/5/2024:#Update - Openreach was unable to complete the installation as a flat roof engineer is required and access to the premises when the shop is quiet. _x000D_07/05/2024: Openreach was unable to complete the installation as a flat roof engineer is required and access to the premises when the shop is quiet. 08/04/2024: New order added to report | 9/9/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_6/9/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_5/9/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_4/9/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_3/9/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_2/9/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_29/8/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_28/8/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_27/8/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_22/8/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_21/8/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_20/8/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_19/8/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_19/8/2024:01378546 _x000D_16/8/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_15/8/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_14/8/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_13/8/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_12/8/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_9/8/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_8/8/2024:28/05/2024 _x000D_6/8/2024:28/05/2024 _x000D_5/8/2024:28/05/2024 _x000D_2/8/2024:28/05/2024 _x000D_1/8/2024:28/05/2024 _x000D_31/7/2024:28/05/2024 _x000D_31/7/2024:28/05/2024 _x000D_30/7/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_29/7/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_29/7/2024:01378546 _x000D_26/7/2024:01378546 _x000D_24/7/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_23/7/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_22/7/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_22/7/2024:#Update:- Allwyn have requested this site be downgraded to site type 3 _x000D_7/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 between 8-10 AM _x000D_6/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 between 8-10 AM _x000D_5/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 between 8-10 AM _x000D_4/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 between 8-10 AM _x000D_31/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 between 8-10 AM _x000D_30/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 between 8-10 AM _x000D_29/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 between 8-10 AM _x000D_28/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 between 8-10 AM _x000D_10/5/2024:#Update - Openreach was unable to complete the installation as a flat roof engineer is required and access to the premises when the shop is quiet. _x000D_07/05/2024: Openreach was unable to complete the installation as a flat roof engineer is required and access to the premises when the shop is quiet. 08/04/2024: New order added to report | 0 | #Update:- Allwyn have requested this site be downgraded to site type 3 |  | 24/05/2024: Allwyn to install rtr as it is a type 3 now 02/05/2024: CSL to provide update. |  |  | 3.Allwyn to arrange rtr install | VFP2324995 | 30013226 | 2.Commissioning | AM |  |  |  |  | 0 |  |  |  | 2024-07-18 | [7 empty] | 0
325 | 655754 | 454 | Batch 3 May24 | Type 1 | SOGEA | Catford Express | London | SE6 4HQ | 2024-06-05 | 19/7/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_18/7/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_17/7/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_16/7/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_15/7/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_12/7/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_11/7/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_10/7/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_9/7/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_4/7/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_3/7/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_27/6/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_25/6/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_24/6/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_20/6/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_19/6/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_18/6/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_17/6/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_14/6/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_13/6/2024:#Update - 03/06 appointment confirmed by retailer. _x000D_12/6/2024:#Update - 03/06 appointment confirmed by retailer. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:Supplier Delay: Delay encountered during automated test of new service _x000D_ | 19/7/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_18/7/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_17/7/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_16/7/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_15/7/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_12/7/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_11/7/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_10/7/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_9/7/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_4/7/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_3/7/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_27/6/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_25/6/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_24/6/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_20/6/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_19/6/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_18/6/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_17/6/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_14/6/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_13/6/2024:#Update - 03/06 appointment confirmed by retailer. _x000D_12/6/2024:#Update - 03/06 appointment confirmed by retailer. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:Supplier Delay: Delay encountered during automated test of new service _x000D_ |  |  | 2024-05-07 | 07/05/2024: Installation in a flat roof and engineer require access to the premises when the shop is quiet. |  |  | 3.Allwyn to arrange rtr install | VFP2300651 | 30013344 | 6.Failed router install | AM |  | 2024-05-03 | 2024-06-03 | 2024-06-04 | TRUE |  |  |  | 2024-07-01 |  |  |  | 2024-08-27 | 242005008361 | 242005008361 | 2024-08-28 | 1
326 | 658862 | 792 | Batch 3 May24 | Type 1 | SoGEA/Mobile | Go Local | Newcastle upon Tyne | NE5 2NN | 2024-09-05 | 6/9/2024:#Update - Completed - First Pole date - 04/09/2024 09:46 _x000D_5/9/2024:#Update - Completed - First Pole date - 04/09/2024 09:46 _x000D_4/9/2024:#Update - Completed - First Pole date - 04/09/2024 09:46 _x000D_3/9/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_2/9/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_29/8/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_28/8/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_27/8/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_22/8/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_21/8/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_20/8/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_19/8/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_19/8/2024:01388369 _x000D_16/8/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_15/8/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_14/8/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_13/8/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_12/8/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_9/8/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_8/8/2024:13/06/2024 _x000D_6/8/2024:13/06/2024 _x000D_5/8/2024:13/06/2024 _x000D_2/8/2024:13/06/2024 _x000D_1/8/2024:13/06/2024 _x000D_31/7/2024:13/06/2024 _x000D_31/7/2024:13/06/2024 _x000D_30/7/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_29/7/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_29/7/2024:01388369 _x000D_26/7/2024:01388369 _x000D_24/7/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_23/7/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_22/7/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_22/7/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_7/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 AM _x000D_6/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 AM _x000D_5/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 AM _x000D_4/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 AM _x000D_31/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 AM _x000D_30/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 AM _x000D_29/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 AM _x000D_28/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 AM _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 9/9/2024:#Update - Completed - First Pole date - 04/09/2024 09:46 _x000D_6/9/2024:#Update - Completed - First Pole date - 04/09/2024 09:46 _x000D_5/9/2024:#Update - Completed - First Pole date - 04/09/2024 09:46 _x000D_4/9/2024:#Update - Completed - First Pole date - 04/09/2024 09:46 _x000D_3/9/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_2/9/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_29/8/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_28/8/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_27/8/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_22/8/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_21/8/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_20/8/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_19/8/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_19/8/2024:01388369 _x000D_16/8/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_15/8/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_14/8/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_13/8/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_12/8/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_9/8/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_8/8/2024:13/06/2024 _x000D_6/8/2024:13/06/2024 _x000D_5/8/2024:13/06/2024 _x000D_2/8/2024:13/06/2024 _x000D_1/8/2024:13/06/2024 _x000D_31/7/2024:13/06/2024 _x000D_31/7/2024:13/06/2024 _x000D_30/7/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_29/7/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_29/7/2024:01388369 _x000D_26/7/2024:01388369 _x000D_24/7/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_23/7/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_22/7/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_22/7/2024:#Update - Openreach still awaiting to hear from PatchLead about OOH work. Therefore appointment from 03/06 did not goahead. I will await for further updates about this site and then will re-appoint accordingly. _x000D_7/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 AM _x000D_6/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 AM _x000D_5/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 AM _x000D_4/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 AM _x000D_31/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 AM _x000D_30/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 AM _x000D_29/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 AM _x000D_28/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 AM _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | Order Completed | #Update - Completed - First Pole date - 04/09/2024 09:46 |  |  |  |  | 2.Allwyn to arrange access | VFS970588 | 30013682 | 2.Commissioning | AM |  | 2024-05-09 | 2024-09-04 |  | 0 | [11 empty] | 0
327 | 443785 | 852 | Batch 3 May24 | Type 1 | SOGEA | SEYMOUR NEWS | NEWENT | GL18 1PP | 2024-06-07 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Order Completed _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Order Completed _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report |  |  | 2024-05-17 | 17/05/2024: Allwyn to arrange access on new date |  |  | 3.Allwyn to arrange rtr install | VFP2301049 | 30013742 | 6.Failed router install | AM |  | 2024-05-16 | 2024-06-03 | 2024-06-03 | TRUE | [7 empty] | 2024-06-24 | 23A004945969 |  | 2024-07-01 | 1
328 | 632131 | 862 | Batch 3 May24 | Type 1 | SOGEA | Sloane Food and Wine | LONDON | SW1W 8DA | 2024-06-07 | 7/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 AM _x000D_6/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 AM _x000D_5/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 AM _x000D_4/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 AM _x000D_31/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 AM _x000D_30/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 AM _x000D_29/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 AM _x000D_28/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 AM _x000D_22/5/2024:#Update - The installation could not be completed due to scaffolding on a nearby premise. Openreach have advised that this is to be taken down by the 30th of May therefore we have reappointed for the 3rd of June 2024, AM. _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 7/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 AM _x000D_6/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 AM _x000D_5/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 AM _x000D_4/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 AM _x000D_31/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 AM _x000D_30/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 AM _x000D_29/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 AM _x000D_28/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/06 AM _x000D_22/5/2024:#Update - The installation could not be completed due to scaffolding on a nearby premise. Openreach have advised that this is to be taken down by the 30th of May therefore we have reappointed for the 3rd of June 2024, AM. _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301059 | 30013752 | 6.Failed router install | AM |  | 2024-05-16 | 2024-06-03 | 2024-06-03 | TRUE | [7 empty] | 2024-06-19 | 23A004949236 |  | 2024-07-01 | 1
329 | 665521 | 1054 | Batch 3 May24 | Type 1 | SOGEA | Fine Foods Post Office | Hedworth | NE32 4LZ | 2024-06-07 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Order Completed _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Order Completed _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301251 | 30013944 | 6.Failed router install | AM |  | 2024-06-03 | 2024-06-03 | 2024-06-03 | TRUE | [7 empty] | 2024-06-27 | 23A004948533 |  | 2024-07-02 | 1
330 | 470338 | 1326 | Batch 4 Jun24 | Type 1 | SOGEA | Nisa Local | Slough | SL3 7DX | 2024-06-07 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Order Completed _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Order Completed _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFS984893 | 30015421 | 6.Failed router install | AM |  | 2024-06-03 | 2024-06-03 | 2024-06-03 | TRUE |  |  |  | 2024-06-26 |  |  |  | 2024-07-17 | 237004907535 |  | 2024-07-18 | 1
331 | 432848 | 1332 | Batch 4 Jun24 | Type 1 | SOGEA | Carisle Supervalu | BALLYNAHINCH | BT24 8FF | 2024-06-07 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Order Completed _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Order Completed _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFS984899 | 30015512 | 2.Commissioning | AM |  | 2024-06-03 | 2024-06-03 | 2024-06-03 | TRUE |  |  |  | 2024-06-25 | [7 empty] | 0
332 | 432941 | 1334 | Batch 4 Jun24 | Type 1 | SoGEA/Mobile | Nisa Local | DARLINGTON | DL1 4QE | 2024-06-07 | 6/9/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_5/9/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_4/9/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_3/9/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_2/9/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_29/8/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_28/8/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_27/8/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_22/8/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_21/8/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_20/8/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_19/8/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_19/8/2024:01425427 _x000D_16/8/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_15/8/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_14/8/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_13/8/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_12/8/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_9/8/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_8/8/2024:18/07/2024 _x000D_6/8/2024:18/07/2024 _x000D_5/8/2024:18/07/2024 _x000D_2/8/2024:18/07/2024 _x000D_1/8/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_30/7/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_29/7/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_29/7/2024:01425427 _x000D_26/7/2024:01425427 _x000D_24/7/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_23/7/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_22/7/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_22/7/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Order Completed _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 9/9/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_6/9/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_5/9/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_4/9/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_3/9/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_2/9/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_29/8/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_28/8/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_27/8/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_22/8/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_21/8/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_20/8/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_19/8/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_19/8/2024:01425427 _x000D_16/8/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_15/8/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_14/8/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_13/8/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_12/8/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_9/8/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_8/8/2024:18/07/2024 _x000D_6/8/2024:18/07/2024 _x000D_5/8/2024:18/07/2024 _x000D_2/8/2024:18/07/2024 _x000D_1/8/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_30/7/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_29/7/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_29/7/2024:01425427 _x000D_26/7/2024:01425427 _x000D_24/7/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_23/7/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_22/7/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_22/7/2024:#Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so _x000D_7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Order Completed _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 0 | #Update - Order has been cancelled for the time being - will re-raise once instructed by Allwyn to do so |  |  |  |  | 2.Allwyn to arrange access | VFS984901 | 30015389 | 1.Provisioning | AM |  | 2024-06-03 |  |  | 0 | [11 empty] | 0
333 | 651163 | 1336 | Batch 4 Jun24 | Type 1 | SOGEA | Cobra Global LTD | Manchester | M44 6FF | 2024-06-07 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Order Completed _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Order Completed _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFS984903 | 30015307 | 6.Failed router install | AM |  | 2024-06-03 | 2024-06-03 | 2024-06-03 | TRUE | [7 empty] | 2024-06-27 | 242005008906 |  | 2024-07-02 | 1
334 | 648788 | 1340 | Batch 4 Jun24 | Type 3 | SoGEA/Mobile | Nisa Local | Chatteris | PE16 6AB | 2024-06-07 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Order Completed _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Order Completed _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 0 | 0 |  |  |  |  | 3.Allwyn to arrange rtr install | VFS984906 | 30015583 | 2.Commissioning | AM |  |  |  |  | 0 |  |  |  | 2024-06-17 | [7 empty] | 0
335 | 654208 | 1341 | Batch 4 Jun24 | Type 1 | SOGEA | Nisa Local | Southampton | SO19 6HQ | 2024-06-07 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Order Completed _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Order Completed _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFS984908 | 30015369 | 2.Commissioning | AM |  | 2024-06-03 | 2024-06-03 | 2024-06-03 | TRUE |  |  |  | 2024-06-17 | [7 empty] | 0
336 | 109493 | 1346 | Batch 4 Jun24 | Type 1 | SOGEA | McAnerneys | ARMAGH | BT61 7EP | 2024-06-07 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Order Completed _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Order Completed _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFS984910 | 30015651 | 6.Failed router install | AM |  | 2024-06-03 | 2024-06-03 | 2024-06-03 | TRUE | [7 empty] | 2024-06-27 | 23A004952965 |  | 2024-07-02 | 1
337 | 624539 | 1348 | Batch 4 Jun24 | Type 1 | FTTP | Centra | Lisburn | BT27 5EY | 2024-06-07 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Order Completed _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Order Completed _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2338474 | 30015313 | 6.Failed router install | AM |  | 2024-06-03 | 2024-06-03 | 2024-06-03 | TRUE | [7 empty] | 2024-06-25 | 242005010329 |  | 2024-07-01 | 1
338 | 448955 | 1752 | Batch 4 Jun24 | Type 1 | FTTP | The Bargain Box | RYE | TN31 7AD | 2024-06-07 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Supplier Delay: Missed CCD and may require further work as the engineer has retained the job for next day _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Supplier Delay: Missed CCD and may require further work as the engineer has retained the job for next day _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983291 | 30015272 | 2.Commissioning | AM |  | 2024-06-03 | 2024-06-03 | 2024-06-03 | TRUE |  |  |  | 2024-07-04 | [7 empty] | 0
339 | 619390 | 1753 | Batch 4 Jun24 | Type 1 | SOGEA | Manor Stores | Chinnor | OX39 4PG | 2024-06-07 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Order Completed _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Order Completed _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983290 | 30015167 | 6.Failed router install | AM |  | 2024-06-03 | 2024-06-03 | 2024-06-04 | TRUE | [7 empty] | 2024-07-02 | 242005008635 |  | 2024-07-04 | 1
340 | 487195 | 1759 | Batch 4 Jun24 | Type 1 | FTTP | Centra | Gilford | BT63 6HQ | 2024-06-07 | 5/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 06/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_2/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 06/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_1/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 06/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 06/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:37660 _x000D_30/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 06/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 06/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:29/07/2024 09:11 _x000D_26/7/2024:26/07/2024 09:34 _x000D_7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Order Completed _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 5/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 06/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_2/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 06/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_1/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 06/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 06/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:37660 _x000D_30/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 06/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 06/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:29/07/2024 09:11 _x000D_26/7/2024:26/07/2024 09:34 _x000D_7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Order Completed _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2337305 | 30015142 | 2.Commissioning | AM |  | 2024-06-03 | 2024-06-03 | 2024-06-03 | TRUE |  |  |  | 2024-06-27 | [7 empty] | 0
341 | 611837 | 1760 | Batch 4 Jun24 | Type 1 | SOGEA | Filco | Mid Glamorgan | CF34 9BT | 2024-06-07 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Order Completed _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/05/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Order Completed _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983296 | 30015220 | 2.Commissioning | AM |  | 2024-06-03 | 2024-06-03 | 2024-06-03 | TRUE |  |  |  | 2024-07-03 | [7 empty] | 0
342 | 635360 | 1805 | Batch 4 Jun24 | Type 1 | SOGEA | Spar Stores | Londonberry | BT47 2PU | 2024-06-07 | 20/6/2024:Your order has been delayed due to a Vodafone system issue which is preventing us from progressing your order. Once the issue has been resolved the order will progress. _x000D_19/6/2024:Update: Order Completed by Supplier _x000D_18/6/2024:Update: Order Completed by Supplier _x000D_17/6/2024:Update: Order Completed by Supplier _x000D_14/6/2024:Your order has been delayed. The engineer has now completed all the external work and our suppliers has advised us to reappoint the order. Please check with end user and reappoint for the first available date. _x000D_13/6/2024:Your order has been delayed. The engineer has now completed all the external work and our suppliers has advised us to reappoint the order. Please check with end user and reappoint for the first available date. _x000D_12/6/2024:Your order has been delayed. The engineer has now completed all the external work and our suppliers has advised us to reappoint the order. Please check with end user and reappoint for the first available date. _x000D_10/6/2024:Your order has been delayed. Our suppliers are raising the required external work, they have given us a review date of 11/06/2024. We will continue to provide update as they become available. _x000D_7/6/2024:Your order has been delayed. Our suppliers are raising the required external work, they have given us a review date of 11/06/2024. We will continue to provide update as they become available. _x000D_6/6/2024:Supplier Missed Appointment _x000D_5/6/2024:Your order has been delayed due to multiskilled engineer work is required, order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 07/06/2024. _x000D_4/6/2024:Supplier Delay: KCI-3 (Order Completed) Delayed in Processing. _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 20/6/2024:Your order has been delayed due to a Vodafone system issue which is preventing us from progressing your order. Once the issue has been resolved the order will progress. _x000D_19/6/2024:Update: Order Completed by Supplier _x000D_18/6/2024:Update: Order Completed by Supplier _x000D_17/6/2024:Update: Order Completed by Supplier _x000D_14/6/2024:Your order has been delayed. The engineer has now completed all the external work and our suppliers has advised us to reappoint the order. Please check with end user and reappoint for the first available date. _x000D_13/6/2024:Your order has been delayed. The engineer has now completed all the external work and our suppliers has advised us to reappoint the order. Please check with end user and reappoint for the first available date. _x000D_12/6/2024:Your order has been delayed. The engineer has now completed all the external work and our suppliers has advised us to reappoint the order. Please check with end user and reappoint for the first available date. _x000D_10/6/2024:Your order has been delayed. Our suppliers are raising the required external work, they have given us a review date of 11/06/2024. We will continue to provide update as they become available. _x000D_7/6/2024:Your order has been delayed. Our suppliers are raising the required external work, they have given us a review date of 11/06/2024. We will continue to provide update as they become available. _x000D_6/6/2024:Supplier Missed Appointment _x000D_5/6/2024:Your order has been delayed due to multiskilled engineer work is required, order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 07/06/2024. _x000D_4/6/2024:Supplier Delay: KCI-3 (Order Completed) Delayed in Processing. _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996756 | 30016080 | 6.Failed router install | AM |  | 2024-06-03 | 2024-06-03 | 2024-06-03 | TRUE | [7 empty] | 2024-06-26 | 242005010325 |  | 2024-07-02 | 1
343 | 460494 | 1810 | Batch 4 Jun24 | Type 1 | SOGEA | Spar Stores | LANCASTER | LA1 2HL | 2024-06-07 | 7/6/2024:#Update - Order has been delayed as a multiskilled engineer is required to complete the installation, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_6/6/2024:#Update - Order has been delayed as a multiskilled engineer is required to complete the installation, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_5/6/2024:#Update - Order has been delayed as a multiskilled engineer is required to complete the installation, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 7/6/2024:#Update - Order has been delayed as a multiskilled engineer is required to complete the installation, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_6/6/2024:#Update - Order has been delayed as a multiskilled engineer is required to complete the installation, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_5/6/2024:#Update - Order has been delayed as a multiskilled engineer is required to complete the installation, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996758 | 30015969 | 2.Commissioning | AM |  | 2024-06-03 | 2024-06-03 | 2024-06-17 | TRUE |  |  |  | 2024-07-16 | [7 empty] | 0
344 | 466228 | 1817 | Batch 4 Jun24 | Type 1 | SOGEA | Spar Stores | Solihull | B91 1BQ | 2024-06-07 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Order Completed _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Order Completed _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996757 | 30016049 | 6.Failed router install | AM |  | 2024-06-03 | 2024-06-03 | 2024-06-04 | TRUE | [7 empty] | 2024-06-27 | 238004917295 |  | 2024-07-02 | 1
345 | 644756 | 1828 | Batch 4 Jun24 | Type 1 | SOGEA | Spar Stores | Stockton-on-Tees | TS23 3XR | 2024-06-07 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Order Completed _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Order Completed _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996760 | 30016019 | 6.Failed router install | AM |  | 2024-06-03 | 2024-06-03 | 2024-06-03 | TRUE | [7 empty] | 2024-06-27 | 237004907023 |  | 2024-07-02 | 1
346 | 619572 | 1848 | Batch 4 Jun24 | Type 1 | SOGEA | Spar Stores | Stourbridge | DY8 3NU | 2024-06-07 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Order Completed _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Order Completed _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996759 | 30016065 | 2.Commissioning | AM |  | 2024-06-03 | 2024-06-03 | 2024-06-03 | TRUE |  |  |  | 2024-06-27 | [7 empty] | 0
347 | 644787 | 1854 | Batch 4 Jun24 | Type 1 | SOGEA | SPAR | Middleton | M24 5LU | 2024-06-07 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Supplier Delay: KCI-3 (Order Completed) Delayed in Processing. _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Supplier Delay: KCI-3 (Order Completed) Delayed in Processing. _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996763 | 30016042 | 2.Commissioning | AM |  | 2024-06-03 | 2024-06-03 | 2024-06-03 | TRUE |  |  |  | 2024-06-27 | [7 empty] | 0
348 | 634060 | 1859 | Batch 4 Jun24 | Type 1 | SOGEA | Spar Crumpsall | Manchester | M8 4ED | 2024-06-07 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Order Completed _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Order Completed _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996761 | 30016113 | 6.Failed router install | AM |  | 2024-06-03 | 2024-06-03 | 2024-06-05 | TRUE |  |  |  | 2024-07-09 |  |  |  | 2024-07-09 | 242005008844 |  |  | 1
349 | 639211 | 1861 | Batch 4 Jun24 | Type 1 | FTTP | Spar | Tyrone | BT79 0DX | 2024-06-07 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Order Completed _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Order Completed _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2353426 | 30015941 | 2.Commissioning | AM |  | 2024-06-03 | 2024-06-03 | 2024-06-03 | TRUE |  |  |  | 2024-06-27 | [7 empty] | 0
350 | 639243 | 1862 | Batch 4 Jun24 | Type 1 | FTTP | Lynchs Spar | Londonderry | BT48 8TE | 2024-06-07 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Order Completed _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Order Completed _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2353427 | 30015965 | 2.Commissioning | AM |  | 2024-06-03 | 2024-06-03 | 2024-06-03 | TRUE |  |  |  | 2024-06-26 | [7 empty] | 0
351 | 669599 | 1868 | Batch 4 Jun24 | Type 1 | SOGEA | Spar Stores | Stourbridge | DY8 5PD | 2024-06-07 | 6/9/2024:#Update - No access as manager knows nothing about it and has to speak to head office. CSL to continue to investigate missing socket. _x000D_5/9/2024:#Update - No access as manager knows nothing about it and has to speak to head office. CSL to continue to investigate missing socket. _x000D_4/9/2024:#Update - No access as manager knows nothing about it and has to speak to head office. CSL to continue to investigate missing socket. _x000D_3/9/2024:#Update - No access as manager knows nothing about it and has to speak to head office. CSL to continue to investigate missing socket. _x000D_2/9/2024:#Update - No access as manager knows nothing about it and has to speak to head office. CSL to continue to investigate missing socket. _x000D_29/8/2024:#Update - No access as manager knows nothing about it and has to speak to head office. CSL to continue to investigate missing socket. _x000D_28/8/2024:#Update - No access as manager knows nothing about it and has to speak to head office. CSL to continue to investigate missing socket. _x000D_7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Order Completed _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 9/9/2024:#Update - No access as manager knows nothing about it and has to speak to head office. CSL to continue to investigate missing socket. _x000D_6/9/2024:#Update - No access as manager knows nothing about it and has to speak to head office. CSL to continue to investigate missing socket. _x000D_5/9/2024:#Update - No access as manager knows nothing about it and has to speak to head office. CSL to continue to investigate missing socket. _x000D_4/9/2024:#Update - No access as manager knows nothing about it and has to speak to head office. CSL to continue to investigate missing socket. _x000D_3/9/2024:#Update - No access as manager knows nothing about it and has to speak to head office. CSL to continue to investigate missing socket. _x000D_2/9/2024:#Update - No access as manager knows nothing about it and has to speak to head office. CSL to continue to investigate missing socket. _x000D_29/8/2024:#Update - No access as manager knows nothing about it and has to speak to head office. CSL to continue to investigate missing socket. _x000D_28/8/2024:#Update - No access as manager knows nothing about it and has to speak to head office. CSL to continue to investigate missing socket. _x000D_7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Order Completed _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 0 | #Update - No access as manager knows nothing about it and has to speak to head office. CSL to continue to investigate missing socket. | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996764 | 30016039 | 2.Commissioning | AM |  | 2024-06-03 | 2024-06-03 | 2024-06-03 | TRUE |  |  |  | 2024-06-27 | [7 empty] | 0
352 | 486325 | 1879 | Batch 4 Jun24 | Type 1 | SOGEA | SPARCAERLEON ROAD | NEWPORT | NP19 7HA | 2024-06-07 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Order Completed _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Order Completed _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996769 | 30016052 | 2.Commissioning | AM |  | 2024-06-03 | 2024-06-03 | 2024-06-03 | TRUE |  |  |  | 2024-07-03 | [7 empty] | 0
353 | 470161 | 89 | Batch 2 Apr24 | Type 1 | FTTP | Premier Hayats Supersave | Dundee | DD4 8LS | 2024-06-05 | 7/6/2024:#Update This order has been rescheduled for 4/06 AM to suit retailer availability. _x000D_6/6/2024:#Update This order has been rescheduled for 4/06 AM to suit retailer availability. _x000D_5/6/2024:#Update This order has been rescheduled for 4/06 AM to suit retailer availability. _x000D_4/6/2024:#Update This order has been rescheduled for 4/06 AM to suit retailer availability. _x000D_31/5/2024:#Update This order has been rescheduled for 4/06 AM to suit retailer availability. _x000D_30/5/2024:#Update This order has been rescheduled for 4/06 AM to suit retailer availability. _x000D_29/5/2024:#Update This order has been rescheduled for 4/06 AM to suit retailer availability. _x000D_28/5/2024:#Update This order has been rescheduled for 4/06 AM to suit retailer availability. _x000D_10/5/2024:#Update This order has been rescheduled for 4/06 AM to suit retailer availability. _x000D_03/04/24: Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. 08/04/2024: New order added to report | 7/6/2024:#Update This order has been rescheduled for 4/06 AM to suit retailer availability. _x000D_6/6/2024:#Update This order has been rescheduled for 4/06 AM to suit retailer availability. _x000D_5/6/2024:#Update This order has been rescheduled for 4/06 AM to suit retailer availability. _x000D_4/6/2024:#Update This order has been rescheduled for 4/06 AM to suit retailer availability. _x000D_31/5/2024:#Update This order has been rescheduled for 4/06 AM to suit retailer availability. _x000D_30/5/2024:#Update This order has been rescheduled for 4/06 AM to suit retailer availability. _x000D_29/5/2024:#Update This order has been rescheduled for 4/06 AM to suit retailer availability. _x000D_28/5/2024:#Update This order has been rescheduled for 4/06 AM to suit retailer availability. _x000D_10/5/2024:#Update This order has been rescheduled for 4/06 AM to suit retailer availability. _x000D_03/04/24: Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. 08/04/2024: New order added to report |  |  | 2024-04-08 | 08/04/2024: Allwyn to make the retailer awar of the new installation date. 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFP2300408 | 30013167 | 6.Failed router install | AM |  | 2024-06-04 | 2024-06-04 | 2024-06-04 | TRUE | [7 empty] | 2024-06-24 | 23A004945403 |  | 2024-07-01 | 1
354 | 469470 | 927 | Batch 3 May24 | Type 1 | SOGEA | Spalding News | Spalding | PE11 1SS | 2024-06-07 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 3.Allwyn to arrange rtr install | VFP2301124 | 30013817 | 2.Commissioning | AM | [8 empty] | 2024-07-02 | [7 empty] | 0
355 | 626753 | 967 | Batch 3 May24 | Type 1 | SOGEA | Green Lane News | Norbury | SW16 3LH | 2024-06-07 | 7/6/2024:#Update - Engineers have given us a review date of 22/05/2024. We will continue to provide update as they become available. _x000D_6/6/2024:#Update - Engineers have given us a review date of 22/05/2024. We will continue to provide update as they become available. _x000D_5/6/2024:#Update - Engineers have given us a review date of 22/05/2024. We will continue to provide update as they become available. _x000D_4/6/2024:#Update - Engineers have given us a review date of 22/05/2024. We will continue to provide update as they become available. _x000D_31/5/2024:#Update - Engineers have given us a review date of 22/05/2024. We will continue to provide update as they become available. _x000D_30/5/2024:#Update - Engineers have given us a review date of 22/05/2024. We will continue to provide update as they become available. _x000D_29/5/2024:#Update - Engineers have given us a review date of 22/05/2024. We will continue to provide update as they become available. _x000D_28/5/2024:#Update - Engineers have given us a review date of 22/05/2024. We will continue to provide update as they become available. _x000D_10/5/2024:#Update - this order is experiencing continued delays due to pair divert work required. Updates to follow accordingly _x000D_08/04/2024: New order added to report | 7/6/2024:#Update - Engineers have given us a review date of 22/05/2024. We will continue to provide update as they become available. _x000D_6/6/2024:#Update - Engineers have given us a review date of 22/05/2024. We will continue to provide update as they become available. _x000D_5/6/2024:#Update - Engineers have given us a review date of 22/05/2024. We will continue to provide update as they become available. _x000D_4/6/2024:#Update - Engineers have given us a review date of 22/05/2024. We will continue to provide update as they become available. _x000D_31/5/2024:#Update - Engineers have given us a review date of 22/05/2024. We will continue to provide update as they become available. _x000D_30/5/2024:#Update - Engineers have given us a review date of 22/05/2024. We will continue to provide update as they become available. _x000D_29/5/2024:#Update - Engineers have given us a review date of 22/05/2024. We will continue to provide update as they become available. _x000D_28/5/2024:#Update - Engineers have given us a review date of 22/05/2024. We will continue to provide update as they become available. _x000D_10/5/2024:#Update - this order is experiencing continued delays due to pair divert work required. Updates to follow accordingly _x000D_08/04/2024: New order added to report |  |  | 2024-05-21 |  |  |  | 3.Allwyn to arrange rtr install | VFP2301164 | 30013857 | 6.Failed router install | AM |  | 2024-05-20 | 2024-06-04 | 2024-06-04 | TRUE | [7 empty] | 2024-07-01 | 242005008637 |  | 2024-07-04 | 1
356 | 668451 | 1215 | Batch 3 May24 | Type 1 | FTTP | Londis | Bracknell | RG12 8UX | 2024-06-07 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:Update: Order Amended _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:Update: Order Amended _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301412 | 30014105 | 6.Failed router install | AM |  | 2024-06-04 | 2024-06-04 | 2024-06-04 | TRUE | [7 empty] | 2024-07-03 | 242005011127 |  |  | 1 | 668451
357 | 625485 | 1311 | Batch 3 May24 | Type 1 | SOGEA | Nisa Local | St Osyth | CO16 8PA | 2024-06-07 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301508 | 30014201 | 6.Failed router install | AM |  | 2024-06-04 | 2024-06-04 | 2024-06-04 | TRUE |  |  |  | 2024-08-08 |  |  |  | 2024-08-08 | 242005008601 |  | 2024-08-09 | 1
358 | 425876 | 1349 | Batch 4 Jun24 | Type 1 | FTTP | Spar Stores | BELFAST | BT8 7EY | 2024-06-07 | 19/7/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_18/7/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_17/7/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_16/7/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_15/7/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_12/7/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_11/7/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_10/7/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_9/7/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_4/7/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_3/7/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_2/7/2024:0 _x000D_1/7/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_27/6/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_25/6/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_24/6/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_20/6/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_19/6/2024:#Update this order will be assigned to a local surveyor within the next 10 working days who will contact the customer and arrange a site visit to discuss method of service. We will continue to update as we receive them, Following review, it has been assigned a Type3 due to site location, please remove from T1 schedule as advised from Allwyn 18/6/2024:#Update this order will be assigned to a local surveyor within the next 10 working days who will contact the customer and arrange a site visit to discuss method of service. We will continue to update as we receive them 17/6/2024:#Update this order will be assigned to a local surveyor within the next 10 working days who will contact the customer and arrange a site visit to discuss method of service. We will continue to update as we receive them 14/6/2024:#Update this order will be assigned to a local surveyor within the next 10 working days who will contact the customer and arrange a site visit to discuss method of service. We will continue to update as we receive them 13/6/2024:#Update this order will be assigned to a local surveyor within the next 10 working days who will contact the customer and arrange a site visit to discuss method of service. We will continue to update as we receive them 12/6/2024:#Update this order will be assigned to a local surveyor within the next 10 working days who will contact the customer and arrange a site visit to discuss method of service. We will continue to update as we receive them 11/6/2024:0 10/6/2024:0 7/6/2024:0 | 19/7/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_18/7/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_17/7/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_16/7/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_15/7/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_12/7/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_11/7/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_10/7/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_9/7/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_4/7/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_3/7/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_2/7/2024:0 _x000D_1/7/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_27/6/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_25/6/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_24/6/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_20/6/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_19/6/2024:#Update this order will be assigned to a local surveyor within the next 10 working days who will contact the customer and arrange a site visit to discuss method of service. We will continue to update as we receive them, Following review, it has been assigned a Type3 due to site location, please remove from T1 schedule as advised from Allwyn 18/6/2024:#Update this order will be assigned to a local surveyor within the next 10 working days who will contact the customer and arrange a site visit to discuss method of service. We will continue to update as we receive them 17/6/2024:#Update this order will be assigned to a local surveyor within the next 10 working days who will contact the customer and arrange a site visit to discuss method of service. We will continue to update as we receive them 14/6/2024:#Update this order will be assigned to a local surveyor within the next 10 working days who will contact the customer and arrange a site visit to discuss method of service. We will continue to update as we receive them 13/6/2024:#Update this order will be assigned to a local surveyor within the next 10 working days who will contact the customer and arrange a site visit to discuss method of service. We will continue to update as we receive them 12/6/2024:#Update this order will be assigned to a local surveyor within the next 10 working days who will contact the customer and arrange a site visit to discuss method of service. We will continue to update as we receive them 11/6/2024:0 10/6/2024:0 7/6/2024:0 | [6 empty] | 3.Allwyn to arrange rtr install | VFP2338475 | 30015465 | 6.Failed router install | AM |  | 2024-06-04 | 2024-06-04 | 2024-06-04 | TRUE | [7 empty] | 2024-07-02 | 242005010402 |  | 2024-07-04 | 1
359 | 430313 | 1350 | Batch 4 Jun24 | Type 3 | FTTP | MACE | BELFAST | BT12 6BA | 2024-06-07 | 6/9/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_5/9/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_4/9/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_3/9/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_2/9/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_29/8/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_28/8/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_27/8/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_22/8/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_21/8/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_20/8/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_19/8/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_19/8/2024:01374527 _x000D_16/8/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_15/8/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_14/8/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_13/8/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_12/8/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_9/8/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_8/8/2024:19/06/2024 _x000D_6/8/2024:19/06/2024 _x000D_5/8/2024:19/06/2024 _x000D_2/8/2024:19/06/2024 _x000D_1/8/2024:19/06/2024 _x000D_31/7/2024:19/06/2024 _x000D_31/7/2024:19/06/2024 _x000D_30/7/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_29/7/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_29/7/2024:01374527 _x000D_26/7/2024:01374527 _x000D_24/7/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_23/7/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_22/7/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_22/7/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:Update: Order Amended _x000D_25/6/2024:Update: Order Amended _x000D_24/6/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 27/06/2024.We will continue to provide update as they become available. _x000D_20/6/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 27/06/2024.We will continue to provide update as they become available. _x000D_19/6/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 27/06/2024.We will continue to provide update as they become available. _x000D_18/6/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 27/06/2024.We will continue to provide update as they become available. _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:Survey required. Potential complex internal solution required. Please refer to the engineers notes and provide a solution _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_6/9/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_5/9/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_4/9/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_3/9/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_2/9/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_29/8/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_28/8/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_27/8/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_22/8/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_21/8/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_20/8/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_19/8/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_19/8/2024:01374527 _x000D_16/8/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_15/8/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_14/8/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_13/8/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_12/8/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_9/8/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_8/8/2024:19/06/2024 _x000D_6/8/2024:19/06/2024 _x000D_5/8/2024:19/06/2024 _x000D_2/8/2024:19/06/2024 _x000D_1/8/2024:19/06/2024 _x000D_31/7/2024:19/06/2024 _x000D_31/7/2024:19/06/2024 _x000D_30/7/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_29/7/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_29/7/2024:01374527 _x000D_26/7/2024:01374527 _x000D_24/7/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_23/7/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_22/7/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_22/7/2024:#Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:Update: Order Amended _x000D_25/6/2024:Update: Order Amended _x000D_24/6/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 27/06/2024.We will continue to provide update as they become available. _x000D_20/6/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 27/06/2024.We will continue to provide update as they become available. _x000D_19/6/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 27/06/2024.We will continue to provide update as they become available. _x000D_18/6/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 27/06/2024.We will continue to provide update as they become available. _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:Survey required. Potential complex internal solution required. Please refer to the engineers notes and provide a solution _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update job has been sent to survey team to identify alternate routing. Once survey is complete order will be progressed further. Update due 4/07 |  |  |  |  | 3.Allwyn to arrange rtr install | VFP2338477 | 30015573 | 2.Commissioning | AM | [8 empty] | 2024-07-25 | [7 empty] | 0
360 | 485097 | 1352 | Batch 4 Jun24 | Type 1 | SOGEA | Mace | Strabane | BT82 9EF | 2024-06-07 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFS984911 | 30015623 | 6.Failed router install | AM |  | 2024-06-04 | 2024-06-04 | 2024-06-04 | TRUE | [7 empty] | 2024-07-03 | 242005010409 |  | 2024-07-04 | 1
361 | 634371 | 1354 | Batch 4 Jun24 | Type 1 | SOGEA | Centra | L'Derry | BT48 6BU | 2024-06-07 | 19/7/2024:#Update Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 26/07/2024.We will continue to provide update as they become available. _x000D_18/7/2024:#Update - order cancelled by Openreach because customer was unaware of the order and didn't want it at this stage. _x000D_17/7/2024:#Update - order cancelled by Openreach because customer was unaware of the order and didn't want it at this stage. _x000D_16/7/2024:#Update - order cancelled by Openreach because customer was unaware of the order and didn't want it at this stage. _x000D_15/7/2024:#Update - order cancelled by Openreach because customer was unaware of the order and didn't want it at this stage. _x000D_12/7/2024:#Update - order cancelled by Openreach because customer was unaware of the order and didn't want it at this stage. _x000D_11/7/2024:#Update - order cancelled by Openreach because customer was unaware of the order and didn't want it at this stage. _x000D_10/7/2024:#Update - order cancelled by Openreach because customer was unaware of the order and didn't want it at this stage. _x000D_9/7/2024:#Update - order cancelled by Openreach because customer was unaware of the order and didn't want it at this stage. _x000D_4/7/2024:#Update - order cancelled by Openreach because customer was unaware of the order and didn't want it at this stage. _x000D_3/7/2024:#Update - order cancelled by Openreach because customer was unaware of the order and didn't want it at this stage. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - order cancelled by Openreach because customer was unaware of the order and didn't want it at this stage. _x000D_27/6/2024:#Update - order cancelled by Openreach because customer was unaware of the order and didn't want it at this stage. _x000D_25/6/2024:#Update - order cancelled by Openreach because customer was unaware of the order and didn't want it at this stage. _x000D_24/6/2024:#Update - order cancelled by Openreach because customer was unaware of the order and didn't want it at this stage. _x000D_20/6/2024:#Update - order cancelled by Openreach because customer was unaware of the order and didn't want it at this stage. _x000D_19/6/2024:#Update - order cancelled by Openreach because customer was unaware of the order and didn't want it at this stage. _x000D_18/6/2024:#Update - order cancelled by Openreach because customer was unaware of the order and didn't want it at this stage. _x000D_17/6/2024:#Update - order cancelled by Openreach because customer was unaware of the order and didn't want it at this stage. _x000D_14/6/2024:PICKED UP BY SURVEY CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_13/6/2024:PICKED UP BY SURVEY CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/6/2024:PICKED UP BY SURVEY CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:#Update Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 26/07/2024.We will continue to provide update as they become available. _x000D_18/7/2024:#Update - order cancelled by Openreach because customer was unaware of the order and didn't want it at this stage. _x000D_17/7/2024:#Update - order cancelled by Openreach because customer was unaware of the order and didn't want it at this stage. _x000D_16/7/2024:#Update - order cancelled by Openreach because customer was unaware of the order and didn't want it at this stage. _x000D_15/7/2024:#Update - order cancelled by Openreach because customer was unaware of the order and didn't want it at this stage. _x000D_12/7/2024:#Update - order cancelled by Openreach because customer was unaware of the order and didn't want it at this stage. _x000D_11/7/2024:#Update - order cancelled by Openreach because customer was unaware of the order and didn't want it at this stage. _x000D_10/7/2024:#Update - order cancelled by Openreach because customer was unaware of the order and didn't want it at this stage. _x000D_9/7/2024:#Update - order cancelled by Openreach because customer was unaware of the order and didn't want it at this stage. _x000D_4/7/2024:#Update - order cancelled by Openreach because customer was unaware of the order and didn't want it at this stage. _x000D_3/7/2024:#Update - order cancelled by Openreach because customer was unaware of the order and didn't want it at this stage. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - order cancelled by Openreach because customer was unaware of the order and didn't want it at this stage. _x000D_27/6/2024:#Update - order cancelled by Openreach because customer was unaware of the order and didn't want it at this stage. _x000D_25/6/2024:#Update - order cancelled by Openreach because customer was unaware of the order and didn't want it at this stage. _x000D_24/6/2024:#Update - order cancelled by Openreach because customer was unaware of the order and didn't want it at this stage. _x000D_20/6/2024:#Update - order cancelled by Openreach because customer was unaware of the order and didn't want it at this stage. _x000D_19/6/2024:#Update - order cancelled by Openreach because customer was unaware of the order and didn't want it at this stage. _x000D_18/6/2024:#Update - order cancelled by Openreach because customer was unaware of the order and didn't want it at this stage. _x000D_17/6/2024:#Update - order cancelled by Openreach because customer was unaware of the order and didn't want it at this stage. _x000D_14/6/2024:PICKED UP BY SURVEY CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_13/6/2024:PICKED UP BY SURVEY CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/6/2024:PICKED UP BY SURVEY CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFS984914 | 30015536 | 2.Commissioning | AM |  | 2024-06-04 | 2024-06-04 | 2024-06-04 | TRUE |  |  |  | 2024-07-03 | [7 empty] | 0
362 | 232930 | 1355 | Batch 4 Jun24 | Type 1 | FTTP/Mobile | Costcutter | LIMAVADY | BT49 0PB | 2024-06-07 | 6/9/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_5/9/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_4/9/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_3/9/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_2/9/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_29/8/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_28/8/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_27/8/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_22/8/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_21/8/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_20/8/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_19/8/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_19/8/2024:01424798 _x000D_16/8/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_15/8/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_14/8/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_13/8/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_12/8/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_9/8/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_8/8/2024:29/07/2024 _x000D_6/8/2024:29/07/2024 _x000D_5/8/2024:29/07/2024 _x000D_2/8/2024:29/07/2024 _x000D_1/8/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_30/7/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_29/7/2024:#Update Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 26/07/2024.We will continue to provide update as they become available. _x000D_29/7/2024:01501594 _x000D_26/7/2024:01501594 _x000D_24/7/2024:#Update Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 26/07/2024.We will continue to provide update as they become available. _x000D_23/7/2024:#Update Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 26/07/2024.We will continue to provide update as they become available. _x000D_22/7/2024:#Update Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 26/07/2024.We will continue to provide update as they become available. _x000D_22/7/2024:#Update Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 26/07/2024.We will continue to provide update as they become available. _x000D_7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 9/9/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_6/9/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_5/9/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_4/9/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_3/9/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_2/9/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_29/8/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_28/8/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_27/8/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_22/8/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_21/8/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_20/8/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_19/8/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_19/8/2024:01424798 _x000D_16/8/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_15/8/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_14/8/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_13/8/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_12/8/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_9/8/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_8/8/2024:29/07/2024 _x000D_6/8/2024:29/07/2024 _x000D_5/8/2024:29/07/2024 _x000D_2/8/2024:29/07/2024 _x000D_1/8/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_30/7/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_29/7/2024:#Update Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 26/07/2024.We will continue to provide update as they become available. _x000D_29/7/2024:01501594 _x000D_26/7/2024:01501594 _x000D_24/7/2024:#Update Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 26/07/2024.We will continue to provide update as they become available. _x000D_23/7/2024:#Update Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 26/07/2024.We will continue to provide update as they become available. _x000D_22/7/2024:#Update Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 26/07/2024.We will continue to provide update as they become available. _x000D_22/7/2024:#Update Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 26/07/2024.We will continue to provide update as they become available. _x000D_7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 0 | #Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. |  |  |  |  | 2.Allwyn to arrange access | VFP2392620 | 30015458 | 1.Provisioning | AM |  | 2024-06-04 | 2024-06-04 |  | 0 | [11 empty] | 0
363 | 487417 | 1359 | Batch 4 Jun24 | Type 1 | SOGEA | Premier | Belfast | BT17 0FL | 2024-06-07 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFS984915 | 30015419 | 6.Failed router install | AM |  | 2024-06-04 | 2024-06-04 | 2024-06-04 | TRUE | [7 empty] | 2024-07-01 | 23A004953004 |  | 2024-07-02 | 1
364 | 417443 | 1363 | Batch 4 Jun24 | Type 1 | SOGEA | CENTRA | LONDONDERRY | BT48 7PB | 2024-06-07 | 27/6/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_25/6/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_24/6/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_20/6/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_19/6/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_18/6/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_17/6/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_14/6/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_13/6/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_12/6/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 27/6/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_25/6/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_24/6/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_20/6/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_19/6/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_18/6/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_17/6/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_14/6/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_13/6/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_12/6/2024:#Update - Order has been delayed as survey work is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2338487 | 30015367 | 2.Commissioning | AM |  | 2024-06-04 | 2024-06-04 | 2024-06-04 | TRUE |  |  |  | 2024-07-03 | [7 empty] | 0
365 | 458691 | 1365 | Batch 4 Jun24 | Type 1 | SOGEA | Donard View SS | BALLYNAHINCH | BT24 8XS | 2024-06-26 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Update: Order Completed by Supplier _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Update: Order Completed by Supplier _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2338489 | 30015497 | 6.Failed router install | AM |  | 2024-06-04 | 2024-06-25 | 2024-06-25 | TRUE |  |  |  | 2024-07-25 |  |  |  | 2024-07-25 | 242005010447 |  | 2024-07-26 | 1
366 | 475756 | 1367 | Batch 4 Jun24 | Type 1 | SOGEA | Moor Park Filling Station | Belfast | BT10 0NF | 2024-06-07 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFS984917 | 30015300 | 2.Commissioning | AM |  | 2024-06-04 | 2024-06-04 | 2024-06-04 | TRUE |  |  |  | 2024-07-01 | [7 empty] | 0
367 | 424030 | 1539 | Batch 4 Jun24 | Type 1 | SoGEA/Mobile | Spar Stores | Oldham | OL8 3HH | 2024-06-07 | 6/9/2024:#Update - Awaiting an update from Allwyn on when the ATM company can attend a joint meet with Openreach _x000D_5/9/2024:#Update - Awaiting an update from Allwyn on when the ATM company can attend a joint meet with Openreach _x000D_4/9/2024:#Update - Awaiting an update from Allwyn on when the ATM company can attend a joint meet with Openreach _x000D_3/9/2024:#Update - Awaiting an update from Allwyn on when the ATM company can attend a joint meet with Openreach _x000D_2/9/2024:#Update - Awaiting an update from Allwyn on when the ATM company can attend a joint meet with Openreach _x000D_29/8/2024:#Update - Awaiting an update from Allwyn on when the ATM company can attend a joint meet with Openreach _x000D_28/8/2024:#Update - Awaiting an update from Allwyn on when the ATM company can attend a joint meet with Openreach _x000D_27/8/2024:#Update - Awaiting an update from Allwyn on when the ATM company can attend a joint meet with Openreach _x000D_22/8/2024:#Update - Awaiting an update from Allwyn on when the ATM company can attend a joint meet with Openreach _x000D_21/8/2024:#Update - NFA - Retailer and ATM Company visit scheduled for 08/08- 9am - Allwyn confirmed with retailer _x000D_20/8/2024:#Update - NFA - Retailer and ATM Company visit scheduled for 08/08- 9am - Allwyn confirmed with retailer _x000D_19/8/2024:#Update - NFA - Retailer and ATM Company visit scheduled for 08/08- 9am - Allwyn confirmed with retailer _x000D_19/8/2024:01371778 _x000D_16/8/2024:#Update - NFA - Retailer and ATM Company visit scheduled for 08/08- 9am - Allwyn confirmed with retailer _x000D_15/8/2024:#Update - NFA - Retailer and ATM Company visit scheduled for 08/08- 9am - Allwyn confirmed with retailer _x000D_14/8/2024:#Update - NFA - Retailer and ATM Company visit scheduled for 08/08- 9am - Allwyn confirmed with retailer _x000D_13/8/2024:#Update - NFA - Retailer and ATM Company visit scheduled for 08/08- 9am - Allwyn confirmed with retailer _x000D_12/8/2024:#Update - NFA - Retailer and ATM Company visit scheduled for 08/08- 9am - Allwyn confirmed with retailer _x000D_9/8/2024:#Update - NFA - Retailer and ATM Company visit scheduled for 08/08- 9am - Allwyn confirmed with retailer _x000D_8/8/2024:19/07/2024 _x000D_6/8/2024:19/07/2024 _x000D_5/8/2024:19/07/2024 _x000D_2/8/2024:19/07/2024 _x000D_1/8/2024:19/07/2024 _x000D_31/7/2024:19/07/2024 _x000D_31/7/2024:19/07/2024 _x000D_30/7/2024:#Update - NFA - Retailer and ATM Company visit scheduled for 08/08- 9am - Allwyn confirmed with retailer _x000D_29/7/2024:#Update - NFA - Retailer and ATM Company visit scheduled for 08/08- 9am - Allwyn confirmed with retailer _x000D_29/7/2024:01371778 _x000D_26/7/2024:01371778 _x000D_24/7/2024:#Update - NFA - Retailer and ATM Company visit scheduled for 08/08- 9am - Allwyn confirmed with retailer _x000D_23/7/2024:#Update - NFA - Retailer and ATM Company visit scheduled for 08/08- 9am - Allwyn confirmed with retailer _x000D_22/7/2024:#Update - NFA - Retailer and ATM Company visit scheduled for 08/08- 9am - Allwyn confirmed with retailer _x000D_22/7/2024:Update: Order Amended _x000D_7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 9/9/2024:#Update - Awaiting an update from Allwyn on when the ATM company can attend a joint meet with Openreach _x000D_6/9/2024:#Update - Awaiting an update from Allwyn on when the ATM company can attend a joint meet with Openreach _x000D_5/9/2024:#Update - Awaiting an update from Allwyn on when the ATM company can attend a joint meet with Openreach _x000D_4/9/2024:#Update - Awaiting an update from Allwyn on when the ATM company can attend a joint meet with Openreach _x000D_3/9/2024:#Update - Awaiting an update from Allwyn on when the ATM company can attend a joint meet with Openreach _x000D_2/9/2024:#Update - Awaiting an update from Allwyn on when the ATM company can attend a joint meet with Openreach _x000D_29/8/2024:#Update - Awaiting an update from Allwyn on when the ATM company can attend a joint meet with Openreach _x000D_28/8/2024:#Update - Awaiting an update from Allwyn on when the ATM company can attend a joint meet with Openreach _x000D_27/8/2024:#Update - Awaiting an update from Allwyn on when the ATM company can attend a joint meet with Openreach _x000D_22/8/2024:#Update - Awaiting an update from Allwyn on when the ATM company can attend a joint meet with Openreach _x000D_21/8/2024:#Update - NFA - Retailer and ATM Company visit scheduled for 08/08- 9am - Allwyn confirmed with retailer _x000D_20/8/2024:#Update - NFA - Retailer and ATM Company visit scheduled for 08/08- 9am - Allwyn confirmed with retailer _x000D_19/8/2024:#Update - NFA - Retailer and ATM Company visit scheduled for 08/08- 9am - Allwyn confirmed with retailer _x000D_19/8/2024:01371778 _x000D_16/8/2024:#Update - NFA - Retailer and ATM Company visit scheduled for 08/08- 9am - Allwyn confirmed with retailer _x000D_15/8/2024:#Update - NFA - Retailer and ATM Company visit scheduled for 08/08- 9am - Allwyn confirmed with retailer _x000D_14/8/2024:#Update - NFA - Retailer and ATM Company visit scheduled for 08/08- 9am - Allwyn confirmed with retailer _x000D_13/8/2024:#Update - NFA - Retailer and ATM Company visit scheduled for 08/08- 9am - Allwyn confirmed with retailer _x000D_12/8/2024:#Update - NFA - Retailer and ATM Company visit scheduled for 08/08- 9am - Allwyn confirmed with retailer _x000D_9/8/2024:#Update - NFA - Retailer and ATM Company visit scheduled for 08/08- 9am - Allwyn confirmed with retailer _x000D_8/8/2024:19/07/2024 _x000D_6/8/2024:19/07/2024 _x000D_5/8/2024:19/07/2024 _x000D_2/8/2024:19/07/2024 _x000D_1/8/2024:19/07/2024 _x000D_31/7/2024:19/07/2024 _x000D_31/7/2024:19/07/2024 _x000D_30/7/2024:#Update - NFA - Retailer and ATM Company visit scheduled for 08/08- 9am - Allwyn confirmed with retailer _x000D_29/7/2024:#Update - NFA - Retailer and ATM Company visit scheduled for 08/08- 9am - Allwyn confirmed with retailer _x000D_29/7/2024:01371778 _x000D_26/7/2024:01371778 _x000D_24/7/2024:#Update - NFA - Retailer and ATM Company visit scheduled for 08/08- 9am - Allwyn confirmed with retailer _x000D_23/7/2024:#Update - NFA - Retailer and ATM Company visit scheduled for 08/08- 9am - Allwyn confirmed with retailer _x000D_22/7/2024:#Update - NFA - Retailer and ATM Company visit scheduled for 08/08- 9am - Allwyn confirmed with retailer _x000D_22/7/2024:Update: Order Amended _x000D_7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 0 | #Update - Awaiting an update from Allwyn on when the ATM company can attend a joint meet with Openreach | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFS1001135 | 30015567 | 1.Provisioning | AM |  | 2024-06-04 | 2024-08-08 |  | 0 | [11 empty] | 0
368 | 649538 | 1768 | Batch 4 Jun24 | Type 1 | SOGEA | Bestone | Audenshaw | M34 5DE | 2024-06-07 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983302 | 30015239 | 2.Commissioning | AM |  | 2024-06-04 | 2024-06-04 | 2024-06-04 | TRUE |  |  |  | 2024-07-09 | [7 empty] | 0
369 | 660882 | 1772 | Batch 4 Jun24 | Type 1 | SOGEA | V&C Stores | Inverness | IV3 8HU | 2024-06-07 | 20/6/2024:#Update - Order has now been complete _x000D_19/6/2024:#Update - Order has now been complete _x000D_18/6/2024:#Update - Tree cutting will be required as cannot see line of slight for where the cable is and the DP. This site also requires a flat roof engineer and a new line through the roof ceiling. _x000D_17/6/2024:#Update - Order has been delayed as tree cutting is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_14/6/2024:#Update - Order has been delayed as tree cutting is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_13/6/2024:#Update - Order has been delayed as tree cutting is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_12/6/2024:#Update - Order has been delayed as tree cutting is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_10/6/2024:#Update - Order has been delayed as tree cutting is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_7/6/2024:#Update - Order has been delayed as tree cutting is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_6/6/2024:#Update - Order has been delayed as tree cutting is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_5/6/2024:Your order has been delayed due to tree cutting is required, order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 11/06/2024. _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 20/6/2024:#Update - Order has now been complete _x000D_19/6/2024:#Update - Order has now been complete _x000D_18/6/2024:#Update - Tree cutting will be required as cannot see line of slight for where the cable is and the DP. This site also requires a flat roof engineer and a new line through the roof ceiling. _x000D_17/6/2024:#Update - Order has been delayed as tree cutting is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_14/6/2024:#Update - Order has been delayed as tree cutting is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_13/6/2024:#Update - Order has been delayed as tree cutting is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_12/6/2024:#Update - Order has been delayed as tree cutting is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_10/6/2024:#Update - Order has been delayed as tree cutting is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_7/6/2024:#Update - Order has been delayed as tree cutting is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_6/6/2024:#Update - Order has been delayed as tree cutting is required, this has been passed onto the controls team to assign an engineer. CSL will update as more information become available. _x000D_5/6/2024:Your order has been delayed due to tree cutting is required, order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 11/06/2024. _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983305 | 30015186 | 6.Failed router install | AM |  | 2024-06-04 | 2024-06-04 | 2024-06-04 | TRUE | [7 empty] | 2024-07-01 | 23A004945517 |  | 2024-07-02 | 1
370 | 664499 | 1867 | Batch 4 Jun24 | Type 1 | FTTP | Trelander Stores & Off Licence | Truro | TR1 1FX | 2024-06-07 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2338444 | 30015787 | 2.Commissioning | AM |  | 2024-06-04 | 2024-06-04 | 2024-06-04 | TRUE |  |  |  | 2024-06-27 | [7 empty] | 0
371 | 669424 | 1894 | Batch 4 Jun24 | Type 1 | SOGEA | Post Office | GRIMSBY | DN34 5NU | 2024-06-07 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996767 | 30016068 | 2.Commissioning | AM |  | 2024-06-04 | 2024-06-04 | 2024-06-04 | TRUE |  |  |  | 2024-07-09 | [7 empty] | 0
372 | 652190 | 1935 | Batch 4 Jun24 | Type 1 | FTTP | Spar | Preston | PR5 5AE | 2024-06-07 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996772 | 30016074 | 2.Commissioning | AM |  | 2024-06-04 | 2024-06-04 | 2024-06-05 | TRUE |  |  |  | 2024-07-09 | [7 empty] | 0
373 | 656975 | 1944 | Batch 4 Jun24 | Type 1 | SOGEA | Spar | Boston | PE21 7DQ | 2024-06-07 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Update: Order Completed by Supplier _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:Order Rejected: Service Incompatible for input CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/05/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Update: Order Completed by Supplier _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:Order Rejected: Service Incompatible for input CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996773 | 30016001 | 6.Failed router install | AM |  | 2024-06-04 | 2024-06-04 | 2024-06-06 | TRUE |  |  |  | 2024-07-28 |  |  |  | 2024-07-25 | 23A004948815 |  | 2024-07-26 | 1
374 | 644692 | 1946 | Batch 4 Jun24 | Type 1 | SOGEA | SPAR | Maryport | CA15 6LW | 2024-06-07 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2353525 | 30015992 | 2.Commissioning | AM |  | 2024-06-04 | 2024-06-04 | 2024-06-04 | TRUE |  |  |  | 2024-07-08 | [7 empty] | 0
375 | 669973 | 1948 | Batch 4 Jun24 | Type 1 | SOGEA | Spar | PLYMOUTH | PL3 6HJ | 2024-06-07 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Update: Order Completed by Supplier _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Update: Order Completed by Supplier _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996776 | 30016036 | 2.Commissioning | AM |  | 2024-06-04 | 2024-06-04 | 2024-06-04 | TRUE |  |  |  | 2024-06-26 | [7 empty] | 0
376 | 613635 | 1967 | Batch 4 Jun24 | Type 1 | SOGEA | Spar | Londonderry | BT47 4HR | 2024-06-07 | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:Update: Order Amended _x000D_25/6/2024:Update: Order Amended _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_7/6/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_6/6/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_5/6/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:Update: Order Amended _x000D_25/6/2024:Update: Order Amended _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_7/6/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_6/6/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_5/6/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2353430 | 30015943 | 2.Commissioning | AM |  | 2024-06-04 | 2024-06-04 | 2024-06-04 | TRUE |  |  |  | 2024-07-03 | [7 empty] | 0
377 | 617680 | 1971 | Batch 4 Jun24 | Type 1 | SOGEA | Spar | Auckley | DN9 3HY | 2024-07-11 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Update: Order Completed by Supplier _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:Update: Order Completed by Supplier _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFS996777 | 30015977 | 6.Failed router install | AM |  | 2024-06-04 | 2024-07-10 | 2024-07-10 | TRUE |  |  |  | 2024-07-31 |  |  |  | 2024-07-31 | 242005008783 |  | 2024-08-01 | 1
378 | 469263 | 1992 | Batch 4 Jun24 | Type 1 | SOGEA | Spar | Cupar | KY15 7JS | 2024-06-07 | 29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1065626 | 30022050 | 2.Commissioning | AM |  | 2024-06-04 | 2024-06-04 | 2024-06-04 | TRUE |  |  |  | 2024-06-25 | [7 empty] | 0
379 | 607163 | 1116 | Batch 4 Jun24 | Type 1 | SOGEA | Fulbar Stores | Paisley | PA2 0EG | 2024-06-07 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996780 | 30016000 | 6.Failed router install | AM |  | 2024-06-04 | 2024-06-04 | 2024-06-04 | TRUE | [7 empty] | 2024-06-26 | 23A004945516 |  | 2024-07-01 | 1
380 | 649052 | 446 | Batch 3 May24 | Type 1 | SOGEA | Tharany Express | London | SW8 2JR | 2024-06-06 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:Your order has been delayed due to a customer missed appointment. Customer not received router. Please check with end user and reappoint the order if still required. _x000D_08/05/2024: Delay on Engineer activities. Wait for further update to confirm re-appointing 08/04/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:Your order has been delayed due to a customer missed appointment. Customer not received router. Please check with end user and reappoint the order if still required. _x000D_08/05/2024: Delay on Engineer activities. Wait for further update to confirm re-appointing 08/04/2024: New order added to report |  |  | 2024-05-07 | 07/05/2024: Action for Allwyn: Please confirm with the retailer what date would be suitable, then CSL will reappoint. |  |  | 3.Allwyn to arrange rtr install | VFP2300643 | 30013336 | 6.Failed router install | AM |  | 2024-05-03 | 2024-06-05 | 2024-06-05 | TRUE | [7 empty] | 2024-07-01 | 242005011068 |  | 2024-07-04 | 1
381 | 487303 | 1377 | Batch 4 Jun24 | Type 1 | FTTP | Eldred Drive Stores | Orpington | BR5 4PE | 2024-06-07 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2338493 | 30015586 | 2.Commissioning | AM |  | 2024-06-05 | 2024-06-05 | 2024-06-05 | TRUE |  |  |  | 2024-07-05 | [7 empty] | 0
382 | 611073 | 1388 | Batch 4 Jun24 | Type 1 | SOGEA | Premier Lundwood Convenience Store | Barnsley | S71 5HS | 2024-06-07 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFS984933 | 30015398 | 2.Commissioning | AM |  | 2024-06-05 | 2024-06-05 | 2024-06-05 | TRUE |  |  |  | 2024-07-08 | [7 empty] | 0
383 | 607266 | 1391 | Batch 4 Jun24 | Type 1 | SOGEA | Premier The Shop On The Corner | Plymouth | PL5 1RD | 2024-06-07 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Update: Order Completed by Supplier _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Update: Order Completed by Supplier _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFS984936 | 30015402 | 2.Commissioning | AM |  | 2024-06-05 | 2024-06-05 | 2024-06-05 | TRUE |  |  |  | 2024-06-26 | [7 empty] | 0
384 | 438549 | 1393 | Batch 4 Jun24 | Type 1 | SOGEA | Beccles Road Supermarket | GREAT YARMOUTH | NR31 0PS | 2024-06-07 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFS984937 | 30015641 | 2.Commissioning | AM |  | 2024-06-05 | 2024-06-05 | 2024-06-05 | TRUE |  |  |  | 2024-07-01 | [7 empty] | 0
385 | 465017 | 1395 | Batch 4 Jun24 | Type 1 | SOGEA | Premier Atwal Convenience Store | BELLSHILL | ML4 2JG | 2024-06-07 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984939 | 30015305 | 2.Commissioning | AM |  | 2024-06-05 | 2024-06-05 | 2024-06-05 | TRUE |  |  |  | 2024-06-26 | [7 empty] | 0
386 | 430496 | 1398 | Batch 4 Jun24 | Type 1 | SOGEA | Mayfield Grocers Ltd | GLASGOW | G20 9RF | 2024-06-07 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Update: Order Completed by Supplier _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Update: Order Completed by Supplier _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984941 | 30015506 | 6.Failed router install | AM |  | 2024-06-05 | 2024-06-05 | 2024-06-05 | TRUE | [7 empty] | 2024-06-26 | 23A004945520 |  | 2024-07-01 | 1
387 | 618682 | 1775 | Batch 4 Jun24 | Type 1 | SOGEA | Londis Lower House Lane | Cheshire | WA8 7DU | 2024-06-07 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983308 | 30015210 | 6.Failed router install | AM |  | 2024-06-05 | 2024-06-05 | 2024-06-05 | TRUE |  |  |  | 2024-07-08 |  |  |  | 2024-07-08 | 242005013555 |  |  | 1
388 | 103972 | 1780 | Batch 4 Jun24 | Type 1 | SOGEA | Danby and Co | YORK | YO42 2AP | 2024-06-07 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:Your order requires planning validation. We may contact your customer if we need to. You will receive a further update by 29-05-2024. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_02/05/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:Your order requires planning validation. We may contact your customer if we need to. You will receive a further update by 29-05-2024. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983313 | 30015209 | 2.Commissioning | AM |  | 2024-06-05 | 2024-06-05 | 2024-06-05 | TRUE |  |  |  | 2024-07-09 | [7 empty] | 0
389 | 656753 | 1783 | Batch 4 Jun24 | Type 1 | SOGEA | Cairnside Premier | Sunderland | SR3 3LS | 2024-06-07 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983316 | 30015207 | 2.Commissioning | AM |  | 2024-06-05 | 2024-06-05 | 2024-06-05 | TRUE |  |  |  | 2024-06-28 | [7 empty] | 0
390 | 664350 | 1227 | Batch 4 Jun24 | Type 1 | SOGEA | Spar Stores | Londonderry | BT48 8JJ | 2024-06-07 | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 04/07/2024. We will continue to provide update as they become available. _x000D_19/6/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 04/07/2024. We will continue to provide update as they become available. _x000D_18/6/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 04/07/2024. We will continue to provide update as they become available. _x000D_17/6/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 04/07/2024. We will continue to provide update as they become available. _x000D_14/6/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 04/07/2024. We will continue to provide update as they become available. _x000D_13/6/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 17/06/2024. We will continue to provide update as they become available. _x000D_12/6/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 17/06/2024. We will continue to provide update as they become available. _x000D_10/6/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 17/06/2024. We will continue to provide update as they become available. _x000D_7/6/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 17/06/2024. We will continue to provide update as they become available. _x000D_6/6/2024:Supplier Delay: Issues relating to permission to provide the network, please await for further details. _x000D_5/6/2024:Supplier Delay: Issues relating to permission to provide the network, please await for further details. _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 04/07/2024. We will continue to provide update as they become available. _x000D_19/6/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 04/07/2024. We will continue to provide update as they become available. _x000D_18/6/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 04/07/2024. We will continue to provide update as they become available. _x000D_17/6/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 04/07/2024. We will continue to provide update as they become available. _x000D_14/6/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 04/07/2024. We will continue to provide update as they become available. _x000D_13/6/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 17/06/2024. We will continue to provide update as they become available. _x000D_12/6/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 17/06/2024. We will continue to provide update as they become available. _x000D_10/6/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 17/06/2024. We will continue to provide update as they become available. _x000D_7/6/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 17/06/2024. We will continue to provide update as they become available. _x000D_6/6/2024:Supplier Delay: Issues relating to permission to provide the network, please await for further details. _x000D_5/6/2024:Supplier Delay: Issues relating to permission to provide the network, please await for further details. _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2353431 | 30015959 | 2.Commissioning | AM |  | 2024-06-05 | 2024-06-05 | 2024-06-05 | TRUE |  |  |  | 2024-07-03 | [7 empty] | 0
391 | 664352 | 1325 | Batch 4 Jun24 | Type 1 | FTTP | Spar Stores | Bolton | BL2 5BP | 2024-07-03 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:Order Completed _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 | 06/06/2024: CSL to provide an update |  |  | 5.CSL | VFP2353433 | 30015964 | 2.Commissioning | AM |  | 2024-06-05 | 2024-07-02 | 2024-07-02 | TRUE |  |  |  | 2024-08-07 | [7 empty] | 0
392 | 666350 | 1397 | Batch 4 Jun24 | Type 1 | FTTP | Spar Southalls Lanesfield | Wolverhampton | WV4 6NR | 2024-06-07 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2353434 | 30015950 | 6.Failed router install | AM |  | 2024-06-05 | 2024-06-05 | 2024-06-05 | TRUE | [7 empty] | 2024-06-27 | 23A004945834 |  | 2024-07-02 | 1
393 | 664775 | 1485 | Batch 4 Jun24 | Type 1 | SoGEA/Mobile | Mickeys Newsagents | Stoke-on-Trent | ST6 6SH | 2024-07-18 | 6/9/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_5/9/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_4/9/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_3/9/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_2/9/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_29/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_28/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_27/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_22/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_21/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_20/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_19/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_19/8/2024:01424442 _x000D_16/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_15/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_14/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_13/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_12/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_9/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_8/8/2024:01/08/2024 _x000D_6/8/2024:01/08/2024 _x000D_5/8/2024:01/08/2024 _x000D_2/8/2024:01/08/2024 _x000D_1/8/2024:19/06/2024 _x000D_31/7/2024:19/06/2024 _x000D_31/7/2024:19/06/2024 _x000D_30/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 17/07 AM _x000D_29/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 17/07 AM _x000D_29/7/2024:01424442 _x000D_26/7/2024:01424442 _x000D_24/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 17/07 AM _x000D_23/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 17/07 AM _x000D_22/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 17/07 AM _x000D_22/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 17/07 AM _x000D_7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 9/9/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_6/9/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_5/9/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_4/9/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_3/9/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_2/9/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_29/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_28/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_27/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_22/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_21/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_20/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_19/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_19/8/2024:01424442 _x000D_16/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_15/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_14/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_13/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_12/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_9/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_8/8/2024:01/08/2024 _x000D_6/8/2024:01/08/2024 _x000D_5/8/2024:01/08/2024 _x000D_2/8/2024:01/08/2024 _x000D_1/8/2024:19/06/2024 _x000D_31/7/2024:19/06/2024 _x000D_31/7/2024:19/06/2024 _x000D_30/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 17/07 AM _x000D_29/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 17/07 AM _x000D_29/7/2024:01424442 _x000D_26/7/2024:01424442 _x000D_24/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 17/07 AM _x000D_23/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 17/07 AM _x000D_22/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 17/07 AM _x000D_22/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 17/07 AM _x000D_7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 0 | #Update - ECC proposal sent to Vodafone on 01/08 | 2024-06-07 | 06/06/2024: CSL to provide an update |  |  | 5.CSL | VFS996786 | 30015983 | 1.Provisioning | AM |  | 2024-06-05 | 2024-08-29 |  | 0 | [11 empty] | 0
394 | 664788 | 1506 | Batch 4 Jun24 | Type 1 | SOGEA | Post Office | Doncaster | DN12 1NP | 2024-06-07 | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996790 | 30016029 | 2.Commissioning | AM |  | 2024-06-05 | 2024-06-05 | 2024-06-05 | TRUE |  |  |  | 2024-07-08 | [7 empty] | 0
395 | 435425 | 3501 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Nisa Local Bains | TIPTON | DY4 8EX | 2024-06-06 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:#Update - Retailer has confirmed new appointment. _x000D_21/8/2024:#Update - Retailer has confirmed new appointment. _x000D_20/8/2024:#Update - Retailer has confirmed new appointment. _x000D_19/8/2024:#Update - Retailer has confirmed new appointment. _x000D_19/8/2024:01426574 _x000D_16/8/2024:#Update - Retailer has confirmed new appointment. _x000D_15/8/2024:#Update - Retailer has confirmed new appointment. _x000D_14/8/2024:#Update - Retailer has confirmed new appointment. _x000D_13/8/2024:#Update - Retailer has confirmed new appointment. _x000D_12/8/2024:#Update - Retailer has confirmed new appointment. _x000D_9/8/2024:#Update - Retailer has confirmed new appointment. _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update - Retailer has confirmed new appointment. _x000D_29/7/2024:#Update - Retailer has confirmed new appointment. _x000D_29/7/2024:01426574 _x000D_26/7/2024:01426574 _x000D_24/7/2024:Supplier Delay: Provision of service will be delayed by a scheduled service outage _x000D_23/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 31/07/2024.We will continue to provide update as they become available. _x000D_22/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 23/07/2024.We will continue to provide update as they become available. _x000D_22/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 23/07/2024.We will continue to provide update as they become available. _x000D_10/6/2024:Order Completed _x000D_7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:#Update - Retailer has confirmed new appointment. _x000D_21/8/2024:#Update - Retailer has confirmed new appointment. _x000D_20/8/2024:#Update - Retailer has confirmed new appointment. _x000D_19/8/2024:#Update - Retailer has confirmed new appointment. _x000D_19/8/2024:01426574 _x000D_16/8/2024:#Update - Retailer has confirmed new appointment. _x000D_15/8/2024:#Update - Retailer has confirmed new appointment. _x000D_14/8/2024:#Update - Retailer has confirmed new appointment. _x000D_13/8/2024:#Update - Retailer has confirmed new appointment. _x000D_12/8/2024:#Update - Retailer has confirmed new appointment. _x000D_9/8/2024:#Update - Retailer has confirmed new appointment. _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update - Retailer has confirmed new appointment. _x000D_29/7/2024:#Update - Retailer has confirmed new appointment. _x000D_29/7/2024:01426574 _x000D_26/7/2024:01426574 _x000D_24/7/2024:Supplier Delay: Provision of service will be delayed by a scheduled service outage _x000D_23/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 31/07/2024.We will continue to provide update as they become available. _x000D_22/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 23/07/2024.We will continue to provide update as they become available. _x000D_22/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 23/07/2024.We will continue to provide update as they become available. _x000D_10/6/2024:Order Completed _x000D_7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 0 | 0 | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2363518 | 30016372 | 2.Commissioning | AM |  | 2024-06-05 | 2024-09-02 |  | 0 |  |  |  | 2024-09-20 | [7 empty] | 0
396 | 627181 | 873 | Batch 3 May24 | Type 1 | SOGEA | Best One | West Auckland | DL14 9HE | 2024-06-07 | 19/7/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_18/7/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_17/7/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_16/7/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_15/7/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_12/7/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_11/7/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_10/7/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_9/7/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_4/7/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_3/7/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_27/6/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_25/6/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_24/6/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_20/6/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_19/6/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_18/6/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_17/6/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_14/6/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_13/6/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_12/6/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 19/7/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_18/7/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_17/7/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_16/7/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_15/7/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_12/7/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_11/7/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_10/7/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_9/7/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_4/7/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_3/7/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_27/6/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_25/6/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_24/6/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_20/6/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_19/6/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_18/6/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_17/6/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_14/6/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_13/6/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_12/6/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301070 | 30013763 | 6.Failed router install | AM |  | 2024-05-16 | 2024-06-06 | 2024-06-06 | TRUE | [7 empty] | 2024-07-01 | 242005008875 |  | 2024-07-02 | 1
397 | 647367 | 964 | Batch 3 May24 | Type 1 | SoGEA/Mobile | Shop Local | PORTSMOUTH | PO6 4HE | 2024-07-04 | 6/9/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_5/9/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_4/9/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_3/9/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_2/9/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_29/8/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_28/8/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_27/8/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_22/8/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_21/8/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_20/8/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_19/8/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_19/8/2024:01402457 _x000D_16/8/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_15/8/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_14/8/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_13/8/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_12/8/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_9/8/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_8/8/2024:21/05/2024 _x000D_6/8/2024:21/05/2024 _x000D_5/8/2024:21/05/2024 _x000D_2/8/2024:21/05/2024 _x000D_1/8/2024:21/05/2024 _x000D_31/7/2024:21/05/2024 _x000D_31/7/2024:21/05/2024 _x000D_30/7/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_29/7/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_29/7/2024:01402457 _x000D_26/7/2024:01402457 _x000D_24/7/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_23/7/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_22/7/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_22/7/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_10/6/2024:#Update Pair divert work required. We will continue to provide update as they become available. _x000D_7/6/2024:#Update Pair divert work required. We will continue to provide update as they become available. _x000D_6/6/2024:#Update Pair divert work required. We will continue to provide update as they become available. _x000D_5/6/2024:#Update Pair divert work required. We will continue to provide update as they become available. _x000D_4/6/2024:#Update Pair divert work required. We will continue to provide update as they become available. _x000D_31/5/2024:#Update Pair divert work required. We will continue to provide update as they become available. _x000D_30/5/2024:#Update Pair divert work required. We will continue to provide update as they become available. _x000D_29/5/2024:#Update Pair divert work required. We will continue to provide update as they become available. _x000D_28/5/2024:#Update Pair divert work required. We will continue to provide update as they become available. _x000D_10/5/2024:#Update awaiting a pair divert to be completed. _x000D_08/04/2024: New order added to report | 9/9/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_6/9/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_5/9/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_4/9/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_3/9/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_2/9/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_29/8/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_28/8/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_27/8/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_22/8/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_21/8/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_20/8/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_19/8/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_19/8/2024:01402457 _x000D_16/8/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_15/8/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_14/8/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_13/8/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_12/8/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_9/8/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_8/8/2024:21/05/2024 _x000D_6/8/2024:21/05/2024 _x000D_5/8/2024:21/05/2024 _x000D_2/8/2024:21/05/2024 _x000D_1/8/2024:21/05/2024 _x000D_31/7/2024:21/05/2024 _x000D_31/7/2024:21/05/2024 _x000D_30/7/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_29/7/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_29/7/2024:01402457 _x000D_26/7/2024:01402457 _x000D_24/7/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_23/7/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_22/7/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_22/7/2024:#Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. _x000D_10/6/2024:#Update Pair divert work required. We will continue to provide update as they become available. _x000D_7/6/2024:#Update Pair divert work required. We will continue to provide update as they become available. _x000D_6/6/2024:#Update Pair divert work required. We will continue to provide update as they become available. _x000D_5/6/2024:#Update Pair divert work required. We will continue to provide update as they become available. _x000D_4/6/2024:#Update Pair divert work required. We will continue to provide update as they become available. _x000D_31/5/2024:#Update Pair divert work required. We will continue to provide update as they become available. _x000D_30/5/2024:#Update Pair divert work required. We will continue to provide update as they become available. _x000D_29/5/2024:#Update Pair divert work required. We will continue to provide update as they become available. _x000D_28/5/2024:#Update Pair divert work required. We will continue to provide update as they become available. _x000D_10/5/2024:#Update awaiting a pair divert to be completed. _x000D_08/04/2024: New order added to report | 0 | #Update Missed appointment due to shop manager on holiday, rescheduled for 6/06 AM. | 2024-05-21 | 21/05/24: CSL to provide an update |  |  | 2.Allwyn to arrange access | VFS978072 | 30013854 | 1.Provisioning | AM |  |  |  |  | 0 | [11 empty] | 0
398 | 666451 | 1153 | Batch 3 May24 | Type 1 | SOGEA | Stretham Stores | ELY | CB6 3JQ | 2024-06-07 | 10/6/2024:Order Completed _x000D_7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 10/6/2024:Order Completed _x000D_7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301350 | 30014043 | 6.Failed router install | AM |  | 2024-06-06 | 2024-06-06 | 2024-06-06 | TRUE |  |  |  | 2024-06-28 |  |  |  | 2024-08-28 | 242005011094 | 242005011094 | 2024-08-29 | 1
399 | 463456 | 1407 | Batch 4 Jun24 | Type 1 | SOGEA | Premier | OLDHAM | OL1 4BW | 2024-06-21 | 10/6/2024:Order Completed _x000D_7/6/2024:Order Completed _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 10/6/2024:Order Completed _x000D_7/6/2024:Order Completed _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 | 7/6/2024: CSL to provide an update |  |  | 3.Allwyn to arrange rtr install | VFS984946 | 30015601 | 6.Failed router install | AM |  | 2024-06-06 | 2024-06-20 | 2024-06-21 | TRUE |  |  |  | 2024-07-12 |  |  |  | 2024-07-12 | 242005008859 |  | 2024-07-15 | 1
400 | 671929 | 1411 | Batch 4 Jun24 | Type 1 | SOGEA | Premier Express Arksey Lane News | Doncaster | DN5 0RX | 2024-06-07 | 19/7/2024:#Update Allwyn is unable to get hold of the retailer. _x000D_18/7/2024:#Update Allwyn is unable to get hold of the retailer. _x000D_17/7/2024:#Update Allwyn is unable to get hold of the retailer. _x000D_16/7/2024:#Update Allwyn is unable to get hold of the retailer. _x000D_15/7/2024:#Update Allwyn is unable to get hold of the retailer. _x000D_12/7/2024:#Update Allwyn is unable to get hold of the retailer. _x000D_11/7/2024:#Update Allwyn is unable to get hold of the retailer. _x000D_10/7/2024:#Update Allwyn is unable to get hold of the retailer. _x000D_9/7/2024:#Update Allwyn is unable to get hold of the retailer. _x000D_4/7/2024:#Update Allwyn is unable to get hold of the retailer. _x000D_3/7/2024:#Update Allwyn is unable to get hold of the retailer. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update Allwyn is unable to get hold of the retailer. _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:Update: Order Amended _x000D_20/6/2024:Update: Order Amended _x000D_19/6/2024:Update: Order Amended _x000D_18/6/2024:Update: Order Amended _x000D_17/6/2024:0 _x000D_14/6/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_13/6/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_12/6/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:#Update Allwyn is unable to get hold of the retailer. _x000D_18/7/2024:#Update Allwyn is unable to get hold of the retailer. _x000D_17/7/2024:#Update Allwyn is unable to get hold of the retailer. _x000D_16/7/2024:#Update Allwyn is unable to get hold of the retailer. _x000D_15/7/2024:#Update Allwyn is unable to get hold of the retailer. _x000D_12/7/2024:#Update Allwyn is unable to get hold of the retailer. _x000D_11/7/2024:#Update Allwyn is unable to get hold of the retailer. _x000D_10/7/2024:#Update Allwyn is unable to get hold of the retailer. _x000D_9/7/2024:#Update Allwyn is unable to get hold of the retailer. _x000D_4/7/2024:#Update Allwyn is unable to get hold of the retailer. _x000D_3/7/2024:#Update Allwyn is unable to get hold of the retailer. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update Allwyn is unable to get hold of the retailer. _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:Update: Order Amended _x000D_20/6/2024:Update: Order Amended _x000D_19/6/2024:Update: Order Amended _x000D_18/6/2024:Update: Order Amended _x000D_17/6/2024:0 _x000D_14/6/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_13/6/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_12/6/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 | 7/6/2024: CSL to provide an update |  |  | 3.Allwyn to arrange rtr install | VFS984950 | 30015371 | 2.Commissioning | AM |  | 2024-06-06 | 2024-06-06 | 2024-06-07 | TRUE |  |  |  | 2024-07-09 | [7 empty] | 0 | 671929
401 | 464860 | 1412 | Batch 4 Jun24 | Type 1 | SoGEA/Mobile | Premier Pennywell Supermarket | Sunderland | SR4 9BY | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:#Update - NFA - Allwyn have confirmed new installation date 13/08 AM with retailer _x000D_15/8/2024:#Update - NFA - Allwyn have confirmed new installation date 13/08 AM with retailer _x000D_14/8/2024:#Update - NFA - Allwyn have confirmed new installation date 13/08 AM with retailer 13/8/2024:#Update - NFA - Allwyn have confirmed new installation date 13/08 AM with retailer 12/8/2024:#Update - NFA - Allwyn have confirmed new installation date 13/08 AM with retailer 9/8/2024:#Update - NFA - Allwyn have confirmed new installation date 13/08 AM with retailer 8/8/2024:31/07/2024 6/8/2024:31/07/2024 5/8/2024:31/07/2024 2/8/2024:31/07/2024 1/8/2024:31/07/2024 31/7/2024:25/07/2024 31/7/2024:25/07/2024 30/7/2024:#Update Reappointed for 13/08 AM, as Allwyn are unable to get hold of the retailer. 29/7/2024:#Update Reappointed for 13/08 AM, as Allwyn are unable to get hold of the retailer. 29/7/2024:01426428 26/7/2024:01426428 24/7/2024:#Update Allwyn is unable to get hold of the retailer. 23/7/2024:#Update Allwyn is unable to get hold of the retailer. 22/7/2024:#Update Allwyn is unable to get hold of the retailer. 22/7/2024:#Update Allwyn is unable to get hold of the retailer. 10/6/2024:Order Completed 7/6/2024:Order Completed 6/6/2024:0 5/6/2024:0 4/6/2024:0 31/5/2024:0 30/5/2024:0 29/5/2024:0 28/5/2024:0 10/5/2024:0 02/05/2024: New order added to report | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:#Update - NFA - Allwyn have confirmed new installation date 13/08 AM with retailer _x000D_15/8/2024:#Update - NFA - Allwyn have confirmed new installation date 13/08 AM with retailer _x000D_14/8/2024:#Update - NFA - Allwyn have confirmed new installation date 13/08 AM with retailer 13/8/2024:#Update - NFA - Allwyn have confirmed new installation date 13/08 AM with retailer 12/8/2024:#Update - NFA - Allwyn have confirmed new installation date 13/08 AM with retailer 9/8/2024:#Update - NFA - Allwyn have confirmed new installation date 13/08 AM with retailer 8/8/2024:31/07/2024 6/8/2024:31/07/2024 5/8/2024:31/07/2024 2/8/2024:31/07/2024 1/8/2024:31/07/2024 31/7/2024:25/07/2024 31/7/2024:25/07/2024 30/7/2024:#Update Reappointed for 13/08 AM, as Allwyn are unable to get hold of the retailer. 29/7/2024:#Update Reappointed for 13/08 AM, as Allwyn are unable to get hold of the retailer. 29/7/2024:01426428 26/7/2024:01426428 24/7/2024:#Update Allwyn is unable to get hold of the retailer. 23/7/2024:#Update Allwyn is unable to get hold of the retailer. 22/7/2024:#Update Allwyn is unable to get hold of the retailer. 22/7/2024:#Update Allwyn is unable to get hold of the retailer. 10/6/2024:Order Completed 7/6/2024:Order Completed 6/6/2024:0 5/6/2024:0 4/6/2024:0 31/5/2024:0 30/5/2024:0 29/5/2024:0 28/5/2024:0 10/5/2024:0 02/05/2024: New order added to report | 0 | 0 | 2024-06-07 | 7/6/2024: CSL to provide an update |  |  | 5.CSL | VFS984680 | 30015471 | 2.Commissioning | AM |  | 2024-06-06 | 2024-08-13 | 2024-08-13 11:50 | 1 |  |  |  | 2024-09-13 | [7 empty] | 0
402 | 444003 | 1415 | Batch 4 Jun24 | Type 1 | SOGEA | Fountain Shop & Bakery | MERTHYR TYDFIL | CF47 8EB | 2024-06-07 | 10/6/2024:Order Completed _x000D_7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 10/6/2024:Order Completed _x000D_7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984682 | 30015323 | 2.Commissioning | AM |  | 2024-06-06 | 2024-06-06 | 2024-06-06 | TRUE |  |  |  | 2024-07-04 | [7 empty] | 0
403 | 273315 | 1418 | Batch 4 Jun24 | Type 1 | SOGEA | Grisdale General Store | WORKINGTON | CA14 2SD | 2024-06-07 | 10/6/2024:Order Completed _x000D_7/6/2024:Order Completed _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 10/6/2024:Order Completed _x000D_7/6/2024:Order Completed _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984686 | 30015355 | 2.Commissioning | AM |  | 2024-06-06 | 2024-06-06 | 2024-06-06 | TRUE |  |  |  | 2024-07-08 | [7 empty] | 0
404 | 624890 | 1419 | Batch 4 Jun24 | Type 1 | SOGEA | Premier Dresden Convenience Store | Stoke On Trent | ST3 4HL | 2024-06-07 | 10/6/2024:Order Completed _x000D_7/6/2024:Order Completed _x000D_6/6/2024:Update: Order Completed by Supplier _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 10/6/2024:Order Completed _x000D_7/6/2024:Order Completed _x000D_6/6/2024:Update: Order Completed by Supplier _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984689 | 30015454 | 2.Commissioning | AM |  | 2024-06-06 | 2024-06-06 | 2024-06-06 | TRUE |  |  |  | 2024-07-10 | [7 empty] | 0
405 | 458738 | 1424 | Batch 4 Jun24 | Type 1 | SOGEA | Premier Express Hightown Convenienc | WREXHAM | LL13 7BE | 2024-06-07 | 10/6/2024:Order Completed _x000D_7/6/2024:Order Completed _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 10/6/2024:Order Completed _x000D_7/6/2024:Order Completed _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984694 | 30015545 | 2.Commissioning | AM |  | 2024-06-06 | 2024-06-06 | 2024-06-06 | TRUE |  |  |  | 2024-07-19 | [7 empty] | 0
406 | 455530 | 1786 | Batch 4 Jun24 | Type 1 | SOGEA | Londis Supermarket | LONDON | N14 4DA | 2024-06-07 | 10/6/2024:Order Completed _x000D_7/6/2024:Order Completed _x000D_6/6/2024:Update: Order Completed by Supplier _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 10/6/2024:Order Completed _x000D_7/6/2024:Order Completed _x000D_6/6/2024:Update: Order Completed by Supplier _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983321 | 30015260 | 2.Commissioning | AM |  | 2024-06-06 | 2024-06-06 | 2024-06-06 | TRUE |  |  |  | 2024-06-28 | [7 empty] | 0
407 | 109554 | 1788 | Batch 4 Jun24 | Type 1 | FTTP | J Howells Stationers | BIGGLESWADE | SG18 8AX | 2024-06-07 | 10/6/2024:Order Completed _x000D_7/6/2024:Order Completed _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 10/6/2024:Order Completed _x000D_7/6/2024:Order Completed _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2337312 | 30015153 | 6.Failed router install | AM |  | 2024-06-06 | 2024-06-06 | 2024-06-06 | TRUE | [7 empty] | 2024-06-28 | 242005008511 |  | 2024-07-02 | 1
408 | 631537 | 1791 | Batch 4 Jun24 | Type 1 | SOGEA | Lukes News | Littlehampton | BN16 3DR | 2024-06-07 | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:Your order has been delayed due to our suppliers being unable to complete the job in required time frame. Please check back on 13/06/2024. _x000D_7/6/2024:Supplier Delay: Missed CCD and may require further work as the engineer has retained the job for next day _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:Your order has been delayed due to our suppliers being unable to complete the job in required time frame. Please check back on 13/06/2024. _x000D_7/6/2024:Supplier Delay: Missed CCD and may require further work as the engineer has retained the job for next day _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 | 7/6/2024: CSL to provide an update |  |  | 3.Allwyn to arrange rtr install | VFS983322 | 30015258 | 6.Failed router install | AM |  | 2024-06-06 | 2024-06-06 | 2024-06-07 | TRUE | [7 empty] | 2024-07-01 | 242005008666 |  | 2024-07-04 | 1
409 | 666625 | 1608 | Batch 4 Jun24 | Type 1 | FTTP | Spar | Limavady | BT49 9EN | 2024-06-07 | 22/8/2024:#Update FLT engineer didn't install 2nd socket but as we are not doing FLT's for missing sockets then this will be resolved. _x000D_21/8/2024:#Update FLT engineer didn't install 2nd socket but as we are not doing FLT's for missing sockets then this will be resolved. _x000D_20/8/2024:#Update FLT engineer didn't install 2nd socket but as we are not doing FLT's for missing sockets then this will be resolved. _x000D_10/6/2024:Order Completed _x000D_7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 22/8/2024:#Update FLT engineer didn't install 2nd socket but as we are not doing FLT's for missing sockets then this will be resolved. _x000D_21/8/2024:#Update FLT engineer didn't install 2nd socket but as we are not doing FLT's for missing sockets then this will be resolved. _x000D_20/8/2024:#Update FLT engineer didn't install 2nd socket but as we are not doing FLT's for missing sockets then this will be resolved. _x000D_10/6/2024:Order Completed _x000D_7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2353442 | 30015962 | 2.Commissioning | AM |  | 2024-06-06 | 2024-06-06 | 2024-06-06 | TRUE |  |  |  | 2024-07-08 | [7 empty] | 0
410 | 664837 | 1612 | Batch 4 Jun24 | Type 1 | FTTP | Eurospar | Magherafelt | BT45 7AJ | 2024-06-07 | 10/6/2024:Order Completed _x000D_7/6/2024:Order Completed _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 10/6/2024:Order Completed _x000D_7/6/2024:Order Completed _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2353441 | 30015944 | 2.Commissioning | AM |  | 2024-06-06 | 2024-06-06 | 2024-06-06 | TRUE |  |  |  | 2024-07-10 | [7 empty] | 0
411 | 668658 | 1709 | Batch 4 Jun24 | Type 1 | SOGEA | Premier Late Shop | Peterborough | PE3 8JT | 2024-06-07 | 10/6/2024:Order Completed _x000D_7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 10/6/2024:Order Completed _x000D_7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996798 | 30016104 | 2.Commissioning | AM |  | 2024-06-06 | 2024-06-06 | 2024-06-06 | TRUE |  |  |  | 2024-06-28 | [7 empty] | 0
412 | 664860 | 1725 | Batch 4 Jun24 | Type 1 | SOGEA | JP Traders Local Convenience Store | Iver | SL0 9QJ | 2024-06-07 | 19/7/2024:#Update new review date of 19/07 _x000D_18/7/2024:#Update new review date of 19/07 _x000D_17/7/2024:#Update new review date of 19/07 _x000D_16/7/2024:#Update Sales query for customer is required, will take 2 days to progress. Update 21/06 _x000D_15/7/2024:#Update Sales query for customer is required, will take 2 days to progress. Update 21/06 _x000D_12/7/2024:#Update Sales query for customer is required, will take 2 days to progress. Update 21/06 _x000D_11/7/2024:#Update Sales query for customer is required, will take 2 days to progress. Update 21/06 _x000D_10/7/2024:#Update Sales query for customer is required, will take 2 days to progress. Update 21/06 _x000D_9/7/2024:#Update Sales query for customer is required, will take 2 days to progress. Update 21/06 _x000D_4/7/2024:#Update Sales query for customer is required, will take 2 days to progress. Update 21/06 _x000D_3/7/2024:#Update Sales query for customer is required, will take 2 days to progress. Update 21/06 _x000D_2/7/2024:0 _x000D_1/7/2024:#Update Sales query for customer is required, will take 2 days to progress. Update 21/06 _x000D_27/6/2024:#Update Sales query for customer is required, will take 2 days to progress. Update 21/06 _x000D_25/6/2024:#Update Sales query for customer is required, will take 2 days to progress. Update 21/06 _x000D_24/6/2024:#Update Sales query for customer is required, will take 2 days to progress. Update 21/06 _x000D_20/6/2024:#Update Sales query for customer is required, will take 2 days to progress. Update 21/06 _x000D_19/6/2024:#Update Lineplant Survey activity has been raised. Update review date 18/06/24 _x000D_18/6/2024:#Update Lineplant Survey activity has been raised. Update review date 18/06/24 _x000D_17/6/2024:#Update Lineplant Survey activity has been raised. Update review date 18/06/24 _x000D_14/6/2024:#Update Lineplant Survey activity has been raised. Update review date 18/06/24 _x000D_13/6/2024:#Update Lineplant Survey activity has been raised. Update review date 18/06/24 _x000D_12/6/2024:#Update Lineplant Survey activity has been raised. Update review date 18/06/24 _x000D_10/6/2024:#Update engineer unable to complete installation as line plant survey is required. Will continue to give updates as we receive them. _x000D_7/6/2024:Supplier Delay: Network Planning issue, please await for further details. _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 19/7/2024:#Update new review date of 19/07 _x000D_18/7/2024:#Update new review date of 19/07 _x000D_17/7/2024:#Update new review date of 19/07 _x000D_16/7/2024:#Update Sales query for customer is required, will take 2 days to progress. Update 21/06 _x000D_15/7/2024:#Update Sales query for customer is required, will take 2 days to progress. Update 21/06 _x000D_12/7/2024:#Update Sales query for customer is required, will take 2 days to progress. Update 21/06 _x000D_11/7/2024:#Update Sales query for customer is required, will take 2 days to progress. Update 21/06 _x000D_10/7/2024:#Update Sales query for customer is required, will take 2 days to progress. Update 21/06 _x000D_9/7/2024:#Update Sales query for customer is required, will take 2 days to progress. Update 21/06 _x000D_4/7/2024:#Update Sales query for customer is required, will take 2 days to progress. Update 21/06 _x000D_3/7/2024:#Update Sales query for customer is required, will take 2 days to progress. Update 21/06 _x000D_2/7/2024:0 _x000D_1/7/2024:#Update Sales query for customer is required, will take 2 days to progress. Update 21/06 _x000D_27/6/2024:#Update Sales query for customer is required, will take 2 days to progress. Update 21/06 _x000D_25/6/2024:#Update Sales query for customer is required, will take 2 days to progress. Update 21/06 _x000D_24/6/2024:#Update Sales query for customer is required, will take 2 days to progress. Update 21/06 _x000D_20/6/2024:#Update Sales query for customer is required, will take 2 days to progress. Update 21/06 _x000D_19/6/2024:#Update Lineplant Survey activity has been raised. Update review date 18/06/24 _x000D_18/6/2024:#Update Lineplant Survey activity has been raised. Update review date 18/06/24 _x000D_17/6/2024:#Update Lineplant Survey activity has been raised. Update review date 18/06/24 _x000D_14/6/2024:#Update Lineplant Survey activity has been raised. Update review date 18/06/24 _x000D_13/6/2024:#Update Lineplant Survey activity has been raised. Update review date 18/06/24 _x000D_12/6/2024:#Update Lineplant Survey activity has been raised. Update review date 18/06/24 _x000D_10/6/2024:#Update engineer unable to complete installation as line plant survey is required. Will continue to give updates as we receive them. _x000D_7/6/2024:Supplier Delay: Network Planning issue, please await for further details. _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996802 | 30016070 | 2.Commissioning | AM |  | 2024-06-06 | 2024-06-06 | 2024-06-06 | TRUE |  |  |  | 2024-07-01 | [7 empty] | 0
413 | 664867 | 1729 | Batch 4 Jun24 | Type 1 | SoGEA/Mobile | NISA TODAY ( MOULSECOOMB SPSO) | Brighton | BN2 4GB | 2024-06-07 | 6/9/2024:#Update Order has been further delayed, review back 21/08 AM _x000D_5/9/2024:#Update Order has been further delayed, review back 21/08 AM _x000D_4/9/2024:#Update Order has been further delayed, review back 21/08 AM _x000D_3/9/2024:#Update Order has been further delayed, review back 21/08 AM _x000D_2/9/2024:#Update Order has been further delayed, review back 21/08 AM _x000D_29/8/2024:#Update Order has been further delayed, review back 21/08 AM _x000D_28/8/2024:#Update Order has been further delayed, review back 21/08 AM _x000D_27/8/2024:#Update Order has been further delayed, review back 21/08 AM _x000D_22/8/2024:#Update Order has been further delayed, review back 21/08 AM _x000D_21/8/2024:#Update Order has been further delayed, review back 21/08 AM _x000D_20/8/2024:#Update Order has been further delayed, review back 21/08 AM _x000D_19/8/2024:#Update Order has been further delayed, review back 21/08 AM _x000D_19/8/2024:01426954 _x000D_16/8/2024:#Update Order has been further delayed, review back 21/08 AM _x000D_15/8/2024:#Update Order has been further delayed, review back 5/08 AM _x000D_14/8/2024:#Update Order has been further delayed, review back 5/08 AM _x000D_13/8/2024:#Update Order has been further delayed, review back 5/08 AM _x000D_12/8/2024:#Update Order has been further delayed, review back 5/08 AM _x000D_9/8/2024:#Update Order has been further delayed, review back 5/08 AM _x000D_8/8/2024:31/07/2024 _x000D_6/8/2024:31/07/2024 _x000D_5/8/2024:31/07/2024 _x000D_2/8/2024:31/07/2024 _x000D_1/8/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_30/7/2024:#Update new review date of 19/07 _x000D_29/7/2024:#Update new review date of 19/07 _x000D_29/7/2024:01426954 _x000D_26/7/2024:01426954 _x000D_24/7/2024:#Update new review date of 19/07 _x000D_23/7/2024:#Update new review date of 19/07 _x000D_22/7/2024:#Update new review date of 19/07 _x000D_22/7/2024:#Update new review date of 19/07 _x000D_19/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_18/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. _x000D_17/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:Update: Order Amended _x000D_25/6/2024:Update: Order Amended _x000D_24/6/2024:Update: Order Amended _x000D_20/6/2024:Order Acknowledged _x000D_19/6/2024:Order Acknowledged _x000D_18/6/2024:Order Acknowledged _x000D_17/6/2024:Order Acknowledged _x000D_14/6/2024:Order Acknowledged _x000D_13/6/2024:Order Acknowledged _x000D_12/6/2024:Supplier Missed Appointment _x000D_10/6/2024:Your order has been delayed due to Engineer retained the job, order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 13/06/2024 _x000D_7/6/2024:Supplier Delay: Missed CCD and may require further work as the engineer has retained the job for next day _x000D_6/6/2024:Supplier Delay: Missed CCD and may require further work as the engineer has retained the job for next day _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 9/9/2024:#Update Order has been further delayed, review back 21/08 AM _x000D_6/9/2024:#Update Order has been further delayed, review back 21/08 AM _x000D_5/9/2024:#Update Order has been further delayed, review back 21/08 AM _x000D_4/9/2024:#Update Order has been further delayed, review back 21/08 AM _x000D_3/9/2024:#Update Order has been further delayed, review back 21/08 AM _x000D_2/9/2024:#Update Order has been further delayed, review back 21/08 AM _x000D_29/8/2024:#Update Order has been further delayed, review back 21/08 AM _x000D_28/8/2024:#Update Order has been further delayed, review back 21/08 AM _x000D_27/8/2024:#Update Order has been further delayed, review back 21/08 AM _x000D_22/8/2024:#Update Order has been further delayed, review back 21/08 AM _x000D_21/8/2024:#Update Order has been further delayed, review back 21/08 AM _x000D_20/8/2024:#Update Order has been further delayed, review back 21/08 AM _x000D_19/8/2024:#Update Order has been further delayed, review back 21/08 AM _x000D_19/8/2024:01426954 _x000D_16/8/2024:#Update Order has been further delayed, review back 21/08 AM _x000D_15/8/2024:#Update Order has been further delayed, review back 5/08 AM _x000D_14/8/2024:#Update Order has been further delayed, review back 5/08 AM _x000D_13/8/2024:#Update Order has been further delayed, review back 5/08 AM _x000D_12/8/2024:#Update Order has been further delayed, review back 5/08 AM _x000D_9/8/2024:#Update Order has been further delayed, review back 5/08 AM _x000D_8/8/2024:31/07/2024 _x000D_6/8/2024:31/07/2024 _x000D_5/8/2024:31/07/2024 _x000D_2/8/2024:31/07/2024 _x000D_1/8/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_30/7/2024:#Update new review date of 19/07 _x000D_29/7/2024:#Update new review date of 19/07 _x000D_29/7/2024:01426954 _x000D_26/7/2024:01426954 _x000D_24/7/2024:#Update new review date of 19/07 _x000D_23/7/2024:#Update new review date of 19/07 _x000D_22/7/2024:#Update new review date of 19/07 _x000D_22/7/2024:#Update new review date of 19/07 _x000D_19/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_18/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. _x000D_17/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:Update: Order Amended _x000D_25/6/2024:Update: Order Amended _x000D_24/6/2024:Update: Order Amended _x000D_20/6/2024:Order Acknowledged _x000D_19/6/2024:Order Acknowledged _x000D_18/6/2024:Order Acknowledged _x000D_17/6/2024:Order Acknowledged _x000D_14/6/2024:Order Acknowledged _x000D_13/6/2024:Order Acknowledged _x000D_12/6/2024:Supplier Missed Appointment _x000D_10/6/2024:Your order has been delayed due to Engineer retained the job, order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 13/06/2024 _x000D_7/6/2024:Supplier Delay: Missed CCD and may require further work as the engineer has retained the job for next day _x000D_6/6/2024:Supplier Delay: Missed CCD and may require further work as the engineer has retained the job for next day _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | Supplier Delay: Unable to complete work please await for further details | #Update Order has been further delayed, review back 21/08 AM | 2024-06-07 | 7/6/2024: CSL to provide an update |  |  | 5.CSL | VFS996804 | 30016098 | 1.Provisioning | AM |  | 2024-06-06 | 2024-06-06 |  | 0 | [11 empty] | 0
414 | 671923 | 1733 | Batch 4 Jun24 | Type 1 | SoGEA/Mobile | Weeley Convenience Store | Clacton-on-Sea | CO16 9JA | 2024-06-07 | 6/9/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Now order got re-appointed for 27/09/2024. _x000D_5/9/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Now order got re-appointed for 27/09/2024. _x000D_4/9/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Now order got re-appointed for 27/09/2024. _x000D_3/9/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Now order got re-appointed for 27/09/2024. _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:Supplier Missed Appointment _x000D_12/8/2024:Supplier Missed Appointment _x000D_9/8/2024:Supplier Missed Appointment _x000D_8/8/2024:Supplier Missed Appointment _x000D_6/8/2024:Your order has been delayed due to a customer missed appointment as it is a duplicate order. Please check with end user and reappoint the order if still required. _x000D_5/8/2024:Supplier Missed Appointment _x000D_2/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_31/7/2024:Supplier Delay: Unable to complete work in the allocated appointment slot, please await further details. _x000D_31/7/2024:37608 _x000D_30/7/2024:Supplier Delay: Unable to complete work in the allocated appointment slot, please await further details. _x000D_29/7/2024:Supplier Delay: Unable to complete work in the allocated appointment slot, please await further details. _x000D_29/7/2024:26/07/2024 14:59 _x000D_26/7/2024:23/07/2024 14:15 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_22/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_22/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_10/6/2024:Order Completed _x000D_7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 9/9/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Now order got re-appointed for 27/09/2024. _x000D_6/9/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Now order got re-appointed for 27/09/2024. _x000D_5/9/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Now order got re-appointed for 27/09/2024. _x000D_4/9/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Now order got re-appointed for 27/09/2024. _x000D_3/9/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Now order got re-appointed for 27/09/2024. _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:Supplier Missed Appointment _x000D_12/8/2024:Supplier Missed Appointment _x000D_9/8/2024:Supplier Missed Appointment _x000D_8/8/2024:Supplier Missed Appointment _x000D_6/8/2024:Your order has been delayed due to a customer missed appointment as it is a duplicate order. Please check with end user and reappoint the order if still required. _x000D_5/8/2024:Supplier Missed Appointment _x000D_2/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_31/7/2024:Supplier Delay: Unable to complete work in the allocated appointment slot, please await further details. _x000D_31/7/2024:37608 _x000D_30/7/2024:Supplier Delay: Unable to complete work in the allocated appointment slot, please await further details. _x000D_29/7/2024:Supplier Delay: Unable to complete work in the allocated appointment slot, please await further details. _x000D_29/7/2024:26/07/2024 14:59 _x000D_26/7/2024:23/07/2024 14:15 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_22/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_22/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_10/6/2024:Order Completed _x000D_7/6/2024:Order Completed _x000D_6/6/2024:Order Completed _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Now order got re-appointed for 27/09/2024. | 0 | 2024-06-07 | 7/6/2024: CSL to provide an update |  |  | 5.CSL | VFS996805 | 30016108 | 1.Provisioning | AM |  | 2024-06-06 | 2024-08-30 |  | 0 | [11 empty] | 0 | 671923
415 | 642118 | 1914 | Batch 4 Jun24 | Type 1 | SOGEA | Spar | Portrush | BT56 8JG | 2024-06-07 | 10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1002075 | 30016120 | 2.Commissioning | AM |  | 2024-06-06 | 2024-06-06 | 2024-06-06 | TRUE |  |  |  | 2024-07-08 | [7 empty] | 0
416 | 200319 | 669 | Batch 3 May24 | Type 1 | SOGEA | 8 TILL LATE | HOUNSLOW | TW3 1JQ | 2024-06-10 | 9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300866 | 30013559 | 6.Failed router install | AM |  | 2024-05-21 | 2024-06-07 | 2024-06-07 | TRUE | [7 empty] | 2024-07-01 | 242005008668 |  |  | 1
417 | 660548 | 683 | Batch 3 May24 | Type 1 | SOGEA | Budgens | Wolverhampton | WV8 1JG | 2024-06-10 | 10/6/2024:Order Completed _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_21/5/2024:Update: Order Amended _x000D_20/5/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 10/6/2024:Order Completed _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_21/5/2024:Update: Order Amended _x000D_20/5/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300880 | 30013573 | 6.Failed router install | AM |  | 2024-05-20 | 2024-06-07 | 2024-06-07 | TRUE | [7 empty] | 2024-07-03 | 23A004945917 |  | 2024-07-04 | 1
418 | 420181 | 899 | Batch 3 May24 | Type 1 | SOGEA | Kalpinas News | LONDON | SE17 2SS | 2024-06-10 | 2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-05-20 | 20/05/24: CSL to provide update |  |  | 3.Allwyn to arrange rtr install | VFP2301096 | 30013789 | 2.Commissioning | AM |  | 2024-05-17 | 2024-06-07 | 2024-06-07 | TRUE |  |  |  | 2024-07-15 | [7 empty] | 0
419 | 635174 | 1443 | Batch 4 Jun24 | Type 1 | SOGEA | Bargain Booze | Dorchester | DT1 2LN | 2024-06-10 | 10/6/2024:Order Completed _x000D_7/6/2024:Order Completed _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 10/6/2024:Order Completed _x000D_7/6/2024:Order Completed _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984712 | 30015406 | 2.Commissioning | AM |  | 2024-06-07 | 2024-06-07 | 2024-06-07 | TRUE |  |  |  | 2024-06-28 | [7 empty] | 0
420 | 477377 | 1797 | Batch 4 Jun24 | Type 1 | SOGEA | Best One | Gosport | PO13 9SP | 2024-06-10 | 10/6/2024:Order Completed _x000D_7/6/2024:Order Completed _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 10/6/2024:Order Completed _x000D_7/6/2024:Order Completed _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983327 | 30015222 | 2.Commissioning | AM |  | 2024-06-07 | 2024-06-07 | 2024-06-07 | TRUE |  |  |  | 2024-09-05 | [7 empty] | 0
421 | 615961 | 1800 | Batch 4 Jun24 | Type 1 | SOGEA | Newell Stores | Coalisland | BT71 4LP | 2024-06-10 | 10/6/2024:Order Completed _x000D_7/6/2024:Order Completed _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 10/6/2024:Order Completed _x000D_7/6/2024:Order Completed _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983330 | 30015251 | 6.Failed router install | AM |  | 2024-06-07 | 2024-06-07 | 2024-06-07 | TRUE | [7 empty] | 2024-07-10 | 242005010287 |  | 2024-07-11 | 1
422 | 629111 | 1801 | Batch 4 Jun24 | Type 1 | SOGEA | Londis | Great Yarmouth | NR30 3AU | 2024-06-10 | 10/6/2024:#Update - Network Planning issues. Please await for further updates _x000D_7/6/2024:#Update - Network Planning issues. Please await for further updates _x000D_6/6/2024:#Update - Network Planning issues. Please await for further updates _x000D_5/6/2024:#Update - Network Planning issues. Please await for further updates _x000D_4/6/2024:#Update - Network Planning issues. Please await for further updates _x000D_31/5/2024:#Update - Network Planning issues. Please await for further updates _x000D_30/5/2024:#Update - Network Planning issues. Please await for further updates _x000D_29/5/2024:#Update - Network Planning issues. Please await for further updates _x000D_28/5/2024:#Update - Network Planning issues. Please await for further updates _x000D_10/5/2024:#Update - Network Planning issues. Please await for further updates _x000D_02/05/2024: New order added to report | 10/6/2024:#Update - Network Planning issues. Please await for further updates _x000D_7/6/2024:#Update - Network Planning issues. Please await for further updates _x000D_6/6/2024:#Update - Network Planning issues. Please await for further updates _x000D_5/6/2024:#Update - Network Planning issues. Please await for further updates _x000D_4/6/2024:#Update - Network Planning issues. Please await for further updates _x000D_31/5/2024:#Update - Network Planning issues. Please await for further updates _x000D_30/5/2024:#Update - Network Planning issues. Please await for further updates _x000D_29/5/2024:#Update - Network Planning issues. Please await for further updates _x000D_28/5/2024:#Update - Network Planning issues. Please await for further updates _x000D_10/5/2024:#Update - Network Planning issues. Please await for further updates _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983332 | 30015275 | 2.Commissioning | AM |  | 2024-06-07 | 2024-06-07 | 2024-06-07 | TRUE |  |  |  | 2024-06-28 | [7 empty] | 0
423 | 660557 | 1802 | Batch 4 Jun24 | Type 1 | SOGEA | PREMIER | ANGLESEY | LL61 6SL | 2024-06-10 | 10/6/2024:Order Completed _x000D_7/6/2024:Order Completed _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 10/6/2024:Order Completed _x000D_7/6/2024:Order Completed _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983333 | 30015202 | 6.Failed router install | AM |  | 2024-06-07 | 2024-06-07 | 2024-06-07 | TRUE |  |  |  | 2024-08-07 |  |  |  | 2024-08-07 | 242005008916 |  | 2024-08-08 | 1
424 | 625945 | 1804 | Batch 4 Jun24 | Type 1 | FTTP | Burwell Premier Store | Cambridge | CB25 0BA | 2024-06-10 | 12/6/2024:Order Completed _x000D_10/6/2024:Order Completed _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 12/6/2024:Order Completed _x000D_10/6/2024:Order Completed _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2337315 | 30015131 | 2.Commissioning | AM |  | 2024-06-07 | 2024-06-07 | 2024-06-07 | TRUE |  |  |  | 2024-06-28 | [7 empty] | 0
425 | 660723 | 1805 | Batch 4 Jun24 | Type 1 | SOGEA | Supernews and Cards Post Office | Ashby De La Zouch | LE65 1AF | 2024-06-10 | 10/6/2024:Order Completed _x000D_7/6/2024:Order Completed _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 10/6/2024:Order Completed _x000D_7/6/2024:Order Completed _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983334 | 30015266 | 2.Commissioning | AM |  | 2024-06-07 | 2024-06-07 | 2024-06-08 | TRUE |  |  |  | 2024-09-06 | [7 empty] | 0
426 | 629913 | 1930 | Batch 4 Jun24 | Type 1 | SOGEA | Spar | Glasgow | G33 5EG | 2024-06-10 | 10/6/2024:Order Completed _x000D_7/6/2024:Order Completed _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 10/6/2024:Order Completed _x000D_7/6/2024:Order Completed _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1018155 | 30016079 | 2.Commissioning | AM |  | 2024-06-07 | 2024-06-07 | 2024-06-07 | TRUE |  |  |  | 2024-07-02 | [7 empty] | 0
427 | 666740 | 1747 | Batch 4 Jun24 | Type 1 | SOGEA | Spar Stores | Carrickfergus | BT38 8JW | 2024-06-10 | 19/7/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_18/7/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_17/7/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_16/7/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_15/7/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_12/7/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_11/7/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_10/7/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_9/7/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_4/7/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_3/7/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_27/6/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_25/6/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_24/6/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_20/6/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_19/6/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_18/6/2024:Update: Order Amended _x000D_17/6/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. _x000D_14/6/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. _x000D_13/6/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. _x000D_12/6/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. _x000D_10/6/2024:End User Missed appointment. Action required _x000D_7/6/2024:End User Missed appointment. Action required _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 19/7/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_18/7/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_17/7/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_16/7/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_15/7/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_12/7/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_11/7/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_10/7/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_9/7/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_4/7/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_3/7/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_27/6/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_25/6/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_24/6/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_20/6/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_19/6/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_18/6/2024:Update: Order Amended _x000D_17/6/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. _x000D_14/6/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. _x000D_13/6/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. _x000D_12/6/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. _x000D_10/6/2024:End User Missed appointment. Action required _x000D_7/6/2024:End User Missed appointment. Action required _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2353448 | 30015956 | 2.Commissioning | AM |  | 2024-06-07 | 2024-06-07 | 2024-06-07 | TRUE |  |  |  | 2024-08-13 | [7 empty] | 0
428 | 666109 | 1750 | Batch 4 Jun24 | Type 3 | SoGEA/Mobile | Post Office | Pembroke Dock | SA72 6PA | 2024-06-10 | 6/9/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_5/9/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_4/9/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_3/9/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_2/9/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_29/8/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_28/8/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_27/8/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_22/8/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_21/8/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_20/8/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_19/8/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_19/8/2024:01430070 _x000D_16/8/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_15/8/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_14/8/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_13/8/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_12/8/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_9/8/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_8/8/2024:19/06/2024 _x000D_6/8/2024:19/06/2024 _x000D_5/8/2024:19/06/2024 _x000D_2/8/2024:19/06/2024 _x000D_1/8/2024:19/06/2024 _x000D_31/7/2024:19/06/2024 _x000D_31/7/2024:19/06/2024 _x000D_30/7/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_29/7/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_29/7/2024:01430070 _x000D_26/7/2024:01430070 _x000D_24/7/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_23/7/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_22/7/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_22/7/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_10/6/2024:Order Completed _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 9/9/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_6/9/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_5/9/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_4/9/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_3/9/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_2/9/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_29/8/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_28/8/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_27/8/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_22/8/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_21/8/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_20/8/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_19/8/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_19/8/2024:01430070 _x000D_16/8/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_15/8/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_14/8/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_13/8/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_12/8/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_9/8/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_8/8/2024:19/06/2024 _x000D_6/8/2024:19/06/2024 _x000D_5/8/2024:19/06/2024 _x000D_2/8/2024:19/06/2024 _x000D_1/8/2024:19/06/2024 _x000D_31/7/2024:19/06/2024 _x000D_31/7/2024:19/06/2024 _x000D_30/7/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_29/7/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_29/7/2024:01430070 _x000D_26/7/2024:01430070 _x000D_24/7/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_23/7/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_22/7/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_22/7/2024:#Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment _x000D_10/6/2024:Order Completed _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 0 | #Update - New line required in busy post office, current line plant is behind shop fronting. OOH appointment required. Allwyn to liaise with retailer re availability to allow access to engineer for OOH appointment | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996808 | 30016038 | 2.Commissioning | AM |  |  |  |  | 0 |  |  |  | 2024-07-29 | [7 empty] | 0
429 | 667393 | 1758 | Batch 4 Jun24 | Type 1 | SOGEA | Spar Stores | Tamworth | B79 8JA | 2024-06-10 | 10/6/2024:Order Completed _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 10/6/2024:Order Completed _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996814 | 30016091 | 6.Failed router install | AM |  | 2024-06-07 | 2024-06-07 | 2024-06-07 | TRUE | [7 empty] | 2024-07-02 | 23A004945844 |  | 2024-07-04 | 1
430 | 666450 | 1766 | Batch 4 Jun24 | Type 1 | SOGEA | Premier Amroth Road | Cardiff | CF5 5TA | 2024-06-10 | 10/6/2024:Order Completed _x000D_7/6/2024:Order Completed _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 10/6/2024:Order Completed _x000D_7/6/2024:Order Completed _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996812 | 30016073 | 2.Commissioning | AM |  | 2024-06-07 | 2024-06-07 | 2024-06-07 | TRUE |  |  |  | 2024-07-08 | [7 empty] | 0
431 | 669445 | 1805 | Batch 4 Jun24 | Type 1 | SOGEA | Spar Stores | Machynlleth | SY20 8EB | 2024-06-10 | 10/6/2024:Order Completed _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 10/6/2024:Order Completed _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996817 | 30016043 | 2.Commissioning | AM |  | 2024-06-07 | 2024-06-07 | 2024-06-07 | TRUE |  |  |  | 2024-08-07 | [7 empty] | 0
432 | 664982 | 1817 | Batch 4 Jun24 | Type 1 | SOGEA | Spar Stores | Glasgow | G71 5QQ | 2024-06-10 | 10/6/2024:Order Completed _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 10/6/2024:Order Completed _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996819 | 30015972 | 2.Commissioning | AM |  | 2024-06-07 | 2024-06-07 | 2024-06-07 | TRUE |  |  |  | 2024-07-02 | [7 empty] | 0
433 | 653984 | 1851 | Batch 4 Jun24 | Type 1 | SOGEA | Spar | Dungannon | BT70 1TF | 2024-06-10 | 10/6/2024:Order Completed _x000D_7/6/2024:Order Completed _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 10/6/2024:Order Completed _x000D_7/6/2024:Order Completed _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996822 | 30016028 | 6.Failed router install | AM |  | 2024-06-07 | 2024-06-07 | 2024-06-07 | TRUE |  |  |  | 2024-07-10 |  |  |  | 2024-07-10 | 242005010281 |  | 2024-07-11 | 1
434 | 665820 | 1168 | Batch 3 May24 | Type 1 | SoGEA/Mobile | Post Office | PONTEFRACT | WF8 2HB | 2024-09-03 | 6/9/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_5/9/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_4/9/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_3/9/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_2/9/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_29/8/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_28/8/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_27/8/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_22/8/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_21/8/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_20/8/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_19/8/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_19/8/2024:01409116 _x000D_16/8/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_15/8/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_14/8/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_13/8/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_12/8/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_9/8/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_8/8/2024:28/06/2024 _x000D_6/8/2024:28/06/2024 _x000D_5/8/2024:28/06/2024 _x000D_2/8/2024:28/06/2024 _x000D_1/8/2024:28/06/2024 _x000D_31/7/2024:28/06/2024 _x000D_31/7/2024:28/06/2024 _x000D_30/7/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_29/7/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_29/7/2024:01409116 _x000D_26/7/2024:01409116 _x000D_24/7/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_23/7/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_22/7/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_22/7/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_6/9/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_5/9/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_4/9/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_3/9/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_2/9/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_29/8/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_28/8/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_27/8/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_22/8/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_21/8/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_20/8/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_19/8/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_19/8/2024:01409116 _x000D_16/8/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_15/8/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_14/8/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_13/8/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_12/8/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_9/8/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_8/8/2024:28/06/2024 _x000D_6/8/2024:28/06/2024 _x000D_5/8/2024:28/06/2024 _x000D_2/8/2024:28/06/2024 _x000D_1/8/2024:28/06/2024 _x000D_31/7/2024:28/06/2024 _x000D_31/7/2024:28/06/2024 _x000D_30/7/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_29/7/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_29/7/2024:01409116 _x000D_26/7/2024:01409116 _x000D_24/7/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_23/7/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_22/7/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_22/7/2024:#UPDATE Order timed out will need to be reraised once charges have been approved _x000D_14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Order Completed | #UPDATE Order timed out will need to be reraised once charges have been approved |  |  |  |  | 2.Allwyn to arrange access | VFS978001 | 30014058 | 2.Commissioning | AM |  | 2024-05-24 | 2024-09-02 |  | 0 | [11 empty] | 0
435 | 605783 | 1402 | Batch 4 Jun24 | Type 1 | FTTP | Walker Superstore | Newcastle Upon Tyne | NE6 2RH | 2024-06-11 | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2338498 | 30015500 | 2.Commissioning | AM |  | 2024-05-21 | 2024-06-10 | 2024-06-10 | TRUE |  |  |  | 2024-07-01 | [7 empty] | 0
436 | 635179 | 1448 | Batch 4 Jun24 | Type 1 | SOGEA | Bargain Booze | TROWBRIDGE | BA14 0JH | 2024-06-11 | 14/6/2024:Update: Order Completed by Supplier _x000D_13/6/2024:Update: Order Completed by Supplier _x000D_12/6/2024:Update: Order Completed by Supplier _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 14/6/2024:Update: Order Completed by Supplier _x000D_13/6/2024:Update: Order Completed by Supplier _x000D_12/6/2024:Update: Order Completed by Supplier _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 5.CSL | VFP2338507 | 30015663 | 6.Failed router install | AM |  | 2024-06-10 | 2024-06-10 | 2024-06-10 | TRUE |  |  |  | 2024-07-18 |  |  |  | 2024-07-18 | 242005010347 |  | 2024-07-19 | 1
437 | 429797 | 1454 | Batch 4 Jun24 | Type 1 | FTTP | Costcutter | STRABANE | BT82 9AG | 2024-06-11 | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2338509 | 30015446 | 6.Failed router install | AM |  | 2024-06-10 | 2024-06-10 | 2024-06-10 | TRUE |  |  |  | 2024-07-08 |  |  |  | 2024-07-08 | 242005010309 |  |  | 1
438 | 447850 | 1458 | Batch 4 Jun24 | Type 1 | SOGEA | Costcutter St Marks Road Store | TIPTON | DY4 0SZ | 2024-06-11 | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984715 | 30015518 | 2.Commissioning | AM |  | 2024-06-10 | 2024-06-10 | 2024-06-10 | TRUE |  |  |  | 2024-07-03 | [7 empty] | 0
439 | 466879 | 1465 | Batch 4 Jun24 | Type 1 | SOGEA | Premier Poundback Stores | MALVERN | WR14 2PE | 2024-06-11 | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984719 | 30015414 | 2.Commissioning | AM |  | 2024-06-10 | 2024-06-10 | 2024-06-10 | TRUE |  |  |  | 2024-07-11 | [7 empty] | 0
440 | 432801 | 1471 | Batch 4 Jun24 | Type 1 | SOGEA | BARGAIN BOOZE | MANCHESTER | M40 7BW | 2024-06-11 | 14/6/2024:Update: Order Completed by Supplier _x000D_13/6/2024:Update: Order Completed by Supplier _x000D_12/6/2024:Update: Order Completed by Supplier _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 14/6/2024:Update: Order Completed by Supplier _x000D_13/6/2024:Update: Order Completed by Supplier _x000D_12/6/2024:Update: Order Completed by Supplier _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS986020 | 30015441 | 6.Failed router install | AM |  | 2024-06-10 | 2024-06-10 | 2024-06-10 | TRUE |  |  |  | 2024-07-11 |  |  |  | 2024-07-11 | 238004924304 |  | 2024-07-12 | 1
441 | 662807 | 1472 | Batch 4 Jun24 | Type 1 | SOGEA | Go Local Community Convenience Stor | Birkenhead | CH41 7BZ | 2024-06-11 | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2338516 | 30015602 | 2.Commissioning | AM |  | 2024-06-10 | 2024-06-10 | 2024-06-10 | TRUE |  |  |  | 2024-07-12 | [7 empty] | 0 | 662807
442 | 625274 | 1807 | Batch 4 Jun24 | Type 1 | SOGEA | Wharncliffe Garage | Barnsley | S70 6BN | 2024-06-11 | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983336 | 30015244 | 2.Commissioning | AM |  | 2024-06-10 | 2024-06-10 | 2024-06-10 | TRUE |  |  |  | 2024-07-10 | [7 empty] | 0
443 | 442393 | 1809 | Batch 4 Jun24 | Type 1 | SOGEA | SPAR | MANCHESTER | M23 2UH | 2024-06-11 | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 10-05-2024 will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL _x000D_02/05/2024: New order added to report | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 10-05-2024 will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983338 | 30015281 | 3.In life | AM |  | 2024-06-10 | 2024-06-10 | 2024-06-10 | TRUE |  |  |  | 2024-09-04 |  |  |  | 2024-09-04 | 238004926187 | 238004926187 | 2024-09-05 | 1
444 | 653644 | 1811 | Batch 4 Jun24 | Type 1 | SOGEA | Nisa | Wareham | BH20 7HL | 2024-06-11 | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:Order Completed _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:Order Completed _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983337 | 30015278 | 2.Commissioning | AM |  | 2024-06-10 | 2024-06-10 | 2024-06-10 | TRUE |  |  |  | 2024-09-04 | [7 empty] | 0
445 | 656854 | 1812 | Batch 4 Jun24 | Type 1 | SOGEA | Mace | Coleraine | BT51 3QJ | 2024-06-11 | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983339 | 30015203 | 6.Failed router install | AM |  | 2024-06-10 | 2024-06-10 | 2024-06-10 | TRUE |  |  |  | 2024-07-08 |  |  |  | 2024-07-08 | 242005010307 |  |  | 1
446 | 659369 | 1815 | Batch 4 Jun24 | Type 1 | SOGEA | Sinals News | London | E7 9HA | 2024-06-11 | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:Update: Order Completed by Supplier _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:Update: Order Completed by Supplier _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983341 | 30015238 | 6.Failed router install | AM |  | 2024-06-10 | 2024-06-10 | 2024-06-10 | TRUE | [7 empty] | 2024-06-24 | 242005008549 |  | 2024-07-01 | 1
447 | 230932 | 1816 | Batch 4 Jun24 | Type 1 | SOGEA | BOLTS SHETLAND | LERWICK | ZE1 0PE | 2024-06-11 | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:Order Completed _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:Order Completed _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983343 | 30015277 | 6.Failed router install | AM |  | 2024-06-10 | 2024-06-10 | 2024-06-10 | TRUE |  |  |  | 2024-07-29 |  |  |  | 2024-07-26 | 23A004952768 |  | 2024-07-29 | 1
448 | 251103 | 1877 | Batch 4 Jun24 | Type 3 | SoGEA/Mobile | Spar Stores | Aberystwyth | SY23 2AE | 2024-06-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:Update: Order Amended _x000D_31/7/2024:Update: Order Amended _x000D_31/7/2024:37023 _x000D_30/7/2024:Update: Order Amended _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:25/07/2024 09:21 _x000D_26/7/2024:25/07/2024 09:21 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_22/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:Order Completed _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:Update: Order Amended _x000D_31/7/2024:Update: Order Amended _x000D_31/7/2024:37023 _x000D_30/7/2024:Update: Order Amended _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:25/07/2024 09:21 _x000D_26/7/2024:25/07/2024 09:21 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_22/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:Order Completed _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 0 | 0 | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1041520 | 30016100 | 2.Commissioning | AM |  | 2024-09-02 | 2024-09-02 |  | 0 | [11 empty] | 0
449 | 205585 | 1896 | Batch 4 Jun24 | Type 1 | SOGEA | Spar Stores | Londonderry | BT48 0LX | 2024-06-11 | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996840 | 30015982 | 6.Failed router install | AM |  | 2024-06-10 | 2024-06-10 | 2024-06-10 | TRUE |  |  |  | 2024-07-08 |  |  |  | 2024-07-08 | 242005010308 |  |  | 1
450 | 445531 | 1907 | Batch 4 Jun24 | Type 1 | SOGEA | SPAR | Larkhall | ML9 3LQ | 2024-06-11 | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996839 | 30016048 | 6.Failed router install | AM |  | 2024-06-10 | 2024-06-10 | 2024-06-10 | TRUE | [7 empty] | 2024-07-02 | 23A004945392 |  | 2024-07-04 | 1
451 | 486400 | 1909 | Batch 4 Jun24 | Type 1 | SOGEA | Spar Stores | Bridgend | CF31 4JR | 2024-06-11 | 14/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 10/06 AM _x000D_13/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 10/06 AM _x000D_12/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 10/06 AM _x000D_10/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 10/06 AM _x000D_7/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 10/06 AM _x000D_6/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 10/06 AM _x000D_5/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 10/06 AM _x000D_4/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 10/06 AM _x000D_31/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 10/06 AM _x000D_30/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 10/06 AM _x000D_29/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 10/06 AM _x000D_28/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 10/06 AM _x000D_10/5/2024:Delay : Sales Query CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/05/2024: New order added to report | 14/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 10/06 AM _x000D_13/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 10/06 AM _x000D_12/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 10/06 AM _x000D_10/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 10/06 AM _x000D_7/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 10/06 AM _x000D_6/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 10/06 AM _x000D_5/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 10/06 AM _x000D_4/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 10/06 AM _x000D_31/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 10/06 AM _x000D_30/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 10/06 AM _x000D_29/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 10/06 AM _x000D_28/5/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 10/06 AM _x000D_10/5/2024:Delay : Sales Query CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996838 | 30016061 | 6.Failed router install | AM |  | 2024-06-10 | 2024-06-10 | 2024-06-10 | TRUE |  |  |  | 2024-07-04 |  |  |  | 2024-07-04 | 242005010342 |  | 2024-07-05 | 1
452 | 669777 | 1911 | Batch 4 Jun24 | Type 1 | SOGEA | Spar Stores | Hartlepool | TS25 2AX | 2024-09-02 | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996842 | 30016096 | 6.Failed router install | AM |  | 2024-06-10 | 2024-06-10 | 2024-06-10 | TRUE |  |  |  | 2024-07-01 |  |  |  | 2024-08-30 | 237004907035 | 237004907035 | 2024-09-02 | 1
453 | 470712 | 1918 | Batch 4 Jun24 | Type 1 | SOGEA | Spar | Craigavon | BT62 1LF | 2024-06-11 | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:Update: Order Completed by Supplier _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:Update: Order Completed by Supplier _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996841 | 30015980 | 2.Commissioning | AM |  | 2024-06-10 | 2024-06-10 | 2024-06-10 | TRUE |  |  |  | 2024-07-10 | [7 empty] | 0
454 | 621902 | 585 | Batch 3 May24 | Type 3 | SOGEA | Premier Vigo Convenience Store | Chester-le-Street | DH3 2EW | 2024-06-12 | 6/9/2024:#Update Sent chaser to VF for site change charges _x000D_5/9/2024:#Update Sent chaser to VF for site change charges _x000D_4/9/2024:#Update Sent chaser to VF for site change charges _x000D_14/6/2024:#Update Order incomplete as engineer needed more time to complete works. Order rescheduled for 11/06 AM to complete works _x000D_13/6/2024:#Update Order incomplete as engineer needed more time to complete works. Order rescheduled for 11/06 AM to complete works _x000D_12/6/2024:#Update Order incomplete as engineer needed more time to complete works. Order rescheduled for 11/06 AM to complete works _x000D_11/6/2024:#Update - Advanced upgrade required due to complexity of install/routing; proposal sent to VF to approve _x000D_10/6/2024:#Update - Advanced upgrade required due to complexity of install/routing; proposal sent to VF to approve _x000D_7/6/2024:#Update - Advanced upgrade required due to complexity of install/routing; proposal sent to VF to approve _x000D_6/6/2024:#Update - Advanced upgrade required due to complexity of install/routing; proposal sent to VF to approve _x000D_5/6/2024:#Update - Advanced upgrade required due to complexity of install/routing; proposal sent to VF to approve _x000D_4/6/2024:#Update - Advanced upgrade required due to complexity of install/routing; proposal sent to VF to approve _x000D_ | 9/9/2024:#Update Sent chaser to VF for site change charges _x000D_6/9/2024:#Update Sent chaser to VF for site change charges _x000D_5/9/2024:#Update Sent chaser to VF for site change charges _x000D_4/9/2024:#Update Sent chaser to VF for site change charges _x000D_14/6/2024:#Update Order incomplete as engineer needed more time to complete works. Order rescheduled for 11/06 AM to complete works _x000D_13/6/2024:#Update Order incomplete as engineer needed more time to complete works. Order rescheduled for 11/06 AM to complete works _x000D_12/6/2024:#Update Order incomplete as engineer needed more time to complete works. Order rescheduled for 11/06 AM to complete works _x000D_11/6/2024:#Update - Advanced upgrade required due to complexity of install/routing; proposal sent to VF to approve _x000D_10/6/2024:#Update - Advanced upgrade required due to complexity of install/routing; proposal sent to VF to approve _x000D_7/6/2024:#Update - Advanced upgrade required due to complexity of install/routing; proposal sent to VF to approve _x000D_6/6/2024:#Update - Advanced upgrade required due to complexity of install/routing; proposal sent to VF to approve _x000D_5/6/2024:#Update - Advanced upgrade required due to complexity of install/routing; proposal sent to VF to approve _x000D_4/6/2024:#Update - Advanced upgrade required due to complexity of install/routing; proposal sent to VF to approve _x000D_ | 0 | #Update Sent chaser to VF for site change charges |  |  |  |  | 3.Allwyn to arrange rtr install | VFP2300782 | 30013475 | 2.Commissioning | AM |  |  |  |  | Not Applicable |  |  |  | 2024-07-25 | [7 empty] | 0
455 | 666738 | 1137 | Batch 3 May24 | Type 1 | SOGEA | SAFFRON LANE POST OFFICE | LEICESTER | LE2 6UN | 2024-06-12 | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301334 | 30014027 | 6.Failed router install | AM |  | 2024-05-24 | 2024-06-11 | 2024-06-11 | TRUE | [7 empty] | 2024-07-02 | 23A004945958 |  | 2024-07-04 | 1
456 | 464506 | 1481 | Batch 4 Jun24 | Type 1 | SoGEA/Mobile | Costcutter | Northolt | UB5 4RR | 2024-06-12 | 6/9/2024:#Update Awaiting Allwyn to get hold of the retailer. _x000D_5/9/2024:#Update Awaiting Allwyn to get hold of the retailer. _x000D_4/9/2024:#Update Awaiting Allwyn to get hold of the retailer. _x000D_3/9/2024:#Update Awaiting Allwyn to get hold of the retailer. _x000D_2/9/2024:#Update Awaiting Allwyn to get hold of the retailer. _x000D_29/8/2024:#Update Awaiting Allwyn to get hold of the retailer. _x000D_28/8/2024:#Update Awaiting Allwyn to get hold of the retailer. _x000D_27/8/2024:#Update Awaiting Allwyn to get hold of the retailer. _x000D_22/8/2024:#Update Awaiting Allwyn to get hold of the retailer. _x000D_21/8/2024:#Update Awaiting Allwyn to get hold of the retailer. _x000D_20/8/2024:#Update Awaiting Allwyn to get hold of the retailer. _x000D_19/8/2024:#Update Awaiting Allwyn to get hold of the retailer. _x000D_19/8/2024:01431780 _x000D_16/8/2024:#Update Awaiting Allwyn to get hold of the retailer. _x000D_15/8/2024:#Update Awaiting Allwyn to get hold of the retailer. _x000D_14/8/2024:#Update Awaiting Allwyn to get hold of the retailer. _x000D_13/8/2024:#Update Awaiting Allwyn to get hold of the retailer. _x000D_12/8/2024:#Update Awaiting Allwyn to get hold of the retailer. _x000D_9/8/2024:#Update Awaiting Allwyn to get hold of the retailer. _x000D_8/8/2024:25/07/2024 _x000D_6/8/2024:25/07/2024 _x000D_5/8/2024:25/07/2024 _x000D_2/8/2024:25/07/2024 _x000D_1/8/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_30/7/2024:#Update Awaiting Allwyn to get hold of the retailer. _x000D_29/7/2024:#Update Awaiting Allwyn to get hold of the retailer. _x000D_29/7/2024:01431780 _x000D_26/7/2024:01431780 _x000D_24/7/2024:#Update Chased Allwyn for an update. _x000D_23/7/2024:#Update Chased Allwyn for an update. _x000D_22/7/2024:#Update Chased Allwyn for an update. _x000D_22/7/2024:#Update Chased Allwyn for an update. _x000D_14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update Awaiting Allwyn to get hold of the retailer. _x000D_6/9/2024:#Update Awaiting Allwyn to get hold of the retailer. _x000D_5/9/2024:#Update Awaiting Allwyn to get hold of the retailer. _x000D_4/9/2024:#Update Awaiting Allwyn to get hold of the retailer. _x000D_3/9/2024:#Update Awaiting Allwyn to get hold of the retailer. _x000D_2/9/2024:#Update Awaiting Allwyn to get hold of the retailer. _x000D_29/8/2024:#Update Awaiting Allwyn to get hold of the retailer. _x000D_28/8/2024:#Update Awaiting Allwyn to get hold of the retailer. _x000D_27/8/2024:#Update Awaiting Allwyn to get hold of the retailer. _x000D_22/8/2024:#Update Awaiting Allwyn to get hold of the retailer. _x000D_21/8/2024:#Update Awaiting Allwyn to get hold of the retailer. _x000D_20/8/2024:#Update Awaiting Allwyn to get hold of the retailer. _x000D_19/8/2024:#Update Awaiting Allwyn to get hold of the retailer. _x000D_19/8/2024:01431780 _x000D_16/8/2024:#Update Awaiting Allwyn to get hold of the retailer. _x000D_15/8/2024:#Update Awaiting Allwyn to get hold of the retailer. _x000D_14/8/2024:#Update Awaiting Allwyn to get hold of the retailer. _x000D_13/8/2024:#Update Awaiting Allwyn to get hold of the retailer. _x000D_12/8/2024:#Update Awaiting Allwyn to get hold of the retailer. _x000D_9/8/2024:#Update Awaiting Allwyn to get hold of the retailer. _x000D_8/8/2024:25/07/2024 _x000D_6/8/2024:25/07/2024 _x000D_5/8/2024:25/07/2024 _x000D_2/8/2024:25/07/2024 _x000D_1/8/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_30/7/2024:#Update Awaiting Allwyn to get hold of the retailer. _x000D_29/7/2024:#Update Awaiting Allwyn to get hold of the retailer. _x000D_29/7/2024:01431780 _x000D_26/7/2024:01431780 _x000D_24/7/2024:#Update Chased Allwyn for an update. _x000D_23/7/2024:#Update Chased Allwyn for an update. _x000D_22/7/2024:#Update Chased Allwyn for an update. _x000D_22/7/2024:#Update Chased Allwyn for an update. _x000D_14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update Awaiting Allwyn to get hold of the retailer. | 2024-06-07 |  |  |  | 5.CSL | VFS984732 | 30015658 | 1.Provisioning | AM |  | 2024-06-11 | 2024-08-23 |  | 0 | [11 empty] | 0
457 | 111974 | 1482 | Batch 4 Jun24 | Type 1 | SOGEA | Costcutter | BEDFORD | MK40 2QH | 2024-06-12 | 19/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect Product Please check with end user and reappoint the order if still required. _x000D_18/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect Product Please check with end user and reappoint the order if still required. _x000D_17/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect Product Please check with end user and reappoint the order if still required. _x000D_14/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect Product Please check with end user and reappoint the order if still required. _x000D_13/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect Product Please check with end user and reappoint the order if still required. _x000D_12/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect Product Please check with end user and reappoint the order if still required. _x000D_18/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect Product Please check with end user and reappoint the order if still required. _x000D_17/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect Product Please check with end user and reappoint the order if still required. _x000D_14/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect Product Please check with end user and reappoint the order if still required. _x000D_13/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect Product Please check with end user and reappoint the order if still required. _x000D_12/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984733 | 30015661 | 2.Commissioning | AM |  | 2024-06-11 | 2024-06-11 | 2024-06-12 | TRUE |  |  |  | 2024-07-08 | [7 empty] | 0
458 | 465283 | 1483 | Batch 4 Jun24 | Type 1 | SoGEA/Mobile | Royal Victoria Infirmary | Newcastle upon Tyne | NE1 4LP | 2024-06-12 | 6/9/2024:#Update - SOGEA/FTTP is not available due to capacity into the property and ADSL will have to be ordered once agreed with Allwyn _x000D_5/9/2024:#Update - SOGEA/FTTP is not available due to capacity into the property and ADSL will have to be ordered once agreed with Allwyn _x000D_4/9/2024:#Update - SOGEA/FTTP is not available due to capacity into the property and ADSL will have to be ordered once agreed with Allwyn _x000D_3/9/2024:#Update - SOGEA/FTTP is not available due to capacity into the property and ADSL will have to be ordered once agreed with Allwyn _x000D_2/9/2024:#Update - SOGEA/FTTP is not available due to capacity into the property and ADSL will have to be ordered once agreed with Allwyn _x000D_29/8/2024:#Update - SOGEA/FTTP is not available due to capacity into the property and ADSL will have to be ordered once agreed with Allwyn _x000D_28/8/2024:#Update - SOGEA/FTTP is not available due to capacity into the property and ADSL will have to be ordered once agreed with Allwyn _x000D_27/8/2024:#Update - SOGEA/FTTP is not available due to capacity into the property and ADSL will have to be ordered once agreed with Allwyn _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - SOGEA/FTTP is not available due to capacity into the property and ADSL will have to be ordered once agreed with Allwyn _x000D_6/9/2024:#Update - SOGEA/FTTP is not available due to capacity into the property and ADSL will have to be ordered once agreed with Allwyn _x000D_5/9/2024:#Update - SOGEA/FTTP is not available due to capacity into the property and ADSL will have to be ordered once agreed with Allwyn _x000D_4/9/2024:#Update - SOGEA/FTTP is not available due to capacity into the property and ADSL will have to be ordered once agreed with Allwyn _x000D_3/9/2024:#Update - SOGEA/FTTP is not available due to capacity into the property and ADSL will have to be ordered once agreed with Allwyn _x000D_2/9/2024:#Update - SOGEA/FTTP is not available due to capacity into the property and ADSL will have to be ordered once agreed with Allwyn _x000D_29/8/2024:#Update - SOGEA/FTTP is not available due to capacity into the property and ADSL will have to be ordered once agreed with Allwyn _x000D_28/8/2024:#Update - SOGEA/FTTP is not available due to capacity into the property and ADSL will have to be ordered once agreed with Allwyn _x000D_27/8/2024:#Update - SOGEA/FTTP is not available due to capacity into the property and ADSL will have to be ordered once agreed with Allwyn _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update - SOGEA/FTTP is not available due to capacity into the property and ADSL will have to be ordered once agreed with Allwyn | 2024-06-07 |  |  |  | 5.CSL | VFS984735 | 30015582 | 1.Provisioning | AM |  | 2024-06-11 | 2024-06-11 |  | 0 | [11 empty] | 0
459 | 634723 | 1485 | Batch 4 Jun24 | Type 1 | FTTP | Russells Food & Drink | BELFAST | BT4 1NT | 2024-06-12 | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2338518 | 30015368 | 2.Commissioning | AM |  | 2024-06-11 | 2024-06-11 | 2024-06-11 | TRUE |  |  |  | 2024-07-17 | [7 empty] | 0
460 | 446160 | 1494 | Batch 4 Jun24 | Type 1 | SOGEA | BIRD'S CORNER | RHYL | LL18 5LS | 2024-06-12 | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_11/6/2024:#Update Third party supplier delay: Network Planning issues. Awaiting further updates from Openreach. _x000D_10/6/2024:#Update Third party supplier delay: Network Planning issues. Awaiting further updates from Openreach. _x000D_7/6/2024:#Update Third party supplier delay: Network Planning issues. Awaiting further updates from Openreach. _x000D_6/6/2024:#Update Third party supplier delay: Network Planning issues. Awaiting further updates from Openreach. _x000D_5/6/2024:#Update Third party supplier delay: Network Planning issues. Awaiting further updates from Openreach. _x000D_4/6/2024:#Update Third party supplier delay: Network Planning issues. Awaiting further updates from Openreach. _x000D_ | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_11/6/2024:#Update Third party supplier delay: Network Planning issues. Awaiting further updates from Openreach. _x000D_10/6/2024:#Update Third party supplier delay: Network Planning issues. Awaiting further updates from Openreach. _x000D_7/6/2024:#Update Third party supplier delay: Network Planning issues. Awaiting further updates from Openreach. _x000D_6/6/2024:#Update Third party supplier delay: Network Planning issues. Awaiting further updates from Openreach. _x000D_5/6/2024:#Update Third party supplier delay: Network Planning issues. Awaiting further updates from Openreach. _x000D_4/6/2024:#Update Third party supplier delay: Network Planning issues. Awaiting further updates from Openreach. _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2338521 | 30015592 | 2.Commissioning | AM |  | 2024-06-11 | 2024-06-11 | 2024-06-11 | TRUE |  |  |  | 2024-07-19 | [7 empty] | 0
461 | 638062 | 1497 | Batch 4 Jun24 | Type 1 | SOGEA | Post Office | London | N19 5QU | 2024-06-12 | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984746 | 30015637 | 6.Failed router install | AM |  | 2024-06-11 | 2024-06-11 | 2024-06-11 | TRUE | [7 empty] | 2024-07-02 | 23A004945285 |  | 2024-07-04 | 1
462 | 113212 | 1499 | Batch 4 Jun24 | Type 1 | FTTP | McFaddens Newsagent | STRABANE | BT82 9AB | 2024-06-12 | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2338523 | 30015344 | 6.Failed router install | AM |  | 2024-06-11 | 2024-06-11 | 2024-06-11 | TRUE |  |  |  | 2024-07-15 |  |  |  | 2024-07-15 | 242005010289 |  | 2024-07-16 | 1
463 | 615677 | 1501 | Batch 4 Jun24 | Type 1 | SOGEA | Nisa Local | PISLEY | PA3 1LW | 2024-06-12 | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984749 | 30015474 | 2.Commissioning | AM |  | 2024-06-11 | 2024-06-11 | 2024-06-11 | TRUE |  |  |  | 2024-07-05 | [7 empty] | 0
464 | 233290 | 1820 | Batch 4 Jun24 | Type 1 | SoGEA/Mobile | Farnsworth | NEWPORT | PO30 1LQ | 2024-06-12 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_28/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_27/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_28/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_27/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 0 | 0 | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1065575 | 30015248 | 2.Commissioning | AM |  | 2024-08-23 | 2024-08-23 |  | 0 |  |  |  | 2024-07-18 | [7 empty] | 0
465 | 646558 | 1821 | Batch 4 Jun24 | Type 1 | SoGEA/Mobile | JWL Perkins and Son | Horncastle | LN9 5HB | 2024-06-12 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 0 | 0 | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1065577 | 30015237 | 2.Commissioning | AM |  | 2024-08-23 | 2024-08-23 |  | 0 |  |  |  | 2024-09-06 | [7 empty] | 0
466 | 658914 | 1823 | Batch 4 Jun24 | Type 1 | SOGEA | Premier Malcolms | Dudley | DY2 7LJ | 2024-06-12 | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983348 | 30015206 | 2.Commissioning | AM |  | 2024-06-11 | 2024-06-11 | 2024-06-11 | TRUE |  |  |  | 2024-07-11 | [7 empty] | 0
467 | 432293 | 1824 | Batch 4 Jun24 | Type 1 | SOGEA | PADWAGGAS NEWSAGENT | PAISLEY | PA1 3PN | 2024-06-12 | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983349 | 30015235 | 2.Commissioning | AM |  | 2024-06-11 | 2024-06-11 | 2024-06-11 | TRUE |  |  |  | 2024-09-05 | [7 empty] | 0
468 | 421425 | 1826 | Batch 4 Jun24 | Type 1 | SOGEA | TAKELEY NEWS | BISHOP'S STORTFORD | CM22 6SH | 2024-06-12 | 19/7/2024:#Update Retailer happy with new appointment 30/07, AM. _x000D_18/7/2024:#Update Retailer happy with new appointment 30/07, AM. _x000D_17/7/2024:#Update Retailer happy with new appointment 30/07, AM. _x000D_16/7/2024:#Update Retailer happy with new appointment 30/07, AM. _x000D_15/7/2024:#Update Retailer happy with new appointment 30/07, AM. _x000D_12/7/2024:#Update Retailer happy with new appointment 30/07, AM. _x000D_11/7/2024:#Update Retailer happy with new appointment 30/07, AM. _x000D_10/7/2024:#Update Retailer happy with new appointment 30/07, AM. _x000D_9/7/2024:#Update Retailer happy with new appointment 30/07, AM. _x000D_4/7/2024:#Update Order delayed due to dig works, we will provide updates when they become available. _x000D_3/7/2024:#Update Order delayed due to dig works, we will provide updates when they become available. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update Order delayed due to dig works, we will provide updates when they become available. _x000D_27/6/2024:#Update Order delayed due to dig works, we will provide updates when they become available. _x000D_25/6/2024:#Update Order delayed due to dig works, we will provide updates when they become available. _x000D_24/6/2024:#Update Order delayed due to dig works, we will provide updates when they become available. _x000D_20/6/2024:0 _x000D_19/6/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 21/06/2024. We will continue to provide update as they become available. _x000D_18/6/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 21/06/2024. We will continue to provide update as they become available. _x000D_17/6/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 21/06/2024. We will continue to provide update as they become available. _x000D_14/6/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 21/06/2024. We will continue to provide update as they become available. _x000D_13/6/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 21/06/2024. We will continue to provide update as they become available. _x000D_12/6/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 21/06/2024. We will continue to provide update as they become available. _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 19/7/2024:#Update Retailer happy with new appointment 30/07, AM. _x000D_18/7/2024:#Update Retailer happy with new appointment 30/07, AM. _x000D_17/7/2024:#Update Retailer happy with new appointment 30/07, AM. _x000D_16/7/2024:#Update Retailer happy with new appointment 30/07, AM. _x000D_15/7/2024:#Update Retailer happy with new appointment 30/07, AM. _x000D_12/7/2024:#Update Retailer happy with new appointment 30/07, AM. _x000D_11/7/2024:#Update Retailer happy with new appointment 30/07, AM. _x000D_10/7/2024:#Update Retailer happy with new appointment 30/07, AM. _x000D_9/7/2024:#Update Retailer happy with new appointment 30/07, AM. _x000D_4/7/2024:#Update Order delayed due to dig works, we will provide updates when they become available. _x000D_3/7/2024:#Update Order delayed due to dig works, we will provide updates when they become available. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update Order delayed due to dig works, we will provide updates when they become available. _x000D_27/6/2024:#Update Order delayed due to dig works, we will provide updates when they become available. _x000D_25/6/2024:#Update Order delayed due to dig works, we will provide updates when they become available. _x000D_24/6/2024:#Update Order delayed due to dig works, we will provide updates when they become available. _x000D_20/6/2024:0 _x000D_19/6/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 21/06/2024. We will continue to provide update as they become available. _x000D_18/6/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 21/06/2024. We will continue to provide update as they become available. _x000D_17/6/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 21/06/2024. We will continue to provide update as they become available. _x000D_14/6/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 21/06/2024. We will continue to provide update as they become available. _x000D_13/6/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 21/06/2024. We will continue to provide update as they become available. _x000D_12/6/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 21/06/2024. We will continue to provide update as they become available. _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983350 | 30015219 | 6.Failed router install | AM |  | 2024-06-11 | 2024-06-11 | 2024-06-11 | TRUE |  |  |  | 2024-07-09 |  |  |  | 2024-07-09 | 242005008576 |  |  | 1
469 | 616223 | 1827 | Batch 4 Jun24 | Type 1 | SoGEA/Mobile | The Gazette | Blackpool | FY4 1AD | 2024-06-12 | 20/8/2024:#Update Order has been delayed. Dig work required. Our Suppliers have given us a review date of 15/08/2024. We will continue to provide updates as they become available. _x000D_19/8/2024:#Update Order has been delayed. Dig work required. Our Suppliers have given us a review date of 15/08/2024. We will continue to provide updates as they become available. _x000D_19/8/2024:01434026 _x000D_16/8/2024:#Update Order has been delayed. Dig work required. Our Suppliers have given us a review date of 15/08/2024. We will continue to provide updates as they become available. _x000D_15/8/2024:#Update Order has been delayed. Dig work required. Our Suppliers have given us a review date of 15/08/2024. We will continue to provide updates as they become available. _x000D_14/8/2024:#Update Order has been delayed. Dig work required. Our Suppliers have given us a review date of 15/08/2024. We will continue to provide updates as they become available. _x000D_13/8/2024:#Update Order has been delayed. Dig work required. Our Suppliers have given us a review date of 15/08/2024. We will continue to provide updates as they become available. _x000D_12/8/2024:#Update Order has been delayed. Dig work required. Our Suppliers have given us a review date of 15/08/2024. We will continue to provide updates as they become available. _x000D_9/8/2024:#Update - Order has been delayed as dig work is required. CSL will update as more information become available. _x000D_8/8/2024:31/07/2024 _x000D_6/8/2024:31/07/2024 _x000D_5/8/2024:31/07/2024 _x000D_2/8/2024:31/07/2024 _x000D_1/8/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_30/7/2024:#Update Retailer happy with new appointment 30/07, AM. _x000D_29/7/2024:#Update Retailer happy with new appointment 30/07, AM. _x000D_29/7/2024:01434026 _x000D_26/7/2024:01434026 _x000D_24/7/2024:#Update Retailer happy with new appointment 30/07, AM. _x000D_23/7/2024:#Update Retailer happy with new appointment 30/07, AM. _x000D_22/7/2024:#Update Retailer happy with new appointment 30/07, AM. _x000D_22/7/2024:#Update Retailer happy with new appointment 30/07, AM. _x000D_14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 20/8/2024:#Update Order has been delayed. Dig work required. Our Suppliers have given us a review date of 15/08/2024. We will continue to provide updates as they become available. _x000D_19/8/2024:#Update Order has been delayed. Dig work required. Our Suppliers have given us a review date of 15/08/2024. We will continue to provide updates as they become available. _x000D_19/8/2024:01434026 _x000D_16/8/2024:#Update Order has been delayed. Dig work required. Our Suppliers have given us a review date of 15/08/2024. We will continue to provide updates as they become available. _x000D_15/8/2024:#Update Order has been delayed. Dig work required. Our Suppliers have given us a review date of 15/08/2024. We will continue to provide updates as they become available. _x000D_14/8/2024:#Update Order has been delayed. Dig work required. Our Suppliers have given us a review date of 15/08/2024. We will continue to provide updates as they become available. _x000D_13/8/2024:#Update Order has been delayed. Dig work required. Our Suppliers have given us a review date of 15/08/2024. We will continue to provide updates as they become available. _x000D_12/8/2024:#Update Order has been delayed. Dig work required. Our Suppliers have given us a review date of 15/08/2024. We will continue to provide updates as they become available. _x000D_9/8/2024:#Update - Order has been delayed as dig work is required. CSL will update as more information become available. _x000D_8/8/2024:31/07/2024 _x000D_6/8/2024:31/07/2024 _x000D_5/8/2024:31/07/2024 _x000D_2/8/2024:31/07/2024 _x000D_1/8/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_30/7/2024:#Update Retailer happy with new appointment 30/07, AM. _x000D_29/7/2024:#Update Retailer happy with new appointment 30/07, AM. _x000D_29/7/2024:01434026 _x000D_26/7/2024:01434026 _x000D_24/7/2024:#Update Retailer happy with new appointment 30/07, AM. _x000D_23/7/2024:#Update Retailer happy with new appointment 30/07, AM. _x000D_22/7/2024:#Update Retailer happy with new appointment 30/07, AM. _x000D_22/7/2024:#Update Retailer happy with new appointment 30/07, AM. _x000D_14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983351 | 30015212 | 2.Commissioning | AM |  | 2024-06-11 | 2024-07-30 |  | 0 |  |  |  | 2024-09-18 | [7 empty] | 0
470 | 463000 | 1979 | Batch 4 Jun24 | Type 1 | SOGEA | Spar Stores | Wrexham | LL14 5HA | 2024-06-12 | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996844 | 30016006 | 2.Commissioning | AM |  | 2024-06-11 | 2024-06-11 | 2024-06-11 | TRUE |  |  |  | 2024-07-19 | [7 empty] | 0
471 | 672637 | 2011 | Batch 4 Jun24 | Type 1 | SOGEA | Post Office | Winchester | SO22 6EW | 2024-06-12 | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996847 | 30015985 | 6.Failed router install | AM |  | 2024-06-11 | 2024-06-11 | 2024-06-11 | TRUE |  |  |  | 2024-07-04 |  |  |  | 2024-07-04 | 242005008640 |  |  | 1
472 | 482290 | 2038 | Batch 4 Jun24 | Type 1 | SOGEA | Spar Stores | Bridport | DT6 3JX | 2024-06-12 | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996848 | 30016014 | 2.Commissioning | AM |  | 2024-06-11 | 2024-06-11 | 2024-06-11 | TRUE |  |  |  | 2024-07-09 | [7 empty] | 0
473 | 458710 | 2097 | Batch 4 Jun24 | Type 1 | SoGEA/Mobile | Spar Stores | Lincoln | LN6 0LP | 2024-06-12 | 6/9/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_5/9/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_4/9/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_3/9/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_2/9/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_29/8/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_28/8/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_27/8/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_22/8/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_21/8/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_20/8/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_19/8/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_19/8/2024:01431961 _x000D_16/8/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_15/8/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_14/8/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_13/8/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_12/8/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_9/8/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_8/8/2024:19/06/2024 _x000D_6/8/2024:19/06/2024 _x000D_5/8/2024:19/06/2024 _x000D_2/8/2024:19/06/2024 _x000D_1/8/2024:19/06/2024 _x000D_31/7/2024:19/06/2024 _x000D_31/7/2024:19/06/2024 _x000D_30/7/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_29/7/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_29/7/2024:01431961 _x000D_26/7/2024:01431961 _x000D_24/7/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_23/7/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_22/7/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_22/7/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 9/9/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_6/9/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_5/9/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_4/9/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_3/9/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_2/9/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_29/8/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_28/8/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_27/8/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_22/8/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_21/8/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_20/8/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_19/8/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_19/8/2024:01431961 _x000D_16/8/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_15/8/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_14/8/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_13/8/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_12/8/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_9/8/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_8/8/2024:19/06/2024 _x000D_6/8/2024:19/06/2024 _x000D_5/8/2024:19/06/2024 _x000D_2/8/2024:19/06/2024 _x000D_1/8/2024:19/06/2024 _x000D_31/7/2024:19/06/2024 _x000D_31/7/2024:19/06/2024 _x000D_30/7/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_29/7/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_29/7/2024:01431961 _x000D_26/7/2024:01431961 _x000D_24/7/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_23/7/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_22/7/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_22/7/2024:#Update - Proposal sent to Vodafone on 19/06. _x000D_14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | Update: Order Amended | #Update - Proposal sent to Vodafone on 19/06. | 2024-06-07 |  |  |  | 5.CSL | VFS996849 | 30016087 | 1.Provisioning | AM |  | 2024-06-11 | 2024-08-30 |  | 0 | [11 empty] | 0
474 | 486439 | 2104 | Batch 4 Jun24 | Type 1 | SOGEA | Spar Stores | Rochester | ME3 9AH | 2024-06-12 | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996853 | 30016088 | 6.Failed router install | AM |  | 2024-06-11 | 2024-06-11 | 2024-06-11 | TRUE |  |  |  | 2024-07-05 |  |  |  | 2024-08-23 | 242005011117 | 242005011117 | 2024-08-27 | 1
475 | 424579 | 2109 | Batch 4 Jun24 | Type 1 | SOGEA | Spar Stores | Dumfries | DG1 4AT | 2024-06-12 | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996857 | 30015967 | 2.Commissioning | AM |  | 2024-06-11 | 2024-06-11 | 2024-06-11 | TRUE |  |  |  | 2024-07-05 | [7 empty] | 0
476 | 654433 | 2113 | Batch 4 Jun24 | Type 1 | SOGEA | Spar/Bargain Booze | South Shields | NE34 7LZ | 2024-06-12 | 19/7/2024:#Update Order delayed due to dig work required. We will provide updates as they become available. _x000D_18/7/2024:#Update Order delayed due to dig work required. We will provide updates as they become available. _x000D_17/7/2024:#Update Order delayed due to dig work required. We will provide updates as they become available. _x000D_16/7/2024:#Update Order delayed due to dig work required. We will provide updates as they become available. _x000D_15/7/2024:#Update Order delayed due to dig work required. We will provide updates as they become available. _x000D_12/7/2024:#Update Order delayed due to dig work required. We will provide updates as they become available. _x000D_11/7/2024:#Update Order delayed due to dig work required. We will provide updates as they become available. _x000D_10/7/2024:#Update Order delayed due to dig work required. We will provide updates as they become available. _x000D_9/7/2024:#Update Order delayed due to dig work required. We will provide updates as they become available. _x000D_4/7/2024:#Update Order delayed due to dig work required. We will provide updates as they become available. _x000D_3/7/2024:#Update Order delayed due to dig work required. We will provide updates as they become available. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update Order delayed due to dig work required. We will provide updates as they become available. _x000D_27/6/2024:#Update Order delayed due to dig work required. We will provide updates as they become available. _x000D_25/6/2024:#Update Order delayed due to dig work required. We will provide updates as they become available. _x000D_24/6/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 02/07/2024. We will continue to provide update as they become available. _x000D_20/6/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 24/06/2024. We will continue to provide update as they become available. _x000D_19/6/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 24/06/2024. We will continue to provide update as they become available. _x000D_18/6/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 24/06/2024. We will continue to provide update as they become available. _x000D_17/6/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 24/06/2024. We will continue to provide update as they become available. _x000D_14/6/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 17/06/2024. We will continue to provide update as they become available. _x000D_13/6/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 17/06/2024. We will continue to provide update as they become available. _x000D_12/6/2024:Supplier Delay: Issues with provision of the underground network, please await for further details. _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 19/7/2024:#Update Order delayed due to dig work required. We will provide updates as they become available. _x000D_18/7/2024:#Update Order delayed due to dig work required. We will provide updates as they become available. _x000D_17/7/2024:#Update Order delayed due to dig work required. We will provide updates as they become available. _x000D_16/7/2024:#Update Order delayed due to dig work required. We will provide updates as they become available. _x000D_15/7/2024:#Update Order delayed due to dig work required. We will provide updates as they become available. _x000D_12/7/2024:#Update Order delayed due to dig work required. We will provide updates as they become available. _x000D_11/7/2024:#Update Order delayed due to dig work required. We will provide updates as they become available. _x000D_10/7/2024:#Update Order delayed due to dig work required. We will provide updates as they become available. _x000D_9/7/2024:#Update Order delayed due to dig work required. We will provide updates as they become available. _x000D_4/7/2024:#Update Order delayed due to dig work required. We will provide updates as they become available. _x000D_3/7/2024:#Update Order delayed due to dig work required. We will provide updates as they become available. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update Order delayed due to dig work required. We will provide updates as they become available. _x000D_27/6/2024:#Update Order delayed due to dig work required. We will provide updates as they become available. _x000D_25/6/2024:#Update Order delayed due to dig work required. We will provide updates as they become available. _x000D_24/6/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 02/07/2024. We will continue to provide update as they become available. _x000D_20/6/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 24/06/2024. We will continue to provide update as they become available. _x000D_19/6/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 24/06/2024. We will continue to provide update as they become available. _x000D_18/6/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 24/06/2024. We will continue to provide update as they become available. _x000D_17/6/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 24/06/2024. We will continue to provide update as they become available. _x000D_14/6/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 17/06/2024. We will continue to provide update as they become available. _x000D_13/6/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 17/06/2024. We will continue to provide update as they become available. _x000D_12/6/2024:Supplier Delay: Issues with provision of the underground network, please await for further details. _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996918 | 30016035 | 2.Commissioning | AM |  | 2024-06-11 | 2024-06-11 | 2024-06-11 | TRUE |  |  |  | 2024-07-17 | [7 empty] | 0
477 | 234097 | 2122 | Batch 4 Jun24 | Type 1 | SoGEA/Mobile | Spar Stores | Llangefni | LL77 7LT | 2024-06-12 | 6/9/2024:#Update Chased Allwyn for an update _x000D_5/9/2024:#Update Chased Allwyn for an update _x000D_4/9/2024:#Update Chased Allwyn for an update _x000D_3/9/2024:#Update Chased Allwyn for an update _x000D_2/9/2024:#Update Chased Allwyn for an update _x000D_29/8/2024:#Update Chased Allwyn for an update _x000D_28/8/2024:#Update Chased Allwyn for an update _x000D_27/8/2024:#Update Chased Allwyn for an update _x000D_22/8/2024:#Update Chased Allwyn for an update _x000D_21/8/2024:#Update Chased Allwyn for an update _x000D_20/8/2024:#Update Chased Allwyn for an update _x000D_19/8/2024:#Update Chased Allwyn for an update _x000D_19/8/2024:01434764 _x000D_16/8/2024:#Update Chased Allwyn for an update _x000D_15/8/2024:#Update Chased Allwyn for an update _x000D_14/8/2024:#Update Chased Allwyn for an update _x000D_13/8/2024:#Update Chased Allwyn for an update _x000D_12/8/2024:#Update Chased Allwyn for an update _x000D_9/8/2024:#Update Chased Allwyn for an update _x000D_8/8/2024:25/07/2024 _x000D_6/8/2024:25/07/2024 _x000D_5/8/2024:25/07/2024 _x000D_2/8/2024:25/07/2024 _x000D_1/8/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_30/7/2024:#Update Chased Allwyn for an update _x000D_29/7/2024:#Update Chased Allwyn for an update _x000D_29/7/2024:01434764 _x000D_26/7/2024:01434764 _x000D_24/7/2024:#Update Order delayed due to dig work required. We will provide updates as they become available. _x000D_23/7/2024:#Update Order delayed due to dig work required. We will provide updates as they become available. _x000D_22/7/2024:#Update Order delayed due to dig work required. We will provide updates as they become available. _x000D_22/7/2024:#Update Order delayed due to dig work required. We will provide updates as they become available. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:Update: Order Amended _x000D_15/7/2024:Update: Order Amended _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:Update: Order Amended _x000D_24/6/2024:Update: Order Amended _x000D_20/6/2024:Update: Order Amended _x000D_19/6/2024:Update: Order Amended _x000D_18/6/2024:Your order has been delayed. The appointment has been delayed due to a Hazard by OR. Please check with end user and reappoint the order if still required. _x000D_17/6/2024:Your order has been delayed. The appointment has been delayed due to a Hazard by OR. Please check with end user and reappoint the order if still required. _x000D_14/6/2024:Your order has been delayed. The appointment has been delayed due to a Hazard by OR. Please check with end user and reappoint the order if still required. _x000D_13/6/2024:Your order has been delayed. The appointment has been delayed due to a Hazard by OR. Please check with end user and reappoint the order if still required. _x000D_12/6/2024:Delay on Engineer activities. Supplier will arrange new appointment _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 9/9/2024:#Update Chased Allwyn for an update _x000D_6/9/2024:#Update Chased Allwyn for an update _x000D_5/9/2024:#Update Chased Allwyn for an update _x000D_4/9/2024:#Update Chased Allwyn for an update _x000D_3/9/2024:#Update Chased Allwyn for an update _x000D_2/9/2024:#Update Chased Allwyn for an update _x000D_29/8/2024:#Update Chased Allwyn for an update _x000D_28/8/2024:#Update Chased Allwyn for an update _x000D_27/8/2024:#Update Chased Allwyn for an update _x000D_22/8/2024:#Update Chased Allwyn for an update _x000D_21/8/2024:#Update Chased Allwyn for an update _x000D_20/8/2024:#Update Chased Allwyn for an update _x000D_19/8/2024:#Update Chased Allwyn for an update _x000D_19/8/2024:01434764 _x000D_16/8/2024:#Update Chased Allwyn for an update _x000D_15/8/2024:#Update Chased Allwyn for an update _x000D_14/8/2024:#Update Chased Allwyn for an update _x000D_13/8/2024:#Update Chased Allwyn for an update _x000D_12/8/2024:#Update Chased Allwyn for an update _x000D_9/8/2024:#Update Chased Allwyn for an update _x000D_8/8/2024:25/07/2024 _x000D_6/8/2024:25/07/2024 _x000D_5/8/2024:25/07/2024 _x000D_2/8/2024:25/07/2024 _x000D_1/8/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_30/7/2024:#Update Chased Allwyn for an update _x000D_29/7/2024:#Update Chased Allwyn for an update _x000D_29/7/2024:01434764 _x000D_26/7/2024:01434764 _x000D_24/7/2024:#Update Order delayed due to dig work required. We will provide updates as they become available. _x000D_23/7/2024:#Update Order delayed due to dig work required. We will provide updates as they become available. _x000D_22/7/2024:#Update Order delayed due to dig work required. We will provide updates as they become available. _x000D_22/7/2024:#Update Order delayed due to dig work required. We will provide updates as they become available. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:Update: Order Amended _x000D_15/7/2024:Update: Order Amended _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:Update: Order Amended _x000D_24/6/2024:Update: Order Amended _x000D_20/6/2024:Update: Order Amended _x000D_19/6/2024:Update: Order Amended _x000D_18/6/2024:Your order has been delayed. The appointment has been delayed due to a Hazard by OR. Please check with end user and reappoint the order if still required. _x000D_17/6/2024:Your order has been delayed. The appointment has been delayed due to a Hazard by OR. Please check with end user and reappoint the order if still required. _x000D_14/6/2024:Your order has been delayed. The appointment has been delayed due to a Hazard by OR. Please check with end user and reappoint the order if still required. _x000D_13/6/2024:Your order has been delayed. The appointment has been delayed due to a Hazard by OR. Please check with end user and reappoint the order if still required. _x000D_12/6/2024:Delay on Engineer activities. Supplier will arrange new appointment _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | Update: Order Amended | #Update Chased Allwyn for an update | 2024-06-07 |  |  |  | 5.CSL | VFS996855 | 30016056 | 1.Provisioning | AM |  | 2024-06-11 | 2024-06-11 |  | 0 | [11 empty] | 0
478 | 429806 | 2150 | Batch 4 Jun24 | Type 3 | SoGEA/Mobile | Spar Stores | Wigan | WN1 3UB | 2024-07-11 | 6/9/2024:#Update - this site has changed to a site type 3/mobile only _x000D_5/9/2024:#Update - this site has changed to a site type 3/mobile only _x000D_4/9/2024:#Update - this site has changed to a site type 3/mobile only _x000D_3/9/2024:#Update - this site has changed to a site type 3/mobile only _x000D_2/9/2024:#Update - this site has changed to a site type 3/mobile only _x000D_29/8/2024:#Update - this site has changed to a site type 3/mobile only _x000D_28/8/2024:#Update - this site has changed to a site type 3/mobile only _x000D_27/8/2024:#Update - this site has changed to a site type 3/mobile only _x000D_22/8/2024:#Update - this site has changed to a site type 3/mobile only _x000D_21/8/2024:#Update - this site has changed to a site type 3/mobile only _x000D_20/8/2024:#Update Upgrade charges sent o VF for approval. _x000D_19/8/2024:#Update Upgrade charges sent o VF for approval. _x000D_19/8/2024:01432261 _x000D_16/8/2024:#Update Upgrade charges sent o VF for approval. _x000D_15/8/2024:#Update Upgrade charges sent o VF for approval. _x000D_14/8/2024:#Update Upgrade charges sent o VF for approval. _x000D_13/8/2024:#Update Upgrade charges sent o VF for approval. _x000D_12/8/2024:#Update Upgrade charges sent o VF for approval. _x000D_9/8/2024:#Update Upgrade charges sent o VF for approval. _x000D_8/8/2024:22/07/2024 _x000D_6/8/2024:22/07/2024 _x000D_5/8/2024:22/07/2024 _x000D_2/8/2024:22/07/2024 _x000D_1/8/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_30/7/2024:#Update Upgrade charges sent o VF for approval. _x000D_29/7/2024:#Update Upgrade charges sent o VF for approval. _x000D_29/7/2024:01432261 _x000D_26/7/2024:01432261 _x000D_24/7/2024:#Update Upgrade charges sent o VF for approval. _x000D_23/7/2024:#Update Upgrade charges sent o VF for approval. _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 9/9/2024:#Update - this site has changed to a site type 3/mobile only _x000D_6/9/2024:#Update - this site has changed to a site type 3/mobile only _x000D_5/9/2024:#Update - this site has changed to a site type 3/mobile only _x000D_4/9/2024:#Update - this site has changed to a site type 3/mobile only _x000D_3/9/2024:#Update - this site has changed to a site type 3/mobile only _x000D_2/9/2024:#Update - this site has changed to a site type 3/mobile only _x000D_29/8/2024:#Update - this site has changed to a site type 3/mobile only _x000D_28/8/2024:#Update - this site has changed to a site type 3/mobile only _x000D_27/8/2024:#Update - this site has changed to a site type 3/mobile only _x000D_22/8/2024:#Update - this site has changed to a site type 3/mobile only _x000D_21/8/2024:#Update - this site has changed to a site type 3/mobile only _x000D_20/8/2024:#Update Upgrade charges sent o VF for approval. _x000D_19/8/2024:#Update Upgrade charges sent o VF for approval. _x000D_19/8/2024:01432261 _x000D_16/8/2024:#Update Upgrade charges sent o VF for approval. _x000D_15/8/2024:#Update Upgrade charges sent o VF for approval. _x000D_14/8/2024:#Update Upgrade charges sent o VF for approval. _x000D_13/8/2024:#Update Upgrade charges sent o VF for approval. _x000D_12/8/2024:#Update Upgrade charges sent o VF for approval. _x000D_9/8/2024:#Update Upgrade charges sent o VF for approval. _x000D_8/8/2024:22/07/2024 _x000D_6/8/2024:22/07/2024 _x000D_5/8/2024:22/07/2024 _x000D_2/8/2024:22/07/2024 _x000D_1/8/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_30/7/2024:#Update Upgrade charges sent o VF for approval. _x000D_29/7/2024:#Update Upgrade charges sent o VF for approval. _x000D_29/7/2024:01432261 _x000D_26/7/2024:01432261 _x000D_24/7/2024:#Update Upgrade charges sent o VF for approval. _x000D_23/7/2024:#Update Upgrade charges sent o VF for approval. _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 0 | #Update - this site has changed to a site type 3/mobile only | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996856 | 30016009 | 2.Commissioning | AM |  |  |  |  | 0 |  |  |  | 2024-08-21 | [7 empty] | 0
479 | 458999 | 2160 | Batch 4 Jun24 | Type 1 | SOGEA | Spar Stores | Newquay | TR7 2RT | 2024-06-26 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:#Update Retailer aware of new appointment 15/07, AM _x000D_14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:#Update Retailer aware of new appointment 15/07, AM _x000D_14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 0 | 0 | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996860 | 30015993 | 2.Commissioning | AM | [16 empty] | 0
480 | 427942 | 2202 | Batch 4 Jun24 | Type 1 | SOGEA | Spar Stores | Market Harborough | LE16 9BX | 2024-06-12 | 19/7/2024:0 18/7/2024:0 17/7/2024:0 16/7/2024:0 15/7/2024:0 12/7/2024:0 11/7/2024:0 10/7/2024:0 9/7/2024:0 4/7/2024:0 3/7/2024:0 2/7/2024:A1 (Site access failure) 1/7/2024:0 27/6/2024:0 25/6/2024:0 24/6/2024:0 20/6/2024: Old ID ( 204008 ) 19/6/2024:0 18/6/2024:0 14/6/2024:#Update Retailer happy with new appointment 11/06,AM. 13/6/2024:#Update Retailer happy with new appointment 11/06,AM. 12/6/2024:#Update Retailer happy with new appointment 11/06,AM. 10/6/2024:#Update Retailer happy with new appointment 11/06,AM. 7/6/2024:#Update Retailer happy with new appointment 11/06,AM. 6/6/2024:#Update Retailer happy with new appointment 11/06,AM. 5/6/2024:#Update Retailer happy with new appointment 11/06,AM. 4/6/2024:#Update Retailer happy with new appointment 11/06,AM. | 19/7/2024:0 18/7/2024:0 17/7/2024:0 16/7/2024:0 15/7/2024:0 12/7/2024:0 11/7/2024:0 10/7/2024:0 9/7/2024:0 4/7/2024:0 3/7/2024:0 2/7/2024:A1 (Site access failure) 1/7/2024:0 27/6/2024:0 25/6/2024:0 24/6/2024:0 20/6/2024: Old ID ( 204008 ) 19/6/2024:0 18/6/2024:0 14/6/2024:#Update Retailer happy with new appointment 11/06,AM. 13/6/2024:#Update Retailer happy with new appointment 11/06,AM. 12/6/2024:#Update Retailer happy with new appointment 11/06,AM. 10/6/2024:#Update Retailer happy with new appointment 11/06,AM. 7/6/2024:#Update Retailer happy with new appointment 11/06,AM. 6/6/2024:#Update Retailer happy with new appointment 11/06,AM. 5/6/2024:#Update Retailer happy with new appointment 11/06,AM. 4/6/2024:#Update Retailer happy with new appointment 11/06,AM. |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1001073 | 30016119 | 6.Failed router install | AM |  | 2024-06-11 | 2024-06-11 | 2024-06-11 | TRUE | [7 empty] | 2024-07-02 | 23A004945959 |  | 2024-07-04 | 1
481 | 670602 | 2994 | Batch 5 Jul24 | Type 1 | SOGEA | Nisa Local | PETERBOROUGH | PE2 8DP | 2024-06-12 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 21/8/2024:0 20/8/2024:0 19/8/2024:0 19/8/2024:0 16/8/2024:0 15/8/2024:0 14/8/2024:0 13/8/2024:0 12/8/2024:0 9/8/2024:0 8/8/2024:0 6/8/2024:0 5/8/2024:0 2/8/2024:0 1/8/2024:0 31/7/2024:0 31/7/2024:0 30/7/2024:0 29/7/2024:0 29/7/2024:0 26/7/2024:0 24/7/2024:0 23/7/2024:0 22/7/2024:0 22/7/2024:0 20/6/2024: Old ID ( 204008 ) 18/6/2024:Order Completed 17/6/2024:Order Completed 14/6/2024:Order Completed 13/6/2024:Supplier Delay: KCI-3 (Order Completed) Delayed in Processing. 12/6/2024:0 11/6/2024:0 10/6/2024:0 7/6/2024:0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 21/8/2024:0 20/8/2024:0 19/8/2024:0 19/8/2024:0 16/8/2024:0 15/8/2024:0 14/8/2024:0 13/8/2024:0 12/8/2024:0 9/8/2024:0 8/8/2024:0 6/8/2024:0 5/8/2024:0 2/8/2024:0 1/8/2024:0 31/7/2024:0 31/7/2024:0 30/7/2024:0 29/7/2024:0 29/7/2024:0 26/7/2024:0 24/7/2024:0 23/7/2024:0 22/7/2024:0 22/7/2024:0 20/6/2024: Old ID ( 204008 ) 18/6/2024:Order Completed 17/6/2024:Order Completed 14/6/2024:Order Completed 13/6/2024:Supplier Delay: KCI-3 (Order Completed) Delayed in Processing. 12/6/2024:0 11/6/2024:0 10/6/2024:0 7/6/2024:0 | 0 | 0 | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS970475 | 30014601 | 2.Commissioning | [9 empty] | 2024-07-03 | [7 empty] | 0
482 | 661872 | 1504 | Batch 4 Jun24 | Type 3 | FTTP/Mobile | SUPERVALU | Lurgan | BT66 7DT | 2024-06-13 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:Your order has been delayed. Survey work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 09/08/2024. We will continue to provide update as they become available. _x000D_2/8/2024:Your order has been delayed. Survey work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 09/08/2024. We will continue to provide update as they become available. _x000D_1/8/2024:Your order has been delayed. Survey work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 09/08/2024. We will continue to provide update as they become available. _x000D_31/7/2024:Your order has been delayed. Survey work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 09/08/2024. We will continue to provide update as they become available. _x000D_31/7/2024:37715 _x000D_30/7/2024:Your order has been delayed. Survey work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 09/08/2024. We will continue to provide update as they become available. _x000D_29/7/2024:Your order has been delayed. Survey work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_29/7/2024:25/07/2024 14:58 _x000D_26/7/2024:25/07/2024 14:58 _x000D_24/7/2024:Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 26/07/2024 for further updates. _x000D_23/7/2024:Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 26/07/2024 for further updates. _x000D_22/7/2024:Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 26/07/2024 for further updates. _x000D_22/7/2024:Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 26/07/2024 for further updates. _x000D_4/7/2024:#Update Upgrade charges with Vodafone to approve _x000D_3/7/2024:#Update Upgrade charges with Vodafone to approve _x000D_2/7/2024:0 _x000D_1/7/2024:#Update Upgrade charges with Vodafone to approve _x000D_01/07/2024: Site name changed from Bargain Booze Select Convenience - Is now a Costcutter 27/6/2024:#Update Upgrade charges with Vodafone to approve 25/6/2024:#Update Upgrade charges with Vodafone to approve 24/6/2024:#Update Upgrade charges with Vodafone to approve 20/6/2024:#Update Upgrade charges with Vodafone to approve 19/6/2024:#Update Upgrade charges with Vodafone to approve 18/6/2024:#Update Upgrade charges with Vodafone to approve 17/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing 14/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing 13/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing 12/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing 11/6/2024:0 10/6/2024:0 7/6/2024:0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:Your order has been delayed. Survey work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 09/08/2024. We will continue to provide update as they become available. _x000D_2/8/2024:Your order has been delayed. Survey work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 09/08/2024. We will continue to provide update as they become available. _x000D_1/8/2024:Your order has been delayed. Survey work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 09/08/2024. We will continue to provide update as they become available. _x000D_31/7/2024:Your order has been delayed. Survey work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 09/08/2024. We will continue to provide update as they become available. _x000D_31/7/2024:37715 _x000D_30/7/2024:Your order has been delayed. Survey work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 09/08/2024. We will continue to provide update as they become available. _x000D_29/7/2024:Your order has been delayed. Survey work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_29/7/2024:25/07/2024 14:58 _x000D_26/7/2024:25/07/2024 14:58 _x000D_24/7/2024:Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 26/07/2024 for further updates. _x000D_23/7/2024:Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 26/07/2024 for further updates. _x000D_22/7/2024:Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 26/07/2024 for further updates. _x000D_22/7/2024:Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 26/07/2024 for further updates. _x000D_4/7/2024:#Update Upgrade charges with Vodafone to approve _x000D_3/7/2024:#Update Upgrade charges with Vodafone to approve _x000D_2/7/2024:0 _x000D_1/7/2024:#Update Upgrade charges with Vodafone to approve _x000D_01/07/2024: Site name changed from Bargain Booze Select Convenience - Is now a Costcutter 27/6/2024:#Update Upgrade charges with Vodafone to approve 25/6/2024:#Update Upgrade charges with Vodafone to approve 24/6/2024:#Update Upgrade charges with Vodafone to approve 20/6/2024:#Update Upgrade charges with Vodafone to approve 19/6/2024:#Update Upgrade charges with Vodafone to approve 18/6/2024:#Update Upgrade charges with Vodafone to approve 17/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing 14/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing 13/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing 12/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing 11/6/2024:0 10/6/2024:0 7/6/2024:0 | 0 | 0 | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2338522 | 30015539 | 2.Commissioning | AM |  | 2024-06-12 | 2024-06-12 |  | 0 |  |  |  | 2024-09-10 | [7 empty] | 0
483 | 484790 | 1521 | Batch 4 Jun24 | Type 3 | SOGEA | Bargain Booze Select Convenience | York | YO32 9QN | 2024-06-13 | 6/9/2024:#Update VF to approve site type change costs _x000D_5/9/2024:#Update VF to approve site type change costs _x000D_4/9/2024:#Update VF to approve site type change costs _x000D_19/7/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_18/7/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_17/7/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_16/7/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_15/7/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_12/7/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_11/7/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_10/7/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_9/7/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_4/7/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_3/7/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_2/7/2024:0 _x000D_1/7/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_27/6/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_25/6/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_24/6/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_20/6/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_19/6/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_18/6/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_17/6/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_14/6/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_13/6/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 9/9/2024:#Update VF to approve site type change costs _x000D_6/9/2024:#Update VF to approve site type change costs _x000D_5/9/2024:#Update VF to approve site type change costs _x000D_4/9/2024:#Update VF to approve site type change costs _x000D_19/7/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_18/7/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_17/7/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_16/7/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_15/7/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_12/7/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_11/7/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_10/7/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_9/7/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_4/7/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_3/7/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_2/7/2024:0 _x000D_1/7/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_27/6/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_25/6/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_24/6/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_20/6/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_19/6/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_18/6/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_17/6/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_14/6/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_13/6/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 0 | #Update VF to approve site type change costs | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984759 | 30015490 | 2.Commissioning | AM |  |  |  |  | Not Applicable |  |  |  | 2024-07-25 | [7 empty] | 0
484 | 609599 | 1832 | Batch 4 Jun24 | Type 1 | FTTP/Mobile | Poole's Supervalu Dromore | Dromore | BT25 1NB | 2024-09-06 | 6/9/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_5/9/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_4/9/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_3/9/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_2/9/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_29/8/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_28/8/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_27/8/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_22/8/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_21/8/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_20/8/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_19/8/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_19/8/2024:01434479 _x000D_16/8/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_15/8/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_14/8/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_13/8/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_12/8/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_9/8/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_8/8/2024:13/06/2024 _x000D_6/8/2024:13/06/2024 _x000D_5/8/2024:13/06/2024 _x000D_2/8/2024:13/06/2024 _x000D_1/8/2024:13/06/2024 _x000D_31/7/2024:13/06/2024 _x000D_31/7/2024:13/06/2024 _x000D_30/7/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_29/7/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_29/7/2024:01434479 _x000D_26/7/2024:01434479 _x000D_24/7/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_23/7/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_22/7/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_22/7/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/07 AM _x000D_11/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/07 AM _x000D_10/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/07 AM _x000D_9/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/07 AM _x000D_4/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/07 AM _x000D_3/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/07 AM _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/07 AM _x000D_27/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/07 AM _x000D_25/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/07 AM _x000D_24/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/07 AM _x000D_20/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/07 AM _x000D_19/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/07 AM _x000D_18/6/2024:#Update - The engineer was unable to access the internal DP at rear of shop as the room is full of produce that needs to be cleared . The retailer said that they will clear it later when they have time. Action for Allwyn: Confirm if the retailer can move the stock and if so, when it can be done by. _x000D_17/6/2024:Your order has been delayed by our Suppliers due to unable to access distribution point within customer premises. Please check with end user and re-appoint order once access arranged. _x000D_14/6/2024:Your order has been delayed by our Suppliers due to unable to access distribution point within customer premises. Please check with end user and re-appoint order once access arranged. _x000D_13/6/2024:Your order has been delayed by our Suppliers due to unable to access distribution point within customer premises. Please check with end user and re-appoint order once access arranged. _x000D_12/6/2024:End User Missed appointment. Action required _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 9/9/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_6/9/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_5/9/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_4/9/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_3/9/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_2/9/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_29/8/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_28/8/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_27/8/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_22/8/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_21/8/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_20/8/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_19/8/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_19/8/2024:01434479 _x000D_16/8/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_15/8/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_14/8/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_13/8/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_12/8/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_9/8/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_8/8/2024:13/06/2024 _x000D_6/8/2024:13/06/2024 _x000D_5/8/2024:13/06/2024 _x000D_2/8/2024:13/06/2024 _x000D_1/8/2024:13/06/2024 _x000D_31/7/2024:13/06/2024 _x000D_31/7/2024:13/06/2024 _x000D_30/7/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_29/7/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_29/7/2024:01434479 _x000D_26/7/2024:01434479 _x000D_24/7/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_23/7/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_22/7/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_22/7/2024:#Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/07 AM _x000D_11/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/07 AM _x000D_10/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/07 AM _x000D_9/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/07 AM _x000D_4/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/07 AM _x000D_3/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/07 AM _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/07 AM _x000D_27/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/07 AM _x000D_25/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/07 AM _x000D_24/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/07 AM _x000D_20/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/07 AM _x000D_19/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/07 AM _x000D_18/6/2024:#Update - The engineer was unable to access the internal DP at rear of shop as the room is full of produce that needs to be cleared . The retailer said that they will clear it later when they have time. Action for Allwyn: Confirm if the retailer can move the stock and if so, when it can be done by. _x000D_17/6/2024:Your order has been delayed by our Suppliers due to unable to access distribution point within customer premises. Please check with end user and re-appoint order once access arranged. _x000D_14/6/2024:Your order has been delayed by our Suppliers due to unable to access distribution point within customer premises. Please check with end user and re-appoint order once access arranged. _x000D_13/6/2024:Your order has been delayed by our Suppliers due to unable to access distribution point within customer premises. Please check with end user and re-appoint order once access arranged. _x000D_12/6/2024:End User Missed appointment. Action required _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | Order Completed | #Update due to scope of work, a planner will need to look at this job. Liaising with OR will update as they come in | 2024-06-07 |  |  |  | 5.CSL | VFS1085135 | 30015127 | 2.Commissioning | AM |  | 2024-06-12 | 2024-06-12 |  | 0 | [11 empty] | 0
485 | 671892 | 2203 | Batch 4 Jun24 | Type 3 | SoGEA/Mobile | Spar Porthcawl | Porthcawl | CF36 3BD | 2024-06-13 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 0 | 0 | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996861 | 30015999 | 2.Commissioning | AM |  |  |  |  | 0 |  |  |  | 2024-08-21 | [7 empty] | 0 | 671892
486 | 662369 | 1841 | Batch 4 Jun24 | Type 1 | SoGEA/Mobile | Star News | Skelmersdale | WN8 6LE | 2024-08-30 | 2/9/2024:#Update - Completed - 29/08/2024 14:04 _x000D_29/8/2024:#Update - Pushed out 28/08 _x000D_28/8/2024:#Update - Pushed out 28/08 _x000D_27/8/2024:#Update - Pushed out 28/08 _x000D_22/8/2024:#Update - Pushed out 28/08 _x000D_21/8/2024:#Update - Pushed out 28/08 _x000D_20/8/2024:#Update - Pushed out 28/08 _x000D_19/8/2024:#Update - Pushed out 28/08 _x000D_19/8/2024:01436558 _x000D_16/8/2024:#Update - Pushed out 28/08 _x000D_15/8/2024:#Update - Pushed out 28/08 _x000D_14/8/2024:#Update - Pushed out 28/08 _x000D_13/8/2024:#Update - Pushed out 28/08 _x000D_12/8/2024:#Update - Pushed out 28/08 _x000D_9/8/2024:#Update - Pushed out 28/08 _x000D_8/8/2024:31/07/2024 _x000D_6/8/2024:31/07/2024 _x000D_5/8/2024:31/07/2024 _x000D_2/8/2024:31/07/2024 _x000D_1/8/2024:31/07/2024 _x000D_31/7/2024:24/06/2024 _x000D_31/7/2024:24/06/2024 _x000D_30/7/2024:#Update - Re-appointed for 15/07 whilst awaiting charges to be approved. _x000D_29/7/2024:#Update - Re-appointed for 15/07 whilst awaiting charges to be approved. _x000D_29/7/2024:01436558 _x000D_26/7/2024:01436558 _x000D_24/7/2024:#Update - Re-appointed for 15/07 whilst awaiting charges to be approved. _x000D_23/7/2024:#Update - Re-appointed for 15/07 whilst awaiting charges to be approved. _x000D_22/7/2024:#Update - Re-appointed for 15/07 whilst awaiting charges to be approved. _x000D_22/7/2024:#Update - Re-appointed for 15/07 whilst awaiting charges to be approved. _x000D_19/7/2024:#Update Reappointed 18/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_18/7/2024:#Update Reappointed 18/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_17/7/2024:#Update Reappointed 18/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_16/7/2024:#Update Reappointed 18/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_15/7/2024:#Update Reappointed 18/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_12/7/2024:#Update Reappointed 18/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_11/7/2024:#Update Reappointed 18/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_10/7/2024:#Update Reappointed 18/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_9/7/2024:#Update Reappointed 18/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_4/7/2024:#Update Reappointed 18/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_3/7/2024:#Update Retailer happy with new appointment 28/06, AM. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update Retailer happy with new appointment 28/06, AM. _x000D_27/6/2024:#Update Retailer happy with new appointment 28/06, AM. _x000D_25/6/2024:#Update Retailer happy with new appointment 28/06, AM. _x000D_24/6/2024:#Update Retailer happy with new appointment 28/06, AM. _x000D_20/6/2024:#Update Retailer happy with new appointment 28/06, AM. _x000D_19/6/2024:#Update Retailer happy with new appointment 28/06, AM. _x000D_18/6/2024:#Update Retailer happy with new appointment 28/06, AM. _x000D_17/6/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_14/6/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 2/9/2024:#Update - Completed - 29/08/2024 14:04 _x000D_29/8/2024:#Update - Pushed out 28/08 _x000D_28/8/2024:#Update - Pushed out 28/08 _x000D_27/8/2024:#Update - Pushed out 28/08 _x000D_22/8/2024:#Update - Pushed out 28/08 _x000D_21/8/2024:#Update - Pushed out 28/08 _x000D_20/8/2024:#Update - Pushed out 28/08 _x000D_19/8/2024:#Update - Pushed out 28/08 _x000D_19/8/2024:01436558 _x000D_16/8/2024:#Update - Pushed out 28/08 _x000D_15/8/2024:#Update - Pushed out 28/08 _x000D_14/8/2024:#Update - Pushed out 28/08 _x000D_13/8/2024:#Update - Pushed out 28/08 _x000D_12/8/2024:#Update - Pushed out 28/08 _x000D_9/8/2024:#Update - Pushed out 28/08 _x000D_8/8/2024:31/07/2024 _x000D_6/8/2024:31/07/2024 _x000D_5/8/2024:31/07/2024 _x000D_2/8/2024:31/07/2024 _x000D_1/8/2024:31/07/2024 _x000D_31/7/2024:24/06/2024 _x000D_31/7/2024:24/06/2024 _x000D_30/7/2024:#Update - Re-appointed for 15/07 whilst awaiting charges to be approved. _x000D_29/7/2024:#Update - Re-appointed for 15/07 whilst awaiting charges to be approved. _x000D_29/7/2024:01436558 _x000D_26/7/2024:01436558 _x000D_24/7/2024:#Update - Re-appointed for 15/07 whilst awaiting charges to be approved. _x000D_23/7/2024:#Update - Re-appointed for 15/07 whilst awaiting charges to be approved. _x000D_22/7/2024:#Update - Re-appointed for 15/07 whilst awaiting charges to be approved. _x000D_22/7/2024:#Update - Re-appointed for 15/07 whilst awaiting charges to be approved. _x000D_19/7/2024:#Update Reappointed 18/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_18/7/2024:#Update Reappointed 18/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_17/7/2024:#Update Reappointed 18/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_16/7/2024:#Update Reappointed 18/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_15/7/2024:#Update Reappointed 18/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_12/7/2024:#Update Reappointed 18/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_11/7/2024:#Update Reappointed 18/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_10/7/2024:#Update Reappointed 18/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_9/7/2024:#Update Reappointed 18/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_4/7/2024:#Update Reappointed 18/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_3/7/2024:#Update Retailer happy with new appointment 28/06, AM. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update Retailer happy with new appointment 28/06, AM. _x000D_27/6/2024:#Update Retailer happy with new appointment 28/06, AM. _x000D_25/6/2024:#Update Retailer happy with new appointment 28/06, AM. _x000D_24/6/2024:#Update Retailer happy with new appointment 28/06, AM. _x000D_20/6/2024:#Update Retailer happy with new appointment 28/06, AM. _x000D_19/6/2024:#Update Retailer happy with new appointment 28/06, AM. _x000D_18/6/2024:#Update Retailer happy with new appointment 28/06, AM. _x000D_17/6/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_14/6/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 5.CSL | VFS983364 | 30015265 | 2.Commissioning | AM |  | 2024-06-13 | 2024-08-29 |  | 0 | [11 empty] | 0
487 | 666914 | 1844 | Batch 4 Jun24 | Type 1 | SoGEA/Mobile | Bicester PO | Bicester | OX26 6TB | 2024-06-14 | 22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:#Update Reappointed 05/08, PM. Action on Allwyn - ensure the retailer knows _x000D_8/8/2024:24/07/2024 _x000D_6/8/2024:24/07/2024 _x000D_5/8/2024:24/07/2024 _x000D_2/8/2024:24/07/2024 _x000D_1/8/2024:24/07/2024 _x000D_31/7/2024:24/07/2024 _x000D_31/7/2024:24/07/2024 _x000D_30/7/2024:#Update Reappointed 05/08, PM. Action on Allwyn - ensure the retailer knows _x000D_29/7/2024:#Update Reappointed 05/08, PM. Action on Allwyn - ensure the retailer knows _x000D_29/7/2024:01436186 _x000D_26/7/2024:01436186 _x000D_24/7/2024:#Update Reappointed 18/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_23/7/2024:#Update Reappointed 18/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_22/7/2024:#Update Reappointed 18/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_22/7/2024:#Update Reappointed 18/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_19/7/2024:Order Completed _x000D_18/7/2024:Order Completed _x000D_17/7/2024:Order Completed _x000D_16/7/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/7/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/7/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_11/7/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 15/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_9/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 15/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 09/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_3/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 09/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_19/6/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_18/6/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_17/6/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_14/6/2024:End User Missed appointment. Action required _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:#Update Reappointed 05/08, PM. Action on Allwyn - ensure the retailer knows _x000D_8/8/2024:24/07/2024 _x000D_6/8/2024:24/07/2024 _x000D_5/8/2024:24/07/2024 _x000D_2/8/2024:24/07/2024 _x000D_1/8/2024:24/07/2024 _x000D_31/7/2024:24/07/2024 _x000D_31/7/2024:24/07/2024 _x000D_30/7/2024:#Update Reappointed 05/08, PM. Action on Allwyn - ensure the retailer knows _x000D_29/7/2024:#Update Reappointed 05/08, PM. Action on Allwyn - ensure the retailer knows _x000D_29/7/2024:01436186 _x000D_26/7/2024:01436186 _x000D_24/7/2024:#Update Reappointed 18/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_23/7/2024:#Update Reappointed 18/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_22/7/2024:#Update Reappointed 18/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_22/7/2024:#Update Reappointed 18/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_19/7/2024:Order Completed _x000D_18/7/2024:Order Completed _x000D_17/7/2024:Order Completed _x000D_16/7/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/7/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/7/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_11/7/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 15/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_9/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 15/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 09/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_3/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 09/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_19/6/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_18/6/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_17/6/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_14/6/2024:End User Missed appointment. Action required _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983369 | 30015261 | 6.Failed router install | AM | [8 empty] | 2024-08-21 |  |  |  | 2024-08-21 | 242005008592 | 242005008592 | 2024-08-22 | 1
488 | 670378 | 1845 | Batch 4 Jun24 | Type 1 | SOGEA | Costcutter | EXETER | EX2 6AU | 2024-06-14 | 22/7/2024:Order Completed _x000D_19/7/2024:#Update Retailer happy with new appointment 19/07, AM. _x000D_18/7/2024:#Update Retailer happy with new appointment 19/07, AM. _x000D_17/7/2024:#Update Retailer happy with new appointment 19/07, AM. _x000D_16/7/2024:#Update Retailer happy with new appointment 19/07, AM. _x000D_15/7/2024:#Update Retailer happy with new appointment 19/07, AM. _x000D_12/7/2024:#Update Retailer happy with new appointment 19/07, AM. _x000D_11/7/2024:#Update Retailer happy with new appointment 19/07, AM. _x000D_10/7/2024:#Update Retailer happy with new appointment 19/07, AM. _x000D_9/7/2024:#Update Retailer happy with new appointment 19/07, AM. _x000D_4/7/2024:#Update Potentially moving to a site type 3. VF / Allwyn to advise. _x000D_3/7/2024:#Update Potentially moving to a site type 3. VF / Allwyn to advise. _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:#Update Potentially moving to a site type 3. VF / Allwyn to advise. _x000D_27/6/2024:Update: Order Amended _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect CRD Please check with end user and reappoint the order if still required. _x000D_19/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect CRD Please check with end user and reappoint the order if still required. _x000D_18/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect CRD Please check with end user and reappoint the order if still required. _x000D_17/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect CRD Please check with end user and reappoint the order if still required. _x000D_14/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect CRD Please check with end user and reappoint the order if still required. _x000D_13/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 22/7/2024:Order Completed _x000D_19/7/2024:#Update Retailer happy with new appointment 19/07, AM. _x000D_18/7/2024:#Update Retailer happy with new appointment 19/07, AM. _x000D_17/7/2024:#Update Retailer happy with new appointment 19/07, AM. _x000D_16/7/2024:#Update Retailer happy with new appointment 19/07, AM. _x000D_15/7/2024:#Update Retailer happy with new appointment 19/07, AM. _x000D_12/7/2024:#Update Retailer happy with new appointment 19/07, AM. _x000D_11/7/2024:#Update Retailer happy with new appointment 19/07, AM. _x000D_10/7/2024:#Update Retailer happy with new appointment 19/07, AM. _x000D_9/7/2024:#Update Retailer happy with new appointment 19/07, AM. _x000D_4/7/2024:#Update Potentially moving to a site type 3. VF / Allwyn to advise. _x000D_3/7/2024:#Update Potentially moving to a site type 3. VF / Allwyn to advise. _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:#Update Potentially moving to a site type 3. VF / Allwyn to advise. _x000D_27/6/2024:Update: Order Amended _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect CRD Please check with end user and reappoint the order if still required. _x000D_19/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect CRD Please check with end user and reappoint the order if still required. _x000D_18/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect CRD Please check with end user and reappoint the order if still required. _x000D_17/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect CRD Please check with end user and reappoint the order if still required. _x000D_14/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect CRD Please check with end user and reappoint the order if still required. _x000D_13/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983370 | 30015252 | 2.Commissioning | AM |  | 2024-06-13 | 2024-07-16 | 2024-07-16 | TRUE |  |  |  | 2024-08-07 | [7 empty] | 0
489 | 665322 | 1848 | Batch 4 Jun24 | Type 1 | SOGEA | Brantwood Post Office | Dundee | DD3 6EW | 2024-06-14 | 21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:#Update Retailer happy with new appointment 19/07, AM. _x000D_22/7/2024:#Update Retailer happy with new appointment 19/07, AM. _x000D_22/7/2024:#Update Retailer happy with new appointment 19/07, AM. _x000D_19/7/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_18/7/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_17/7/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_16/7/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_15/7/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_12/7/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_11/7/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_10/7/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_9/7/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_4/7/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_3/7/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_27/6/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_25/6/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_24/6/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_20/6/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_19/6/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_18/6/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_17/6/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_14/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:#Update Retailer happy with new appointment 19/07, AM. _x000D_22/7/2024:#Update Retailer happy with new appointment 19/07, AM. _x000D_22/7/2024:#Update Retailer happy with new appointment 19/07, AM. _x000D_19/7/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_18/7/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_17/7/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_16/7/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_15/7/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_12/7/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_11/7/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_10/7/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_9/7/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_4/7/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_3/7/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_27/6/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_25/6/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_24/6/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_20/6/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_19/6/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_18/6/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_17/6/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_14/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983373 | 30015201 | 6.Failed router install | AM | [8 empty] | 2024-08-21 |  |  |  | 2024-08-20 | 23A004945391 | 23A004945391 | 2024-08-21 | 1
490 | 664828 | 1849 | Batch 4 Jun24 | Type 1 | SoGEA/Mobile | Bargain Booze | STOKE-ON-TRENT | ST3 6PZ | 2024-06-14 | 6/9/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_5/9/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_4/9/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_3/9/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_2/9/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_29/8/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_28/8/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_27/8/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_22/8/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_21/8/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_20/8/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_19/8/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_19/8/2024:01436196 _x000D_16/8/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_15/8/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_14/8/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_13/8/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_12/8/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_9/8/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_8/8/2024:17/06/2024 _x000D_6/8/2024:17/06/2024 _x000D_5/8/2024:17/06/2024 _x000D_2/8/2024:17/06/2024 _x000D_1/8/2024:17/06/2024 _x000D_31/7/2024:17/06/2024 _x000D_31/7/2024:17/06/2024 _x000D_30/7/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_29/7/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_29/7/2024:01436196 _x000D_26/7/2024:01436196 _x000D_24/7/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_23/7/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_22/7/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_22/7/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_19/7/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_18/7/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_17/7/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_16/7/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_15/7/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_12/7/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_11/7/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_10/7/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_9/7/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_4/7/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_3/7/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_2/7/2024:0 _x000D_1/7/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_27/6/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_25/6/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_24/6/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_20/6/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_19/6/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_18/6/2024:#Update Order has been sent to survey, will get updated 28/06 _x000D_17/6/2024:#Update Order has been sent to survey, will get updated 28/06 _x000D_14/6/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 01/07/2204.We will continue to provide update as they become available. _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 9/9/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_6/9/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_5/9/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_4/9/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_3/9/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_2/9/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_29/8/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_28/8/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_27/8/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_22/8/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_21/8/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_20/8/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_19/8/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_19/8/2024:01436196 _x000D_16/8/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_15/8/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_14/8/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_13/8/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_12/8/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_9/8/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_8/8/2024:17/06/2024 _x000D_6/8/2024:17/06/2024 _x000D_5/8/2024:17/06/2024 _x000D_2/8/2024:17/06/2024 _x000D_1/8/2024:17/06/2024 _x000D_31/7/2024:17/06/2024 _x000D_31/7/2024:17/06/2024 _x000D_30/7/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_29/7/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_29/7/2024:01436196 _x000D_26/7/2024:01436196 _x000D_24/7/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_23/7/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_22/7/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_22/7/2024:#Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. _x000D_19/7/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_18/7/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_17/7/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_16/7/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_15/7/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_12/7/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_11/7/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_10/7/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_9/7/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_4/7/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_3/7/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_2/7/2024:0 _x000D_1/7/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_27/6/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_25/6/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_24/6/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_20/6/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_19/6/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_18/6/2024:#Update Order has been sent to survey, will get updated 28/06 _x000D_17/6/2024:#Update Order has been sent to survey, will get updated 28/06 _x000D_14/6/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 01/07/2204.We will continue to provide update as they become available. _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 0 | #Update - Missed appointment - The retailer was unaware of the order and therefore refused entry. Additionally the till is in the middle of the shop floor, therefore it required 2 hours of OOH work. | 2024-06-07 |  |  |  | 5.CSL | VFS983374 | 30015282 | 1.Provisioning | AM |  | 2024-06-13 | 2024-08-29 |  | 0 | [11 empty] | 0
491 | 666469 | 1902 | Batch 4 Jun24 | Type 1 | FTTP/Mobile | COSTCUTTER & PO | NEWRY | BT35 7JG | 2024-06-14 | 6/9/2024:#Update - Your order has been delayed as site survey is required. This has been sent to the survey engineers and further updates will follow _x000D_5/9/2024:#Update - Your order has been delayed as site survey is required. This has been sent to the survey engineers and further updates will follow _x000D_4/9/2024:#Update - Your order has been delayed as site survey is required. This has been sent to the survey engineers and further updates will follow _x000D_3/9/2024:#Update - Your order has been delayed as site survey is required. This has been sent to the survey engineers and further updates will follow _x000D_2/9/2024:#Update - Your order has been delayed as site survey is required. This has been sent to the survey engineers and further updates will follow _x000D_29/8/2024:#Update - Your order has been delayed as site survey is required. This has been sent to the survey engineers and further updates will follow _x000D_28/8/2024:#Update - Your order has been delayed as site survey is required. This has been sent to the survey engineers and further updates will follow _x000D_27/8/2024:#Update - Your order has been delayed as site survey is required. This has been sent to the survey engineers and further updates will follow _x000D_22/8/2024:#Update - Supplier Delays: Issues with the line plant at step 1 stage - further updates to follow _x000D_21/8/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_20/8/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_19/8/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_19/8/2024:01437872 _x000D_16/8/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_15/8/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_14/8/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_13/8/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_12/8/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_9/8/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_8/8/2024:18/06/2024 _x000D_6/8/2024:18/06/2024 _x000D_5/8/2024:18/06/2024 _x000D_2/8/2024:18/06/2024 _x000D_1/8/2024:18/06/2024 _x000D_31/7/2024:18/06/2024 _x000D_31/7/2024:18/06/2024 _x000D_30/7/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_29/7/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_29/7/2024:01437872 _x000D_26/7/2024:01437872 _x000D_24/7/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_23/7/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_22/7/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_22/7/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_19/7/2024:#Update - The Openreach notes state that 'the owner does not want anything done as he has remodeled his shop and does not want any drilling where the engineers would need to drill around the back wall. If the owner wants the installation to take place, there would need to be a survey so the engineers could possibly find another solution to get the cabling through, but shop keeper said he does not want any work taking place.' Action for Allwyn: discuss with the retailer how they would like to continue, if no work is consented to it may need to move to a site type 3. _x000D_18/7/2024:#Update - The Openreach notes state that 'the owner does not want anything done as he has remodeled his shop and does not want any drilling where the engineers would need to drill around the back wall. If the owner wants the installation to take place, there would need to be a survey so the engineers could possibly find another solution to get the cabling through, but shop keeper said he does not want any work taking place.' Action for Allwyn: discuss with the retailer how they would like to continue, if no work is consented to it may need to move to a site type 3. _x000D_17/7/2024:#Update - The Openreach notes state that 'the owner does not want anything done as he has remodeled his shop and does not want any drilling where the engineers would need to drill around the back wall. If the owner wants the installation to take place, there would need to be a survey so the engineers could possibly find another solution to get the cabling through, but shop keeper said he does not want any work taking place.' Action for Allwyn: discuss with the retailer how they would like to continue, if no work is consented to it may need to move to a site type 3. _x000D_16/7/2024:#Update - The Openreach notes state that 'the owner does not want anything done as he has remodeled his shop and does not want any drilling where the engineers would need to drill around the back wall. If the owner wants the installation to take place, there would need to be a survey so the engineers could possibly find another solution to get the cabling through, but shop keeper said he does not want any work taking place.' Action for Allwyn: discuss with the retailer how they would like to continue, if no work is consented to it may need to move to a site type 3. _x000D_15/7/2024:#Update - The Openreach notes state that 'the owner does not want anything done as he has remodeled his shop and does not want any drilling where the engineers would need to drill around the back wall. If the owner wants the installation to take place, there would need to be a survey so the engineers could possibly find another solution to get the cabling through, but shop keeper said he does not want any work taking place.' Action for Allwyn: discuss with the retailer how they would like to continue, if no work is consented to it may need to move to a site type 3. _x000D_12/7/2024:#Update - The Openreach notes state that 'the owner does not want anything done as he has remodeled his shop and does not want any drilling where the engineers would need to drill around the back wall. If the owner wants the installation to take place, there would need to be a survey so the engineers could possibly find another solution to get the cabling through, but shop keeper said he does not want any work taking place.' Action for Allwyn: discuss with the retailer how they would like to continue, if no work is consented to it may need to move to a site type 3. _x000D_11/7/2024:#Update - The Openreach notes state that 'the owner does not want anything done as he has remodeled his shop and does not want any drilling where the engineers would need to drill around the back wall. If the owner wants the installation to take place, there would need to be a survey so the engineers could possibly find another solution to get the cabling through, but shop keeper said he does not want any work taking place.' Action for Allwyn: discuss with the retailer how they would like to continue, if no work is consented to it may need to move to a site type 3. _x000D_10/7/2024:#Update - The Openreach notes state that 'the owner does not want anything done as he has remodeled his shop and does not want any drilling where the engineers would need to drill around the back wall. If the owner wants the installation to take place, there would need to be a survey so the engineers could possibly find another solution to get the cabling through, but shop keeper said he does not want any work taking place.' Action for Allwyn: discuss with the retailer how they would like to continue, if no work is consented to it may need to move to a site type 3. _x000D_9/7/2024:#Update - The Openreach notes state that 'the owner does not want anything done as he has remodeled his shop and does not want any drilling where the engineers would need to drill around the back wall. If the owner wants the installation to take place, there would need to be a survey so the engineers could possibly find another solution to get the cabling through, but shop keeper said he does not want any work taking place.' Action for Allwyn: discuss with the retailer how they would like to continue, if no work is consented to it may need to move to a site type 3. _x000D_4/7/2024:#Update - The Openreach notes state that 'the owner does not want anything done as he has remodeled his shop and does not want any drilling where the engineers would need to drill around the back wall. If the owner wants the installation to take place, there would need to be a survey so the engineers could possibly find another solution to get the cabling through, but shop keeper said he does not want any work taking place.' Action for Allwyn: discuss with the retailer how they would like to continue, if no work is consented to it may need to move to a site type 3. _x000D_3/7/2024:#Update - The Openreach notes state that 'the owner does not want anything done as he has remodeled his shop and does not want any drilling where the engineers would need to drill around the back wall. If the owner wants the installation to take place, there would need to be a survey so the engineers could possibly find another solution to get the cabling through, but shop keeper said he does not want any work taking place.' Action for Allwyn: discuss with the retailer how they would like to continue, if no work is consented to it may need to move to a site type 3. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - The Openreach notes state that 'the owner does not want anything done as he has remodeled his shop and does not want any drilling where the engineers would need to drill around the back wall. If the owner wants the installation to take place, there would need to be a survey so the engineers could possibly find another solution to get the cabling through, but shop keeper said he does not want any work taking place.' Action for Allwyn: discuss with the retailer how they would like to continue, if no work is consented to it may need to move to a site type 3. _x000D_27/6/2024:#Update - The Openreach notes state that 'the owner does not want anything done as he has remodeled his shop and does not want any drilling where the engineers would need to drill around the back wall. If the owner wants the installation to take place, there would need to be a survey so the engineers could possibly find another solution to get the cabling through, but shop keeper said he does not want any work taking place.' Action for Allwyn: discuss with the retailer how they would like to continue, if no work is consented to it may need to move to a site type 3. _x000D_25/6/2024:#Update - The Openreach notes state that 'the owner does not want anything done as he has remodeled his shop and does not want any drilling where the engineers would need to drill around the back wall. If the owner wants the installation to take place, there would need to be a survey so the engineers could possibly find another solution to get the cabling through, but shop keeper said he does not want any work taking place.' Action for Allwyn: discuss with the retailer how they would like to continue, if no work is consented to it may need to move to a site type 3. _x000D_24/6/2024:#Update - The Openreach notes state that 'the owner does not want anything done as he has remodeled his shop and does not want any drilling where the engineers would need to drill around the back wall. If the owner wants the installation to take place, there would need to be a survey so the engineers could possibly find another solution to get the cabling through, but shop keeper said he does not want any work taking place.' Action for Allwyn: discuss with the retailer how they would like to continue, if no work is consented to it may need to move to a site type 3. _x000D_20/6/2024:#Update - The Openreach notes state that 'the owner does not want anything done as he has remodeled his shop and does not want any drilling where the engineers would need to drill around the back wall. If the owner wants the installation to take place, there would need to be a survey so the engineers could possibly find another solution to get the cabling through, but shop keeper said he does not want any work taking place.' Action for Allwyn: discuss with the retailer how they would like to continue, if no work is consented to it may need to move to a site type 3. _x000D_19/6/2024:#Update - The Openreach notes state that 'the owner does not want anything done as he has remodeled his shop and does not want any drilling where the engineers would need to drill around the back wall. If the owner wants the installation to take place, there would need to be a survey so the engineers could possibly find another solution to get the cabling through, but shop keeper said he does not want any work taking place.' Action for Allwyn: discuss with the retailer how they would like to continue, if no work is consented to it may need to move to a site type 3. _x000D_18/6/2024:#Update - The Openreach notes state that 'the owner does not want anything done as he has remodeled his shop and does not want any drilling where the engineers would need to drill around the back wall. If the owner wants the installation to take place, there would need to be a survey so the engineers could possibly find another solution to get the cabling through, but shop keeper said he does not want any work taking place.' Action for Allwyn: discuss with the retailer how they would like to continue, if no work is consented to it may need to move to a site type 3. _x000D_17/6/2024:#Update - Missed Appointment - The retailer was unaware of the order and therefore refused entry. CSL to reappoint the installation and update with a committed date. _x000D_14/6/2024:#Update - Missed Appointment - The retailer was unaware of the order and therefore refused entry. CSL to reappoint the installation and update with a committed date. _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 9/9/2024:#Update - Your order has been delayed as site survey is required. This has been sent to the survey engineers and further updates will follow _x000D_6/9/2024:#Update - Your order has been delayed as site survey is required. This has been sent to the survey engineers and further updates will follow _x000D_5/9/2024:#Update - Your order has been delayed as site survey is required. This has been sent to the survey engineers and further updates will follow _x000D_4/9/2024:#Update - Your order has been delayed as site survey is required. This has been sent to the survey engineers and further updates will follow _x000D_3/9/2024:#Update - Your order has been delayed as site survey is required. This has been sent to the survey engineers and further updates will follow _x000D_2/9/2024:#Update - Your order has been delayed as site survey is required. This has been sent to the survey engineers and further updates will follow _x000D_29/8/2024:#Update - Your order has been delayed as site survey is required. This has been sent to the survey engineers and further updates will follow _x000D_28/8/2024:#Update - Your order has been delayed as site survey is required. This has been sent to the survey engineers and further updates will follow _x000D_27/8/2024:#Update - Your order has been delayed as site survey is required. This has been sent to the survey engineers and further updates will follow _x000D_22/8/2024:#Update - Supplier Delays: Issues with the line plant at step 1 stage - further updates to follow _x000D_21/8/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_20/8/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_19/8/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_19/8/2024:01437872 _x000D_16/8/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_15/8/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_14/8/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_13/8/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_12/8/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_9/8/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_8/8/2024:18/06/2024 _x000D_6/8/2024:18/06/2024 _x000D_5/8/2024:18/06/2024 _x000D_2/8/2024:18/06/2024 _x000D_1/8/2024:18/06/2024 _x000D_31/7/2024:18/06/2024 _x000D_31/7/2024:18/06/2024 _x000D_30/7/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_29/7/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_29/7/2024:01437872 _x000D_26/7/2024:01437872 _x000D_24/7/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_23/7/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_22/7/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_22/7/2024:#Update due to address issues order needs to be cancelled and reordered _x000D_19/7/2024:#Update - The Openreach notes state that 'the owner does not want anything done as he has remodeled his shop and does not want any drilling where the engineers would need to drill around the back wall. If the owner wants the installation to take place, there would need to be a survey so the engineers could possibly find another solution to get the cabling through, but shop keeper said he does not want any work taking place.' Action for Allwyn: discuss with the retailer how they would like to continue, if no work is consented to it may need to move to a site type 3. _x000D_18/7/2024:#Update - The Openreach notes state that 'the owner does not want anything done as he has remodeled his shop and does not want any drilling where the engineers would need to drill around the back wall. If the owner wants the installation to take place, there would need to be a survey so the engineers could possibly find another solution to get the cabling through, but shop keeper said he does not want any work taking place.' Action for Allwyn: discuss with the retailer how they would like to continue, if no work is consented to it may need to move to a site type 3. _x000D_17/7/2024:#Update - The Openreach notes state that 'the owner does not want anything done as he has remodeled his shop and does not want any drilling where the engineers would need to drill around the back wall. If the owner wants the installation to take place, there would need to be a survey so the engineers could possibly find another solution to get the cabling through, but shop keeper said he does not want any work taking place.' Action for Allwyn: discuss with the retailer how they would like to continue, if no work is consented to it may need to move to a site type 3. _x000D_16/7/2024:#Update - The Openreach notes state that 'the owner does not want anything done as he has remodeled his shop and does not want any drilling where the engineers would need to drill around the back wall. If the owner wants the installation to take place, there would need to be a survey so the engineers could possibly find another solution to get the cabling through, but shop keeper said he does not want any work taking place.' Action for Allwyn: discuss with the retailer how they would like to continue, if no work is consented to it may need to move to a site type 3. _x000D_15/7/2024:#Update - The Openreach notes state that 'the owner does not want anything done as he has remodeled his shop and does not want any drilling where the engineers would need to drill around the back wall. If the owner wants the installation to take place, there would need to be a survey so the engineers could possibly find another solution to get the cabling through, but shop keeper said he does not want any work taking place.' Action for Allwyn: discuss with the retailer how they would like to continue, if no work is consented to it may need to move to a site type 3. _x000D_12/7/2024:#Update - The Openreach notes state that 'the owner does not want anything done as he has remodeled his shop and does not want any drilling where the engineers would need to drill around the back wall. If the owner wants the installation to take place, there would need to be a survey so the engineers could possibly find another solution to get the cabling through, but shop keeper said he does not want any work taking place.' Action for Allwyn: discuss with the retailer how they would like to continue, if no work is consented to it may need to move to a site type 3. _x000D_11/7/2024:#Update - The Openreach notes state that 'the owner does not want anything done as he has remodeled his shop and does not want any drilling where the engineers would need to drill around the back wall. If the owner wants the installation to take place, there would need to be a survey so the engineers could possibly find another solution to get the cabling through, but shop keeper said he does not want any work taking place.' Action for Allwyn: discuss with the retailer how they would like to continue, if no work is consented to it may need to move to a site type 3. _x000D_10/7/2024:#Update - The Openreach notes state that 'the owner does not want anything done as he has remodeled his shop and does not want any drilling where the engineers would need to drill around the back wall. If the owner wants the installation to take place, there would need to be a survey so the engineers could possibly find another solution to get the cabling through, but shop keeper said he does not want any work taking place.' Action for Allwyn: discuss with the retailer how they would like to continue, if no work is consented to it may need to move to a site type 3. _x000D_9/7/2024:#Update - The Openreach notes state that 'the owner does not want anything done as he has remodeled his shop and does not want any drilling where the engineers would need to drill around the back wall. If the owner wants the installation to take place, there would need to be a survey so the engineers could possibly find another solution to get the cabling through, but shop keeper said he does not want any work taking place.' Action for Allwyn: discuss with the retailer how they would like to continue, if no work is consented to it may need to move to a site type 3. _x000D_4/7/2024:#Update - The Openreach notes state that 'the owner does not want anything done as he has remodeled his shop and does not want any drilling where the engineers would need to drill around the back wall. If the owner wants the installation to take place, there would need to be a survey so the engineers could possibly find another solution to get the cabling through, but shop keeper said he does not want any work taking place.' Action for Allwyn: discuss with the retailer how they would like to continue, if no work is consented to it may need to move to a site type 3. _x000D_3/7/2024:#Update - The Openreach notes state that 'the owner does not want anything done as he has remodeled his shop and does not want any drilling where the engineers would need to drill around the back wall. If the owner wants the installation to take place, there would need to be a survey so the engineers could possibly find another solution to get the cabling through, but shop keeper said he does not want any work taking place.' Action for Allwyn: discuss with the retailer how they would like to continue, if no work is consented to it may need to move to a site type 3. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - The Openreach notes state that 'the owner does not want anything done as he has remodeled his shop and does not want any drilling where the engineers would need to drill around the back wall. If the owner wants the installation to take place, there would need to be a survey so the engineers could possibly find another solution to get the cabling through, but shop keeper said he does not want any work taking place.' Action for Allwyn: discuss with the retailer how they would like to continue, if no work is consented to it may need to move to a site type 3. _x000D_27/6/2024:#Update - The Openreach notes state that 'the owner does not want anything done as he has remodeled his shop and does not want any drilling where the engineers would need to drill around the back wall. If the owner wants the installation to take place, there would need to be a survey so the engineers could possibly find another solution to get the cabling through, but shop keeper said he does not want any work taking place.' Action for Allwyn: discuss with the retailer how they would like to continue, if no work is consented to it may need to move to a site type 3. _x000D_25/6/2024:#Update - The Openreach notes state that 'the owner does not want anything done as he has remodeled his shop and does not want any drilling where the engineers would need to drill around the back wall. If the owner wants the installation to take place, there would need to be a survey so the engineers could possibly find another solution to get the cabling through, but shop keeper said he does not want any work taking place.' Action for Allwyn: discuss with the retailer how they would like to continue, if no work is consented to it may need to move to a site type 3. _x000D_24/6/2024:#Update - The Openreach notes state that 'the owner does not want anything done as he has remodeled his shop and does not want any drilling where the engineers would need to drill around the back wall. If the owner wants the installation to take place, there would need to be a survey so the engineers could possibly find another solution to get the cabling through, but shop keeper said he does not want any work taking place.' Action for Allwyn: discuss with the retailer how they would like to continue, if no work is consented to it may need to move to a site type 3. _x000D_20/6/2024:#Update - The Openreach notes state that 'the owner does not want anything done as he has remodeled his shop and does not want any drilling where the engineers would need to drill around the back wall. If the owner wants the installation to take place, there would need to be a survey so the engineers could possibly find another solution to get the cabling through, but shop keeper said he does not want any work taking place.' Action for Allwyn: discuss with the retailer how they would like to continue, if no work is consented to it may need to move to a site type 3. _x000D_19/6/2024:#Update - The Openreach notes state that 'the owner does not want anything done as he has remodeled his shop and does not want any drilling where the engineers would need to drill around the back wall. If the owner wants the installation to take place, there would need to be a survey so the engineers could possibly find another solution to get the cabling through, but shop keeper said he does not want any work taking place.' Action for Allwyn: discuss with the retailer how they would like to continue, if no work is consented to it may need to move to a site type 3. _x000D_18/6/2024:#Update - The Openreach notes state that 'the owner does not want anything done as he has remodeled his shop and does not want any drilling where the engineers would need to drill around the back wall. If the owner wants the installation to take place, there would need to be a survey so the engineers could possibly find another solution to get the cabling through, but shop keeper said he does not want any work taking place.' Action for Allwyn: discuss with the retailer how they would like to continue, if no work is consented to it may need to move to a site type 3. _x000D_17/6/2024:#Update - Missed Appointment - The retailer was unaware of the order and therefore refused entry. CSL to reappoint the installation and update with a committed date. _x000D_14/6/2024:#Update - Missed Appointment - The retailer was unaware of the order and therefore refused entry. CSL to reappoint the installation and update with a committed date. _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 0 | #Update - Your order has been delayed as site survey is required. This has been sent to the survey engineers and further updates will follow | 2024-06-07 |  |  |  | 5.CSL | VFP2431173 | 30015690 | 1.Provisioning | AM |  | 2024-08-21 | 2024-08-21 |  | 0 | [11 empty] | 0
492 | 449747 | 1905 | Batch 4 Jun24 | Type 1 | FTTP/Mobile | Star Supermarket | DONCASTER | DN2 4BD | 2024-08-30 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 PM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 PM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 PM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 PM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 13/08 PM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 13/08 PM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 13/08 PM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 13/08 PM _x000D_19/8/2024:01435615 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 13/08 PM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 13/08 PM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 13/08 PM _x000D_13/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 13/08 PM _x000D_12/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 13/08 PM _x000D_9/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 13/08 PM _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 13/08 PM _x000D_29/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 13/08 PM _x000D_29/7/2024:01435615 _x000D_26/7/2024:01435615 _x000D_24/7/2024:#Update - The Openreach notes state that 'the owner does not want anything done as he has remodeled his shop and does not want any drilling where the engineers would need to drill around the back wall. If the owner wants the installation to take place, there would need to be a survey so the engineers could possibly find another solution to get the cabling through, but shop keeper said he does not want any work taking place.' Action for Allwyn: discuss with the retailer how they would like to continue, if no work is consented to it may need to move to a site type 3. _x000D_23/7/2024:#Update - The Openreach notes state that 'the owner does not want anything done as he has remodeled his shop and does not want any drilling where the engineers would need to drill around the back wall. If the owner wants the installation to take place, there would need to be a survey so the engineers could possibly find another solution to get the cabling through, but shop keeper said he does not want any work taking place.' Action for Allwyn: discuss with the retailer how they would like to continue, if no work is consented to it may need to move to a site type 3. _x000D_22/7/2024:#Update - The Openreach notes state that 'the owner does not want anything done as he has remodeled his shop and does not want any drilling where the engineers would need to drill around the back wall. If the owner wants the installation to take place, there would need to be a survey so the engineers could possibly find another solution to get the cabling through, but shop keeper said he does not want any work taking place.' Action for Allwyn: discuss with the retailer how they would like to continue, if no work is consented to it may need to move to a site type 3. _x000D_22/7/2024:#Update - The Openreach notes state that 'the owner does not want anything done as he has remodeled his shop and does not want any drilling where the engineers would need to drill around the back wall. If the owner wants the installation to take place, there would need to be a survey so the engineers could possibly find another solution to get the cabling through, but shop keeper said he does not want any work taking place.' Action for Allwyn: discuss with the retailer how they would like to continue, if no work is consented to it may need to move to a site type 3. _x000D_19/6/2024:#Update - Order Complete _x000D_18/6/2024:#Update - Order Complete _x000D_17/6/2024:#Update - Order Complete _x000D_14/6/2024:Supplier Delay: KCI-3 (Order Completed) Delayed in Processing. _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 PM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 PM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 PM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 PM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 13/08 PM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 13/08 PM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 13/08 PM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 13/08 PM _x000D_19/8/2024:01435615 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 13/08 PM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 13/08 PM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 13/08 PM _x000D_13/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 13/08 PM _x000D_12/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 13/08 PM _x000D_9/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 13/08 PM _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 13/08 PM _x000D_29/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 13/08 PM _x000D_29/7/2024:01435615 _x000D_26/7/2024:01435615 _x000D_24/7/2024:#Update - The Openreach notes state that 'the owner does not want anything done as he has remodeled his shop and does not want any drilling where the engineers would need to drill around the back wall. If the owner wants the installation to take place, there would need to be a survey so the engineers could possibly find another solution to get the cabling through, but shop keeper said he does not want any work taking place.' Action for Allwyn: discuss with the retailer how they would like to continue, if no work is consented to it may need to move to a site type 3. _x000D_23/7/2024:#Update - The Openreach notes state that 'the owner does not want anything done as he has remodeled his shop and does not want any drilling where the engineers would need to drill around the back wall. If the owner wants the installation to take place, there would need to be a survey so the engineers could possibly find another solution to get the cabling through, but shop keeper said he does not want any work taking place.' Action for Allwyn: discuss with the retailer how they would like to continue, if no work is consented to it may need to move to a site type 3. _x000D_22/7/2024:#Update - The Openreach notes state that 'the owner does not want anything done as he has remodeled his shop and does not want any drilling where the engineers would need to drill around the back wall. If the owner wants the installation to take place, there would need to be a survey so the engineers could possibly find another solution to get the cabling through, but shop keeper said he does not want any work taking place.' Action for Allwyn: discuss with the retailer how they would like to continue, if no work is consented to it may need to move to a site type 3. _x000D_22/7/2024:#Update - The Openreach notes state that 'the owner does not want anything done as he has remodeled his shop and does not want any drilling where the engineers would need to drill around the back wall. If the owner wants the installation to take place, there would need to be a survey so the engineers could possibly find another solution to get the cabling through, but shop keeper said he does not want any work taking place.' Action for Allwyn: discuss with the retailer how they would like to continue, if no work is consented to it may need to move to a site type 3. _x000D_19/6/2024:#Update - Order Complete _x000D_18/6/2024:#Update - Order Complete _x000D_17/6/2024:#Update - Order Complete _x000D_14/6/2024:Supplier Delay: KCI-3 (Order Completed) Delayed in Processing. _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 0 | 0 | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFP2337372 | 30015683 | 2.Commissioning | AM |  | 2024-06-13 | 2024-08-13 |  | 0 | [11 empty] | 0
493 | 430320 | 2512 | Batch 4 Jun24 | Type 3 | SoGEA/Mobile | Spar Stores | Mablethorpe | LN12 2EY | 2024-06-14 | 6/9/2024:#Update - Downgraded to a site type 3 _x000D_5/9/2024:#Update - Downgraded to a site type 3 _x000D_4/9/2024:#Update - Downgraded to a site type 3 _x000D_3/9/2024:#Update - Downgraded to a site type 3 _x000D_2/9/2024:#Update - Downgraded to a site type 3 _x000D_29/8/2024:#Update - Downgraded to a site type 3 _x000D_28/8/2024:#Update - Downgraded to a site type 3 _x000D_27/8/2024:#Update - Downgraded to a site type 3 _x000D_22/8/2024:#Update - Downgraded to a site type 3 _x000D_21/8/2024:#Update - Downgraded to a site type 3 _x000D_20/8/2024:#Update - Downgraded to a site type 3 _x000D_19/8/2024:#Update - Downgraded to a site type 3 _x000D_19/8/2024:01436042 _x000D_16/8/2024:#Update - Downgraded to a site type 3 _x000D_15/8/2024:#Update - Downgraded to a site type 3 _x000D_14/8/2024:#Update - Downgraded to a site type 3 _x000D_13/8/2024:#Update - Downgraded to a site type 3 _x000D_12/8/2024:#Update - Downgraded to a site type 3 _x000D_9/8/2024:#Update - Downgraded to a site type 3 _x000D_8/8/2024:31/07/2024 _x000D_6/8/2024:31/07/2024 _x000D_5/8/2024:31/07/2024 _x000D_2/8/2024:31/07/2024 _x000D_1/8/2024:31/07/2024 _x000D_31/7/2024:24/06/2024 _x000D_31/7/2024:24/06/2024 _x000D_30/7/2024:#Update ; Awaiting approval for Premium, 2x Engineers OOH work for 3 hours. _x000D_29/7/2024:#Update ; Awaiting approval for Premium, 2x Engineers OOH work for 3 hours. _x000D_29/7/2024:01436042 _x000D_26/7/2024:01436042 _x000D_24/7/2024:#Update ; Awaiting approval for Premium, 2x Engineers OOH work for 3 hours. _x000D_23/7/2024:#Update ; Awaiting approval for Premium, 2x Engineers OOH work for 3 hours. _x000D_22/7/2024:#Update ; Awaiting approval for Premium, 2x Engineers OOH work for 3 hours. _x000D_22/7/2024:#Update ; Awaiting approval for Premium, 2x Engineers OOH work for 3 hours. _x000D_4/7/2024:#Update supplier missed appointment due to routing issue - has been rescheduled for 3/07 AM _x000D_3/7/2024:#Update supplier missed appointment due to routing issue - has been rescheduled for 3/07 AM _x000D_2/7/2024:0 _x000D_1/7/2024:#Update supplier missed appointment due to routing issue - has been rescheduled for 3/07 AM _x000D_27/6/2024:#Update supplier missed appointment due to routing issue - has been rescheduled for 3/07 AM _x000D_25/6/2024:#Update supplier missed appointment due to routing issue - has been rescheduled for 3/07 AM _x000D_24/6/2024:#Update supplier missed appointment due to routing issue - has been rescheduled for 3/07 AM _x000D_20/6/2024:#Update supplier missed appointment due to routing issue - has been rescheduled for 3/07 AM _x000D_19/6/2024:#Update supplier missed appointment due to routing issue - has been rescheduled for 3/07 AM _x000D_18/6/2024:#Update Engineer was unable to complete job due to incorrect routing - will reappoint once updates for Openreach come in _x000D_17/6/2024:#Update Engineer was unable to complete job due to incorrect routing - will reappoint once updates for Openreach come in _x000D_14/6/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_13/6/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 9/9/2024:#Update - Downgraded to a site type 3 _x000D_6/9/2024:#Update - Downgraded to a site type 3 _x000D_5/9/2024:#Update - Downgraded to a site type 3 _x000D_4/9/2024:#Update - Downgraded to a site type 3 _x000D_3/9/2024:#Update - Downgraded to a site type 3 _x000D_2/9/2024:#Update - Downgraded to a site type 3 _x000D_29/8/2024:#Update - Downgraded to a site type 3 _x000D_28/8/2024:#Update - Downgraded to a site type 3 _x000D_27/8/2024:#Update - Downgraded to a site type 3 _x000D_22/8/2024:#Update - Downgraded to a site type 3 _x000D_21/8/2024:#Update - Downgraded to a site type 3 _x000D_20/8/2024:#Update - Downgraded to a site type 3 _x000D_19/8/2024:#Update - Downgraded to a site type 3 _x000D_19/8/2024:01436042 _x000D_16/8/2024:#Update - Downgraded to a site type 3 _x000D_15/8/2024:#Update - Downgraded to a site type 3 _x000D_14/8/2024:#Update - Downgraded to a site type 3 _x000D_13/8/2024:#Update - Downgraded to a site type 3 _x000D_12/8/2024:#Update - Downgraded to a site type 3 _x000D_9/8/2024:#Update - Downgraded to a site type 3 _x000D_8/8/2024:31/07/2024 _x000D_6/8/2024:31/07/2024 _x000D_5/8/2024:31/07/2024 _x000D_2/8/2024:31/07/2024 _x000D_1/8/2024:31/07/2024 _x000D_31/7/2024:24/06/2024 _x000D_31/7/2024:24/06/2024 _x000D_30/7/2024:#Update ; Awaiting approval for Premium, 2x Engineers OOH work for 3 hours. _x000D_29/7/2024:#Update ; Awaiting approval for Premium, 2x Engineers OOH work for 3 hours. _x000D_29/7/2024:01436042 _x000D_26/7/2024:01436042 _x000D_24/7/2024:#Update ; Awaiting approval for Premium, 2x Engineers OOH work for 3 hours. _x000D_23/7/2024:#Update ; Awaiting approval for Premium, 2x Engineers OOH work for 3 hours. _x000D_22/7/2024:#Update ; Awaiting approval for Premium, 2x Engineers OOH work for 3 hours. _x000D_22/7/2024:#Update ; Awaiting approval for Premium, 2x Engineers OOH work for 3 hours. _x000D_4/7/2024:#Update supplier missed appointment due to routing issue - has been rescheduled for 3/07 AM _x000D_3/7/2024:#Update supplier missed appointment due to routing issue - has been rescheduled for 3/07 AM _x000D_2/7/2024:0 _x000D_1/7/2024:#Update supplier missed appointment due to routing issue - has been rescheduled for 3/07 AM _x000D_27/6/2024:#Update supplier missed appointment due to routing issue - has been rescheduled for 3/07 AM _x000D_25/6/2024:#Update supplier missed appointment due to routing issue - has been rescheduled for 3/07 AM _x000D_24/6/2024:#Update supplier missed appointment due to routing issue - has been rescheduled for 3/07 AM _x000D_20/6/2024:#Update supplier missed appointment due to routing issue - has been rescheduled for 3/07 AM _x000D_19/6/2024:#Update supplier missed appointment due to routing issue - has been rescheduled for 3/07 AM _x000D_18/6/2024:#Update Engineer was unable to complete job due to incorrect routing - will reappoint once updates for Openreach come in _x000D_17/6/2024:#Update Engineer was unable to complete job due to incorrect routing - will reappoint once updates for Openreach come in _x000D_14/6/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_13/6/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 0 | #Update - Downgraded to a site type 3 | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996915 | 30016026 | 2.Commissioning | AM |  |  |  |  | 0 | [11 empty] | 0
494 | 631170 | 2602 | Batch 4 Jun24 | Type 1 | SOGEA | Spar Stores | Chester | CH3 5LB | 2024-07-04 | 9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:#Update - Order cancel is being attempted. EU advised this is a duplicate order under previous owners details. EU would like to cancel this order as the manager no longer works at shop. _x000D_17/6/2024:#Update - Order cancel is being attempted. EU advised this is a duplicate order under previous owners details. EU would like to cancel this order as the manager no longer works at shop. _x000D_14/6/2024:#Update - Order cancel is being attempted. EU advised this is a duplicate order under previous owners details. EU would like to cancel this order as the manager no longer works at shop. _x000D_13/6/2024:#Update - Order cancel is being attempted. EU advised this is a duplicate order under previous owners details. EU would like to cancel this order as the manager no longer works at shop. _x000D_12/6/2024:#Update - Order cancel is being attempted. EU advised this is a duplicate order under previous owners details. EU would like to cancel this order as the manager no longer works at shop. _x000D_11/6/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:#Update - Order cancel is being attempted. EU advised this is a duplicate order under previous owners details. EU would like to cancel this order as the manager no longer works at shop. _x000D_17/6/2024:#Update - Order cancel is being attempted. EU advised this is a duplicate order under previous owners details. EU would like to cancel this order as the manager no longer works at shop. _x000D_14/6/2024:#Update - Order cancel is being attempted. EU advised this is a duplicate order under previous owners details. EU would like to cancel this order as the manager no longer works at shop. _x000D_13/6/2024:#Update - Order cancel is being attempted. EU advised this is a duplicate order under previous owners details. EU would like to cancel this order as the manager no longer works at shop. _x000D_12/6/2024:#Update - Order cancel is being attempted. EU advised this is a duplicate order under previous owners details. EU would like to cancel this order as the manager no longer works at shop. _x000D_11/6/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ |  |  | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFS996897 | 30016018 | 2.Commissioning | AM |  | 2024-06-13 | 2024-07-03 | 2024-07-03 | TRUE |  |  |  | 2024-08-01 | [7 empty] | 0
495 | 457976 | 895 | Batch 3 May24 | Type 1 | SOGEA | NISA LOCAL | HUNTINGDON | PE29 1NJ | 2024-06-07 | 22/7/2024:#Update - Retailer to confirm new appoint of 15/07. _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:#Update - Allwyn to discuss with retailer about retaining access to the back of the building so the engineer can access DP as it is behind a locked area which retailer could not access without a key. Re-appointed for 14.06 AM. Allwyn to confirm with retailer that this date is suitable. _x000D_17/6/2024:#Update - Allwyn to discuss with retailer about retaining access to the back of the building so the engineer can access DP as it is behind a locked area which retailer could not access without a key. Re-appointed for 14.06 AM. Allwyn to confirm with retailer that this date is suitable. _x000D_14/6/2024:#Update - Allwyn to discuss with retailer about retaining access to the back of the building so the engineer can access DP as it is behind a locked area which retailer could not access without a key. Re-appointed for 14.06 AM. Allwyn to confirm with retailer that this date is suitable. _x000D_13/6/2024:#Update - Allwyn to discuss with retailer about retaining access to the back of the building so the engineer can access DP as it is behind a locked area which retailer could not access without a key. Re-appointed for 14.06 AM. Allwyn to confirm with retailer that this date is suitable. _x000D_12/6/2024:#Update - Allwyn to discuss with retailer about retaining access to the back of the building so the engineer can access DP as it is behind a locked area which retailer could not access without a key. Re-appointed for 14.06 AM. Allwyn to confirm with retailer that this date is suitable. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 22/7/2024:#Update - Retailer to confirm new appoint of 15/07. _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:#Update - Allwyn to discuss with retailer about retaining access to the back of the building so the engineer can access DP as it is behind a locked area which retailer could not access without a key. Re-appointed for 14.06 AM. Allwyn to confirm with retailer that this date is suitable. _x000D_17/6/2024:#Update - Allwyn to discuss with retailer about retaining access to the back of the building so the engineer can access DP as it is behind a locked area which retailer could not access without a key. Re-appointed for 14.06 AM. Allwyn to confirm with retailer that this date is suitable. _x000D_14/6/2024:#Update - Allwyn to discuss with retailer about retaining access to the back of the building so the engineer can access DP as it is behind a locked area which retailer could not access without a key. Re-appointed for 14.06 AM. Allwyn to confirm with retailer that this date is suitable. _x000D_13/6/2024:#Update - Allwyn to discuss with retailer about retaining access to the back of the building so the engineer can access DP as it is behind a locked area which retailer could not access without a key. Re-appointed for 14.06 AM. Allwyn to confirm with retailer that this date is suitable. _x000D_12/6/2024:#Update - Allwyn to discuss with retailer about retaining access to the back of the building so the engineer can access DP as it is behind a locked area which retailer could not access without a key. Re-appointed for 14.06 AM. Allwyn to confirm with retailer that this date is suitable. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-05-20 | 20/05/24: CSL to provide update |  |  | 3.Allwyn to arrange rtr install | VFP2301092 | 30013785 | 2.Commissioning | AM |  | 2024-05-17 | 2024-07-15 | 2024-07-15 | TRUE |  |  |  | 2024-08-02 | [7 empty] | 0
496 | 670119 | 1073 | Batch 3 May24 | Type 3 | SoGEA/Mobile | Spar Stores | NEWPORT | NP19 8JH | 2024-06-07 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:21/06/2024 _x000D_1/8/2024:21/06/2024 _x000D_31/7/2024:21/06/2024 _x000D_31/7/2024:21/06/2024 _x000D_30/7/2024:#Update - Site type change to Type 3 as approved by allwyn. 21/03 _x000D_29/7/2024:#Update - Site type change to Type 3 as approved by allwyn. 21/03 _x000D_29/7/2024:01405708 _x000D_26/7/2024:01405708 _x000D_24/7/2024:#Update - Site type change to Type 3 as approved by allwyn. 21/03 _x000D_23/7/2024:#Update - Site type change to Type 3 as approved by allwyn. 21/03 _x000D_22/7/2024:#Update - Site type change to Type 3 as approved by allwyn. 21/03 _x000D_22/7/2024:#Update - Site type change to Type 3 as approved by allwyn. 21/03 _x000D_18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:21/06/2024 _x000D_1/8/2024:21/06/2024 _x000D_31/7/2024:21/06/2024 _x000D_31/7/2024:21/06/2024 _x000D_30/7/2024:#Update - Site type change to Type 3 as approved by allwyn. 21/03 _x000D_29/7/2024:#Update - Site type change to Type 3 as approved by allwyn. 21/03 _x000D_29/7/2024:01405708 _x000D_26/7/2024:01405708 _x000D_24/7/2024:#Update - Site type change to Type 3 as approved by allwyn. 21/03 _x000D_23/7/2024:#Update - Site type change to Type 3 as approved by allwyn. 21/03 _x000D_22/7/2024:#Update - Site type change to Type 3 as approved by allwyn. 21/03 _x000D_22/7/2024:#Update - Site type change to Type 3 as approved by allwyn. 21/03 _x000D_18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | 0 | 2024-05-23 | 23/05/2024: CSL to provide an update |  |  | 3.Allwyn to arrange rtr install | VFP2301270 | 30013963 | 2.Commissioning | AM | [8 empty] | 2024-07-24 | [7 empty] | 0
497 | 471658 | 1207 | Batch 3 May24 | Type 1 | FTTP | Broadstairs Londis | Broadstairs | CT10 1LP | 2024-06-07 | 18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:Order Completed _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:Order Completed _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301404 | 30014097 | 6.Failed router install | AM |  | 2024-05-28 | 2024-06-14 | 2024-06-14 | TRUE | [7 empty] | 2024-07-03 | 242005008591 |  | 2024-07-04 | 1
498 | 634695 | 1537 | Batch 4 Jun24 | Type 1 | SoGEA/Mobile | SPAR Greater Leys | Oxford | OX4 7EX | 2024-06-07 | 6/9/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_5/9/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_4/9/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_3/9/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_2/9/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_29/8/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_28/8/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_27/8/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_22/8/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_21/8/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_20/8/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_19/8/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_19/8/2024:01437956 _x000D_16/8/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_15/8/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_14/8/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_13/8/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_12/8/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_9/8/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_8/8/2024:19/06/2024 _x000D_6/8/2024:19/06/2024 _x000D_5/8/2024:19/06/2024 _x000D_2/8/2024:19/06/2024 _x000D_1/8/2024:19/06/2024 _x000D_31/7/2024:19/06/2024 _x000D_31/7/2024:19/06/2024 _x000D_30/7/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_29/7/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_29/7/2024:01437956 _x000D_26/7/2024:01437956 _x000D_24/7/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_23/7/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_22/7/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_22/7/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_19/7/2024:Update: Order Amended _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:Update: Order Amended _x000D_25/6/2024:Update: Order Amended _x000D_24/6/2024:Update: Order Amended _x000D_20/6/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 04/07/2024.We will continue to provide update as they become available. _x000D_19/6/2024:This order is with Surveyor Joe O¿Neill. Survey will be completed within 5 working days. Notes will be updated and order progressed when solution has been agreed with customer. _x000D_18/6/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 20/06/2024.We will continue to provide update as they become available. _x000D_17/6/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_6/9/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_5/9/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_4/9/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_3/9/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_2/9/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_29/8/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_28/8/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_27/8/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_22/8/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_21/8/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_20/8/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_19/8/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_19/8/2024:01437956 _x000D_16/8/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_15/8/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_14/8/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_13/8/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_12/8/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_9/8/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_8/8/2024:19/06/2024 _x000D_6/8/2024:19/06/2024 _x000D_5/8/2024:19/06/2024 _x000D_2/8/2024:19/06/2024 _x000D_1/8/2024:19/06/2024 _x000D_31/7/2024:19/06/2024 _x000D_31/7/2024:19/06/2024 _x000D_30/7/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_29/7/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_29/7/2024:01437956 _x000D_26/7/2024:01437956 _x000D_24/7/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_23/7/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_22/7/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_22/7/2024:#Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 _x000D_19/7/2024:Update: Order Amended _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:Update: Order Amended _x000D_25/6/2024:Update: Order Amended _x000D_24/6/2024:Update: Order Amended _x000D_20/6/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 04/07/2024.We will continue to provide update as they become available. _x000D_19/6/2024:This order is with Surveyor Joe O¿Neill. Survey will be completed within 5 working days. Notes will be updated and order progressed when solution has been agreed with customer. _x000D_18/6/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 20/06/2024.We will continue to provide update as they become available. _x000D_17/6/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update - An advanced upgrade is required - proposal sent to Vodafone on 19/06 | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFS984875 | 30015303 | 1.Provisioning | AM |  | 2024-06-14 | 2024-08-21 |  | 0 | [11 empty] | 0
499 | 638835 | 1538 | Batch 4 Jun24 | Type 1 | FTTP/Mobile | Spar Stores | Ballymena | BT43 6SA | 2024-06-07 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:Update: Order Amended _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:Update: Order Amended _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | 0 | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFP2338536 | 30015544 | 1.Provisioning | AM |  | 2024-06-14 | 2024-08-22 |  | 0 | [11 empty] | 0
500 | 669703 | 1540 | Batch 4 Jun24 | Type 1 | FTTP | Select Convenience Store | Newcastle upon Tyne | NE12 8GA | 2024-06-07 | 19/7/2024:#Update - NFA - Allwyn confirmed new install date 31/07 with retailer _x000D_18/7/2024:#Update - NFA - Allwyn confirmed new install date 31/07 with retailer _x000D_17/7/2024:#Update - NFA - Allwyn confirmed new install date 31/07 with retailer _x000D_16/7/2024:#Update - installation unsuccessful due to a hoist support requirement - cannot deploy Tetra / Ladder system. Appointment to be rescheduled with appropriate engineer _x000D_15/7/2024:#Update - installation unsuccessful due to a hoist support requirement - cannot deploy Tetra / Ladder system. Appointment to be rescheduled with appropriate engineer _x000D_12/7/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer _x000D_11/7/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer _x000D_10/7/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer _x000D_9/7/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer _x000D_4/7/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer _x000D_3/7/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer _x000D_27/6/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer _x000D_25/6/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer _x000D_24/6/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer _x000D_20/6/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer _x000D_19/6/2024:#Update - NFA - Allwyn confirmed reappointed install date with retailer _x000D_18/6/2024:#Update - NFA - Allwyn confirmed reappointed install date with retailer _x000D_17/6/2024:#Update - NFA - Allwyn confirmed reappointed install date with retailer _x000D_14/6/2024:#Update - NFA - Allwyn confirmed reappointed install date with retailer _x000D_13/6/2024:#Update - NFA - Allwyn confirmed reappointed install date with retailer _x000D_12/6/2024:#Update - NFA - Allwyn confirmed reappointed install date with retailer _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:#Update - NFA - Allwyn confirmed new install date 31/07 with retailer _x000D_18/7/2024:#Update - NFA - Allwyn confirmed new install date 31/07 with retailer _x000D_17/7/2024:#Update - NFA - Allwyn confirmed new install date 31/07 with retailer _x000D_16/7/2024:#Update - installation unsuccessful due to a hoist support requirement - cannot deploy Tetra / Ladder system. Appointment to be rescheduled with appropriate engineer _x000D_15/7/2024:#Update - installation unsuccessful due to a hoist support requirement - cannot deploy Tetra / Ladder system. Appointment to be rescheduled with appropriate engineer _x000D_12/7/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer _x000D_11/7/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer _x000D_10/7/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer _x000D_9/7/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer _x000D_4/7/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer _x000D_3/7/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer _x000D_27/6/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer _x000D_25/6/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer _x000D_24/6/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer _x000D_20/6/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer _x000D_19/6/2024:#Update - NFA - Allwyn confirmed reappointed install date with retailer _x000D_18/6/2024:#Update - NFA - Allwyn confirmed reappointed install date with retailer _x000D_17/6/2024:#Update - NFA - Allwyn confirmed reappointed install date with retailer _x000D_14/6/2024:#Update - NFA - Allwyn confirmed reappointed install date with retailer _x000D_13/6/2024:#Update - NFA - Allwyn confirmed reappointed install date with retailer _x000D_12/6/2024:#Update - NFA - Allwyn confirmed reappointed install date with retailer _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 5.CSL | VFP2338603 | 30015380 | 6.Failed router install | AM |  | 2024-06-14 | 2024-06-14 | 2024-06-14 | TRUE |  |  |  | 2024-07-17 |  |  |  | 2024-07-17 | 238004926221 |  | 2024-07-18 | 1
501 | 665291 | 1852 | Batch 4 Jun24 | Type 1 | SoGEA/Mobile | Watcombe Post Office | TORQUAY | TQ2 8NU | 2024-09-02 | 3/9/2024:#Update - Completed - 30/08/2024 09:01 _x000D_2/9/2024:#Update - Completed - 30/08/2024 09:01 _x000D_29/8/2024:#Update - Awaiting feedback from OR. _x000D_28/8/2024:#Update - Awaiting feedback from OR. _x000D_27/8/2024:#Update - Awaiting feedback from OR. _x000D_22/8/2024:#Update - Awaiting feedback from OR. _x000D_21/8/2024:#Update - Awaiting feedback from OR. _x000D_20/8/2024:#Update - Awaiting feedback from OR. _x000D_19/8/2024:#Update - Awaiting feedback from OR. _x000D_19/8/2024:01437724 _x000D_16/8/2024:#Update - Awaiting feedback from OR. _x000D_15/8/2024:#Update - Awaiting feedback from OR. _x000D_14/8/2024:#Update - Awaiting feedback from OR. _x000D_13/8/2024:#Update - Awaiting feedback from OR. _x000D_12/8/2024:#Update - Awaiting feedback from OR. _x000D_9/8/2024:#Update - Awaiting feedback from OR. _x000D_8/8/2024:01/08/2024 _x000D_6/8/2024:01/08/2024 _x000D_5/8/2024:01/08/2024 _x000D_2/8/2024:01/08/2024 _x000D_1/8/2024:01/08/2024 _x000D_31/7/2024:Update: Order Amended _x000D_31/7/2024:37893 _x000D_30/7/2024:Update: Order Amended _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:25/07/2024 07:45 _x000D_26/7/2024:25/07/2024 07:45 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:Your order has been delayed by our Suppliers due to unable to access distribution point within customer premises. Please check with end user and re-appoint order once access arranged. _x000D_22/7/2024:Your order has been delayed by our Suppliers due to unable to access distribution point within customer premises. Please check with end user and re-appoint order once access arranged. _x000D_18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 3/9/2024:#Update - Completed - 30/08/2024 09:01 _x000D_2/9/2024:#Update - Completed - 30/08/2024 09:01 _x000D_29/8/2024:#Update - Awaiting feedback from OR. _x000D_28/8/2024:#Update - Awaiting feedback from OR. _x000D_27/8/2024:#Update - Awaiting feedback from OR. _x000D_22/8/2024:#Update - Awaiting feedback from OR. _x000D_21/8/2024:#Update - Awaiting feedback from OR. _x000D_20/8/2024:#Update - Awaiting feedback from OR. _x000D_19/8/2024:#Update - Awaiting feedback from OR. _x000D_19/8/2024:01437724 _x000D_16/8/2024:#Update - Awaiting feedback from OR. _x000D_15/8/2024:#Update - Awaiting feedback from OR. _x000D_14/8/2024:#Update - Awaiting feedback from OR. _x000D_13/8/2024:#Update - Awaiting feedback from OR. _x000D_12/8/2024:#Update - Awaiting feedback from OR. _x000D_9/8/2024:#Update - Awaiting feedback from OR. _x000D_8/8/2024:01/08/2024 _x000D_6/8/2024:01/08/2024 _x000D_5/8/2024:01/08/2024 _x000D_2/8/2024:01/08/2024 _x000D_1/8/2024:01/08/2024 _x000D_31/7/2024:Update: Order Amended _x000D_31/7/2024:37893 _x000D_30/7/2024:Update: Order Amended _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:25/07/2024 07:45 _x000D_26/7/2024:25/07/2024 07:45 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:Your order has been delayed by our Suppliers due to unable to access distribution point within customer premises. Please check with end user and re-appoint order once access arranged. _x000D_22/7/2024:Your order has been delayed by our Suppliers due to unable to access distribution point within customer premises. Please check with end user and re-appoint order once access arranged. _x000D_18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFS983276 | 30015259 | 2.Commissioning | AM |  | 2024-06-14 | 2024-08-29 |  | 0 | [11 empty] | 0
502 | 667394 | 1855 | Batch 4 Jun24 | Type 1 | SOGEA | Premier Centrall Stores | PONTYPRIDD | CF37 4PN | 2024-06-07 | 18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983376 | 30015234 | 2.Commissioning | AM |  | 2024-06-14 | 2024-06-14 | 2024-06-14 | TRUE |  |  |  | 2024-07-17 | [7 empty] | 0
503 | 665033 | 1857 | Batch 4 Jun24 | Type 1 | SOGEA | One Stop | ST. ALBANS | AL3 8HZ | 2024-06-07 | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:Update: Order Amended _x000D_24/6/2024:Update: Order Amended _x000D_20/6/2024:Update: Order Amended _x000D_19/6/2024:Update: Order Amended _x000D_18/6/2024:Your order has been delayed by our Suppliers due to a hoist being required to complete the installation. Please check with end user and re-appoint order for earliest date. _x000D_17/6/2024:Supplier Delay: Delayed due to health and safety issues _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:Update: Order Amended _x000D_24/6/2024:Update: Order Amended _x000D_20/6/2024:Update: Order Amended _x000D_19/6/2024:Update: Order Amended _x000D_18/6/2024:Your order has been delayed by our Suppliers due to a hoist being required to complete the installation. Please check with end user and re-appoint order for earliest date. _x000D_17/6/2024:Supplier Delay: Delayed due to health and safety issues _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983377 | 30015264 | 2.Commissioning | AM |  | 2024-06-14 | 2024-06-14 | 2024-06-14 | TRUE |  |  |  | 2024-07-08 | [7 empty] | 0
504 | 665543 | 1858 | Batch 4 Jun24 | Type 1 | SOGEA | Gwalchmai PO | HOLYHEAD | LL65 4PU | 2024-06-07 | 23/7/2024:Order Completed _x000D_22/7/2024:Order Completed _x000D_22/7/2024:0 _x000D_18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 23/7/2024:Order Completed _x000D_22/7/2024:Order Completed _x000D_22/7/2024:0 _x000D_18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983379 | 30015217 | 2.Commissioning | AM |  | 2024-06-14 | 2024-07-19 | 2024-07-19 | TRUE |  |  |  | 2024-08-14 | [7 empty] | 0
505 | 609912 | 1928 | Batch 4 Jun24 | Type 1 | SOGEA | Centra Sweeneys | Omagh | BT78 5HY | 2024-06-07 | 18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983508 | 30015740 | 6.Failed router install | AM |  | 2024-06-14 | 2024-06-14 | 2024-06-14 | TRUE |  |  |  | 2024-07-11 |  |  |  | 2024-07-11 | 242005010290 |  | 2024-07-11 | 1
506 | 616709 | 1931 | Batch 4 Jun24 | Type 1 | SOGEA | Andys Convenience Store | Newport | NP20 2ED | 2024-06-07 | 18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983509 | 30015716 | 6.Failed router install | AM |  | 2024-06-14 | 2024-06-14 | 2024-06-14 | TRUE |  |  |  | 2024-07-15 |  |  |  | 2024-07-15 | 23A004945360 |  | 2024-07-16 | 1
507 | 602848 | 1935 | Batch 4 Jun24 | Type 1 | SOGEA | Boughton Convenience Store | Newark | NG22 9HN | 2024-06-07 | 18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983512 | 30015696 | 6.Failed router install | AM |  | 2024-06-14 | 2024-06-14 | 2024-06-14 | TRUE |  |  |  | 2024-07-05 |  |  |  | 2024-07-11 | 23A004945885 |  | 2024-07-23 | 1
508 | 467201 | 1937 | Batch 4 Jun24 | Type 1 | SOGEA | Premier Sandal Convenience Store | Wakefield | WF1 5NU | 2024-06-07 | 19/7/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_18/7/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_17/7/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_16/7/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_15/7/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_12/7/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_11/7/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_10/7/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_9/7/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_4/7/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_3/7/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_27/6/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_25/6/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_24/6/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_20/6/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_19/6/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_18/6/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_17/6/2024:Supplier Delay: Issues with provision of the underground network, please await for further details. _x000D_14/6/2024:Supplier Delay: Issues with provision of the underground network, please await for further details. _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 19/7/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_18/7/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_17/7/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_16/7/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_15/7/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_12/7/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_11/7/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_10/7/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_9/7/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_4/7/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_3/7/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_27/6/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_25/6/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_24/6/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_20/6/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_19/6/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_18/6/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_17/6/2024:Supplier Delay: Issues with provision of the underground network, please await for further details. _x000D_14/6/2024:Supplier Delay: Issues with provision of the underground network, please await for further details. _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983513 | 30015725 | 6.Failed router install | AM |  | 2024-06-14 | 2024-06-14 | 2024-06-14 | TRUE |  |  |  | 2024-07-11 |  |  |  | 2024-07-11 | 242005008877 |  | 2024-07-11 | 1
509 | 455456 | 1938 | Batch 4 Jun24 | Type 1 | SoGEA/Mobile | P and M Convenience | WAKEFIELD | WF4 2HF | 2024-06-07 | 9/8/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_8/8/2024:17/06/2024 _x000D_6/8/2024:17/06/2024 _x000D_5/8/2024:17/06/2024 _x000D_2/8/2024:17/06/2024 _x000D_1/8/2024:17/06/2024 _x000D_31/7/2024:17/06/2024 _x000D_31/7/2024:17/06/2024 _x000D_30/7/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_29/7/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_29/7/2024:01441059 _x000D_26/7/2024:01441059 _x000D_24/7/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_23/7/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_22/7/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_22/7/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 9/8/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_8/8/2024:17/06/2024 _x000D_6/8/2024:17/06/2024 _x000D_5/8/2024:17/06/2024 _x000D_2/8/2024:17/06/2024 _x000D_1/8/2024:17/06/2024 _x000D_31/7/2024:17/06/2024 _x000D_31/7/2024:17/06/2024 _x000D_30/7/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_29/7/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_29/7/2024:01441059 _x000D_26/7/2024:01441059 _x000D_24/7/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_23/7/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_22/7/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_22/7/2024:#Update - Installation was not completed on 14/06.Complex dig is required. Dig activity has been raised. Please allow 7 working days for an update. _x000D_18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983515 | 30015709 | 2.Commissioning | AM |  | 2024-06-14 | 2024-08-05 | 2024-08-05 14:00 | TRUE | [11 empty] | 0
510 | 635182 | 1941 | Batch 4 Jun24 | Type 1 | SOGEA | Central Convenience | Bristol | BS15 4QT | 2024-06-07 | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_3/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_27/6/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_25/6/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_24/6/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_20/6/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_19/6/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_18/6/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_17/6/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_14/6/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_3/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_27/6/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_25/6/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_24/6/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_20/6/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_19/6/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_18/6/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_17/6/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_14/6/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983516 | 30015699 | 2.Commissioning | AM |  | 2024-06-14 | 2024-06-14 | 2024-06-14 | TRUE |  |  |  | 2024-09-04 | [7 empty] | 0
511 | 207437 | 1943 | Batch 4 Jun24 | Type 1 | SOGEA | Saracens Filling Station | DUNMOW | CM6 2LT | 2024-07-03 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:Order Completed _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:Order Completed _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 0 | 0 | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFS983518 | 30015703 | 2.Commissioning | AM | [8 empty] | 2024-07-24 | [7 empty] | 0
512 | 448871 | 1944 | Batch 4 Jun24 | Type 1 | SOGEA | Best One Aquarius News | BRADFORD | BD1 3JL | 2024-06-07 | 18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983519 | 30015701 | 6.Failed router install | AM |  | 2024-06-14 | 2024-06-14 | 2024-06-14 | TRUE |  |  |  | 2024-07-10 |  |  |  | 2024-07-10 | 242005008869 |  |  | 1
513 | 627912 | 1945 | Batch 4 Jun24 | Type 1 | FTTP | Russells Food & Drink | Donaghadee | BT21 0AD | 2024-06-07 | 18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2337380 | 30015675 | 6.Failed router install | AM |  | 2024-06-14 | 2024-06-14 | 2024-06-14 | TRUE |  |  |  | 2024-07-05 |  |  |  | 2024-07-05 | 242005010408 |  |  | 1
514 | 438357 | 1947 | Batch 4 Jun24 | Type 1 | SOGEA | Gareth Rees Newsagents | ABERDARE | CF44 7AP | 2024-06-07 | 18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983521 | 30015712 | 6.Failed router install | AM |  | 2024-06-14 | 2024-06-14 | 2024-06-14 | TRUE |  |  |  | 2024-07-16 |  |  |  | 2024-07-16 | 23A004945351 |  | 2024-07-17 | 1
515 | 632351 | 1948 | Batch 4 Jun24 | Type 1 | FTTP | LINDSAY HILL | Newry | BT34 1HH | 2024-06-07 | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:Update: Order Amended _x000D_15/7/2024:Update: Order Amended _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:0 _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:Update: Order Amended _x000D_25/6/2024:0 _x000D_24/6/2024:Your order has been delayed. The appointment has been delayed due to a Hazard. Landlord permission required. Please check with end user and reappoint the order if still required. _x000D_20/6/2024:Your order has been delayed. The appointment has been delayed due to a Hazard. Landlord permission required. Please check with end user and reappoint the order if still required. _x000D_19/6/2024:Your order has been delayed. The appointment has been delayed due to a Hazard. Landlord permission required. Please check with end user and reappoint the order if still required. _x000D_18/6/2024:Your order has been delayed. The appointment has been delayed due to a Hazard. Landlord permission required. Please check with end user and reappoint the order if still required. _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:Update: Order Amended _x000D_15/7/2024:Update: Order Amended _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:0 _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:Update: Order Amended _x000D_25/6/2024:0 _x000D_24/6/2024:Your order has been delayed. The appointment has been delayed due to a Hazard. Landlord permission required. Please check with end user and reappoint the order if still required. _x000D_20/6/2024:Your order has been delayed. The appointment has been delayed due to a Hazard. Landlord permission required. Please check with end user and reappoint the order if still required. _x000D_19/6/2024:Your order has been delayed. The appointment has been delayed due to a Hazard. Landlord permission required. Please check with end user and reappoint the order if still required. _x000D_18/6/2024:Your order has been delayed. The appointment has been delayed due to a Hazard. Landlord permission required. Please check with end user and reappoint the order if still required. _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2337379 | 30015681 | 2.Commissioning | AM |  | 2024-06-14 | 2024-06-14 | 2024-06-14 | TRUE |  |  |  | 2024-07-16 | [7 empty] | 0
516 | 444324 | 1950 | Batch 4 Jun24 | Type 1 | FTTP/Mobile | Nisa Local | HITCHIN | SG5 2PD | 2024-07-11 | 6/9/2024:#Update Your order has been delayed. Dig work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 04/09/2024. We will continue to provide update as they become available. _x000D_5/9/2024:#Update Your order has been delayed. Dig work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 04/09/2024. We will continue to provide update as they become available. _x000D_4/9/2024:#Update Your order has been delayed. Dig work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 04/09/2024. We will continue to provide update as they become available. _x000D_3/9/2024:#Update Your order has been delayed. Dig work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 04/09/2024. We will continue to provide update as they become available. _x000D_2/9/2024:#Update Your order has been delayed. Dig work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 04/09/2024. We will continue to provide update as they become available. _x000D_29/8/2024:#Update Your order has been delayed. Dig work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 04/09/2024. We will continue to provide update as they become available. _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:Your order has been delayed. Dig work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 27/08/2024. We will continue to provide update as they become available. _x000D_21/8/2024:Your order has been delayed. Dig work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 27/08/2024. We will continue to provide update as they become available. _x000D_20/8/2024:Your order has been delayed. Dig work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 27/08/2024. We will continue to provide update as they become available. _x000D_19/8/2024:Your order has been delayed. Civils work required. Our Suppliers have given us a review date of 28/08/2024. We will continue to provide update as they become available. _x000D_19/8/2024:16/08/2024 18:54 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:Update: Order Amended _x000D_31/7/2024:Update: Order Amended _x000D_31/7/2024:37119 _x000D_30/7/2024:Update: Order Amended _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:25/07/2024 16:19 _x000D_26/7/2024:25/07/2024 16:19 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:Order Completed _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 9/9/2024:#Update Your order has been delayed. Dig work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 04/09/2024. We will continue to provide update as they become available. _x000D_6/9/2024:#Update Your order has been delayed. Dig work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 04/09/2024. We will continue to provide update as they become available. _x000D_5/9/2024:#Update Your order has been delayed. Dig work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 04/09/2024. We will continue to provide update as they become available. _x000D_4/9/2024:#Update Your order has been delayed. Dig work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 04/09/2024. We will continue to provide update as they become available. _x000D_3/9/2024:#Update Your order has been delayed. Dig work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 04/09/2024. We will continue to provide update as they become available. _x000D_2/9/2024:#Update Your order has been delayed. Dig work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 04/09/2024. We will continue to provide update as they become available. _x000D_29/8/2024:#Update Your order has been delayed. Dig work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 04/09/2024. We will continue to provide update as they become available. _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:Your order has been delayed. Dig work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 27/08/2024. We will continue to provide update as they become available. _x000D_21/8/2024:Your order has been delayed. Dig work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 27/08/2024. We will continue to provide update as they become available. _x000D_20/8/2024:Your order has been delayed. Dig work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 27/08/2024. We will continue to provide update as they become available. _x000D_19/8/2024:Your order has been delayed. Civils work required. Our Suppliers have given us a review date of 28/08/2024. We will continue to provide update as they become available. _x000D_19/8/2024:16/08/2024 18:54 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:Update: Order Amended _x000D_31/7/2024:Update: Order Amended _x000D_31/7/2024:37119 _x000D_30/7/2024:Update: Order Amended _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:25/07/2024 16:19 _x000D_26/7/2024:25/07/2024 16:19 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:Order Completed _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | Your order has been delayed. Dig work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 13/09/2024. We will continue to provide update as they become available. | #Update Your order has been delayed. Dig work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 04/09/2024. We will continue to provide update as they become available. | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFP2347986 | 30015732 | 1.Provisioning | AM |  | 2024-06-14 | 2024-08-15 |  | 0 | [11 empty] | 0
517 | 205360 | 1954 | Batch 4 Jun24 | Type 1 | SOGEA | Vivo | MAGHERA | BT46 5AG | 2024-06-07 | 19/7/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_18/7/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_17/7/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_16/7/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_15/7/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_12/7/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_11/7/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_10/7/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_9/7/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_4/7/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_3/7/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_2/7/2024:0 _x000D_1/7/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_27/6/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_25/6/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_24/6/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_20/6/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_19/6/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_18/6/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_17/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 19/7/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_18/7/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_17/7/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_16/7/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_15/7/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_12/7/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_11/7/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_10/7/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_9/7/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_4/7/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_3/7/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_2/7/2024:0 _x000D_1/7/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_27/6/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_25/6/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_24/6/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_20/6/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_19/6/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_18/6/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_17/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983524 | 30015745 | 2.Commissioning | AM |  | 2024-06-14 | 2024-06-14 | 2024-06-14 | TRUE |  |  |  | 2024-07-08 | [7 empty] | 0
518 | 231999 | 1955 | Batch 4 Jun24 | Type 1 | SoGEA/Mobile | Kennys Food Fayre | COLERAINE | BT51 5QP | 2024-06-07 | 9/8/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_8/8/2024:17/06/2024 _x000D_6/8/2024:17/06/2024 _x000D_5/8/2024:17/06/2024 _x000D_2/8/2024:17/06/2024 _x000D_1/8/2024:17/06/2024 _x000D_31/7/2024:17/06/2024 _x000D_31/7/2024:17/06/2024 _x000D_30/7/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_29/7/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_29/7/2024:01438250 _x000D_26/7/2024:01438250 _x000D_24/7/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_23/7/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_22/7/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_22/7/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 9/8/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_8/8/2024:17/06/2024 _x000D_6/8/2024:17/06/2024 _x000D_5/8/2024:17/06/2024 _x000D_2/8/2024:17/06/2024 _x000D_1/8/2024:17/06/2024 _x000D_31/7/2024:17/06/2024 _x000D_31/7/2024:17/06/2024 _x000D_30/7/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_29/7/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_29/7/2024:01438250 _x000D_26/7/2024:01438250 _x000D_24/7/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_23/7/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_22/7/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_22/7/2024:#Update missed appointment due to the site only having FTTP available. Will cancel and reorder correct service then update _x000D_18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983525 | 30015702 | 2.Commissioning | AM |  | 2024-06-14 | 2024-08-05 | 2024-08-05 12:06 | TRUE | [11 empty] | 0
519 | 644706 | 2766 | Batch 4 Jun24 | Type 1 | SOGEA | Spar Stores | Rossendale | BB4 8EW | 2024-05-10 | 18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:Update: Order Completed by Supplier _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:Update: Order Completed by Supplier _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996899 | 30016115 | 2.Commissioning | AM |  | 2024-06-14 | 2024-06-14 | 2024-06-14 | TRUE |  |  |  | 2024-07-15 | [7 empty] | 0
520 | 669524 | 2799 | Batch 4 Jun24 | Type 1 | SOGEA | Post Office | Skegness | PE25 1QY | 2024-05-10 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 0 | 0 | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFS1032720 | 30016021 | 2.Commissioning | AM | [8 empty] | 2024-07-25 | [7 empty] | 0
521 | 455162 | 2926 | Batch 4 Jun24 | Type 1 | SOGEA | Budgens Stores Ltd | Holt | NR25 6DN | 2024-05-10 | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2353451 | 30015966 | 2.Commissioning | AM |  | 2024-06-14 | 2024-06-14 | 2024-06-14 | TRUE |  |  |  | 2024-07-03 | [7 empty] | 0
522 | 113218 | 2929 | Batch 4 Jun24 | Type 1 | FTTP/Mobile | Spar | Newry | BT34 1QA | 2024-05-10 | 6/9/2024:#update - confirmed re-appointment, _x000D_5/9/2024:#update - confirmed re-appointment, _x000D_4/9/2024:#update - confirmed re-appointment, _x000D_3/9/2024:#update - confirmed re-appointment, _x000D_2/9/2024:#update - confirmed re-appointment, _x000D_29/8/2024:#update - confirmed re-appointment, _x000D_28/8/2024:#Update - order reraised - new installation date 27/08 - AM _x000D_27/08 - order reraised, forecasted install date 16/09 | 9/9/2024:#update - confirmed re-appointment, _x000D_6/9/2024:#update - confirmed re-appointment, _x000D_5/9/2024:#update - confirmed re-appointment, _x000D_4/9/2024:#update - confirmed re-appointment, _x000D_3/9/2024:#update - confirmed re-appointment, _x000D_2/9/2024:#update - confirmed re-appointment, _x000D_29/8/2024:#update - confirmed re-appointment, _x000D_28/8/2024:#Update - order reraised - new installation date 27/08 - AM _x000D_27/08 - order reraised, forecasted install date 16/09 | 0 | #update - confirmed re-appointment, | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFP2353453 | 30015947 | 1.Provisioning | AM |  | 2024-06-14 | 2024-06-14 |  | 0 | [11 empty] | 0
523 | 671971 | 2930 | Batch 4 Jun24 | Type 1 | SOGEA | Spar Ballynure | Ballyclare | BT39 9UA | 2024-05-10 | 6/9/2024:#Update - Engineer found the socket, but it needs a socket relocation. - Engineer called back. He's found what looks to be the socket, however, it's not labelled and it's located upstairs, which is far too far away from the terminal. He's emailing in some photo's that I'll merge to this case once delivered. _x000D_5/9/2024:#Update - Engineer found the socket, but it needs a socket relocation. - Engineer called back. He's found what looks to be the socket, however, it's not labelled and it's located upstairs, which is far too far away from the terminal. He's emailing in some photo's that I'll merge to this case once delivered. _x000D_4/9/2024:#Update - Engineer found the socket, but it needs a socket relocation. - Engineer called back. He's found what looks to be the socket, however, it's not labelled and it's located upstairs, which is far too far away from the terminal. He's emailing in some photo's that I'll merge to this case once delivered. _x000D_3/9/2024:#Update - Engineer found the socket, but it needs a socket relocation. - Engineer called back. He's found what looks to be the socket, however, it's not labelled and it's located upstairs, which is far too far away from the terminal. He's emailing in some photo's that I'll merge to this case once delivered. _x000D_2/9/2024:#Update - Engineer found the socket, but it needs a socket relocation. - Engineer called back. He's found what looks to be the socket, however, it's not labelled and it's located upstairs, which is far too far away from the terminal. He's emailing in some photo's that I'll merge to this case once delivered. _x000D_29/8/2024:#Update - Engineer found the socket, but it needs a socket relocation. - Engineer called back. He's found what looks to be the socket, however, it's not labelled and it's located upstairs, which is far too far away from the terminal. He's emailing in some photo's that I'll merge to this case once delivered. _x000D_28/8/2024:#Update - Engineer found the socket, but it needs a socket relocation. - Engineer called back. He's found what looks to be the socket, however, it's not labelled and it's located upstairs, which is far too far away from the terminal. He's emailing in some photo's that I'll merge to this case once delivered. _x000D_27/8/2024:#Update - Engineer found the socket, but it needs a socket relocation. - Engineer called back. He's found what looks to be the socket, however, it's not labelled and it's located upstairs, which is far too far away from the terminal. He's emailing in some photo's that I'll merge to this case once delivered. _x000D_18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 9/9/2024:#Update - Engineer found the socket, but it needs a socket relocation. - Engineer called back. He's found what looks to be the socket, however, it's not labelled and it's located upstairs, which is far too far away from the terminal. He's emailing in some photo's that I'll merge to this case once delivered. _x000D_6/9/2024:#Update - Engineer found the socket, but it needs a socket relocation. - Engineer called back. He's found what looks to be the socket, however, it's not labelled and it's located upstairs, which is far too far away from the terminal. He's emailing in some photo's that I'll merge to this case once delivered. _x000D_5/9/2024:#Update - Engineer found the socket, but it needs a socket relocation. - Engineer called back. He's found what looks to be the socket, however, it's not labelled and it's located upstairs, which is far too far away from the terminal. He's emailing in some photo's that I'll merge to this case once delivered. _x000D_4/9/2024:#Update - Engineer found the socket, but it needs a socket relocation. - Engineer called back. He's found what looks to be the socket, however, it's not labelled and it's located upstairs, which is far too far away from the terminal. He's emailing in some photo's that I'll merge to this case once delivered. _x000D_3/9/2024:#Update - Engineer found the socket, but it needs a socket relocation. - Engineer called back. He's found what looks to be the socket, however, it's not labelled and it's located upstairs, which is far too far away from the terminal. He's emailing in some photo's that I'll merge to this case once delivered. _x000D_2/9/2024:#Update - Engineer found the socket, but it needs a socket relocation. - Engineer called back. He's found what looks to be the socket, however, it's not labelled and it's located upstairs, which is far too far away from the terminal. He's emailing in some photo's that I'll merge to this case once delivered. _x000D_29/8/2024:#Update - Engineer found the socket, but it needs a socket relocation. - Engineer called back. He's found what looks to be the socket, however, it's not labelled and it's located upstairs, which is far too far away from the terminal. He's emailing in some photo's that I'll merge to this case once delivered. _x000D_28/8/2024:#Update - Engineer found the socket, but it needs a socket relocation. - Engineer called back. He's found what looks to be the socket, however, it's not labelled and it's located upstairs, which is far too far away from the terminal. He's emailing in some photo's that I'll merge to this case once delivered. _x000D_27/8/2024:#Update - Engineer found the socket, but it needs a socket relocation. - Engineer called back. He's found what looks to be the socket, however, it's not labelled and it's located upstairs, which is far too far away from the terminal. He's emailing in some photo's that I'll merge to this case once delivered. _x000D_18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 0 | #Update - Engineer found the socket, but it needs a socket relocation. - Engineer called back. He's found what looks to be the socket, however, it's not labelled and it's located upstairs, which is far too far away from the terminal. He's emailing in some photo's that I'll merge to this case once delivered. | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2353450 | 30015948 | 2.Commissioning | AM |  | 2024-06-14 | 2024-06-14 | 2024-06-14 | TRUE |  |  |  | 2024-08-19 | [7 empty] | 0 | 671971
524 | 457932 | 2964 | Batch 4 Jun24 | Type 1 | SOGEA | Spar Stores | Tamworth | B77 2ED | 2024-05-10 | 18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996909 | 30016041 | 6.Failed router install | AM |  | 2024-06-14 | 2024-06-14 | 2024-06-14 | TRUE |  |  |  | 2024-07-04 |  |  |  | 2024-07-04 | 23A004945913 |  | 2024-07-05 | 1
525 | 638326 | 172 | Batch 2 Apr24 | Type 1 | SOGEA | Royal Food | London | NW9 6LP | 2024-05-30 | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:Update: Order Completed by Supplier _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:Update: Order Completed by Supplier _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-05-08 | 08/05/2024: CSL to provide an update 25/04/2024: Allwyn to make retailer aware of visit as per the date in column T 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 2.Allwyn to arrange access | VFS939447 | 30013046 | 6.Failed router install | AM |  | 2024-05-07 | 2024-05-07 | 2024-06-25 | TRUE |  |  |  | 2024-04-30 |  | Hassan Shariff | Hassan Shariff | 2024-08-28 | 242005011148 | 242005011148 | 2024-08-29 | 1
526 | 648090 | 558 | Batch 3 May24 | Type 1 | SOGEA | Kandola at Rockingham Way | Stevenage | SG1 1SJ | 2024-06-07 | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:#Update - Allwyn confirmed with retailer for new appointment date. 08/07 _x000D_11/7/2024:#Update - Allwyn confirmed with retailer for new appointment date. 08/07 _x000D_10/7/2024:#Update - Allwyn confirmed with retailer for new appointment date. 08/07 _x000D_9/7/2024:#Update - Allwyn confirmed with retailer for new appointment date. 08/07 _x000D_4/7/2024:#Update - Allwyn confirmed with retailer for new appointment date. 08/07 _x000D_3/7/2024:#Update - Allwyn confirmed with retailer for new appointment date. 08/07 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Allwyn confirmed with retailer for new appointment date. 08/07 _x000D_27/6/2024:#Update - Allwyn confirmed with retailer for new appointment date. 08/07 _x000D_25/6/2024:#Update - Allwyn confirmed with retailer for new appointment date. 08/07 _x000D_24/6/2024:#Update - Allwyn confirmed with retailer for new appointment date. 08/07 _x000D_20/6/2024:#Update - Allwyn confirmed with retailer for new appointment date. 08/07 _x000D_19/6/2024:#Update - Allwyn confirmed with retailer for new appointment date. 08/07 _x000D_18/6/2024:#Update - Allwyn have confirmed appointment for 17/06 AM with the retailer _x000D_17/6/2024:#Update - Allwyn have confirmed appointment for 17/06 AM with the retailer _x000D_14/6/2024:#Update - Allwyn have confirmed appointment for 17/06 AM with the retailer _x000D_13/6/2024:#Update - Allwyn have confirmed appointment for 17/06 AM with the retailer _x000D_12/6/2024:#Update - Allwyn have confirmed appointment for 17/06 AM with the retailer _x000D_11/6/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 17/06/2024. We will continue to provide update as they become available. _x000D_10/6/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 17/06/2024. We will continue to provide update as they become available. _x000D_7/6/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 17/06/2024. We will continue to provide update as they become available. _x000D_6/6/2024:Supplier Delay: Issues relating to permission to provide the network, please await for further details. _x000D_5/6/2024:Supplier Delay: Issues relating to permission to provide the network, please await for further details. _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:#Update - Allwyn confirmed with retailer for new appointment date. 08/07 _x000D_11/7/2024:#Update - Allwyn confirmed with retailer for new appointment date. 08/07 _x000D_10/7/2024:#Update - Allwyn confirmed with retailer for new appointment date. 08/07 _x000D_9/7/2024:#Update - Allwyn confirmed with retailer for new appointment date. 08/07 _x000D_4/7/2024:#Update - Allwyn confirmed with retailer for new appointment date. 08/07 _x000D_3/7/2024:#Update - Allwyn confirmed with retailer for new appointment date. 08/07 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Allwyn confirmed with retailer for new appointment date. 08/07 _x000D_27/6/2024:#Update - Allwyn confirmed with retailer for new appointment date. 08/07 _x000D_25/6/2024:#Update - Allwyn confirmed with retailer for new appointment date. 08/07 _x000D_24/6/2024:#Update - Allwyn confirmed with retailer for new appointment date. 08/07 _x000D_20/6/2024:#Update - Allwyn confirmed with retailer for new appointment date. 08/07 _x000D_19/6/2024:#Update - Allwyn confirmed with retailer for new appointment date. 08/07 _x000D_18/6/2024:#Update - Allwyn have confirmed appointment for 17/06 AM with the retailer _x000D_17/6/2024:#Update - Allwyn have confirmed appointment for 17/06 AM with the retailer _x000D_14/6/2024:#Update - Allwyn have confirmed appointment for 17/06 AM with the retailer _x000D_13/6/2024:#Update - Allwyn have confirmed appointment for 17/06 AM with the retailer _x000D_12/6/2024:#Update - Allwyn have confirmed appointment for 17/06 AM with the retailer _x000D_11/6/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 17/06/2024. We will continue to provide update as they become available. _x000D_10/6/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 17/06/2024. We will continue to provide update as they become available. _x000D_7/6/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 17/06/2024. We will continue to provide update as they become available. _x000D_6/6/2024:Supplier Delay: Issues relating to permission to provide the network, please await for further details. _x000D_5/6/2024:Supplier Delay: Issues relating to permission to provide the network, please await for further details. _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-06 | 06/06/2024: CSL to provide an update |  |  | 3.Allwyn to arrange rtr install | VFP2300755 | 30013448 | 6.Failed router install | AM |  | 2024-05-07 | 2024-06-17 | 2024-06-17 | TRUE |  |  |  | 2024-08-07 |  |  |  | 2024-08-07 | 237004907536 |  | 2024-08-08 | 1
527 | 609272 | 590 | Batch 3 May24 | Type 1 | SOGEA | Dennis Beckton Ltd | Beckton | E6 5NG | 2024-06-07 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | 0 | 2024-05-23 | 23/05/24: Allwyn to arrange access on the new date |  |  | 3.Allwyn to arrange rtr install | VFP2300787 | 30013480 | 2.Commissioning | AM | [8 empty] | 2024-08-01 | [7 empty] | 0
528 | 447846 | 980 | Batch 3 May24 | Type 1 | SOGEA | Raja Bros | MANCHESTER | M18 7NF | 2024-06-07 | 31/5/2024:#Update - Hoist will be arranged for 17th June, AM. Action for Allwyn, Please confirm 17/06 AM appointment date with retailer. _x000D_30/5/2024:#Update - Hoist will be arranged for 17th June, AM. Action for Allwyn, Please confirm 17/06 AM appointment date with retailer. _x000D_29/5/2024:#Update - Hoist will be arranged for 17th June, AM. Action for Allwyn, Please confirm 17/06 AM appointment date with retailer. _x000D_28/5/2024:Supplier Delay: Delayed due to health and safety issues _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | 31/5/2024:#Update - Hoist will be arranged for 17th June, AM. Action for Allwyn, Please confirm 17/06 AM appointment date with retailer. _x000D_30/5/2024:#Update - Hoist will be arranged for 17th June, AM. Action for Allwyn, Please confirm 17/06 AM appointment date with retailer. _x000D_29/5/2024:#Update - Hoist will be arranged for 17th June, AM. Action for Allwyn, Please confirm 17/06 AM appointment date with retailer. _x000D_28/5/2024:Supplier Delay: Delayed due to health and safety issues _x000D_10/5/2024:0 _x000D_08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301177 | 30013870 | 6.Failed router install | AM |  | 2024-05-21 | 2024-06-17 | 2024-06-17 | TRUE |  |  |  | 2024-07-12 |  |  |  | 2024-07-12 | 242005013518 |  | 2024-07-15 | 1
529 | 664247 | 1542 | Batch 4 Jun24 | Type 1 | FTTP | Gortmerron Spar | DUNGANNON | BT71 6LS | 2024-06-07 | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2338537 | 30015456 | 2.Commissioning | AM |  | 2024-06-17 | 2024-06-17 | 2024-06-17 | TRUE |  |  |  | 2024-07-09 | [7 empty] | 0 | 664247
530 | 644724 | 1544 | Batch 4 Jun24 | Type 1 | FTTP | Spar Stores | ACCRINGTON | BB5 6DW | 2024-06-07 | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:EU Missed Appointment. Supplier engineer has been unable to gain access. _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:EU Missed Appointment. Supplier engineer has been unable to gain access. _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2338538 | 30015558 | 2.Commissioning | AM |  | 2024-06-17 | 2024-06-17 | 2024-06-17 | TRUE |  |  |  | 2024-07-15 | [7 empty] | 0
531 | 446182 | 1545 | Batch 4 Jun24 | Type 1 | FTTP | Spar Stores | Annan | DG12 5BD | 2024-07-11 | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2338539 | 30015596 | 6.Failed router install | AM |  | 2024-06-17 | 2024-07-10 | 2024-06-19 | TRUE |  |  |  | 2024-07-22 |  |  |  | 2024-07-22 | 239004929542 |  | 2024-07-23 | 1
532 | 446169 | 1546 | Batch 4 Jun24 | Type 1 | SOGEA | Eurospar | Londonderry | BT48 0RX | 2024-06-07 | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:Update: Order Completed by Supplier _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:Update: Order Completed by Supplier _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984767 | 30015664 | 2.Commissioning | AM |  | 2024-06-17 | 2024-06-17 | 2024-06-17 | TRUE |  |  |  | 2024-07-08 | [7 empty] | 0
533 | 449761 | 1550 | Batch 4 Jun24 | Type 1 | SOGEA | Spar Stores | SALFORD | M6 6BA | 2024-06-07 | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984770 | 30015334 | 2.Commissioning | AM |  | 2024-06-17 | 2024-06-17 | 2024-06-17 | TRUE |  |  |  | 2024-07-12 | [7 empty] | 0
534 | 449333 | 1551 | Batch 4 Jun24 | Type 1 | FTTP | Spar Stores | BARNSTAPLE | EX32 9BG | 2024-06-07 | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984771 | 30015543 | 2.Commissioning | AM |  | 2024-06-17 | 2024-06-17 | 2024-06-17 | TRUE |  |  |  | 2024-07-25 | [7 empty] | 0
535 | 625030 | 1555 | Batch 4 Jun24 | Type 1 | FTTP | Spar Stores | Conwy | LL32 8DE | 2024-06-07 | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984773 | 30015379 | 2.Commissioning | AM |  | 2024-06-17 | 2024-06-17 | 2024-06-17 | TRUE |  |  |  | 2024-07-19 | [7 empty] | 0
536 | 468179 | 1559 | Batch 4 Jun24 | Type 1 | SOGEA | Spar | Bonnybridge | FK4 2DE | 2024-06-07 | 12/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/07 AM _x000D_11/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/07 AM _x000D_10/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/07 AM _x000D_9/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/07 AM _x000D_4/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/07 AM _x000D_3/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/07 AM _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Action for Allwyn - Installation has now been amended to 04/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 04/07 is a suitable date. _x000D_27/6/2024:#Update - Action for Allwyn - Installation has now been amended to 04/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 04/07 is a suitable date. _x000D_25/6/2024:#Update - Action for Allwyn - Installation has now been amended to 04/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 04/07 is a suitable date. _x000D_24/6/2024:#Update - Action for Allwyn - Installation has now been amended to 04/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 04/07 is a suitable date. _x000D_20/6/2024:#Update - Action for Allwyn - Installation has now been amended to 04/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 04/07 is a suitable date. _x000D_19/6/2024:#Update - Action for Allwyn - Installation has now been amended to 04/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 04/07 is a suitable date. _x000D_18/6/2024:Supplier Delay: Unable to complete work in the allocated appointment slot, please await further details. _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 12/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/07 AM _x000D_11/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/07 AM _x000D_10/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/07 AM _x000D_9/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/07 AM _x000D_4/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/07 AM _x000D_3/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/07 AM _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Action for Allwyn - Installation has now been amended to 04/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 04/07 is a suitable date. _x000D_27/6/2024:#Update - Action for Allwyn - Installation has now been amended to 04/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 04/07 is a suitable date. _x000D_25/6/2024:#Update - Action for Allwyn - Installation has now been amended to 04/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 04/07 is a suitable date. _x000D_24/6/2024:#Update - Action for Allwyn - Installation has now been amended to 04/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 04/07 is a suitable date. _x000D_20/6/2024:#Update - Action for Allwyn - Installation has now been amended to 04/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 04/07 is a suitable date. _x000D_19/6/2024:#Update - Action for Allwyn - Installation has now been amended to 04/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 04/07 is a suitable date. _x000D_18/6/2024:Supplier Delay: Unable to complete work in the allocated appointment slot, please await further details. _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984615 | 30015789 | 2.Commissioning | AM |  | 2024-06-17 | 2024-06-17 | 2024-06-17 | TRUE |  |  |  | 2024-07-08 | [7 empty] | 0
537 | 482639 | 1565 | Batch 4 Jun24 | Type 1 | SOGEA | Hillhead Stores | Glasgow | G66 2JD | 2024-06-07 | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984784 | 30015342 | 6.Failed router install | AM |  | 2024-06-17 | 2024-06-17 | 2024-06-17 | TRUE |  |  |  | 2024-07-04 |  |  |  | 2024-08-16 | 239004929618 | 239004929618 | 2024-08-19 | 1
538 | 644755 | 1568 | Batch 4 Jun24 | Type 1 | FTTP | Spar Stores | Milnthorpe | LA7 7QL | 2024-06-07 | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_10/6/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_7/6/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_6/6/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_5/6/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_4/6/2024:#Update- Network records need to be updated. Review 03/06. OR to provide updates as they become available. Will review 03/06 _x000D_ | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_10/6/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_7/6/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_6/6/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_5/6/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_4/6/2024:#Update- Network records need to be updated. Review 03/06. OR to provide updates as they become available. Will review 03/06 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2338596 | 30015296 | 6.Failed router install | AM |  | 2024-06-17 | 2024-06-17 | 2024-06-17 | TRUE |  |  |  | 2024-07-16 |  |  |  | 2024-07-16 | 242005013513 |  | 2024-07-17 | 1
539 | 654408 | 1573 | Batch 4 Jun24 | Type 1 | SOGEA | SPAR | NEWCASTLE UPON TYNE | NE4 9RX | 2024-06-07 | 19/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:Supplier Delay: Unable to complete work please await for further details _x000D_24/6/2024:Supplier Delay: Unable to complete work please await for further details _x000D_20/6/2024:Supplier Delay: Unable to complete work please await for further details _x000D_19/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_18/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_17/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:Supplier Delay: Unable to complete work please await for further details _x000D_24/6/2024:Supplier Delay: Unable to complete work please await for further details _x000D_20/6/2024:Supplier Delay: Unable to complete work please await for further details _x000D_19/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_18/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_17/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984787 | 30015332 | 2.Commissioning | AM |  | 2024-06-17 | 2024-06-17 | 2024-06-17 | TRUE |  |  |  | 2024-07-17 | [7 empty] | 0
540 | 485589 | 1574 | Batch 4 Jun24 | Type 1 | SoGEA/Mobile | Spar Stores | Belfast | BT7 1JQ | 2024-07-03 | 6/9/2024:#Update - Cancelled down - Cancellation reason - ADSL is the only available product. Cannot raise. _x000D_5/9/2024:#Update - Cancelled down - Cancellation reason - ADSL is the only available product. Cannot raise. _x000D_4/9/2024:0 _x000D_3/9/2024:Engineer is unable to provide a data service to the End Customer _x000D_2/9/2024:Engineer is unable to provide a data service to the End Customer _x000D_29/8/2024:Engineer is unable to provide a data service to the End Customer _x000D_28/8/2024:Engineer is unable to provide a data service to the End Customer _x000D_27/8/2024:Engineer is unable to provide a data service to the End Customer _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - order has been delayed as a site survey is required. This has been sent to the survey engineers and we will continue to provide updates as they become available. _x000D_18/7/2024:#Update - No line of sight to premises, multiple blockages detected , spoke with local planner who advised me to send back to him (survey) patch lead aware. _x000D_17/7/2024:#Update - No line of sight to premises, multiple blockages detected , spoke with local planner who advised me to send back to him (survey) patch lead aware. _x000D_16/7/2024:#Update - No line of sight to premises, multiple blockages detected , spoke with local planner who advised me to send back to him (survey) patch lead aware. _x000D_15/7/2024:#Update - No line of sight to premises, multiple blockages detected , spoke with local planner who advised me to send back to him (survey) patch lead aware. _x000D_12/7/2024:#Update - No line of sight to premises, multiple blockages detected , spoke with local planner who advised me to send back to him (survey) patch lead aware. _x000D_11/7/2024:#Update - No line of sight to premises, multiple blockages detected , spoke with local planner who advised me to send back to him (survey) patch lead aware. _x000D_10/7/2024:#Update - No line of sight to premises, multiple blockages detected , spoke with local planner who advised me to send back to him (survey) patch lead aware. _x000D_9/7/2024:#Update - No line of sight to premises, multiple blockages detected , spoke with local planner who advised me to send back to him (survey) patch lead aware. _x000D_4/7/2024:#Update - No line of sight to premises, multiple blockages detected , spoke with local planner who advised me to send back to him (survey) patch lead aware. _x000D_3/7/2024:#Update - No line of sight to premises, multiple blockages detected , spoke with local planner who advised me to send back to him (survey) patch lead aware. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - No line of sight to premises, multiple blockages detected , spoke with local planner who advised me to send back to him (survey) patch lead aware. _x000D_27/6/2024:#Update - No line of sight to premises, multiple blockages detected , spoke with local planner who advised me to send back to him (survey) patch lead aware. _x000D_25/6/2024:#Update - No line of sight to premises, multiple blockages detected , spoke with local planner who advised me to send back to him (survey) patch lead aware. _x000D_24/6/2024:#Update - No line of sight to premises, multiple blockages detected , spoke with local planner who advised me to send back to him (survey) patch lead aware. _x000D_20/6/2024:#Update - No line of sight to premises, multiple blockages detected , spoke with local planner who advised me to send back to him (survey) patch lead aware. _x000D_19/6/2024:#Update - No line of sight to premises, multiple blockages detected , spoke with local planner who advised me to send back to him (survey) patch lead aware. _x000D_18/6/2024:#Update - No line of sight to premises, multiple blockages detected , spoke with local planner who advised me to send back to him (survey) patch lead aware. _x000D_17/6/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - Cancelled down - Cancellation reason - ADSL is the only available product. Cannot raise. _x000D_6/9/2024:#Update - Cancelled down - Cancellation reason - ADSL is the only available product. Cannot raise. _x000D_5/9/2024:#Update - Cancelled down - Cancellation reason - ADSL is the only available product. Cannot raise. _x000D_4/9/2024:0 _x000D_3/9/2024:Engineer is unable to provide a data service to the End Customer _x000D_2/9/2024:Engineer is unable to provide a data service to the End Customer _x000D_29/8/2024:Engineer is unable to provide a data service to the End Customer _x000D_28/8/2024:Engineer is unable to provide a data service to the End Customer _x000D_27/8/2024:Engineer is unable to provide a data service to the End Customer _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - order has been delayed as a site survey is required. This has been sent to the survey engineers and we will continue to provide updates as they become available. _x000D_18/7/2024:#Update - No line of sight to premises, multiple blockages detected , spoke with local planner who advised me to send back to him (survey) patch lead aware. _x000D_17/7/2024:#Update - No line of sight to premises, multiple blockages detected , spoke with local planner who advised me to send back to him (survey) patch lead aware. _x000D_16/7/2024:#Update - No line of sight to premises, multiple blockages detected , spoke with local planner who advised me to send back to him (survey) patch lead aware. _x000D_15/7/2024:#Update - No line of sight to premises, multiple blockages detected , spoke with local planner who advised me to send back to him (survey) patch lead aware. _x000D_12/7/2024:#Update - No line of sight to premises, multiple blockages detected , spoke with local planner who advised me to send back to him (survey) patch lead aware. _x000D_11/7/2024:#Update - No line of sight to premises, multiple blockages detected , spoke with local planner who advised me to send back to him (survey) patch lead aware. _x000D_10/7/2024:#Update - No line of sight to premises, multiple blockages detected , spoke with local planner who advised me to send back to him (survey) patch lead aware. _x000D_9/7/2024:#Update - No line of sight to premises, multiple blockages detected , spoke with local planner who advised me to send back to him (survey) patch lead aware. _x000D_4/7/2024:#Update - No line of sight to premises, multiple blockages detected , spoke with local planner who advised me to send back to him (survey) patch lead aware. _x000D_3/7/2024:#Update - No line of sight to premises, multiple blockages detected , spoke with local planner who advised me to send back to him (survey) patch lead aware. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - No line of sight to premises, multiple blockages detected , spoke with local planner who advised me to send back to him (survey) patch lead aware. _x000D_27/6/2024:#Update - No line of sight to premises, multiple blockages detected , spoke with local planner who advised me to send back to him (survey) patch lead aware. _x000D_25/6/2024:#Update - No line of sight to premises, multiple blockages detected , spoke with local planner who advised me to send back to him (survey) patch lead aware. _x000D_24/6/2024:#Update - No line of sight to premises, multiple blockages detected , spoke with local planner who advised me to send back to him (survey) patch lead aware. _x000D_20/6/2024:#Update - No line of sight to premises, multiple blockages detected , spoke with local planner who advised me to send back to him (survey) patch lead aware. _x000D_19/6/2024:#Update - No line of sight to premises, multiple blockages detected , spoke with local planner who advised me to send back to him (survey) patch lead aware. _x000D_18/6/2024:#Update - No line of sight to premises, multiple blockages detected , spoke with local planner who advised me to send back to him (survey) patch lead aware. _x000D_17/6/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update - Cancelled down - Cancellation reason - ADSL is the only available product. Cannot raise. | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFS984788 | 30015615 | 1.Provisioning | AM |  | 2024-07-02 | 2024-08-27 |  | 0 | [11 empty] | 0
541 | 607070 | 1575 | Batch 4 Jun24 | Type 1 | FTTP/Mobile | Spar Stores | Newry | BT35 8EB | 2024-06-07 | 6/9/2024:#Update - awaiting ECC approval from customer, proposal sent to VF 08/08 _x000D_5/9/2024:#Update - awaiting ECC approval from customer, proposal sent to VF 08/08 _x000D_4/9/2024:#Update - awaiting ECC approval from customer, proposal sent to VF 08/08 _x000D_3/9/2024:#Update - awaiting ECC approval from customer, proposal sent to VF 08/08 _x000D_2/9/2024:#Update - awaiting ECC approval from customer, proposal sent to VF 08/08 _x000D_29/8/2024:#Update - awaiting ECC approval from customer, proposal sent to VF 08/08 _x000D_28/8/2024:#Update - awaiting ECC approval from customer, proposal sent to VF 08/08 _x000D_27/8/2024:#Update - awaiting ECC approval from customer, proposal sent to VF 08/08 _x000D_22/8/2024:#Update - awaiting ECC approval from customer, proposal sent to VF 08/08 _x000D_21/8/2024:#Update - awaiting ECC approval from customer, proposal sent to VF 08/08 _x000D_20/8/2024:#Update - Your order has been delayed. Landlord permission required. We will provide further updates accordingly _x000D_19/8/2024:#Update - Your order has been delayed. Landlord permission required. We will provide further updates accordingly _x000D_19/8/2024:01440135 _x000D_16/8/2024:#Update - Your order has been delayed. Landlord permission required. We will provide further updates accordingly _x000D_15/8/2024:#Update - Your order has been delayed. Landlord permission required. We will provide further updates accordingly _x000D_14/8/2024:#Update - Your order has been delayed. Landlord permission required. We will provide further updates accordingly _x000D_13/8/2024:#Update - Your order has been delayed. Landlord permission required. We will provide further updates accordingly _x000D_12/8/2024:#Update - Your order has been delayed. Landlord permission required. We will provide further updates accordingly _x000D_9/8/2024:#Update - Your order has been delayed. Landlord permission required. We will provide further updates accordingly _x000D_8/8/2024:25/07/2024 _x000D_6/8/2024:25/07/2024 _x000D_5/8/2024:25/07/2024 _x000D_2/8/2024:25/07/2024 _x000D_1/8/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_30/7/2024:#Update - Your order has been delayed. Landlord permission required. We will provide further updates accordingly _x000D_29/7/2024:#Update - Your order has been delayed. Landlord permission required. We will provide further updates accordingly _x000D_29/7/2024:01440135 _x000D_26/7/2024:01440135 _x000D_24/7/2024:#Update - order has been delayed as a site survey is required. This has been sent to the survey engineers and we will continue to provide updates as they become available. _x000D_23/7/2024:#Update - order has been delayed as a site survey is required. This has been sent to the survey engineers and we will continue to provide updates as they become available. _x000D_22/7/2024:#Update - order has been delayed as a site survey is required. This has been sent to the survey engineers and we will continue to provide updates as they become available. _x000D_22/7/2024:#Update - order has been delayed as a site survey is required. This has been sent to the survey engineers and we will continue to provide updates as they become available. _x000D_20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 9/9/2024:#Update - awaiting ECC approval from customer, proposal sent to VF 08/08 _x000D_6/9/2024:#Update - awaiting ECC approval from customer, proposal sent to VF 08/08 _x000D_5/9/2024:#Update - awaiting ECC approval from customer, proposal sent to VF 08/08 _x000D_4/9/2024:#Update - awaiting ECC approval from customer, proposal sent to VF 08/08 _x000D_3/9/2024:#Update - awaiting ECC approval from customer, proposal sent to VF 08/08 _x000D_2/9/2024:#Update - awaiting ECC approval from customer, proposal sent to VF 08/08 _x000D_29/8/2024:#Update - awaiting ECC approval from customer, proposal sent to VF 08/08 _x000D_28/8/2024:#Update - awaiting ECC approval from customer, proposal sent to VF 08/08 _x000D_27/8/2024:#Update - awaiting ECC approval from customer, proposal sent to VF 08/08 _x000D_22/8/2024:#Update - awaiting ECC approval from customer, proposal sent to VF 08/08 _x000D_21/8/2024:#Update - awaiting ECC approval from customer, proposal sent to VF 08/08 _x000D_20/8/2024:#Update - Your order has been delayed. Landlord permission required. We will provide further updates accordingly _x000D_19/8/2024:#Update - Your order has been delayed. Landlord permission required. We will provide further updates accordingly _x000D_19/8/2024:01440135 _x000D_16/8/2024:#Update - Your order has been delayed. Landlord permission required. We will provide further updates accordingly _x000D_15/8/2024:#Update - Your order has been delayed. Landlord permission required. We will provide further updates accordingly _x000D_14/8/2024:#Update - Your order has been delayed. Landlord permission required. We will provide further updates accordingly _x000D_13/8/2024:#Update - Your order has been delayed. Landlord permission required. We will provide further updates accordingly _x000D_12/8/2024:#Update - Your order has been delayed. Landlord permission required. We will provide further updates accordingly _x000D_9/8/2024:#Update - Your order has been delayed. Landlord permission required. We will provide further updates accordingly _x000D_8/8/2024:25/07/2024 _x000D_6/8/2024:25/07/2024 _x000D_5/8/2024:25/07/2024 _x000D_2/8/2024:25/07/2024 _x000D_1/8/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_30/7/2024:#Update - Your order has been delayed. Landlord permission required. We will provide further updates accordingly _x000D_29/7/2024:#Update - Your order has been delayed. Landlord permission required. We will provide further updates accordingly _x000D_29/7/2024:01440135 _x000D_26/7/2024:01440135 _x000D_24/7/2024:#Update - order has been delayed as a site survey is required. This has been sent to the survey engineers and we will continue to provide updates as they become available. _x000D_23/7/2024:#Update - order has been delayed as a site survey is required. This has been sent to the survey engineers and we will continue to provide updates as they become available. _x000D_22/7/2024:#Update - order has been delayed as a site survey is required. This has been sent to the survey engineers and we will continue to provide updates as they become available. _x000D_22/7/2024:#Update - order has been delayed as a site survey is required. This has been sent to the survey engineers and we will continue to provide updates as they become available. _x000D_20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. | #Update - awaiting ECC approval from customer, proposal sent to VF 08/08 | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFP2338547 | 30015489 | 1.Provisioning | AM |  | 2024-06-17 | 2024-06-17 |  | 0 | [11 empty] | 0
542 | 660580 | 1577 | Batch 4 Jun24 | Type 1 | FTTP/Mobile | Spar | Tyrone | BT71 4HU | 2024-06-07 | 2/8/2024:18/07/2024 _x000D_1/8/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_30/7/2024:#Update Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_29/7/2024:#Update Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_29/7/2024:01501606 _x000D_26/7/2024:01501606 _x000D_24/7/2024:#Update Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_23/7/2024:#Update Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_22/7/2024:#Update Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_22/7/2024:#Update Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 2/8/2024:18/07/2024 _x000D_1/8/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_30/7/2024:#Update Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_29/7/2024:#Update Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_29/7/2024:01501606 _x000D_26/7/2024:01501606 _x000D_24/7/2024:#Update Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_23/7/2024:#Update Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_22/7/2024:#Update Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_22/7/2024:#Update Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2338548 | 30015440 | 2.Commissioning | AM |  | 2024-06-17 | 2024-07-31 | 2024-07-31 | TRUE |  |  |  | 2024-08-21 | [7 empty] | 0
543 | 671626 | 1580 | Batch 4 Jun24 | Type 1 | SOGEA | Spar Ely | Ely | CB7 4LQ | 2024-06-07 | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984792 | 30015317 | 2.Commissioning | AM |  | 2024-06-17 | 2024-06-17 | 2024-06-17 | TRUE |  |  |  | 2024-07-03 | [7 empty] | 0 | 671626
544 | 616612 | 1585 | Batch 4 Jun24 | Type 1 | SOGEA | Eglinton Service Station | Londonderry | BT47 3PG | 2024-06-07 | 19/7/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_18/7/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_17/7/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_16/7/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_15/7/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_12/7/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_11/7/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_10/7/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_9/7/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_4/7/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_3/7/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_27/6/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_25/6/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_24/6/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_20/6/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_19/6/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_18/6/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_18/7/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_17/7/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_16/7/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_15/7/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_12/7/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_11/7/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_10/7/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_9/7/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_4/7/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_3/7/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_27/6/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_25/6/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_24/6/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_20/6/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_19/6/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_18/6/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984794 | 30015370 | 2.Commissioning | AM |  | 2024-06-17 | 2024-06-17 | 2024-06-17 | TRUE |  |  |  | 2024-07-08 | [7 empty] | 0
545 | 617731 | 1586 | Batch 4 Jun24 | Type 1 | SoGEA/Mobile | Spar Boutport Steeet | Barnstaple | EX31 1RP | 2024-09-03 | 6/9/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_5/9/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_4/9/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_3/9/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_2/9/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_29/8/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_28/8/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_27/8/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_22/8/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_21/8/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_20/8/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_19/8/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_19/8/2024:01440418 _x000D_16/8/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_15/8/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_14/8/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_13/8/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_12/8/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_9/8/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_8/8/2024:17/06/2024 _x000D_6/8/2024:17/06/2024 _x000D_5/8/2024:17/06/2024 _x000D_2/8/2024:17/06/2024 _x000D_1/8/2024:17/06/2024 _x000D_31/7/2024:17/06/2024 _x000D_31/7/2024:17/06/2024 _x000D_30/7/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_29/7/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_29/7/2024:01440418 _x000D_26/7/2024:01440418 _x000D_24/7/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_23/7/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_22/7/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_22/7/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_6/9/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_5/9/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_4/9/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_3/9/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_2/9/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_29/8/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_28/8/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_27/8/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_22/8/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_21/8/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_20/8/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_19/8/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_19/8/2024:01440418 _x000D_16/8/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_15/8/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_14/8/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_13/8/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_12/8/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_9/8/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_8/8/2024:17/06/2024 _x000D_6/8/2024:17/06/2024 _x000D_5/8/2024:17/06/2024 _x000D_2/8/2024:17/06/2024 _x000D_1/8/2024:17/06/2024 _x000D_31/7/2024:17/06/2024 _x000D_31/7/2024:17/06/2024 _x000D_30/7/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_29/7/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_29/7/2024:01440418 _x000D_26/7/2024:01440418 _x000D_24/7/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_23/7/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_22/7/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_22/7/2024:#Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. _x000D_20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:Order Completed _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Order Completed | #Update - internal fit complete and line proven but Scaffolding up in the shops means that external works is still required. | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFS984796 | 30015629 | 2.Commissioning | AM |  | 2024-06-17 | 2024-09-02 |  | 0 | [11 empty] | 0
546 | 631176 | 1587 | Batch 4 Jun24 | Type 1 | SOGEA | Spar Stores | Chester | CH1 5HW | 2024-06-07 | 19/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:Update: Order Amended _x000D_20/6/2024:Update: Order Amended _x000D_19/6/2024:Update: Order Amended _x000D_18/6/2024:Update: Order Amended _x000D_17/6/2024:Supplier Delay: Unable to complete work at appointment due to Network Planning. Wait for new appointment. _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:Update: Order Amended _x000D_20/6/2024:Update: Order Amended _x000D_19/6/2024:Update: Order Amended _x000D_18/6/2024:Update: Order Amended _x000D_17/6/2024:Supplier Delay: Unable to complete work at appointment due to Network Planning. Wait for new appointment. _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984795 | 30015659 | 2.Commissioning | AM |  | 2024-06-17 | 2024-06-17 | 2024-06-17 | TRUE |  |  |  | 2024-07-12 | [7 empty] | 0
547 | 620450 | 1588 | Batch 4 Jun24 | Type 1 | FTTP/Mobile | McCullaghs Spar Classic Service Station | Omagh | BT78 1QZ | 2024-06-07 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 15:13 _x000D_26/7/2024:22/07/2024 15:13 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:Update: Order Completed by Supplier _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 15:13 _x000D_26/7/2024:22/07/2024 15:13 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:Update: Order Completed by Supplier _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFP2395498 | 30015425 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
548 | 629112 | 1592 | Batch 4 Jun24 | Type 1 | SoGEA/Mobile | Spar Newton Abbot | Newton Abbot | TQ12 2AQ | 2024-06-07 | 6/9/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_5/9/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_4/9/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_3/9/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_2/9/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_29/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_28/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_27/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_22/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_21/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_20/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_19/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_19/8/2024:01440519 _x000D_16/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_15/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_14/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_13/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_12/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_9/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_8/8/2024:05/07/2024 _x000D_6/8/2024:05/07/2024 _x000D_5/8/2024:05/07/2024 _x000D_2/8/2024:05/07/2024 _x000D_1/8/2024:05/07/2024 _x000D_31/7/2024:05/07/2024 _x000D_31/7/2024:05/07/2024 _x000D_30/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_29/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_29/7/2024:01440519 _x000D_26/7/2024:01440519 _x000D_24/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_23/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_22/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_22/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_6/9/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_5/9/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_4/9/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_3/9/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_2/9/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_29/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_28/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_27/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_22/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_21/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_20/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_19/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_19/8/2024:01440519 _x000D_16/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_15/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_14/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_13/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_12/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_9/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_8/8/2024:05/07/2024 _x000D_6/8/2024:05/07/2024 _x000D_5/8/2024:05/07/2024 _x000D_2/8/2024:05/07/2024 _x000D_1/8/2024:05/07/2024 _x000D_31/7/2024:05/07/2024 _x000D_31/7/2024:05/07/2024 _x000D_30/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_29/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_29/7/2024:01440519 _x000D_26/7/2024:01440519 _x000D_24/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_23/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_22/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_22/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update - ECC proposal sent to Vodafone on 05/07 | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFS984799 | 30015584 | 1.Provisioning | AM |  | 2024-06-17 | 2024-08-22 |  | 0 | [11 empty] | 0
549 | 633655 | 1593 | Batch 4 Jun24 | Type 1 | SOGEA | Spar Lennons | Castlewellan | BT31 9DP | 2024-06-07 | 19/7/2024:Update: Order Amended _x000D_18/7/2024:Update: Order Amended _x000D_17/7/2024:Update: Order Amended _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:Update: Order Amended _x000D_24/6/2024:Update: Order Amended _x000D_20/6/2024:Update: Order Amended _x000D_19/6/2024:Update: Order Amended _x000D_18/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_17/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:Update: Order Amended _x000D_18/7/2024:Update: Order Amended _x000D_17/7/2024:Update: Order Amended _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:Update: Order Amended _x000D_24/6/2024:Update: Order Amended _x000D_20/6/2024:Update: Order Amended _x000D_19/6/2024:Update: Order Amended _x000D_18/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_17/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2338555 | 30015616 | 2.Commissioning | AM |  | 2024-06-17 | 2024-06-17 | 2024-06-17 | TRUE |  |  |  | 2024-07-09 | [7 empty] | 0
550 | 634788 | 1595 | Batch 4 Jun24 | Type 1 | FTTP | Spar Stores | Omagh | BT78 5BB | 2024-06-07 | 19/7/2024:0 _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_20/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_19/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_18/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 19/7/2024:0 _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_20/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_19/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_18/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2338556 | 30015653 | 2.Commissioning | AM |  | 2024-06-17 | 2024-06-17 | 2024-06-17 | TRUE |  |  |  | 2024-07-09 | [7 empty] | 0
551 | 655081 | 1596 | Batch 4 Jun24 | Type 1 | FTTP/Mobile | Spar | Spalding | PE11 1HQ | 2024-06-07 | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 09:52 _x000D_26/7/2024:22/07/2024 09:52 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 09:52 _x000D_26/7/2024:22/07/2024 09:52 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 0 | 0 | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFP2404071 | 30015568 | 1.Provisioning | AM |  | 2024-06-17 | 2024-09-06 |  | 0 | [11 empty] | 0
552 | 647242 | 1598 | Batch 4 Jun24 | Type 3 | SoGEA/Mobile | Upper Holway Stores | Taunton | TA1 2QA | 2024-06-07 | 6/9/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_5/9/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_4/9/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_3/9/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_2/9/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_29/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_28/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_27/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_22/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_21/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_20/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_19/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_19/8/2024:01440612 _x000D_16/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_15/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_14/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_13/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_12/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_9/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_8/8/2024:05/08/2024 _x000D_6/8/2024:05/08/2024 _x000D_5/8/2024:05/08/2024 _x000D_2/8/2024:29/07/2024 _x000D_1/8/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_30/7/2024:#Update- Site Type Change : Mobile Only Option _x000D_29/7/2024:#Update - Awaiting approval for ECCS _x000D_29/7/2024:01440612 _x000D_26/7/2024:01440612 _x000D_24/7/2024:#Update - Awaiting approval for ECCS _x000D_23/7/2024:#Update - Awaiting approval for ECCS _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 9/9/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_6/9/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_5/9/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_4/9/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_3/9/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_2/9/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_29/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_28/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_27/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_22/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_21/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_20/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_19/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_19/8/2024:01440612 _x000D_16/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_15/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_14/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_13/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_12/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_9/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_8/8/2024:05/08/2024 _x000D_6/8/2024:05/08/2024 _x000D_5/8/2024:05/08/2024 _x000D_2/8/2024:29/07/2024 _x000D_1/8/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_30/7/2024:#Update- Site Type Change : Mobile Only Option _x000D_29/7/2024:#Update - Awaiting approval for ECCS _x000D_29/7/2024:01440612 _x000D_26/7/2024:01440612 _x000D_24/7/2024:#Update - Awaiting approval for ECCS _x000D_23/7/2024:#Update - Awaiting approval for ECCS _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 0 | #Update - this site has changed to a site type 3 / mobile only as per customer request | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984806 | 30015669 | 2.Commissioning | AM |  | 2024-08-22 | 2024-08-22 |  | 0 |  |  |  | 2024-09-03 | [7 empty] | 0
553 | 645449 | 1934 | Batch 4 Jun24 | Type 1 | SOGEA | SPAR | Maerdy | CF43 4BA | 2024-06-07 | 29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1018156 | 30016033 | 2.Commissioning | AM |  | 2024-06-17 | 2024-06-17 | 2024-06-17 | TRUE |  |  |  | 2024-07-16 | [7 empty] | 0
554 | 428382 | 3400 | Batch 5 Jul24 | Type 1 | SOGEA | SPAR INGOLDMELLS | Skegness | PE25 1LH |  | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:#Update - Appointment confirmed with retailer. _x000D_19/6/2024:#Update - Appointment confirmed with retailer. _x000D_18/6/2024:#Update - Appointment confirmed with retailer. _x000D_17/6/2024:#Update - Allwyn confirmed appointment with Retailer, required adjustment to 18/06 as per retailers req. Got permission for Sharing contact details with OR. _x000D_14/6/2024:#Update - Allwyn confirmed appointment with Retailer, required adjustment to 18/06 as per retailers req. Got permission for Sharing contact details with OR. _x000D_13/6/2024:#Update - Allwyn confirmed appointment with Retailer, required adjustment to 18/06 as per retailers req. Got permission for Sharing contact details with OR. _x000D_12/6/2024:#Update - Allwyn confirmed appointment with Retailer, required adjustment to 18/06 as per retailers req. Got permission for Sharing contact details with OR. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:#Update - Appointment confirmed with retailer. _x000D_19/6/2024:#Update - Appointment confirmed with retailer. _x000D_18/6/2024:#Update - Appointment confirmed with retailer. _x000D_17/6/2024:#Update - Allwyn confirmed appointment with Retailer, required adjustment to 18/06 as per retailers req. Got permission for Sharing contact details with OR. _x000D_14/6/2024:#Update - Allwyn confirmed appointment with Retailer, required adjustment to 18/06 as per retailers req. Got permission for Sharing contact details with OR. _x000D_13/6/2024:#Update - Allwyn confirmed appointment with Retailer, required adjustment to 18/06 as per retailers req. Got permission for Sharing contact details with OR. _x000D_12/6/2024:#Update - Allwyn confirmed appointment with Retailer, required adjustment to 18/06 as per retailers req. Got permission for Sharing contact details with OR. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015526 | 30016822 | 2.Commissioning |  |  | 2024-06-17 | 2024-06-17 | 2024-06-17 | TRUE |  |  |  | 2024-07-10 | [7 empty] | 0
555 | 662592 | 1151 | Batch 3 May24 | Type 1 | FTTP | Ash News | HYDE | SK14 4HH | 2024-06-07 | 16/7/2024:#Update Retailer confirmed new appointment. _x000D_15/7/2024:#Update Retailer confirmed new appointment. _x000D_12/7/2024:#Update Retailer confirmed new appointment. _x000D_11/7/2024:#Update Retailer confirmed new appointment. _x000D_10/7/2024:#Update Retailer confirmed new appointment. _x000D_9/7/2024:#Update Retailer confirmed new appointment. _x000D_4/7/2024:#Update Retailer confirmed new appointment. _x000D_3/7/2024:#Update Retailer confirmed new appointment. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update Retailer confirmed new appointment. _x000D_27/6/2024:#Update Retailer confirmed new appointment. _x000D_25/6/2024:#Update Retailer confirmed new appointment. _x000D_24/6/2024:#Update Retailer confirmed new appointment. _x000D_20/6/2024:#Update Reappointed 04/07, PM. Action on Allwyn - ensure the retailer is aware. _x000D_19/6/2024:Supplier Delay: Unable to complete work in the allocated appointment slot, please await further details. _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 16/7/2024:#Update Retailer confirmed new appointment. _x000D_15/7/2024:#Update Retailer confirmed new appointment. _x000D_12/7/2024:#Update Retailer confirmed new appointment. _x000D_11/7/2024:#Update Retailer confirmed new appointment. _x000D_10/7/2024:#Update Retailer confirmed new appointment. _x000D_9/7/2024:#Update Retailer confirmed new appointment. _x000D_4/7/2024:#Update Retailer confirmed new appointment. _x000D_3/7/2024:#Update Retailer confirmed new appointment. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update Retailer confirmed new appointment. _x000D_27/6/2024:#Update Retailer confirmed new appointment. _x000D_25/6/2024:#Update Retailer confirmed new appointment. _x000D_24/6/2024:#Update Retailer confirmed new appointment. _x000D_20/6/2024:#Update Reappointed 04/07, PM. Action on Allwyn - ensure the retailer is aware. _x000D_19/6/2024:Supplier Delay: Unable to complete work in the allocated appointment slot, please await further details. _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301348 | 30014041 | 6.Failed router install | AM |  | 2024-05-24 | 2024-06-18 | 2024-06-18 | TRUE |  |  |  | 2024-07-12 |  |  |  | 2024-07-12 | 242005008841 |  | 2024-07-15 | 1
556 | 100714 | 1212 | Batch 3 May24 | Type 1 | SoGEA/Mobile | Londis | HEMEL HEMPSTEAD | HP3 8EW | 2024-06-07 | 6/9/2024:#Update Awaiting further information from OR _x000D_5/9/2024:#Update Awaiting further information from OR _x000D_4/9/2024:#Update Awaiting further information from OR _x000D_3/9/2024:#Update Awaiting further information from OR _x000D_2/9/2024:#Update Awaiting further information from OR _x000D_29/8/2024:#Update Awaiting further information from OR _x000D_28/8/2024:#Update Awaiting further information from OR _x000D_27/8/2024:#Update Awaiting further information from OR _x000D_22/8/2024:#Update Awaiting further information from OR _x000D_21/8/2024:#Update Awaiting further information from OR _x000D_20/8/2024:#Update Awaiting further information from OR _x000D_19/8/2024:#Update Awaiting further information from OR _x000D_19/8/2024:01413973 _x000D_16/8/2024:#Update Awaiting further information from OR _x000D_15/8/2024:#Update Awaiting further information from OR _x000D_14/8/2024:#Update Awaiting further information from OR _x000D_13/8/2024:#Update Awaiting further information from OR _x000D_12/8/2024:#Update Awaiting further information from OR _x000D_9/8/2024:#Update Awaiting further information from OR _x000D_8/8/2024:25/07/2024 _x000D_6/8/2024:25/07/2024 _x000D_5/8/2024:25/07/2024 _x000D_2/8/2024:25/07/2024 _x000D_1/8/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_30/7/2024:#Update Awaiting further information from OR _x000D_29/7/2024:#Update Awaiting further information from OR _x000D_29/7/2024:01413973 _x000D_26/7/2024:01413973 _x000D_24/7/2024:#Update Retailer happy with new appointment, 18/06, AM. _x000D_23/7/2024:#Update Retailer happy with new appointment, 18/06, AM. _x000D_22/7/2024:#Update Retailer happy with new appointment, 18/06, AM. _x000D_22/7/2024:#Update Retailer happy with new appointment, 18/06, AM. _x000D_20/6/2024:#Update Multiskilled engineer work is required, we will provide updates when they become available. _x000D_19/6/2024:#Update Multiskilled engineer work is required, we will provide updates when they become available. _x000D_18/6/2024:#Update Multiskilled engineer work is required, we will provide updates when they become available. _x000D_17/6/2024:#Update Multiskilled engineer work is required, we will provide updates when they become available. _x000D_14/6/2024:#Update Multiskilled engineer work is required, we will provide updates when they become available. _x000D_13/6/2024:#Update Multiskilled engineer work is required, we will provide updates when they become available. _x000D_12/6/2024:#Update Multiskilled engineer work is required, we will provide updates when they become available. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update Awaiting further information from OR _x000D_6/9/2024:#Update Awaiting further information from OR _x000D_5/9/2024:#Update Awaiting further information from OR _x000D_4/9/2024:#Update Awaiting further information from OR _x000D_3/9/2024:#Update Awaiting further information from OR _x000D_2/9/2024:#Update Awaiting further information from OR _x000D_29/8/2024:#Update Awaiting further information from OR _x000D_28/8/2024:#Update Awaiting further information from OR _x000D_27/8/2024:#Update Awaiting further information from OR _x000D_22/8/2024:#Update Awaiting further information from OR _x000D_21/8/2024:#Update Awaiting further information from OR _x000D_20/8/2024:#Update Awaiting further information from OR _x000D_19/8/2024:#Update Awaiting further information from OR _x000D_19/8/2024:01413973 _x000D_16/8/2024:#Update Awaiting further information from OR _x000D_15/8/2024:#Update Awaiting further information from OR _x000D_14/8/2024:#Update Awaiting further information from OR _x000D_13/8/2024:#Update Awaiting further information from OR _x000D_12/8/2024:#Update Awaiting further information from OR _x000D_9/8/2024:#Update Awaiting further information from OR _x000D_8/8/2024:25/07/2024 _x000D_6/8/2024:25/07/2024 _x000D_5/8/2024:25/07/2024 _x000D_2/8/2024:25/07/2024 _x000D_1/8/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_30/7/2024:#Update Awaiting further information from OR _x000D_29/7/2024:#Update Awaiting further information from OR _x000D_29/7/2024:01413973 _x000D_26/7/2024:01413973 _x000D_24/7/2024:#Update Retailer happy with new appointment, 18/06, AM. _x000D_23/7/2024:#Update Retailer happy with new appointment, 18/06, AM. _x000D_22/7/2024:#Update Retailer happy with new appointment, 18/06, AM. _x000D_22/7/2024:#Update Retailer happy with new appointment, 18/06, AM. _x000D_20/6/2024:#Update Multiskilled engineer work is required, we will provide updates when they become available. _x000D_19/6/2024:#Update Multiskilled engineer work is required, we will provide updates when they become available. _x000D_18/6/2024:#Update Multiskilled engineer work is required, we will provide updates when they become available. _x000D_17/6/2024:#Update Multiskilled engineer work is required, we will provide updates when they become available. _x000D_14/6/2024:#Update Multiskilled engineer work is required, we will provide updates when they become available. _x000D_13/6/2024:#Update Multiskilled engineer work is required, we will provide updates when they become available. _x000D_12/6/2024:#Update Multiskilled engineer work is required, we will provide updates when they become available. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update Awaiting further information from OR | 2024-05-29 | 29/05/24: CSL to provide an update |  |  | 2.Allwyn to arrange access | VFS978209 | 30014102 | 1.Provisioning | AM |  | 2024-05-28 | 2024-08-08 |  | 0 | [11 empty] | 0
557 | 602876 | 1219 | Batch 3 May24 | Type 1 | SOGEA | Londis | Beddington | CR0 4QR | 2024-06-07 | 2/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:Your order has been delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/07/2024. We will continue to provide update as they become available. _x000D_25/6/2024:Your order has been delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/07/2024. We will continue to provide update as they become available. _x000D_24/6/2024:Your order has been delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/07/2024. We will continue to provide update as they become available. _x000D_20/6/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_19/6/2024:Supplier Delay: Network Planning issue, please await for further details. _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 2/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:Your order has been delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/07/2024. We will continue to provide update as they become available. _x000D_25/6/2024:Your order has been delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/07/2024. We will continue to provide update as they become available. _x000D_24/6/2024:Your order has been delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/07/2024. We will continue to provide update as they become available. _x000D_20/6/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_19/6/2024:Supplier Delay: Network Planning issue, please await for further details. _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-05-29 | 29/05/24: CSL to provide an update |  |  | 3.Allwyn to arrange rtr install | VFP2301416 | 30014109 | 6.Failed router install | AM |  | 2024-05-28 | 2024-06-18 | 2024-06-18 | TRUE |  |  |  | 2024-07-11 |  |  |  | 2024-07-11 | 242005008621 |  | 2024-07-12 | 1
558 | 469448 | 1303 | Batch 3 May24 | Type 1 | SOGEA | Nisa Local Sangha Supermarket | Bilston | WV14 0AX | 2024-06-07 | 6/9/2024:#Update - New order raised and is committed for 05/09. Allwyn aware _x000D_5/9/2024:#Update - New order raised and is committed for 05/09. Allwyn aware _x000D_4/9/2024:#Update - New order raised and is committed for 05/09. Allwyn aware _x000D_3/9/2024:#Update - New order raised and is committed for 05/09. Allwyn aware _x000D_2/9/2024:#Update - New order raised and is committed for 05/09. Allwyn aware _x000D_29/8/2024:#Update - New order raised and is committed for 05/09. Allwyn aware _x000D_28/8/2024:#Update - New order raised and is committed for 05/09. Allwyn aware _x000D_27/8/2024:#Update - New order raised and is committed for 05/09. Allwyn aware _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:#Update rescheduled to 18/06 AM, due to no contact with retailer yet. _x000D_19/6/2024:#Update rescheduled to 18/06 AM, due to no contact with retailer yet. _x000D_18/6/2024:#Update rescheduled to 18/06 AM, due to no contact with retailer yet. _x000D_17/6/2024:#Update rescheduled to 18/06 AM, due to no contact with retailer yet. _x000D_14/6/2024:#Update rescheduled to 18/06 AM, due to no contact with retailer yet. _x000D_13/6/2024:#Update rescheduled to 18/06 AM, due to no contact with retailer yet. _x000D_12/6/2024:#Update rescheduled to 18/06 AM, due to no contact with retailer yet. _x000D_11/6/2024:0 _x000D_10/6/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a estimate completion date of 05/07/2024 and given us a review date of 08/07/2024. We will continue to provide update as they become available. _x000D_7/6/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a estimate completion date of 05/07/2024 and given us a review date of 08/07/2024. We will continue to provide update as they become available. _x000D_6/6/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a estimate completion date of 05/07/2024 and given us a review date of 08/07/2024. We will continue to provide update as they become available. _x000D_5/6/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a estimate completion date of 05/07/2024 and given us a review date of 08/07/2024. We will continue to provide update as they become available. _x000D_4/6/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a estimate completion date of 05/07/2024 and given us a review date of 08/07/2024. We will continue to provide update as they become available. _x000D_ | 9/9/2024:#Update - New order raised and is committed for 05/09. Allwyn aware _x000D_6/9/2024:#Update - New order raised and is committed for 05/09. Allwyn aware _x000D_5/9/2024:#Update - New order raised and is committed for 05/09. Allwyn aware _x000D_4/9/2024:#Update - New order raised and is committed for 05/09. Allwyn aware _x000D_3/9/2024:#Update - New order raised and is committed for 05/09. Allwyn aware _x000D_2/9/2024:#Update - New order raised and is committed for 05/09. Allwyn aware _x000D_29/8/2024:#Update - New order raised and is committed for 05/09. Allwyn aware _x000D_28/8/2024:#Update - New order raised and is committed for 05/09. Allwyn aware _x000D_27/8/2024:#Update - New order raised and is committed for 05/09. Allwyn aware _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:#Update rescheduled to 18/06 AM, due to no contact with retailer yet. _x000D_19/6/2024:#Update rescheduled to 18/06 AM, due to no contact with retailer yet. _x000D_18/6/2024:#Update rescheduled to 18/06 AM, due to no contact with retailer yet. _x000D_17/6/2024:#Update rescheduled to 18/06 AM, due to no contact with retailer yet. _x000D_14/6/2024:#Update rescheduled to 18/06 AM, due to no contact with retailer yet. _x000D_13/6/2024:#Update rescheduled to 18/06 AM, due to no contact with retailer yet. _x000D_12/6/2024:#Update rescheduled to 18/06 AM, due to no contact with retailer yet. _x000D_11/6/2024:0 _x000D_10/6/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a estimate completion date of 05/07/2024 and given us a review date of 08/07/2024. We will continue to provide update as they become available. _x000D_7/6/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a estimate completion date of 05/07/2024 and given us a review date of 08/07/2024. We will continue to provide update as they become available. _x000D_6/6/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a estimate completion date of 05/07/2024 and given us a review date of 08/07/2024. We will continue to provide update as they become available. _x000D_5/6/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a estimate completion date of 05/07/2024 and given us a review date of 08/07/2024. We will continue to provide update as they become available. _x000D_4/6/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a estimate completion date of 05/07/2024 and given us a review date of 08/07/2024. We will continue to provide update as they become available. _x000D_ | Order Completed | #Update - New order raised and is committed for 05/09. Allwyn aware |  |  |  |  | 3.Allwyn to arrange rtr install | VFS978258 | 30014193 | 2.Commissioning | AM |  | 2024-05-30 | 2024-06-18 | 2024-06-28 | TRUE |  |  |  | 2024-08-05 | [7 empty] | 0
559 | 233676 | 1610 | Batch 4 Jun24 | Type 1 | SOGEA | Spar Stores | HUNTINGDON | PE27 3XS | 2024-06-07 | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 6.No action | VFS984814 | 30015382 | 6.Failed router install | AM |  | 2024-06-18 | 2024-06-18 | 2024-06-18 | TRUE |  |  |  | 2024-07-10 |  |  |  | 2024-07-10 | 242005008563 |  | 2024-07-12 | 1
560 | 209964 | 1611 | Batch 4 Jun24 | Type 1 | FTTP | Spar Stores | Glasgow | G46 7RY | 2024-06-07 | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2338563 | 30015610 | 2.Commissioning | AM |  | 2024-06-18 | 2024-06-18 | 2024-06-18 | TRUE |  |  |  | 2024-07-23 | [7 empty] | 0
561 | 652086 | 1612 | Batch 4 Jun24 | Type 1 | FTTP | Spar Forehill | Ayr | KA7 3EN | 2024-06-07 | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2338562 | 30015585 | 6.Failed router install | AM |  | 2024-06-18 | 2024-06-18 | 2024-06-18 | TRUE |  |  |  | 2024-07-23 |  |  |  | 2024-07-23 | 239004929546 |  | 2024-07-24 | 1
562 | 651179 | 1621 | Batch 4 Jun24 | Type 1 | FTTP | Spar | Magherafelt | BT45 5AL | 2024-06-07 | 19/7/2024:#Update - Allwyn have reached out to retailer and are waiting to hear back from him with regards for suitable routing. (Asbestos present ) _x000D_18/7/2024:#Update - Allwyn have reached out to retailer and are waiting to hear back from him with regards for suitable routing. (Asbestos present ) _x000D_17/7/2024:#Update - Allwyn have reached out to retailer and are waiting to hear back from him with regards for suitable routing. (Asbestos present ) _x000D_16/7/2024:#Update - Allwyn have reached out to retailer and are waiting to hear back from him with regards for suitable routing. (Asbestos present ) _x000D_15/7/2024:#Update - Allwyn have reached out to retailer and are waiting to hear back from him with regards for suitable routing. (Asbestos present ) _x000D_12/7/2024:#Update - Allwyn have reached out to retailer and are waiting to hear back from him with regards for suitable routing. (Asbestos present ) _x000D_11/7/2024:#Update - Allwyn have reached out to retailer and are waiting to hear back from him with regards for suitable routing. (Asbestos present ) _x000D_10/7/2024:#Update - Allwyn have reached out to retailer and are waiting to hear back from him with regards for suitable routing. (Asbestos present ) _x000D_9/7/2024:#Update - Allwyn have reached out to retailer and are waiting to hear back from him with regards for suitable routing. (Asbestos present ) _x000D_4/7/2024:#Update- Asbestos inside the shop. CSL investigating with OR engineer for alternative route, _x000D_3/7/2024:#Update- Asbestos inside the shop. CSL investigating with OR engineer for alternative route, _x000D_2/7/2024:0 _x000D_1/7/2024:#Update- Asbestos inside the shop. CSL investigating with OR engineer for alternative route, _x000D_27/6/2024:#Update- Asbestos inside the shop. CSL investigating with OR engineer for alternative route, _x000D_25/6/2024:#Update- Asbestos inside the shop. CSL investigating with OR engineer for alternative route, _x000D_24/6/2024:#Update- Asbestos inside the shop. CSL investigating with OR engineer for alternative route, _x000D_20/6/2024:#Update- Asbestos inside the shop. CSL investigating with OR engineer for alternative route, _x000D_19/6/2024:#Update- Asbestos inside the shop. CSL investigating with OR engineer for alternative route, _x000D_18/6/2024:#Update- Asbestos inside the shop. CSL investigating with OR engineer for alternative route, _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 19/7/2024:#Update - Allwyn have reached out to retailer and are waiting to hear back from him with regards for suitable routing. (Asbestos present ) _x000D_18/7/2024:#Update - Allwyn have reached out to retailer and are waiting to hear back from him with regards for suitable routing. (Asbestos present ) _x000D_17/7/2024:#Update - Allwyn have reached out to retailer and are waiting to hear back from him with regards for suitable routing. (Asbestos present ) _x000D_16/7/2024:#Update - Allwyn have reached out to retailer and are waiting to hear back from him with regards for suitable routing. (Asbestos present ) _x000D_15/7/2024:#Update - Allwyn have reached out to retailer and are waiting to hear back from him with regards for suitable routing. (Asbestos present ) _x000D_12/7/2024:#Update - Allwyn have reached out to retailer and are waiting to hear back from him with regards for suitable routing. (Asbestos present ) _x000D_11/7/2024:#Update - Allwyn have reached out to retailer and are waiting to hear back from him with regards for suitable routing. (Asbestos present ) _x000D_10/7/2024:#Update - Allwyn have reached out to retailer and are waiting to hear back from him with regards for suitable routing. (Asbestos present ) _x000D_9/7/2024:#Update - Allwyn have reached out to retailer and are waiting to hear back from him with regards for suitable routing. (Asbestos present ) _x000D_4/7/2024:#Update- Asbestos inside the shop. CSL investigating with OR engineer for alternative route, _x000D_3/7/2024:#Update- Asbestos inside the shop. CSL investigating with OR engineer for alternative route, _x000D_2/7/2024:0 _x000D_1/7/2024:#Update- Asbestos inside the shop. CSL investigating with OR engineer for alternative route, _x000D_27/6/2024:#Update- Asbestos inside the shop. CSL investigating with OR engineer for alternative route, _x000D_25/6/2024:#Update- Asbestos inside the shop. CSL investigating with OR engineer for alternative route, _x000D_24/6/2024:#Update- Asbestos inside the shop. CSL investigating with OR engineer for alternative route, _x000D_20/6/2024:#Update- Asbestos inside the shop. CSL investigating with OR engineer for alternative route, _x000D_19/6/2024:#Update- Asbestos inside the shop. CSL investigating with OR engineer for alternative route, _x000D_18/6/2024:#Update- Asbestos inside the shop. CSL investigating with OR engineer for alternative route, _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2338569 | 30015328 | 6.Failed router install | AM |  | 2024-06-18 | 2024-06-18 | 2024-06-18 | TRUE |  |  |  | 2024-07-23 |  |  |  | 2024-07-23 | 242005010277 |  | 2024-07-24 | 1
563 | 669758 | 1622 | Batch 4 Jun24 | Type 3 | FTTP/Mobile | Bathgate Cfpo & Spar | BATHGATE | EH48 4PN | 2024-06-07 | 6/9/2024:#Update - Action for allwyn: Please ask retailer to locate asbestos register. _x000D_5/9/2024:#Update - Action for allwyn: Please ask retailer to locate asbestos register. _x000D_4/9/2024:#Update - Action for allwyn: Please ask retailer to locate asbestos register. _x000D_3/9/2024:#Update - Action for allwyn: Please ask retailer to locate asbestos register. _x000D_2/9/2024:#Update - Action for allwyn: Please ask retailer to locate asbestos register. _x000D_29/8/2024:#Update - Action for allwyn: Please ask retailer to locate asbestos register. _x000D_28/8/2024:#Update - Action for allwyn: Please ask retailer to locate asbestos register. _x000D_27/8/2024:#Update - Action for allwyn: Please ask retailer to locate asbestos register. _x000D_22/8/2024:#Update - Action for allwyn: Please ask retailer to locate asbestos register. _x000D_21/8/2024:#Update - Action for allwyn: Please ask retailer to locate asbestos register. _x000D_20/8/2024:#Update - Action for allwyn: Please ask retailer to locate asbestos register. _x000D_19/8/2024:#Update - Action for allwyn: Please ask retailer to locate asbestos register. _x000D_19/8/2024:01442046 _x000D_16/8/2024:#Update - Action for allwyn: Please ask retailer to locate asbestos register. _x000D_15/8/2024:#Update - Action for allwyn: Please ask retailer to locate asbestos register. _x000D_14/8/2024:#Update - Action for allwyn: Please ask retailer to locate asbestos register. _x000D_13/8/2024:#Update - Action for allwyn: Please ask retailer to locate asbestos register. _x000D_12/8/2024:#Update - Action for allwyn: Please ask retailer to locate asbestos register. _x000D_9/8/2024:#Update - Action for allwyn: Please ask retailer to locate asbestos register. _x000D_8/8/2024:31/07/2024 _x000D_6/8/2024:31/07/2024 _x000D_5/8/2024:31/07/2024 _x000D_2/8/2024:31/07/2024 _x000D_1/8/2024:31/07/2024 _x000D_31/7/2024:08/07/2024 _x000D_31/7/2024:08/07/2024 _x000D_30/7/2024:#Update - Allwyn have reached out to retailer and are waiting to hear back from him with regards for suitable routing. (Asbestos present ) _x000D_29/7/2024:#Update - Allwyn have reached out to retailer and are waiting to hear back from him with regards for suitable routing. (Asbestos present ) _x000D_29/7/2024:01442046 _x000D_26/7/2024:01442046 _x000D_24/7/2024:#Update - Allwyn have reached out to retailer and are waiting to hear back from him with regards for suitable routing. (Asbestos present ) _x000D_23/7/2024:#Update - Allwyn have reached out to retailer and are waiting to hear back from him with regards for suitable routing. (Asbestos present ) _x000D_22/7/2024:#Update - Allwyn have reached out to retailer and are waiting to hear back from him with regards for suitable routing. (Asbestos present ) _x000D_22/7/2024:#Update - Allwyn have reached out to retailer and are waiting to hear back from him with regards for suitable routing. (Asbestos present ) _x000D_20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 9/9/2024:#Update - Action for allwyn: Please ask retailer to locate asbestos register. _x000D_6/9/2024:#Update - Action for allwyn: Please ask retailer to locate asbestos register. _x000D_5/9/2024:#Update - Action for allwyn: Please ask retailer to locate asbestos register. _x000D_4/9/2024:#Update - Action for allwyn: Please ask retailer to locate asbestos register. _x000D_3/9/2024:#Update - Action for allwyn: Please ask retailer to locate asbestos register. _x000D_2/9/2024:#Update - Action for allwyn: Please ask retailer to locate asbestos register. _x000D_29/8/2024:#Update - Action for allwyn: Please ask retailer to locate asbestos register. _x000D_28/8/2024:#Update - Action for allwyn: Please ask retailer to locate asbestos register. _x000D_27/8/2024:#Update - Action for allwyn: Please ask retailer to locate asbestos register. _x000D_22/8/2024:#Update - Action for allwyn: Please ask retailer to locate asbestos register. _x000D_21/8/2024:#Update - Action for allwyn: Please ask retailer to locate asbestos register. _x000D_20/8/2024:#Update - Action for allwyn: Please ask retailer to locate asbestos register. _x000D_19/8/2024:#Update - Action for allwyn: Please ask retailer to locate asbestos register. _x000D_19/8/2024:01442046 _x000D_16/8/2024:#Update - Action for allwyn: Please ask retailer to locate asbestos register. _x000D_15/8/2024:#Update - Action for allwyn: Please ask retailer to locate asbestos register. _x000D_14/8/2024:#Update - Action for allwyn: Please ask retailer to locate asbestos register. _x000D_13/8/2024:#Update - Action for allwyn: Please ask retailer to locate asbestos register. _x000D_12/8/2024:#Update - Action for allwyn: Please ask retailer to locate asbestos register. _x000D_9/8/2024:#Update - Action for allwyn: Please ask retailer to locate asbestos register. _x000D_8/8/2024:31/07/2024 _x000D_6/8/2024:31/07/2024 _x000D_5/8/2024:31/07/2024 _x000D_2/8/2024:31/07/2024 _x000D_1/8/2024:31/07/2024 _x000D_31/7/2024:08/07/2024 _x000D_31/7/2024:08/07/2024 _x000D_30/7/2024:#Update - Allwyn have reached out to retailer and are waiting to hear back from him with regards for suitable routing. (Asbestos present ) _x000D_29/7/2024:#Update - Allwyn have reached out to retailer and are waiting to hear back from him with regards for suitable routing. (Asbestos present ) _x000D_29/7/2024:01442046 _x000D_26/7/2024:01442046 _x000D_24/7/2024:#Update - Allwyn have reached out to retailer and are waiting to hear back from him with regards for suitable routing. (Asbestos present ) _x000D_23/7/2024:#Update - Allwyn have reached out to retailer and are waiting to hear back from him with regards for suitable routing. (Asbestos present ) _x000D_22/7/2024:#Update - Allwyn have reached out to retailer and are waiting to hear back from him with regards for suitable routing. (Asbestos present ) _x000D_22/7/2024:#Update - Allwyn have reached out to retailer and are waiting to hear back from him with regards for suitable routing. (Asbestos present ) _x000D_20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 0 | #Update - Action for allwyn: Please ask retailer to locate asbestos register. | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2338570 | 30015650 | 2.Commissioning | AM | [8 empty] | 2024-09-04 | [7 empty] | 0
564 | 623522 | 1627 | Batch 4 Jun24 | Type 1 | SOGEA | Spar | Larne | BT40 2AL | 2024-06-07 | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984818 | 30015493 | 6.Failed router install | AM |  | 2024-06-18 | 2024-06-18 | 2024-06-18 | TRUE |  |  |  | 2024-07-24 |  |  |  | 2024-07-24 | 23A004952996 |  | 2024-07-25 | 1
565 | 418784 | 1629 | Batch 4 Jun24 | Type 1 | SOGEA | SPAR HAMPTON | PETERBOROUGH | PE3 7JA | 2024-06-07 | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984817 | 30015590 | 6.Failed router install | AM |  | 2024-06-18 | 2024-06-18 | 2024-06-18 | TRUE |  |  |  | 2024-07-10 |  |  |  | 2024-07-10 | 242005008561 |  | 2024-07-15 | 1
566 | 442674 | 1631 | Batch 4 Jun24 | Type 1 | SOGEA | SPAR | ARMAGH | BT60 4DA | 2024-06-07 | 19/7/2024:#Update - Sent to survey group. _x000D_18/7/2024:#Update - Sent to survey group. _x000D_17/7/2024:#Update - Sent to survey group. _x000D_16/7/2024:#Update - Sent to survey group. _x000D_15/7/2024:#Update - Sent to survey group. _x000D_12/7/2024:#Update - Line plant work required - review date 23/07/2024 _x000D_11/7/2024:#Update - Line plant work required - review date 23/07/2024 _x000D_10/7/2024:#Update - Once the survey is completed the order will be progress further, will review the tracker on 3/7/2024 for next updates. _x000D_9/7/2024:#Update - Once the survey is completed the order will be progress further, will review the tracker on 3/7/2024 for next updates. _x000D_4/7/2024:#Update - Once the survey is completed the order will be progress further, will review the tracker on 3/7/2024 for next updates. _x000D_3/7/2024:#Update - Once the survey is completed the order will be progress further, will review the tracker on 3/7/2024 for next updates. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Once the survey is completed the order will be progress further, will review the tracker on 3/7/2024 for next updates. _x000D_27/6/2024:#Update - Once the survey is completed the order will be progress further, will review the tracker on 3/7/2024 for next updates. _x000D_25/6/2024:#Update - Once the survey is completed the order will be progress further, will review the tracker on 3/7/2024 for next updates. _x000D_24/6/2024:#Update - Supplier delay. Awaiting updates. _x000D_20/6/2024:#Update - Supplier delay. Awaiting updates. _x000D_19/6/2024:#Update - Supplier delay. Awaiting updates. _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 19/7/2024:#Update - Sent to survey group. _x000D_18/7/2024:#Update - Sent to survey group. _x000D_17/7/2024:#Update - Sent to survey group. _x000D_16/7/2024:#Update - Sent to survey group. _x000D_15/7/2024:#Update - Sent to survey group. _x000D_12/7/2024:#Update - Line plant work required - review date 23/07/2024 _x000D_11/7/2024:#Update - Line plant work required - review date 23/07/2024 _x000D_10/7/2024:#Update - Once the survey is completed the order will be progress further, will review the tracker on 3/7/2024 for next updates. _x000D_9/7/2024:#Update - Once the survey is completed the order will be progress further, will review the tracker on 3/7/2024 for next updates. _x000D_4/7/2024:#Update - Once the survey is completed the order will be progress further, will review the tracker on 3/7/2024 for next updates. _x000D_3/7/2024:#Update - Once the survey is completed the order will be progress further, will review the tracker on 3/7/2024 for next updates. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Once the survey is completed the order will be progress further, will review the tracker on 3/7/2024 for next updates. _x000D_27/6/2024:#Update - Once the survey is completed the order will be progress further, will review the tracker on 3/7/2024 for next updates. _x000D_25/6/2024:#Update - Once the survey is completed the order will be progress further, will review the tracker on 3/7/2024 for next updates. _x000D_24/6/2024:#Update - Supplier delay. Awaiting updates. _x000D_20/6/2024:#Update - Supplier delay. Awaiting updates. _x000D_19/6/2024:#Update - Supplier delay. Awaiting updates. _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984819 | 30015667 | 2.Commissioning | AM |  | 2024-06-18 | 2024-06-18 | 2024-06-18 | TRUE |  |  |  | 2024-07-10 | [7 empty] | 0
567 | 461570 | 1632 | Batch 4 Jun24 | Type 1 | FTTP/Mobile | SPAR | LONDONDERRY | BT47 4PE | 2024-06-07 | 6/9/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_5/9/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_4/9/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_3/9/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_2/9/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_29/8/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_28/8/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_27/8/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_22/8/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_21/8/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_20/8/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_19/8/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_19/8/2024:01442727 _x000D_16/8/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_15/8/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_14/8/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_13/8/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_12/8/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_9/8/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_8/8/2024:22/07/2024 _x000D_6/8/2024:22/07/2024 _x000D_5/8/2024:22/07/2024 _x000D_2/8/2024:22/07/2024 _x000D_1/8/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_30/7/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_29/7/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_29/7/2024:01442727 _x000D_26/7/2024:01442727 _x000D_24/7/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_23/7/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_22/7/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_22/7/2024:#Update - Sent to survey group. _x000D_20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 9/9/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_6/9/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_5/9/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_4/9/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_3/9/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_2/9/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_29/8/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_28/8/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_27/8/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_22/8/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_21/8/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_20/8/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_19/8/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_19/8/2024:01442727 _x000D_16/8/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_15/8/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_14/8/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_13/8/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_12/8/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_9/8/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_8/8/2024:22/07/2024 _x000D_6/8/2024:22/07/2024 _x000D_5/8/2024:22/07/2024 _x000D_2/8/2024:22/07/2024 _x000D_1/8/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_30/7/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_29/7/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_29/7/2024:01442727 _x000D_26/7/2024:01442727 _x000D_24/7/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_23/7/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_22/7/2024:#Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. _x000D_22/7/2024:#Update - Sent to survey group. _x000D_20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | Your order has been delayed. Survey work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 13/09/2024. We will continue to provide update as they become available. | #Update - . Network build work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 30/07/2024. We will continue to provide update as they become available. | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFP2338575 | 30015346 | 1.Provisioning | AM |  | 2024-06-18 | 2024-06-18 |  | 0 | [11 empty] | 0
568 | 659969 | 1637 | Batch 4 Jun24 | Type 3 | FTTP/Mobile | Bellevue Service Station | CRAIGAVON | BT67 9BW | 2024-06-07 | 6/9/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_5/9/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_4/9/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_3/9/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_2/9/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_29/8/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_28/8/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_27/8/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_22/8/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_21/8/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_20/8/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_19/8/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_19/8/2024:01442505 _x000D_16/8/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_15/8/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_14/8/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_13/8/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_12/8/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_9/8/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_8/8/2024:20/06/2024 _x000D_6/8/2024:20/06/2024 _x000D_5/8/2024:20/06/2024 _x000D_2/8/2024:20/06/2024 _x000D_1/8/2024:20/06/2024 _x000D_31/7/2024:20/06/2024 _x000D_31/7/2024:20/06/2024 _x000D_30/7/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_29/7/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_29/7/2024:01442505 _x000D_26/7/2024:01442505 _x000D_24/7/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_23/7/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_22/7/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_22/7/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 9/9/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_6/9/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_5/9/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_4/9/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_3/9/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_2/9/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_29/8/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_28/8/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_27/8/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_22/8/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_21/8/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_20/8/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_19/8/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_19/8/2024:01442505 _x000D_16/8/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_15/8/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_14/8/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_13/8/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_12/8/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_9/8/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_8/8/2024:20/06/2024 _x000D_6/8/2024:20/06/2024 _x000D_5/8/2024:20/06/2024 _x000D_2/8/2024:20/06/2024 _x000D_1/8/2024:20/06/2024 _x000D_31/7/2024:20/06/2024 _x000D_31/7/2024:20/06/2024 _x000D_30/7/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_29/7/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_29/7/2024:01442505 _x000D_26/7/2024:01442505 _x000D_24/7/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_23/7/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_22/7/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_22/7/2024:#Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. _x000D_20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 0 | #Update - Openreach have advised that the retailer needs to install a conduit beside the lottery machine by the next install date. CSL are liaising with Openreach for more information on what is required. | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2338576 | 30015606 | 2.Commissioning | AM |  |  |  |  | 0 |  |  |  | 2024-08-21 | [7 empty] | 0
569 | 469609 | 1638 | Batch 4 Jun24 | Type 1 | SOGEA | Spar | MAGHERAFELT | BT45 7QS | 2024-06-07 | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984826 | 30015613 | 6.Failed router install | AM |  | 2024-06-18 | 2024-06-18 | 2024-06-18 | TRUE |  |  |  | 2024-07-23 |  |  |  | 2024-07-23 | 242005010276 |  | 2024-07-24 | 1
570 | 623504 | 1646 | Batch 4 Jun24 | Type 1 | SOGEA | Creightons of Balmoral | Belfast | BT10 0AA | 2024-06-07 | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984832 | 30015407 | 6.Failed router install | AM |  | 2024-06-18 | 2024-06-18 | 2024-06-18 | TRUE |  |  |  | 2024-07-18 |  |  |  | 2024-07-18 | 242005010312 |  | 2024-07-18 | 1
571 | 625847 | 1647 | Batch 4 Jun24 | Type 1 | SOGEA | Spar | Kent | ME5 0DE | 2024-06-07 | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Update: Order Completed by Supplier _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Update: Order Completed by Supplier _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984884 | 30015575 | 6.Failed router install | AM |  | 2024-06-18 | 2024-06-18 | 2024-06-18 | TRUE |  |  |  | 2024-07-11 |  |  |  | 2024-07-12 | 242005008669 |  | 2024-07-16 | 1
572 | 634489 | 1649 | Batch 4 Jun24 | Type 3 | SoGEA/Mobile | Spar | Rotherham | S66 9LA | 2024-07-29 | 6/9/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_5/9/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_4/9/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_3/9/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_2/9/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_29/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_28/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_27/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_22/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_21/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_20/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_19/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_19/8/2024:01442367 _x000D_16/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_15/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_14/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_13/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_12/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_9/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_8/8/2024:01/08/2024 _x000D_6/8/2024:01/08/2024 _x000D_5/8/2024:01/08/2024 _x000D_2/8/2024:01/08/2024 _x000D_1/8/2024:20/06/2024 _x000D_31/7/2024:20/06/2024 _x000D_31/7/2024:20/06/2024 _x000D_30/7/2024:#Update - Proposal sent to Vodafone on 20/06 _x000D_29/7/2024:#Update - Proposal sent to Vodafone on 20/06 _x000D_29/7/2024:01442367 _x000D_26/7/2024:01442367 _x000D_24/7/2024:#Update - Proposal sent to Vodafone on 20/06 _x000D_23/7/2024:#Update - Proposal sent to Vodafone on 20/06 _x000D_22/7/2024:#Update - Proposal sent to Vodafone on 20/06 _x000D_22/7/2024:#Update - Proposal sent to Vodafone on 20/06 _x000D_20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 9/9/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_6/9/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_5/9/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_4/9/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_3/9/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_2/9/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_29/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_28/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_27/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_22/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_21/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_20/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_19/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_19/8/2024:01442367 _x000D_16/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_15/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_14/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_13/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_12/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_9/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_8/8/2024:01/08/2024 _x000D_6/8/2024:01/08/2024 _x000D_5/8/2024:01/08/2024 _x000D_2/8/2024:01/08/2024 _x000D_1/8/2024:20/06/2024 _x000D_31/7/2024:20/06/2024 _x000D_31/7/2024:20/06/2024 _x000D_30/7/2024:#Update - Proposal sent to Vodafone on 20/06 _x000D_29/7/2024:#Update - Proposal sent to Vodafone on 20/06 _x000D_29/7/2024:01442367 _x000D_26/7/2024:01442367 _x000D_24/7/2024:#Update - Proposal sent to Vodafone on 20/06 _x000D_23/7/2024:#Update - Proposal sent to Vodafone on 20/06 _x000D_22/7/2024:#Update - Proposal sent to Vodafone on 20/06 _x000D_22/7/2024:#Update - Proposal sent to Vodafone on 20/06 _x000D_20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 0 | #Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984833 | 30015473 | 2.Commissioning | AM | [8 empty] | 2024-08-23 | [7 empty] | 0
573 | 669971 | 1655 | Batch 4 Jun24 | Type 1 | SoGEA/Mobile | SPAR | PRESTON | PR2 6TY | 2024-06-07 | 6/9/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_5/9/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_4/9/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_3/9/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_2/9/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_29/8/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_28/8/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_27/8/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_22/8/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_21/8/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_20/8/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_19/8/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_19/8/2024:01442570 _x000D_16/8/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_15/8/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_14/8/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_13/8/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_12/8/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_9/8/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_8/8/2024:12/07/2024 _x000D_6/8/2024:12/07/2024 _x000D_5/8/2024:12/07/2024 _x000D_2/8/2024:12/07/2024 _x000D_1/8/2024:12/07/2024 _x000D_31/7/2024:12/07/2024 _x000D_31/7/2024:12/07/2024 _x000D_30/7/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_29/7/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_29/7/2024:01442570 _x000D_26/7/2024:01442570 _x000D_24/7/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_23/7/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_22/7/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_22/7/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_20/6/2024:#Update - Order has now been complete _x000D_19/6/2024:Order Completed _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 9/9/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_6/9/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_5/9/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_4/9/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_3/9/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_2/9/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_29/8/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_28/8/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_27/8/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_22/8/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_21/8/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_20/8/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_19/8/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_19/8/2024:01442570 _x000D_16/8/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_15/8/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_14/8/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_13/8/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_12/8/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_9/8/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_8/8/2024:12/07/2024 _x000D_6/8/2024:12/07/2024 _x000D_5/8/2024:12/07/2024 _x000D_2/8/2024:12/07/2024 _x000D_1/8/2024:12/07/2024 _x000D_31/7/2024:12/07/2024 _x000D_31/7/2024:12/07/2024 _x000D_30/7/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_29/7/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_29/7/2024:01442570 _x000D_26/7/2024:01442570 _x000D_24/7/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_23/7/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_22/7/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_22/7/2024:#Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. _x000D_20/6/2024:#Update - Order has now been complete _x000D_19/6/2024:Order Completed _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | Update: Order Amended | #Update - Allwyn are reviewing this site as the spar has very long opening hours and may be difficult to faciliate OOH appointments. I have submitted the ECC's in presumption for approval, but this may take time to arrange. Awaiting feedback from both Allwyn and approval for the ECC's. Will arrange with OR if this can go ahead to find a engineer that will attend before 6am. | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFS984836 | 30015514 | 1.Provisioning | AM |  | 2024-06-18 | 2024-08-19 |  | 0 | [11 empty] | 0
574 | 672597 | 1658 | Batch 4 Jun24 | Type 1 | SOGEA | SPAR | CALLINGTON | PL17 7AD | 2024-06-07 | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Update: Order Completed by Supplier _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Update: Order Completed by Supplier _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984779 | 30015491 | 2.Commissioning | AM |  | 2024-06-18 | 2024-06-18 | 2024-06-18 | TRUE |  |  |  | 2024-07-10 | [7 empty] | 0
575 | 619947 | 1660 | Batch 4 Jun24 | Type 1 | SoGEA/Mobile | Spar | Spalding | PE11 3RA | 2024-06-07 | 6/9/2024:#Update - chasing OR project team for an update re. scope of OOH work _x000D_5/9/2024:#Update - chasing OR project team for an update re. scope of OOH work _x000D_4/9/2024:#Update - chasing OR project team for an update re. scope of OOH work _x000D_3/9/2024:#Update - chasing OR project team for an update re. scope of OOH work _x000D_2/9/2024:#Update - chasing OR project team for an update re. scope of OOH work _x000D_29/8/2024:#Update - chasing OR project team for an update re. scope of OOH work _x000D_28/8/2024:#Update - chasing OR project team for an update re. scope of OOH work _x000D_27/8/2024:#Update - chasing OR project team for an update re. scope of OOH work _x000D_22/8/2024:#Update - chasing OR project team for an update re. scope of OOH work _x000D_21/8/2024:#Update - chasing OR project team for an update re. scope of OOH work _x000D_20/8/2024:#Update - chasing OR project team for an update re. scope of OOH work _x000D_19/8/2024:#Update - chasing OR project team for an update re. scope of OOH work _x000D_19/8/2024:01442427 _x000D_16/8/2024:#Update - chasing OR project team for an update re. scope of OOH work _x000D_15/8/2024:#Update - chasing OR project team for an update re. scope of OOH work _x000D_14/8/2024:#Update - unsuccessful installation - engineer cannot work in store/behind till area during shop opening hours for safety reasons. OOH attendance required. Hoist may be required at premises to access - awaiting OR update re. scope of OOH work required _x000D_13/8/2024:#Update - unsuccessful installation - engineer cannot work in store/behind till area during shop opening hours for safety reasons. OOH attendance required. Hoist may be required at premises to access - awaiting OR update re. scope of OOH work required _x000D_12/8/2024:#Update - unsuccessful installation - engineer cannot work in store/behind till area during shop opening hours for safety reasons. OOH attendance required. Hoist may be required at premises to access - awaiting OR update re. scope of OOH work required _x000D_9/8/2024:#Update - unsuccessful installation - engineer cannot work in store/behind till area during shop opening hours for safety reasons. OOH attendance required. Hoist may be required at premises to access - awaiting OR update re. scope of OOH work required _x000D_8/8/2024:18/06/2024 _x000D_6/8/2024:18/06/2024 _x000D_5/8/2024:18/06/2024 _x000D_2/8/2024:18/06/2024 _x000D_1/8/2024:18/06/2024 _x000D_31/7/2024:18/06/2024 _x000D_31/7/2024:18/06/2024 _x000D_30/7/2024:#Update - unsuccessful installation - engineer cannot work in store/behind till area during shop opening hours for safety reasons. OOH attendance required. Hoist may be required at premises to access - awaiting OR update re. scope of OOH work required _x000D_29/7/2024:#Update - unsuccessful installation - engineer cannot work in store/behind till area during shop opening hours for safety reasons. OOH attendance required. Hoist may be required at premises to access - awaiting OR update re. scope of OOH work required _x000D_29/7/2024:01442427 _x000D_26/7/2024:01442427 _x000D_24/7/2024:#Update - unsuccessful installation - engineer cannot work in store/behind till area during shop opening hours for safety reasons. OOH attendance required. Hoist may be required at premises to access - awaiting OR update re. scope of OOH work required _x000D_23/7/2024:#Update - unsuccessful installation - engineer cannot work in store/behind till area during shop opening hours for safety reasons. OOH attendance required. Hoist may be required at premises to access - awaiting OR update re. scope of OOH work required _x000D_22/7/2024:#Update - unsuccessful installation - engineer cannot work in store/behind till area during shop opening hours for safety reasons. OOH attendance required. Hoist may be required at premises to access - awaiting OR update re. scope of OOH work required _x000D_22/7/2024:#Update - unsuccessful installation - engineer cannot work in store/behind till area during shop opening hours for safety reasons. OOH attendance required. Hoist may be required at premises to access - awaiting OR update re. scope of OOH work required _x000D_20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 9/9/2024:#Update - chasing OR project team for an update re. scope of OOH work _x000D_6/9/2024:#Update - chasing OR project team for an update re. scope of OOH work _x000D_5/9/2024:#Update - chasing OR project team for an update re. scope of OOH work _x000D_4/9/2024:#Update - chasing OR project team for an update re. scope of OOH work _x000D_3/9/2024:#Update - chasing OR project team for an update re. scope of OOH work _x000D_2/9/2024:#Update - chasing OR project team for an update re. scope of OOH work _x000D_29/8/2024:#Update - chasing OR project team for an update re. scope of OOH work _x000D_28/8/2024:#Update - chasing OR project team for an update re. scope of OOH work _x000D_27/8/2024:#Update - chasing OR project team for an update re. scope of OOH work _x000D_22/8/2024:#Update - chasing OR project team for an update re. scope of OOH work _x000D_21/8/2024:#Update - chasing OR project team for an update re. scope of OOH work _x000D_20/8/2024:#Update - chasing OR project team for an update re. scope of OOH work _x000D_19/8/2024:#Update - chasing OR project team for an update re. scope of OOH work _x000D_19/8/2024:01442427 _x000D_16/8/2024:#Update - chasing OR project team for an update re. scope of OOH work _x000D_15/8/2024:#Update - chasing OR project team for an update re. scope of OOH work _x000D_14/8/2024:#Update - unsuccessful installation - engineer cannot work in store/behind till area during shop opening hours for safety reasons. OOH attendance required. Hoist may be required at premises to access - awaiting OR update re. scope of OOH work required _x000D_13/8/2024:#Update - unsuccessful installation - engineer cannot work in store/behind till area during shop opening hours for safety reasons. OOH attendance required. Hoist may be required at premises to access - awaiting OR update re. scope of OOH work required _x000D_12/8/2024:#Update - unsuccessful installation - engineer cannot work in store/behind till area during shop opening hours for safety reasons. OOH attendance required. Hoist may be required at premises to access - awaiting OR update re. scope of OOH work required _x000D_9/8/2024:#Update - unsuccessful installation - engineer cannot work in store/behind till area during shop opening hours for safety reasons. OOH attendance required. Hoist may be required at premises to access - awaiting OR update re. scope of OOH work required _x000D_8/8/2024:18/06/2024 _x000D_6/8/2024:18/06/2024 _x000D_5/8/2024:18/06/2024 _x000D_2/8/2024:18/06/2024 _x000D_1/8/2024:18/06/2024 _x000D_31/7/2024:18/06/2024 _x000D_31/7/2024:18/06/2024 _x000D_30/7/2024:#Update - unsuccessful installation - engineer cannot work in store/behind till area during shop opening hours for safety reasons. OOH attendance required. Hoist may be required at premises to access - awaiting OR update re. scope of OOH work required _x000D_29/7/2024:#Update - unsuccessful installation - engineer cannot work in store/behind till area during shop opening hours for safety reasons. OOH attendance required. Hoist may be required at premises to access - awaiting OR update re. scope of OOH work required _x000D_29/7/2024:01442427 _x000D_26/7/2024:01442427 _x000D_24/7/2024:#Update - unsuccessful installation - engineer cannot work in store/behind till area during shop opening hours for safety reasons. OOH attendance required. Hoist may be required at premises to access - awaiting OR update re. scope of OOH work required _x000D_23/7/2024:#Update - unsuccessful installation - engineer cannot work in store/behind till area during shop opening hours for safety reasons. OOH attendance required. Hoist may be required at premises to access - awaiting OR update re. scope of OOH work required _x000D_22/7/2024:#Update - unsuccessful installation - engineer cannot work in store/behind till area during shop opening hours for safety reasons. OOH attendance required. Hoist may be required at premises to access - awaiting OR update re. scope of OOH work required _x000D_22/7/2024:#Update - unsuccessful installation - engineer cannot work in store/behind till area during shop opening hours for safety reasons. OOH attendance required. Hoist may be required at premises to access - awaiting OR update re. scope of OOH work required _x000D_20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 0 | #Update - chasing OR project team for an update re. scope of OOH work | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFS984835 | 30015470 | 1.Provisioning | AM |  | 2024-06-18 | 2024-08-23 |  | 0 | [11 empty] | 0
576 | 111067 | 1661 | Batch 4 Jun24 | Type 1 | SOGEA | SPAR | GLASGOW | G67 3AZ | 2024-06-07 | 20/6/2024:#Update - Install completed - 18/06 _x000D_19/6/2024:#Update - Install completed - 18/06 _x000D_18/6/2024:Supplier Delay: Delay due to Frames Complications, please await for further details _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 20/6/2024:#Update - Install completed - 18/06 _x000D_19/6/2024:#Update - Install completed - 18/06 _x000D_18/6/2024:Supplier Delay: Delay due to Frames Complications, please await for further details _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984888 | 30015430 | 2.Commissioning | AM |  | 2024-06-18 | 2024-06-18 | 2024-06-18 | TRUE |  |  |  | 2024-07-23 | [7 empty] | 0
577 | 610453 | 1664 | Batch 4 Jun24 | Type 1 | FTTP/Mobile | Spar | Dungannon | BT70 1HX | 2024-06-07 | 6/9/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_5/9/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_4/9/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_3/9/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_2/9/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_29/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_28/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_27/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_22/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_21/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_20/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_19/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_19/8/2024:01462274 _x000D_16/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_15/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_14/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_13/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_12/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_9/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_8/8/2024:08/07/2024 _x000D_6/8/2024:08/07/2024 _x000D_5/8/2024:08/07/2024 _x000D_2/8/2024:08/07/2024 _x000D_1/8/2024:08/07/2024 _x000D_31/7/2024:08/07/2024 _x000D_31/7/2024:08/07/2024 _x000D_30/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_29/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_29/7/2024:01462274 _x000D_26/7/2024:01462274 _x000D_24/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_23/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_22/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_22/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 9/9/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_6/9/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_5/9/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_4/9/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_3/9/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_2/9/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_29/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_28/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_27/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_22/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_21/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_20/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_19/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_19/8/2024:01462274 _x000D_16/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_15/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_14/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_13/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_12/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_9/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_8/8/2024:08/07/2024 _x000D_6/8/2024:08/07/2024 _x000D_5/8/2024:08/07/2024 _x000D_2/8/2024:08/07/2024 _x000D_1/8/2024:08/07/2024 _x000D_31/7/2024:08/07/2024 _x000D_31/7/2024:08/07/2024 _x000D_30/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_29/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_29/7/2024:01462274 _x000D_26/7/2024:01462274 _x000D_24/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_23/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_22/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_22/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:Order Completed _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 0 | #Update - ECC proposal sent to Vodafone on 08/07 | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFP2338577 | 30015529 | 1.Provisioning | AM |  | 2024-06-18 | 2024-06-18 |  | 0 | [11 empty] | 0
578 | 434283 | 1666 | Batch 4 Jun24 | Type 1 | FTTP | Eurospar | DUNGANNON | BT71 7SL | 2024-06-07 | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2338579 | 30015356 | 2.Commissioning | AM |  | 2024-06-18 | 2024-06-18 | 2024-06-19 | TRUE |  |  |  | 2024-07-10 | [7 empty] | 0
579 | 669767 | 1670 | Batch 4 Jun24 | Type 1 | SOGEA | SPAR | CARNOUSTIE | DD7 7QQ | 2024-06-07 | 20/6/2024:Order Completed 19/6/2024:Order Completed 18/6/2024:0 17/6/2024:0 14/6/2024:0 13/6/2024:0 12/6/2024:0 10/6/2024:0 7/6/2024:0 6/6/2024:0 5/6/2024:0 4/6/2024:0 31/5/2024:0 30/5/2024:0 29/5/2024:0 28/5/2024:0 10/5/2024:0 02/05/2024: New order added to report | 20/6/2024:Order Completed 19/6/2024:Order Completed 18/6/2024:0 17/6/2024:0 14/6/2024:0 13/6/2024:0 12/6/2024:0 10/6/2024:0 7/6/2024:0 6/6/2024:0 5/6/2024:0 4/6/2024:0 31/5/2024:0 30/5/2024:0 29/5/2024:0 28/5/2024:0 10/5/2024:0 02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984838 | 30015336 | 2.Commissioning | AM |  | 2024-06-18 | 2024-06-18 | 2024-06-18 | TRUE |  |  |  | 2024-07-24 | [7 empty] | 0
580 | 429745 | 1671 | Batch 4 Jun24 | Type 1 | FTTP | SPAR | BELFAST | BT11 9HF | 2024-06-07 | 19/7/2024:#Update - Order is still delayed as cable work is required. CSL will update as more information become available. _x000D_18/7/2024:#Update - Order is still delayed as cable work is required. CSL will update as more information become available. _x000D_17/7/2024:#Update - Order has been delayed as cable work is required. CSL will update as more information become available. _x000D_16/7/2024:#Update - Order has been delayed as cable work is required. CSL will update as more information become available. _x000D_15/7/2024:#Update - Order has been delayed as cable work is required. CSL will update as more information become available. _x000D_12/7/2024:#Update - Order has been delayed as cable work is required. CSL will update as more information become available. _x000D_11/7/2024:#Update - Order has been delayed as cable work is required. CSL will update as more information become available. _x000D_10/7/2024:#Update - Order has been delayed as line lant planning work is required. CSL will update as more information become available. _x000D_9/7/2024:#Update - Order has been delayed as line lant planning work is required. CSL will update as more information become available. _x000D_4/7/2024:Your order has been delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 04/07/2024..We will continue to provide update as they become available. _x000D_25/6/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 04/07/2024..We will continue to provide update as they become available. _x000D_24/6/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 04/07/2024..We will continue to provide update as they become available. _x000D_20/6/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 04/07/2024..We will continue to provide update as they become available. _x000D_19/6/2024:Supplier Delay: Issues with the line plant, please await for further details. _x000D_18/6/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 19/7/2024:#Update - Order is still delayed as cable work is required. CSL will update as more information become available. _x000D_18/7/2024:#Update - Order is still delayed as cable work is required. CSL will update as more information become available. _x000D_17/7/2024:#Update - Order has been delayed as cable work is required. CSL will update as more information become available. _x000D_16/7/2024:#Update - Order has been delayed as cable work is required. CSL will update as more information become available. _x000D_15/7/2024:#Update - Order has been delayed as cable work is required. CSL will update as more information become available. _x000D_12/7/2024:#Update - Order has been delayed as cable work is required. CSL will update as more information become available. _x000D_11/7/2024:#Update - Order has been delayed as cable work is required. CSL will update as more information become available. _x000D_10/7/2024:#Update - Order has been delayed as line lant planning work is required. CSL will update as more information become available. _x000D_9/7/2024:#Update - Order has been delayed as line lant planning work is required. CSL will update as more information become available. _x000D_4/7/2024:Your order has been delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 04/07/2024..We will continue to provide update as they become available. _x000D_25/6/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 04/07/2024..We will continue to provide update as they become available. _x000D_24/6/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 04/07/2024..We will continue to provide update as they become available. _x000D_20/6/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 04/07/2024..We will continue to provide update as they become available. _x000D_19/6/2024:Supplier Delay: Issues with the line plant, please await for further details. _x000D_18/6/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2338584 | 30015450 | 2.Commissioning | AM |  | 2024-06-18 | 2024-06-18 | 2024-06-18 | TRUE |  |  |  | 2024-07-18 | [7 empty] | 0
581 | 616199 | 1672 | Batch 4 Jun24 | Type 1 | FTTP/Mobile | Spar | Belfast | BT15 5EY | 2024-08-13 | 16/8/2024:#Update - Order is still delayed as cable work is required. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order is still delayed as cable work is required. CSL will update as more information become available. _x000D_14/8/2024:#Update - Order is still delayed as cable work is required. CSL will update as more information become available. _x000D_13/8/2024:#Update - Order is still delayed as cable work is required. CSL will update as more information become available. _x000D_12/8/2024:#Update - Order is still delayed as cable work is required. CSL will update as more information become available. _x000D_9/8/2024:#Update - Order is still delayed as cable work is required. CSL will update as more information become available. _x000D_8/8/2024:18/07/2024 _x000D_6/8/2024:18/07/2024 _x000D_5/8/2024:18/07/2024 _x000D_2/8/2024:18/07/2024 _x000D_1/8/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_30/7/2024:#Update - Order is still delayed as cable work is required. CSL will update as more information become available. _x000D_29/7/2024:#Update - Order is still delayed as cable work is required. CSL will update as more information become available. _x000D_29/7/2024:01466663 _x000D_26/7/2024:01466663 _x000D_24/7/2024:#Update - Order is still delayed as cable work is required. CSL will update as more information become available. _x000D_23/7/2024:#Update - Order is still delayed as cable work is required. CSL will update as more information become available. _x000D_22/7/2024:#Update - Order is still delayed as cable work is required. CSL will update as more information become available. _x000D_22/7/2024:#Update - Order is still delayed as cable work is required. CSL will update as more information become available. _x000D_20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 16/8/2024:#Update - Order is still delayed as cable work is required. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order is still delayed as cable work is required. CSL will update as more information become available. _x000D_14/8/2024:#Update - Order is still delayed as cable work is required. CSL will update as more information become available. _x000D_13/8/2024:#Update - Order is still delayed as cable work is required. CSL will update as more information become available. _x000D_12/8/2024:#Update - Order is still delayed as cable work is required. CSL will update as more information become available. _x000D_9/8/2024:#Update - Order is still delayed as cable work is required. CSL will update as more information become available. _x000D_8/8/2024:18/07/2024 _x000D_6/8/2024:18/07/2024 _x000D_5/8/2024:18/07/2024 _x000D_2/8/2024:18/07/2024 _x000D_1/8/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_30/7/2024:#Update - Order is still delayed as cable work is required. CSL will update as more information become available. _x000D_29/7/2024:#Update - Order is still delayed as cable work is required. CSL will update as more information become available. _x000D_29/7/2024:01466663 _x000D_26/7/2024:01466663 _x000D_24/7/2024:#Update - Order is still delayed as cable work is required. CSL will update as more information become available. _x000D_23/7/2024:#Update - Order is still delayed as cable work is required. CSL will update as more information become available. _x000D_22/7/2024:#Update - Order is still delayed as cable work is required. CSL will update as more information become available. _x000D_22/7/2024:#Update - Order is still delayed as cable work is required. CSL will update as more information become available. _x000D_20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFP2338585 | 30015665 | 2.Commissioning | AM |  | 2024-06-18 | 2024-06-18 | 2024-08-12 07:54 | 1 |  |  |  | 2024-09-03 | [7 empty] | 0
582 | 230967 | 1818 | Batch 4 Jun24 | Type 1 | FTTP/Mobile | Shepperton News & Wine | SHEPPERTON | TW17 0DZ | 2024-06-12 | 6/9/2024:#Update - install delayed due to poling estimate has not been completed as of yet, as it has been found that the poling works need completing with the use of traffic management. The traffic management plan has been received, and OR are now waiting for a date to be requested for the works to be completed. Further updates to follow accordingly. _x000D_5/9/2024:#Update - install delayed due to poling estimate has not been completed as of yet, as it has been found that the poling works need completing with the use of traffic management. The traffic management plan has been received, and OR are now waiting for a date to be requested for the works to be completed. Further updates to follow accordingly. _x000D_4/9/2024:#Update - install delayed due to poling estimate has not been completed as of yet, as it has been found that the poling works need completing with the use of traffic management. The traffic management plan has been received, and OR are now waiting for a date to be requested for the works to be completed. Further updates to follow accordingly. _x000D_3/9/2024:#Update - install delayed due to poling estimate has not been completed as of yet, as it has been found that the poling works need completing with the use of traffic management. The traffic management plan has been received, and OR are now waiting for a date to be requested for the works to be completed. Further updates to follow accordingly. _x000D_2/9/2024:#Update - install delayed due to poling estimate has not been completed as of yet, as it has been found that the poling works need completing with the use of traffic management. The traffic management plan has been received, and OR are now waiting for a date to be requested for the works to be completed. Further updates to follow accordingly. _x000D_29/8/2024:#Update - install delayed due to poling estimate has not been completed as of yet, as it has been found that the poling works need completing with the use of traffic management. The traffic management plan has been received, and OR are now waiting for a date to be requested for the works to be completed. Further updates to follow accordingly. _x000D_28/8/2024:#Update - install delayed due to poling estimate has not been completed as of yet, as it has been found that the poling works need completing with the use of traffic management. The traffic management plan has been received, and OR are now waiting for a date to be requested for the works to be completed. Further updates to follow accordingly. _x000D_27/8/2024:#Update - install delayed due to poling estimate has not been completed as of yet, as it has been found that the poling works need completing with the use of traffic management. The traffic management plan has been received, and OR are now waiting for a date to be requested for the works to be completed. Further updates to follow accordingly. _x000D_22/8/2024:#Update - install delayed due to poling estimate has not been completed as of yet, as it has been found that the poling works need completing with the use of traffic management. The traffic management plan has been received, and OR are now waiting for a date to be requested for the works to be completed. Further updates to follow accordingly. _x000D_21/8/2024:#Update - install delayed due to poling estimate has not been completed as of yet, as it has been found that the poling works need completing with the use of traffic management. The traffic management plan has been received, and OR are now waiting for a date to be requested for the works to be completed. Further updates to follow accordingly. _x000D_20/8/2024:#Update - install delayed due to poling estimate has not been completed as of yet, as it has been found that the poling works need completing with the use of traffic management. The traffic management plan has been received, and OR are now waiting for a date to be requested for the works to be completed. Further updates to follow accordingly. _x000D_19/8/2024:#Update - install delayed due to poling estimate has not been completed as of yet, as it has been found that the poling works need completing with the use of traffic management. The traffic management plan has been received, and OR are now waiting for a date to be requested for the works to be completed. Further updates to follow accordingly. _x000D_19/8/2024:01432938 _x000D_16/8/2024:#Update - install delayed due to poling estimate has not been completed as of yet, as it has been found that the poling works need completing with the use of traffic management. The traffic management plan has been received, and OR are now waiting for a date to be requested for the works to be completed. Further updates to follow accordingly. _x000D_15/8/2024:#Update - install delayed due to poling estimate has not been completed as of yet, as it has been found that the poling works need completing with the use of traffic management. The traffic management plan has been received, and OR are now waiting for a date to be requested for the works to be completed. Further updates to follow accordingly. _x000D_14/8/2024:#Update - install delayed due to poling estimate has not been completed as of yet, as it has been found that the poling works need completing with the use of traffic management. The traffic management plan has been received, and OR are now waiting for a date to be requested for the works to be completed. Further updates to follow accordingly. _x000D_13/8/2024:#Update - install delayed due to poling estimate has not been completed as of yet, as it has been found that the poling works need completing with the use of traffic management. The traffic management plan has been received, and OR are now waiting for a date to be requested for the works to be completed. Further updates to follow accordingly. _x000D_12/8/2024:#Update - install delayed due to poling estimate has not been completed as of yet, as it has been found that the poling works need completing with the use of traffic management. The traffic management plan has been received, and OR are now waiting for a date to be requested for the works to be completed. Further updates to follow accordingly. _x000D_9/8/2024:#Update - install delayed due to poling estimate has not been completed as of yet, as it has been found that the poling works need completing with the use of traffic management. The traffic management plan has been received, and OR are now waiting for a date to be requested for the works to be completed. Further updates to follow accordingly. _x000D_8/8/2024:30/07/2024 _x000D_6/8/2024:30/07/2024 _x000D_5/8/2024:30/07/2024 _x000D_2/8/2024:30/07/2024 _x000D_1/8/2024:30/07/2024 _x000D_31/7/2024:30/07/2024 _x000D_31/7/2024:30/07/2024 _x000D_30/7/2024:#Update - order has been delayed. Pole work required. We will continue to provide update as they become available. _x000D_29/7/2024:#Update - order has been delayed. Pole work required. We will continue to provide update as they become available. _x000D_29/7/2024:01432938 _x000D_26/7/2024:01432938 _x000D_24/7/2024:#Update - order has been delayed. Pole work required. We will continue to provide update as they become available. _x000D_23/7/2024:#Update - order has been delayed. Pole work required. We will continue to provide update as they become available. _x000D_22/7/2024:#Update - order has been delayed. Pole work required. We will continue to provide update as they become available. _x000D_22/7/2024:#Update - order has been delayed. Pole work required. We will continue to provide update as they become available. _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 20/05 AM _x000D_19/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 20/05 AM _x000D_18/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 20/05 AM _x000D_17/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 20/05 AM _x000D_14/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 20/05 AM _x000D_13/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 20/05 AM _x000D_12/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 20/05 AM _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 9/9/2024:#Update - install delayed due to poling estimate has not been completed as of yet, as it has been found that the poling works need completing with the use of traffic management. The traffic management plan has been received, and OR are now waiting for a date to be requested for the works to be completed. Further updates to follow accordingly. _x000D_6/9/2024:#Update - install delayed due to poling estimate has not been completed as of yet, as it has been found that the poling works need completing with the use of traffic management. The traffic management plan has been received, and OR are now waiting for a date to be requested for the works to be completed. Further updates to follow accordingly. _x000D_5/9/2024:#Update - install delayed due to poling estimate has not been completed as of yet, as it has been found that the poling works need completing with the use of traffic management. The traffic management plan has been received, and OR are now waiting for a date to be requested for the works to be completed. Further updates to follow accordingly. _x000D_4/9/2024:#Update - install delayed due to poling estimate has not been completed as of yet, as it has been found that the poling works need completing with the use of traffic management. The traffic management plan has been received, and OR are now waiting for a date to be requested for the works to be completed. Further updates to follow accordingly. _x000D_3/9/2024:#Update - install delayed due to poling estimate has not been completed as of yet, as it has been found that the poling works need completing with the use of traffic management. The traffic management plan has been received, and OR are now waiting for a date to be requested for the works to be completed. Further updates to follow accordingly. _x000D_2/9/2024:#Update - install delayed due to poling estimate has not been completed as of yet, as it has been found that the poling works need completing with the use of traffic management. The traffic management plan has been received, and OR are now waiting for a date to be requested for the works to be completed. Further updates to follow accordingly. _x000D_29/8/2024:#Update - install delayed due to poling estimate has not been completed as of yet, as it has been found that the poling works need completing with the use of traffic management. The traffic management plan has been received, and OR are now waiting for a date to be requested for the works to be completed. Further updates to follow accordingly. _x000D_28/8/2024:#Update - install delayed due to poling estimate has not been completed as of yet, as it has been found that the poling works need completing with the use of traffic management. The traffic management plan has been received, and OR are now waiting for a date to be requested for the works to be completed. Further updates to follow accordingly. _x000D_27/8/2024:#Update - install delayed due to poling estimate has not been completed as of yet, as it has been found that the poling works need completing with the use of traffic management. The traffic management plan has been received, and OR are now waiting for a date to be requested for the works to be completed. Further updates to follow accordingly. _x000D_22/8/2024:#Update - install delayed due to poling estimate has not been completed as of yet, as it has been found that the poling works need completing with the use of traffic management. The traffic management plan has been received, and OR are now waiting for a date to be requested for the works to be completed. Further updates to follow accordingly. _x000D_21/8/2024:#Update - install delayed due to poling estimate has not been completed as of yet, as it has been found that the poling works need completing with the use of traffic management. The traffic management plan has been received, and OR are now waiting for a date to be requested for the works to be completed. Further updates to follow accordingly. _x000D_20/8/2024:#Update - install delayed due to poling estimate has not been completed as of yet, as it has been found that the poling works need completing with the use of traffic management. The traffic management plan has been received, and OR are now waiting for a date to be requested for the works to be completed. Further updates to follow accordingly. _x000D_19/8/2024:#Update - install delayed due to poling estimate has not been completed as of yet, as it has been found that the poling works need completing with the use of traffic management. The traffic management plan has been received, and OR are now waiting for a date to be requested for the works to be completed. Further updates to follow accordingly. _x000D_19/8/2024:01432938 _x000D_16/8/2024:#Update - install delayed due to poling estimate has not been completed as of yet, as it has been found that the poling works need completing with the use of traffic management. The traffic management plan has been received, and OR are now waiting for a date to be requested for the works to be completed. Further updates to follow accordingly. _x000D_15/8/2024:#Update - install delayed due to poling estimate has not been completed as of yet, as it has been found that the poling works need completing with the use of traffic management. The traffic management plan has been received, and OR are now waiting for a date to be requested for the works to be completed. Further updates to follow accordingly. _x000D_14/8/2024:#Update - install delayed due to poling estimate has not been completed as of yet, as it has been found that the poling works need completing with the use of traffic management. The traffic management plan has been received, and OR are now waiting for a date to be requested for the works to be completed. Further updates to follow accordingly. _x000D_13/8/2024:#Update - install delayed due to poling estimate has not been completed as of yet, as it has been found that the poling works need completing with the use of traffic management. The traffic management plan has been received, and OR are now waiting for a date to be requested for the works to be completed. Further updates to follow accordingly. _x000D_12/8/2024:#Update - install delayed due to poling estimate has not been completed as of yet, as it has been found that the poling works need completing with the use of traffic management. The traffic management plan has been received, and OR are now waiting for a date to be requested for the works to be completed. Further updates to follow accordingly. _x000D_9/8/2024:#Update - install delayed due to poling estimate has not been completed as of yet, as it has been found that the poling works need completing with the use of traffic management. The traffic management plan has been received, and OR are now waiting for a date to be requested for the works to be completed. Further updates to follow accordingly. _x000D_8/8/2024:30/07/2024 _x000D_6/8/2024:30/07/2024 _x000D_5/8/2024:30/07/2024 _x000D_2/8/2024:30/07/2024 _x000D_1/8/2024:30/07/2024 _x000D_31/7/2024:30/07/2024 _x000D_31/7/2024:30/07/2024 _x000D_30/7/2024:#Update - order has been delayed. Pole work required. We will continue to provide update as they become available. _x000D_29/7/2024:#Update - order has been delayed. Pole work required. We will continue to provide update as they become available. _x000D_29/7/2024:01432938 _x000D_26/7/2024:01432938 _x000D_24/7/2024:#Update - order has been delayed. Pole work required. We will continue to provide update as they become available. _x000D_23/7/2024:#Update - order has been delayed. Pole work required. We will continue to provide update as they become available. _x000D_22/7/2024:#Update - order has been delayed. Pole work required. We will continue to provide update as they become available. _x000D_22/7/2024:#Update - order has been delayed. Pole work required. We will continue to provide update as they become available. _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 20/05 AM _x000D_19/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 20/05 AM _x000D_18/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 20/05 AM _x000D_17/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 20/05 AM _x000D_14/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 20/05 AM _x000D_13/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 20/05 AM _x000D_12/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 20/05 AM _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 0 | #Update - install delayed due to poling estimate has not been completed as of yet, as it has been found that the poling works need completing with the use of traffic management. The traffic management plan has been received, and OR are now waiting for a date to be requested for the works to be completed. Further updates to follow accordingly. | 2024-06-07 |  |  |  | 5.CSL | VFP2337318 | 30015126 | 1.Provisioning | AM |  | 2024-06-11 | 2024-06-18 |  | 0 | [11 empty] | 0
583 | 646604 | 771 | Batch 3 May24 | Type 1 | SoGEA/Mobile | Morker News | Leicester | LE4 5LD | 2024-06-07 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_19/8/2024:01389263 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_13/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_12/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_9/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_8/8/2024:05/08/2024 _x000D_6/8/2024:05/08/2024 _x000D_5/8/2024:05/08/2024 _x000D_2/8/2024:31/07/2024 _x000D_1/8/2024:31/07/2024 _x000D_31/7/2024:17/06/2024 _x000D_31/7/2024:17/06/2024 _x000D_30/7/2024:#Update - Pushed out date as requested from Allwyn. Action for allwyn: Confirm new apointment date of 0807-Am. _x000D_29/7/2024:#Update - Pushed out date as requested from Allwyn. Action for allwyn: Confirm new apointment date of 0807-Am. _x000D_29/7/2024:01389263 _x000D_26/7/2024:01389263 _x000D_24/7/2024:#Update - Pushed out date as requested from Allwyn. Action for allwyn: Confirm new apointment date of 0807-Am. _x000D_23/7/2024:#Update - Pushed out date as requested from Allwyn. Action for allwyn: Confirm new apointment date of 0807-Am. _x000D_22/7/2024:#Update - Pushed out date as requested from Allwyn. Action for allwyn: Confirm new apointment date of 0807-Am. _x000D_22/7/2024:#Update - Pushed out date as requested from Allwyn. Action for allwyn: Confirm new apointment date of 0807-Am. _x000D_19/7/2024:Order Completed _x000D_18/7/2024:Order Completed _x000D_17/7/2024:Order Completed _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:Line Identified is not compatible with the requested service _x000D_2/7/2024:0 _x000D_1/7/2024:Line Identified is not compatible with the requested service _x000D_27/6/2024:Line Identified is not compatible with the requested service _x000D_25/6/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_24/6/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_20/6/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_19/8/2024:01389263 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_13/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_12/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_9/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_8/8/2024:05/08/2024 _x000D_6/8/2024:05/08/2024 _x000D_5/8/2024:05/08/2024 _x000D_2/8/2024:31/07/2024 _x000D_1/8/2024:31/07/2024 _x000D_31/7/2024:17/06/2024 _x000D_31/7/2024:17/06/2024 _x000D_30/7/2024:#Update - Pushed out date as requested from Allwyn. Action for allwyn: Confirm new apointment date of 0807-Am. _x000D_29/7/2024:#Update - Pushed out date as requested from Allwyn. Action for allwyn: Confirm new apointment date of 0807-Am. _x000D_29/7/2024:01389263 _x000D_26/7/2024:01389263 _x000D_24/7/2024:#Update - Pushed out date as requested from Allwyn. Action for allwyn: Confirm new apointment date of 0807-Am. _x000D_23/7/2024:#Update - Pushed out date as requested from Allwyn. Action for allwyn: Confirm new apointment date of 0807-Am. _x000D_22/7/2024:#Update - Pushed out date as requested from Allwyn. Action for allwyn: Confirm new apointment date of 0807-Am. _x000D_22/7/2024:#Update - Pushed out date as requested from Allwyn. Action for allwyn: Confirm new apointment date of 0807-Am. _x000D_19/7/2024:Order Completed _x000D_18/7/2024:Order Completed _x000D_17/7/2024:Order Completed _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:Line Identified is not compatible with the requested service _x000D_2/7/2024:0 _x000D_1/7/2024:Line Identified is not compatible with the requested service _x000D_27/6/2024:Line Identified is not compatible with the requested service _x000D_25/6/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_24/6/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_20/6/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 5.CSL | VFP2300968 | 30013661 | 2.Commissioning | AM |  | 2024-05-09 | 2024-08-23 |  | 0 | [11 empty] | 0
584 | 638589 | 1033 | Batch 3 May24 | Type 1 | SOGEA | Lidget Green Convenience | Bradford | BD7 2AA | 2024-06-07 | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:#Update - NFA - Allwyn confirmed amended installation date with retailer _x000D_19/6/2024:#Update - NFA - Allwyn confirmed amended installation date with retailer _x000D_18/6/2024:#Update - NFA - Allwyn confirmed amended installation date with retailer _x000D_17/6/2024:#Update - NFA - Allwyn confirmed amended installation date with retailer _x000D_14/6/2024:#Update - NFA - Allwyn confirmed amended installation date with retailer _x000D_13/6/2024:#Update - customer missed appointment, Store manager unaware of visit and unable to accommodate, will reappoint install date. _x000D_12/6/2024:#Update - customer missed appointment, Store manager unaware of visit and unable to accommodate, will reappoint install date. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:#Update - NFA - Allwyn confirmed amended installation date with retailer _x000D_19/6/2024:#Update - NFA - Allwyn confirmed amended installation date with retailer _x000D_18/6/2024:#Update - NFA - Allwyn confirmed amended installation date with retailer _x000D_17/6/2024:#Update - NFA - Allwyn confirmed amended installation date with retailer _x000D_14/6/2024:#Update - NFA - Allwyn confirmed amended installation date with retailer _x000D_13/6/2024:#Update - customer missed appointment, Store manager unaware of visit and unable to accommodate, will reappoint install date. _x000D_12/6/2024:#Update - customer missed appointment, Store manager unaware of visit and unable to accommodate, will reappoint install date. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-05-23 | 23/05/2024: CSL to provide an update |  |  | 3.Allwyn to arrange rtr install | VFP2301230 | 30013923 | 6.Failed router install | AM |  | 2024-05-22 | 2024-06-19 | 2024-06-19 | TRUE |  |  |  | 2024-07-20 |  |  |  | 2024-08-22 | 238004923983 | 238004923983 | 2024-08-27 | 1
585 | 616478 | 1254 | Batch 3 May24 | Type 1 | SOGEA | Loco | Coventry | CV1 5JD | 2024-07-05 | 6/9/2024:#Update - Spoke to engineer who attended fault 31st July, NTE is in drawer to left of lotto machine. _x000D_5/9/2024:#Update - Spoke to engineer who attended fault 31st July, NTE is in drawer to left of lotto machine. _x000D_4/9/2024:#Update - Spoke to engineer who attended fault 31st July, NTE is in drawer to left of lotto machine. _x000D_3/9/2024:#Update - Spoke to engineer who attended fault 31st July, NTE is in drawer to left of lotto machine. _x000D_2/9/2024:#Update - Spoke to engineer who attended fault 31st July, NTE is in drawer to left of lotto machine. _x000D_29/8/2024:#Update - Spoke to engineer who attended fault 31st July, NTE is in drawer to left of lotto machine. _x000D_28/8/2024:#Update - Spoke to engineer who attended fault 31st July, NTE is in drawer to left of lotto machine. _x000D_27/8/2024:#Update - Spoke to engineer who attended fault 31st July, NTE is in drawer to left of lotto machine. _x000D_22/8/2024:#Update - Spoke to engineer who attended fault 31st July, NTE is in drawer to left of lotto machine. _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_4/7/2024:#Update - this order has been changed to a site type 3/mobile only _x000D_3/7/2024:#Update - this order has been changed to a site type 3/mobile only _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:#Update - install unsuccessful due to H&S issues with cabling in ceiling. CSL awaiting further update from OR and will reappoint accordingly _x000D_27/6/2024:#Update - install unsuccessful due to H&S issues with cabling in ceiling. CSL awaiting further update from OR and will reappoint accordingly _x000D_25/6/2024:#Update - install unsuccessful due to H&S issues with cabling in ceiling. CSL awaiting further update from OR and will reappoint accordingly _x000D_24/6/2024:#Update - install unsuccessful due to H&S issues with cabling in ceiling. CSL awaiting further update from OR and will reappoint accordingly _x000D_20/6/2024:#Update - install unsuccessful due to H&S issues with cabling in ceiling. CSL awaiting further update from OR and will reappoint accordingly _x000D_19/6/2024:#Update - install unsuccessful due to H&S issues with cabling in ceiling. CSL awaiting further update from OR and will reappoint accordingly _x000D_18/6/2024:#Update - install unsuccessful due to H&S issues with cabling in ceiling. CSL awaiting further update from OR and will reappoint accordingly _x000D_17/6/2024:#Update - install unsuccessful due to H&S issues with cabling in ceiling. CSL awaiting further update from OR and will reappoint accordingly _x000D_14/6/2024:#Update - install unsuccessful due to H&S issues with cabling in ceiling. CSL awaiting further update from OR and will reappoint accordingly _x000D_13/6/2024:#Update - install unsuccessful due to H&S issues with cabling in ceiling. CSL awaiting further update from OR and will reappoint accordingly _x000D_12/6/2024:#Update - install unsuccessful due to H&S issues with cabling in ceiling. CSL awaiting further update from OR and will reappoint accordingly _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - Spoke to engineer who attended fault 31st July, NTE is in drawer to left of lotto machine. _x000D_6/9/2024:#Update - Spoke to engineer who attended fault 31st July, NTE is in drawer to left of lotto machine. _x000D_5/9/2024:#Update - Spoke to engineer who attended fault 31st July, NTE is in drawer to left of lotto machine. _x000D_4/9/2024:#Update - Spoke to engineer who attended fault 31st July, NTE is in drawer to left of lotto machine. _x000D_3/9/2024:#Update - Spoke to engineer who attended fault 31st July, NTE is in drawer to left of lotto machine. _x000D_2/9/2024:#Update - Spoke to engineer who attended fault 31st July, NTE is in drawer to left of lotto machine. _x000D_29/8/2024:#Update - Spoke to engineer who attended fault 31st July, NTE is in drawer to left of lotto machine. _x000D_28/8/2024:#Update - Spoke to engineer who attended fault 31st July, NTE is in drawer to left of lotto machine. _x000D_27/8/2024:#Update - Spoke to engineer who attended fault 31st July, NTE is in drawer to left of lotto machine. _x000D_22/8/2024:#Update - Spoke to engineer who attended fault 31st July, NTE is in drawer to left of lotto machine. _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_4/7/2024:#Update - this order has been changed to a site type 3/mobile only _x000D_3/7/2024:#Update - this order has been changed to a site type 3/mobile only _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:#Update - install unsuccessful due to H&S issues with cabling in ceiling. CSL awaiting further update from OR and will reappoint accordingly _x000D_27/6/2024:#Update - install unsuccessful due to H&S issues with cabling in ceiling. CSL awaiting further update from OR and will reappoint accordingly _x000D_25/6/2024:#Update - install unsuccessful due to H&S issues with cabling in ceiling. CSL awaiting further update from OR and will reappoint accordingly _x000D_24/6/2024:#Update - install unsuccessful due to H&S issues with cabling in ceiling. CSL awaiting further update from OR and will reappoint accordingly _x000D_20/6/2024:#Update - install unsuccessful due to H&S issues with cabling in ceiling. CSL awaiting further update from OR and will reappoint accordingly _x000D_19/6/2024:#Update - install unsuccessful due to H&S issues with cabling in ceiling. CSL awaiting further update from OR and will reappoint accordingly _x000D_18/6/2024:#Update - install unsuccessful due to H&S issues with cabling in ceiling. CSL awaiting further update from OR and will reappoint accordingly _x000D_17/6/2024:#Update - install unsuccessful due to H&S issues with cabling in ceiling. CSL awaiting further update from OR and will reappoint accordingly _x000D_14/6/2024:#Update - install unsuccessful due to H&S issues with cabling in ceiling. CSL awaiting further update from OR and will reappoint accordingly _x000D_13/6/2024:#Update - install unsuccessful due to H&S issues with cabling in ceiling. CSL awaiting further update from OR and will reappoint accordingly _x000D_12/6/2024:#Update - install unsuccessful due to H&S issues with cabling in ceiling. CSL awaiting further update from OR and will reappoint accordingly _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update - Spoke to engineer who attended fault 31st July, NTE is in drawer to left of lotto machine. |  |  |  |  | 2.Allwyn to arrange access | VFP2301451 | 30014144 | 2.Commissioning | AM | [8 empty] | 2024-07-30 | [7 empty] | 0
586 | 621913 | 1259 | Batch 3 May24 | Type 3 | SOGEA | Nisa Local | Wrexham | LL14 6NL | 2024-06-07 | 6/9/2024:#Update - this order has been changed to a site type 3/mobile only _x000D_5/9/2024:#Update - this order has been changed to a site type 3/mobile only _x000D_4/9/2024:#Update - this order has been changed to a site type 3/mobile only _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:#Update - NFA - Allwyn have confirmed new installation date with retailer of 04/07 _x000D_4/7/2024:#Update - NFA - Allwyn have confirmed new installation date with retailer of 04/07 _x000D_3/7/2024:#Update - NFA - Allwyn have confirmed new installation date with retailer of 04/07 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - NFA - Allwyn have confirmed new installation date with retailer of 04/07 _x000D_27/6/2024:#Update - NFA - Allwyn have confirmed new installation date with retailer of 04/07 _x000D_25/6/2024:#Update - NFA - Allwyn have confirmed new installation date with retailer of 04/07 _x000D_24/6/2024:#Update - NFA - Allwyn have confirmed new installation date with retailer of 04/07 _x000D_20/6/2024:#Update - NFA - Allwyn have confirmed new installation date with retailer of 04/07 _x000D_19/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_18/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_17/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_14/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_13/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_12/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - this order has been changed to a site type 3/mobile only _x000D_6/9/2024:#Update - this order has been changed to a site type 3/mobile only _x000D_5/9/2024:#Update - this order has been changed to a site type 3/mobile only _x000D_4/9/2024:#Update - this order has been changed to a site type 3/mobile only _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:#Update - NFA - Allwyn have confirmed new installation date with retailer of 04/07 _x000D_4/7/2024:#Update - NFA - Allwyn have confirmed new installation date with retailer of 04/07 _x000D_3/7/2024:#Update - NFA - Allwyn have confirmed new installation date with retailer of 04/07 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - NFA - Allwyn have confirmed new installation date with retailer of 04/07 _x000D_27/6/2024:#Update - NFA - Allwyn have confirmed new installation date with retailer of 04/07 _x000D_25/6/2024:#Update - NFA - Allwyn have confirmed new installation date with retailer of 04/07 _x000D_24/6/2024:#Update - NFA - Allwyn have confirmed new installation date with retailer of 04/07 _x000D_20/6/2024:#Update - NFA - Allwyn have confirmed new installation date with retailer of 04/07 _x000D_19/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_18/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_17/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_14/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_13/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_12/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update - this order has been changed to a site type 3/mobile only |  |  |  |  | 3.Allwyn to arrange rtr install | VFP2301456 | 30014149 | 2.Commissioning | AM |  |  |  |  | Not Applicable |  |  |  | 2024-08-06 |  |  |  | 2024-08-06 |  |  |  | 0
587 | 471448 | 1305 | Batch 3 May24 | Type 1 | SoGEA/Mobile | CK's Supermarket | SWANSEA | SA2 8JJ | 2024-06-07 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:#Update - Allwyn Confirmed appointment of 09/07 _x000D_9/8/2024:#Update - Allwyn Confirmed appointment of 09/07 _x000D_8/8/2024:20/06/2024 _x000D_6/8/2024:20/06/2024 _x000D_5/8/2024:20/06/2024 _x000D_2/8/2024:20/06/2024 _x000D_1/8/2024:20/06/2024 _x000D_31/7/2024:20/06/2024 _x000D_31/7/2024:20/06/2024 _x000D_30/7/2024:#Update - Allwyn Confirmed appointment of 09/07 _x000D_29/7/2024:#Update - Allwyn Confirmed appointment of 09/07 _x000D_29/7/2024:01418573 _x000D_26/7/2024:01418573 _x000D_24/7/2024:#Update - Allwyn Confirmed appointment of 09/07 _x000D_23/7/2024:#Update - Allwyn Confirmed appointment of 09/07 _x000D_22/7/2024:#Update - Allwyn Confirmed appointment of 09/07 _x000D_22/7/2024:#Update - Allwyn Confirmed appointment of 09/07 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A4 (ECC) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 14/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/6/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 10/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_7/6/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 10/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_6/6/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 10/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_5/6/2024:0 _x000D_4/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 05/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:#Update - Allwyn Confirmed appointment of 09/07 _x000D_9/8/2024:#Update - Allwyn Confirmed appointment of 09/07 _x000D_8/8/2024:20/06/2024 _x000D_6/8/2024:20/06/2024 _x000D_5/8/2024:20/06/2024 _x000D_2/8/2024:20/06/2024 _x000D_1/8/2024:20/06/2024 _x000D_31/7/2024:20/06/2024 _x000D_31/7/2024:20/06/2024 _x000D_30/7/2024:#Update - Allwyn Confirmed appointment of 09/07 _x000D_29/7/2024:#Update - Allwyn Confirmed appointment of 09/07 _x000D_29/7/2024:01418573 _x000D_26/7/2024:01418573 _x000D_24/7/2024:#Update - Allwyn Confirmed appointment of 09/07 _x000D_23/7/2024:#Update - Allwyn Confirmed appointment of 09/07 _x000D_22/7/2024:#Update - Allwyn Confirmed appointment of 09/07 _x000D_22/7/2024:#Update - Allwyn Confirmed appointment of 09/07 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A4 (ECC) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 14/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/6/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 10/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_7/6/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 10/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_6/6/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 10/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_5/6/2024:0 _x000D_4/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 05/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 0 | 0 |  |  |  |  | 3.Allwyn to arrange rtr install | VFP2301502 | 30014195 | 2.Commissioning | AM | [8 empty] | 2024-08-29 | [7 empty] | 0
588 | 264591 | 1308 | Batch 3 May24 | Type 1 | SOGEA | Nisa Local | DRIFFIELD | YO25 5HB | 2024-06-07 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:Order Completed _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:Update: Order Amended _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:Order Completed _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:Update: Order Amended _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 3.Allwyn to arrange rtr install | VFP2301505 | 30014198 | 2.Commissioning | AM | [8 empty] | 2024-07-19 | [7 empty] | 0
589 | 482273 | 1375 | Batch 4 Jun24 | Type 1 | FTTP | Woodfield Convenience Store | Harrogate | HG1 4JB | 2024-06-07 | 23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:#Update supplier missed appointment due to a hoist being required. Reappointed for 3/07 AM _x000D_3/7/2024:#Update supplier missed appointment due to a hoist being required. Reappointed for 3/07 AM _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update supplier missed appointment due to a hoist being required. Reappointed for 3/07 AM _x000D_27/6/2024:#Update supplier missed appointment due to a hoist being required. Reappointed for 3/07 AM _x000D_25/6/2024:#Update supplier missed appointment due to a hoist being required. Reappointed for 3/07 AM _x000D_24/6/2024:#Update supplier missed appointment due to a hoist being required. Reappointed for 3/07 AM _x000D_20/6/2024:#Update supplier missed appointment due to a hoist being required. Reappointed for 3/07 AM _x000D_19/6/2024:#Update Shop owner not present, staff member unaware of order so refused order. Reappointed for 19/06 AM. _x000D_18/6/2024:#Update Shop owner not present, staff member unaware of order so refused order. Reappointed for 19/06 AM. _x000D_17/6/2024:#Update Shop owner not present, staff member unaware of order so refused order. Reappointed for 19/06 AM. _x000D_14/6/2024:#Update Shop owner not present, staff member unaware of order so refused order. Reappointed for 19/06 AM. _x000D_13/6/2024:#Update Shop owner not present, staff member unaware of order so refused order. Reappointed for 19/06 AM. _x000D_12/6/2024:#Update Shop owner not present, staff member unaware of order so refused order. Reappointed for 19/06 AM. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:#Update supplier missed appointment due to a hoist being required. Reappointed for 3/07 AM _x000D_3/7/2024:#Update supplier missed appointment due to a hoist being required. Reappointed for 3/07 AM _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update supplier missed appointment due to a hoist being required. Reappointed for 3/07 AM _x000D_27/6/2024:#Update supplier missed appointment due to a hoist being required. Reappointed for 3/07 AM _x000D_25/6/2024:#Update supplier missed appointment due to a hoist being required. Reappointed for 3/07 AM _x000D_24/6/2024:#Update supplier missed appointment due to a hoist being required. Reappointed for 3/07 AM _x000D_20/6/2024:#Update supplier missed appointment due to a hoist being required. Reappointed for 3/07 AM _x000D_19/6/2024:#Update Shop owner not present, staff member unaware of order so refused order. Reappointed for 19/06 AM. _x000D_18/6/2024:#Update Shop owner not present, staff member unaware of order so refused order. Reappointed for 19/06 AM. _x000D_17/6/2024:#Update Shop owner not present, staff member unaware of order so refused order. Reappointed for 19/06 AM. _x000D_14/6/2024:#Update Shop owner not present, staff member unaware of order so refused order. Reappointed for 19/06 AM. _x000D_13/6/2024:#Update Shop owner not present, staff member unaware of order so refused order. Reappointed for 19/06 AM. _x000D_12/6/2024:#Update Shop owner not present, staff member unaware of order so refused order. Reappointed for 19/06 AM. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2338492 | 30015365 | 6.Failed router install | AM |  | 2024-06-04 | 2024-06-19 | 2024-06-19 | TRUE |  |  |  | 2024-07-20 |  |  |  | 2024-07-20 | 238004924230 |  | 2024-07-23 | 1
590 | 463367 | 1676 | Batch 4 Jun24 | Type 1 | SOGEA | Spar | LANCASTER | LA1 5NA | 2024-06-07 | 20/6/2024:Order Completed _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 20/6/2024:Order Completed _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984776 | 30015607 | 6.Failed router install | AM |  | 2024-06-19 | 2024-06-19 | 2024-06-19 | TRUE |  |  |  | 2024-07-24 |  |  |  | 2024-07-24 | 242005008813 |  | 2024-07-25 | 1
591 | 671342 | 1682 | Batch 4 Jun24 | Type 1 | SoGEA/Mobile | Spar Samani Monmouth | MONMOUTH | NP25 5BQ | 2024-06-07 | 28/08/2024:Order Completed on 23/08/2024 27/8/2024:#Update - ECC's approved. Awaiting arrangement of OOH engineer from OR for appointed date. 22/8/2024:#Update - ECC's approved. Awaiting arrangement of OOH engineer from OR for appointed date. 21/8/2024:#Update - ECC's approved. Awaiting arrangement of OOH engineer from OR for appointed date. 20/8/2024:#Update - ECC's approved. Awaiting arrangement of OOH engineer from OR for appointed date. 19/8/2024:#Update - ECC's approved. Awaiting arrangement of OOH engineer from OR for appointed date. 19/8/2024:01444133 16/8/2024:#Update - ECC's approved. Awaiting arrangement of OOH engineer from OR for appointed date. 15/8/2024:#Update order has been re-raised for the new store name for 23/08 (AM) 14/8/2024:#Update order has been re-raised for the new store name for 23/08 (AM) 13/8/2024:#Update order has been re-raised for the new store name for 23/08 (AM) 12/8/2024:#Update order has been re-raised for the new store name for 23/08 (AM) 9/8/2024:#Update order has been re-raised for the new store name for 23/08 (AM) 8/8/2024:07/08/2024 6/8/2024:20/06/2024 5/8/2024:20/06/2024 2/8/2024:20/06/2024 31/7/2024:20/06/2024 31/7/2024:20/06/2024 30/7/2024:#Update- 30m cabling, OOH internal works required. Awaiting approval of upgrade to premium. 29/7/2024:#Update- 30m cabling, OOH internal works required. Awaiting approval of upgrade to premium. 29/7/2024:01444133 26/7/2024:01444133 24/7/2024:#Update- 30m cabling, OOH internal works required. Awaiting approval of upgrade to premium. 23/7/2024:#Update- 30m cabling, OOH internal works required. Awaiting approval of upgrade to premium. 22/7/2024:#Update- 30m cabling, OOH internal works required. Awaiting approval of upgrade to premium. 22/7/2024:#Update- 30m cabling, OOH internal works required. Awaiting approval of upgrade to premium. 20/6/2024:Order Completed 19/6/2024:Order Completed 18/6/2024:0 17/6/2024:0 14/6/2024:0 13/6/2024:0 12/6/2024:0 10/6/2024:0 7/6/2024:0 6/6/2024:0 5/6/2024:0 4/6/2024:0 31/5/2024:0 30/5/2024:0 29/5/2024:0 28/5/2024:0 10/5/2024:0 02/05/2024: New order added to report | 28/08/2024:Order Completed on 23/08/2024 27/8/2024:#Update - ECC's approved. Awaiting arrangement of OOH engineer from OR for appointed date. 22/8/2024:#Update - ECC's approved. Awaiting arrangement of OOH engineer from OR for appointed date. 21/8/2024:#Update - ECC's approved. Awaiting arrangement of OOH engineer from OR for appointed date. 20/8/2024:#Update - ECC's approved. Awaiting arrangement of OOH engineer from OR for appointed date. 19/8/2024:#Update - ECC's approved. Awaiting arrangement of OOH engineer from OR for appointed date. 19/8/2024:01444133 16/8/2024:#Update - ECC's approved. Awaiting arrangement of OOH engineer from OR for appointed date. 15/8/2024:#Update order has been re-raised for the new store name for 23/08 (AM) 14/8/2024:#Update order has been re-raised for the new store name for 23/08 (AM) 13/8/2024:#Update order has been re-raised for the new store name for 23/08 (AM) 12/8/2024:#Update order has been re-raised for the new store name for 23/08 (AM) 9/8/2024:#Update order has been re-raised for the new store name for 23/08 (AM) 8/8/2024:07/08/2024 6/8/2024:20/06/2024 5/8/2024:20/06/2024 2/8/2024:20/06/2024 31/7/2024:20/06/2024 31/7/2024:20/06/2024 30/7/2024:#Update- 30m cabling, OOH internal works required. Awaiting approval of upgrade to premium. 29/7/2024:#Update- 30m cabling, OOH internal works required. Awaiting approval of upgrade to premium. 29/7/2024:01444133 26/7/2024:01444133 24/7/2024:#Update- 30m cabling, OOH internal works required. Awaiting approval of upgrade to premium. 23/7/2024:#Update- 30m cabling, OOH internal works required. Awaiting approval of upgrade to premium. 22/7/2024:#Update- 30m cabling, OOH internal works required. Awaiting approval of upgrade to premium. 22/7/2024:#Update- 30m cabling, OOH internal works required. Awaiting approval of upgrade to premium. 20/6/2024:Order Completed 19/6/2024:Order Completed 18/6/2024:0 17/6/2024:0 14/6/2024:0 13/6/2024:0 12/6/2024:0 10/6/2024:0 7/6/2024:0 6/6/2024:0 5/6/2024:0 4/6/2024:0 31/5/2024:0 30/5/2024:0 29/5/2024:0 28/5/2024:0 10/5/2024:0 02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFS984843 | 30015509 | 2.Commissioning | AM |  | 2024-06-19 | 2024-08-23 |  | 0 | [11 empty] | 0 | 671342
592 | 672612 | 1684 | Batch 4 Jun24 | Type 1 | SOGEA | SPAR | SALTASH | PL12 4JY | 2024-06-07 | 20/6/2024:Order Completed _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 20/6/2024:Order Completed _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984844 | 30015642 | 2.Commissioning | AM |  | 2024-06-19 | 2024-06-19 | 2024-06-19 | TRUE |  |  |  | 2024-07-10 | [7 empty] | 0
593 | 672615 | 1685 | Batch 4 Jun24 | Type 1 | FTTP | SPAR | BODMIN | PL31 1NR | 2024-06-07 | 20/6/2024:Order Completed _x000D_19/6/2024:Update: Order Completed by Supplier _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 20/6/2024:Order Completed _x000D_19/6/2024:Update: Order Completed by Supplier _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2338588 | 30015372 | 2.Commissioning | AM |  | 2024-06-19 | 2024-06-19 | 2024-06-19 | TRUE |  |  |  | 2024-07-10 | [7 empty] | 0
594 | 669992 | 1687 | Batch 4 Jun24 | Type 3 | SoGEA/Mobile | SPAR LIVERPOOL ROAD | SOUTHPORT | PR8 4PL | 2024-06-07 | 6/9/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_5/9/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_4/9/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_3/9/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_2/9/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_29/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_28/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_27/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_22/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_21/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_20/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_19/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_19/8/2024:01444286 _x000D_16/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_15/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_14/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_13/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_12/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_9/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_8/8/2024:01/08/2024 _x000D_6/8/2024:01/08/2024 _x000D_5/8/2024:01/08/2024 _x000D_2/8/2024:01/08/2024 _x000D_1/8/2024:05/07/2024 _x000D_31/7/2024:05/07/2024 _x000D_31/7/2024:05/07/2024 _x000D_30/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_29/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_29/7/2024:01444286 _x000D_26/7/2024:01444286 _x000D_24/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_23/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_22/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_22/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_20/6/2024:Order Completed _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 9/9/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_6/9/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_5/9/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_4/9/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_3/9/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_2/9/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_29/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_28/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_27/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_22/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_21/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_20/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_19/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_19/8/2024:01444286 _x000D_16/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_15/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_14/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_13/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_12/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_9/8/2024:#Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled _x000D_8/8/2024:01/08/2024 _x000D_6/8/2024:01/08/2024 _x000D_5/8/2024:01/08/2024 _x000D_2/8/2024:01/08/2024 _x000D_1/8/2024:05/07/2024 _x000D_31/7/2024:05/07/2024 _x000D_31/7/2024:05/07/2024 _x000D_30/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_29/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_29/7/2024:01444286 _x000D_26/7/2024:01444286 _x000D_24/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_23/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_22/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_22/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_20/6/2024:Order Completed _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 0 | #Update - Allwyn have requested this site moves from a site type 1 to a site type 3. The fixed line order has now been cancelled | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984846 | 30015435 | 2.Commissioning | AM | [8 empty] | 2024-08-22 | [7 empty] | 0
595 | 483588 | 1688 | Batch 4 Jun24 | Type 1 | SOGEA | SPAR | Rotherham | S66 7NG | 2024-06-07 | 19/7/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_18/7/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_17/7/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_16/7/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_15/7/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_12/7/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_11/7/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_10/7/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_9/7/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_4/7/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_3/7/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_27/6/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_25/6/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_24/6/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_20/6/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_19/6/2024:End User Missed appointment. Action required _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 19/7/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_18/7/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_17/7/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_16/7/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_15/7/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_12/7/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_11/7/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_10/7/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_9/7/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_4/7/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_3/7/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_27/6/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_25/6/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_24/6/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_20/6/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_19/6/2024:End User Missed appointment. Action required _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984848 | 30015625 | 2.Commissioning | AM |  | 2024-06-19 | 2024-06-19 | 2024-06-19 | TRUE |  |  |  | 2024-07-20 | [7 empty] | 0
596 | 486405 | 1689 | Batch 4 Jun24 | Type 1 | SoGEA/Mobile | SPAR ABERAVON | PORT TALBOT | SA12 6TT | 2024-06-07 | 6/9/2024:#Update - awaiting ECC approval - sent to VF on 10/07 _x000D_5/9/2024:#Update - awaiting ECC approval - sent to VF on 10/07 _x000D_4/9/2024:#Update - awaiting ECC approval - sent to VF on 10/07 _x000D_3/9/2024:#Update - awaiting ECC approval - sent to VF on 10/07 _x000D_2/9/2024:#Update - awaiting ECC approval - sent to VF on 10/07 _x000D_29/8/2024:#Update - awaiting ECC approval - sent to VF on 10/07 _x000D_28/8/2024:#Update - awaiting ECC approval - sent to VF on 10/07 _x000D_27/8/2024:#Update - awaiting ECC approval - sent to VF on 10/07 _x000D_22/8/2024:#Update - awaiting ECC approval - sent to VF on 10/07 _x000D_21/8/2024:#Update - awaiting ECC approval - sent to VF on 10/07 _x000D_20/8/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_19/8/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_19/8/2024:01444262 _x000D_16/8/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_15/8/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_14/8/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_13/8/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_12/8/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_9/8/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_8/8/2024:20/06/2024 _x000D_6/8/2024:20/06/2024 _x000D_5/8/2024:20/06/2024 _x000D_2/8/2024:20/06/2024 _x000D_1/8/2024:20/06/2024 _x000D_31/7/2024:20/06/2024 _x000D_31/7/2024:20/06/2024 _x000D_30/7/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_29/7/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_29/7/2024:01444262 _x000D_26/7/2024:01444262 _x000D_24/7/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_23/7/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_22/7/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_22/7/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 9/9/2024:#Update - awaiting ECC approval - sent to VF on 10/07 _x000D_6/9/2024:#Update - awaiting ECC approval - sent to VF on 10/07 _x000D_5/9/2024:#Update - awaiting ECC approval - sent to VF on 10/07 _x000D_4/9/2024:#Update - awaiting ECC approval - sent to VF on 10/07 _x000D_3/9/2024:#Update - awaiting ECC approval - sent to VF on 10/07 _x000D_2/9/2024:#Update - awaiting ECC approval - sent to VF on 10/07 _x000D_29/8/2024:#Update - awaiting ECC approval - sent to VF on 10/07 _x000D_28/8/2024:#Update - awaiting ECC approval - sent to VF on 10/07 _x000D_27/8/2024:#Update - awaiting ECC approval - sent to VF on 10/07 _x000D_22/8/2024:#Update - awaiting ECC approval - sent to VF on 10/07 _x000D_21/8/2024:#Update - awaiting ECC approval - sent to VF on 10/07 _x000D_20/8/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_19/8/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_19/8/2024:01444262 _x000D_16/8/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_15/8/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_14/8/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_13/8/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_12/8/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_9/8/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_8/8/2024:20/06/2024 _x000D_6/8/2024:20/06/2024 _x000D_5/8/2024:20/06/2024 _x000D_2/8/2024:20/06/2024 _x000D_1/8/2024:20/06/2024 _x000D_31/7/2024:20/06/2024 _x000D_31/7/2024:20/06/2024 _x000D_30/7/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_29/7/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_29/7/2024:01444262 _x000D_26/7/2024:01444262 _x000D_24/7/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_23/7/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_22/7/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_22/7/2024:#Update - installation unsuccessful - requires an upgrade, awaiting OR update to provide further scope of work _x000D_20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 0 | #Update - awaiting ECC approval - sent to VF on 10/07 | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFS984847 | 30015378 | 1.Provisioning | AM |  | 2024-06-19 | 2024-08-29 |  | 0 | [11 empty] | 0
597 | 250841 | 1690 | Batch 4 Jun24 | Type 1 | SOGEA | SPAR NEWTOWN | Newtown | SY16 2AY | 2024-06-07 | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984849 | 30015404 | 6.Failed router install | AM |  | 2024-06-19 | 2024-06-19 | 2024-06-19 | TRUE |  |  |  | 2024-07-18 |  |  |  | 2024-07-18 | 242005008823 |  | 2024-07-19 | 1
598 | 465149 | 1692 | Batch 4 Jun24 | Type 1 | FTTP | SPAR BURY ST EDMUNDS | BURY ST. EDMUNDS | IP32 6SP | 2024-06-07 | 20/6/2024:Order Completed _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 20/6/2024:Order Completed _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2338589 | 30015437 | 2.Commissioning | AM |  | 2024-06-19 | 2024-06-19 | 2024-06-19 | TRUE |  |  |  | 2024-07-10 | [7 empty] | 0
599 | 469259 | 1694 | Batch 4 Jun24 | Type 1 | SOGEA | Spar | St Andrews | KY16 8EL | 2024-06-07 | 20/6/2024:Order Completed _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 20/6/2024:Order Completed _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984851 | 30015662 | 2.Commissioning | AM |  | 2024-06-19 | 2024-06-19 | 2024-06-19 | TRUE |  |  |  | 2024-07-24 | [7 empty] | 0
600 | 654682 | 1695 | Batch 4 Jun24 | Type 1 | SOGEA | Spar | Witney | OX29 4NL | 2024-06-07 | 20/6/2024:Order Completed _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 20/6/2024:Order Completed _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984853 | 30015390 | 6.Failed router install | AM |  | 2024-06-19 | 2024-06-19 | 2024-06-19 | TRUE |  |  |  | 2024-07-05 |  |  |  | 2024-07-05 | 242005008522 |  |  | 1
601 | 465424 | 1699 | Batch 4 Jun24 | Type 1 | FTTP/Mobile | SPAR BRUNSWICK ROAD | BUCKLEY | CH7 2ED | 2024-06-07 | 6/9/2024:#Update - Supplier delay - review date of 16/09/2024. We will continue to provide update as they become available. _x000D_5/9/2024:#Update- OOH was approved but this order was unexpectedly cancelled down. I have re-raised the order. _x000D_4/9/2024:#Update- OOH was approved but this order was unexpectedly cancelled down. I have re-raised the order. _x000D_3/9/2024:#Update- OOH was approved but this order was unexpectedly cancelled down. I have re-raised the order. _x000D_2/9/2024:#Update- OOH was approved but this order was unexpectedly cancelled down. I have re-raised the order. _x000D_29/8/2024:#Update- OOH was approved but this order was unexpectedly cancelled down. I have re-raised the order. _x000D_28/8/2024:#Update- OOH was approved but this order was unexpectedly cancelled down. I have re-raised the order. _x000D_27/8/2024:#Update- OOH was approved but this order was unexpectedly cancelled down. I have re-raised the order. _x000D_22/8/2024:#Update- OOH was approved but this order was unexpectedly cancelled down. I have re-raised the order. _x000D_21/8/2024:#Update- OOH was approved but this order was unexpectedly cancelled down. I have re-raised the order. _x000D_20/8/2024:#Update- OOH was approved but this order was unexpectedly cancelled down. I have re-raised the order. _x000D_19/8/2024:#Update - this order is currently delayed due to external network required to be built so that new lines can be provided. This job is with the survey team and further updates will follow accordingly _x000D_19/8/2024:01444866 _x000D_16/8/2024:#Update - this order is currently delayed due to external network required to be built so that new lines can be provided. This job is with the survey team and further updates will follow accordingly _x000D_15/8/2024:#Update - this order is currently delayed due to external network required to be built so that new lines can be provided. This job is with the survey team and further updates will follow accordingly _x000D_14/8/2024:#Update - this order is currently delayed due to external network required to be built so that new lines can be provided. This job is with the survey team and further updates will follow accordingly _x000D_13/8/2024:#Update - this order is currently delayed due to external network required to be built so that new lines can be provided. This job is with the survey team and further updates will follow accordingly _x000D_12/8/2024:#Update - this order is currently delayed due to external network required to be built so that new lines can be provided. This job is with the survey team and further updates will follow accordingly _x000D_9/8/2024:#Update - this order is currently delayed due to external network required to be built so that new lines can be provided. This job is with the survey team and further updates will follow accordingly _x000D_8/8/2024:05/08/2024 _x000D_6/8/2024:05/08/2024 _x000D_5/8/2024:05/08/2024 _x000D_2/8/2024:31/07/2024 _x000D_1/8/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_30/7/2024:#Update - OOH Approved- Awaiting confirmation from OR for which date an engineer can be assigned for a Sunday AM appointment. Will appoint for this date. _x000D_29/7/2024:#Update - OOH Approved- Awaiting confirmation from OR for which date an engineer can be assigned for a Sunday AM appointment. Will appoint for this date. _x000D_29/7/2024:01444866 _x000D_26/7/2024:01444866 _x000D_24/7/2024:#Update - OOH Approved- Awaiting confirmation from OR for which date an engineer can be assigned for a Sunday AM appointment. Will appoint for this date. _x000D_23/7/2024:#Update - OOH Approved- Awaiting confirmation from OR for which date an engineer can be assigned for a Sunday AM appointment. Will appoint for this date. _x000D_22/7/2024:#Update - OOH Approved- Awaiting confirmation from OR for which date an engineer can be assigned for a Sunday AM appointment. Will appoint for this date. _x000D_22/7/2024:#Update - OOH Approved- Awaiting confirmation from OR for which date an engineer can be assigned for a Sunday AM appointment. Will appoint for this date. _x000D_20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 9/9/2024:#Update - Supplier delay - review date of 16/09/2024. We will continue to provide update as they become available. _x000D_6/9/2024:#Update - Supplier delay - review date of 16/09/2024. We will continue to provide update as they become available. _x000D_5/9/2024:#Update- OOH was approved but this order was unexpectedly cancelled down. I have re-raised the order. _x000D_4/9/2024:#Update- OOH was approved but this order was unexpectedly cancelled down. I have re-raised the order. _x000D_3/9/2024:#Update- OOH was approved but this order was unexpectedly cancelled down. I have re-raised the order. _x000D_2/9/2024:#Update- OOH was approved but this order was unexpectedly cancelled down. I have re-raised the order. _x000D_29/8/2024:#Update- OOH was approved but this order was unexpectedly cancelled down. I have re-raised the order. _x000D_28/8/2024:#Update- OOH was approved but this order was unexpectedly cancelled down. I have re-raised the order. _x000D_27/8/2024:#Update- OOH was approved but this order was unexpectedly cancelled down. I have re-raised the order. _x000D_22/8/2024:#Update- OOH was approved but this order was unexpectedly cancelled down. I have re-raised the order. _x000D_21/8/2024:#Update- OOH was approved but this order was unexpectedly cancelled down. I have re-raised the order. _x000D_20/8/2024:#Update- OOH was approved but this order was unexpectedly cancelled down. I have re-raised the order. _x000D_19/8/2024:#Update - this order is currently delayed due to external network required to be built so that new lines can be provided. This job is with the survey team and further updates will follow accordingly _x000D_19/8/2024:01444866 _x000D_16/8/2024:#Update - this order is currently delayed due to external network required to be built so that new lines can be provided. This job is with the survey team and further updates will follow accordingly _x000D_15/8/2024:#Update - this order is currently delayed due to external network required to be built so that new lines can be provided. This job is with the survey team and further updates will follow accordingly _x000D_14/8/2024:#Update - this order is currently delayed due to external network required to be built so that new lines can be provided. This job is with the survey team and further updates will follow accordingly _x000D_13/8/2024:#Update - this order is currently delayed due to external network required to be built so that new lines can be provided. This job is with the survey team and further updates will follow accordingly _x000D_12/8/2024:#Update - this order is currently delayed due to external network required to be built so that new lines can be provided. This job is with the survey team and further updates will follow accordingly _x000D_9/8/2024:#Update - this order is currently delayed due to external network required to be built so that new lines can be provided. This job is with the survey team and further updates will follow accordingly _x000D_8/8/2024:05/08/2024 _x000D_6/8/2024:05/08/2024 _x000D_5/8/2024:05/08/2024 _x000D_2/8/2024:31/07/2024 _x000D_1/8/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_30/7/2024:#Update - OOH Approved- Awaiting confirmation from OR for which date an engineer can be assigned for a Sunday AM appointment. Will appoint for this date. _x000D_29/7/2024:#Update - OOH Approved- Awaiting confirmation from OR for which date an engineer can be assigned for a Sunday AM appointment. Will appoint for this date. _x000D_29/7/2024:01444866 _x000D_26/7/2024:01444866 _x000D_24/7/2024:#Update - OOH Approved- Awaiting confirmation from OR for which date an engineer can be assigned for a Sunday AM appointment. Will appoint for this date. _x000D_23/7/2024:#Update - OOH Approved- Awaiting confirmation from OR for which date an engineer can be assigned for a Sunday AM appointment. Will appoint for this date. _x000D_22/7/2024:#Update - OOH Approved- Awaiting confirmation from OR for which date an engineer can be assigned for a Sunday AM appointment. Will appoint for this date. _x000D_22/7/2024:#Update - OOH Approved- Awaiting confirmation from OR for which date an engineer can be assigned for a Sunday AM appointment. Will appoint for this date. _x000D_20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 16/09/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received | #Update - Supplier delay - review date of 16/09/2024. We will continue to provide update as they become available. | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFP2338591 | 30015488 | 1.Provisioning | AM |  | 2024-06-19 | 2024-07-29 |  | 0 | [11 empty] | 0
602 | 616145 | 1701 | Batch 4 Jun24 | Type 1 | SOGEA | Spar | BELFAST | BT10 0LN | 2024-06-07 | 20/6/2024:#Update - this order is in delay due to Frames Complications, we will share update accordingly _x000D_19/6/2024:#Update - this order is in delay due to Frames Complications, we will share update accordingly _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 20/6/2024:#Update - this order is in delay due to Frames Complications, we will share update accordingly _x000D_19/6/2024:#Update - this order is in delay due to Frames Complications, we will share update accordingly _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984781 | 30015330 | 6.Failed router install | AM |  | 2024-06-19 | 2024-06-19 | 2024-06-19 | TRUE |  |  |  | 2024-07-18 |  |  |  | 2024-07-18 | 242005010318 |  | 2024-07-23 | 1
603 | 664310 | 1718 | Batch 4 Jun24 | Type 1 | FTTP | Spar Stores | Londonderry | BT47 6DE | 2024-06-07 | 24/6/2024:#Update - Engineer has retained job for tomorrow - 20/06 _x000D_20/6/2024:#Update - Engineer has retained job for tomorrow - 20/06 _x000D_19/6/2024:#Update - Engineer has retained job for tomorrow - 20/06 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 24/6/2024:#Update - Engineer has retained job for tomorrow - 20/06 _x000D_20/6/2024:#Update - Engineer has retained job for tomorrow - 20/06 _x000D_19/6/2024:#Update - Engineer has retained job for tomorrow - 20/06 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2337288 | 30015151 | 2.Commissioning | AM |  | 2024-06-19 | 2024-06-19 | 2024-06-19 | TRUE |  |  |  | 2024-07-22 | [7 empty] | 0
604 | 471482 | 1731 | Batch 4 Jun24 | Type 1 | FTTP | COSTCUTTER | Bridlington | YO15 3DZ | 2024-06-07 | 20/6/2024:Order Completed _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 20/6/2024:Order Completed _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983272 | 30015199 | 6.Failed router install | AM |  | 2024-06-19 | 2024-06-19 | 2024-06-20 | TRUE |  |  |  | 2024-07-19 |  |  |  | 2024-07-19 | 238004926111 |  | 2024-07-23 | 1
605 | 671229 | 1747 | Batch 4 Jun24 | Type 1 | FTTP/Mobile | Nearby | Belfast | BT5 5FP | 2024-06-07 | 6/9/2024:#Update - Pushed out for 12/08 _x000D_5/9/2024:#Update - Pushed out for 12/08 _x000D_4/9/2024:#Update - Pushed out for 12/08 _x000D_3/9/2024:#Update - Pushed out for 12/08 _x000D_2/9/2024:#Update - Pushed out for 12/08 _x000D_29/8/2024:#Update - Pushed out for 12/08 _x000D_28/8/2024:#Update - Pushed out for 12/08 _x000D_27/8/2024:#Update - Pushed out for 12/08 _x000D_22/8/2024:#Update - Pushed out for 12/08 _x000D_21/8/2024:#Update - Pushed out for 12/08 _x000D_20/8/2024:#Update - Pushed out for 12/08 _x000D_19/8/2024:#Update - Pushed out for 12/08 _x000D_19/8/2024:01463475 _x000D_16/8/2024:#Update - Pushed out for 12/08 _x000D_15/8/2024:#Update - Pushed out for 12/08 _x000D_14/8/2024:#Update - Pushed out for 12/08 _x000D_13/8/2024:#Update - Pushed out for 12/08 _x000D_12/8/2024:#Update - Pushed out for 12/08 _x000D_9/8/2024:#Update - Pushed out for 12/08 _x000D_8/8/2024:17/07/2024 _x000D_6/8/2024:17/07/2024 _x000D_5/8/2024:17/07/2024 _x000D_2/8/2024:17/07/2024 _x000D_31/7/2024:17/07/2024 _x000D_31/7/2024:17/07/2024 _x000D_30/7/2024:#Update - Pushed out for 12/08 _x000D_29/7/2024:#Update - Pushed out for 12/08 _x000D_29/7/2024:01463475 _x000D_26/7/2024:01463475 _x000D_24/7/2024:#Update - Pushed out for 12/08 _x000D_23/7/2024:#Update - Pushed out for 12/08 _x000D_22/7/2024:#Update - Pushed out for 12/08 _x000D_22/7/2024:#Update - Pushed out for 12/08 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:Update: Order Amended _x000D_15/7/2024:Update: Order Amended _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:Update: Order Amended _x000D_20/6/2024:Update: Order Amended _x000D_19/6/2024:Update: Order Amended _x000D_18/6/2024:Update: Order Amended _x000D_17/6/2024:0 _x000D_14/6/2024:Supplier Delay: Delay encountered during automated test of new service _x000D_13/6/2024:Supplier Delay: Delay encountered during automated test of new service _x000D_12/6/2024:Supplier Delay: Delay encountered during automated test of new service _x000D_10/6/2024:Supplier Delay: Delay encountered during automated test of new service _x000D_7/6/2024:Update: Order Amended _x000D_6/6/2024:Update: Order Amended _x000D_5/6/2024:Update: Order Amended _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 9/9/2024:#Update - Pushed out for 12/08 _x000D_6/9/2024:#Update - Pushed out for 12/08 _x000D_5/9/2024:#Update - Pushed out for 12/08 _x000D_4/9/2024:#Update - Pushed out for 12/08 _x000D_3/9/2024:#Update - Pushed out for 12/08 _x000D_2/9/2024:#Update - Pushed out for 12/08 _x000D_29/8/2024:#Update - Pushed out for 12/08 _x000D_28/8/2024:#Update - Pushed out for 12/08 _x000D_27/8/2024:#Update - Pushed out for 12/08 _x000D_22/8/2024:#Update - Pushed out for 12/08 _x000D_21/8/2024:#Update - Pushed out for 12/08 _x000D_20/8/2024:#Update - Pushed out for 12/08 _x000D_19/8/2024:#Update - Pushed out for 12/08 _x000D_19/8/2024:01463475 _x000D_16/8/2024:#Update - Pushed out for 12/08 _x000D_15/8/2024:#Update - Pushed out for 12/08 _x000D_14/8/2024:#Update - Pushed out for 12/08 _x000D_13/8/2024:#Update - Pushed out for 12/08 _x000D_12/8/2024:#Update - Pushed out for 12/08 _x000D_9/8/2024:#Update - Pushed out for 12/08 _x000D_8/8/2024:17/07/2024 _x000D_6/8/2024:17/07/2024 _x000D_5/8/2024:17/07/2024 _x000D_2/8/2024:17/07/2024 _x000D_31/7/2024:17/07/2024 _x000D_31/7/2024:17/07/2024 _x000D_30/7/2024:#Update - Pushed out for 12/08 _x000D_29/7/2024:#Update - Pushed out for 12/08 _x000D_29/7/2024:01463475 _x000D_26/7/2024:01463475 _x000D_24/7/2024:#Update - Pushed out for 12/08 _x000D_23/7/2024:#Update - Pushed out for 12/08 _x000D_22/7/2024:#Update - Pushed out for 12/08 _x000D_22/7/2024:#Update - Pushed out for 12/08 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:Update: Order Amended _x000D_15/7/2024:Update: Order Amended _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:Update: Order Amended _x000D_20/6/2024:Update: Order Amended _x000D_19/6/2024:Update: Order Amended _x000D_18/6/2024:Update: Order Amended _x000D_17/6/2024:0 _x000D_14/6/2024:Supplier Delay: Delay encountered during automated test of new service _x000D_13/6/2024:Supplier Delay: Delay encountered during automated test of new service _x000D_12/6/2024:Supplier Delay: Delay encountered during automated test of new service _x000D_10/6/2024:Supplier Delay: Delay encountered during automated test of new service _x000D_7/6/2024:Update: Order Amended _x000D_6/6/2024:Update: Order Amended _x000D_5/6/2024:Update: Order Amended _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 0 | #Update - Pushed out for 12/08 | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFP2337303 | 30015159 | 2.Commissioning | AM |  | 2024-06-19 | 2024-08-12 | 2024-08-12 13:09 | 1 | [11 empty] | 0 | 671229
606 | 668587 | 1876 | Batch 4 Jun24 | Type 1 | FTTP/Mobile | Twickenham Drive Supermarket | Wirral | CH46 2QE | 2024-06-07 | 6/9/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_5/9/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_4/9/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_3/9/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_2/9/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_29/8/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_28/8/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_27/8/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_22/8/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_21/8/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_20/8/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_19/8/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_19/8/2024:01381907 _x000D_16/8/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_15/8/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_14/8/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_13/8/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_12/8/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_9/8/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_8/8/2024:18/07/2024 _x000D_6/8/2024:18/07/2024 _x000D_5/8/2024:18/07/2024 _x000D_2/8/2024:18/07/2024 _x000D_1/8/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_30/7/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_29/7/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_29/7/2024:01381907 _x000D_26/7/2024:01381907 _x000D_24/7/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_23/7/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_22/7/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_22/7/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_20/6/2024:Order Completed _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 9/9/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_6/9/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_5/9/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_4/9/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_3/9/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_2/9/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_29/8/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_28/8/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_27/8/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_22/8/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_21/8/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_20/8/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_19/8/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_19/8/2024:01381907 _x000D_16/8/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_15/8/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_14/8/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_13/8/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_12/8/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_9/8/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_8/8/2024:18/07/2024 _x000D_6/8/2024:18/07/2024 _x000D_5/8/2024:18/07/2024 _x000D_2/8/2024:18/07/2024 _x000D_1/8/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_30/7/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_29/7/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_29/7/2024:01381907 _x000D_26/7/2024:01381907 _x000D_24/7/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_23/7/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_22/7/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_22/7/2024:#Update - awaiting advanced upgrade and OOH request feedback _x000D_20/6/2024:Order Completed _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | Update: Order Amended | #Update - awaiting advanced upgrade and OOH request feedback | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFP2360292 | 30015774 | 1.Provisioning | AM |  | 2024-06-04 | 2024-09-04 |  | 0 | [11 empty] | 0
607 | 661292 | 3002 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Nisa Local J&N Superfoods | Wednesfield | WV11 1BH |  | 9/8/2024:#Update - Order cancelled and re-raised. _x000D_8/8/2024:04/07/2024 _x000D_6/8/2024:04/07/2024 _x000D_5/8/2024:04/07/2024 _x000D_2/8/2024:04/07/2024 _x000D_1/8/2024:04/07/2024 _x000D_31/7/2024:04/07/2024 _x000D_31/7/2024:04/07/2024 _x000D_30/7/2024:#Update - Order cancelled and re-raised. _x000D_29/7/2024:#Update - Order cancelled and re-raised. _x000D_29/7/2024:01444198 _x000D_26/7/2024:01444198 _x000D_24/7/2024:#Update - Order cancelled and re-raised. _x000D_23/7/2024:#Update - Order cancelled and re-raised. _x000D_22/7/2024:#Update - Order cancelled and re-raised. _x000D_22/7/2024:#Update - Order cancelled and re-raised. _x000D_20/6/2024:Order Completed _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/8/2024:#Update - Order cancelled and re-raised. _x000D_8/8/2024:04/07/2024 _x000D_6/8/2024:04/07/2024 _x000D_5/8/2024:04/07/2024 _x000D_2/8/2024:04/07/2024 _x000D_1/8/2024:04/07/2024 _x000D_31/7/2024:04/07/2024 _x000D_31/7/2024:04/07/2024 _x000D_30/7/2024:#Update - Order cancelled and re-raised. _x000D_29/7/2024:#Update - Order cancelled and re-raised. _x000D_29/7/2024:01444198 _x000D_26/7/2024:01444198 _x000D_24/7/2024:#Update - Order cancelled and re-raised. _x000D_23/7/2024:#Update - Order cancelled and re-raised. _x000D_22/7/2024:#Update - Order cancelled and re-raised. _x000D_22/7/2024:#Update - Order cancelled and re-raised. _x000D_20/6/2024:Order Completed _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015628 | 30016984 | 2.Commissioning |  |  | 2024-06-19 | 2024-08-05 | 2024-08-05 12:00 | TRUE |  |  |  | 2024-08-26 | [7 empty] | 0
608 | 668064 | 3003 | Batch 5 Jul24 | Type 1 | FTTP | Dallington Post Office | NORTHAMPTON | NN5 7EG |  | 19/7/2024:Update: Order Amended _x000D_18/7/2024:Update: Order Amended _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:0 _x000D_27/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect CRD Please check with end user and reappoint the order if still required. _x000D_25/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect CRD Please check with end user and reappoint the order if still required. _x000D_24/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect CRD Please check with end user and reappoint the order if still required. _x000D_20/6/2024:Update: Order Amended _x000D_19/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 19/7/2024:Update: Order Amended _x000D_18/7/2024:Update: Order Amended _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:0 _x000D_27/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect CRD Please check with end user and reappoint the order if still required. _x000D_25/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect CRD Please check with end user and reappoint the order if still required. _x000D_24/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect CRD Please check with end user and reappoint the order if still required. _x000D_20/6/2024:Update: Order Amended _x000D_19/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366039 | 30016969 | 6.Failed router install |  |  | 2024-06-19 | 2024-06-19 | 2024-06-19 | TRUE |  |  |  | 2024-07-12 |  |  |  | 2024-07-12 | 242005008627 |  | 2024-07-15 | 1
609 | 655996 | 3004 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Vel Murugan Enterprises | London | E6 1JD |  | 6/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 20/06 _x000D_5/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 20/06 _x000D_4/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 20/06 _x000D_3/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 20/06 _x000D_2/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 20/06 _x000D_29/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 20/06 _x000D_28/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 20/06 _x000D_27/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 20/06 _x000D_22/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 20/06 _x000D_21/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 20/06 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_20/6/2024:Order Completed _x000D_19/6/2024:Update: Order Completed by Supplier _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 20/06 _x000D_6/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 20/06 _x000D_5/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 20/06 _x000D_4/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 20/06 _x000D_3/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 20/06 _x000D_2/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 20/06 _x000D_29/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 20/06 _x000D_28/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 20/06 _x000D_27/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 20/06 _x000D_22/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 20/06 _x000D_21/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 20/06 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_20/6/2024:Order Completed _x000D_19/6/2024:Update: Order Completed by Supplier _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | #Update - awaiting ECC approval from customer - proposal sent to VF 20/06 | 2024-06-07 |  |  |  |  | VFS1015514 | 30017022 | 1.Provisioning | AM |  | 2024-06-19 | 2024-08-30 |  | 0 | [11 empty] | 0
610 | 665388 | 3006 | Batch 5 Jul24 | Type 1 | SOGEA | Lateshopper | SPALDING | PE11 2HX |  | 20/6/2024:Order Completed _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 20/6/2024:Order Completed _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015513 | 30016662 | 2.Commissioning |  |  | 2024-06-19 | 2024-06-19 | 2024-06-19 | TRUE |  |  |  | 2024-07-10 | [7 empty] | 0
611 | 486436 | 3015 | Batch 5 Jul24 | Type 3 | SoGEA/Mobile | SPAR CHATHAM | CHATHAM | ME5 0QX |  | 6/9/2024:#Update - Customer changed order to site type 3. No socket onsite _x000D_5/9/2024:#Update - Customer changed order to site type 3. No socket onsite _x000D_4/9/2024:#Update - Customer changed order to site type 3. No socket onsite _x000D_3/9/2024:#Update - Customer changed order to site type 3. No socket onsite _x000D_2/9/2024:#Update - Customer changed order to site type 3. No socket onsite _x000D_29/8/2024:#Update - Customer changed order to site type 3. No socket onsite _x000D_28/8/2024:#Update - Customer changed order to site type 3. No socket onsite _x000D_27/8/2024:#Update - Customer changed order to site type 3. No socket onsite _x000D_22/8/2024:#Update - Needs upgrade, 6hrs OOh, & 2 engineers. Waiting to hear back from OR about instruction for retailer to potentially remove panels prior to engineer visit. Will send proposal to Alwyn once I can understand the notes. _x000D_21/8/2024:#Update - Needs upgrade, 6hrs OOh, & 2 engineers. Waiting to hear back from OR about instruction for retailer to potentially remove panels prior to engineer visit. Will send proposal to Alwyn once I can understand the notes. _x000D_20/8/2024:#Update - Needs upgrade, 6hrs OOh, & 2 engineers. Waiting to hear back from OR about instruction for retailer to potentially remove panels prior to engineer visit. Will send proposal to Alwyn once I can understand the notes. _x000D_19/8/2024:#Update - Needs upgrade, 6hrs OOh, & 2 engineers. Waiting to hear back from OR about instruction for retailer to potentially remove panels prior to engineer visit. Will send proposal to Alwyn once I can understand the notes. _x000D_19/8/2024:01444841 _x000D_16/8/2024:#Update - Needs upgrade, 6hrs OOh, & 2 engineers. Waiting to hear back from OR about instruction for retailer to potentially remove panels prior to engineer visit. Will send proposal to Alwyn once I can understand the notes. _x000D_15/8/2024:#Update - Needs upgrade, 6hrs OOh, & 2 engineers. Waiting to hear back from OR about instruction for retailer to potentially remove panels prior to engineer visit. Will send proposal to Alwyn once I can understand the notes. _x000D_14/8/2024:#Update - Needs upgrade, 6hrs OOh, & 2 engineers. Waiting to hear back from OR about instruction for retailer to potentially remove panels prior to engineer visit. Will send proposal to Alwyn once I can understand the notes. _x000D_13/8/2024:#Update - Needs upgrade, 6hrs OOh, & 2 engineers. Waiting to hear back from OR about instruction for retailer to potentially remove panels prior to engineer visit. Will send proposal to Alwyn once I can understand the notes. _x000D_12/8/2024:#Update - Needs upgrade, 6hrs OOh, & 2 engineers. Waiting to hear back from OR about instruction for retailer to potentially remove panels prior to engineer visit. Will send proposal to Alwyn once I can understand the notes. _x000D_9/8/2024:#Update - Needs upgrade, 6hrs OOh, & 2 engineers. Waiting to hear back from OR about instruction for retailer to potentially remove panels prior to engineer visit. Will send proposal to Alwyn once I can understand the notes. _x000D_8/8/2024:24/06/2024 _x000D_6/8/2024:24/06/2024 _x000D_5/8/2024:24/06/2024 _x000D_2/8/2024:24/06/2024 _x000D_1/8/2024:24/06/2024 _x000D_31/7/2024:24/06/2024 _x000D_31/7/2024:24/06/2024 _x000D_30/7/2024:#Update - Needs upgrade, 6hrs OOh, & 2 engineers. Waiting to hear back from OR about instruction for retailer to potentially remove panels prior to engineer visit. Will send proposal to Alwyn once I can understand the notes. _x000D_29/7/2024:#Update - Needs upgrade, 6hrs OOh, & 2 engineers. Waiting to hear back from OR about instruction for retailer to potentially remove panels prior to engineer visit. Will send proposal to Alwyn once I can understand the notes. _x000D_29/7/2024:01444841 _x000D_26/7/2024:01444841 _x000D_24/7/2024:#Update - Needs upgrade, 6hrs OOh, & 2 engineers. Waiting to hear back from OR about instruction for retailer to potentially remove panels prior to engineer visit. Will send proposal to Alwyn once I can understand the notes. _x000D_23/7/2024:#Update - Needs upgrade, 6hrs OOh, & 2 engineers. Waiting to hear back from OR about instruction for retailer to potentially remove panels prior to engineer visit. Will send proposal to Alwyn once I can understand the notes. _x000D_22/7/2024:#Update - Needs upgrade, 6hrs OOh, & 2 engineers. Waiting to hear back from OR about instruction for retailer to potentially remove panels prior to engineer visit. Will send proposal to Alwyn once I can understand the notes. _x000D_22/7/2024:#Update - Needs upgrade, 6hrs OOh, & 2 engineers. Waiting to hear back from OR about instruction for retailer to potentially remove panels prior to engineer visit. Will send proposal to Alwyn once I can understand the notes. _x000D_20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:#Update - Customer changed order to site type 3. No socket onsite _x000D_6/9/2024:#Update - Customer changed order to site type 3. No socket onsite _x000D_5/9/2024:#Update - Customer changed order to site type 3. No socket onsite _x000D_4/9/2024:#Update - Customer changed order to site type 3. No socket onsite _x000D_3/9/2024:#Update - Customer changed order to site type 3. No socket onsite _x000D_2/9/2024:#Update - Customer changed order to site type 3. No socket onsite _x000D_29/8/2024:#Update - Customer changed order to site type 3. No socket onsite _x000D_28/8/2024:#Update - Customer changed order to site type 3. No socket onsite _x000D_27/8/2024:#Update - Customer changed order to site type 3. No socket onsite _x000D_22/8/2024:#Update - Needs upgrade, 6hrs OOh, & 2 engineers. Waiting to hear back from OR about instruction for retailer to potentially remove panels prior to engineer visit. Will send proposal to Alwyn once I can understand the notes. _x000D_21/8/2024:#Update - Needs upgrade, 6hrs OOh, & 2 engineers. Waiting to hear back from OR about instruction for retailer to potentially remove panels prior to engineer visit. Will send proposal to Alwyn once I can understand the notes. _x000D_20/8/2024:#Update - Needs upgrade, 6hrs OOh, & 2 engineers. Waiting to hear back from OR about instruction for retailer to potentially remove panels prior to engineer visit. Will send proposal to Alwyn once I can understand the notes. _x000D_19/8/2024:#Update - Needs upgrade, 6hrs OOh, & 2 engineers. Waiting to hear back from OR about instruction for retailer to potentially remove panels prior to engineer visit. Will send proposal to Alwyn once I can understand the notes. _x000D_19/8/2024:01444841 _x000D_16/8/2024:#Update - Needs upgrade, 6hrs OOh, & 2 engineers. Waiting to hear back from OR about instruction for retailer to potentially remove panels prior to engineer visit. Will send proposal to Alwyn once I can understand the notes. _x000D_15/8/2024:#Update - Needs upgrade, 6hrs OOh, & 2 engineers. Waiting to hear back from OR about instruction for retailer to potentially remove panels prior to engineer visit. Will send proposal to Alwyn once I can understand the notes. _x000D_14/8/2024:#Update - Needs upgrade, 6hrs OOh, & 2 engineers. Waiting to hear back from OR about instruction for retailer to potentially remove panels prior to engineer visit. Will send proposal to Alwyn once I can understand the notes. _x000D_13/8/2024:#Update - Needs upgrade, 6hrs OOh, & 2 engineers. Waiting to hear back from OR about instruction for retailer to potentially remove panels prior to engineer visit. Will send proposal to Alwyn once I can understand the notes. _x000D_12/8/2024:#Update - Needs upgrade, 6hrs OOh, & 2 engineers. Waiting to hear back from OR about instruction for retailer to potentially remove panels prior to engineer visit. Will send proposal to Alwyn once I can understand the notes. _x000D_9/8/2024:#Update - Needs upgrade, 6hrs OOh, & 2 engineers. Waiting to hear back from OR about instruction for retailer to potentially remove panels prior to engineer visit. Will send proposal to Alwyn once I can understand the notes. _x000D_8/8/2024:24/06/2024 _x000D_6/8/2024:24/06/2024 _x000D_5/8/2024:24/06/2024 _x000D_2/8/2024:24/06/2024 _x000D_1/8/2024:24/06/2024 _x000D_31/7/2024:24/06/2024 _x000D_31/7/2024:24/06/2024 _x000D_30/7/2024:#Update - Needs upgrade, 6hrs OOh, & 2 engineers. Waiting to hear back from OR about instruction for retailer to potentially remove panels prior to engineer visit. Will send proposal to Alwyn once I can understand the notes. _x000D_29/7/2024:#Update - Needs upgrade, 6hrs OOh, & 2 engineers. Waiting to hear back from OR about instruction for retailer to potentially remove panels prior to engineer visit. Will send proposal to Alwyn once I can understand the notes. _x000D_29/7/2024:01444841 _x000D_26/7/2024:01444841 _x000D_24/7/2024:#Update - Needs upgrade, 6hrs OOh, & 2 engineers. Waiting to hear back from OR about instruction for retailer to potentially remove panels prior to engineer visit. Will send proposal to Alwyn once I can understand the notes. _x000D_23/7/2024:#Update - Needs upgrade, 6hrs OOh, & 2 engineers. Waiting to hear back from OR about instruction for retailer to potentially remove panels prior to engineer visit. Will send proposal to Alwyn once I can understand the notes. _x000D_22/7/2024:#Update - Needs upgrade, 6hrs OOh, & 2 engineers. Waiting to hear back from OR about instruction for retailer to potentially remove panels prior to engineer visit. Will send proposal to Alwyn once I can understand the notes. _x000D_22/7/2024:#Update - Needs upgrade, 6hrs OOh, & 2 engineers. Waiting to hear back from OR about instruction for retailer to potentially remove panels prior to engineer visit. Will send proposal to Alwyn once I can understand the notes. _x000D_20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | #Update - Customer changed order to site type 3. No socket onsite | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015621 | 30016825 | 2.Commissioning | AM |  |  |  |  | 0 |  |  |  | 2024-08-23 | [7 empty] | 0
612 | 469938 | 3016 | Batch 5 Jul24 | Type 1 | SOGEA | Nisa Extra | Liverpool | L28 1NR |  | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 20/6/2024:Order Completed _x000D_19/6/2024:Order Completed _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015620 | 30016620 | 2.Commissioning |  |  | 2024-06-19 | 2024-06-19 | 2024-06-19 | TRUE |  |  |  | 2024-07-11 | [7 empty] | 0
613 | 486607 | 496 | Batch 3 May24 | Type 1 | SoGEA/Mobile | Ocean | Tredegar | NP22 3EJ | 2024-05-30 | 6/9/2024:#Update - awaiting ECC approval from customer - sent to VF 03/06 _x000D_5/9/2024:#Update - awaiting ECC approval from customer - sent to VF 03/06 _x000D_4/9/2024:#Update - awaiting ECC approval from customer - sent to VF 03/06 _x000D_3/9/2024:#Update - awaiting ECC approval from customer - sent to VF 03/06 _x000D_2/9/2024:#Update - awaiting ECC approval from customer - sent to VF 03/06 _x000D_29/8/2024:#Update - awaiting ECC approval from customer - sent to VF 03/06 _x000D_28/8/2024:#Update - awaiting ECC approval from customer - sent to VF 03/06 _x000D_27/8/2024:#Update - awaiting ECC approval from customer - sent to VF 03/06 _x000D_22/8/2024:#Update - awaiting ECC approval from customer - sent to VF 03/06 _x000D_21/8/2024:#Update - awaiting ECC approval from customer - sent to VF 03/06 _x000D_20/8/2024:#Update - CSL have chased Openreach to obtain details of the OOH works that are required and will update accordingly _x000D_19/8/2024:#Update - CSL have chased Openreach to obtain details of the OOH works that are required and will update accordingly _x000D_19/8/2024:01409315 _x000D_16/8/2024:#Update - CSL have chased Openreach to obtain details of the OOH works that are required and will update accordingly _x000D_15/8/2024:#Update - CSL have chased Openreach to obtain details of the OOH works that are required and will update accordingly _x000D_14/8/2024:#Update - CSL have chased Openreach to obtain details of the OOH works that are required and will update accordingly _x000D_13/8/2024:#Update - CSL have chased Openreach to obtain details of the OOH works that are required and will update accordingly _x000D_12/8/2024:#Update - CSL have chased Openreach to obtain details of the OOH works that are required and will update accordingly _x000D_9/8/2024:#Update - CSL have chased Openreach to obtain details of the OOH works that are required and will update accordingly _x000D_8/8/2024:31/05/2024 _x000D_6/8/2024:31/05/2024 _x000D_5/8/2024:31/05/2024 _x000D_2/8/2024:31/05/2024 _x000D_1/8/2024:31/05/2024 _x000D_31/7/2024:31/05/2024 _x000D_31/7/2024:31/05/2024 _x000D_30/7/2024:#Update - CSL have chased Openreach to obtain details of the OOH works that are required and will update accordingly _x000D_29/7/2024:#Update - CSL have chased Openreach to obtain details of the OOH works that are required and will update accordingly _x000D_29/7/2024:01409315 _x000D_26/7/2024:01409315 _x000D_24/7/2024:#Update - CSL have chased Openreach to obtain details of the OOH works that are required and will update accordingly _x000D_23/7/2024:#Update - CSL have chased Openreach to obtain details of the OOH works that are required and will update accordingly _x000D_22/7/2024:#Update - CSL have chased Openreach to obtain details of the OOH works that are required and will update accordingly _x000D_22/7/2024:#Update - CSL have chased Openreach to obtain details of the OOH works that are required and will update accordingly _x000D_25/6/2024:Order Completed _x000D_24/6/2024:Order Completed _x000D_20/6/2024:Supplier Delay: Missed CCD and may require further work as the engineer has retained the job for next day _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:#Update - awaiting ECC approval from customer - sent to VF 03/06 _x000D_6/9/2024:#Update - awaiting ECC approval from customer - sent to VF 03/06 _x000D_5/9/2024:#Update - awaiting ECC approval from customer - sent to VF 03/06 _x000D_4/9/2024:#Update - awaiting ECC approval from customer - sent to VF 03/06 _x000D_3/9/2024:#Update - awaiting ECC approval from customer - sent to VF 03/06 _x000D_2/9/2024:#Update - awaiting ECC approval from customer - sent to VF 03/06 _x000D_29/8/2024:#Update - awaiting ECC approval from customer - sent to VF 03/06 _x000D_28/8/2024:#Update - awaiting ECC approval from customer - sent to VF 03/06 _x000D_27/8/2024:#Update - awaiting ECC approval from customer - sent to VF 03/06 _x000D_22/8/2024:#Update - awaiting ECC approval from customer - sent to VF 03/06 _x000D_21/8/2024:#Update - awaiting ECC approval from customer - sent to VF 03/06 _x000D_20/8/2024:#Update - CSL have chased Openreach to obtain details of the OOH works that are required and will update accordingly _x000D_19/8/2024:#Update - CSL have chased Openreach to obtain details of the OOH works that are required and will update accordingly _x000D_19/8/2024:01409315 _x000D_16/8/2024:#Update - CSL have chased Openreach to obtain details of the OOH works that are required and will update accordingly _x000D_15/8/2024:#Update - CSL have chased Openreach to obtain details of the OOH works that are required and will update accordingly _x000D_14/8/2024:#Update - CSL have chased Openreach to obtain details of the OOH works that are required and will update accordingly _x000D_13/8/2024:#Update - CSL have chased Openreach to obtain details of the OOH works that are required and will update accordingly _x000D_12/8/2024:#Update - CSL have chased Openreach to obtain details of the OOH works that are required and will update accordingly _x000D_9/8/2024:#Update - CSL have chased Openreach to obtain details of the OOH works that are required and will update accordingly _x000D_8/8/2024:31/05/2024 _x000D_6/8/2024:31/05/2024 _x000D_5/8/2024:31/05/2024 _x000D_2/8/2024:31/05/2024 _x000D_1/8/2024:31/05/2024 _x000D_31/7/2024:31/05/2024 _x000D_31/7/2024:31/05/2024 _x000D_30/7/2024:#Update - CSL have chased Openreach to obtain details of the OOH works that are required and will update accordingly _x000D_29/7/2024:#Update - CSL have chased Openreach to obtain details of the OOH works that are required and will update accordingly _x000D_29/7/2024:01409315 _x000D_26/7/2024:01409315 _x000D_24/7/2024:#Update - CSL have chased Openreach to obtain details of the OOH works that are required and will update accordingly _x000D_23/7/2024:#Update - CSL have chased Openreach to obtain details of the OOH works that are required and will update accordingly _x000D_22/7/2024:#Update - CSL have chased Openreach to obtain details of the OOH works that are required and will update accordingly _x000D_22/7/2024:#Update - CSL have chased Openreach to obtain details of the OOH works that are required and will update accordingly _x000D_25/6/2024:Order Completed _x000D_24/6/2024:Order Completed _x000D_20/6/2024:Supplier Delay: Missed CCD and may require further work as the engineer has retained the job for next day _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | #Update - awaiting ECC approval from customer - sent to VF 03/06 |  |  |  |  | 5.CSL | VFS970640 | 30013386 | 1.Provisioning | AM |  | 2024-05-24 | 2024-08-30 |  | 0 | [11 empty] | 0
614 | 200483 | 726 | Batch 3 May24 | Type 1 | FTTP | Bains Newsagents | COVENTRY | CV2 5BE | 2024-06-21 | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:Update: Order Amended _x000D_15/7/2024:Update: Order Amended _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:Update: Order Amended _x000D_24/6/2024:Update: Order Amended _x000D_20/6/2024:Update: Order Amended _x000D_19/6/2024:Update: Order Amended _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:Update: Order Amended _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:Update: Order Amended _x000D_15/7/2024:Update: Order Amended _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:Update: Order Amended _x000D_24/6/2024:Update: Order Amended _x000D_20/6/2024:Update: Order Amended _x000D_19/6/2024:Update: Order Amended _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:Update: Order Amended _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-05-09 | 09/05/2024: Allwyn to make the retailer aware in the date in column U |  |  | 3.Allwyn to arrange rtr install | VFP2300923 | 30013616 | 6.Failed router install | AM |  | 2024-05-08 | 2024-06-20 | 2024-06-22 | TRUE |  |  |  | 2024-07-11 |  |  |  | 2024-07-12 | 237004907559 |  | 2024-07-15 | 1
615 | 661088 | 930 | Batch 3 May24 | Type 1 | SoGEA/Mobile | Audrey Ridden | Newcastle upon Tyne | NE15 9NS | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_3/9/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_2/9/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_29/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:Update: Order Amended _x000D_31/7/2024:Update: Order Amended _x000D_31/7/2024:37768 _x000D_30/7/2024:Update: Order Amended _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_27/6/2024:#Update - Retailer confirmed 20th June. _x000D_25/6/2024:#Update - Retailer confirmed 20th June. _x000D_24/6/2024:#Update - Retailer confirmed 20th June. _x000D_20/6/2024:#Update - Retailer confirmed 20th June. _x000D_19/6/2024:#Update - Retailer confirmed 20th June. _x000D_18/6/2024:#Update - Retailer confirmed 20th June. _x000D_17/6/2024:#Update - Retailer confirmed 20th June. _x000D_14/6/2024:#Update - Retailer confirmed 20th June. _x000D_13/6/2024:#Update - OR have requested CSL to await further updates as the Teletower was unavailable today for the engineer to reach the DP. OR have re-scheduled a date for the engineer to revisit the site with the correct facilities in order to complete install. Will await further updates due on 05.06 _x000D_12/6/2024:#Update - OR have requested CSL to await further updates as the Teletower was unavailable today for the engineer to reach the DP. OR have re-scheduled a date for the engineer to revisit the site with the correct facilities in order to complete install. Will await further updates due on 05.06 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_3/9/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_2/9/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_29/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:Update: Order Amended _x000D_31/7/2024:Update: Order Amended _x000D_31/7/2024:37768 _x000D_30/7/2024:Update: Order Amended _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_27/6/2024:#Update - Retailer confirmed 20th June. _x000D_25/6/2024:#Update - Retailer confirmed 20th June. _x000D_24/6/2024:#Update - Retailer confirmed 20th June. _x000D_20/6/2024:#Update - Retailer confirmed 20th June. _x000D_19/6/2024:#Update - Retailer confirmed 20th June. _x000D_18/6/2024:#Update - Retailer confirmed 20th June. _x000D_17/6/2024:#Update - Retailer confirmed 20th June. _x000D_14/6/2024:#Update - Retailer confirmed 20th June. _x000D_13/6/2024:#Update - OR have requested CSL to await further updates as the Teletower was unavailable today for the engineer to reach the DP. OR have re-scheduled a date for the engineer to revisit the site with the correct facilities in order to complete install. Will await further updates due on 05.06 _x000D_12/6/2024:#Update - OR have requested CSL to await further updates as the Teletower was unavailable today for the engineer to reach the DP. OR have re-scheduled a date for the engineer to revisit the site with the correct facilities in order to complete install. Will await further updates due on 05.06 _x000D_0 | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFS975510 | 30013820 | 1.Provisioning | AM |  | 2024-06-20 | 2024-08-28 |  | 0 | [11 empty] | 0
616 | 665311 | 1076 | Batch 3 May24 | Type 1 | SOGEA | Post Office | LONDON | SE28 8BG | 2024-06-21 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_18/7/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_17/7/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_16/7/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_15/7/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_12/7/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_11/7/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_10/7/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_9/7/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_4/7/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_3/7/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_27/6/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_25/6/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_24/6/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_20/6/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_19/6/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_18/6/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_17/6/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_14/6/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_13/6/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_12/6/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_18/7/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_17/7/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_16/7/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_15/7/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_12/7/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_11/7/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_10/7/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_9/7/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_4/7/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_3/7/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_27/6/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_25/6/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_24/6/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_20/6/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_19/6/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_18/6/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_17/6/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_14/6/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_13/6/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_12/6/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 3.Allwyn to arrange rtr install | VFP2301273 | 30013966 | 2.Commissioning | AM | [8 empty] | 2024-07-11 | [7 empty] | 0
617 | 618353 | 1256 | Batch 3 May24 | Type 3 | FTTP/Mobile | Nettlehill Service Station | Lisburn | BT28 3RF | 2024-06-21 | 6/9/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_5/9/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_4/9/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_3/9/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_2/9/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_29/8/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_28/8/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_27/8/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_22/8/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_21/8/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_20/8/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_19/8/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_19/8/2024:01414737 _x000D_16/8/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_15/8/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_14/8/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_13/8/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_12/8/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_9/8/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_8/8/2024:29/05/2024 _x000D_6/8/2024:29/05/2024 _x000D_5/8/2024:29/05/2024 _x000D_2/8/2024:29/05/2024 _x000D_1/8/2024:29/05/2024 _x000D_31/7/2024:29/05/2024 _x000D_31/7/2024:29/05/2024 _x000D_30/7/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_29/7/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_29/7/2024:01414737 _x000D_26/7/2024:01414737 _x000D_24/7/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_23/7/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_22/7/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_22/7/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Order Completed _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:Update: Order Amended _x000D_24/6/2024:Update: Order Amended _x000D_20/6/2024:Update: Order Amended _x000D_19/6/2024:Update: Order Amended _x000D_18/6/2024:Update: Order Amended _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:Update: Order Amended _x000D_12/6/2024:Update: Order Amended _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_6/9/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_5/9/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_4/9/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_3/9/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_2/9/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_29/8/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_28/8/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_27/8/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_22/8/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_21/8/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_20/8/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_19/8/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_19/8/2024:01414737 _x000D_16/8/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_15/8/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_14/8/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_13/8/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_12/8/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_9/8/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_8/8/2024:29/05/2024 _x000D_6/8/2024:29/05/2024 _x000D_5/8/2024:29/05/2024 _x000D_2/8/2024:29/05/2024 _x000D_1/8/2024:29/05/2024 _x000D_31/7/2024:29/05/2024 _x000D_31/7/2024:29/05/2024 _x000D_30/7/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_29/7/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_29/7/2024:01414737 _x000D_26/7/2024:01414737 _x000D_24/7/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_23/7/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_22/7/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_22/7/2024:#Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Order Completed _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:Update: Order Amended _x000D_24/6/2024:Update: Order Amended _x000D_20/6/2024:Update: Order Amended _x000D_19/6/2024:Update: Order Amended _x000D_18/6/2024:Update: Order Amended _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:Update: Order Amended _x000D_12/6/2024:Update: Order Amended _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update Installation not completed 29/05/2024 - civils work may be required, awaiting further details from Supplier on how to proceed. |  |  |  |  | 3.Allwyn to arrange rtr install | VFP2301453 | 30014146 | 2.Commissioning | AM |  | 2024-09-16 | 2024-09-16 |  | 0 |  |  |  | 2024-08-21 | [7 empty] | 0
618 | 485024 | 1337 | Batch 4 Jun24 | Type 1 | SOGEA | Nisa Local Thorpe Street | Middleton | LS10 4EZ | 2024-07-04 | 29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_24/6/2024:Order Completed _x000D_20/6/2024:Order Completed _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:Update: Order Amended _x000D_12/6/2024:Update: Order Amended _x000D_0 | 29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_24/6/2024:Order Completed _x000D_20/6/2024:Order Completed _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:Update: Order Amended _x000D_12/6/2024:Update: Order Amended _x000D_0 | [6 empty] | 2.Allwyn to arrange access | VFS984904 | 30015301 | 6.Failed router install | AM |  | 2024-06-03 | 2024-07-03 | 2024-07-03 | TRUE |  |  |  | 2024-07-26 |  |  |  | 2024-07-26 | 238004924223 |  | 2024-07-29 | 1
619 | 231432 | 1417 | Batch 4 Jun24 | Type 1 | SoGEA/Mobile | Premier Silcox Stores | CWMBRAN | NP44 1DY | 2024-06-07 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:#Update customer missed appointment as they were unaware of order. Also shop is too busy for installation to go ahead during opening hours OOH may be required. Reappointed for 30/07. _x000D_21/8/2024:#Update customer missed appointment as they were unaware of order. Also shop is too busy for installation to go ahead during opening hours OOH may be required. Reappointed for 30/07. _x000D_20/8/2024:#Update customer missed appointment as they were unaware of order. Also shop is too busy for installation to go ahead during opening hours OOH may be required. Reappointed for 30/07. _x000D_19/8/2024:#Update customer missed appointment as they were unaware of order. Also shop is too busy for installation to go ahead during opening hours OOH may be required. Reappointed for 30/07. _x000D_19/8/2024:01425829 _x000D_16/8/2024:#Update customer missed appointment as they were unaware of order. Also shop is too busy for installation to go ahead during opening hours OOH may be required. Reappointed for 30/07. _x000D_15/8/2024:#Update customer missed appointment as they were unaware of order. Also shop is too busy for installation to go ahead during opening hours OOH may be required. Reappointed for 30/07. _x000D_14/8/2024:#Update customer missed appointment as they were unaware of order. Also shop is too busy for installation to go ahead during opening hours OOH may be required. Reappointed for 30/07. _x000D_13/8/2024:#Update customer missed appointment as they were unaware of order. Also shop is too busy for installation to go ahead during opening hours OOH may be required. Reappointed for 30/07. _x000D_12/8/2024:#Update customer missed appointment as they were unaware of order. Also shop is too busy for installation to go ahead during opening hours OOH may be required. Reappointed for 30/07. _x000D_9/8/2024:#Update customer missed appointment as they were unaware of order. Also shop is too busy for installation to go ahead during opening hours OOH may be required. Reappointed for 30/07. _x000D_8/8/2024:25/06/2024 _x000D_6/8/2024:25/06/2024 _x000D_5/8/2024:25/06/2024 _x000D_2/8/2024:25/06/2024 _x000D_1/8/2024:25/06/2024 _x000D_31/7/2024:25/06/2024 _x000D_31/7/2024:25/06/2024 _x000D_30/7/2024:#Update customer missed appointment as they were unaware of order. Also shop is too busy for installation to go ahead during opening hours OOH may be required. Reappointed for 30/07. _x000D_29/7/2024:#Update customer missed appointment as they were unaware of order. Also shop is too busy for installation to go ahead during opening hours OOH may be required. Reappointed for 30/07. _x000D_29/7/2024:01425829 _x000D_26/7/2024:01425829 _x000D_24/7/2024:#Update customer missed appointment as they were unaware of order. Also shop is too busy for installation to go ahead during opening hours OOH may be required. Reappointed for 30/07. _x000D_23/7/2024:#Update customer missed appointment as they were unaware of order. Also shop is too busy for installation to go ahead during opening hours OOH may be required. Reappointed for 30/07. _x000D_22/7/2024:#Update customer missed appointment as they were unaware of order. Also shop is too busy for installation to go ahead during opening hours OOH may be required. Reappointed for 30/07. _x000D_22/7/2024:#Update customer missed appointment as they were unaware of order. Also shop is too busy for installation to go ahead during opening hours OOH may be required. Reappointed for 30/07. _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:Update: Order Amended _x000D_17/7/2024:Update: Order Amended _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:Update: Order Amended _x000D_24/6/2024:Update: Order Amended _x000D_20/6/2024:Update: Order Amended _x000D_19/6/2024:Update: Order Amended _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:Update: Order Amended _x000D_12/6/2024:Update: Order Amended _x000D_10/6/2024:Update: Order Amended _x000D_7/6/2024:Update: Order Amended _x000D_6/6/2024:Update: Order Amended _x000D_5/6/2024:End User Missed appointment. Action required _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:#Update customer missed appointment as they were unaware of order. Also shop is too busy for installation to go ahead during opening hours OOH may be required. Reappointed for 30/07. _x000D_21/8/2024:#Update customer missed appointment as they were unaware of order. Also shop is too busy for installation to go ahead during opening hours OOH may be required. Reappointed for 30/07. _x000D_20/8/2024:#Update customer missed appointment as they were unaware of order. Also shop is too busy for installation to go ahead during opening hours OOH may be required. Reappointed for 30/07. _x000D_19/8/2024:#Update customer missed appointment as they were unaware of order. Also shop is too busy for installation to go ahead during opening hours OOH may be required. Reappointed for 30/07. _x000D_19/8/2024:01425829 _x000D_16/8/2024:#Update customer missed appointment as they were unaware of order. Also shop is too busy for installation to go ahead during opening hours OOH may be required. Reappointed for 30/07. _x000D_15/8/2024:#Update customer missed appointment as they were unaware of order. Also shop is too busy for installation to go ahead during opening hours OOH may be required. Reappointed for 30/07. _x000D_14/8/2024:#Update customer missed appointment as they were unaware of order. Also shop is too busy for installation to go ahead during opening hours OOH may be required. Reappointed for 30/07. _x000D_13/8/2024:#Update customer missed appointment as they were unaware of order. Also shop is too busy for installation to go ahead during opening hours OOH may be required. Reappointed for 30/07. _x000D_12/8/2024:#Update customer missed appointment as they were unaware of order. Also shop is too busy for installation to go ahead during opening hours OOH may be required. Reappointed for 30/07. _x000D_9/8/2024:#Update customer missed appointment as they were unaware of order. Also shop is too busy for installation to go ahead during opening hours OOH may be required. Reappointed for 30/07. _x000D_8/8/2024:25/06/2024 _x000D_6/8/2024:25/06/2024 _x000D_5/8/2024:25/06/2024 _x000D_2/8/2024:25/06/2024 _x000D_1/8/2024:25/06/2024 _x000D_31/7/2024:25/06/2024 _x000D_31/7/2024:25/06/2024 _x000D_30/7/2024:#Update customer missed appointment as they were unaware of order. Also shop is too busy for installation to go ahead during opening hours OOH may be required. Reappointed for 30/07. _x000D_29/7/2024:#Update customer missed appointment as they were unaware of order. Also shop is too busy for installation to go ahead during opening hours OOH may be required. Reappointed for 30/07. _x000D_29/7/2024:01425829 _x000D_26/7/2024:01425829 _x000D_24/7/2024:#Update customer missed appointment as they were unaware of order. Also shop is too busy for installation to go ahead during opening hours OOH may be required. Reappointed for 30/07. _x000D_23/7/2024:#Update customer missed appointment as they were unaware of order. Also shop is too busy for installation to go ahead during opening hours OOH may be required. Reappointed for 30/07. _x000D_22/7/2024:#Update customer missed appointment as they were unaware of order. Also shop is too busy for installation to go ahead during opening hours OOH may be required. Reappointed for 30/07. _x000D_22/7/2024:#Update customer missed appointment as they were unaware of order. Also shop is too busy for installation to go ahead during opening hours OOH may be required. Reappointed for 30/07. _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:Update: Order Amended _x000D_17/7/2024:Update: Order Amended _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:Update: Order Amended _x000D_24/6/2024:Update: Order Amended _x000D_20/6/2024:Update: Order Amended _x000D_19/6/2024:Update: Order Amended _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:Update: Order Amended _x000D_12/6/2024:Update: Order Amended _x000D_10/6/2024:Update: Order Amended _x000D_7/6/2024:Update: Order Amended _x000D_6/6/2024:Update: Order Amended _x000D_5/6/2024:End User Missed appointment. Action required _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 0 | 0 | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984688 | 30015415 | 2.Commissioning | AM |  | 2024-06-06 | 2024-08-19 |  | 0 |  |  |  | 2024-09-18 | [7 empty] | 0
620 | 624847 | 1927 | Batch 4 Jun24 | Type 3 | SoGEA/Mobile | Spar | Peterborough | PE7 3JJ | 2024-06-07 | 6/9/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_5/9/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_4/9/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_3/9/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_2/9/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_29/8/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_28/8/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_27/8/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_22/8/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_21/8/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_20/8/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_19/8/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_19/8/2024:01424677 _x000D_16/8/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_15/8/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_14/8/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_13/8/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_12/8/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_9/8/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_8/8/2024:22/07/2024 _x000D_6/8/2024:22/07/2024 _x000D_5/8/2024:22/07/2024 _x000D_2/8/2024:22/07/2024 _x000D_1/8/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_30/7/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_29/7/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_29/7/2024:01424677 _x000D_26/7/2024:01424677 _x000D_24/7/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_23/7/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:#Update - NFA - Allwyn have liaised with retailer who is aware of new installation date of 26/07 _x000D_18/7/2024:#Update - NFA - Allwyn have liaised with retailer who is aware of new installation date of 26/07 _x000D_17/7/2024:#Update - NFA - Allwyn have liaised with retailer who is aware of new installation date of 26/07 _x000D_16/7/2024:#Update - NFA - Allwyn have liaised with retailer who is aware of new installation date of 26/07 _x000D_15/7/2024:#Update - NFA - Allwyn have liaised with retailer who is aware of new installation date of 26/07 _x000D_12/7/2024:#Update - NFA - Allwyn have liaised with retailer who is aware of new installation date of 26/07 _x000D_11/7/2024:#Update - NFA - Allwyn have liaised with retailer who is aware of new installation date of 26/07 _x000D_10/7/2024:#Update - NFA - Allwyn have liaised with retailer who is aware of new installation date of 26/07 _x000D_9/7/2024:#Update - NFA - Allwyn have liaised with retailer who is aware of new installation date of 26/07 _x000D_4/7/2024:#Update - NFA - Allwyn have liaised with retailer who is aware of new installation date of 26/07 _x000D_3/7/2024:#Update - NFA - Allwyn have liaised with retailer who is aware of new installation date of 26/07 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_27/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_25/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_24/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_20/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_19/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_18/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_17/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_14/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_13/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_12/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_10/6/2024:Update: Order Amended _x000D_7/6/2024:Update: Order Amended _x000D_6/6/2024:Update: Order Amended _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 9/9/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_6/9/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_5/9/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_4/9/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_3/9/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_2/9/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_29/8/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_28/8/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_27/8/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_22/8/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_21/8/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_20/8/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_19/8/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_19/8/2024:01424677 _x000D_16/8/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_15/8/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_14/8/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_13/8/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_12/8/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_9/8/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_8/8/2024:22/07/2024 _x000D_6/8/2024:22/07/2024 _x000D_5/8/2024:22/07/2024 _x000D_2/8/2024:22/07/2024 _x000D_1/8/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_30/7/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_29/7/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_29/7/2024:01424677 _x000D_26/7/2024:01424677 _x000D_24/7/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_23/7/2024:#Update - Awaiting Upgrade&OOH ECCS _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:#Update - NFA - Allwyn have liaised with retailer who is aware of new installation date of 26/07 _x000D_18/7/2024:#Update - NFA - Allwyn have liaised with retailer who is aware of new installation date of 26/07 _x000D_17/7/2024:#Update - NFA - Allwyn have liaised with retailer who is aware of new installation date of 26/07 _x000D_16/7/2024:#Update - NFA - Allwyn have liaised with retailer who is aware of new installation date of 26/07 _x000D_15/7/2024:#Update - NFA - Allwyn have liaised with retailer who is aware of new installation date of 26/07 _x000D_12/7/2024:#Update - NFA - Allwyn have liaised with retailer who is aware of new installation date of 26/07 _x000D_11/7/2024:#Update - NFA - Allwyn have liaised with retailer who is aware of new installation date of 26/07 _x000D_10/7/2024:#Update - NFA - Allwyn have liaised with retailer who is aware of new installation date of 26/07 _x000D_9/7/2024:#Update - NFA - Allwyn have liaised with retailer who is aware of new installation date of 26/07 _x000D_4/7/2024:#Update - NFA - Allwyn have liaised with retailer who is aware of new installation date of 26/07 _x000D_3/7/2024:#Update - NFA - Allwyn have liaised with retailer who is aware of new installation date of 26/07 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_27/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_25/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_24/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_20/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_19/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_18/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_17/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_14/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_13/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_12/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_10/6/2024:Update: Order Amended _x000D_7/6/2024:Update: Order Amended _x000D_6/6/2024:Update: Order Amended _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 0 | #Update - Awaiting Upgrade&OOH ECCS | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996771 | 30016077 | 2.Commissioning | AM |  |  |  |  | 0 | [11 empty] | 0
621 | 666288 | 1716 | Batch 4 Jun24 | Type 1 | SOGEA | High Street Store Go Local Extra | Barnsley | S71 4RW | 2024-07-29 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:#Update - NFA - Allwyn have liaised with retailer who is aware of new installation date of 26/07 _x000D_29/7/2024:#Update - NFA - Allwyn have liaised with retailer who is aware of new installation date of 26/07 _x000D_29/7/2024:01425930 _x000D_26/7/2024:01425930 _x000D_24/7/2024:#Update - NFA - Allwyn have liaised with retailer who is aware of new installation date of 26/07 _x000D_23/7/2024:#Update - NFA - Allwyn have liaised with retailer who is aware of new installation date of 26/07 _x000D_22/7/2024:#Update - NFA - Allwyn have liaised with retailer who is aware of new installation date of 26/07 _x000D_22/7/2024:#Update - NFA - Allwyn have liaised with retailer who is aware of new installation date of 26/07 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:End User Missed appointment. Action required _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:Update: Order Amended _x000D_25/6/2024:Update: Order Amended _x000D_24/6/2024:Update: Order Amended _x000D_20/6/2024:0 _x000D_19/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_18/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_17/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_14/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_13/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:#Update - NFA - Allwyn have liaised with retailer who is aware of new installation date of 26/07 _x000D_29/7/2024:#Update - NFA - Allwyn have liaised with retailer who is aware of new installation date of 26/07 _x000D_29/7/2024:01425930 _x000D_26/7/2024:01425930 _x000D_24/7/2024:#Update - NFA - Allwyn have liaised with retailer who is aware of new installation date of 26/07 _x000D_23/7/2024:#Update - NFA - Allwyn have liaised with retailer who is aware of new installation date of 26/07 _x000D_22/7/2024:#Update - NFA - Allwyn have liaised with retailer who is aware of new installation date of 26/07 _x000D_22/7/2024:#Update - NFA - Allwyn have liaised with retailer who is aware of new installation date of 26/07 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:End User Missed appointment. Action required _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:Update: Order Amended _x000D_25/6/2024:Update: Order Amended _x000D_24/6/2024:Update: Order Amended _x000D_20/6/2024:0 _x000D_19/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_18/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_17/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_14/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_13/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 0 | 0 | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFS996799 | 30016083 | 2.Commissioning | AM | [8 empty] | 2024-08-15 | [7 empty] | 0
622 | 659755 | 3014 | Batch 5 Jul24 | Type 3 | SoGEA/Mobile | Pay and Play | Merthyr Tydfil | CF47 0AE | 2024-07-05 | 6/9/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_5/9/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_4/9/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_28/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_27/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_22/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_21/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_20/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_19/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_19/8/2024:01446364 _x000D_16/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_15/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_14/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_13/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_12/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_9/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_8/8/2024:05/08/2024 _x000D_6/8/2024:05/08/2024 _x000D_5/8/2024:05/08/2024 _x000D_2/8/2024:25/07/2024 _x000D_1/8/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_30/7/2024:#Update - Switching to type site 3. _x000D_29/7/2024:#Update - Switching to type site 3. _x000D_29/7/2024:01446364 _x000D_26/7/2024:01446364 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_6/9/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_5/9/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_4/9/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_28/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_27/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_22/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_21/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_20/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_19/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_19/8/2024:01446364 _x000D_16/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_15/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_14/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_13/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_12/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_9/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_8/8/2024:05/08/2024 _x000D_6/8/2024:05/08/2024 _x000D_5/8/2024:05/08/2024 _x000D_2/8/2024:25/07/2024 _x000D_1/8/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_30/7/2024:#Update - Switching to type site 3. _x000D_29/7/2024:#Update - Switching to type site 3. _x000D_29/7/2024:01446364 _x000D_26/7/2024:01446364 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | #Update - this site has changed to a site type 3 / mobile only as per customer request | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015623 | 30016880 | 6.Failed router install | AM |  | 2024-08-15 | 2024-08-15 |  | 0 |  |  |  | 2024-08-22 |  |  |  | 2024-08-22 | 242005010458 | 242005010458 | 2024-08-28 | 1
623 | 430634 | 3022 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Centra | NEWTOWNARDS | BT23 4RE | 2024-06-21 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:18 _x000D_26/7/2024:22/07/2024 10:18 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect Product Please check with end user and reappoint the order if still required. _x000D_25/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect Product Please check with end user and reappoint the order if still required. _x000D_24/6/2024:Supplier Delay: KCI-3 (Order Completed) Delayed in Processing. _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:18 _x000D_26/7/2024:22/07/2024 10:18 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect Product Please check with end user and reappoint the order if still required. _x000D_25/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect Product Please check with end user and reappoint the order if still required. _x000D_24/6/2024:Supplier Delay: KCI-3 (Order Completed) Delayed in Processing. _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  | 5.CSL | VFP2366040 | 30016740 | 1.Provisioning | AM |  | 2024-06-20 | 2024-09-06 |  | 0 | [11 empty] | 0
624 | 651859 | 3023 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Centra | Carrickfergus | BT38 8HQ | 2024-06-21 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:08 _x000D_26/7/2024:22/07/2024 10:08 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_4/7/2024:#Update - Pushed out to 15/07- AM _x000D_3/7/2024:#Update - Pushed out to 15/07- AM _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Pushed out to 15/07- AM _x000D_27/6/2024:#Update - Pushed out to 15/07- AM _x000D_25/6/2024:#Update - Pushed out to 15/07- AM _x000D_24/6/2024:#Update - ATM in the way of DP, could not find alternative route for install. Shop is having ATM removed on 5th July, aiming to have this appointed around then. Action for Alwyn: confirm that the atm is being removed on the 5th, then we can appoint this install. _x000D_20/6/2024:#Update - ATM in the way of DP, could not find alternative route for install. Shop is having ATM removed on 5th July, aiming to have this appointed around then. Action for Alwyn: confirm that the atm is being removed on the 5th, then we can appoint this install. _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:08 _x000D_26/7/2024:22/07/2024 10:08 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_4/7/2024:#Update - Pushed out to 15/07- AM _x000D_3/7/2024:#Update - Pushed out to 15/07- AM _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Pushed out to 15/07- AM _x000D_27/6/2024:#Update - Pushed out to 15/07- AM _x000D_25/6/2024:#Update - Pushed out to 15/07- AM _x000D_24/6/2024:#Update - ATM in the way of DP, could not find alternative route for install. Shop is having ATM removed on 5th July, aiming to have this appointed around then. Action for Alwyn: confirm that the atm is being removed on the 5th, then we can appoint this install. _x000D_20/6/2024:#Update - ATM in the way of DP, could not find alternative route for install. Shop is having ATM removed on 5th July, aiming to have this appointed around then. Action for Alwyn: confirm that the atm is being removed on the 5th, then we can appoint this install. _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  | 5.CSL | VFP2366159 | 30016990 | 1.Provisioning | AM |  | 2024-06-20 | 2024-09-06 |  | 0 | [11 empty] | 0
625 | 672244 | 3024 | Batch 5 Jul24 | Type 1 | FTTP | Sheldon News | Birmingham | B26 3JB | 2024-08-02 | 2/8/2024:09/07/2024 _x000D_24/6/2024:Order Completed _x000D_20/6/2024:Update: Order Completed by Supplier _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 2/8/2024:09/07/2024 _x000D_24/6/2024:Order Completed _x000D_20/6/2024:Update: Order Completed by Supplier _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFP2366157 | 30017007 | 6.Failed router install |  |  |  |  | 2024-07-29 | TRUE |  |  |  | 2024-08-21 |  |  |  | 2024-08-23 | 237004907562 | 237004907562 | 2024-08-27 | 1 | 672244
626 | 471663 | 3027 | Batch 5 Jul24 | Type 1 | FTTP | Croft News | WALSALL | WS9 8LY | 2024-06-21 | 19/7/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_18/7/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_17/7/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_16/7/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_15/7/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_12/7/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_11/7/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_10/7/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_9/7/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_4/7/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_3/7/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update Multi-skilled engineer is needed, reappointed 05/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_27/6/2024:Your order has been delayed. Engineer required access to the end user premises to complete the external works . Please check with the end user and book a new appointment. _x000D_25/6/2024:Your order has been delayed. Engineer required access to the end user premises to complete the external works . Please check with the end user and book a new appointment. _x000D_24/6/2024:This is a delay message. We are currently unable to complete all engineering activities required to fulfil this order. Further indoor and outdoor work is required. End User presence will be required. _x000D_20/6/2024:This is a delay message. We are currently unable to complete all engineering activities required to fulfil this order. Further indoor and outdoor work is required. End User presence will be required. _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 19/7/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_18/7/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_17/7/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_16/7/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_15/7/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_12/7/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_11/7/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_10/7/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_9/7/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_4/7/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_3/7/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update Multi-skilled engineer is needed, reappointed 05/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_27/6/2024:Your order has been delayed. Engineer required access to the end user premises to complete the external works . Please check with the end user and book a new appointment. _x000D_25/6/2024:Your order has been delayed. Engineer required access to the end user premises to complete the external works . Please check with the end user and book a new appointment. _x000D_24/6/2024:This is a delay message. We are currently unable to complete all engineering activities required to fulfil this order. Further indoor and outdoor work is required. End User presence will be required. _x000D_20/6/2024:This is a delay message. We are currently unable to complete all engineering activities required to fulfil this order. Further indoor and outdoor work is required. End User presence will be required. _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015512 | 30016947 | 6.Failed router install |  |  | 2024-06-20 | 2024-06-20 | 2024-06-20 | TRUE |  |  |  | 2024-07-10 |  |  |  | 2024-07-10 | 23A004945886 |  | 2024-07-11 | 1
627 | 111552 | 3028 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | W Marshall and Son | WALSALL | WS3 3LQ | 2024-07-23 | 6/9/2024:#Update OR thought this site was a multi port and reappointed to 06/09, turns out not to be a multi port but retailer happy with appointment on 06/09, AM. _x000D_5/9/2024:#Update OR thought this site was a multi port and reappointed to 06/09, turns out not to be a multi port but retailer happy with appointment on 06/09, AM. _x000D_4/9/2024:#Update OR thought this site was a multi port and reappointed to 06/09, turns out not to be a multi port but retailer happy with appointment on 06/09, AM. _x000D_3/9/2024:#Update OR thought this site was a multi port and reappointed to 06/09, turns out not to be a multi port but retailer happy with appointment on 06/09, AM. _x000D_2/9/2024:#Update OR thought this site was a multi port and reappointed to 06/09, turns out not to be a multi port but retailer happy with appointment on 06/09, AM. _x000D_29/8/2024:#Update OR thought this site was a multi port and reappointed to 06/09, turns out not to be a multi port but retailer happy with appointment on 06/09, AM. _x000D_28/8/2024:#Update OR thought this site was a multi port and reappointed to 06/09, turns out not to be a multi port but retailer happy with appointment on 06/09, AM. _x000D_27/8/2024:#Update OR thought this site was a multi port and reappointed to 06/09, turns out not to be a multi port but retailer happy with appointment on 06/09, AM. _x000D_22/8/2024:#Update OR thought this site was a multi port and reappointed to 06/09, turns out not to be a multi port but retailer happy with appointment on 06/09, AM. _x000D_21/8/2024:#Update OR thought this site was a multi port and reappointed to 06/09, turns out not to be a multi port but retailer happy with appointment on 06/09, AM. _x000D_20/8/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_19/8/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_19/8/2024:01445980 _x000D_16/8/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_15/8/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_14/8/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_13/8/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_12/8/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_9/8/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_8/8/2024:02/07/2024 _x000D_6/8/2024:02/07/2024 _x000D_5/8/2024:02/07/2024 _x000D_2/8/2024:02/07/2024 _x000D_1/8/2024:02/07/2024 _x000D_31/7/2024:02/07/2024 _x000D_31/7/2024:02/07/2024 _x000D_30/7/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_29/7/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_29/7/2024:01445980 _x000D_26/7/2024:01445980 _x000D_24/7/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_23/7/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_22/7/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_22/7/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect Product Please check with end user and reappoint the order if still required. _x000D_25/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect Product Please check with end user and reappoint the order if still required. _x000D_24/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect Product Please check with end user and reappoint the order if still required. _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:#Update OR thought this site was a multi port and reappointed to 06/09, turns out not to be a multi port but retailer happy with appointment on 06/09, AM. _x000D_6/9/2024:#Update OR thought this site was a multi port and reappointed to 06/09, turns out not to be a multi port but retailer happy with appointment on 06/09, AM. _x000D_5/9/2024:#Update OR thought this site was a multi port and reappointed to 06/09, turns out not to be a multi port but retailer happy with appointment on 06/09, AM. _x000D_4/9/2024:#Update OR thought this site was a multi port and reappointed to 06/09, turns out not to be a multi port but retailer happy with appointment on 06/09, AM. _x000D_3/9/2024:#Update OR thought this site was a multi port and reappointed to 06/09, turns out not to be a multi port but retailer happy with appointment on 06/09, AM. _x000D_2/9/2024:#Update OR thought this site was a multi port and reappointed to 06/09, turns out not to be a multi port but retailer happy with appointment on 06/09, AM. _x000D_29/8/2024:#Update OR thought this site was a multi port and reappointed to 06/09, turns out not to be a multi port but retailer happy with appointment on 06/09, AM. _x000D_28/8/2024:#Update OR thought this site was a multi port and reappointed to 06/09, turns out not to be a multi port but retailer happy with appointment on 06/09, AM. _x000D_27/8/2024:#Update OR thought this site was a multi port and reappointed to 06/09, turns out not to be a multi port but retailer happy with appointment on 06/09, AM. _x000D_22/8/2024:#Update OR thought this site was a multi port and reappointed to 06/09, turns out not to be a multi port but retailer happy with appointment on 06/09, AM. _x000D_21/8/2024:#Update OR thought this site was a multi port and reappointed to 06/09, turns out not to be a multi port but retailer happy with appointment on 06/09, AM. _x000D_20/8/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_19/8/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_19/8/2024:01445980 _x000D_16/8/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_15/8/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_14/8/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_13/8/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_12/8/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_9/8/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_8/8/2024:02/07/2024 _x000D_6/8/2024:02/07/2024 _x000D_5/8/2024:02/07/2024 _x000D_2/8/2024:02/07/2024 _x000D_1/8/2024:02/07/2024 _x000D_31/7/2024:02/07/2024 _x000D_31/7/2024:02/07/2024 _x000D_30/7/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_29/7/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_29/7/2024:01445980 _x000D_26/7/2024:01445980 _x000D_24/7/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_23/7/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_22/7/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_22/7/2024:#Update Retailer happy with new appointment 05/07,AM. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect Product Please check with end user and reappoint the order if still required. _x000D_25/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect Product Please check with end user and reappoint the order if still required. _x000D_24/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect Product Please check with end user and reappoint the order if still required. _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | Update: Order Amended | #Update OR thought this site was a multi port and reappointed to 06/09, turns out not to be a multi port but retailer happy with appointment on 06/09, AM. | 2024-06-07 |  |  |  | 5.CSL | VFP2366158 | 30016839 | 1.Provisioning | AM |  | 2024-06-20 | 2024-08-19 |  | 0 | [11 empty] | 0
628 | 665390 | 3029 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Spar Turf Lodge | BELFAST | BT11 8EF | 2024-06-21 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 09:52 _x000D_26/7/2024:22/07/2024 09:52 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 09:52 _x000D_26/7/2024:22/07/2024 09:52 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  | 5.CSL | VFP2366156 | 30017017 | 1.Provisioning | AM |  | 2024-06-20 | 2024-09-06 |  | 0 | [11 empty] | 0
629 | 467388 | 3030 | Batch 5 Jul24 | Type 1 | FTTP | Mace | Belfast | BT1 2BD | 2024-06-21 | 24/6/2024:Order Completed _x000D_20/6/2024:Order Completed _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 24/6/2024:Order Completed _x000D_20/6/2024:Order Completed _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366155 | 30016669 | 6.Failed router install |  |  | 2024-06-20 | 2024-06-20 | 2024-06-20 | TRUE |  |  |  | 2024-07-19 |  |  |  | 2024-07-19 | 242005010274 |  | 2024-07-23 | 1
630 | 627925 | 3034 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Russells Food & Drink | Belfast | BT6 9DL |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 09:53 _x000D_26/7/2024:22/07/2024 09:53 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_24/6/2024:Order Completed _x000D_20/6/2024:Order Completed _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 09:53 _x000D_26/7/2024:22/07/2024 09:53 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_24/6/2024:Order Completed _x000D_20/6/2024:Order Completed _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2366152 | 30016837 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
631 | 463548 | 3036 | Batch 5 Jul24 | Type 1 | SOGEA | Londis News & Views | THETFORD | IP24 1TA | 2024-06-21 | 24/6/2024:Order Completed _x000D_20/6/2024:Update: Order Completed by Supplier _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 24/6/2024:Order Completed _x000D_20/6/2024:Update: Order Completed by Supplier _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015617 | 30016617 | 2.Commissioning |  |  | 2024-06-20 | 2024-06-20 | 2024-06-20 | TRUE |  |  |  | 2024-07-10 | [7 empty] | 0
632 | 624623 | 3041 | Batch 5 Jul24 | Type 1 | SOGEA | Globe Food and Wine | Mile End | E1 4DU | 2024-06-21 | 19/7/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_18/7/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_17/7/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_16/7/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_15/7/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_12/7/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_11/7/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_10/7/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_9/7/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_4/7/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_3/7/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_27/6/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_25/6/2024:#Update - Retained by OR to reappoint with multi skilled engineer, Supplier delay. _x000D_24/6/2024:#Update - Retained by OR to reappoint with multi skilled engineer, Supplier delay. _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 19/7/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_18/7/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_17/7/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_16/7/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_15/7/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_12/7/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_11/7/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_10/7/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_9/7/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_4/7/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_3/7/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_27/6/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_25/6/2024:#Update - Retained by OR to reappoint with multi skilled engineer, Supplier delay. _x000D_24/6/2024:#Update - Retained by OR to reappoint with multi skilled engineer, Supplier delay. _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015508 | 30016893 | 2.Commissioning |  |  | 2024-06-20 | 2024-06-20 | 2024-06-20 | TRUE |  |  |  | 2024-07-10 | [7 empty] | 0
633 | 655468 | 3042 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Plaza News Key Store | Edinburgh | EH14 2SW | 2024-06-21 | 6/9/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_5/9/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_4/9/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_3/9/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_2/9/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_29/8/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_28/8/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_27/8/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_22/8/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_21/8/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_20/8/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_19/8/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_19/8/2024:01451566 _x000D_16/8/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_15/8/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_14/8/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_13/8/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_12/8/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_9/8/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_8/8/2024:26/06/2024 _x000D_6/8/2024:26/06/2024 _x000D_5/8/2024:26/06/2024 _x000D_2/8/2024:26/06/2024 _x000D_1/8/2024:26/06/2024 _x000D_31/7/2024:26/06/2024 _x000D_31/7/2024:26/06/2024 _x000D_30/7/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_29/7/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_29/7/2024:01451566 _x000D_26/7/2024:01451566 _x000D_24/7/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_23/7/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_22/7/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_22/7/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_24/6/2024:Order Completed _x000D_20/6/2024:Order Completed _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_6/9/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_5/9/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_4/9/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_3/9/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_2/9/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_29/8/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_28/8/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_27/8/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_22/8/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_21/8/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_20/8/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_19/8/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_19/8/2024:01451566 _x000D_16/8/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_15/8/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_14/8/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_13/8/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_12/8/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_9/8/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_8/8/2024:26/06/2024 _x000D_6/8/2024:26/06/2024 _x000D_5/8/2024:26/06/2024 _x000D_2/8/2024:26/06/2024 _x000D_1/8/2024:26/06/2024 _x000D_31/7/2024:26/06/2024 _x000D_31/7/2024:26/06/2024 _x000D_30/7/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_29/7/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_29/7/2024:01451566 _x000D_26/7/2024:01451566 _x000D_24/7/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_23/7/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_22/7/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_22/7/2024:#Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. _x000D_24/6/2024:Order Completed _x000D_20/6/2024:Order Completed _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | #Update - Awaiting information about the TRC banding - DP is located across a multi-story store and will likely need OOH(?) will investigate. | 2024-06-07 |  |  |  | 5.CSL | VFS1015614 | 30016953 | 1.Provisioning | AM |  | 2024-06-20 | 2024-08-30 |  | 0 | [11 empty] | 0
634 | 654709 | 3044 | Batch 5 Jul24 | Type 1 | FTTP | Nisa Local | Bedford | MK42 0NT | 2024-06-21 | 19/7/2024:#Update - This order has now been reraised under the correct address - 76 Prince Andrew Way, Carrickfergus _x000D_18/7/2024:#Update - This order has now been reraised under the correct address - 76 Prince Andrew Way, Carrickfergus _x000D_17/7/2024:#Update - This order has now been reraised under the correct address - 76 Prince Andrew Way, Carrickfergus _x000D_16/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a care home which backs onto the petrol station (correct location). Action for Allwyn: Please confirm the correct address for the premise. _x000D_15/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a care home which backs onto the petrol station (correct location). Action for Allwyn: Please confirm the correct address for the premise. _x000D_12/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a care home which backs onto the petrol station (correct location). Action for Allwyn: Please confirm the correct address for the premise. _x000D_11/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a care home which backs onto the petrol station (correct location). Action for Allwyn: Please confirm the correct address for the premise. _x000D_10/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a care home which backs onto the petrol station (correct location). Action for Allwyn: Please confirm the correct address for the premise. _x000D_9/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a care home which backs onto the petrol station (correct location). Action for Allwyn: Please confirm the correct address for the premise. _x000D_4/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a care home which backs onto the petrol station (correct location). Action for Allwyn: Please confirm the correct address for the premise. _x000D_3/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a care home which backs onto the petrol station (correct location). Action for Allwyn: Please confirm the correct address for the premise. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a care home which backs onto the petrol station (correct location). Action for Allwyn: Please confirm the correct address for the premise. _x000D_27/6/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a care home which backs onto the petrol station (correct location). Action for Allwyn: Please confirm the correct address for the premise. _x000D_25/6/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a care home which backs onto the petrol station (correct location). Action for Allwyn: Please confirm the correct address for the premise. _x000D_24/6/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a care home which backs onto the petrol station (correct location). Action for Allwyn: Please confirm the correct address for the premise. _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 19/7/2024:#Update - This order has now been reraised under the correct address - 76 Prince Andrew Way, Carrickfergus _x000D_18/7/2024:#Update - This order has now been reraised under the correct address - 76 Prince Andrew Way, Carrickfergus _x000D_17/7/2024:#Update - This order has now been reraised under the correct address - 76 Prince Andrew Way, Carrickfergus _x000D_16/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a care home which backs onto the petrol station (correct location). Action for Allwyn: Please confirm the correct address for the premise. _x000D_15/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a care home which backs onto the petrol station (correct location). Action for Allwyn: Please confirm the correct address for the premise. _x000D_12/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a care home which backs onto the petrol station (correct location). Action for Allwyn: Please confirm the correct address for the premise. _x000D_11/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a care home which backs onto the petrol station (correct location). Action for Allwyn: Please confirm the correct address for the premise. _x000D_10/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a care home which backs onto the petrol station (correct location). Action for Allwyn: Please confirm the correct address for the premise. _x000D_9/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a care home which backs onto the petrol station (correct location). Action for Allwyn: Please confirm the correct address for the premise. _x000D_4/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a care home which backs onto the petrol station (correct location). Action for Allwyn: Please confirm the correct address for the premise. _x000D_3/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a care home which backs onto the petrol station (correct location). Action for Allwyn: Please confirm the correct address for the premise. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a care home which backs onto the petrol station (correct location). Action for Allwyn: Please confirm the correct address for the premise. _x000D_27/6/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a care home which backs onto the petrol station (correct location). Action for Allwyn: Please confirm the correct address for the premise. _x000D_25/6/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a care home which backs onto the petrol station (correct location). Action for Allwyn: Please confirm the correct address for the premise. _x000D_24/6/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a care home which backs onto the petrol station (correct location). Action for Allwyn: Please confirm the correct address for the premise. _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366151 | 30016679 | 6.Failed router install |  |  | 2024-06-20 | 2024-06-20 | 2024-06-20 | TRUE |  |  |  | 2024-07-12 |  |  |  | 2024-07-15 | 242005008628 |  | 2024-07-16 | 1
635 | 663234 | 3045 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Musgrave Centra | Carrickfergus | BT38 7JA | 2024-06-21 | 6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_19/8/2024:01447073 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_13/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_12/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_9/8/2024:#Update - Order has been raised with the correct address - Allwyn have confirmed the 05/08 AM with the retailer _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update - Order has been raised with the correct address - Allwyn have confirmed the 05/08 AM with the retailer _x000D_29/7/2024:#Update - Order has been raised with the correct address - Allwyn have confirmed the 05/08 AM with the retailer _x000D_29/7/2024:01535079 _x000D_26/7/2024:01535079 _x000D_24/7/2024:#Update - This order has now been reraised under the correct address - 76 Prince Andrew Way, Carrickfergus _x000D_23/7/2024:#Update - This order has now been reraised under the correct address - 76 Prince Andrew Way, Carrickfergus _x000D_22/7/2024:#Update - This order has now been reraised under the correct address - 76 Prince Andrew Way, Carrickfergus _x000D_22/7/2024:#Update - This order has now been reraised under the correct address - 76 Prince Andrew Way, Carrickfergus _x000D_24/6/2024:Order Completed _x000D_20/6/2024:Order Completed _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_19/8/2024:01447073 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_13/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_12/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_9/8/2024:#Update - Order has been raised with the correct address - Allwyn have confirmed the 05/08 AM with the retailer _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update - Order has been raised with the correct address - Allwyn have confirmed the 05/08 AM with the retailer _x000D_29/7/2024:#Update - Order has been raised with the correct address - Allwyn have confirmed the 05/08 AM with the retailer _x000D_29/7/2024:01535079 _x000D_26/7/2024:01535079 _x000D_24/7/2024:#Update - This order has now been reraised under the correct address - 76 Prince Andrew Way, Carrickfergus _x000D_23/7/2024:#Update - This order has now been reraised under the correct address - 76 Prince Andrew Way, Carrickfergus _x000D_22/7/2024:#Update - This order has now been reraised under the correct address - 76 Prince Andrew Way, Carrickfergus _x000D_22/7/2024:#Update - This order has now been reraised under the correct address - 76 Prince Andrew Way, Carrickfergus _x000D_24/6/2024:Order Completed _x000D_20/6/2024:Order Completed _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | #Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1057121 | 30021848 | 2.Commissioning | [9 empty] | 2024-08-27 | [7 empty] | 0
636 | 614449 | 3046 | Batch 5 Jul24 | Type 1 | FTTP | Empire Convenience Store | Sheffield | S5 9ND | 2024-06-21 | 19/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a house directly across the road from the spar and the routing mapped for this job is the routing mapped for the residential home. Action for Allwyn: Please confirm the correct address for the premise. _x000D_18/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a house directly across the road from the spar and the routing mapped for this job is the routing mapped for the residential home. Action for Allwyn: Please confirm the correct address for the premise. _x000D_17/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a house directly across the road from the spar and the routing mapped for this job is the routing mapped for the residential home. Action for Allwyn: Please confirm the correct address for the premise. _x000D_16/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a house directly across the road from the spar and the routing mapped for this job is the routing mapped for the residential home. Action for Allwyn: Please confirm the correct address for the premise. _x000D_15/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a house directly across the road from the spar and the routing mapped for this job is the routing mapped for the residential home. Action for Allwyn: Please confirm the correct address for the premise. _x000D_12/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a house directly across the road from the spar and the routing mapped for this job is the routing mapped for the residential home. Action for Allwyn: Please confirm the correct address for the premise. _x000D_11/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a house directly across the road from the spar and the routing mapped for this job is the routing mapped for the residential home. Action for Allwyn: Please confirm the correct address for the premise. _x000D_10/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a house directly across the road from the spar and the routing mapped for this job is the routing mapped for the residential home. Action for Allwyn: Please confirm the correct address for the premise. _x000D_9/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a house directly across the road from the spar and the routing mapped for this job is the routing mapped for the residential home. Action for Allwyn: Please confirm the correct address for the premise. _x000D_4/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a house directly across the road from the spar and the routing mapped for this job is the routing mapped for the residential home. Action for Allwyn: Please confirm the correct address for the premise. _x000D_3/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a house directly across the road from the spar and the routing mapped for this job is the routing mapped for the residential home. Action for Allwyn: Please confirm the correct address for the premise. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a house directly across the road from the spar and the routing mapped for this job is the routing mapped for the residential home. Action for Allwyn: Please confirm the correct address for the premise. _x000D_27/6/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a house directly across the road from the spar and the routing mapped for this job is the routing mapped for the residential home. Action for Allwyn: Please confirm the correct address for the premise. _x000D_25/6/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a house directly across the road from the spar and the routing mapped for this job is the routing mapped for the residential home. Action for Allwyn: Please confirm the correct address for the premise. _x000D_24/6/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a house directly across the road from the spar and the routing mapped for this job is the routing mapped for the residential home. Action for Allwyn: Please confirm the correct address for the premise. _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 19/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a house directly across the road from the spar and the routing mapped for this job is the routing mapped for the residential home. Action for Allwyn: Please confirm the correct address for the premise. _x000D_18/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a house directly across the road from the spar and the routing mapped for this job is the routing mapped for the residential home. Action for Allwyn: Please confirm the correct address for the premise. _x000D_17/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a house directly across the road from the spar and the routing mapped for this job is the routing mapped for the residential home. Action for Allwyn: Please confirm the correct address for the premise. _x000D_16/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a house directly across the road from the spar and the routing mapped for this job is the routing mapped for the residential home. Action for Allwyn: Please confirm the correct address for the premise. _x000D_15/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a house directly across the road from the spar and the routing mapped for this job is the routing mapped for the residential home. Action for Allwyn: Please confirm the correct address for the premise. _x000D_12/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a house directly across the road from the spar and the routing mapped for this job is the routing mapped for the residential home. Action for Allwyn: Please confirm the correct address for the premise. _x000D_11/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a house directly across the road from the spar and the routing mapped for this job is the routing mapped for the residential home. Action for Allwyn: Please confirm the correct address for the premise. _x000D_10/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a house directly across the road from the spar and the routing mapped for this job is the routing mapped for the residential home. Action for Allwyn: Please confirm the correct address for the premise. _x000D_9/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a house directly across the road from the spar and the routing mapped for this job is the routing mapped for the residential home. Action for Allwyn: Please confirm the correct address for the premise. _x000D_4/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a house directly across the road from the spar and the routing mapped for this job is the routing mapped for the residential home. Action for Allwyn: Please confirm the correct address for the premise. _x000D_3/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a house directly across the road from the spar and the routing mapped for this job is the routing mapped for the residential home. Action for Allwyn: Please confirm the correct address for the premise. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a house directly across the road from the spar and the routing mapped for this job is the routing mapped for the residential home. Action for Allwyn: Please confirm the correct address for the premise. _x000D_27/6/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a house directly across the road from the spar and the routing mapped for this job is the routing mapped for the residential home. Action for Allwyn: Please confirm the correct address for the premise. _x000D_25/6/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a house directly across the road from the spar and the routing mapped for this job is the routing mapped for the residential home. Action for Allwyn: Please confirm the correct address for the premise. _x000D_24/6/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a house directly across the road from the spar and the routing mapped for this job is the routing mapped for the residential home. Action for Allwyn: Please confirm the correct address for the premise. _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366150 | 30016919 | 6.Failed router install |  |  | 2024-06-20 | 2024-06-20 | 2024-06-20 | TRUE |  |  |  | 2024-07-20 |  |  |  | 2024-07-20 | 242005013661 |  | 2024-07-23 | 1
637 | 671970 | 3047 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Spar Ballybeen | Belfast | BT16 2RY | 2024-06-21 | 6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 17/09 PM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 17/09 PM _x000D_4/9/2024:#Update - The routing was incorrect at this site however it has now been resolved and the install can progress as usual. The installation has now been amended to 17/09 PM. Please speak with the retailer regarding installation details and confirm to CSL if 17/09 is a suitable date. _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_19/8/2024:01447018 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_13/8/2024:#Update - Allwyn have confirmed that this store has had a change of Proprietorship (COP) from 603966 - Spar - Belfast to 671970 - SPAR - Ballybeen. The order has now been reraised with the correct information. _x000D_12/8/2024:#Update - Allwyn have confirmed that this store has had a change of Proprietorship (COP) from 603966 - Spar - Belfast to 671970 - SPAR - Ballybeen. The order has now been reraised with the correct information. _x000D_9/8/2024:#Update - Allwyn have confirmed that this store has had a change of Proprietorship (COP) from 603966 - Spar - Belfast to 671970 - SPAR - Ballybeen. The order has now been reraised with the correct information. _x000D_8/8/2024:31/07/2024 _x000D_6/8/2024:31/07/2024 _x000D_5/8/2024:31/07/2024 _x000D_2/8/2024:31/07/2024 _x000D_30/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a house directly across the road from the spar and the routing mapped for this job is the routing mapped for the residential home. Action for Allwyn: Please confirm the correct address for the premise. _x000D_29/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a house directly across the road from the spar and the routing mapped for this job is the routing mapped for the residential home. Action for Allwyn: Please confirm the correct address for the premise. _x000D_29/7/2024:01447018 _x000D_26/7/2024:01447018 _x000D_24/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a house directly across the road from the spar and the routing mapped for this job is the routing mapped for the residential home. Action for Allwyn: Please confirm the correct address for the premise. _x000D_23/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a house directly across the road from the spar and the routing mapped for this job is the routing mapped for the residential home. Action for Allwyn: Please confirm the correct address for the premise. _x000D_22/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a house directly across the road from the spar and the routing mapped for this job is the routing mapped for the residential home. Action for Allwyn: Please confirm the correct address for the premise. _x000D_22/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a house directly across the road from the spar and the routing mapped for this job is the routing mapped for the residential home. Action for Allwyn: Please confirm the correct address for the premise. _x000D_25/6/2024:Order Completed _x000D_24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 17/09 PM _x000D_6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 17/09 PM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 17/09 PM _x000D_4/9/2024:#Update - The routing was incorrect at this site however it has now been resolved and the install can progress as usual. The installation has now been amended to 17/09 PM. Please speak with the retailer regarding installation details and confirm to CSL if 17/09 is a suitable date. _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_19/8/2024:01447018 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_13/8/2024:#Update - Allwyn have confirmed that this store has had a change of Proprietorship (COP) from 603966 - Spar - Belfast to 671970 - SPAR - Ballybeen. The order has now been reraised with the correct information. _x000D_12/8/2024:#Update - Allwyn have confirmed that this store has had a change of Proprietorship (COP) from 603966 - Spar - Belfast to 671970 - SPAR - Ballybeen. The order has now been reraised with the correct information. _x000D_9/8/2024:#Update - Allwyn have confirmed that this store has had a change of Proprietorship (COP) from 603966 - Spar - Belfast to 671970 - SPAR - Ballybeen. The order has now been reraised with the correct information. _x000D_8/8/2024:31/07/2024 _x000D_6/8/2024:31/07/2024 _x000D_5/8/2024:31/07/2024 _x000D_2/8/2024:31/07/2024 _x000D_30/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a house directly across the road from the spar and the routing mapped for this job is the routing mapped for the residential home. Action for Allwyn: Please confirm the correct address for the premise. _x000D_29/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a house directly across the road from the spar and the routing mapped for this job is the routing mapped for the residential home. Action for Allwyn: Please confirm the correct address for the premise. _x000D_29/7/2024:01447018 _x000D_26/7/2024:01447018 _x000D_24/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a house directly across the road from the spar and the routing mapped for this job is the routing mapped for the residential home. Action for Allwyn: Please confirm the correct address for the premise. _x000D_23/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a house directly across the road from the spar and the routing mapped for this job is the routing mapped for the residential home. Action for Allwyn: Please confirm the correct address for the premise. _x000D_22/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a house directly across the road from the spar and the routing mapped for this job is the routing mapped for the residential home. Action for Allwyn: Please confirm the correct address for the premise. _x000D_22/7/2024:#Update - Address verification required - The engineer who attended site stated the address on the job is a house directly across the road from the spar and the routing mapped for this job is the routing mapped for the residential home. Action for Allwyn: Please confirm the correct address for the premise. _x000D_25/6/2024:Order Completed _x000D_24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | Update: Order Amended | #Update - Allwyn confirmed Retailer has agreed to installation on 17/09 PM | 2024-06-07 |  |  |  | 5.CSL | VFP2436017 | 30016665 | 1.Provisioning | AM |  | 2024-06-20 | 2024-08-29 |  | 0 | [11 empty] | 0 | 671970
638 | 638614 | 3050 | Batch 5 Jul24 | Type 1 | FTTP | Mace | Belfast | BT1 1GH | 2024-06-21 | 24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366147 | 30016657 | 6.Failed router install |  |  | 2024-06-20 | 2024-06-20 | 2024-06-20 | TRUE |  |  |  | 2024-07-19 |  |  |  | 2024-07-19 | 242005010311 |  | 2024-07-23 | 1
639 | 663199 | 3051 | Batch 5 Jul24 | Type 1 | SOGEA | Mace | Northampton | NN1 2QL | 2024-06-21 | 24/6/2024:Order Completed _x000D_20/6/2024:Update: Order Completed by Supplier _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 24/6/2024:Order Completed _x000D_20/6/2024:Update: Order Completed by Supplier _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015613 | 30016723 | 6.Failed router install |  |  | 2024-06-20 | 2024-06-20 | 2024-06-20 | TRUE |  |  |  | 2024-07-12 |  |  |  | 2024-07-12 | 242005008629 |  | 2024-07-15 | 1
640 | 233369 | 3058 | Batch 5 Jul24 | Type 1 | FTTP | J P News | SWINDON | SN1 1PN | 2024-06-21 | 24/6/2024:Order Completed _x000D_20/6/2024:Order Completed _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 24/6/2024:Order Completed _x000D_20/6/2024:Order Completed _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366146 | 30016864 | 2.Commissioning |  |  | 2024-06-20 | 2024-06-20 | 2024-06-20 | TRUE |  |  |  | 2024-07-22 | [7 empty] | 0
641 | 472563 | 3059 | Batch 5 Jul24 | Type 1 | SOGEA | Premier Supersave Minimarket | Burnley | BB10 1UA | 2024-06-21 | 24/6/2024:Order Completed _x000D_20/6/2024:Order Completed _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 24/6/2024:Order Completed _x000D_20/6/2024:Order Completed _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015504 | 30016863 | 6.Failed router install |  |  | 2024-06-20 | 2024-06-20 | 2024-06-20 | TRUE |  |  |  | 2024-07-25 |  |  |  | 2024-08-01 | 238004926158 |  | 2024-08-02 | 1
642 | 445091 | 3060 | Batch 5 Jul24 | Type 1 | FTTP | The Bookcorner | LLANDUDNO | LL30 2PS | 2024-06-21 | 24/6/2024:Order Completed _x000D_20/6/2024:Order Completed _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 24/6/2024:Order Completed _x000D_20/6/2024:Order Completed _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366144 | 30016890 | 2.Commissioning |  |  | 2024-06-20 | 2024-06-20 | 2024-06-20 | TRUE |  |  |  | 2024-07-19 | [7 empty] | 0
643 | 641513 | 3061 | Batch 5 Jul24 | Type 1 | SOGEA | Killie Convenience | Kilmarnock | KA1 1LT | 2024-06-21 | 24/6/2024:Order Completed _x000D_20/6/2024:Order Completed _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 24/6/2024:Order Completed _x000D_20/6/2024:Order Completed _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015506 | 30016982 | 2.Commissioning |  |  | 2024-06-20 | 2024-06-20 | 2024-06-20 | TRUE |  |  |  | 2024-07-23 | [7 empty] | 0
644 | 464542 | 3064 | Batch 5 Jul24 | Type 1 | FTTP | Spar | LURGAN | BT66 6JA | 2024-06-21 | 19/7/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_18/7/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_17/7/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_16/7/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_15/7/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_12/7/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_11/7/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_10/7/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_9/7/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_4/7/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_3/7/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_27/6/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_25/6/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_24/6/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_20/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 19/7/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_18/7/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_17/7/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_16/7/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_15/7/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_12/7/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_11/7/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_10/7/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_9/7/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_4/7/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_3/7/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_27/6/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_25/6/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_24/6/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_20/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366143 | 30016923 | 2.Commissioning |  |  | 2024-06-20 | 2024-06-20 | 2024-06-20 | TRUE |  |  |  | 2024-07-10 | [7 empty] | 0
645 | 100498 | 3065 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Premier Sna Supermarket | Southampton | SO18 4QD | 2024-06-21 | 6/9/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_5/9/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_4/9/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_3/9/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_2/9/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_29/8/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_28/8/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_27/8/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_22/8/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_21/8/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_20/8/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_19/8/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_19/8/2024:01445479 _x000D_16/8/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_15/8/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_14/8/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_13/8/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_12/8/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_9/8/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_8/8/2024:21/06/2024 _x000D_6/8/2024:21/06/2024 _x000D_5/8/2024:21/06/2024 _x000D_2/8/2024:21/06/2024 _x000D_1/8/2024:21/06/2024 _x000D_31/7/2024:21/06/2024 _x000D_31/7/2024:21/06/2024 _x000D_30/7/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_29/7/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_29/7/2024:01445479 _x000D_26/7/2024:01445479 _x000D_24/7/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_23/7/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_22/7/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_22/7/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_6/9/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_5/9/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_4/9/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_3/9/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_2/9/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_29/8/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_28/8/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_27/8/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_22/8/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_21/8/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_20/8/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_19/8/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_19/8/2024:01445479 _x000D_16/8/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_15/8/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_14/8/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_13/8/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_12/8/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_9/8/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_8/8/2024:21/06/2024 _x000D_6/8/2024:21/06/2024 _x000D_5/8/2024:21/06/2024 _x000D_2/8/2024:21/06/2024 _x000D_1/8/2024:21/06/2024 _x000D_31/7/2024:21/06/2024 _x000D_31/7/2024:21/06/2024 _x000D_30/7/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_29/7/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_29/7/2024:01445479 _x000D_26/7/2024:01445479 _x000D_24/7/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_23/7/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_22/7/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_22/7/2024:#Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. _x000D_24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | Update: Order Amended | #Update - Missed Appointment - The retailer advised that the line is not required until September. Action for Allwyn: Please discuss this with the retailer to understand why this is and confirm. | 2024-06-07 |  |  |  | 5.CSL | VFS1015502 | 30016728 | 1.Provisioning | AM |  | 2024-06-20 | 2024-09-04 |  | 0 | [11 empty] | 0
646 | 665912 | 3066 | Batch 5 Jul24 | Type 1 | FTTP | Cardonald Post Office | Glasgow | G52 3PF | 2024-06-21 | 24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366141 | 30016739 | 6.Failed router install |  |  | 2024-06-20 | 2024-06-20 | 2024-06-20 | TRUE |  |  |  | 2024-07-23 |  |  |  | 2024-08-16 | 242005009507 | 242005009507 | 2024-08-19 | 1
647 | 664420 | 3067 | Batch 5 Jul24 | Type 1 | SOGEA | Spar Galliagh | LONDONDERRY | BT48 8NU | 2024-06-21 | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:#Update - Retailer aware of new appointment. _x000D_15/7/2024:#Update - Retailer aware of new appointment. _x000D_12/7/2024:#Update - Retailer aware of new appointment. _x000D_11/7/2024:#Update - Retailer aware of new appointment. _x000D_10/7/2024:#Update - Retailer aware of new appointment. _x000D_9/7/2024:#Update - Retailer aware of new appointment. _x000D_4/7/2024:#Update - Shop owner has no idea of this order. So no work carried out - Re-appointed for 11th July - Action for Allwyn : Confirm re-appointment for 11th July Am _x000D_3/7/2024:#Update - Shop owner has no idea of this order. So no work carried out - Re-appointed for 11th July - Action for Allwyn : Confirm re-appointment for 11th July Am _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Shop owner has no idea of this order. So no work carried out - Re-appointed for 11th July - Action for Allwyn : Confirm re-appointment for 11th July Am _x000D_27/6/2024:#Update - Shop owner has no idea of this order. So no work carried out - Re-appointed for 11th July - Action for Allwyn : Confirm re-appointment for 11th July Am _x000D_25/6/2024:#Update - Shop owner has no idea of this order. So no work carried out - Re-appointed for 11th July - Action for Allwyn : Confirm re-appointment for 11th July Am _x000D_24/6/2024:#Update - Shop owner has no idea of this order. So no work carried out - Re-appointed for 11th July - Action for Allwyn : Confirm re-appointment for 11th July Am _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:#Update - Retailer aware of new appointment. _x000D_15/7/2024:#Update - Retailer aware of new appointment. _x000D_12/7/2024:#Update - Retailer aware of new appointment. _x000D_11/7/2024:#Update - Retailer aware of new appointment. _x000D_10/7/2024:#Update - Retailer aware of new appointment. _x000D_9/7/2024:#Update - Retailer aware of new appointment. _x000D_4/7/2024:#Update - Shop owner has no idea of this order. So no work carried out - Re-appointed for 11th July - Action for Allwyn : Confirm re-appointment for 11th July Am _x000D_3/7/2024:#Update - Shop owner has no idea of this order. So no work carried out - Re-appointed for 11th July - Action for Allwyn : Confirm re-appointment for 11th July Am _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Shop owner has no idea of this order. So no work carried out - Re-appointed for 11th July - Action for Allwyn : Confirm re-appointment for 11th July Am _x000D_27/6/2024:#Update - Shop owner has no idea of this order. So no work carried out - Re-appointed for 11th July - Action for Allwyn : Confirm re-appointment for 11th July Am _x000D_25/6/2024:#Update - Shop owner has no idea of this order. So no work carried out - Re-appointed for 11th July - Action for Allwyn : Confirm re-appointment for 11th July Am _x000D_24/6/2024:#Update - Shop owner has no idea of this order. So no work carried out - Re-appointed for 11th July - Action for Allwyn : Confirm re-appointment for 11th July Am _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366142 | 30016914 | 6.Failed router install |  |  | 2024-06-20 | 2024-06-20 | 2024-06-20 | TRUE |  |  |  | 2024-07-22 |  |  |  | 2024-07-22 | 242005010278 |  | 2024-07-23 | 1
648 | 626592 | 3068 | Batch 5 Jul24 | Type 1 | FTTP | Gill News | Wolverhampton | WV6 0QW |  | 14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366140 | 30016756 | 6.Failed router install |  |  | 2024-06-20 | 2024-07-11 | 2024-07-11 | TRUE |  |  |  | 2024-08-12 |  |  |  | 2024-08-12 | 238004926105 | 238004926105 | 2024-08-13 | 1
649 | 652408 | 3070 | Batch 5 Jul24 | Type 1 | FTTP | Newsagents | Northwich | CW8 3EU | 2024-06-21 | 30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:Our test shows the ONT has not been powered up. Contact your end customer to power up the ONT, contact us if they have done so and the service does not work following order completion. CSL Note: Invalid appointment slot received CSL Note: Invalid data rec _x000D_ | 30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:Our test shows the ONT has not been powered up. Contact your end customer to power up the ONT, contact us if they have done so and the service does not work following order completion. CSL Note: Invalid appointment slot received CSL Note: Invalid data rec _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366139 | 30016960 | 2.Commissioning |  |  | 2024-06-20 | 2024-06-20 | 2024-06-20 | TRUE | [11 empty] | 0
650 | 471069 | 3071 | Batch 5 Jul24 | Type 1 | FTTP | Spar | N Ireland | BT82 9EX | 2024-06-21 | 24/6/2024:Order Completed _x000D_20/6/2024:Order Completed _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 24/6/2024:Order Completed _x000D_20/6/2024:Order Completed _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366036 | 30016618 | 6.Failed router install |  |  | 2024-06-20 | 2024-06-20 | 2024-06-20 | TRUE |  |  |  | 2024-07-22 |  |  |  | 2024-07-22 | 242005010317 |  | 2024-07-23 | 1
651 | 486307 | 3073 | Batch 5 Jul24 | Type 1 | SOGEA | SPAR RHYDYFELIN | PONTYPRIDD | CF37 5RW | 2024-06-21 | 4/7/2024:Order Completed _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:Update: Order Amended _x000D_25/6/2024:Update: Order Amended _x000D_24/6/2024:Update: Order Amended _x000D_20/6/2024:Supplier Delay: New Appointment might be required _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 4/7/2024:Order Completed _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:Update: Order Amended _x000D_25/6/2024:Update: Order Amended _x000D_24/6/2024:Update: Order Amended _x000D_20/6/2024:Supplier Delay: New Appointment might be required _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015609 | 30016779 | 6.Failed router install |  |  | 2024-06-20 | 2024-06-20 | 2024-06-20 | TRUE |  |  |  | 2024-07-24 |  |  |  | 2024-07-24 | 239004929406 |  | 2024-07-25 | 1
652 | 631177 | 3074 | Batch 5 Jul24 | Type 1 | SOGEA | SPAR BLACON | Chester | CH1 5PN | 2024-07-05 | 24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1015608 | 30016830 | 2.Commissioning |  |  | 2024-06-20 | 2024-07-04 | 2024-07-04 | TRUE |  |  |  | 2024-08-01 | [7 empty] | 0
653 | 667832 | 3076 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Londis | LEICESTER | LE3 9AR |  | 6/9/2024:#Update - Pushed out to 16/09- AM _x000D_5/9/2024:#Update - Pushed out to 16/09- AM _x000D_4/9/2024:#Update - Pushed out to 16/09- AM _x000D_3/9/2024:#Update - Pushed out to 16/09- AM _x000D_2/9/2024:#Update - Pushed out to 16/09- AM _x000D_29/8/2024:#Update - Pushed out to 16/09- AM _x000D_28/8/2024:#Update - Pushed out to 16/09- AM _x000D_27/8/2024:#Update - Pushed out to 16/09- AM _x000D_22/8/2024:#Update - Retailer has advised that they would prefer to push this further back as they are on holiday - 2nd September _x000D_21/8/2024:#Update - Retailer has advised that they would prefer to push this further back as they are on holiday - 2nd September _x000D_20/8/2024:#Update - Retailer has advised that they would prefer to push this further back as they are on holiday - 2nd September _x000D_19/8/2024:#Update - Retailer has advised that they would prefer to push this further back as they are on holiday - 2nd September _x000D_19/8/2024:01445979 _x000D_16/8/2024:#Update - Retailer has advised that they would prefer to push this further back as they are on holiday - 2nd September _x000D_15/8/2024:#Update - Retailer has advised that they would prefer to push this further back as they are on holiday - 2nd September _x000D_14/8/2024:#Update - Retailer has advised that they would prefer to push this further back as they are on holiday - 2nd September _x000D_13/8/2024:#Update - Retailer has advised that they would prefer to push this further back as they are on holiday - 2nd September _x000D_12/8/2024:#Update - Retailer has advised that they would prefer to push this further back as they are on holiday - 2nd September _x000D_9/8/2024:#Update - Retailer has advised that they would prefer to push this further back as they are on holiday - 2nd September _x000D_8/8/2024:11/07/2024 _x000D_6/8/2024:11/07/2024 _x000D_5/8/2024:11/07/2024 _x000D_2/8/2024:11/07/2024 _x000D_1/8/2024:11/07/2024 _x000D_31/7/2024:11/07/2024 _x000D_31/7/2024:11/07/2024 _x000D_30/7/2024:#Update - Retailer has advised that they would prefer to push this further back as they are on holiday - 2nd September _x000D_29/7/2024:#Update - Retailer has advised that they would prefer to push this further back as they are on holiday - 2nd September _x000D_29/7/2024:01445979 _x000D_26/7/2024:01445979 _x000D_24/7/2024:#Update - Retailer has advised that they would prefer to push this further back as they are on holiday - 2nd September _x000D_23/7/2024:#Update - Retailer has advised that they would prefer to push this further back as they are on holiday - 2nd September _x000D_22/7/2024:#Update - Retailer has advised that they would prefer to push this further back as they are on holiday - 2nd September _x000D_22/7/2024:#Update - Retailer has advised that they would prefer to push this further back as they are on holiday - 2nd September _x000D_19/7/2024:#Update Chased Allwyn for an update. _x000D_18/7/2024:#Update Chased Allwyn for an update. _x000D_17/7/2024:#Update Chased Allwyn for an update. _x000D_16/7/2024:#Update Chased Allwyn for an update. _x000D_15/7/2024:#Update Chased Allwyn for an update. _x000D_12/7/2024:#Update Chased Allwyn for an update. _x000D_11/7/2024:#Update Chased Allwyn for an update. _x000D_10/7/2024:#Update Chased Allwyn for an update. _x000D_9/7/2024:#Update Chased Allwyn for an update. _x000D_4/7/2024:#Update Chased Allwyn for an update. _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:Your order has been delayed. The appointment has been delayed due to a Hazard. Neighbour permission required. Please check with end user and reappoint the order if still required. _x000D_25/6/2024:Your order has been delayed. The appointment has been delayed due to a Hazard. Neighbour permission required. Please check with end user and reappoint the order if still required. _x000D_24/6/2024:Your order has been delayed. The appointment has been delayed due to a Hazard. Neighbour permission required. Please check with end user and reappoint the order if still required. _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:#Update - Pushed out to 16/09- AM _x000D_6/9/2024:#Update - Pushed out to 16/09- AM _x000D_5/9/2024:#Update - Pushed out to 16/09- AM _x000D_4/9/2024:#Update - Pushed out to 16/09- AM _x000D_3/9/2024:#Update - Pushed out to 16/09- AM _x000D_2/9/2024:#Update - Pushed out to 16/09- AM _x000D_29/8/2024:#Update - Pushed out to 16/09- AM _x000D_28/8/2024:#Update - Pushed out to 16/09- AM _x000D_27/8/2024:#Update - Pushed out to 16/09- AM _x000D_22/8/2024:#Update - Retailer has advised that they would prefer to push this further back as they are on holiday - 2nd September _x000D_21/8/2024:#Update - Retailer has advised that they would prefer to push this further back as they are on holiday - 2nd September _x000D_20/8/2024:#Update - Retailer has advised that they would prefer to push this further back as they are on holiday - 2nd September _x000D_19/8/2024:#Update - Retailer has advised that they would prefer to push this further back as they are on holiday - 2nd September _x000D_19/8/2024:01445979 _x000D_16/8/2024:#Update - Retailer has advised that they would prefer to push this further back as they are on holiday - 2nd September _x000D_15/8/2024:#Update - Retailer has advised that they would prefer to push this further back as they are on holiday - 2nd September _x000D_14/8/2024:#Update - Retailer has advised that they would prefer to push this further back as they are on holiday - 2nd September _x000D_13/8/2024:#Update - Retailer has advised that they would prefer to push this further back as they are on holiday - 2nd September _x000D_12/8/2024:#Update - Retailer has advised that they would prefer to push this further back as they are on holiday - 2nd September _x000D_9/8/2024:#Update - Retailer has advised that they would prefer to push this further back as they are on holiday - 2nd September _x000D_8/8/2024:11/07/2024 _x000D_6/8/2024:11/07/2024 _x000D_5/8/2024:11/07/2024 _x000D_2/8/2024:11/07/2024 _x000D_1/8/2024:11/07/2024 _x000D_31/7/2024:11/07/2024 _x000D_31/7/2024:11/07/2024 _x000D_30/7/2024:#Update - Retailer has advised that they would prefer to push this further back as they are on holiday - 2nd September _x000D_29/7/2024:#Update - Retailer has advised that they would prefer to push this further back as they are on holiday - 2nd September _x000D_29/7/2024:01445979 _x000D_26/7/2024:01445979 _x000D_24/7/2024:#Update - Retailer has advised that they would prefer to push this further back as they are on holiday - 2nd September _x000D_23/7/2024:#Update - Retailer has advised that they would prefer to push this further back as they are on holiday - 2nd September _x000D_22/7/2024:#Update - Retailer has advised that they would prefer to push this further back as they are on holiday - 2nd September _x000D_22/7/2024:#Update - Retailer has advised that they would prefer to push this further back as they are on holiday - 2nd September _x000D_19/7/2024:#Update Chased Allwyn for an update. _x000D_18/7/2024:#Update Chased Allwyn for an update. _x000D_17/7/2024:#Update Chased Allwyn for an update. _x000D_16/7/2024:#Update Chased Allwyn for an update. _x000D_15/7/2024:#Update Chased Allwyn for an update. _x000D_12/7/2024:#Update Chased Allwyn for an update. _x000D_11/7/2024:#Update Chased Allwyn for an update. _x000D_10/7/2024:#Update Chased Allwyn for an update. _x000D_9/7/2024:#Update Chased Allwyn for an update. _x000D_4/7/2024:#Update Chased Allwyn for an update. _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:Your order has been delayed. The appointment has been delayed due to a Hazard. Neighbour permission required. Please check with end user and reappoint the order if still required. _x000D_25/6/2024:Your order has been delayed. The appointment has been delayed due to a Hazard. Neighbour permission required. Please check with end user and reappoint the order if still required. _x000D_24/6/2024:Your order has been delayed. The appointment has been delayed due to a Hazard. Neighbour permission required. Please check with end user and reappoint the order if still required. _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | #Update - Pushed out to 16/09- AM | 2024-06-07 |  |  |  |  | VFS1015501 | 30016636 | 1.Provisioning | AM |  | 2024-06-20 | 2024-09-02 |  | 0 | [11 empty] | 0
654 | 448273 | 470 | Batch 3 May24 | Type 1 | SOGEA | Hardings Newsagents | LONDON | SW11 3JR | 2024-05-30 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:#Update Retailer confirmed new appointment 21/06, AM. _x000D_24/6/2024:#Update Retailer confirmed new appointment 21/06, AM. _x000D_20/6/2024:#Update Retailer confirmed new appointment 21/06, AM. _x000D_19/6/2024:#Update Retailer confirmed new appointment 21/06, AM. _x000D_18/6/2024:#Update Retailer confirmed new appointment 21/06, AM. _x000D_17/6/2024:#Update Retailer confirmed new appointment 21/06, AM. _x000D_14/6/2024:#Update Retailer confirmed new appointment 21/06, AM. _x000D_13/6/2024:#Update Allwyn unable to get hold of retailer, pushed out to 21/06, AM. Action on Allwyn - make retailer aware of new appointment. _x000D_12/6/2024:#Update Allwyn unable to get hold of retailer, pushed out to 21/06, AM. Action on Allwyn - make retailer aware of new appointment. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:#Update Retailer confirmed new appointment 21/06, AM. _x000D_24/6/2024:#Update Retailer confirmed new appointment 21/06, AM. _x000D_20/6/2024:#Update Retailer confirmed new appointment 21/06, AM. _x000D_19/6/2024:#Update Retailer confirmed new appointment 21/06, AM. _x000D_18/6/2024:#Update Retailer confirmed new appointment 21/06, AM. _x000D_17/6/2024:#Update Retailer confirmed new appointment 21/06, AM. _x000D_14/6/2024:#Update Retailer confirmed new appointment 21/06, AM. _x000D_13/6/2024:#Update Allwyn unable to get hold of retailer, pushed out to 21/06, AM. Action on Allwyn - make retailer aware of new appointment. _x000D_12/6/2024:#Update Allwyn unable to get hold of retailer, pushed out to 21/06, AM. Action on Allwyn - make retailer aware of new appointment. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 0 | 0 | 2024-05-07 | 07/05/2024: CSL to provide an update |  |  | 3.Allwyn to arrange rtr install | VFP2300667 | 30013360 | 2.Commissioning | AM | [8 empty] | 2024-08-02 | [7 empty] | 0
655 | 612211 | 674 | Batch 3 May24 | Type 1 | FTTP | Kellys Booze | Everton | L5 6PT | 2024-06-07 | 11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 21/06 at 8 AM _x000D_24/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 21/06 at 8 AM _x000D_20/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 21/06 at 8 AM _x000D_19/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 21/06 at 8 AM _x000D_18/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 21/06 at 8 AM _x000D_17/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 21/06 at 8 AM _x000D_14/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 21/06 at 8 AM _x000D_13/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 21/06 at 8 AM _x000D_12/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 21/06 at 8 AM _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 21/06 at 8 AM _x000D_24/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 21/06 at 8 AM _x000D_20/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 21/06 at 8 AM _x000D_19/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 21/06 at 8 AM _x000D_18/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 21/06 at 8 AM _x000D_17/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 21/06 at 8 AM _x000D_14/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 21/06 at 8 AM _x000D_13/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 21/06 at 8 AM _x000D_12/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 21/06 at 8 AM _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-05-16 |  |  |  | 3.Allwyn to arrange rtr install | VFP2300871 | 30013564 | 6.Failed router install | AM |  | 2024-05-15 | 2024-06-21 | 2024-06-21 | TRUE |  |  |  | 2024-07-11 |  |  |  | 2024-07-11 | 242005008856 |  | 2024-07-12 | 1
656 | 411177 | 981 | Batch 3 May24 | Type 1 | SoGEA/Mobile | Khan Post Office | MANCHESTER | M18 7QT | 2024-06-07 | 6/9/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_5/9/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_4/9/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_3/9/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_2/9/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_29/8/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_28/8/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_27/8/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_22/8/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_21/8/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_20/8/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_19/8/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_19/8/2024:01404145 _x000D_16/8/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_15/8/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_14/8/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_13/8/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_12/8/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_9/8/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_8/8/2024:05/06/2024 _x000D_6/8/2024:05/06/2024 _x000D_5/8/2024:05/06/2024 _x000D_2/8/2024:05/06/2024 _x000D_1/8/2024:05/06/2024 _x000D_31/7/2024:05/06/2024 _x000D_31/7/2024:05/06/2024 _x000D_30/7/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_29/7/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_29/7/2024:01404145 _x000D_26/7/2024:01404145 _x000D_24/7/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_23/7/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_22/7/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_22/7/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_19/7/2024:#Update Retailer aware of new appointment 26/07, AM. _x000D_18/7/2024:#Update Retailer aware of new appointment 26/07, AM. _x000D_17/7/2024:#Update Retailer aware of new appointment 26/07, AM. _x000D_16/7/2024:#Update Retailer happy with new appointment 12/07, AM. _x000D_15/7/2024:#Update Retailer happy with new appointment 12/07, AM. _x000D_12/7/2024:#Update Retailer happy with new appointment 12/07, AM. _x000D_11/7/2024:#Update Retailer happy with new appointment 12/07, AM. _x000D_10/7/2024:#Update Retailer happy with new appointment 12/07, AM. _x000D_9/7/2024:#Update Retailer happy with new appointment 12/07, AM. _x000D_4/7/2024:#Update Retailer happy with new appointment 12/07, AM. _x000D_3/7/2024:#Update Retailer happy with new appointment 12/07, AM. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update Missed appointment due to retailer being on holiday. Action on Allwyn - find out when they are back so I can reappoint. _x000D_27/6/2024:#Update Missed appointment due to retailer being on holiday. Action on Allwyn - find out when they are back so I can reappoint. _x000D_25/6/2024:#Update Missed appointment due to retailer being on holiday. Action on Allwyn - find out when they are back so I can reappoint. _x000D_24/6/2024:#Update Missed appointment due to retailer being on holiday. Action on Allwyn - find out when they are back so I can reappoint. _x000D_20/6/2024:#Update Missed appointment due to retailer being on holiday. Action on Allwyn - find out when they are back so I can reappoint. _x000D_19/6/2024:#Update Missed appointment due to retailer being on holiday. Action on Allwyn - find out when they are back so I can reappoint. _x000D_18/6/2024:#Update Missed appointment due to retailer being on holiday. Action on Allwyn - find out when they are back so I can reappoint. _x000D_17/6/2024:#Update Missed appointment due to retailer being on holiday. Action on Allwyn - find out when they are back so I can reappoint. _x000D_14/6/2024:#Update Missed appointment due to retailer being on holiday. Action on Allwyn - find out when they are back so I can reappoint. _x000D_13/6/2024:#Update Missed appointment due to retailer being on holiday. Action on Allwyn - find out when they are back so I can reappoint. _x000D_12/6/2024:#Update Missed appointment due to retailer being on holiday. Action on Allwyn - find out when they are back so I can reappoint. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_6/9/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_5/9/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_4/9/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_3/9/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_2/9/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_29/8/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_28/8/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_27/8/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_22/8/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_21/8/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_20/8/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_19/8/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_19/8/2024:01404145 _x000D_16/8/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_15/8/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_14/8/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_13/8/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_12/8/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_9/8/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_8/8/2024:05/06/2024 _x000D_6/8/2024:05/06/2024 _x000D_5/8/2024:05/06/2024 _x000D_2/8/2024:05/06/2024 _x000D_1/8/2024:05/06/2024 _x000D_31/7/2024:05/06/2024 _x000D_31/7/2024:05/06/2024 _x000D_30/7/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_29/7/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_29/7/2024:01404145 _x000D_26/7/2024:01404145 _x000D_24/7/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_23/7/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_22/7/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_22/7/2024:#Update - awaiting approval for OOH proposal, sent 31/05 _x000D_19/7/2024:#Update Retailer aware of new appointment 26/07, AM. _x000D_18/7/2024:#Update Retailer aware of new appointment 26/07, AM. _x000D_17/7/2024:#Update Retailer aware of new appointment 26/07, AM. _x000D_16/7/2024:#Update Retailer happy with new appointment 12/07, AM. _x000D_15/7/2024:#Update Retailer happy with new appointment 12/07, AM. _x000D_12/7/2024:#Update Retailer happy with new appointment 12/07, AM. _x000D_11/7/2024:#Update Retailer happy with new appointment 12/07, AM. _x000D_10/7/2024:#Update Retailer happy with new appointment 12/07, AM. _x000D_9/7/2024:#Update Retailer happy with new appointment 12/07, AM. _x000D_4/7/2024:#Update Retailer happy with new appointment 12/07, AM. _x000D_3/7/2024:#Update Retailer happy with new appointment 12/07, AM. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update Missed appointment due to retailer being on holiday. Action on Allwyn - find out when they are back so I can reappoint. _x000D_27/6/2024:#Update Missed appointment due to retailer being on holiday. Action on Allwyn - find out when they are back so I can reappoint. _x000D_25/6/2024:#Update Missed appointment due to retailer being on holiday. Action on Allwyn - find out when they are back so I can reappoint. _x000D_24/6/2024:#Update Missed appointment due to retailer being on holiday. Action on Allwyn - find out when they are back so I can reappoint. _x000D_20/6/2024:#Update Missed appointment due to retailer being on holiday. Action on Allwyn - find out when they are back so I can reappoint. _x000D_19/6/2024:#Update Missed appointment due to retailer being on holiday. Action on Allwyn - find out when they are back so I can reappoint. _x000D_18/6/2024:#Update Missed appointment due to retailer being on holiday. Action on Allwyn - find out when they are back so I can reappoint. _x000D_17/6/2024:#Update Missed appointment due to retailer being on holiday. Action on Allwyn - find out when they are back so I can reappoint. _x000D_14/6/2024:#Update Missed appointment due to retailer being on holiday. Action on Allwyn - find out when they are back so I can reappoint. _x000D_13/6/2024:#Update Missed appointment due to retailer being on holiday. Action on Allwyn - find out when they are back so I can reappoint. _x000D_12/6/2024:#Update Missed appointment due to retailer being on holiday. Action on Allwyn - find out when they are back so I can reappoint. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | #Update - awaiting approval for OOH proposal, sent 31/05 |  |  |  |  | 2.Allwyn to arrange access | VFS978088 | 30013871 | 1.Provisioning | AM |  | 2024-05-21 | 2024-09-16 |  | 0 | [11 empty] | 0
657 | 424019 | 991 | Batch 3 May24 | Type 1 | SoGEA/Mobile | NEWS PLUS | Brechin | DD9 6EG | 2024-06-07 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:Update: Order Amended _x000D_28/8/2024:Update: Order Amended _x000D_27/8/2024:0 _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:Update: Order Amended _x000D_19/8/2024:Update: Order Amended _x000D_19/8/2024:16/08/2024 07:58 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:Update: Order Amended _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:23/07/2024 09:06 _x000D_26/7/2024:23/07/2024 09:06 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:#Update - NFA = Allwyn confirmed new install date with retailer _x000D_25/6/2024:#Update - NFA = Allwyn confirmed new install date with retailer _x000D_24/6/2024:#Update - NFA = Allwyn confirmed new install date with retailer _x000D_20/6/2024:#Update - NFA = Allwyn confirmed new install date with retailer _x000D_19/6/2024:#Update - NFA = Allwyn confirmed new install date with retailer _x000D_18/6/2024:#Update - NFA = Allwyn confirmed new install date with retailer _x000D_17/6/2024:#Update - NFA = Allwyn confirmed new install date with retailer _x000D_14/6/2024:#Update - NFA = Allwyn confirmed new install date with retailer _x000D_13/6/2024:#Update - NFA = Allwyn confirmed new install date with retailer _x000D_12/6/2024:#Update - NFA = Allwyn confirmed new install date with retailer _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:Update: Order Amended _x000D_28/8/2024:Update: Order Amended _x000D_27/8/2024:0 _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:Update: Order Amended _x000D_19/8/2024:Update: Order Amended _x000D_19/8/2024:16/08/2024 07:58 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:Update: Order Amended _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:23/07/2024 09:06 _x000D_26/7/2024:23/07/2024 09:06 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:#Update - NFA = Allwyn confirmed new install date with retailer _x000D_25/6/2024:#Update - NFA = Allwyn confirmed new install date with retailer _x000D_24/6/2024:#Update - NFA = Allwyn confirmed new install date with retailer _x000D_20/6/2024:#Update - NFA = Allwyn confirmed new install date with retailer _x000D_19/6/2024:#Update - NFA = Allwyn confirmed new install date with retailer _x000D_18/6/2024:#Update - NFA = Allwyn confirmed new install date with retailer _x000D_17/6/2024:#Update - NFA = Allwyn confirmed new install date with retailer _x000D_14/6/2024:#Update - NFA = Allwyn confirmed new install date with retailer _x000D_13/6/2024:#Update - NFA = Allwyn confirmed new install date with retailer _x000D_12/6/2024:#Update - NFA = Allwyn confirmed new install date with retailer _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | 0 | 2024-05-22 | 22/05/24: CSL to provide the new date |  |  | 5.CSL | VFS975529 | 30013881 | 1.Provisioning | AM |  | 2024-05-21 | 2024-08-19 |  | 0 | [11 empty] | 0
658 | 665632 | 1059 | Batch 3 May24 | Type 1 | FTTP/Mobile | Post Office | Lothian | EH33 1AE | 2024-06-07 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:Update: Order Amended _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:Update: Order Amended _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:0 _x000D_27/6/2024:#Update Retailer aware of the new appointment. _x000D_25/6/2024:#Update Retailer aware of the new appointment. _x000D_24/6/2024:#Update Retailer aware of the new appointment. _x000D_20/6/2024:#Update Retailer aware of the new appointment. _x000D_19/6/2024:#Update Retailer aware of the new appointment. _x000D_18/6/2024:#Update Retailer aware of the new appointment. _x000D_17/6/2024:#Update Retailer aware of the new appointment. _x000D_14/6/2024:#Update Reappointed to 21/06 due to needing a scaffolding tower to access DP. Action on Allwyn - ensure the retailer is aware. _x000D_13/6/2024:#Update Reappointed to 21/06 due to needing a scaffolding tower to access DP. Action on Allwyn - ensure the retailer is aware. _x000D_12/6/2024:#Update Scaffold tower needed to access DP. Awaiting a reply from OR to advise further. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:Update: Order Amended _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:Update: Order Amended _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:0 _x000D_27/6/2024:#Update Retailer aware of the new appointment. _x000D_25/6/2024:#Update Retailer aware of the new appointment. _x000D_24/6/2024:#Update Retailer aware of the new appointment. _x000D_20/6/2024:#Update Retailer aware of the new appointment. _x000D_19/6/2024:#Update Retailer aware of the new appointment. _x000D_18/6/2024:#Update Retailer aware of the new appointment. _x000D_17/6/2024:#Update Retailer aware of the new appointment. _x000D_14/6/2024:#Update Reappointed to 21/06 due to needing a scaffolding tower to access DP. Action on Allwyn - ensure the retailer is aware. _x000D_13/6/2024:#Update Reappointed to 21/06 due to needing a scaffolding tower to access DP. Action on Allwyn - ensure the retailer is aware. _x000D_12/6/2024:#Update Scaffold tower needed to access DP. Awaiting a reply from OR to advise further. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | 0 | 2024-05-23 | 23/05/24: Allwyn to arrange access on the new date |  |  | 2.Allwyn to arrange access | VFP2330406 | 30013949 | 1.Provisioning | AM |  | 2024-05-22 | 2024-08-30 |  | 0 | [11 empty] | 0
659 | 486179 | 1203 | Batch 3 May24 | Type 1 | SOGEA | Londis Supermarket | Anstey | LE7 7AZ | 2024-06-07 | 23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_25/6/2024:Order Completed _x000D_24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_25/6/2024:Order Completed _x000D_24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-05-29 | 29/05/24: CSL to provide an update |  |  | 3.Allwyn to arrange rtr install | VFP2301400 | 30014093 | 6.Failed router install | AM |  | 2024-05-28 | 2024-06-21 | 2024-06-24 | TRUE |  |  |  | 2024-07-22 |  |  |  | 2024-07-22 | 23A004946003 |  | 2024-07-23 | 1
660 | 629867 | 1291 | Batch 3 May24 | Type 1 | SOGEA | Daily Stop | Liverpool | L14 9PW | 2024-06-07 | 19/7/2024:Order Completed _x000D_18/7/2024:Order Completed _x000D_17/7/2024:Order Completed _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:Update: Order Amended _x000D_24/6/2024:Update: Order Amended _x000D_20/6/2024:Update: Order Amended _x000D_19/6/2024:Update: Order Amended _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:Update: Order Amended _x000D_12/6/2024:Update: Order Amended _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:Order Completed _x000D_18/7/2024:Order Completed _x000D_17/7/2024:Order Completed _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:Update: Order Amended _x000D_24/6/2024:Update: Order Amended _x000D_20/6/2024:Update: Order Amended _x000D_19/6/2024:Update: Order Amended _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:Update: Order Amended _x000D_12/6/2024:Update: Order Amended _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301488 | 30014181 | 2.Commissioning | AM |  | 2024-05-30 | 2024-06-21 | 2024-06-21 | TRUE |  |  |  | 2024-07-11 | [7 empty] | 0
661 | 670356 | 1330 | Batch 4 Jun24 | Type 1 | SOGEA | Nisa Local | DUNFERMLINE | KY11 4HA | 2024-06-07 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_25/6/2024:#Update - Order Complete _x000D_24/6/2024:#Update - Order Complete _x000D_20/6/2024:#Update Order reappointed to 21/06/2024 - pending updates from Openreach _x000D_19/6/2024:#Update Order reappointed to 21/06/2024 - pending updates from Openreach _x000D_18/6/2024:#Update Order reappointed to 21/06/2024 - pending updates from Openreach _x000D_17/6/2024:#Update Order reappointed to 21/06/2024 - pending updates from Openreach _x000D_14/6/2024:#Update Order reappointed to 21/06/2024 - pending updates from Openreach _x000D_13/6/2024:#Update Order reappointed to 21/06/2024 - pending updates from Openreach _x000D_12/6/2024:#Update Order reappointed to 21/06/2024 - pending updates from Openreach _x000D_10/6/2024:#Update Order reappointed to 21/06/2024 - pending updates from Openreach _x000D_7/6/2024:#Update Order reappointed to 21/06/2024 - pending updates from Openreach _x000D_6/6/2024:Supplier Delay: New Appointment might be required _x000D_5/6/2024:Supplier Delay: New Appointment might be required _x000D_4/6/2024:Supplier Delay: New Appointment might be required _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_25/6/2024:#Update - Order Complete _x000D_24/6/2024:#Update - Order Complete _x000D_20/6/2024:#Update Order reappointed to 21/06/2024 - pending updates from Openreach _x000D_19/6/2024:#Update Order reappointed to 21/06/2024 - pending updates from Openreach _x000D_18/6/2024:#Update Order reappointed to 21/06/2024 - pending updates from Openreach _x000D_17/6/2024:#Update Order reappointed to 21/06/2024 - pending updates from Openreach _x000D_14/6/2024:#Update Order reappointed to 21/06/2024 - pending updates from Openreach _x000D_13/6/2024:#Update Order reappointed to 21/06/2024 - pending updates from Openreach _x000D_12/6/2024:#Update Order reappointed to 21/06/2024 - pending updates from Openreach _x000D_10/6/2024:#Update Order reappointed to 21/06/2024 - pending updates from Openreach _x000D_7/6/2024:#Update Order reappointed to 21/06/2024 - pending updates from Openreach _x000D_6/6/2024:Supplier Delay: New Appointment might be required _x000D_5/6/2024:Supplier Delay: New Appointment might be required _x000D_4/6/2024:Supplier Delay: New Appointment might be required _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 0 | 0 |  |  |  |  | 3.Allwyn to arrange rtr install | VFS984896 | 30015639 | 2.Commissioning | AM | [8 empty] | 2024-08-20 | [7 empty] | 0 | 670356
662 | 657544 | 1766 | Batch 4 Jun24 | Type 1 | SOGEA | S A News | Sheffield | S9 5HQ | 2024-06-07 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_18/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_17/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_16/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_15/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_12/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_11/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_10/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_9/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_4/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_3/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - NFA - Allwyn have confirmed new installation date with retailer _x000D_27/6/2024:#Update - NFA - Allwyn have confirmed new installation date with retailer _x000D_25/6/2024:#Update - NFA - Allwyn have confirmed new installation date with retailer _x000D_24/6/2024:#Update - NFA - Allwyn have confirmed new installation date with retailer _x000D_20/6/2024:#Update - NFA - Allwyn have confirmed new installation date with retailer _x000D_19/6/2024:#Update - NFA - Allwyn have confirmed new installation date with retailer _x000D_18/6/2024:#Update - NFA - Allwyn have confirmed new installation date with retailer _x000D_17/6/2024:#Update - NFA - Allwyn have confirmed rescheduled install date with retailer _x000D_14/6/2024:#Update - NFA - Allwyn have confirmed rescheduled install date with retailer _x000D_13/6/2024:#Update - NFA - Allwyn have confirmed rescheduled install date with retailer _x000D_12/6/2024:#Update - NFA - Allwyn have confirmed rescheduled install date with retailer _x000D_10/6/2024:Update: Order Amended _x000D_7/6/2024:End User Missed appointment. Action required _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_18/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_17/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_16/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_15/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_12/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_11/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_10/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_9/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_4/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_3/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - NFA - Allwyn have confirmed new installation date with retailer _x000D_27/6/2024:#Update - NFA - Allwyn have confirmed new installation date with retailer _x000D_25/6/2024:#Update - NFA - Allwyn have confirmed new installation date with retailer _x000D_24/6/2024:#Update - NFA - Allwyn have confirmed new installation date with retailer _x000D_20/6/2024:#Update - NFA - Allwyn have confirmed new installation date with retailer _x000D_19/6/2024:#Update - NFA - Allwyn have confirmed new installation date with retailer _x000D_18/6/2024:#Update - NFA - Allwyn have confirmed new installation date with retailer _x000D_17/6/2024:#Update - NFA - Allwyn have confirmed rescheduled install date with retailer _x000D_14/6/2024:#Update - NFA - Allwyn have confirmed rescheduled install date with retailer _x000D_13/6/2024:#Update - NFA - Allwyn have confirmed rescheduled install date with retailer _x000D_12/6/2024:#Update - NFA - Allwyn have confirmed rescheduled install date with retailer _x000D_10/6/2024:Update: Order Amended _x000D_7/6/2024:End User Missed appointment. Action required _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 0 | 0 | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983300 | 30015232 | 2.Commissioning | AM | [8 empty] | 2024-07-20 | [7 empty] | 0
663 | 625230 | 1785 | Batch 4 Jun24 | Type 1 | SoGEA/Mobile | Westpoint Food Center | London | N9 9BU | 2024-07-11 | 6/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 11/07 _x000D_5/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 11/07 _x000D_4/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 11/07 _x000D_3/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 11/07 _x000D_2/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 11/07 _x000D_29/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 11/07 _x000D_28/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 11/07 _x000D_27/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 11/07 _x000D_22/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 11/07 _x000D_21/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 11/07 _x000D_20/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_19/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_19/8/2024:01426965 _x000D_16/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_15/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_14/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_13/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_12/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_9/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_8/8/2024:02/07/2024 _x000D_6/8/2024:02/07/2024 _x000D_5/8/2024:02/07/2024 _x000D_2/8/2024:02/07/2024 _x000D_1/8/2024:02/07/2024 _x000D_31/7/2024:02/07/2024 _x000D_31/7/2024:02/07/2024 _x000D_30/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_29/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_29/7/2024:01426965 _x000D_26/7/2024:01426965 _x000D_24/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_23/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_22/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_22/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:#Update Retailer confirmed new appointment, 21/06, AM. _x000D_24/6/2024:#Update Retailer confirmed new appointment, 21/06, AM. _x000D_20/6/2024:#Update Retailer confirmed new appointment, 21/06, AM. _x000D_19/6/2024:#Update Retailer confirmed new appointment, 21/06, AM. _x000D_18/6/2024:#Update Retailer confirmed new appointment, 21/06, AM. _x000D_17/6/2024:#Update Retailer confirmed new appointment, 21/06, AM. _x000D_14/6/2024:#Update Retailer confirmed new appointment, 21/06, AM. _x000D_13/6/2024:#Update Retailer confirmed new appointment, 21/06, AM. _x000D_12/6/2024:#Update Retailer confirmed new appointment, 21/06, AM. _x000D_10/6/2024:Supplier Delay: New Appointment might be required _x000D_7/6/2024:Supplier Delay: New Appointment might be required _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 9/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 11/07 _x000D_6/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 11/07 _x000D_5/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 11/07 _x000D_4/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 11/07 _x000D_3/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 11/07 _x000D_2/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 11/07 _x000D_29/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 11/07 _x000D_28/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 11/07 _x000D_27/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 11/07 _x000D_22/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 11/07 _x000D_21/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 11/07 _x000D_20/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_19/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_19/8/2024:01426965 _x000D_16/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_15/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_14/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_13/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_12/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_9/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_8/8/2024:02/07/2024 _x000D_6/8/2024:02/07/2024 _x000D_5/8/2024:02/07/2024 _x000D_2/8/2024:02/07/2024 _x000D_1/8/2024:02/07/2024 _x000D_31/7/2024:02/07/2024 _x000D_31/7/2024:02/07/2024 _x000D_30/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_29/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_29/7/2024:01426965 _x000D_26/7/2024:01426965 _x000D_24/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_23/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_22/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_22/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 10/07 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:#Update Retailer confirmed new appointment, 21/06, AM. _x000D_24/6/2024:#Update Retailer confirmed new appointment, 21/06, AM. _x000D_20/6/2024:#Update Retailer confirmed new appointment, 21/06, AM. _x000D_19/6/2024:#Update Retailer confirmed new appointment, 21/06, AM. _x000D_18/6/2024:#Update Retailer confirmed new appointment, 21/06, AM. _x000D_17/6/2024:#Update Retailer confirmed new appointment, 21/06, AM. _x000D_14/6/2024:#Update Retailer confirmed new appointment, 21/06, AM. _x000D_13/6/2024:#Update Retailer confirmed new appointment, 21/06, AM. _x000D_12/6/2024:#Update Retailer confirmed new appointment, 21/06, AM. _x000D_10/6/2024:Supplier Delay: New Appointment might be required _x000D_7/6/2024:Supplier Delay: New Appointment might be required _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 0 | #Update - awaiting ECC approval from customer - proposal sent to VF 11/07 | 2024-06-07 | 7/6/2024: CSL to provide an update |  |  | 5.CSL | VFS983318 | 30015176 | 1.Provisioning | AM |  | 2024-06-06 | 2024-08-28 |  | 0 | [11 empty] | 0
664 | 627910 | 1946 | Batch 4 Jun24 | Type 1 | SOGEA | Greenisland Service Station | Greenisland | BT38 8RH | 2024-06-10 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:Update: Order Amended _x000D_15/7/2024:Update: Order Amended _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:Update: Order Amended _x000D_25/6/2024:Update: Order Amended _x000D_24/6/2024:Update: Order Amended _x000D_20/6/2024:Update: Order Amended _x000D_19/6/2024:Update: Order Amended _x000D_18/6/2024:Update: Order Amended _x000D_17/6/2024:0 _x000D_14/6/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Now order got re-appointed for 21/06/2024 _x000D_13/6/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Now order got re-appointed for 21/06/2024 _x000D_12/6/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Now order got re-appointed for 21/06/2024 _x000D_10/6/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Now order got re-appointed for 21/06/2024 _x000D_7/6/2024:End User Missed appointment. Action required _x000D_6/6/2024:End User Missed appointment. Action required _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:Update: Order Amended _x000D_15/7/2024:Update: Order Amended _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:Update: Order Amended _x000D_25/6/2024:Update: Order Amended _x000D_24/6/2024:Update: Order Amended _x000D_20/6/2024:Update: Order Amended _x000D_19/6/2024:Update: Order Amended _x000D_18/6/2024:Update: Order Amended _x000D_17/6/2024:0 _x000D_14/6/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Now order got re-appointed for 21/06/2024 _x000D_13/6/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Now order got re-appointed for 21/06/2024 _x000D_12/6/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Now order got re-appointed for 21/06/2024 _x000D_10/6/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Now order got re-appointed for 21/06/2024 _x000D_7/6/2024:End User Missed appointment. Action required _x000D_6/6/2024:End User Missed appointment. Action required _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 0 | 0 | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983520 | 30015728 | 2.Commissioning | AM | [8 empty] | 2024-07-24 | [7 empty] | 0
665 | 664850 | 1703 | Batch 4 Jun24 | Type 1 | SoGEA/Mobile | Post Office | Llanbydder | SA40 9XP | 2024-06-07 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:Your order has been delayed due to a customer missed appointment. OOH appointment required. Please check with end user and reappoint the order if still required. _x000D_22/8/2024:Your order has been delayed due to a customer missed appointment. OOH appointment required. Please check with end user and reappoint the order if still required. _x000D_21/8/2024:Your order has been delayed due to a customer missed appointment. OOH appointment required. Please check with end user and reappoint the order if still required. _x000D_20/8/2024:End User Missed appointment. Action required _x000D_19/8/2024:End User Missed appointment. Action required _x000D_19/8/2024:19/08/2024 08:43 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 06:18 _x000D_26/7/2024:22/07/2024 06:18 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer (12/08) _x000D_18/7/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer (12/08) _x000D_17/7/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer (12/08) _x000D_16/7/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer (12/08) _x000D_15/7/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer (12/08) _x000D_12/7/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer (12/08) _x000D_11/7/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer (12/08) _x000D_10/7/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer (12/08) _x000D_9/7/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer (12/08) _x000D_4/7/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer (12/08) _x000D_3/7/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer (12/08) _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer (12/08) _x000D_27/6/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer (12/08) _x000D_25/6/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer (12/08) _x000D_24/6/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer (12/08) _x000D_20/6/2024:Update: Order Amended _x000D_19/6/2024:Update: Order Amended _x000D_18/6/2024:Update: Order Amended _x000D_17/6/2024:0 _x000D_14/6/2024:Update: Order Amended _x000D_13/6/2024:Update: Order Amended _x000D_12/6/2024:Update: Order Amended _x000D_10/6/2024:Update: Order Amended _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:Your order has been delayed due to a customer missed appointment. OOH appointment required. Please check with end user and reappoint the order if still required. _x000D_22/8/2024:Your order has been delayed due to a customer missed appointment. OOH appointment required. Please check with end user and reappoint the order if still required. _x000D_21/8/2024:Your order has been delayed due to a customer missed appointment. OOH appointment required. Please check with end user and reappoint the order if still required. _x000D_20/8/2024:End User Missed appointment. Action required _x000D_19/8/2024:End User Missed appointment. Action required _x000D_19/8/2024:19/08/2024 08:43 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 06:18 _x000D_26/7/2024:22/07/2024 06:18 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer (12/08) _x000D_18/7/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer (12/08) _x000D_17/7/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer (12/08) _x000D_16/7/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer (12/08) _x000D_15/7/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer (12/08) _x000D_12/7/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer (12/08) _x000D_11/7/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer (12/08) _x000D_10/7/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer (12/08) _x000D_9/7/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer (12/08) _x000D_4/7/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer (12/08) _x000D_3/7/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer (12/08) _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer (12/08) _x000D_27/6/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer (12/08) _x000D_25/6/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer (12/08) _x000D_24/6/2024:#Update - NFA - Allwyn confirmed rescheduled install date with retailer (12/08) _x000D_20/6/2024:Update: Order Amended _x000D_19/6/2024:Update: Order Amended _x000D_18/6/2024:Update: Order Amended _x000D_17/6/2024:0 _x000D_14/6/2024:Update: Order Amended _x000D_13/6/2024:Update: Order Amended _x000D_12/6/2024:Update: Order Amended _x000D_10/6/2024:Update: Order Amended _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 0 | 0 | 2024-06-07 | 7/6/2024: CSL to provide an update |  |  | 5.CSL | VFS996795 | 30016117 | 1.Provisioning | AM |  | 2024-06-06 | 2024-08-19 |  | 0 | [11 empty] | 0
666 | 664962 | 1760 | Batch 4 Jun24 | Type 1 | SOGEA | Premier Top Shop | Wrexham | LL14 3UY | 2024-06-07 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_25/6/2024:Order Completed _x000D_24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_18/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_17/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_14/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_13/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_12/6/2024:Your order has been delayed due to a Vodafone system issue which is preventing us from progressing your order. Once the issue has been resolved the order will progress. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/6/2024:Supplier Delay: Network Planning issue, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_7/6/2024:Supplier Delay: Network Planning issue, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/6/2024:Supplier Delay: Network Planning issue, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/6/2024:Supplier Delay: Network Planning issue, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/6/2024:0 _x000D_31/5/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_30/5/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/5/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_28/5/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/5/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/05/2024: New order added to report | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_25/6/2024:Order Completed _x000D_24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_18/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_17/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_14/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_13/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_12/6/2024:Your order has been delayed due to a Vodafone system issue which is preventing us from progressing your order. Once the issue has been resolved the order will progress. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/6/2024:Supplier Delay: Network Planning issue, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_7/6/2024:Supplier Delay: Network Planning issue, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/6/2024:Supplier Delay: Network Planning issue, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/6/2024:Supplier Delay: Network Planning issue, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/6/2024:0 _x000D_31/5/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_30/5/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/5/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_28/5/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/5/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/05/2024: New order added to report | 0 | 0 | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996813 | 30015975 | 2.Commissioning | AM | [8 empty] | 2024-08-13 | [7 empty] | 0
667 | 660888 | 3084 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Good News | Harlesden | NW10 8TR |  | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 12:36 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_25/6/2024:Order Completed _x000D_24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 12:36 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_25/6/2024:Order Completed _x000D_24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015602 | 30016912 | 2.Commissioning | AM |  | 2024-06-21 | 2024-08-16 |  | 0 |  |  |  | 2024-09-18 | [7 empty] | 0
668 | 430685 | 3090 | Batch 5 Jul24 | Type 3 | SoGEA/Mobile | Market Square Londis | DOVER | CT16 1NX |  | 6/9/2024:#Update - Allwyn have requested for this order to be downgrade from site type 1 to site type 3. _x000D_5/9/2024:#Update - Allwyn have requested for this order to be downgrade from site type 1 to site type 3. _x000D_4/9/2024:#Update - Allwyn have requested for this order to be downgrade from site type 1 to site type 3. _x000D_3/9/2024:#Update - Allwyn have requested for this order to be downgrade from site type 1 to site type 3. _x000D_2/9/2024:#Update - Allwyn have requested for this order to be downgrade from site type 1 to site type 3. _x000D_29/8/2024:#Update - Allwyn have requested for this order to be downgrade from site type 1 to site type 3. _x000D_28/8/2024:#Update - Allwyn have requested for this order to be downgrade from site type 1 to site type 3. _x000D_27/8/2024:#Update - Allwyn have requested for this order to be downgrade from site type 1 to site type 3. _x000D_22/8/2024:#Update - Allwyn have requested for this order to be downgrade from site type 1 to site type 3. _x000D_21/8/2024:#Update - Allwyn have requested for this order to be downgrade from site type 1 to site type 3. _x000D_20/8/2024:#Update - Allwyn have requested for this order to be downgrade from site type 1 to site type 3. _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 31/07 AM _x000D_19/8/2024:01448149 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 31/07 AM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 31/07 AM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 31/07 AM _x000D_13/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 31/07 AM _x000D_12/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 31/07 AM _x000D_9/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 31/07 AM _x000D_8/8/2024:10/07/2024 _x000D_6/8/2024:10/07/2024 _x000D_5/8/2024:10/07/2024 _x000D_2/8/2024:10/07/2024 _x000D_1/8/2024:10/07/2024 _x000D_31/7/2024:10/07/2024 _x000D_31/7/2024:10/07/2024 _x000D_30/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 31/07 AM _x000D_29/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 31/07 AM _x000D_29/7/2024:01448149 _x000D_26/7/2024:01448149 _x000D_24/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 31/07 AM _x000D_23/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 31/07 AM _x000D_22/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 31/07 AM _x000D_22/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 31/07 AM _x000D_25/6/2024:Order Completed _x000D_24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:Supplier Delay: Delay encountered during automated test of new service _x000D_ | 9/9/2024:#Update - Allwyn have requested for this order to be downgrade from site type 1 to site type 3. _x000D_6/9/2024:#Update - Allwyn have requested for this order to be downgrade from site type 1 to site type 3. _x000D_5/9/2024:#Update - Allwyn have requested for this order to be downgrade from site type 1 to site type 3. _x000D_4/9/2024:#Update - Allwyn have requested for this order to be downgrade from site type 1 to site type 3. _x000D_3/9/2024:#Update - Allwyn have requested for this order to be downgrade from site type 1 to site type 3. _x000D_2/9/2024:#Update - Allwyn have requested for this order to be downgrade from site type 1 to site type 3. _x000D_29/8/2024:#Update - Allwyn have requested for this order to be downgrade from site type 1 to site type 3. _x000D_28/8/2024:#Update - Allwyn have requested for this order to be downgrade from site type 1 to site type 3. _x000D_27/8/2024:#Update - Allwyn have requested for this order to be downgrade from site type 1 to site type 3. _x000D_22/8/2024:#Update - Allwyn have requested for this order to be downgrade from site type 1 to site type 3. _x000D_21/8/2024:#Update - Allwyn have requested for this order to be downgrade from site type 1 to site type 3. _x000D_20/8/2024:#Update - Allwyn have requested for this order to be downgrade from site type 1 to site type 3. _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 31/07 AM _x000D_19/8/2024:01448149 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 31/07 AM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 31/07 AM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 31/07 AM _x000D_13/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 31/07 AM _x000D_12/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 31/07 AM _x000D_9/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 31/07 AM _x000D_8/8/2024:10/07/2024 _x000D_6/8/2024:10/07/2024 _x000D_5/8/2024:10/07/2024 _x000D_2/8/2024:10/07/2024 _x000D_1/8/2024:10/07/2024 _x000D_31/7/2024:10/07/2024 _x000D_31/7/2024:10/07/2024 _x000D_30/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 31/07 AM _x000D_29/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 31/07 AM _x000D_29/7/2024:01448149 _x000D_26/7/2024:01448149 _x000D_24/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 31/07 AM _x000D_23/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 31/07 AM _x000D_22/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 31/07 AM _x000D_22/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 31/07 AM _x000D_25/6/2024:Order Completed _x000D_24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:Supplier Delay: Delay encountered during automated test of new service _x000D_ | 0 | #Update - Allwyn have requested for this order to be downgrade from site type 1 to site type 3. | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015496 | 30016774 | 2.Commissioning | AM |  | 2024-06-21 | 2024-08-12 |  | 0 | [11 empty] | 0
669 | 652477 | 3092 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | KP Newsagents | Warwick | CV34 5RN |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:Update: Order Amended _x000D_19/8/2024:Update: Order Amended _x000D_19/8/2024:14/08/2024 13:46 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 06:31 _x000D_26/7/2024:22/07/2024 06:31 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_16/7/2024:#Update Retailer happy with new appointment - 11/07, AM _x000D_15/7/2024:#Update Retailer happy with new appointment - 11/07, AM _x000D_12/7/2024:#Update Retailer happy with new appointment - 11/07, AM _x000D_11/7/2024:#Update Retailer happy with new appointment - 11/07, AM _x000D_10/7/2024:#Update Retailer happy with new appointment - 11/07, AM _x000D_9/7/2024:#Update Retailer happy with new appointment - 11/07, AM _x000D_4/7/2024:#Update Retailer happy with new appointment - 11/07, AM _x000D_3/7/2024:#Update Retailer happy with new appointment - 11/07, AM _x000D_2/7/2024:0 _x000D_1/7/2024:#Update Retailer happy with new appointment - 11/07, AM _x000D_27/6/2024:#Update Retailer happy with new appointment - 11/07, AM _x000D_25/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect Product. Please check with end user and reappoint the order if still required. _x000D_24/6/2024:Supplier Delay: KCI-3 (Order Completed) Delayed in Processing. _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:Update: Order Amended _x000D_19/8/2024:Update: Order Amended _x000D_19/8/2024:14/08/2024 13:46 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 06:31 _x000D_26/7/2024:22/07/2024 06:31 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_16/7/2024:#Update Retailer happy with new appointment - 11/07, AM _x000D_15/7/2024:#Update Retailer happy with new appointment - 11/07, AM _x000D_12/7/2024:#Update Retailer happy with new appointment - 11/07, AM _x000D_11/7/2024:#Update Retailer happy with new appointment - 11/07, AM _x000D_10/7/2024:#Update Retailer happy with new appointment - 11/07, AM _x000D_9/7/2024:#Update Retailer happy with new appointment - 11/07, AM _x000D_4/7/2024:#Update Retailer happy with new appointment - 11/07, AM _x000D_3/7/2024:#Update Retailer happy with new appointment - 11/07, AM _x000D_2/7/2024:0 _x000D_1/7/2024:#Update Retailer happy with new appointment - 11/07, AM _x000D_27/6/2024:#Update Retailer happy with new appointment - 11/07, AM _x000D_25/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect Product. Please check with end user and reappoint the order if still required. _x000D_24/6/2024:Supplier Delay: KCI-3 (Order Completed) Delayed in Processing. _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFS1049649 | 30016944 | 1.Provisioning | AM |  | 2024-06-21 | 2024-09-04 |  | 0 | [11 empty] | 0
670 | 647958 | 3094 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Quality Stores | Leicester | LE4 6BB |  | 6/9/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_5/9/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_4/9/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_3/9/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_2/9/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_29/8/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_28/8/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_27/8/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_22/8/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_21/8/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_20/8/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_19/8/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_19/8/2024:01447634 _x000D_16/8/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_15/8/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_14/8/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_13/8/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_12/8/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_9/8/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_8/8/2024:04/07/2024 _x000D_6/8/2024:04/07/2024 _x000D_5/8/2024:04/07/2024 _x000D_2/8/2024:04/07/2024 _x000D_1/8/2024:04/07/2024 _x000D_31/7/2024:04/07/2024 _x000D_31/7/2024:04/07/2024 _x000D_30/7/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_29/7/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_29/7/2024:01447634 _x000D_26/7/2024:01447634 _x000D_24/7/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_23/7/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_22/7/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_22/7/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_25/6/2024:Order Completed _x000D_24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 9/9/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_6/9/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_5/9/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_4/9/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_3/9/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_2/9/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_29/8/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_28/8/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_27/8/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_22/8/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_21/8/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_20/8/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_19/8/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_19/8/2024:01447634 _x000D_16/8/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_15/8/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_14/8/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_13/8/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_12/8/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_9/8/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_8/8/2024:04/07/2024 _x000D_6/8/2024:04/07/2024 _x000D_5/8/2024:04/07/2024 _x000D_2/8/2024:04/07/2024 _x000D_1/8/2024:04/07/2024 _x000D_31/7/2024:04/07/2024 _x000D_31/7/2024:04/07/2024 _x000D_30/7/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_29/7/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_29/7/2024:01447634 _x000D_26/7/2024:01447634 _x000D_24/7/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_23/7/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_22/7/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_22/7/2024:#Update - ECC proposal sent to Vodafone on 04/07 _x000D_25/6/2024:Order Completed _x000D_24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | Update: Order Amended | #Update - ECC proposal sent to Vodafone on 04/07 | 2024-06-07 |  |  |  |  | VFS1015601 | 30016926 | 1.Provisioning | AM |  | 2024-06-21 | 2024-08-21 |  | 0 | [11 empty] | 0
671 | 444383 | 3095 | Batch 5 Jul24 | Type 1 | FTTP | Central | BALLYMENA | BT42 2BJ |  | 19/7/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_18/7/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_17/7/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_16/7/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_15/7/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_12/7/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_11/7/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_10/7/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_9/7/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_4/7/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_3/7/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_27/6/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_25/6/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_24/6/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 19/7/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_18/7/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_17/7/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_16/7/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_15/7/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_12/7/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_11/7/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_10/7/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_9/7/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_4/7/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_3/7/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_27/6/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_25/6/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_24/6/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366133 | 30016813 | 6.Failed router install |  |  | 2024-06-21 | 2024-06-21 | 2024-06-21 | TRUE |  |  |  | 2024-07-23 |  |  |  | 2024-07-23 | 23A004953011 |  | 2024-07-24 | 1
672 | 475977 | 3097 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Premier | Faversham | ME13 7EG | 2024-08-15 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_15/8/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_14/8/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_13/8/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_12/8/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_9/8/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_8/8/2024:21/06/2024 _x000D_6/8/2024:21/06/2024 _x000D_5/8/2024:21/06/2024 _x000D_2/8/2024:21/06/2024 _x000D_1/8/2024:21/06/2024 _x000D_31/7/2024:21/06/2024 _x000D_31/7/2024:21/06/2024 _x000D_30/7/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_29/7/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_29/7/2024:01447702 _x000D_26/7/2024:01447702 _x000D_24/7/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_23/7/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_22/7/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_22/7/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_25/6/2024:Order Completed _x000D_24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_15/8/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_14/8/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_13/8/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_12/8/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_9/8/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_8/8/2024:21/06/2024 _x000D_6/8/2024:21/06/2024 _x000D_5/8/2024:21/06/2024 _x000D_2/8/2024:21/06/2024 _x000D_1/8/2024:21/06/2024 _x000D_31/7/2024:21/06/2024 _x000D_31/7/2024:21/06/2024 _x000D_30/7/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_29/7/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_29/7/2024:01447702 _x000D_26/7/2024:01447702 _x000D_24/7/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_23/7/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_22/7/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_22/7/2024:#Update - Missed Appointment - The staff were unaware of the order and the store manager was offsite/not contactable therefore entry was refused. The store requested to reschedule for a date when the store manager is present. _x000D_25/6/2024:Order Completed _x000D_24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | 0 | 2024-06-07 |  |  |  |  | VFP2366132 | 30016659 | 2.Commissioning | AM |  | 2024-06-21 | 2024-08-14 | 2024-08-14 15:28 | 1 |  |  |  | 2024-09-06 | [7 empty] | 0
673 | 421839 | 3099 | Batch 5 Jul24 | Type 1 | FTTP | Sinclairs | BELFAST | BT4 3EN |  | 19/7/2024:#Update Delayed install due to complex dig work required. Update 4/07 _x000D_18/7/2024:#Update Delayed install due to complex dig work required. Update 4/07 _x000D_17/7/2024:#Update Delayed install due to complex dig work required. Update 4/07 _x000D_16/7/2024:#Update Delayed install due to complex dig work required. Update 4/07 _x000D_15/7/2024:#Update Delayed install due to complex dig work required. Update 4/07 _x000D_12/7/2024:#Update Delayed install due to complex dig work required. Update 4/07 _x000D_11/7/2024:#Update Delayed install due to complex dig work required. Update 4/07 _x000D_10/7/2024:#Update Delayed install due to complex dig work required. Update 4/07 _x000D_9/7/2024:#Update Delayed install due to complex dig work required. Update 4/07 _x000D_4/7/2024:#Update Delayed install due to complex dig work required. Update 4/07 _x000D_3/7/2024:#Update Delayed install due to complex dig work required. Update 4/07 _x000D_2/7/2024:0 _x000D_1/7/2024:#Update Delayed install due to complex dig work required. Update 4/07 _x000D_27/6/2024:#Update Delayed install due to complex dig work required. Update 4/07 _x000D_25/6/2024:#update delayed due to dig work required. More updates due 3/07 _x000D_24/6/2024:Supplier Delay: Issues with provision of the underground network, please await for further details. _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 19/7/2024:#Update Delayed install due to complex dig work required. Update 4/07 _x000D_18/7/2024:#Update Delayed install due to complex dig work required. Update 4/07 _x000D_17/7/2024:#Update Delayed install due to complex dig work required. Update 4/07 _x000D_16/7/2024:#Update Delayed install due to complex dig work required. Update 4/07 _x000D_15/7/2024:#Update Delayed install due to complex dig work required. Update 4/07 _x000D_12/7/2024:#Update Delayed install due to complex dig work required. Update 4/07 _x000D_11/7/2024:#Update Delayed install due to complex dig work required. Update 4/07 _x000D_10/7/2024:#Update Delayed install due to complex dig work required. Update 4/07 _x000D_9/7/2024:#Update Delayed install due to complex dig work required. Update 4/07 _x000D_4/7/2024:#Update Delayed install due to complex dig work required. Update 4/07 _x000D_3/7/2024:#Update Delayed install due to complex dig work required. Update 4/07 _x000D_2/7/2024:0 _x000D_1/7/2024:#Update Delayed install due to complex dig work required. Update 4/07 _x000D_27/6/2024:#Update Delayed install due to complex dig work required. Update 4/07 _x000D_25/6/2024:#update delayed due to dig work required. More updates due 3/07 _x000D_24/6/2024:Supplier Delay: Issues with provision of the underground network, please await for further details. _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366130 | 30016649 | 6.Failed router install |  |  | 2024-06-21 | 2024-06-21 | 2024-06-21 | TRUE |  |  |  | 2024-07-19 |  |  |  | 2024-07-19 | 242005010319 |  | 2024-07-23 | 1
674 | 462631 | 3106 | Batch 5 Jul24 | Type 1 | FTTP | Kumars | LUTON | LU1 1LY | 2024-07-29 | 30/7/2024:Order Completed _x000D_29/7/2024:Order Completed _x000D_29/7/2024:26/07/2024 10:12 _x000D_26/7/2024:26/07/2024 09:40 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_25/6/2024:Order Completed _x000D_24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 30/7/2024:Order Completed _x000D_29/7/2024:Order Completed _x000D_29/7/2024:26/07/2024 10:12 _x000D_26/7/2024:26/07/2024 09:40 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_25/6/2024:Order Completed _x000D_24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFP2397971 | 30016995 | 2.Commissioning |  |  | 2024-06-21 | 2024-07-26 | 2024-07-26 | TRUE |  |  |  | 2024-08-15 | [7 empty] | 0
675 | 646408 | 3114 | Batch 5 Jul24 | Type 1 | SOGEA | Premier Bulwark Convenience Store | Chepstow | NP16 5JW |  | 25/6/2024:Order Completed _x000D_24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 25/6/2024:Order Completed _x000D_24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366127 | 30016966 | 6.Failed router install |  |  | 2024-06-21 | 2024-06-21 | 2024-06-21 | TRUE |  |  |  | 2024-07-25 |  |  |  | 2024-07-25 | 239004929554 |  | 2024-07-29 | 1
676 | 444811 | 3119 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | The Pagoda | WELLINGBOROUGH | NN8 1AN |  | 6/9/2024:#Update - Your order has been delayed. Dig work required. Further updates will follow _x000D_5/9/2024:#Update - Your order has been delayed. Dig work required. Further updates will follow _x000D_4/9/2024:#Update - Your order has been delayed. Dig work required. Further updates will follow _x000D_3/9/2024:#Update - Your order has been delayed. Dig work required. Further updates will follow _x000D_2/9/2024:#Update - Your order has been delayed. Dig work required. Further updates will follow _x000D_29/8/2024:#Update - Your order has been delayed. Dig work required. Further updates will follow _x000D_28/8/2024:#Update - Order has been delayed as dig work is required. CSL will update as more information becomes available. _x000D_27/8/2024:#Update - Order has been delayed as dig work is required. CSL will update as more information becomes available. _x000D_22/8/2024:#Update - Order has been delayed as dig work is required. CSL will update as more information becomes available. _x000D_21/8/2024:#Update - Order has been delayed as dig work is required. CSL will update as more information becomes available. _x000D_20/8/2024:#Update - Order has been delayed as dig work is required. CSL will update as more information becomes available. _x000D_19/8/2024:#Update - Order has been delayed as dig work is required. CSL will update as more information becomes available. _x000D_19/8/2024:01451188 _x000D_16/8/2024:#Update - Order has been delayed as dig work is required. CSL will update as more information becomes available. _x000D_15/8/2024:#Update - Order has been delayed as dig work is required. CSL will update as more information becomes available. _x000D_14/8/2024:#Update - Order has been delayed as dig work is required. CSL will update as more information becomes available. _x000D_13/8/2024:#Update - Order has been delayed as dig work is required. CSL will update as more information becomes available. _x000D_12/8/2024:#Update - Order has been delayed as dig work is required. CSL will update as more information becomes available. _x000D_9/8/2024:#Update - Order has been delayed as dig work is required. CSL will update as more information becomes available. _x000D_8/8/2024:25/06/2024 _x000D_6/8/2024:25/06/2024 _x000D_5/8/2024:25/06/2024 _x000D_2/8/2024:25/06/2024 _x000D_1/8/2024:25/06/2024 _x000D_31/7/2024:25/06/2024 _x000D_31/7/2024:25/06/2024 _x000D_30/7/2024:#Update - Order has been delayed as dig work is required. CSL will update as more information becomes available. _x000D_29/7/2024:#Update - Order has been delayed as dig work is required. CSL will update as more information becomes available. _x000D_29/7/2024:01451188 _x000D_26/7/2024:01451188 _x000D_24/7/2024:#Update - Order has been delayed as dig work is required. CSL will update as more information becomes available. _x000D_23/7/2024:#Update - Order has been delayed as dig work is required. CSL will update as more information becomes available. _x000D_22/7/2024:#Update - Order has been delayed as dig work is required. CSL will update as more information becomes available. _x000D_22/7/2024:#Update - Order has been delayed as dig work is required. CSL will update as more information becomes available. _x000D_19/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_18/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_17/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_16/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_15/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_12/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_11/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_10/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_9/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_4/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:Update: Order Amended _x000D_25/6/2024:Update: Order Amended _x000D_24/6/2024:Update: Order Amended _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:#Update - Your order has been delayed. Dig work required. Further updates will follow _x000D_6/9/2024:#Update - Your order has been delayed. Dig work required. Further updates will follow _x000D_5/9/2024:#Update - Your order has been delayed. Dig work required. Further updates will follow _x000D_4/9/2024:#Update - Your order has been delayed. Dig work required. Further updates will follow _x000D_3/9/2024:#Update - Your order has been delayed. Dig work required. Further updates will follow _x000D_2/9/2024:#Update - Your order has been delayed. Dig work required. Further updates will follow _x000D_29/8/2024:#Update - Your order has been delayed. Dig work required. Further updates will follow _x000D_28/8/2024:#Update - Order has been delayed as dig work is required. CSL will update as more information becomes available. _x000D_27/8/2024:#Update - Order has been delayed as dig work is required. CSL will update as more information becomes available. _x000D_22/8/2024:#Update - Order has been delayed as dig work is required. CSL will update as more information becomes available. _x000D_21/8/2024:#Update - Order has been delayed as dig work is required. CSL will update as more information becomes available. _x000D_20/8/2024:#Update - Order has been delayed as dig work is required. CSL will update as more information becomes available. _x000D_19/8/2024:#Update - Order has been delayed as dig work is required. CSL will update as more information becomes available. _x000D_19/8/2024:01451188 _x000D_16/8/2024:#Update - Order has been delayed as dig work is required. CSL will update as more information becomes available. _x000D_15/8/2024:#Update - Order has been delayed as dig work is required. CSL will update as more information becomes available. _x000D_14/8/2024:#Update - Order has been delayed as dig work is required. CSL will update as more information becomes available. _x000D_13/8/2024:#Update - Order has been delayed as dig work is required. CSL will update as more information becomes available. _x000D_12/8/2024:#Update - Order has been delayed as dig work is required. CSL will update as more information becomes available. _x000D_9/8/2024:#Update - Order has been delayed as dig work is required. CSL will update as more information becomes available. _x000D_8/8/2024:25/06/2024 _x000D_6/8/2024:25/06/2024 _x000D_5/8/2024:25/06/2024 _x000D_2/8/2024:25/06/2024 _x000D_1/8/2024:25/06/2024 _x000D_31/7/2024:25/06/2024 _x000D_31/7/2024:25/06/2024 _x000D_30/7/2024:#Update - Order has been delayed as dig work is required. CSL will update as more information becomes available. _x000D_29/7/2024:#Update - Order has been delayed as dig work is required. CSL will update as more information becomes available. _x000D_29/7/2024:01451188 _x000D_26/7/2024:01451188 _x000D_24/7/2024:#Update - Order has been delayed as dig work is required. CSL will update as more information becomes available. _x000D_23/7/2024:#Update - Order has been delayed as dig work is required. CSL will update as more information becomes available. _x000D_22/7/2024:#Update - Order has been delayed as dig work is required. CSL will update as more information becomes available. _x000D_22/7/2024:#Update - Order has been delayed as dig work is required. CSL will update as more information becomes available. _x000D_19/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_18/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_17/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_16/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_15/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_12/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_11/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_10/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_9/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_4/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:Update: Order Amended _x000D_25/6/2024:Update: Order Amended _x000D_24/6/2024:Update: Order Amended _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | #Update - Your order has been delayed. Dig work required. Further updates will follow | 2024-06-07 |  |  |  |  | VFP2366126 | 30016852 | 1.Provisioning | AM |  | 2024-06-21 | 2024-06-21 |  | 0 | [11 empty] | 0
677 | 639484 | 3120 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Spar Droitwich | Droitwich | WR9 8PQ | 2024-09-03 | 6/9/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_5/9/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_4/9/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_3/9/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_2/9/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_29/8/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_28/8/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_27/8/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_22/8/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_21/8/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_20/8/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_19/8/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_19/8/2024:01447959 _x000D_16/8/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_15/8/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_14/8/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_13/8/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_12/8/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_9/8/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_8/8/2024:03/07/2024 _x000D_6/8/2024:03/07/2024 _x000D_5/8/2024:03/07/2024 _x000D_2/8/2024:03/07/2024 _x000D_1/8/2024:03/07/2024 _x000D_31/7/2024:03/07/2024 _x000D_31/7/2024:03/07/2024 _x000D_30/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_29/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_29/7/2024:01447959 _x000D_26/7/2024:01447959 _x000D_24/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_23/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_22/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_22/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_19/7/2024:#Update - Action for Allwyn - Installation has now been amended to 06/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 06/08 is a suitable date. _x000D_18/7/2024:#Update - Missed Appointment - The retailer was unaware of the order and therefore refused entry. Additionally, they do not want any work to be done when customers are in the store. _x000D_17/7/2024:#Update - Missed Appointment - The retailer was unaware of the order and therefore refused entry. Additionally, they do not want any work to be done when customers are in the store. _x000D_16/7/2024:#Update - Missed Appointment - The retailer was unaware of the order and therefore refused entry. Additionally, they do not want any work to be done when customers are in the store. _x000D_15/7/2024:#Update - Missed Appointment - The retailer was unaware of the order and therefore refused entry. Additionally, they do not want any work to be done when customers are in the store. _x000D_12/7/2024:#Update - Missed Appointment - The retailer was unaware of the order and therefore refused entry. Additionally, they do not want any work to be done when customers are in the store. _x000D_11/7/2024:#Update - Missed Appointment - The retailer was unaware of the order and therefore refused entry. Additionally, they do not want any work to be done when customers are in the store. _x000D_10/7/2024:#Update - Missed Appointment - The retailer was unaware of the order and therefore refused entry. Additionally, they do not want any work to be done when customers are in the store. _x000D_9/7/2024:#Update - Missed Appointment - The retailer was unaware of the order and therefore refused entry. Additionally, they do not want any work to be done when customers are in the store. _x000D_4/7/2024:#Update - Missed Appointment - The retailer was unaware of the order and therefore refused entry. Additionally, they do not want any work to be done when customers are in the store. _x000D_3/7/2024:#Update - Missed Appointment - The retailer was unaware of the order and therefore refused entry. Additionally, they do not want any work to be done when customers are in the store. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Missed Appointment - The retailer was unaware of the order and therefore refused entry. Additionally, they do not want any work to be done when customers are in the store. _x000D_27/6/2024:#Update - Missed Appointment - The retailer was unaware of the order and therefore refused entry. Additionally, they do not want any work to be done when customers are in the store. _x000D_25/6/2024:#Update - Missed Appointment - The retailer was unaware of the order and therefore refused entry. Additionally, they do not want any work to be done when customers are in the store. _x000D_24/6/2024:#Update - Missed Appointment - The retailer was unaware of the order and therefore refused entry. Additionally, they do not want any work to be done when customers are in the store. _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_6/9/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_5/9/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_4/9/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_3/9/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_2/9/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_29/8/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_28/8/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_27/8/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_22/8/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_21/8/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_20/8/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_19/8/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_19/8/2024:01447959 _x000D_16/8/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_15/8/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_14/8/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_13/8/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_12/8/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_9/8/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_8/8/2024:03/07/2024 _x000D_6/8/2024:03/07/2024 _x000D_5/8/2024:03/07/2024 _x000D_2/8/2024:03/07/2024 _x000D_1/8/2024:03/07/2024 _x000D_31/7/2024:03/07/2024 _x000D_31/7/2024:03/07/2024 _x000D_30/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_29/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_29/7/2024:01447959 _x000D_26/7/2024:01447959 _x000D_24/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_23/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_22/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_22/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_19/7/2024:#Update - Action for Allwyn - Installation has now been amended to 06/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 06/08 is a suitable date. _x000D_18/7/2024:#Update - Missed Appointment - The retailer was unaware of the order and therefore refused entry. Additionally, they do not want any work to be done when customers are in the store. _x000D_17/7/2024:#Update - Missed Appointment - The retailer was unaware of the order and therefore refused entry. Additionally, they do not want any work to be done when customers are in the store. _x000D_16/7/2024:#Update - Missed Appointment - The retailer was unaware of the order and therefore refused entry. Additionally, they do not want any work to be done when customers are in the store. _x000D_15/7/2024:#Update - Missed Appointment - The retailer was unaware of the order and therefore refused entry. Additionally, they do not want any work to be done when customers are in the store. _x000D_12/7/2024:#Update - Missed Appointment - The retailer was unaware of the order and therefore refused entry. Additionally, they do not want any work to be done when customers are in the store. _x000D_11/7/2024:#Update - Missed Appointment - The retailer was unaware of the order and therefore refused entry. Additionally, they do not want any work to be done when customers are in the store. _x000D_10/7/2024:#Update - Missed Appointment - The retailer was unaware of the order and therefore refused entry. Additionally, they do not want any work to be done when customers are in the store. _x000D_9/7/2024:#Update - Missed Appointment - The retailer was unaware of the order and therefore refused entry. Additionally, they do not want any work to be done when customers are in the store. _x000D_4/7/2024:#Update - Missed Appointment - The retailer was unaware of the order and therefore refused entry. Additionally, they do not want any work to be done when customers are in the store. _x000D_3/7/2024:#Update - Missed Appointment - The retailer was unaware of the order and therefore refused entry. Additionally, they do not want any work to be done when customers are in the store. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Missed Appointment - The retailer was unaware of the order and therefore refused entry. Additionally, they do not want any work to be done when customers are in the store. _x000D_27/6/2024:#Update - Missed Appointment - The retailer was unaware of the order and therefore refused entry. Additionally, they do not want any work to be done when customers are in the store. _x000D_25/6/2024:#Update - Missed Appointment - The retailer was unaware of the order and therefore refused entry. Additionally, they do not want any work to be done when customers are in the store. _x000D_24/6/2024:#Update - Missed Appointment - The retailer was unaware of the order and therefore refused entry. Additionally, they do not want any work to be done when customers are in the store. _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | Order Completed | #Update Retailer happy with new appointment 18/07, AM. | 2024-06-07 |  |  |  |  | VFS1015491 | 30016632 | 2.Commissioning | AM |  | 2024-09-02 | 2024-09-02 |  | 0 |  |  |  | 2024-08-16 | [7 empty] | 0
678 | 651606 | 3121 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | T and A Local | Knottingley | WF11 8NQ | 2024-08-07 | 6/9/2024:#Update - The retailer is having a refurbishment in 2025 therefore Allwyn have cancelled the order and will re-raise after this work has been completed. _x000D_5/9/2024:#Update - The retailer is having a refurbishment in 2025 therefore Allwyn have cancelled the order and will re-raise after this work has been completed. _x000D_4/9/2024:#Update - The retailer is having a refurbishment in 2025 therefore Allwyn have cancelled the order and will re-raise after this work has been completed. _x000D_3/9/2024:#Update - The retailer is having a refurbishment in 2025 therefore Allwyn have cancelled the order and will re-raise after this work has been completed. _x000D_2/9/2024:#Update - The retailer is having a refurbishment in 2025 therefore Allwyn have cancelled the order and will re-raise after this work has been completed. _x000D_29/8/2024:#Update - The internal installation requires a pole from the stand alone till up into the ceiling as it is not possible to get the line from the wall to the till area without causing a tripping hazard. Additionally the store is undergoing a refurbishment in January and the till will be moving position so it will require another revisit once this is complete. _x000D_28/8/2024:#Update - The internal installation requires a pole from the stand alone till up into the ceiling as it is not possible to get the line from the wall to the till area without causing a tripping hazard. Additionally the store is undergoing a refurbishment in January and the till will be moving position so it will require another revisit once this is complete. _x000D_27/8/2024:#Update - The internal installation requires a pole from the stand alone till up into the ceiling as it is not possible to get the line from the wall to the till area without causing a tripping hazard. Additionally the store is undergoing a refurbishment in January and the till will be moving position so it will require another revisit once this is complete. _x000D_22/8/2024:#Update - The internal installation requires a pole from the stand alone till up into the ceiling as it is not possible to get the line from the wall to the till area without causing a tripping hazard. Additionally the store is undergoing a refurbishment in January and the till will be moving position so it will require another revisit once this is complete. _x000D_21/8/2024:#Update - The internal installation requires a pole from the stand alone till up into the ceiling as it is not possible to get the line from the wall to the till area without causing a tripping hazard. Additionally the store is undergoing a refurbishment in January and the till will be moving position so it will require another revisit once this is complete. _x000D_20/8/2024:#Update - The internal installation requires a pole from the stand alone till up into the ceiling as it is not possible to get the line from the wall to the till area without causing a tripping hazard. Additionally the store is undergoing a refurbishment in January and the till will be moving position so it will require another revisit once this is complete. _x000D_19/8/2024:#Update - The internal installation requires a pole from the stand alone till up into the ceiling as it is not possible to get the line from the wall to the till area without causing a tripping hazard. Additionally the store is undergoing a refurbishment in January and the till will be moving position so it will require another revisit once this is complete. _x000D_19/8/2024:01447936 _x000D_16/8/2024:#Update - The internal installation requires a pole from the stand alone till up into the ceiling as it is not possible to get the line from the wall to the till area without causing a tripping hazard. Additionally the store is undergoing a refurbishment in January and the till will be moving position so it will require another revisit once this is complete. _x000D_15/8/2024:#Update - The internal installation requires a pole from the stand alone till up into the ceiling as it is not possible to get the line from the wall to the till area without causing a tripping hazard. Additionally the store is undergoing a refurbishment in January and the till will be moving position so it will require another revisit once this is complete. _x000D_14/8/2024:#Update - The internal installation requires a pole from the stand alone till up into the ceiling as it is not possible to get the line from the wall to the till area without causing a tripping hazard. Additionally the store is undergoing a refurbishment in January and the till will be moving position so it will require another revisit once this is complete. _x000D_13/8/2024:#Update - The internal installation requires a pole from the stand alone till up into the ceiling as it is not possible to get the line from the wall to the till area without causing a tripping hazard. Additionally the store is undergoing a refurbishment in January and the till will be moving position so it will require another revisit once this is complete. _x000D_12/8/2024:#Update - The internal installation requires a pole from the stand alone till up into the ceiling as it is not possible to get the line from the wall to the till area without causing a tripping hazard. Additionally the store is undergoing a refurbishment in January and the till will be moving position so it will require another revisit once this is complete. _x000D_9/8/2024:#Update - The internal installation requires a pole from the stand alone till up into the ceiling as it is not possible to get the line from the wall to the till area without causing a tripping hazard. Additionally the store is undergoing a refurbishment in January and the till will be moving position so it will require another revisit once this is complete. _x000D_8/8/2024:07/08/2024 _x000D_6/8/2024:25/07/2024 _x000D_5/8/2024:25/07/2024 _x000D_2/8/2024:25/07/2024 _x000D_1/8/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_30/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 AM _x000D_29/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 AM _x000D_29/7/2024:01447936 _x000D_26/7/2024:01447936 _x000D_24/7/2024:#Update - Action for Allwyn - Installation has now been amended to 06/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 06/08 is a suitable date. _x000D_23/7/2024:#Update - Action for Allwyn - Installation has now been amended to 06/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 06/08 is a suitable date. _x000D_22/7/2024:#Update - Action for Allwyn - Installation has now been amended to 06/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 06/08 is a suitable date. _x000D_22/7/2024:#Update - Action for Allwyn - Installation has now been amended to 06/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 06/08 is a suitable date. _x000D_25/6/2024:Order Completed _x000D_24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:#Update - The retailer is having a refurbishment in 2025 therefore Allwyn have cancelled the order and will re-raise after this work has been completed. _x000D_6/9/2024:#Update - The retailer is having a refurbishment in 2025 therefore Allwyn have cancelled the order and will re-raise after this work has been completed. _x000D_5/9/2024:#Update - The retailer is having a refurbishment in 2025 therefore Allwyn have cancelled the order and will re-raise after this work has been completed. _x000D_4/9/2024:#Update - The retailer is having a refurbishment in 2025 therefore Allwyn have cancelled the order and will re-raise after this work has been completed. _x000D_3/9/2024:#Update - The retailer is having a refurbishment in 2025 therefore Allwyn have cancelled the order and will re-raise after this work has been completed. _x000D_2/9/2024:#Update - The retailer is having a refurbishment in 2025 therefore Allwyn have cancelled the order and will re-raise after this work has been completed. _x000D_29/8/2024:#Update - The internal installation requires a pole from the stand alone till up into the ceiling as it is not possible to get the line from the wall to the till area without causing a tripping hazard. Additionally the store is undergoing a refurbishment in January and the till will be moving position so it will require another revisit once this is complete. _x000D_28/8/2024:#Update - The internal installation requires a pole from the stand alone till up into the ceiling as it is not possible to get the line from the wall to the till area without causing a tripping hazard. Additionally the store is undergoing a refurbishment in January and the till will be moving position so it will require another revisit once this is complete. _x000D_27/8/2024:#Update - The internal installation requires a pole from the stand alone till up into the ceiling as it is not possible to get the line from the wall to the till area without causing a tripping hazard. Additionally the store is undergoing a refurbishment in January and the till will be moving position so it will require another revisit once this is complete. _x000D_22/8/2024:#Update - The internal installation requires a pole from the stand alone till up into the ceiling as it is not possible to get the line from the wall to the till area without causing a tripping hazard. Additionally the store is undergoing a refurbishment in January and the till will be moving position so it will require another revisit once this is complete. _x000D_21/8/2024:#Update - The internal installation requires a pole from the stand alone till up into the ceiling as it is not possible to get the line from the wall to the till area without causing a tripping hazard. Additionally the store is undergoing a refurbishment in January and the till will be moving position so it will require another revisit once this is complete. _x000D_20/8/2024:#Update - The internal installation requires a pole from the stand alone till up into the ceiling as it is not possible to get the line from the wall to the till area without causing a tripping hazard. Additionally the store is undergoing a refurbishment in January and the till will be moving position so it will require another revisit once this is complete. _x000D_19/8/2024:#Update - The internal installation requires a pole from the stand alone till up into the ceiling as it is not possible to get the line from the wall to the till area without causing a tripping hazard. Additionally the store is undergoing a refurbishment in January and the till will be moving position so it will require another revisit once this is complete. _x000D_19/8/2024:01447936 _x000D_16/8/2024:#Update - The internal installation requires a pole from the stand alone till up into the ceiling as it is not possible to get the line from the wall to the till area without causing a tripping hazard. Additionally the store is undergoing a refurbishment in January and the till will be moving position so it will require another revisit once this is complete. _x000D_15/8/2024:#Update - The internal installation requires a pole from the stand alone till up into the ceiling as it is not possible to get the line from the wall to the till area without causing a tripping hazard. Additionally the store is undergoing a refurbishment in January and the till will be moving position so it will require another revisit once this is complete. _x000D_14/8/2024:#Update - The internal installation requires a pole from the stand alone till up into the ceiling as it is not possible to get the line from the wall to the till area without causing a tripping hazard. Additionally the store is undergoing a refurbishment in January and the till will be moving position so it will require another revisit once this is complete. _x000D_13/8/2024:#Update - The internal installation requires a pole from the stand alone till up into the ceiling as it is not possible to get the line from the wall to the till area without causing a tripping hazard. Additionally the store is undergoing a refurbishment in January and the till will be moving position so it will require another revisit once this is complete. _x000D_12/8/2024:#Update - The internal installation requires a pole from the stand alone till up into the ceiling as it is not possible to get the line from the wall to the till area without causing a tripping hazard. Additionally the store is undergoing a refurbishment in January and the till will be moving position so it will require another revisit once this is complete. _x000D_9/8/2024:#Update - The internal installation requires a pole from the stand alone till up into the ceiling as it is not possible to get the line from the wall to the till area without causing a tripping hazard. Additionally the store is undergoing a refurbishment in January and the till will be moving position so it will require another revisit once this is complete. _x000D_8/8/2024:07/08/2024 _x000D_6/8/2024:25/07/2024 _x000D_5/8/2024:25/07/2024 _x000D_2/8/2024:25/07/2024 _x000D_1/8/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_30/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 AM _x000D_29/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 AM _x000D_29/7/2024:01447936 _x000D_26/7/2024:01447936 _x000D_24/7/2024:#Update - Action for Allwyn - Installation has now been amended to 06/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 06/08 is a suitable date. _x000D_23/7/2024:#Update - Action for Allwyn - Installation has now been amended to 06/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 06/08 is a suitable date. _x000D_22/7/2024:#Update - Action for Allwyn - Installation has now been amended to 06/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 06/08 is a suitable date. _x000D_22/7/2024:#Update - Action for Allwyn - Installation has now been amended to 06/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 06/08 is a suitable date. _x000D_25/6/2024:Order Completed _x000D_24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | #Update - The retailer is having a refurbishment in 2025 therefore Allwyn have cancelled the order and will re-raise after this work has been completed. | 2024-06-07 |  |  |  |  | VFP2366123 | 30016993 | 1.Provisioning | AM |  | 2024-06-21 | 2024-09-09 |  | 0 | [11 empty] | 0
679 | 486281 | 3123 | Batch 5 Jul24 | Type 1 | SOGEA | SPAR MOUNT CRESCENT | SWANSEA | SA6 6AP |  | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:#Update Reappointed 12/07 AM as retailer unaware of the first app. Action on Allwyn - ensure retailer is aware of new appointment. _x000D_15/7/2024:#Update Reappointed 12/07 AM as retailer unaware of the first app. Action on Allwyn - ensure retailer is aware of new appointment. _x000D_12/7/2024:#Update Reappointed 12/07 AM as retailer unaware of the first app. Action on Allwyn - ensure retailer is aware of new appointment. _x000D_11/7/2024:#Update Reappointed 12/07 AM as retailer unaware of the first app. Action on Allwyn - ensure retailer is aware of new appointment. _x000D_10/7/2024:#Update Reappointed 12/07 AM as retailer unaware of the first app. Action on Allwyn - ensure retailer is aware of new appointment. _x000D_9/7/2024:#Update Reappointed 12/07 AM as retailer unaware of the first app. Action on Allwyn - ensure retailer is aware of new appointment. _x000D_4/7/2024:#Update Reappointed 12/07 AM as retailer unaware of the first app. Action on Allwyn - ensure retailer is aware of new appointment. _x000D_3/7/2024:#Update Reappointed 12/07 AM as retailer unaware of the first app. Action on Allwyn - ensure retailer is aware of new appointment. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update Reappointed 12/07 AM as retailer unaware of the first app. Action on Allwyn - ensure retailer is aware of new appointment. _x000D_27/6/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_25/6/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:#Update Reappointed 12/07 AM as retailer unaware of the first app. Action on Allwyn - ensure retailer is aware of new appointment. _x000D_15/7/2024:#Update Reappointed 12/07 AM as retailer unaware of the first app. Action on Allwyn - ensure retailer is aware of new appointment. _x000D_12/7/2024:#Update Reappointed 12/07 AM as retailer unaware of the first app. Action on Allwyn - ensure retailer is aware of new appointment. _x000D_11/7/2024:#Update Reappointed 12/07 AM as retailer unaware of the first app. Action on Allwyn - ensure retailer is aware of new appointment. _x000D_10/7/2024:#Update Reappointed 12/07 AM as retailer unaware of the first app. Action on Allwyn - ensure retailer is aware of new appointment. _x000D_9/7/2024:#Update Reappointed 12/07 AM as retailer unaware of the first app. Action on Allwyn - ensure retailer is aware of new appointment. _x000D_4/7/2024:#Update Reappointed 12/07 AM as retailer unaware of the first app. Action on Allwyn - ensure retailer is aware of new appointment. _x000D_3/7/2024:#Update Reappointed 12/07 AM as retailer unaware of the first app. Action on Allwyn - ensure retailer is aware of new appointment. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update Reappointed 12/07 AM as retailer unaware of the first app. Action on Allwyn - ensure retailer is aware of new appointment. _x000D_27/6/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_25/6/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015595 | 30016811 | 6.Failed router install |  |  | 2024-06-21 | 2024-06-21 | 2024-06-21 | TRUE |  |  |  | 2024-07-23 |  |  |  | 2024-07-23 | 242005010416 |  | 2024-07-24 | 1
680 | 449467 | 3124 | Batch 5 Jul24 | Type 1 | FTTP | A One Star News and Convenience | BIRMINGHAM | B33 9HG |  | 9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_25/6/2024:Order Completed _x000D_24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_25/6/2024:Order Completed _x000D_24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366122 | 30016922 | 6.Failed router install |  |  | 2024-06-21 | 2024-07-12 | 2024-07-12 | TRUE |  |  |  | 2024-08-08 |  |  |  | 2024-08-08 | 23A004948342 |  | 2024-08-09 | 1
681 | 435933 | 3127 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | The Cabin Convenience Store | Littlehampton | BN17 5HZ |  | 6/9/2024:#Update Sent chaser to VF on approving upgrade / OHH _x000D_5/9/2024:#Update Sent chaser to VF on approving upgrade / OHH _x000D_4/9/2024:#Update Sent chaser to VF on approving upgrade / OHH _x000D_3/9/2024:#Update Sent chaser to VF on approving upgrade / OHH _x000D_2/9/2024:#Update Sent chaser to VF on approving upgrade / OHH _x000D_29/8/2024:#Update Sent chaser to VF on approving upgrade / OHH _x000D_28/8/2024:#Update Sent chaser to VF on approving upgrade / OHH _x000D_27/8/2024:#Update Sent chaser to VF on approving upgrade / OHH _x000D_22/8/2024:#Update Sent chaser to VF on approving upgrade / OHH _x000D_21/8/2024:#Update Sent chaser to VF on approving upgrade / OHH _x000D_20/8/2024:#Update Sent chaser to VF on approving upgrade / OHH _x000D_19/8/2024:#Update Sent chaser to VF on approving upgrade / OHH _x000D_19/8/2024:01447580 _x000D_16/8/2024:#Update Sent chaser to VF on approving upgrade / OHH _x000D_15/8/2024:#Update Sent chaser to VF on approving upgrade / OHH _x000D_14/8/2024:#Update Sent chaser to VF on approving upgrade / OHH _x000D_13/8/2024:#Update Sent chaser to VF on approving upgrade / OHH _x000D_12/8/2024:#Update Sent chaser to VF on approving upgrade / OHH _x000D_9/8/2024:#Update Sent chaser to VF on approving upgrade / OHH _x000D_8/8/2024:25/07/2024 _x000D_6/8/2024:25/07/2024 _x000D_5/8/2024:25/07/2024 _x000D_2/8/2024:25/07/2024 _x000D_1/8/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_30/7/2024:#Update Sent chaser to VF on approving upgrade / OHH _x000D_29/7/2024:#Update Sent chaser to VF on approving upgrade / OHH _x000D_29/7/2024:01447580 _x000D_26/7/2024:01447580 _x000D_24/7/2024:#Update Upgrade sent to VF for approval. OOH also needed, Allwyn to speak to the retailer for dates/times that suit for works to take place. _x000D_23/7/2024:#Update Upgrade sent to VF for approval. OOH also needed, Allwyn to speak to the retailer for dates/times that suit for works to take place. _x000D_22/7/2024:#Update Upgrade sent to VF for approval. OOH also needed, Allwyn to speak to the retailer for dates/times that suit for works to take place. _x000D_22/7/2024:#Update Upgrade sent to VF for approval. OOH also needed, Allwyn to speak to the retailer for dates/times that suit for works to take place. _x000D_25/6/2024:Order Completed _x000D_24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:#Update Sent chaser to VF on approving upgrade / OHH _x000D_6/9/2024:#Update Sent chaser to VF on approving upgrade / OHH _x000D_5/9/2024:#Update Sent chaser to VF on approving upgrade / OHH _x000D_4/9/2024:#Update Sent chaser to VF on approving upgrade / OHH _x000D_3/9/2024:#Update Sent chaser to VF on approving upgrade / OHH _x000D_2/9/2024:#Update Sent chaser to VF on approving upgrade / OHH _x000D_29/8/2024:#Update Sent chaser to VF on approving upgrade / OHH _x000D_28/8/2024:#Update Sent chaser to VF on approving upgrade / OHH _x000D_27/8/2024:#Update Sent chaser to VF on approving upgrade / OHH _x000D_22/8/2024:#Update Sent chaser to VF on approving upgrade / OHH _x000D_21/8/2024:#Update Sent chaser to VF on approving upgrade / OHH _x000D_20/8/2024:#Update Sent chaser to VF on approving upgrade / OHH _x000D_19/8/2024:#Update Sent chaser to VF on approving upgrade / OHH _x000D_19/8/2024:01447580 _x000D_16/8/2024:#Update Sent chaser to VF on approving upgrade / OHH _x000D_15/8/2024:#Update Sent chaser to VF on approving upgrade / OHH _x000D_14/8/2024:#Update Sent chaser to VF on approving upgrade / OHH _x000D_13/8/2024:#Update Sent chaser to VF on approving upgrade / OHH _x000D_12/8/2024:#Update Sent chaser to VF on approving upgrade / OHH _x000D_9/8/2024:#Update Sent chaser to VF on approving upgrade / OHH _x000D_8/8/2024:25/07/2024 _x000D_6/8/2024:25/07/2024 _x000D_5/8/2024:25/07/2024 _x000D_2/8/2024:25/07/2024 _x000D_1/8/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_30/7/2024:#Update Sent chaser to VF on approving upgrade / OHH _x000D_29/7/2024:#Update Sent chaser to VF on approving upgrade / OHH _x000D_29/7/2024:01447580 _x000D_26/7/2024:01447580 _x000D_24/7/2024:#Update Upgrade sent to VF for approval. OOH also needed, Allwyn to speak to the retailer for dates/times that suit for works to take place. _x000D_23/7/2024:#Update Upgrade sent to VF for approval. OOH also needed, Allwyn to speak to the retailer for dates/times that suit for works to take place. _x000D_22/7/2024:#Update Upgrade sent to VF for approval. OOH also needed, Allwyn to speak to the retailer for dates/times that suit for works to take place. _x000D_22/7/2024:#Update Upgrade sent to VF for approval. OOH also needed, Allwyn to speak to the retailer for dates/times that suit for works to take place. _x000D_25/6/2024:Order Completed _x000D_24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | Update: Order Amended | #Update Sent chaser to VF on approving upgrade / OHH | 2024-06-07 |  |  |  |  | VFS1015593 | 30016963 | 1.Provisioning | AM |  | 2024-06-21 | 2024-09-06 |  | 0 | [11 empty] | 0
682 | 450047 | 3128 | Batch 5 Jul24 | Type 1 | FTTP | Am Pm Convenience Store | WREXHAM | LL11 6LW |  | 25/6/2024:Order Completed _x000D_24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 25/6/2024:Order Completed _x000D_24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366120 | 30016734 | 2.Commissioning |  |  | 2024-06-21 | 2024-06-21 | 2024-06-21 | TRUE |  |  |  | 2024-07-19 | [7 empty] | 0
683 | 465554 | 3132 | Batch 5 Jul24 | Type 1 | SOGEA | SPAR LEEGOMERY | Telford | TF1 6XQ |  | 25/6/2024:Order Completed _x000D_24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 25/6/2024:Order Completed _x000D_24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015590 | 30016885 | 6.Failed router install |  |  | 2024-06-21 | 2024-06-21 | 2024-06-24 | TRUE |  |  |  | 2024-07-18 |  |  |  | 2024-08-27 | 23A004948618 | 23A004948618 | 2024-08-28 | 1
684 | 201180 | 3133 | Batch 5 Jul24 | Type 1 | SOGEA | Buchandyke Filling Station | GLASGOW | G74 3LT |  | 25/6/2024:Order Completed _x000D_24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 25/6/2024:Order Completed _x000D_24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015591 | 30016780 | 6.Failed router install |  |  | 2024-06-21 | 2024-06-21 | 2024-06-21 | TRUE |  |  |  | 2024-07-23 |  |  |  | 2024-07-23 | 239004929543 |  | 2024-07-24 | 1
685 | 631172 | 3134 | Batch 5 Jul24 | Type 1 | FTTP | SPAR | DEESIDE | CH5 1SU |  | 9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:Update: Order Amended _x000D_25/6/2024:Update: Order Amended _x000D_24/6/2024:Update: Order Amended _x000D_20/6/2024:Update: Order Amended _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:Update: Order Amended _x000D_25/6/2024:Update: Order Amended _x000D_24/6/2024:Update: Order Amended _x000D_20/6/2024:Update: Order Amended _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366121 | 30016951 | 6.Failed router install |  |  | 2024-06-21 | 2024-06-21 | 2024-06-21 | TRUE |  |  |  | 2024-07-11 |  |  |  | 2024-07-11 | 242005008854 |  | 2024-07-12 | 1
686 | 664460 | 3136 | Batch 5 Jul24 | Type 1 | SOGEA | Eurospar Lagmore | Belfast | BT17 0LB |  | 25/6/2024:Order Completed _x000D_24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 25/6/2024:Order Completed _x000D_24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015489 | 30017010 | 6.Failed router install |  |  | 2024-06-21 | 2024-06-21 | 2024-06-21 | TRUE |  |  |  | 2024-07-18 |  |  |  | 2024-07-18 | 242005010313 |  | 2024-07-18 | 1
687 | 660777 | 281 | Batch 2 Apr24 | Type 1 | FTTP/Mobile | Metro Stores | Rotherham | S65 2DE | 2024-05-30 | 6/9/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_5/9/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_4/9/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_3/9/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_2/9/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_29/8/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_28/8/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_27/8/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_22/8/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_21/8/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_20/8/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_19/8/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_19/8/2024:01352818 _x000D_16/8/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_15/8/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_14/8/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_13/8/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_12/8/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_9/8/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_8/8/2024:18/06/2024 _x000D_6/8/2024:18/06/2024 _x000D_5/8/2024:18/06/2024 _x000D_2/8/2024:18/06/2024 _x000D_1/8/2024:18/06/2024 _x000D_31/7/2024:18/06/2024 _x000D_31/7/2024:18/06/2024 _x000D_30/7/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_29/7/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_29/7/2024:01352818 _x000D_26/7/2024:01352818 _x000D_24/7/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_23/7/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_22/7/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_22/7/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:#Update - OR confirmed engineers to attend Monday 8th -Am _x000D_11/7/2024:#Update - OR confirmed engineers to attend Monday 8th -Am _x000D_10/7/2024:#Update - OR confirmed engineers to attend Monday 8th -Am _x000D_9/7/2024:#Update - OR confirmed engineers to attend Monday 8th -Am _x000D_4/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 between 8-10 AM - Retailer is closing the store during this time period. _x000D_3/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 between 8-10 AM - Retailer is closing the store during this time period. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 between 8-10 AM - Retailer is closing the store during this time period. _x000D_27/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 between 8-10 AM - Retailer is closing the store during this time period. _x000D_25/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 between 8-10 AM - Retailer is closing the store during this time period. _x000D_24/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 between 8-10 AM - Retailer is closing the store during this time period. _x000D_20/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 between 8-10 AM - Retailer is closing the store during this time period. _x000D_19/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 between 8-10 AM - Retailer is closing the store during this time period. _x000D_18/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 between 8-10 AM - Retailer is closing the store during this time period. _x000D_17/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 between 8-10 AM - Retailer is closing the store during this time period. _x000D_14/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 between 8-10 AM - Retailer is closing the store during this time period. _x000D_13/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 between 8-10 AM - Retailer is closing the store during this time period. _x000D_12/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 between 8-10 AM - Retailer is closing the store during this time period. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 9/9/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_6/9/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_5/9/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_4/9/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_3/9/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_2/9/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_29/8/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_28/8/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_27/8/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_22/8/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_21/8/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_20/8/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_19/8/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_19/8/2024:01352818 _x000D_16/8/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_15/8/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_14/8/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_13/8/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_12/8/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_9/8/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_8/8/2024:18/06/2024 _x000D_6/8/2024:18/06/2024 _x000D_5/8/2024:18/06/2024 _x000D_2/8/2024:18/06/2024 _x000D_1/8/2024:18/06/2024 _x000D_31/7/2024:18/06/2024 _x000D_31/7/2024:18/06/2024 _x000D_30/7/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_29/7/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_29/7/2024:01352818 _x000D_26/7/2024:01352818 _x000D_24/7/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_23/7/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_22/7/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_22/7/2024:#Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:#Update - OR confirmed engineers to attend Monday 8th -Am _x000D_11/7/2024:#Update - OR confirmed engineers to attend Monday 8th -Am _x000D_10/7/2024:#Update - OR confirmed engineers to attend Monday 8th -Am _x000D_9/7/2024:#Update - OR confirmed engineers to attend Monday 8th -Am _x000D_4/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 between 8-10 AM - Retailer is closing the store during this time period. _x000D_3/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 between 8-10 AM - Retailer is closing the store during this time period. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 between 8-10 AM - Retailer is closing the store during this time period. _x000D_27/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 between 8-10 AM - Retailer is closing the store during this time period. _x000D_25/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 between 8-10 AM - Retailer is closing the store during this time period. _x000D_24/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 between 8-10 AM - Retailer is closing the store during this time period. _x000D_20/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 between 8-10 AM - Retailer is closing the store during this time period. _x000D_19/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 between 8-10 AM - Retailer is closing the store during this time period. _x000D_18/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 between 8-10 AM - Retailer is closing the store during this time period. _x000D_17/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 between 8-10 AM - Retailer is closing the store during this time period. _x000D_14/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 between 8-10 AM - Retailer is closing the store during this time period. _x000D_13/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 between 8-10 AM - Retailer is closing the store during this time period. _x000D_12/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 between 8-10 AM - Retailer is closing the store during this time period. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | Update: Order Amended | #Update - Order has been pushed out to 15/07 - awaiting for the additional charges to be accepted | 2024-05-09 | 09/05/2024: CSL to provide an update 12/04/2024: Allwyn to make the retailer aware. 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 5.CSL | VFP2300543 | 30013285 | 1.Provisioning | AM |  | 2024-04-12 | 2024-08-29 |  | 0 | [11 empty] | 0
688 | 618280 | 476 | Batch 3 May24 | Type 1 | SOGEA | Craghead Pharmacy | Stanley | DH9 6DD | 2024-05-10 | 19/7/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_18/7/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_17/7/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_16/7/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_15/7/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_12/7/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_11/7/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_10/7/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_9/7/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_4/7/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_3/7/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_2/7/2024:0 _x000D_1/7/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_27/6/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_25/6/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_24/6/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_20/6/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_19/6/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_18/6/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_17/6/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_14/6/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_13/6/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_12/6/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 19/7/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_18/7/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_17/7/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_16/7/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_15/7/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_12/7/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_11/7/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_10/7/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_9/7/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_4/7/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_3/7/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_2/7/2024:0 _x000D_1/7/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_27/6/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_25/6/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_24/6/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_20/6/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_19/6/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_18/6/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_17/6/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_14/6/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_13/6/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_12/6/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-05-07 | 07/05/2024: CSL to provide an update |  |  | 3.Allwyn to arrange rtr install | VFP2300673 | 30013366 | 6.Failed router install | AM |  | 2024-05-03 | 2024-06-24 | 2024-06-24 | TRUE |  |  |  | 2024-07-17 |  |  |  | 2024-07-17 | 238004926195 |  | 2024-07-17 | 1
689 | 637344 | 571 | Batch 3 May24 | Type 1 | SoGEA/Mobile | Budgens | Cambridge | CB4 2JQ | 2024-08-15 | 16/8/2024:#Update - Openreach organised out of hours access to for 13/08 - 10PM. Allwyn aware. _x000D_15/8/2024:#Update - Openreach organised out of hours access to for 13/08 - 10PM. Allwyn aware. _x000D_14/8/2024:#Update - Openreach organised out of hours access to for 13/08 - 10PM. Allwyn aware. _x000D_13/8/2024:#Update - Openreach organised out of hours access to for 13/08 - 10PM. Allwyn aware. _x000D_12/8/2024:#Update - Openreach organised out of hours access to for 13/08 - 10PM. Allwyn aware. _x000D_9/8/2024:#Update - Openreach organised out of hours access to for 13/08 - 10PM. Allwyn aware. _x000D_8/8/2024:06/08/2024 _x000D_6/8/2024:29/07/2024 _x000D_5/8/2024:29/07/2024 _x000D_2/8/2024:29/07/2024 _x000D_1/8/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_30/7/2024:#Update - Pushed out to the 05/08 - awaiting ECC approval _x000D_29/7/2024:#Update - Pushed out to the 05/08 - awaiting ECC approval _x000D_29/7/2024:01409047 _x000D_26/7/2024:01409047 _x000D_24/7/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_23/7/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_22/7/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_22/7/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_19/7/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_18/7/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_17/7/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_16/7/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_15/7/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_12/7/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_11/7/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_10/7/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_9/7/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_4/7/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_3/7/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_2/7/2024:A4 (ECC) _x000D_1/7/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_27/6/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_25/6/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_24/6/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_20/6/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_19/6/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_18/6/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_17/6/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_14/6/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_13/6/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_12/6/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 16/8/2024:#Update - Openreach organised out of hours access to for 13/08 - 10PM. Allwyn aware. _x000D_15/8/2024:#Update - Openreach organised out of hours access to for 13/08 - 10PM. Allwyn aware. _x000D_14/8/2024:#Update - Openreach organised out of hours access to for 13/08 - 10PM. Allwyn aware. _x000D_13/8/2024:#Update - Openreach organised out of hours access to for 13/08 - 10PM. Allwyn aware. _x000D_12/8/2024:#Update - Openreach organised out of hours access to for 13/08 - 10PM. Allwyn aware. _x000D_9/8/2024:#Update - Openreach organised out of hours access to for 13/08 - 10PM. Allwyn aware. _x000D_8/8/2024:06/08/2024 _x000D_6/8/2024:29/07/2024 _x000D_5/8/2024:29/07/2024 _x000D_2/8/2024:29/07/2024 _x000D_1/8/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_30/7/2024:#Update - Pushed out to the 05/08 - awaiting ECC approval _x000D_29/7/2024:#Update - Pushed out to the 05/08 - awaiting ECC approval _x000D_29/7/2024:01409047 _x000D_26/7/2024:01409047 _x000D_24/7/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_23/7/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_22/7/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_22/7/2024:#Update Appointment missed 07/06/2024, will be amended to 24/06/2024 _x000D_19/7/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_18/7/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_17/7/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_16/7/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_15/7/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_12/7/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_11/7/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_10/7/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_9/7/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_4/7/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_3/7/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_2/7/2024:A4 (ECC) _x000D_1/7/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_27/6/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_25/6/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_24/6/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_20/6/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_19/6/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_18/6/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_17/6/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_14/6/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_13/6/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_12/6/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | [6 empty] | 2.Allwyn to arrange access | VFP2300768 | 30013461 | 2.Commissioning | AM |  | 2024-05-23 | 2024-08-14 | 2024-08-14 09:32 | 1 | [11 empty] | 0
690 | 663314 | 617 | Batch 3 May24 | Type 1 | FTTP/Mobile | Triple A Foodhall | Nuneaton | CV10 0PH | 2024-09-04 | 6/9/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_5/9/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_4/9/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_3/9/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_2/9/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_29/8/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_28/8/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_27/8/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_22/8/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_21/8/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_20/8/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_19/8/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_19/8/2024:01398878 _x000D_16/8/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_15/8/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_14/8/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_13/8/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_12/8/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_9/8/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_8/8/2024:28/05/2024 _x000D_6/8/2024:28/05/2024 _x000D_5/8/2024:28/05/2024 _x000D_2/8/2024:28/05/2024 _x000D_1/8/2024:28/05/2024 _x000D_31/7/2024:28/05/2024 _x000D_31/7/2024:28/05/2024 _x000D_30/7/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_29/7/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_29/7/2024:01398878 _x000D_26/7/2024:01398878 _x000D_24/7/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_23/7/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_22/7/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_22/7/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:#Update - Allwyn confirmed re-appointment of 24/06 with retailer. _x000D_25/6/2024:#Update - Allwyn confirmed re-appointment of 24/06 with retailer. _x000D_24/6/2024:#Update - Allwyn confirmed re-appointment of 24/06 with retailer. _x000D_20/6/2024:#Update - Allwyn confirmed re-appointment of 24/06 with retailer. _x000D_19/6/2024:#Update - Allwyn confirmed re-appointment of 24/06 with retailer. _x000D_18/6/2024:#Update - Allwyn confirmed re-appointment of 24/06 with retailer. _x000D_17/6/2024:#Update - Allwyn confirmed re-appointment of 24/06 with retailer. _x000D_14/6/2024:#Update - Allwyn confirmed re-appointment of 24/06 with retailer. _x000D_13/6/2024:#Update - Allwyn confirmed re-appointment of 24/06 with retailer. _x000D_12/6/2024:#Update - Retailer unaware/Engineer asked not to start work. Allwyn to confirm new appointment date of 24/06 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 9/9/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_6/9/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_5/9/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_4/9/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_3/9/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_2/9/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_29/8/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_28/8/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_27/8/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_22/8/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_21/8/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_20/8/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_19/8/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_19/8/2024:01398878 _x000D_16/8/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_15/8/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_14/8/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_13/8/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_12/8/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_9/8/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_8/8/2024:28/05/2024 _x000D_6/8/2024:28/05/2024 _x000D_5/8/2024:28/05/2024 _x000D_2/8/2024:28/05/2024 _x000D_1/8/2024:28/05/2024 _x000D_31/7/2024:28/05/2024 _x000D_31/7/2024:28/05/2024 _x000D_30/7/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_29/7/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_29/7/2024:01398878 _x000D_26/7/2024:01398878 _x000D_24/7/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_23/7/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_22/7/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_22/7/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:#Update - Allwyn confirmed re-appointment of 24/06 with retailer. _x000D_25/6/2024:#Update - Allwyn confirmed re-appointment of 24/06 with retailer. _x000D_24/6/2024:#Update - Allwyn confirmed re-appointment of 24/06 with retailer. _x000D_20/6/2024:#Update - Allwyn confirmed re-appointment of 24/06 with retailer. _x000D_19/6/2024:#Update - Allwyn confirmed re-appointment of 24/06 with retailer. _x000D_18/6/2024:#Update - Allwyn confirmed re-appointment of 24/06 with retailer. _x000D_17/6/2024:#Update - Allwyn confirmed re-appointment of 24/06 with retailer. _x000D_14/6/2024:#Update - Allwyn confirmed re-appointment of 24/06 with retailer. _x000D_13/6/2024:#Update - Allwyn confirmed re-appointment of 24/06 with retailer. _x000D_12/6/2024:#Update - Retailer unaware/Engineer asked not to start work. Allwyn to confirm new appointment date of 24/06 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | Order Completed | #Update - NFA - Allwyn have confirmed reappointed install date with retailer | 2024-05-17 | 17/05/2024: Allwyn to arrange access on new date |  |  | 2.Allwyn to arrange access | VFP2325341 | 30013507 | 2.Commissioning | AM |  | 2024-05-16 | 2024-08-06 |  | 0 | [11 empty] | 0
691 | 664890 | 1107 | Batch 3 May24 | Type 1 | SoGEA/Mobile | BUSY LANE PO | SHIPLEY | BD18 1DZ | 2024-06-07 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:#Update Customer missed appointment due to customer not being ready for installation. Reappointed for 24/06 PM _x000D_21/8/2024:#Update Customer missed appointment due to customer not being ready for installation. Reappointed for 24/06 PM _x000D_20/8/2024:#Update Customer missed appointment due to customer not being ready for installation. Reappointed for 24/06 PM _x000D_19/8/2024:#Update Customer missed appointment due to customer not being ready for installation. Reappointed for 24/06 PM _x000D_19/8/2024:01407499 _x000D_16/8/2024:#Update Customer missed appointment due to customer not being ready for installation. Reappointed for 24/06 PM _x000D_15/8/2024:#Update Customer missed appointment due to customer not being ready for installation. Reappointed for 24/06 PM _x000D_14/8/2024:#Update Customer missed appointment due to customer not being ready for installation. Reappointed for 24/06 PM _x000D_13/8/2024:#Update Customer missed appointment due to customer not being ready for installation. Reappointed for 24/06 PM _x000D_12/8/2024:#Update Customer missed appointment due to customer not being ready for installation. Reappointed for 24/06 PM _x000D_9/8/2024:#Update Customer missed appointment due to customer not being ready for installation. Reappointed for 24/06 PM _x000D_8/8/2024:10/06/2024 _x000D_6/8/2024:10/06/2024 _x000D_5/8/2024:10/06/2024 _x000D_2/8/2024:10/06/2024 _x000D_1/8/2024:10/06/2024 _x000D_31/7/2024:10/06/2024 _x000D_31/7/2024:10/06/2024 _x000D_30/7/2024:#Update Customer missed appointment due to customer not being ready for installation. Reappointed for 24/06 PM _x000D_29/7/2024:#Update Customer missed appointment due to customer not being ready for installation. Reappointed for 24/06 PM _x000D_29/7/2024:01407499 _x000D_26/7/2024:01407499 _x000D_24/7/2024:#Update Customer missed appointment due to customer not being ready for installation. Reappointed for 24/06 PM _x000D_23/7/2024:#Update Customer missed appointment due to customer not being ready for installation. Reappointed for 24/06 PM _x000D_22/7/2024:#Update Customer missed appointment due to customer not being ready for installation. Reappointed for 24/06 PM _x000D_22/7/2024:#Update Customer missed appointment due to customer not being ready for installation. Reappointed for 24/06 PM _x000D_19/7/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_18/7/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_17/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 AM _x000D_16/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 AM _x000D_15/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 AM _x000D_12/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 AM _x000D_11/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 AM _x000D_10/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 AM _x000D_9/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 AM _x000D_4/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 AM _x000D_3/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 AM _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 AM _x000D_27/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 AM _x000D_25/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 AM _x000D_24/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 AM _x000D_20/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 AM _x000D_19/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 AM _x000D_18/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 AM _x000D_17/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 AM _x000D_14/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 AM _x000D_13/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 AM _x000D_12/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 AM _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:#Update Customer missed appointment due to customer not being ready for installation. Reappointed for 24/06 PM _x000D_21/8/2024:#Update Customer missed appointment due to customer not being ready for installation. Reappointed for 24/06 PM _x000D_20/8/2024:#Update Customer missed appointment due to customer not being ready for installation. Reappointed for 24/06 PM _x000D_19/8/2024:#Update Customer missed appointment due to customer not being ready for installation. Reappointed for 24/06 PM _x000D_19/8/2024:01407499 _x000D_16/8/2024:#Update Customer missed appointment due to customer not being ready for installation. Reappointed for 24/06 PM _x000D_15/8/2024:#Update Customer missed appointment due to customer not being ready for installation. Reappointed for 24/06 PM _x000D_14/8/2024:#Update Customer missed appointment due to customer not being ready for installation. Reappointed for 24/06 PM _x000D_13/8/2024:#Update Customer missed appointment due to customer not being ready for installation. Reappointed for 24/06 PM _x000D_12/8/2024:#Update Customer missed appointment due to customer not being ready for installation. Reappointed for 24/06 PM _x000D_9/8/2024:#Update Customer missed appointment due to customer not being ready for installation. Reappointed for 24/06 PM _x000D_8/8/2024:10/06/2024 _x000D_6/8/2024:10/06/2024 _x000D_5/8/2024:10/06/2024 _x000D_2/8/2024:10/06/2024 _x000D_1/8/2024:10/06/2024 _x000D_31/7/2024:10/06/2024 _x000D_31/7/2024:10/06/2024 _x000D_30/7/2024:#Update Customer missed appointment due to customer not being ready for installation. Reappointed for 24/06 PM _x000D_29/7/2024:#Update Customer missed appointment due to customer not being ready for installation. Reappointed for 24/06 PM _x000D_29/7/2024:01407499 _x000D_26/7/2024:01407499 _x000D_24/7/2024:#Update Customer missed appointment due to customer not being ready for installation. Reappointed for 24/06 PM _x000D_23/7/2024:#Update Customer missed appointment due to customer not being ready for installation. Reappointed for 24/06 PM _x000D_22/7/2024:#Update Customer missed appointment due to customer not being ready for installation. Reappointed for 24/06 PM _x000D_22/7/2024:#Update Customer missed appointment due to customer not being ready for installation. Reappointed for 24/06 PM _x000D_19/7/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_18/7/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_17/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 AM _x000D_16/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 AM _x000D_15/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 AM _x000D_12/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 AM _x000D_11/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 AM _x000D_10/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 AM _x000D_9/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 AM _x000D_4/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 AM _x000D_3/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 AM _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 AM _x000D_27/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 AM _x000D_25/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 AM _x000D_24/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 AM _x000D_20/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 AM _x000D_19/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 AM _x000D_18/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 AM _x000D_17/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 AM _x000D_14/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 AM _x000D_13/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 AM _x000D_12/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 24/06 AM _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 3.Allwyn to arrange rtr install | VFP2301304 | 30013997 | 2.Commissioning | AM |  | 2024-05-23 | 2024-08-21 |  | 0 |  |  |  | 2024-09-19 | [7 empty] | 0
692 | 665098 | 1169 | Batch 3 May24 | Type 1 | SoGEA/Mobile | Upton Lea PO | Slough | SL2 5JX | 2024-06-07 | 6/9/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_5/9/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_4/9/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_3/9/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_2/9/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_29/8/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_28/8/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_27/8/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_22/8/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_21/8/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_20/8/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_19/8/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_19/8/2024:01412450 _x000D_16/8/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_15/8/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_14/8/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_13/8/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_12/8/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_9/8/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_8/8/2024:17/07/2024 _x000D_6/8/2024:17/07/2024 _x000D_5/8/2024:17/07/2024 _x000D_2/8/2024:17/07/2024 _x000D_1/8/2024:17/07/2024 _x000D_31/7/2024:17/07/2024 _x000D_31/7/2024:17/07/2024 _x000D_30/7/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_29/7/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_29/7/2024:01412450 _x000D_26/7/2024:01412450 _x000D_24/7/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_23/7/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_22/7/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_22/7/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:Update: Order Amended _x000D_14/6/2024:Update: Order Amended _x000D_13/6/2024:Update: Order Amended _x000D_12/6/2024:Update: Order Amended _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_6/9/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_5/9/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_4/9/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_3/9/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_2/9/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_29/8/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_28/8/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_27/8/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_22/8/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_21/8/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_20/8/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_19/8/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_19/8/2024:01412450 _x000D_16/8/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_15/8/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_14/8/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_13/8/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_12/8/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_9/8/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_8/8/2024:17/07/2024 _x000D_6/8/2024:17/07/2024 _x000D_5/8/2024:17/07/2024 _x000D_2/8/2024:17/07/2024 _x000D_1/8/2024:17/07/2024 _x000D_31/7/2024:17/07/2024 _x000D_31/7/2024:17/07/2024 _x000D_30/7/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_29/7/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_29/7/2024:01412450 _x000D_26/7/2024:01412450 _x000D_24/7/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_23/7/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_22/7/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_22/7/2024:#Update - ECC proposal sent to Vodafone on 17/07 _x000D_27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:Update: Order Amended _x000D_14/6/2024:Update: Order Amended _x000D_13/6/2024:Update: Order Amended _x000D_12/6/2024:Update: Order Amended _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update - ECC proposal sent to Vodafone on 17/07 |  |  |  |  | 2.Allwyn to arrange access | VFS978004 | 30014059 | 1.Provisioning | AM |  | 2024-05-24 | 2024-08-22 |  | 0 | [11 empty] | 0
693 | 443997 | 1403 | Batch 4 Jun24 | Type 1 | SOGEA | Premier Arbourne | SWANSEA | SA1 7JZ | 2024-06-07 | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:#Update Missed appointment, retailer unaware. Reappointed 08/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_11/7/2024:#Update Missed appointment, retailer unaware. Reappointed 08/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_10/7/2024:#Update Missed appointment, retailer unaware. Reappointed 08/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_9/7/2024:#Update Missed appointment, retailer unaware. Reappointed 08/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_4/7/2024:#Update Missed appointment, retailer unaware. Reappointed 08/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_3/7/2024:#Update Missed appointment, retailer unaware. Reappointed 08/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update Missed appointment, retailer unaware. Reappointed 08/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_27/6/2024:Update: Order Amended _x000D_25/6/2024:Update: Order Amended _x000D_24/6/2024:End User Missed appointment. Action required _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:Update: Order Amended _x000D_14/6/2024:Update: Order Amended _x000D_13/6/2024:Update: Order Amended _x000D_12/6/2024:Update: Order Amended _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:#Update Missed appointment, retailer unaware. Reappointed 08/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_11/7/2024:#Update Missed appointment, retailer unaware. Reappointed 08/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_10/7/2024:#Update Missed appointment, retailer unaware. Reappointed 08/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_9/7/2024:#Update Missed appointment, retailer unaware. Reappointed 08/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_4/7/2024:#Update Missed appointment, retailer unaware. Reappointed 08/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_3/7/2024:#Update Missed appointment, retailer unaware. Reappointed 08/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update Missed appointment, retailer unaware. Reappointed 08/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_27/6/2024:Update: Order Amended _x000D_25/6/2024:Update: Order Amended _x000D_24/6/2024:End User Missed appointment. Action required _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:Update: Order Amended _x000D_14/6/2024:Update: Order Amended _x000D_13/6/2024:Update: Order Amended _x000D_12/6/2024:Update: Order Amended _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 | 7/6/2024: CSL to provide an update |  |  | 3.Allwyn to arrange rtr install | VFS984943 | 30015345 | 2.Commissioning | AM |  | 2024-06-06 | 2024-06-24 | 2024-06-24 | TRUE |  |  |  | 2024-07-30 | [7 empty] | 0
694 | 486426 | 1607 | Batch 4 Jun24 | Type 1 | SOGEA | SPAR WELLS | Wells | BA5 2DZ | 2024-06-26 | 27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:Update: Order Amended _x000D_7/6/2024:Update: Order Amended _x000D_6/6/2024:Update: Order Amended _x000D_5/6/2024:Update: Order Amended _x000D_4/6/2024:Update: Order Amended _x000D_31/5/2024:0 _x000D_02/05/2024: New order added to report | 27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:Update: Order Amended _x000D_7/6/2024:Update: Order Amended _x000D_6/6/2024:Update: Order Amended _x000D_5/6/2024:Update: Order Amended _x000D_4/6/2024:Update: Order Amended _x000D_31/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 | 31/05/24: CSL to provide an update |  |  | 3.Allwyn to arrange rtr install | VFS984810 | 30015297 | 6.Failed router install | AM |  | 2024-06-24 | 2024-06-24 | 2024-06-25 | TRUE |  |  |  | 2024-07-25 |  |  |  | 2024-07-25 | 242005010340 |  | 2024-07-26 | 1
695 | 651845 | 1742 | Batch 4 Jun24 | Type 1 | SOGEA | Whitemountain Stores & Filling Station | Lisburn | BT28 3SN | 2024-06-07 | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A4 (ECC) _x000D_1/7/2024:0 _x000D_27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:Update: Order Amended _x000D_13/6/2024:Update: Order Amended _x000D_12/6/2024:Update: Order Amended _x000D_10/6/2024:Update: Order Amended _x000D_7/6/2024:Supplier Delay: New Appointment might be required _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A4 (ECC) _x000D_1/7/2024:0 _x000D_27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:Update: Order Amended _x000D_13/6/2024:Update: Order Amended _x000D_12/6/2024:Update: Order Amended _x000D_10/6/2024:Update: Order Amended _x000D_7/6/2024:Supplier Delay: New Appointment might be required _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2369637 | 30017057 | 6.Failed router install | AM |  | 2024-06-24 | 2024-06-24 | 2024-06-24 | TRUE |  |  |  | 2024-07-29 |  |  |  | 2024-07-29 | 23A004952892 |  | 2024-07-30 | 1
696 | 627227 | 1810 | Batch 4 Jun24 | Type 1 | FTTP | Best One | Llanelli | SA15 2NP | 2024-06-07 | 27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:Update: Order Amended _x000D_7/6/2024:Update: Order Amended _x000D_6/6/2024:Update: Order Amended _x000D_5/6/2024:Update: Order Amended _x000D_4/6/2024:Update: Order Amended _x000D_31/5/2024:0 _x000D_02/05/2024: New order added to report | 27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:Update: Order Amended _x000D_7/6/2024:Update: Order Amended _x000D_6/6/2024:Update: Order Amended _x000D_5/6/2024:Update: Order Amended _x000D_4/6/2024:Update: Order Amended _x000D_31/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2369638 | 30017062 | 2.Commissioning | AM |  | 2024-06-24 | 2024-06-24 | 2024-06-24 | TRUE |  |  |  | 2024-09-09 | [7 empty] | 0
697 | 252561 | 1921 | Batch 4 Jun24 | Type 1 | SOGEA | Nisa Local | BOOTLE | L30 1QB | 2024-06-07 | 2/7/2024:0 _x000D_1/7/2024:#Update Your order has been delayed due to FlatRoof work is required, order is now with controls team to get the engineer reassigned. We will provide updates when they become available. _x000D_27/6/2024:#Update Your order has been delayed due to FlatRoof work is required, order is now with controls team to get the engineer reassigned. We will provide updates when they become available. _x000D_25/6/2024:The Order Target Date for this order has been updated to 25/06/2024. This is to complete the remaining outdoor activities only. No further engineering work is required at the End User¿s premises and their presence is not required. _x000D_24/6/2024:The Order Target Date for this order has been updated to 25/06/2024. This is to complete the remaining outdoor activities only. No further engineering work is required at the End User¿s premises and their presence is not required. _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:Update: Order Amended _x000D_7/6/2024:Update: Order Amended _x000D_6/6/2024:Update: Order Amended _x000D_5/6/2024:Update: Order Amended _x000D_4/6/2024:Update: Order Amended _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 2/7/2024:0 _x000D_1/7/2024:#Update Your order has been delayed due to FlatRoof work is required, order is now with controls team to get the engineer reassigned. We will provide updates when they become available. _x000D_27/6/2024:#Update Your order has been delayed due to FlatRoof work is required, order is now with controls team to get the engineer reassigned. We will provide updates when they become available. _x000D_25/6/2024:The Order Target Date for this order has been updated to 25/06/2024. This is to complete the remaining outdoor activities only. No further engineering work is required at the End User¿s premises and their presence is not required. _x000D_24/6/2024:The Order Target Date for this order has been updated to 25/06/2024. This is to complete the remaining outdoor activities only. No further engineering work is required at the End User¿s premises and their presence is not required. _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:Update: Order Amended _x000D_7/6/2024:Update: Order Amended _x000D_6/6/2024:Update: Order Amended _x000D_5/6/2024:Update: Order Amended _x000D_4/6/2024:Update: Order Amended _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1019384 | 30017054 | 2.Commissioning | AM |  | 2024-06-24 | 2024-06-24 | 2024-06-24 | TRUE |  |  |  | 2024-07-25 | [7 empty] | 0
698 | 630335 | 1931 | Batch 4 Jun24 | Type 1 | SOGEA | Spar | Huntingdon | PE28 2SA | 2024-06-07 | 19/7/2024:#Update - Site type change - Switching to site type 3 _x000D_18/7/2024:#Update - Site type change - Switching to site type 3 _x000D_17/7/2024:#Update - Site type change - Switching to site type 3 _x000D_16/7/2024:#Update - Site type change - Switching to site type 3 _x000D_15/7/2024:#Update - Site type change - Switching to site type 3 _x000D_12/7/2024:#Update - Site type change - Switching to site type 3 _x000D_11/7/2024:#Update - Site type change - Switching to site type 3 _x000D_10/7/2024:#Update - Site type change - Switching to site type 3 _x000D_9/7/2024:#Update - Site type change - Switching to site type 3 _x000D_4/7/2024:#Update - Probably need an upgrade to advance. Awaiting feedback from OR about this one. May need to place on hold until the planned renovations have begun as ceiling will be accessible then. Action for allwyn: Please confirm renovations date. I will provide info about upgrade IE hrs required once we hear back from OR. _x000D_3/7/2024:#Update - Probably need an upgrade to advance. Awaiting feedback from OR about this one. May need to place on hold until the planned renovations have begun as ceiling will be accessible then. Action for allwyn: Please confirm renovations date. I will provide info about upgrade IE hrs required once we hear back from OR. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Probably need an upgrade to advance. Awaiting feedback from OR about this one. May need to place on hold until the planned renovations have begun as ceiling will be accessible then. Action for allwyn: Please confirm renovations date. I will provide info about upgrade IE hrs required once we hear back from OR. _x000D_27/6/2024:#Update - Probably need an upgrade to advance. Awaiting feedback from OR about this one. May need to place on hold until the planned renovations have begun as ceiling will be accessible then. Action for allwyn: Please confirm renovations date. I will provide info about upgrade IE hrs required once we hear back from OR. _x000D_25/6/2024:#Update - Probably need an upgrade to advance. Awaiting feedback from OR about this one. May need to place on hold until the planned renovations have begun as ceiling will be accessible then. Action for allwyn: Please confirm renovations date. I will provide info about upgrade IE hrs required once we hear back from OR. _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:Update: Order Amended _x000D_7/6/2024:Update: Order Amended _x000D_6/6/2024:Update: Order Amended _x000D_5/6/2024:Update: Order Amended _x000D_4/6/2024:Update: Order Amended _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 19/7/2024:#Update - Site type change - Switching to site type 3 _x000D_18/7/2024:#Update - Site type change - Switching to site type 3 _x000D_17/7/2024:#Update - Site type change - Switching to site type 3 _x000D_16/7/2024:#Update - Site type change - Switching to site type 3 _x000D_15/7/2024:#Update - Site type change - Switching to site type 3 _x000D_12/7/2024:#Update - Site type change - Switching to site type 3 _x000D_11/7/2024:#Update - Site type change - Switching to site type 3 _x000D_10/7/2024:#Update - Site type change - Switching to site type 3 _x000D_9/7/2024:#Update - Site type change - Switching to site type 3 _x000D_4/7/2024:#Update - Probably need an upgrade to advance. Awaiting feedback from OR about this one. May need to place on hold until the planned renovations have begun as ceiling will be accessible then. Action for allwyn: Please confirm renovations date. I will provide info about upgrade IE hrs required once we hear back from OR. _x000D_3/7/2024:#Update - Probably need an upgrade to advance. Awaiting feedback from OR about this one. May need to place on hold until the planned renovations have begun as ceiling will be accessible then. Action for allwyn: Please confirm renovations date. I will provide info about upgrade IE hrs required once we hear back from OR. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Probably need an upgrade to advance. Awaiting feedback from OR about this one. May need to place on hold until the planned renovations have begun as ceiling will be accessible then. Action for allwyn: Please confirm renovations date. I will provide info about upgrade IE hrs required once we hear back from OR. _x000D_27/6/2024:#Update - Probably need an upgrade to advance. Awaiting feedback from OR about this one. May need to place on hold until the planned renovations have begun as ceiling will be accessible then. Action for allwyn: Please confirm renovations date. I will provide info about upgrade IE hrs required once we hear back from OR. _x000D_25/6/2024:#Update - Probably need an upgrade to advance. Awaiting feedback from OR about this one. May need to place on hold until the planned renovations have begun as ceiling will be accessible then. Action for allwyn: Please confirm renovations date. I will provide info about upgrade IE hrs required once we hear back from OR. _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:Update: Order Amended _x000D_7/6/2024:Update: Order Amended _x000D_6/6/2024:Update: Order Amended _x000D_5/6/2024:Update: Order Amended _x000D_4/6/2024:Update: Order Amended _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2368366 | 30016107 | 2.Commissioning | AM |  | 2024-06-24 | 2024-06-24 | 2024-06-28 | TRUE |  |  |  | 2024-07-24 | [7 empty] | 0
699 | 447346 | 2931 | Batch 4 Jun24 | Type 3 | FTTP/Mobile | Spar | Antrim | BT41 2EB | 2024-05-10 | 6/9/2024:#Update - Site type change - Switching to site type 3 _x000D_5/9/2024:#Update - Site type change - Switching to site type 3 _x000D_4/9/2024:#Update - Site type change - Switching to site type 3 _x000D_3/9/2024:#Update - Site type change - Switching to site type 3 _x000D_2/9/2024:#Update - Site type change - Switching to site type 3 _x000D_29/8/2024:#Update - Site type change - Switching to site type 3 _x000D_28/8/2024:#Update - Site type change - Switching to site type 3 _x000D_27/8/2024:#Update - Site type change - Switching to site type 3 _x000D_22/8/2024:#Update - Site type change - Switching to site type 3 _x000D_21/8/2024:#Update - Site type change - Switching to site type 3 _x000D_20/8/2024:#Update - Site type change - Switching to site type 3 _x000D_19/8/2024:#Update - Site type change - Switching to site type 3 _x000D_19/8/2024:01450046 _x000D_16/8/2024:#Update - Site type change - Switching to site type 3 _x000D_15/8/2024:#Update - Site type change - Switching to site type 3 _x000D_14/8/2024:#Update - Site type change - Switching to site type 3 _x000D_13/8/2024:#Update - Site type change - Switching to site type 3 _x000D_12/8/2024:#Update - Site type change - Switching to site type 3 _x000D_9/8/2024:#Update - Site type change - Switching to site type 3 _x000D_8/8/2024:05/07/2024 _x000D_6/8/2024:05/07/2024 _x000D_5/8/2024:05/07/2024 _x000D_2/8/2024:05/07/2024 _x000D_1/8/2024:05/07/2024 _x000D_31/7/2024:05/07/2024 _x000D_31/7/2024:05/07/2024 _x000D_30/7/2024:#Update - Site type change - Switching to site type 3 _x000D_29/7/2024:#Update - Site type change - Switching to site type 3 _x000D_29/7/2024:01450046 _x000D_26/7/2024:01450046 _x000D_24/7/2024:#Update - Site type change - Switching to site type 3 _x000D_23/7/2024:#Update - Site type change - Switching to site type 3 _x000D_22/7/2024:#Update - Site type change - Switching to site type 3 _x000D_22/7/2024:#Update - Site type change - Switching to site type 3 _x000D_27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_12/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_10/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_7/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 9/9/2024:#Update - Site type change - Switching to site type 3 _x000D_6/9/2024:#Update - Site type change - Switching to site type 3 _x000D_5/9/2024:#Update - Site type change - Switching to site type 3 _x000D_4/9/2024:#Update - Site type change - Switching to site type 3 _x000D_3/9/2024:#Update - Site type change - Switching to site type 3 _x000D_2/9/2024:#Update - Site type change - Switching to site type 3 _x000D_29/8/2024:#Update - Site type change - Switching to site type 3 _x000D_28/8/2024:#Update - Site type change - Switching to site type 3 _x000D_27/8/2024:#Update - Site type change - Switching to site type 3 _x000D_22/8/2024:#Update - Site type change - Switching to site type 3 _x000D_21/8/2024:#Update - Site type change - Switching to site type 3 _x000D_20/8/2024:#Update - Site type change - Switching to site type 3 _x000D_19/8/2024:#Update - Site type change - Switching to site type 3 _x000D_19/8/2024:01450046 _x000D_16/8/2024:#Update - Site type change - Switching to site type 3 _x000D_15/8/2024:#Update - Site type change - Switching to site type 3 _x000D_14/8/2024:#Update - Site type change - Switching to site type 3 _x000D_13/8/2024:#Update - Site type change - Switching to site type 3 _x000D_12/8/2024:#Update - Site type change - Switching to site type 3 _x000D_9/8/2024:#Update - Site type change - Switching to site type 3 _x000D_8/8/2024:05/07/2024 _x000D_6/8/2024:05/07/2024 _x000D_5/8/2024:05/07/2024 _x000D_2/8/2024:05/07/2024 _x000D_1/8/2024:05/07/2024 _x000D_31/7/2024:05/07/2024 _x000D_31/7/2024:05/07/2024 _x000D_30/7/2024:#Update - Site type change - Switching to site type 3 _x000D_29/7/2024:#Update - Site type change - Switching to site type 3 _x000D_29/7/2024:01450046 _x000D_26/7/2024:01450046 _x000D_24/7/2024:#Update - Site type change - Switching to site type 3 _x000D_23/7/2024:#Update - Site type change - Switching to site type 3 _x000D_22/7/2024:#Update - Site type change - Switching to site type 3 _x000D_22/7/2024:#Update - Site type change - Switching to site type 3 _x000D_27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_12/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_10/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_7/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 0 | #Update - Site type change - Switching to site type 3 | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2368365 | 30015963 | 2.Commissioning | AM |  |  |  |  | 0 |  |  |  | 2024-07-25 | [7 empty] | 0
700 | 461423 | 3140 | Batch 5 Jul24 | Type 1 | SOGEA | Barkers Of Bridlington | Bridlington | YO15 2DX |  | 27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015588 | 30016693 | 2.Commissioning |  |  | 2024-06-24 | 2024-06-24 | 2024-06-24 | TRUE |  |  |  | 2024-07-19 | [7 empty] | 0
701 | 652151 | 3141 | Batch 5 Jul24 | Type 1 | FTTP | Thriftys Nisalocal | Preston | PR2 1LQ |  | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:Your order has been delayed. The appointment has been delayed due to Landlord permission required. Please check with end user and reappoint the order if still required. _x000D_25/6/2024:Supplier Delay: KCI-3 (Order Completed) Delayed in Processing. _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:Your order has been delayed. The appointment has been delayed due to Landlord permission required. Please check with end user and reappoint the order if still required. _x000D_25/6/2024:Supplier Delay: KCI-3 (Order Completed) Delayed in Processing. _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366029 | 30016790 | 2.Commissioning |  |  | 2024-06-24 | 2024-06-24 | 2024-06-24 | TRUE |  |  |  | 2024-07-29 | [7 empty] | 0
702 | 458858 | 3142 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Spar | LONDONDERRY | BT48 0EH |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:11 _x000D_26/7/2024:22/07/2024 10:11 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:11 _x000D_26/7/2024:22/07/2024 10:11 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2366190 | 30016973 | 1.Provisioning | AM |  | 2024-06-24 | 2024-09-06 |  | 0 | [11 empty] | 0
703 | 484272 | 3143 | Batch 5 Jul24 | Type 1 | SOGEA | Nisa Local Little Dawley | Telford | TF4 3HA |  | 27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015589 | 30017024 | 2.Commissioning |  |  | 2024-06-24 | 2024-06-24 | 2024-06-24 | TRUE |  |  |  | 2024-07-30 | [7 empty] | 0
704 | 629981 | 3146 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Your Local | Leicester | LE5 0EG |  | 6/9/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_5/9/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_4/9/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_3/9/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_2/9/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_29/8/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_28/8/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_27/8/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_22/8/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_21/8/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_20/8/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_19/8/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_19/8/2024:01450001 _x000D_16/8/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_15/8/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_14/8/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_13/8/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_12/8/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_9/8/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_8/8/2024:02/07/2024 _x000D_6/8/2024:02/07/2024 _x000D_5/8/2024:02/07/2024 _x000D_2/8/2024:02/07/2024 _x000D_1/8/2024:02/07/2024 _x000D_31/7/2024:02/07/2024 _x000D_31/7/2024:02/07/2024 _x000D_30/7/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_29/7/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_29/7/2024:01450001 _x000D_26/7/2024:01450001 _x000D_24/7/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_23/7/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_22/7/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_22/7/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_19/7/2024:#Update - Retailer has confirmed new appointment date of 15/07. _x000D_18/7/2024:#Update - Retailer has confirmed new appointment date of 15/07. _x000D_17/7/2024:#Update - Retailer has confirmed new appointment date of 15/07. _x000D_16/7/2024:#Update - Retailer has confirmed new appointment date of 15/07. _x000D_15/7/2024:#Update - Retailer has confirmed new appointment date of 15/07. _x000D_12/7/2024:#Update - Retailer has confirmed new appointment date of 15/07. _x000D_11/7/2024:#Update - Retailer has confirmed new appointment date of 15/07. _x000D_10/7/2024:#Update - Retailer has confirmed new appointment date of 15/07. _x000D_9/7/2024:#Update - Retailer has confirmed new appointment date of 15/07. _x000D_4/7/2024:#Update - Retailer has confirmed new appointment date of 15/07. _x000D_3/7/2024:#Update - Retailer has confirmed new appointment date of 15/07. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Retailer has confirmed new appointment date of 15/07. _x000D_27/6/2024:#Update - Retailer has confirmed new appointment date of 15/07. _x000D_25/6/2024:#Update - Retailer has confirmed new appointment date of 15/07. _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_6/9/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_5/9/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_4/9/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_3/9/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_2/9/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_29/8/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_28/8/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_27/8/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_22/8/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_21/8/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_20/8/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_19/8/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_19/8/2024:01450001 _x000D_16/8/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_15/8/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_14/8/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_13/8/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_12/8/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_9/8/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_8/8/2024:02/07/2024 _x000D_6/8/2024:02/07/2024 _x000D_5/8/2024:02/07/2024 _x000D_2/8/2024:02/07/2024 _x000D_1/8/2024:02/07/2024 _x000D_31/7/2024:02/07/2024 _x000D_31/7/2024:02/07/2024 _x000D_30/7/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_29/7/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_29/7/2024:01450001 _x000D_26/7/2024:01450001 _x000D_24/7/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_23/7/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_22/7/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_22/7/2024:#Update - Pushed out 29/07 whilst we wait for engineer feedback _x000D_19/7/2024:#Update - Retailer has confirmed new appointment date of 15/07. _x000D_18/7/2024:#Update - Retailer has confirmed new appointment date of 15/07. _x000D_17/7/2024:#Update - Retailer has confirmed new appointment date of 15/07. _x000D_16/7/2024:#Update - Retailer has confirmed new appointment date of 15/07. _x000D_15/7/2024:#Update - Retailer has confirmed new appointment date of 15/07. _x000D_12/7/2024:#Update - Retailer has confirmed new appointment date of 15/07. _x000D_11/7/2024:#Update - Retailer has confirmed new appointment date of 15/07. _x000D_10/7/2024:#Update - Retailer has confirmed new appointment date of 15/07. _x000D_9/7/2024:#Update - Retailer has confirmed new appointment date of 15/07. _x000D_4/7/2024:#Update - Retailer has confirmed new appointment date of 15/07. _x000D_3/7/2024:#Update - Retailer has confirmed new appointment date of 15/07. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Retailer has confirmed new appointment date of 15/07. _x000D_27/6/2024:#Update - Retailer has confirmed new appointment date of 15/07. _x000D_25/6/2024:#Update - Retailer has confirmed new appointment date of 15/07. _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | #Update - Pushed out 29/07 whilst we wait for engineer feedback | 2024-06-07 |  |  |  |  | VFS1015586 | 30016699 | 1.Provisioning | AM |  | 2024-06-24 | 2024-08-30 |  | 0 | [11 empty] | 0
705 | 669679 | 3149 | Batch 5 Jul24 | Type 1 | SOGEA | Spar Rhossdu Road | WREXHAM | LL11 2NW |  | 27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015587 | 30016656 | 2.Commissioning |  |  | 2024-06-24 | 2024-06-24 | 2024-06-24 | TRUE |  |  |  | 2024-07-30 | [7 empty] | 0
706 | 108494 | 3152 | Batch 5 Jul24 | Type 1 | SOGEA | Nisa Local | PETERBOROUGH | PE7 1XU |  | 27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015585 | 30016853 | 2.Commissioning |  |  | 2024-06-24 | 2024-06-24 | 2024-06-24 | TRUE |  |  |  | 2024-07-17 | [7 empty] | 0
707 | 484929 | 3153 | Batch 5 Jul24 | Type 1 | FTTP | Nisa Local Pye Green Road | Cannock | WS11 5RP |  | 27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015485 | 30016900 | 2.Commissioning |  |  | 2024-06-24 | 2024-06-24 | 2024-06-24 | TRUE |  |  |  | 2024-07-18 | [7 empty] | 0
708 | 637400 | 3160 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Premier Rams Convenience Store | PRESTON | PR1 4SY |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:#Update - Retailer confirmed 23.08 re appointment, _x000D_22/8/2024:#Update - Retailer confirmed 23.08 re appointment, _x000D_21/8/2024:#Update - Retailer confirmed 23.08 re appointment, _x000D_20/8/2024:#Update - Retailer confirmed 23.08 re appointment, _x000D_19/8/2024:#Update - Retailer confirmed 23.08 re appointment, _x000D_19/8/2024:01450345 _x000D_16/8/2024:#Update - Retailer confirmed 23.08 re appointment, _x000D_15/8/2024:#Update - Retailer confirmed 23.08 re appointment, _x000D_14/8/2024:#Update - Retailer confirmed 23.08 re appointment, _x000D_13/8/2024:#Update - Retailer confirmed 23.08 re appointment, _x000D_12/8/2024:#Update - Retailer confirmed 23.08 re appointment, _x000D_9/8/2024:#Update - Retailer confirmed 23.08 re appointment, _x000D_8/8/2024:25/06/2024 _x000D_6/8/2024:25/06/2024 _x000D_5/8/2024:25/06/2024 _x000D_2/8/2024:25/06/2024 _x000D_1/8/2024:25/06/2024 _x000D_31/7/2024:25/06/2024 _x000D_31/7/2024:25/06/2024 _x000D_30/7/2024:#Update - Retailer confirmed 23.08 re appointment, _x000D_29/7/2024:#Update - Retailer confirmed 23.08 re appointment, _x000D_29/7/2024:01450345 _x000D_26/7/2024:01450345 _x000D_24/7/2024:#Update - Retailer confirmed 23.08 re appointment, _x000D_23/7/2024:#Update - Retailer confirmed 23.08 re appointment, _x000D_22/7/2024:#Update - Retailer confirmed 23.08 re appointment, _x000D_22/7/2024:#Update - Retailer confirmed 23.08 re appointment, _x000D_4/7/2024:#Update - Allwyn has requested for this site to be changed from a site type 1 to a site type 3. _x000D_3/7/2024:#Update - The retailer advised that he would like to discuss his needs regarding the installation. A complex solution is required which would involve 2 engineers for 4 hours work. Parts of the shop will be closed off from the public whilst overhead work carried out and the customer doesn't want any disruption. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - The retailer advised that he would like to discuss his needs regarding the installation. A complex solution is required which would involve 2 engineers for 4 hours work. Parts of the shop will be closed off from the public whilst overhead work carried out and the customer doesn't want any disruption. _x000D_27/6/2024:#Update - The retailer advised that he would like to discuss his needs regarding the installation. A complex solution is required which would involve 2 engineers for 4 hours work. Parts of the shop will be closed off from the public whilst overhead work carried out and the customer doesn't want any disruption. _x000D_25/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_24/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:#Update - Retailer confirmed 23.08 re appointment, _x000D_22/8/2024:#Update - Retailer confirmed 23.08 re appointment, _x000D_21/8/2024:#Update - Retailer confirmed 23.08 re appointment, _x000D_20/8/2024:#Update - Retailer confirmed 23.08 re appointment, _x000D_19/8/2024:#Update - Retailer confirmed 23.08 re appointment, _x000D_19/8/2024:01450345 _x000D_16/8/2024:#Update - Retailer confirmed 23.08 re appointment, _x000D_15/8/2024:#Update - Retailer confirmed 23.08 re appointment, _x000D_14/8/2024:#Update - Retailer confirmed 23.08 re appointment, _x000D_13/8/2024:#Update - Retailer confirmed 23.08 re appointment, _x000D_12/8/2024:#Update - Retailer confirmed 23.08 re appointment, _x000D_9/8/2024:#Update - Retailer confirmed 23.08 re appointment, _x000D_8/8/2024:25/06/2024 _x000D_6/8/2024:25/06/2024 _x000D_5/8/2024:25/06/2024 _x000D_2/8/2024:25/06/2024 _x000D_1/8/2024:25/06/2024 _x000D_31/7/2024:25/06/2024 _x000D_31/7/2024:25/06/2024 _x000D_30/7/2024:#Update - Retailer confirmed 23.08 re appointment, _x000D_29/7/2024:#Update - Retailer confirmed 23.08 re appointment, _x000D_29/7/2024:01450345 _x000D_26/7/2024:01450345 _x000D_24/7/2024:#Update - Retailer confirmed 23.08 re appointment, _x000D_23/7/2024:#Update - Retailer confirmed 23.08 re appointment, _x000D_22/7/2024:#Update - Retailer confirmed 23.08 re appointment, _x000D_22/7/2024:#Update - Retailer confirmed 23.08 re appointment, _x000D_4/7/2024:#Update - Allwyn has requested for this site to be changed from a site type 1 to a site type 3. _x000D_3/7/2024:#Update - The retailer advised that he would like to discuss his needs regarding the installation. A complex solution is required which would involve 2 engineers for 4 hours work. Parts of the shop will be closed off from the public whilst overhead work carried out and the customer doesn't want any disruption. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - The retailer advised that he would like to discuss his needs regarding the installation. A complex solution is required which would involve 2 engineers for 4 hours work. Parts of the shop will be closed off from the public whilst overhead work carried out and the customer doesn't want any disruption. _x000D_27/6/2024:#Update - The retailer advised that he would like to discuss his needs regarding the installation. A complex solution is required which would involve 2 engineers for 4 hours work. Parts of the shop will be closed off from the public whilst overhead work carried out and the customer doesn't want any disruption. _x000D_25/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_24/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | 0 | 2024-06-07 |  |  |  |  | VFS1015583 | 30016836 | 2.Commissioning | AM |  | 2024-06-24 | 2024-08-23 |  | 0 | [11 empty] | 0
709 | 633205 | 3161 | Batch 5 Jul24 | Type 3 | SOGEA | Abhinay Express | Leicester | LE4 6EL |  | 6/9/2024:#Update - Allwyn has requested for this site to be changed from a site type 1 to a site type 3. _x000D_5/9/2024:#Update - Allwyn has requested for this site to be changed from a site type 1 to a site type 3. _x000D_4/9/2024:#Update - Allwyn has requested for this site to be changed from a site type 1 to a site type 3. _x000D_27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn has requested for this site to be changed from a site type 1 to a site type 3. _x000D_6/9/2024:#Update - Allwyn has requested for this site to be changed from a site type 1 to a site type 3. _x000D_5/9/2024:#Update - Allwyn has requested for this site to be changed from a site type 1 to a site type 3. _x000D_4/9/2024:#Update - Allwyn has requested for this site to be changed from a site type 1 to a site type 3. _x000D_27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | #Update - Allwyn has requested for this site to be changed from a site type 1 to a site type 3. | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015482 | 30016877 | 2.Commissioning | [5 empty] | Not Applicable |  |  |  | 2024-07-26 | [7 empty] | 0
710 | 465624 | 3162 | Batch 5 Jul24 | Type 1 | FTTP | Harrys | LARNE | BT40 1SD |  | 27/6/2024:#Update - Order Complete _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 27/6/2024:#Update - Order Complete _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366187 | 30016732 | 6.Failed router install |  |  | 2024-06-24 | 2024-06-24 | 2024-06-24 | TRUE |  |  |  | 2024-07-26 |  |  |  | 2024-07-26 | 23A004952994 |  | 2024-07-29 | 1
711 | 485919 | 3164 | Batch 5 Jul24 | Type 1 | FTTP | S News | Bulwell | NG6 8EW |  | 27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 5.CSL | VFP2366184 | 30016738 | 6.Failed router install |  |  | 2024-06-24 | 2024-06-24 | 2024-06-24 | TRUE |  |  |  | 2024-07-18 |  |  |  | 2024-07-18 | 23A004946005 |  | 2024-07-19 | 1
712 | 458668 | 3166 | Batch 5 Jul24 | Type 1 | FTTP | Eurospar | ENNISKILLEN | BT92 0JB |  | 27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366185 | 30016907 | 6.Failed router install |  |  | 2024-06-24 | 2024-06-24 | 2024-06-24 | TRUE |  |  |  | 2024-07-30 |  |  |  | 2024-07-30 | 23A004952998 |  | 2024-07-31 | 1
713 | 665040 | 3169 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | King Square Post Office & Stores | BARRY | CF63 4HL |  | 6/9/2024:#Update - The engineer has advised that the store does not have fire clamps in the false ceiling and it therefore does not comply with fire regulations. Once the retailer has installed fire clamps then the engineer can revisit and run the cable safely. If the retailer is not able to, this will have to move to a site type 3. _x000D_5/9/2024:#Update - The engineer has advised that the store does not have fire clamps in the false ceiling and it therefore does not comply with fire regulations. Once the retailer has installed fire clamps then the engineer can revisit and run the cable safely. If the retailer is not able to, this will have to move to a site type 3. _x000D_4/9/2024:#Update - The engineer has advised that the store does not have fire clamps in the false ceiling and it therefore does not comply with fire regulations. Once the retailer has installed fire clamps then the engineer can revisit and run the cable safely. If the retailer is not able to, this will have to move to a site type 3. _x000D_3/9/2024:#Update - The engineer has advised that the store does not have fire clamps in the false ceiling and it therefore does not comply with fire regulations. Once the retailer has installed fire clamps then the engineer can revisit and run the cable safely. If the retailer is not able to, this will have to move to a site type 3. _x000D_2/9/2024:#Update - The engineer has advised that the store does not have fire clamps in the false ceiling and it therefore does not comply with fire regulations. Once the retailer has installed fire clamps then the engineer can revisit and run the cable safely. If the retailer is not able to, this will have to move to a site type 3. _x000D_29/8/2024:#Update - The engineer has advised that the store does not have fire clamps in the false ceiling and it therefore does not comply with fire regulations. Once the retailer has installed fire clamps then the engineer can revisit and run the cable safely. If the retailer is not able to, this will have to move to a site type 3. _x000D_28/8/2024:#Update - The engineer has advised that the store does not have fire clamps in the false ceiling and it therefore does not comply with fire regulations. Once the retailer has installed fire clamps then the engineer can revisit and run the cable safely. If the retailer is not able to, this will have to move to a site type 3. _x000D_27/8/2024:#Update - The engineer has advised that the store does not have fire clamps in the false ceiling and it therefore does not comply with fire regulations. Once the retailer has installed fire clamps then the engineer can revisit and run the cable safely. If the retailer is not able to, this will have to move to a site type 3. _x000D_22/8/2024:#Update - The engineer has advised that the store does not have fire clamps in the false ceiling and it therefore does not comply with fire regulations. Once the retailer has installed fire clamps then the engineer can revisit and run the cable safely. If the retailer is not able to, this will have to move to a site type 3. _x000D_21/8/2024:#Update - The engineer has advised that the store does not have fire clamps in the false ceiling and it therefore does not comply with fire regulations. Once the retailer has installed fire clamps then the engineer can revisit and run the cable safely. If the retailer is not able to, this will have to move to a site type 3. _x000D_20/8/2024:#Update - The engineer has advised that the store does not have fire clamps in the false ceiling and it therefore does not comply with fire regulations. Once the retailer has installed fire clamps then the engineer can revisit and run the cable safely. If the retailer is not able to, this will have to move to a site type 3. _x000D_19/8/2024:#Update - The engineer has advised that the store does not have fire clamps in the false ceiling and it therefore does not comply with fire regulations. Once the retailer has installed fire clamps then the engineer can revisit and run the cable safely. If the retailer is not able to, this will have to move to a site type 3. _x000D_19/8/2024:01450659 _x000D_16/8/2024:#Update - The engineer has advised that the store does not have fire clamps in the false ceiling and it therefore does not comply with fire regulations. Once the retailer has installed fire clamps then the engineer can revisit and run the cable safely. If the retailer is not able to, this will have to move to a site type 3. _x000D_15/8/2024:#Update - The engineer has advised that the store does not have fire clamps in the false ceiling and it therefore does not comply with fire regulations. Once the retailer has installed fire clamps then the engineer can revisit and run the cable safely. If the retailer is not able to, this will have to move to a site type 3. _x000D_14/8/2024:#Update - The engineer has advised that the store does not have fire clamps in the false ceiling and it therefore does not comply with fire regulations. Once the retailer has installed fire clamps then the engineer can revisit and run the cable safely. If the retailer is not able to, this will have to move to a site type 3. _x000D_13/8/2024:#Update - The engineer has advised that the store does not have fire clamps in the false ceiling and it therefore does not comply with fire regulations. Once the retailer has installed fire clamps then the engineer can revisit and run the cable safely. If the retailer is not able to, this will have to move to a site type 3. _x000D_12/8/2024:#Update - The engineer has advised that the store does not have fire clamps in the false ceiling and it therefore does not comply with fire regulations. Once the retailer has installed fire clamps then the engineer can revisit and run the cable safely. If the retailer is not able to, this will have to move to a site type 3. _x000D_9/8/2024:#Update - The engineer has advised that the store does not have fire clamps in the false ceiling and it therefore does not comply with fire regulations. Once the retailer has installed fire clamps then the engineer can revisit and run the cable safely. If the retailer is not able to, this will have to move to a site type 3. _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update - The engineer has advised that the store does not have fire clamps in the false ceiling and it therefore does not comply with fire regulations. Once the retailer has installed fire clamps then the engineer can revisit and run the cable safely. If the retailer is not able to, this will have to move to a site type 3. _x000D_29/7/2024:#Update - The engineer has advised that the store does not have fire clamps in the false ceiling and it therefore does not comply with fire regulations. Once the retailer has installed fire clamps then the engineer can revisit and run the cable safely. If the retailer is not able to, this will have to move to a site type 3. _x000D_29/7/2024:01450659 _x000D_26/7/2024:01450659 _x000D_24/7/2024:#Update - CSL are awaiting for more information on how to progress at this site and will update as soon as this becomes available. _x000D_23/7/2024:#Update - CSL are awaiting for more information on how to progress at this site and will update as soon as this becomes available. _x000D_22/7/2024:#Update - CSL are awaiting for more information on how to progress at this site and will update as soon as this becomes available. _x000D_22/7/2024:#Update - CSL are awaiting for more information on how to progress at this site and will update as soon as this becomes available. _x000D_19/7/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_18/7/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_17/7/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_16/7/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_15/7/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_12/7/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_11/7/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_10/7/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_9/7/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_4/7/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_3/7/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_27/6/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_25/6/2024:Supplier Missed Appointment - exceptional circumstances. _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:#Update - The engineer has advised that the store does not have fire clamps in the false ceiling and it therefore does not comply with fire regulations. Once the retailer has installed fire clamps then the engineer can revisit and run the cable safely. If the retailer is not able to, this will have to move to a site type 3. _x000D_6/9/2024:#Update - The engineer has advised that the store does not have fire clamps in the false ceiling and it therefore does not comply with fire regulations. Once the retailer has installed fire clamps then the engineer can revisit and run the cable safely. If the retailer is not able to, this will have to move to a site type 3. _x000D_5/9/2024:#Update - The engineer has advised that the store does not have fire clamps in the false ceiling and it therefore does not comply with fire regulations. Once the retailer has installed fire clamps then the engineer can revisit and run the cable safely. If the retailer is not able to, this will have to move to a site type 3. _x000D_4/9/2024:#Update - The engineer has advised that the store does not have fire clamps in the false ceiling and it therefore does not comply with fire regulations. Once the retailer has installed fire clamps then the engineer can revisit and run the cable safely. If the retailer is not able to, this will have to move to a site type 3. _x000D_3/9/2024:#Update - The engineer has advised that the store does not have fire clamps in the false ceiling and it therefore does not comply with fire regulations. Once the retailer has installed fire clamps then the engineer can revisit and run the cable safely. If the retailer is not able to, this will have to move to a site type 3. _x000D_2/9/2024:#Update - The engineer has advised that the store does not have fire clamps in the false ceiling and it therefore does not comply with fire regulations. Once the retailer has installed fire clamps then the engineer can revisit and run the cable safely. If the retailer is not able to, this will have to move to a site type 3. _x000D_29/8/2024:#Update - The engineer has advised that the store does not have fire clamps in the false ceiling and it therefore does not comply with fire regulations. Once the retailer has installed fire clamps then the engineer can revisit and run the cable safely. If the retailer is not able to, this will have to move to a site type 3. _x000D_28/8/2024:#Update - The engineer has advised that the store does not have fire clamps in the false ceiling and it therefore does not comply with fire regulations. Once the retailer has installed fire clamps then the engineer can revisit and run the cable safely. If the retailer is not able to, this will have to move to a site type 3. _x000D_27/8/2024:#Update - The engineer has advised that the store does not have fire clamps in the false ceiling and it therefore does not comply with fire regulations. Once the retailer has installed fire clamps then the engineer can revisit and run the cable safely. If the retailer is not able to, this will have to move to a site type 3. _x000D_22/8/2024:#Update - The engineer has advised that the store does not have fire clamps in the false ceiling and it therefore does not comply with fire regulations. Once the retailer has installed fire clamps then the engineer can revisit and run the cable safely. If the retailer is not able to, this will have to move to a site type 3. _x000D_21/8/2024:#Update - The engineer has advised that the store does not have fire clamps in the false ceiling and it therefore does not comply with fire regulations. Once the retailer has installed fire clamps then the engineer can revisit and run the cable safely. If the retailer is not able to, this will have to move to a site type 3. _x000D_20/8/2024:#Update - The engineer has advised that the store does not have fire clamps in the false ceiling and it therefore does not comply with fire regulations. Once the retailer has installed fire clamps then the engineer can revisit and run the cable safely. If the retailer is not able to, this will have to move to a site type 3. _x000D_19/8/2024:#Update - The engineer has advised that the store does not have fire clamps in the false ceiling and it therefore does not comply with fire regulations. Once the retailer has installed fire clamps then the engineer can revisit and run the cable safely. If the retailer is not able to, this will have to move to a site type 3. _x000D_19/8/2024:01450659 _x000D_16/8/2024:#Update - The engineer has advised that the store does not have fire clamps in the false ceiling and it therefore does not comply with fire regulations. Once the retailer has installed fire clamps then the engineer can revisit and run the cable safely. If the retailer is not able to, this will have to move to a site type 3. _x000D_15/8/2024:#Update - The engineer has advised that the store does not have fire clamps in the false ceiling and it therefore does not comply with fire regulations. Once the retailer has installed fire clamps then the engineer can revisit and run the cable safely. If the retailer is not able to, this will have to move to a site type 3. _x000D_14/8/2024:#Update - The engineer has advised that the store does not have fire clamps in the false ceiling and it therefore does not comply with fire regulations. Once the retailer has installed fire clamps then the engineer can revisit and run the cable safely. If the retailer is not able to, this will have to move to a site type 3. _x000D_13/8/2024:#Update - The engineer has advised that the store does not have fire clamps in the false ceiling and it therefore does not comply with fire regulations. Once the retailer has installed fire clamps then the engineer can revisit and run the cable safely. If the retailer is not able to, this will have to move to a site type 3. _x000D_12/8/2024:#Update - The engineer has advised that the store does not have fire clamps in the false ceiling and it therefore does not comply with fire regulations. Once the retailer has installed fire clamps then the engineer can revisit and run the cable safely. If the retailer is not able to, this will have to move to a site type 3. _x000D_9/8/2024:#Update - The engineer has advised that the store does not have fire clamps in the false ceiling and it therefore does not comply with fire regulations. Once the retailer has installed fire clamps then the engineer can revisit and run the cable safely. If the retailer is not able to, this will have to move to a site type 3. _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update - The engineer has advised that the store does not have fire clamps in the false ceiling and it therefore does not comply with fire regulations. Once the retailer has installed fire clamps then the engineer can revisit and run the cable safely. If the retailer is not able to, this will have to move to a site type 3. _x000D_29/7/2024:#Update - The engineer has advised that the store does not have fire clamps in the false ceiling and it therefore does not comply with fire regulations. Once the retailer has installed fire clamps then the engineer can revisit and run the cable safely. If the retailer is not able to, this will have to move to a site type 3. _x000D_29/7/2024:01450659 _x000D_26/7/2024:01450659 _x000D_24/7/2024:#Update - CSL are awaiting for more information on how to progress at this site and will update as soon as this becomes available. _x000D_23/7/2024:#Update - CSL are awaiting for more information on how to progress at this site and will update as soon as this becomes available. _x000D_22/7/2024:#Update - CSL are awaiting for more information on how to progress at this site and will update as soon as this becomes available. _x000D_22/7/2024:#Update - CSL are awaiting for more information on how to progress at this site and will update as soon as this becomes available. _x000D_19/7/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_18/7/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_17/7/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_16/7/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_15/7/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_12/7/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_11/7/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_10/7/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_9/7/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_4/7/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_3/7/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_27/6/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_25/6/2024:Supplier Missed Appointment - exceptional circumstances. _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | #Update - The engineer has advised that the store does not have fire clamps in the false ceiling and it therefore does not comply with fire regulations. Once the retailer has installed fire clamps then the engineer can revisit and run the cable safely. If the retailer is not able to, this will have to move to a site type 3. | 2024-06-07 |  |  |  |  | VFP2366181 | 30016678 | 1.Provisioning | AM |  | 2024-06-24 | 2024-06-24 |  | 0 | [11 empty] | 0
714 | 655820 | 3170 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Abhinay Express | Leicester | LE5 4DG |  | 6/9/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_5/9/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_4/9/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_3/9/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_2/9/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_29/8/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_28/8/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_27/8/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_22/8/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_21/8/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_20/8/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_19/8/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_19/8/2024:01450991 _x000D_16/8/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_15/8/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_14/8/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_13/8/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_12/8/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_9/8/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_8/8/2024:26/06/2024 _x000D_6/8/2024:26/06/2024 _x000D_5/8/2024:26/06/2024 _x000D_2/8/2024:26/06/2024 _x000D_1/8/2024:26/06/2024 _x000D_31/7/2024:26/06/2024 _x000D_31/7/2024:26/06/2024 _x000D_30/7/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_29/7/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_29/7/2024:01450991 _x000D_26/7/2024:01450991 _x000D_24/7/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_23/7/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_22/7/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_22/7/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:Update: Order Completed by Supplier _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_6/9/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_5/9/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_4/9/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_3/9/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_2/9/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_29/8/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_28/8/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_27/8/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_22/8/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_21/8/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_20/8/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_19/8/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_19/8/2024:01450991 _x000D_16/8/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_15/8/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_14/8/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_13/8/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_12/8/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_9/8/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_8/8/2024:26/06/2024 _x000D_6/8/2024:26/06/2024 _x000D_5/8/2024:26/06/2024 _x000D_2/8/2024:26/06/2024 _x000D_1/8/2024:26/06/2024 _x000D_31/7/2024:26/06/2024 _x000D_31/7/2024:26/06/2024 _x000D_30/7/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_29/7/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_29/7/2024:01450991 _x000D_26/7/2024:01450991 _x000D_24/7/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_23/7/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_22/7/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_22/7/2024:#Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed _x000D_27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:Update: Order Completed by Supplier _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | #Update Failed install, unable to access the network due to vehicle parked blocking access point. Unable to park within 200m of shop. Busy area. Tried multiple streets and on multiple occasions. Engineer will need to return at a quieter time. OR will contact EU to get this reappointed | 2024-06-07 |  |  |  |  | VFP2366179 | 30017009 | 1.Provisioning | AM |  | 2024-06-24 | 2024-09-05 |  | 0 | [11 empty] | 0
715 | 101866 | 3172 | Batch 5 Jul24 | Type 1 | SOGEA | Spar Sandylands | KENDAL | LA9 6EU |  | 27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015580 | 30016771 | 6.Failed router install |  |  | 2024-06-24 | 2024-06-24 | 2024-06-24 | TRUE |  |  |  | 2024-07-29 |  |  |  | 2024-07-29 | 242005008950 |  | 2024-07-30 | 1
716 | 657443 | 3173 | Batch 5 Jul24 | Type 1 | SOGEA | Scoop | Newtownabbey | BT37 9UH |  | 27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:Update: Order Completed by Supplier _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:Update: Order Completed by Supplier _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015483 | 30016999 | 2.Commissioning |  |  | 2024-06-24 | 2024-06-24 | 2024-06-24 | TRUE |  |  |  | 2024-07-26 | [7 empty] | 0
717 | 443790 | 3175 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | SPAR BUCKLEY | Buckley | CH7 2NJ |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:10 _x000D_26/7/2024:22/07/2024 10:10 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_18/7/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_17/7/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_16/7/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_15/7/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_12/7/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_11/7/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_10/7/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_9/7/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_4/7/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_3/7/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_27/6/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_25/6/2024:Delay on Engineer activities. Supplier will arrange new appointment _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_17/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_14/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_13/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_12/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:10 _x000D_26/7/2024:22/07/2024 10:10 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_18/7/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_17/7/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_16/7/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_15/7/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_12/7/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_11/7/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_10/7/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_9/7/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_4/7/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_3/7/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_27/6/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_25/6/2024:Delay on Engineer activities. Supplier will arrange new appointment _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_17/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_14/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_13/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_12/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2366178 | 30016917 | 1.Provisioning | AM |  | 2024-06-24 | 2024-09-06 |  | 0 | [11 empty] | 0
718 | 612189 | 3176 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Spar | St Columb | TR9 6QX |  | 16/8/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_15/8/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_14/8/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_13/8/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_12/8/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_9/8/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_8/8/2024:26/06/2024 _x000D_6/8/2024:26/06/2024 _x000D_5/8/2024:26/06/2024 _x000D_2/8/2024:26/06/2024 _x000D_1/8/2024:26/06/2024 _x000D_31/7/2024:26/06/2024 _x000D_31/7/2024:26/06/2024 _x000D_30/7/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_29/7/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_29/7/2024:01454873 _x000D_26/7/2024:01454873 _x000D_24/7/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_23/7/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_22/7/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_22/7/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect Product Please check with end user and reappoint the order if still required. _x000D_25/6/2024:Supplier Delay: KCI-3 (Order Completed) Delayed in Processing. _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:Supplier Delay: Delay encountered during automated test of new service _x000D_ | 16/8/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_15/8/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_14/8/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_13/8/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_12/8/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_9/8/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_8/8/2024:26/06/2024 _x000D_6/8/2024:26/06/2024 _x000D_5/8/2024:26/06/2024 _x000D_2/8/2024:26/06/2024 _x000D_1/8/2024:26/06/2024 _x000D_31/7/2024:26/06/2024 _x000D_31/7/2024:26/06/2024 _x000D_30/7/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_29/7/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_29/7/2024:01454873 _x000D_26/7/2024:01454873 _x000D_24/7/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_23/7/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_22/7/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_22/7/2024:#Update Supplier delay - Multiskilled engineer work is required. Our Suppliers have given us a review date of 02/07/2024. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect Product Please check with end user and reappoint the order if still required. _x000D_25/6/2024:Supplier Delay: KCI-3 (Order Completed) Delayed in Processing. _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:Supplier Delay: Delay encountered during automated test of new service _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1015578 | 30016817 | 2.Commissioning | AM |  | 2024-06-24 | 2024-08-12 | 2024-08-12 09:28 | 1 |  |  |  | 2024-09-04 | [7 empty] | 0
719 | 665747 | 3178 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Lord Lane Post Office | Manchester | M35 0QH |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:05 _x000D_26/7/2024:22/07/2024 10:05 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:05 _x000D_26/7/2024:22/07/2024 10:05 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2366177 | 30016737 | 1.Provisioning | AM |  | 2024-06-24 | 2024-09-06 |  | 0 | [11 empty] | 0
720 | 651860 | 3179 | Batch 5 Jul24 | Type 1 | SOGEA | Supervalu Barbican Newcastle | Newcastle | BT33 0LN |  | 27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:Order Completed _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015577 | 30016924 | 2.Commissioning |  |  | 2024-06-24 | 2024-06-24 | 2024-06-24 | TRUE |  |  |  | 2024-07-25 | [7 empty] | 0
721 | 450199 | 3185 | Batch 5 Jul24 | Type 1 | FTTP | Costcutter | WALLASEY | CH44 9DG |  | 27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015477 | 30016658 | 2.Commissioning |  |  | 2024-06-24 | 2024-06-24 | 2024-06-24 | TRUE |  |  |  | 2024-07-25 | [7 empty] | 0
722 | 631010 | 3187 | Batch 5 Jul24 | Type 1 | SOGEA | Premier Bell Dean Convenience Stor | Bradford | BD15 7YZ |  | 27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015478 | 30016874 | 2.Commissioning |  |  | 2024-06-24 | 2024-06-24 | 2024-06-24 | TRUE |  |  |  | 2024-07-20 | [7 empty] | 0
723 | 665120 | 3189 | Batch 5 Jul24 | Type 1 | FTTP | Londis | Merthyr Tydfil | CF48 3LT |  | 19/7/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_18/7/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_17/7/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_16/7/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_15/7/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_12/7/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_11/7/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_10/7/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_9/7/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_4/7/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_3/7/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_27/6/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_25/6/2024:End User Missed appointment. Action required _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 19/7/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_18/7/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_17/7/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_16/7/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_15/7/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_12/7/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_11/7/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_10/7/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_9/7/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_4/7/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_3/7/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_27/6/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_25/6/2024:End User Missed appointment. Action required _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366176 | 30016892 | 6.Failed router install |  |  | 2024-06-24 | 2024-06-24 | 2024-06-24 | TRUE |  |  |  | 2024-07-31 |  |  |  | 2024-09-02 | 239004929548 | 239004929548 | 2024-09-03 | 1
724 | 436273 | 3191 | Batch 5 Jul24 | Type 3 | SoGEA/Mobile | Premier Morrison Road Late Shop | PORT TALBOT | SA12 6TH |  | 6/9/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_5/9/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_4/9/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_3/9/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_2/9/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_29/8/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_28/8/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_27/8/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_22/8/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_21/8/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_20/8/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_19/8/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_19/8/2024:01450643 _x000D_16/8/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_15/8/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_14/8/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_13/8/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_12/8/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_9/8/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_8/8/2024:25/06/2024 _x000D_6/8/2024:25/06/2024 _x000D_5/8/2024:25/06/2024 _x000D_2/8/2024:25/06/2024 _x000D_1/8/2024:25/06/2024 _x000D_31/7/2024:25/06/2024 _x000D_31/7/2024:25/06/2024 _x000D_30/7/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_29/7/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_29/7/2024:01450643 _x000D_26/7/2024:01450643 _x000D_24/7/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_23/7/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_22/7/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_22/7/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect Address Please check with end user and reappoint the order if still required. _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_6/9/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_5/9/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_4/9/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_3/9/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_2/9/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_29/8/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_28/8/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_27/8/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_22/8/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_21/8/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_20/8/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_19/8/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_19/8/2024:01450643 _x000D_16/8/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_15/8/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_14/8/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_13/8/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_12/8/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_9/8/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_8/8/2024:25/06/2024 _x000D_6/8/2024:25/06/2024 _x000D_5/8/2024:25/06/2024 _x000D_2/8/2024:25/06/2024 _x000D_1/8/2024:25/06/2024 _x000D_31/7/2024:25/06/2024 _x000D_31/7/2024:25/06/2024 _x000D_30/7/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_29/7/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_29/7/2024:01450643 _x000D_26/7/2024:01450643 _x000D_24/7/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_23/7/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_22/7/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_22/7/2024:#Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect Address Please check with end user and reappoint the order if still required. _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | #Update - Installation requires OOH as cabling needs to run through false ceiling and under the floor. Openreach have advised there is no existing cable to work off of. | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015575 | 30016936 | 2.Commissioning | AM |  |  |  |  | 0 |  |  |  | 2024-08-21 | [7 empty] | 0
725 | 670360 | 3192 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | KILLYCOMAIN PO | Craigavon | BT63 5EF |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:21 _x000D_26/7/2024:22/07/2024 10:21 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Retailer requested 26th July AM appointment _x000D_18/7/2024:#Update - Retailer requested 26th July AM appointment _x000D_17/7/2024:#Update - Retailer requested 26th July AM appointment _x000D_16/7/2024:#Update - Retailer requested 26th July AM appointment _x000D_15/7/2024:#Update - Retailer requested 26th July AM appointment _x000D_12/7/2024:#Update - Retailer requested 26th July AM appointment _x000D_11/7/2024:#Update - Retailer requested 26th July AM appointment _x000D_10/7/2024:#Update - Re-appointed for 22.07 AM - Action for allwyn; Please confirm with retailer that this date is suitable. _x000D_9/7/2024:#Update - Re-appointed for 22.07 AM - Action for allwyn; Please confirm with retailer that this date is suitable. _x000D_4/7/2024:#Update - Re-appointed for 22.07 AM - Action for allwyn; Please confirm with retailer that this date is suitable. _x000D_3/7/2024:#Update - Re-appointed for 22.07 AM - Action for allwyn; Please confirm with retailer that this date is suitable. _x000D_2/7/2024:A4 (ECC) _x000D_1/7/2024:#Update - Re-appointed for 22.07 AM - Action for allwyn; Please confirm with retailer that this date is suitable. _x000D_27/6/2024:#Update - Re-appointed for 22.07 AM - Action for allwyn; Please confirm with retailer that this date is suitable. _x000D_25/6/2024:#Update - Re-appointed for 22.07 AM - Action for allwyn; Please confirm with retailer that this date is suitable. _x000D_24/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:21 _x000D_26/7/2024:22/07/2024 10:21 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Retailer requested 26th July AM appointment _x000D_18/7/2024:#Update - Retailer requested 26th July AM appointment _x000D_17/7/2024:#Update - Retailer requested 26th July AM appointment _x000D_16/7/2024:#Update - Retailer requested 26th July AM appointment _x000D_15/7/2024:#Update - Retailer requested 26th July AM appointment _x000D_12/7/2024:#Update - Retailer requested 26th July AM appointment _x000D_11/7/2024:#Update - Retailer requested 26th July AM appointment _x000D_10/7/2024:#Update - Re-appointed for 22.07 AM - Action for allwyn; Please confirm with retailer that this date is suitable. _x000D_9/7/2024:#Update - Re-appointed for 22.07 AM - Action for allwyn; Please confirm with retailer that this date is suitable. _x000D_4/7/2024:#Update - Re-appointed for 22.07 AM - Action for allwyn; Please confirm with retailer that this date is suitable. _x000D_3/7/2024:#Update - Re-appointed for 22.07 AM - Action for allwyn; Please confirm with retailer that this date is suitable. _x000D_2/7/2024:A4 (ECC) _x000D_1/7/2024:#Update - Re-appointed for 22.07 AM - Action for allwyn; Please confirm with retailer that this date is suitable. _x000D_27/6/2024:#Update - Re-appointed for 22.07 AM - Action for allwyn; Please confirm with retailer that this date is suitable. _x000D_25/6/2024:#Update - Re-appointed for 22.07 AM - Action for allwyn; Please confirm with retailer that this date is suitable. _x000D_24/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2366024 | 30016747 | 1.Provisioning | AM |  | 2024-06-24 | 2024-09-06 |  | 0 | [11 empty] | 0
726 | 486338 | 3194 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | SPAR BETTWS | NEWPORT | NP20 7TN |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:Update: Order Amended _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:Update: Order Amended _x000D_31/7/2024:Update: Order Amended _x000D_31/7/2024:37079 _x000D_30/7/2024:Update: Order Amended _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:25/07/2024 13:31 _x000D_26/7/2024:25/07/2024 13:31 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:Update: Order Amended _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:Update: Order Amended _x000D_31/7/2024:Update: Order Amended _x000D_31/7/2024:37079 _x000D_30/7/2024:Update: Order Amended _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:25/07/2024 13:31 _x000D_26/7/2024:25/07/2024 13:31 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | 0 | 2024-06-07 |  |  |  |  | VFP2366025 | 30016850 | 1.Provisioning | AM |  | 2024-06-24 | 2024-08-28 |  | 0 | [11 empty] | 0
727 | 627725 | 3197 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Raj Convenience Store | London | SW8 2JS |  | 6/9/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_5/9/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_4/9/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_3/9/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_2/9/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_29/8/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_28/8/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_27/8/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_22/8/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_21/8/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_20/8/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_19/8/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_19/8/2024:01449903 _x000D_16/8/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_15/8/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_14/8/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_13/8/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_12/8/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_9/8/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_8/8/2024:26/06/2024 _x000D_6/8/2024:26/06/2024 _x000D_5/8/2024:26/06/2024 _x000D_2/8/2024:26/06/2024 _x000D_1/8/2024:26/06/2024 _x000D_31/7/2024:26/06/2024 _x000D_31/7/2024:26/06/2024 _x000D_30/7/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_29/7/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_29/7/2024:01449903 _x000D_26/7/2024:01449903 _x000D_24/7/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_23/7/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_22/7/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_22/7/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_6/9/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_5/9/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_4/9/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_3/9/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_2/9/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_29/8/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_28/8/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_27/8/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_22/8/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_21/8/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_20/8/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_19/8/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_19/8/2024:01449903 _x000D_16/8/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_15/8/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_14/8/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_13/8/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_12/8/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_9/8/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_8/8/2024:26/06/2024 _x000D_6/8/2024:26/06/2024 _x000D_5/8/2024:26/06/2024 _x000D_2/8/2024:26/06/2024 _x000D_1/8/2024:26/06/2024 _x000D_31/7/2024:26/06/2024 _x000D_31/7/2024:26/06/2024 _x000D_30/7/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_29/7/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_29/7/2024:01449903 _x000D_26/7/2024:01449903 _x000D_24/7/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_23/7/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_22/7/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_22/7/2024:#Update - Order cancelled. looking into why and will re-raise if needed _x000D_27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | #Update - Order cancelled. looking into why and will re-raise if needed | 2024-06-07 |  |  |  |  | VFS1015476 | 30016673 | 1.Provisioning | AM |  | 2024-06-24 | 2024-09-16 |  | 0 | [11 empty] | 0
728 | 486297 | 3198 | Batch 5 Jul24 | Type 1 | SOGEA | SPAR TREHERBERT | TREORCHY | CF42 5NR |  | 19/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_18/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_17/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_16/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_15/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_12/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_11/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_10/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_9/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_4/7/2024:#Update - Allwyn have requested that the install date be pushed out as far as possible due to difficulties contacting the retailer - Reappointed for the 05/08 _x000D_3/7/2024:#Update - Allwyn have requested that the install date be pushed out as far as possible due to difficulties contacting the retailer - Reappointed for the 05/08 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Allwyn have requested that the install date be pushed out as far as possible due to difficulties contacting the retailer - Reappointed for the 05/08 _x000D_27/6/2024:#Update - Allwyn have requested that the install date be pushed out as far as possible due to difficulties contacting the retailer - Reappointed for the 05/08 _x000D_25/6/2024:#Update - Allwyn have requested that the install date be pushed out as far as possible due to difficulties contacting the retailer - Reappointed for the 05/08 _x000D_24/6/2024:#Update - Allwyn have requested that the install date be pushed out as far as possible due to difficulties contacting the retailer - Reappointed for the 05/08 _x000D_20/6/2024:#Update - Action for Allwyn - Installation has now been amended to 06/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 06/06 is a suitable date. _x000D_19/6/2024:#Update - Action for Allwyn - Installation has now been amended to 06/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 06/06 is a suitable date. _x000D_18/6/2024:#Update - Action for Allwyn - Installation has now been amended to 06/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 06/06 is a suitable date. _x000D_17/6/2024:#Update - Action for Allwyn - Installation has now been amended to 06/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 06/06 is a suitable date. _x000D_14/6/2024:#Update - Action for Allwyn - Installation has now been amended to 06/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 06/06 is a suitable date. _x000D_13/6/2024:#Update - Action for Allwyn - Installation has now been amended to 06/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 06/06 is a suitable date. _x000D_12/6/2024:#Update - Action for Allwyn - Installation has now been amended to 06/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 06/06 is a suitable date. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 19/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_18/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_17/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_16/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_15/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_12/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_11/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_10/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_9/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_4/7/2024:#Update - Allwyn have requested that the install date be pushed out as far as possible due to difficulties contacting the retailer - Reappointed for the 05/08 _x000D_3/7/2024:#Update - Allwyn have requested that the install date be pushed out as far as possible due to difficulties contacting the retailer - Reappointed for the 05/08 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Allwyn have requested that the install date be pushed out as far as possible due to difficulties contacting the retailer - Reappointed for the 05/08 _x000D_27/6/2024:#Update - Allwyn have requested that the install date be pushed out as far as possible due to difficulties contacting the retailer - Reappointed for the 05/08 _x000D_25/6/2024:#Update - Allwyn have requested that the install date be pushed out as far as possible due to difficulties contacting the retailer - Reappointed for the 05/08 _x000D_24/6/2024:#Update - Allwyn have requested that the install date be pushed out as far as possible due to difficulties contacting the retailer - Reappointed for the 05/08 _x000D_20/6/2024:#Update - Action for Allwyn - Installation has now been amended to 06/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 06/06 is a suitable date. _x000D_19/6/2024:#Update - Action for Allwyn - Installation has now been amended to 06/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 06/06 is a suitable date. _x000D_18/6/2024:#Update - Action for Allwyn - Installation has now been amended to 06/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 06/06 is a suitable date. _x000D_17/6/2024:#Update - Action for Allwyn - Installation has now been amended to 06/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 06/06 is a suitable date. _x000D_14/6/2024:#Update - Action for Allwyn - Installation has now been amended to 06/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 06/06 is a suitable date. _x000D_13/6/2024:#Update - Action for Allwyn - Installation has now been amended to 06/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 06/06 is a suitable date. _x000D_12/6/2024:#Update - Action for Allwyn - Installation has now been amended to 06/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 06/06 is a suitable date. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015572 | 30016959 | 2.Commissioning |  |  | 2024-06-24 | 2024-06-24 | 2024-06-24 | TRUE |  |  |  | 2024-07-31 | [7 empty] | 0
729 | 101762 | 637 | Batch 3 May24 | Type 1 | FTTP | WHITEHORSE STORES | CROYDON | CR0 2LF | 2024-06-26 | 19/7/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_18/7/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_17/7/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_16/7/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_15/7/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_12/7/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_11/7/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_10/7/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_9/7/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_4/7/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_3/7/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_27/6/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_25/6/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_24/6/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_20/6/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_19/6/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_18/6/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_17/6/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_14/6/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_13/6/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_12/6/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 19/7/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_18/7/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_17/7/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_16/7/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_15/7/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_12/7/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_11/7/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_10/7/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_9/7/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_4/7/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_3/7/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_27/6/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_25/6/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_24/6/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_20/6/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_19/6/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_18/6/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_17/6/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_14/6/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_13/6/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_12/6/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300834 | 30013527 | 6.Failed router install | AM |  | 2024-05-21 | 2024-07-11 | 2024-07-11 | TRUE |  |  |  | 2024-08-02 |  |  |  | 2024-08-02 | 242005011007 |  | 2024-08-06 | 1
730 | 668695 | 924 | Batch 3 May24 | Type 1 | SoGEA/Mobile | A & S Supermarket | Brentwood | CM13 2BN | 2024-06-07 | 6/9/2024:#Update - NFA - Allwyn confirmed rescheduled install date 16/08 with retailer _x000D_5/9/2024:#Update - NFA - Allwyn confirmed rescheduled install date 16/08 with retailer _x000D_4/9/2024:#Update - NFA - Allwyn confirmed rescheduled install date 16/08 with retailer _x000D_3/9/2024:#Update - NFA - Allwyn confirmed rescheduled install date 16/08 with retailer _x000D_2/9/2024:#Update - NFA - Allwyn confirmed rescheduled install date 16/08 with retailer _x000D_29/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date 16/08 with retailer _x000D_28/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date 16/08 with retailer _x000D_27/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date 16/08 with retailer _x000D_22/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date 16/08 with retailer _x000D_21/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date 16/08 with retailer _x000D_20/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date 16/08 with retailer _x000D_19/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date 16/08 with retailer _x000D_19/8/2024:01427621 _x000D_16/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date 16/08 with retailer _x000D_15/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date 16/08 with retailer _x000D_14/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date 16/08 with retailer _x000D_13/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date 16/08 with retailer _x000D_12/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date 16/08 with retailer _x000D_9/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date 16/08 with retailer _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_24/7/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_23/7/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_22/7/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_22/7/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_19/7/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_18/7/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_17/7/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_16/7/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_15/7/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_12/7/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_11/7/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_10/7/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_9/7/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_4/7/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_3/7/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_27/6/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_25/6/2024:#Update - Openreach have advised this install requires 2 hours of OOH - proposal sent to VF to approve with customer _x000D_24/6/2024:#Update - Openreach have advised this install requires 2 hours of OOH - proposal sent to VF to approve with customer _x000D_20/6/2024:#Update - Openreach have advised this install requires 2 hours of OOH - proposal sent to VF to approve with customer _x000D_19/6/2024:#Update - Openreach have advised this install requires 2 hours of OOH - proposal sent to VF to approve with customer _x000D_18/6/2024:#Update - Openreach have advised this install requires 2 hours of OOH - proposal sent to VF to approve with customer _x000D_17/6/2024:#Update - Openreach have advised this install requires 2 hours of OOH - proposal sent to VF to approve with customer _x000D_14/6/2024:#Update - Openreach have advised this install requires 2 hours of OOH - proposal sent to VF to approve with customer _x000D_13/6/2024:#Update - Openreach have advised this install requires 2 hours of OOH - proposal sent to VF to approve with customer _x000D_12/6/2024:#Update - Openreach have advised this install requires 2 hours of OOH - proposal sent to VF to approve with customer _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - NFA - Allwyn confirmed rescheduled install date 16/08 with retailer _x000D_6/9/2024:#Update - NFA - Allwyn confirmed rescheduled install date 16/08 with retailer _x000D_5/9/2024:#Update - NFA - Allwyn confirmed rescheduled install date 16/08 with retailer _x000D_4/9/2024:#Update - NFA - Allwyn confirmed rescheduled install date 16/08 with retailer _x000D_3/9/2024:#Update - NFA - Allwyn confirmed rescheduled install date 16/08 with retailer _x000D_2/9/2024:#Update - NFA - Allwyn confirmed rescheduled install date 16/08 with retailer _x000D_29/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date 16/08 with retailer _x000D_28/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date 16/08 with retailer _x000D_27/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date 16/08 with retailer _x000D_22/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date 16/08 with retailer _x000D_21/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date 16/08 with retailer _x000D_20/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date 16/08 with retailer _x000D_19/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date 16/08 with retailer _x000D_19/8/2024:01427621 _x000D_16/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date 16/08 with retailer _x000D_15/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date 16/08 with retailer _x000D_14/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date 16/08 with retailer _x000D_13/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date 16/08 with retailer _x000D_12/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date 16/08 with retailer _x000D_9/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date 16/08 with retailer _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_24/7/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_23/7/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_22/7/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_22/7/2024:#Update - OOH appointment required, awaiting scope of work from OR. _x000D_19/7/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_18/7/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_17/7/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_16/7/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_15/7/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_12/7/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_11/7/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_10/7/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_9/7/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_4/7/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_3/7/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_27/6/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_25/6/2024:#Update - Openreach have advised this install requires 2 hours of OOH - proposal sent to VF to approve with customer _x000D_24/6/2024:#Update - Openreach have advised this install requires 2 hours of OOH - proposal sent to VF to approve with customer _x000D_20/6/2024:#Update - Openreach have advised this install requires 2 hours of OOH - proposal sent to VF to approve with customer _x000D_19/6/2024:#Update - Openreach have advised this install requires 2 hours of OOH - proposal sent to VF to approve with customer _x000D_18/6/2024:#Update - Openreach have advised this install requires 2 hours of OOH - proposal sent to VF to approve with customer _x000D_17/6/2024:#Update - Openreach have advised this install requires 2 hours of OOH - proposal sent to VF to approve with customer _x000D_14/6/2024:#Update - Openreach have advised this install requires 2 hours of OOH - proposal sent to VF to approve with customer _x000D_13/6/2024:#Update - Openreach have advised this install requires 2 hours of OOH - proposal sent to VF to approve with customer _x000D_12/6/2024:#Update - Openreach have advised this install requires 2 hours of OOH - proposal sent to VF to approve with customer _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | #Update - NFA - Allwyn confirmed rescheduled install date 16/08 with retailer | 2024-06-07 | 7/6/2024: CSL to provide an update |  |  | 5.CSL | VFS978046 | 30013814 | 1.Provisioning | AM |  | 2024-06-06 | 2024-08-27 |  | 0 | [11 empty] | 0 | 668695
731 | 664938 | 1139 | Batch 3 May24 | Type 1 | SoGEA/Mobile | Premier Dickleburgh Stores | DISS | IP21 4NW | 2024-06-26 | 6/9/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_5/9/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_4/9/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_3/9/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_2/9/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_29/8/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_28/8/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_27/8/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_22/8/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_21/8/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_20/8/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_19/8/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_19/8/2024:01410547 _x000D_16/8/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_15/8/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_14/8/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_13/8/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_12/8/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_9/8/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_8/8/2024:27/06/2024 _x000D_6/8/2024:27/06/2024 _x000D_5/8/2024:27/06/2024 _x000D_2/8/2024:27/06/2024 _x000D_1/8/2024:27/06/2024 _x000D_31/7/2024:27/06/2024 _x000D_31/7/2024:27/06/2024 _x000D_30/7/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_29/7/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_29/7/2024:01410547 _x000D_26/7/2024:01410547 _x000D_24/7/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_23/7/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_22/7/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_22/7/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_19/7/2024:#Update Order delayed by our Suppliers due to a Multiskilled Engineer being required to complete the installation. We will provide updates as they become available. _x000D_18/7/2024:#Update Order delayed by our Suppliers due to a Multiskilled Engineer being required to complete the installation. We will provide updates as they become available. _x000D_17/7/2024:#Update Order delayed by our Suppliers due to a Multiskilled Engineer being required to complete the installation. We will provide updates as they become available. _x000D_16/7/2024:#Update Order delayed by our Suppliers due to a Multiskilled Engineer being required to complete the installation. We will provide updates as they become available. _x000D_15/7/2024:#Update Order delayed by our Suppliers due to a Multiskilled Engineer being required to complete the installation. We will provide updates as they become available. _x000D_12/7/2024:#Update Order delayed by our Suppliers due to a Multiskilled Engineer being required to complete the installation. We will provide updates as they become available. _x000D_11/7/2024:#Update Order delayed by our Suppliers due to a Multiskilled Engineer being required to complete the installation. We will provide updates as they become available. _x000D_10/7/2024:#Update Order delayed by our Suppliers due to a Multiskilled Engineer being required to complete the installation. We will provide updates as they become available. _x000D_9/7/2024:#Update Order delayed by our Suppliers due to a Multiskilled Engineer being required to complete the installation. We will provide updates as they become available. _x000D_4/7/2024:#Update Order delayed by our Suppliers due to a Multiskilled Engineer being required to complete the installation. We will provide updates as they become available. _x000D_3/7/2024:#Update Order delayed by our Suppliers due to a Multiskilled Engineer being required to complete the installation. We will provide updates as they become available. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update Order delayed by our Suppliers due to a Multiskilled Engineer being required to complete the installation. We will provide updates as they become available. _x000D_27/6/2024:#Update Retailer happy with new appointment - 25/06, AM. _x000D_25/6/2024:#Update Retailer happy with new appointment - 25/06, AM. _x000D_24/6/2024:#Update Retailer happy with new appointment - 25/06, AM. _x000D_20/6/2024:#Update Retailer happy with new appointment - 25/06, AM. _x000D_19/6/2024:#Update Retailer happy with new appointment - 25/06, AM. _x000D_18/6/2024:#Update Retailer happy with new appointment - 25/06, AM. _x000D_17/6/2024:#Update Retailer happy with new appointment - 25/06, AM. _x000D_14/6/2024:#Update Retailer happy with new appointment - 25/06, AM. _x000D_13/6/2024:#Update Order has been delayed due as engineer unable to access DP. order is now with controls team to get the engineer reassigned. Updates to follow. _x000D_12/6/2024:#Update Order has been delayed due as engineer unable to access DP. order is now with controls team to get the engineer reassigned. Updates to follow. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_6/9/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_5/9/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_4/9/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_3/9/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_2/9/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_29/8/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_28/8/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_27/8/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_22/8/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_21/8/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_20/8/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_19/8/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_19/8/2024:01410547 _x000D_16/8/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_15/8/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_14/8/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_13/8/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_12/8/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_9/8/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_8/8/2024:27/06/2024 _x000D_6/8/2024:27/06/2024 _x000D_5/8/2024:27/06/2024 _x000D_2/8/2024:27/06/2024 _x000D_1/8/2024:27/06/2024 _x000D_31/7/2024:27/06/2024 _x000D_31/7/2024:27/06/2024 _x000D_30/7/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_29/7/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_29/7/2024:01410547 _x000D_26/7/2024:01410547 _x000D_24/7/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_23/7/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_22/7/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_22/7/2024:#Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request _x000D_19/7/2024:#Update Order delayed by our Suppliers due to a Multiskilled Engineer being required to complete the installation. We will provide updates as they become available. _x000D_18/7/2024:#Update Order delayed by our Suppliers due to a Multiskilled Engineer being required to complete the installation. We will provide updates as they become available. _x000D_17/7/2024:#Update Order delayed by our Suppliers due to a Multiskilled Engineer being required to complete the installation. We will provide updates as they become available. _x000D_16/7/2024:#Update Order delayed by our Suppliers due to a Multiskilled Engineer being required to complete the installation. We will provide updates as they become available. _x000D_15/7/2024:#Update Order delayed by our Suppliers due to a Multiskilled Engineer being required to complete the installation. We will provide updates as they become available. _x000D_12/7/2024:#Update Order delayed by our Suppliers due to a Multiskilled Engineer being required to complete the installation. We will provide updates as they become available. _x000D_11/7/2024:#Update Order delayed by our Suppliers due to a Multiskilled Engineer being required to complete the installation. We will provide updates as they become available. _x000D_10/7/2024:#Update Order delayed by our Suppliers due to a Multiskilled Engineer being required to complete the installation. We will provide updates as they become available. _x000D_9/7/2024:#Update Order delayed by our Suppliers due to a Multiskilled Engineer being required to complete the installation. We will provide updates as they become available. _x000D_4/7/2024:#Update Order delayed by our Suppliers due to a Multiskilled Engineer being required to complete the installation. We will provide updates as they become available. _x000D_3/7/2024:#Update Order delayed by our Suppliers due to a Multiskilled Engineer being required to complete the installation. We will provide updates as they become available. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update Order delayed by our Suppliers due to a Multiskilled Engineer being required to complete the installation. We will provide updates as they become available. _x000D_27/6/2024:#Update Retailer happy with new appointment - 25/06, AM. _x000D_25/6/2024:#Update Retailer happy with new appointment - 25/06, AM. _x000D_24/6/2024:#Update Retailer happy with new appointment - 25/06, AM. _x000D_20/6/2024:#Update Retailer happy with new appointment - 25/06, AM. _x000D_19/6/2024:#Update Retailer happy with new appointment - 25/06, AM. _x000D_18/6/2024:#Update Retailer happy with new appointment - 25/06, AM. _x000D_17/6/2024:#Update Retailer happy with new appointment - 25/06, AM. _x000D_14/6/2024:#Update Retailer happy with new appointment - 25/06, AM. _x000D_13/6/2024:#Update Order has been delayed due as engineer unable to access DP. order is now with controls team to get the engineer reassigned. Updates to follow. _x000D_12/6/2024:#Update Order has been delayed due as engineer unable to access DP. order is now with controls team to get the engineer reassigned. Updates to follow. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | #Update - installation is on hold whilst we are awaiting feedback for out of hours/TRC request |  |  |  |  | 1.Allwyn to approve additional charges | VFS978150 | 30014029 | 1.Provisioning | AM |  | 2024-05-24 | 2024-08-21 |  | 0 | [11 empty] | 0
732 | 666806 | 1177 | Batch 3 May24 | Type 1 | SoGEA/Mobile | Broad Park Post Office News | COVENTRY | CV2 1DB | 2024-06-26 | 6/9/2024:#Update Upgrade charges approved and retailer happy with new appointment 23/09, AM. _x000D_5/9/2024:#Update Upgrade charges approved and retailer happy with new appointment 23/09, AM. _x000D_4/9/2024:#Update Upgrade charges approved and retailer happy with new appointment 23/09, AM. _x000D_3/9/2024:#Update Upgrade charges approved and retailer happy with new appointment 23/09, AM. _x000D_2/9/2024:#Update Upgrade charges approved and retailer happy with new appointment 23/09, AM. _x000D_29/8/2024:#Update Upgrade charges approved and retailer happy with new appointment 23/09, AM. _x000D_28/8/2024:#Update Upgrade charges approved and retailer happy with new appointment 23/09, AM. _x000D_27/8/2024:#Update Upgrade charges approved and retailer happy with new appointment 23/09, AM. _x000D_22/8/2024:#Update Upgrade charges approved and retailer happy with new appointment 23/09, AM. _x000D_21/8/2024:#Update Retailer happy with new appointment 07/08, AM _x000D_20/8/2024:#Update Retailer happy with new appointment 07/08, AM _x000D_19/8/2024:#Update Retailer happy with new appointment 07/08, AM _x000D_19/8/2024:01414061 _x000D_16/8/2024:#Update Retailer happy with new appointment 07/08, AM _x000D_15/8/2024:#Update Retailer happy with new appointment 07/08, AM _x000D_14/8/2024:#Update Retailer happy with new appointment 07/08, AM _x000D_13/8/2024:#Update Retailer happy with new appointment 07/08, AM _x000D_12/8/2024:#Update Retailer happy with new appointment 07/08, AM _x000D_9/8/2024:#Update Retailer happy with new appointment 07/08, AM _x000D_8/8/2024:23/07/2024 _x000D_6/8/2024:23/07/2024 _x000D_5/8/2024:23/07/2024 _x000D_2/8/2024:23/07/2024 _x000D_1/8/2024:23/07/2024 _x000D_31/7/2024:23/07/2024 _x000D_31/7/2024:23/07/2024 _x000D_30/7/2024:#Update Retailer happy with new appointment 07/08, AM _x000D_29/7/2024:#Update Retailer happy with new appointment 07/08, AM _x000D_29/7/2024:01414061 _x000D_26/7/2024:01414061 _x000D_24/7/2024:#Update Retailer happy with new appointment 07/08, AM _x000D_23/7/2024:#Update Retailer happy with new appointment 07/08, AM _x000D_22/7/2024:#Update Order delayed by our Suppliers due to a Multiskilled Engineer being required to complete the installation. We will provide updates as they become available. _x000D_22/7/2024:#Update Order delayed by our Suppliers due to a Multiskilled Engineer being required to complete the installation. We will provide updates as they become available. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:#Update - Retailer aware of 25/06 am Appointment _x000D_25/6/2024:#Update - Retailer aware of 25/06 am Appointment _x000D_24/6/2024:#Update - Retailer aware of 25/06 am Appointment _x000D_20/6/2024:#Update - Retailer aware of 25/06 am Appointment _x000D_19/6/2024:#Update - Retailer aware of 25/06 am Appointment _x000D_18/6/2024:#Update - Retailer aware of 25/06 am Appointment _x000D_17/6/2024:#Update - Retailer aware of 25/06 am Appointment _x000D_14/6/2024:#Update - Retailer aware of 25/06 am Appointment _x000D_13/6/2024:#Update - Retailer aware of 25/06 am Appointment _x000D_12/6/2024:#Update Reappointed 25/06, AM. Action on Allwyn - make the retailer aware of the new appointment. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update Upgrade charges approved and retailer happy with new appointment 23/09, AM. _x000D_6/9/2024:#Update Upgrade charges approved and retailer happy with new appointment 23/09, AM. _x000D_5/9/2024:#Update Upgrade charges approved and retailer happy with new appointment 23/09, AM. _x000D_4/9/2024:#Update Upgrade charges approved and retailer happy with new appointment 23/09, AM. _x000D_3/9/2024:#Update Upgrade charges approved and retailer happy with new appointment 23/09, AM. _x000D_2/9/2024:#Update Upgrade charges approved and retailer happy with new appointment 23/09, AM. _x000D_29/8/2024:#Update Upgrade charges approved and retailer happy with new appointment 23/09, AM. _x000D_28/8/2024:#Update Upgrade charges approved and retailer happy with new appointment 23/09, AM. _x000D_27/8/2024:#Update Upgrade charges approved and retailer happy with new appointment 23/09, AM. _x000D_22/8/2024:#Update Upgrade charges approved and retailer happy with new appointment 23/09, AM. _x000D_21/8/2024:#Update Retailer happy with new appointment 07/08, AM _x000D_20/8/2024:#Update Retailer happy with new appointment 07/08, AM _x000D_19/8/2024:#Update Retailer happy with new appointment 07/08, AM _x000D_19/8/2024:01414061 _x000D_16/8/2024:#Update Retailer happy with new appointment 07/08, AM _x000D_15/8/2024:#Update Retailer happy with new appointment 07/08, AM _x000D_14/8/2024:#Update Retailer happy with new appointment 07/08, AM _x000D_13/8/2024:#Update Retailer happy with new appointment 07/08, AM _x000D_12/8/2024:#Update Retailer happy with new appointment 07/08, AM _x000D_9/8/2024:#Update Retailer happy with new appointment 07/08, AM _x000D_8/8/2024:23/07/2024 _x000D_6/8/2024:23/07/2024 _x000D_5/8/2024:23/07/2024 _x000D_2/8/2024:23/07/2024 _x000D_1/8/2024:23/07/2024 _x000D_31/7/2024:23/07/2024 _x000D_31/7/2024:23/07/2024 _x000D_30/7/2024:#Update Retailer happy with new appointment 07/08, AM _x000D_29/7/2024:#Update Retailer happy with new appointment 07/08, AM _x000D_29/7/2024:01414061 _x000D_26/7/2024:01414061 _x000D_24/7/2024:#Update Retailer happy with new appointment 07/08, AM _x000D_23/7/2024:#Update Retailer happy with new appointment 07/08, AM _x000D_22/7/2024:#Update Order delayed by our Suppliers due to a Multiskilled Engineer being required to complete the installation. We will provide updates as they become available. _x000D_22/7/2024:#Update Order delayed by our Suppliers due to a Multiskilled Engineer being required to complete the installation. We will provide updates as they become available. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:#Update - Retailer aware of 25/06 am Appointment _x000D_25/6/2024:#Update - Retailer aware of 25/06 am Appointment _x000D_24/6/2024:#Update - Retailer aware of 25/06 am Appointment _x000D_20/6/2024:#Update - Retailer aware of 25/06 am Appointment _x000D_19/6/2024:#Update - Retailer aware of 25/06 am Appointment _x000D_18/6/2024:#Update - Retailer aware of 25/06 am Appointment _x000D_17/6/2024:#Update - Retailer aware of 25/06 am Appointment _x000D_14/6/2024:#Update - Retailer aware of 25/06 am Appointment _x000D_13/6/2024:#Update - Retailer aware of 25/06 am Appointment _x000D_12/6/2024:#Update Reappointed 25/06, AM. Action on Allwyn - make the retailer aware of the new appointment. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update Upgrade charges approved and retailer happy with new appointment 23/09, AM. | 2024-05-29 | 29/05/24: CSL to provide an update |  |  | 2.Allwyn to arrange access | VFS978013 | 30014067 | 1.Provisioning | AM |  | 2024-05-28 | 2024-08-22 |  | 0 | [11 empty] | 0
733 | 471562 | 1399 | Batch 4 Jun24 | Type 1 | SOGEA | Premier | Girvan | KA26 0AA | 2024-06-26 | 27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:Update: Order Amended _x000D_7/6/2024:Update: Order Amended _x000D_6/6/2024:Update: Order Amended _x000D_5/6/2024:Update: Order Amended _x000D_4/6/2024:Update: Order Amended _x000D_31/5/2024:0 _x000D_02/05/2024: New order added to report | 27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:Update: Order Amended _x000D_7/6/2024:Update: Order Amended _x000D_6/6/2024:Update: Order Amended _x000D_5/6/2024:Update: Order Amended _x000D_4/6/2024:Update: Order Amended _x000D_31/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 | 31/05/24: CSL to provide an update |  |  | 3.Allwyn to arrange rtr install | VFS984867 | 30015635 | 2.Commissioning | AM |  | 2024-06-25 | 2024-06-25 | 2024-06-25 | TRUE |  |  |  | 2024-07-19 | [7 empty] | 0
734 | 656824 | 1651 | Batch 4 Jun24 | Type 1 | SOGEA | Spar | Belfast | BT13 2JF | 2024-06-26 | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:Your order has been delayed due to a customer missed appointment. Customer Unavailable for the appointment. Now the order got re-appointed for 25/06/2024. _x000D_17/6/2024:Your order has been delayed due to a customer missed appointment. Customer Unavailable for the appointment. Now the order got re-appointed for 25/06/2024. _x000D_14/6/2024:Your order has been delayed due to a customer missed appointment. Customer Unavailable for the appointment. Now the order got re-appointed for 25/06/2024. _x000D_13/6/2024:Your order has been delayed due to a customer missed appointment. Customer Unavailable for the appointment. Now the order got re-appointed for 25/06/2024. _x000D_12/6/2024:Your order has been delayed due to a customer missed appointment. Customer Unavailable for the appointment. Now the order got re-appointed for 25/06/2024. _x000D_10/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:Your order has been delayed due to a customer missed appointment. Customer Unavailable for the appointment. Now the order got re-appointed for 25/06/2024. _x000D_17/6/2024:Your order has been delayed due to a customer missed appointment. Customer Unavailable for the appointment. Now the order got re-appointed for 25/06/2024. _x000D_14/6/2024:Your order has been delayed due to a customer missed appointment. Customer Unavailable for the appointment. Now the order got re-appointed for 25/06/2024. _x000D_13/6/2024:Your order has been delayed due to a customer missed appointment. Customer Unavailable for the appointment. Now the order got re-appointed for 25/06/2024. _x000D_12/6/2024:Your order has been delayed due to a customer missed appointment. Customer Unavailable for the appointment. Now the order got re-appointed for 25/06/2024. _x000D_10/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2369640 | 30017061 | 2.Commissioning | AM |  | 2024-06-25 | 2024-06-25 | 2024-06-25 | TRUE |  |  |  | 2024-07-25 | [7 empty] | 0
735 | 632534 | 1856 | Batch 4 Jun24 | Type 1 | FTTP/Mobile | SPAR | Magherafelt | BT45 6EN | 2024-06-26 | 6/9/2024:#Update - Landlord details for us to obtain a permission to work form as a survey is required at this site, request sent to Allwyn to respond to, once received we will share with Openreach _x000D_5/9/2024:#Update - Landlord details for us to obtain a permission to work form as a survey is required at this site, request sent to Allwyn to respond to, once received we will share with Openreach _x000D_4/9/2024:#Update - Landlord details for us to obtain a permission to work form as a survey is required at this site, request sent to Allwyn to respond to, once received we will share with Openreach _x000D_3/9/2024:#Update - Landlord details for us to obtain a permission to work form as a survey is required at this site, request sent to Allwyn to respond to, once received we will share with Openreach _x000D_2/9/2024:#Update - Landlord details for us to obtain a permission to work form as a survey is required at this site, request sent to Allwyn to respond to, once received we will share with Openreach _x000D_29/8/2024:#Update - Landlord details for us to obtain a permission to work form as a survey is required at this site, request sent to Allwyn to respond to, once received we will share with Openreach _x000D_28/8/2024:#Update - Landlord details for us to obtain a permission to work form as a survey is required at this site, request sent to Allwyn to respond to, once received we will share with Openreach _x000D_27/8/2024:#Update - Landlord details for us to obtain a permission to work form as a survey is required at this site, request sent to Allwyn to respond to, once received we will share with Openreach _x000D_22/8/2024:#Update - Landlord details for us to obtain a permission to work form as a survey is required at this site, request sent to Allwyn to respond to, once received we will share with Openreach _x000D_21/8/2024:#Update - Landlord details for us to obtain a permission to work form as a survey is required at this site, request sent to Allwyn to respond to, once received we will share with Openreach _x000D_20/8/2024:#Update - Landlord details for us to obtain a permission to work form as a survey is required at this site, request sent to Allwyn to respond to, once received we will share with Openreach _x000D_19/8/2024:#Update - Landlord details for us to obtain a permission to work form as a survey is required at this site, request sent to Allwyn to respond to, once received we will share with Openreach _x000D_19/8/2024:01394866 _x000D_16/8/2024:#Update - Landlord details for us to obtain a permission to work form as a survey is required at this site, request sent to Allwyn to respond to, once received we will share with Openreach _x000D_15/8/2024:#Update - Landlord details for us to obtain a permission to work form as a survey is required at this site, request sent to Allwyn to respond to, once received we will share with Openreach _x000D_14/8/2024:#Update - Landlord details for us to obtain a permission to work form as a survey is required at this site, request sent to Allwyn to respond to, once received we will share with Openreach _x000D_13/8/2024:#Update - Landlord details for us to obtain a permission to work form as a survey is required at this site, request sent to Allwyn to respond to, once received we will share with Openreach _x000D_12/8/2024:#Update - Landlord details for us to obtain a permission to work form as a survey is required at this site, request sent to Allwyn to respond to, once received we will share with Openreach _x000D_9/8/2024:#Update - Landlord details for us to obtain a permission to work form as a survey is required at this site, request sent to Allwyn to respond to, once received we will share with Openreach _x000D_8/8/2024:05/08/2024 _x000D_6/8/2024:05/08/2024 _x000D_5/8/2024:25/07/2024 _x000D_2/8/2024:25/07/2024 _x000D_1/8/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_30/7/2024:#Update Sent chaser to VF for survey approval _x000D_29/7/2024:#Update Sent chaser to VF for survey approval _x000D_29/7/2024:01394866 _x000D_26/7/2024:01394866 _x000D_24/7/2024:#Update Upgrade with VF to view. _x000D_23/7/2024:#Update Upgrade with VF to view. _x000D_22/7/2024:#Update Upgrade with VF to view. _x000D_22/7/2024:#Update Upgrade with VF to view. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_25/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_24/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_20/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_19/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_18/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_17/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_14/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_13/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_12/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 9/9/2024:#Update - Landlord details for us to obtain a permission to work form as a survey is required at this site, request sent to Allwyn to respond to, once received we will share with Openreach _x000D_6/9/2024:#Update - Landlord details for us to obtain a permission to work form as a survey is required at this site, request sent to Allwyn to respond to, once received we will share with Openreach _x000D_5/9/2024:#Update - Landlord details for us to obtain a permission to work form as a survey is required at this site, request sent to Allwyn to respond to, once received we will share with Openreach _x000D_4/9/2024:#Update - Landlord details for us to obtain a permission to work form as a survey is required at this site, request sent to Allwyn to respond to, once received we will share with Openreach _x000D_3/9/2024:#Update - Landlord details for us to obtain a permission to work form as a survey is required at this site, request sent to Allwyn to respond to, once received we will share with Openreach _x000D_2/9/2024:#Update - Landlord details for us to obtain a permission to work form as a survey is required at this site, request sent to Allwyn to respond to, once received we will share with Openreach _x000D_29/8/2024:#Update - Landlord details for us to obtain a permission to work form as a survey is required at this site, request sent to Allwyn to respond to, once received we will share with Openreach _x000D_28/8/2024:#Update - Landlord details for us to obtain a permission to work form as a survey is required at this site, request sent to Allwyn to respond to, once received we will share with Openreach _x000D_27/8/2024:#Update - Landlord details for us to obtain a permission to work form as a survey is required at this site, request sent to Allwyn to respond to, once received we will share with Openreach _x000D_22/8/2024:#Update - Landlord details for us to obtain a permission to work form as a survey is required at this site, request sent to Allwyn to respond to, once received we will share with Openreach _x000D_21/8/2024:#Update - Landlord details for us to obtain a permission to work form as a survey is required at this site, request sent to Allwyn to respond to, once received we will share with Openreach _x000D_20/8/2024:#Update - Landlord details for us to obtain a permission to work form as a survey is required at this site, request sent to Allwyn to respond to, once received we will share with Openreach _x000D_19/8/2024:#Update - Landlord details for us to obtain a permission to work form as a survey is required at this site, request sent to Allwyn to respond to, once received we will share with Openreach _x000D_19/8/2024:01394866 _x000D_16/8/2024:#Update - Landlord details for us to obtain a permission to work form as a survey is required at this site, request sent to Allwyn to respond to, once received we will share with Openreach _x000D_15/8/2024:#Update - Landlord details for us to obtain a permission to work form as a survey is required at this site, request sent to Allwyn to respond to, once received we will share with Openreach _x000D_14/8/2024:#Update - Landlord details for us to obtain a permission to work form as a survey is required at this site, request sent to Allwyn to respond to, once received we will share with Openreach _x000D_13/8/2024:#Update - Landlord details for us to obtain a permission to work form as a survey is required at this site, request sent to Allwyn to respond to, once received we will share with Openreach _x000D_12/8/2024:#Update - Landlord details for us to obtain a permission to work form as a survey is required at this site, request sent to Allwyn to respond to, once received we will share with Openreach _x000D_9/8/2024:#Update - Landlord details for us to obtain a permission to work form as a survey is required at this site, request sent to Allwyn to respond to, once received we will share with Openreach _x000D_8/8/2024:05/08/2024 _x000D_6/8/2024:05/08/2024 _x000D_5/8/2024:25/07/2024 _x000D_2/8/2024:25/07/2024 _x000D_1/8/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_30/7/2024:#Update Sent chaser to VF for survey approval _x000D_29/7/2024:#Update Sent chaser to VF for survey approval _x000D_29/7/2024:01394866 _x000D_26/7/2024:01394866 _x000D_24/7/2024:#Update Upgrade with VF to view. _x000D_23/7/2024:#Update Upgrade with VF to view. _x000D_22/7/2024:#Update Upgrade with VF to view. _x000D_22/7/2024:#Update Upgrade with VF to view. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_25/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_24/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_20/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_19/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_18/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_17/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_14/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_13/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_12/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 0 | #Update - Landlord details for us to obtain a permission to work form as a survey is required at this site, request sent to Allwyn to respond to, once received we will share with Openreach | 2024-06-07 |  |  |  | 5.CSL | VFP2353425 | 30015954 | 1.Provisioning | AM |  | 2024-06-03 | 2024-06-25 |  | 0 | [11 empty] | 0
736 | 665063 | 1928 | Batch 4 Jun24 | Type 1 | SOGEA | Royal Mail | Colchester | CO6 1DT | 2024-07-11 | 2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update Retailer aware of visit 25/07, AM. _x000D_18/7/2024:#Update Retailer aware of visit 25/07, AM. _x000D_17/7/2024:#Update Retailer aware of visit 25/07, AM. _x000D_16/7/2024:#Update Retailer aware of visit 25/07, AM. _x000D_15/7/2024:#Update Retailer aware of visit 25/07, AM. _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_27/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_18/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_17/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_14/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_13/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_12/6/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/6/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_30/5/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/5/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_28/5/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/5/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/05/2024: New order added to report | 2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update Retailer aware of visit 25/07, AM. _x000D_18/7/2024:#Update Retailer aware of visit 25/07, AM. _x000D_17/7/2024:#Update Retailer aware of visit 25/07, AM. _x000D_16/7/2024:#Update Retailer aware of visit 25/07, AM. _x000D_15/7/2024:#Update Retailer aware of visit 25/07, AM. _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_27/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_18/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_17/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_14/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_13/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_12/6/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/6/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_30/5/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/5/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_28/5/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/5/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFS996846 | 30016030 | 6.Failed router install | AM |  | 2024-06-11 | 2024-06-25 | 2024-07-10 | TRUE |  |  |  | 2024-08-01 |  |  |  | 2024-08-01 | 242005008605 |  | 2024-08-02 | 1
737 | 642102 | 3199 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Day Today | MUSSELBURGH | EH21 8BQ | 2024-06-26 | 6/9/2024:#Update - Charges approved - Awaiting go ahead from OR for 05/08 _x000D_5/9/2024:#Update - Charges approved - Awaiting go ahead from OR for 05/08 _x000D_4/9/2024:#Update - Charges approved - Awaiting go ahead from OR for 05/08 _x000D_3/9/2024:#Update - Charges approved - Awaiting go ahead from OR for 05/08 _x000D_2/9/2024:#Update - Charges approved - Awaiting go ahead from OR for 05/08 _x000D_29/8/2024:#Update - Charges approved - Awaiting go ahead from OR for 05/08 _x000D_28/8/2024:#Update - Charges approved - Awaiting go ahead from OR for 05/08 _x000D_27/8/2024:#Update - Charges approved - Awaiting go ahead from OR for 05/08 _x000D_22/8/2024:#Update - Charges approved - Awaiting go ahead from OR for 05/08 _x000D_21/8/2024:#Update - Charges approved - Awaiting go ahead from OR for 05/08 _x000D_20/8/2024:#Update - Charges approved - Awaiting go ahead from OR for 05/08 _x000D_19/8/2024:#Update - Charges approved - Awaiting go ahead from OR for 05/08 _x000D_19/8/2024:01472829 _x000D_16/8/2024:#Update - Charges approved - Awaiting go ahead from OR for 05/08 _x000D_15/8/2024:#Update - Charges approved - Awaiting go ahead from OR for 05/08 _x000D_14/8/2024:#Update - Charges approved - Awaiting go ahead from OR for 05/08 _x000D_13/8/2024:#Update - Charges approved - Awaiting go ahead from OR for 05/08 _x000D_12/8/2024:#Update - Charges approved - Awaiting go ahead from OR for 05/08 _x000D_9/8/2024:#Update - Charges approved - Awaiting go ahead from OR for 05/08 _x000D_8/8/2024:30/07/2024 _x000D_6/8/2024:30/07/2024 _x000D_5/8/2024:30/07/2024 _x000D_2/8/2024:30/07/2024 _x000D_1/8/2024:30/07/2024 _x000D_31/7/2024:30/07/2024 _x000D_31/7/2024:30/07/2024 _x000D_30/7/2024:#Update - Charges approved - Awaiting go ahead from OR for 05/08 _x000D_29/7/2024:#Update - Awaiting ECC approval. _x000D_29/7/2024:01472829 _x000D_26/7/2024:01472829 _x000D_24/7/2024:#Update - Awaiting ECC approval. _x000D_23/7/2024:#Update - Awaiting ECC approval. _x000D_22/7/2024:#Update - Awaiting ECC approval. _x000D_22/7/2024:#Update - Awaiting ECC approval. _x000D_27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:#Update - Charges approved - Awaiting go ahead from OR for 05/08 _x000D_6/9/2024:#Update - Charges approved - Awaiting go ahead from OR for 05/08 _x000D_5/9/2024:#Update - Charges approved - Awaiting go ahead from OR for 05/08 _x000D_4/9/2024:#Update - Charges approved - Awaiting go ahead from OR for 05/08 _x000D_3/9/2024:#Update - Charges approved - Awaiting go ahead from OR for 05/08 _x000D_2/9/2024:#Update - Charges approved - Awaiting go ahead from OR for 05/08 _x000D_29/8/2024:#Update - Charges approved - Awaiting go ahead from OR for 05/08 _x000D_28/8/2024:#Update - Charges approved - Awaiting go ahead from OR for 05/08 _x000D_27/8/2024:#Update - Charges approved - Awaiting go ahead from OR for 05/08 _x000D_22/8/2024:#Update - Charges approved - Awaiting go ahead from OR for 05/08 _x000D_21/8/2024:#Update - Charges approved - Awaiting go ahead from OR for 05/08 _x000D_20/8/2024:#Update - Charges approved - Awaiting go ahead from OR for 05/08 _x000D_19/8/2024:#Update - Charges approved - Awaiting go ahead from OR for 05/08 _x000D_19/8/2024:01472829 _x000D_16/8/2024:#Update - Charges approved - Awaiting go ahead from OR for 05/08 _x000D_15/8/2024:#Update - Charges approved - Awaiting go ahead from OR for 05/08 _x000D_14/8/2024:#Update - Charges approved - Awaiting go ahead from OR for 05/08 _x000D_13/8/2024:#Update - Charges approved - Awaiting go ahead from OR for 05/08 _x000D_12/8/2024:#Update - Charges approved - Awaiting go ahead from OR for 05/08 _x000D_9/8/2024:#Update - Charges approved - Awaiting go ahead from OR for 05/08 _x000D_8/8/2024:30/07/2024 _x000D_6/8/2024:30/07/2024 _x000D_5/8/2024:30/07/2024 _x000D_2/8/2024:30/07/2024 _x000D_1/8/2024:30/07/2024 _x000D_31/7/2024:30/07/2024 _x000D_31/7/2024:30/07/2024 _x000D_30/7/2024:#Update - Charges approved - Awaiting go ahead from OR for 05/08 _x000D_29/7/2024:#Update - Awaiting ECC approval. _x000D_29/7/2024:01472829 _x000D_26/7/2024:01472829 _x000D_24/7/2024:#Update - Awaiting ECC approval. _x000D_23/7/2024:#Update - Awaiting ECC approval. _x000D_22/7/2024:#Update - Awaiting ECC approval. _x000D_22/7/2024:#Update - Awaiting ECC approval. _x000D_27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | #Update - Charges approved - Awaiting go ahead from OR for 05/08 | 2024-06-07 |  |  |  | 5.CSL | VFS1015475 | 30016703 | 1.Provisioning | AM |  | 2024-06-25 | 2024-09-02 |  | 0 | [11 empty] | 0
738 | 661238 | 3201 | Batch 5 Jul24 | Type 1 | FTTP | Queensway Post Office and Store | Stourbridge | DY9 9HJ | 2024-06-26 | 27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366174 | 30016691 | 6.Failed router install |  |  | 2024-06-25 | 2024-06-25 | 2024-06-25 | TRUE |  |  |  | 2024-07-17 |  |  |  | 2024-07-17 | 237004907477 |  | 2024-07-18 | 1
739 | 435672 | 3202 | Batch 5 Jul24 | Type 1 | SOGEA | SPAR HERLINGTON | PETERBOROUGH | PE2 5PW | 2024-06-26 | 27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015474 | 30016955 | 2.Commissioning |  |  | 2024-06-25 | 2024-06-25 | 2024-06-25 | TRUE |  |  |  | 2024-07-17 | [7 empty] | 0
740 | 486424 | 3204 | Batch 5 Jul24 | Type 1 | FTTP | SPAR GILLINGHAM | GILLINGHAM | ME8 6XJ | 2024-06-26 | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366175 | 30016696 | 2.Commissioning |  |  | 2024-06-25 | 2024-06-25 | 2024-06-25 | TRUE |  |  |  | 2024-07-17 | [7 empty] | 0
741 | 627922 | 3205 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Russells Food & Drink | Newtownards | BT23 7HS | 2024-06-26 | 6/9/2024:#Update - Address verification issue, email sent to VF 18/07 - order is cancelled and will be reraised accordingly _x000D_5/9/2024:#Update - Address verification issue, email sent to VF 18/07 - order is cancelled and will be reraised accordingly _x000D_4/9/2024:#Update - Address verification issue, email sent to VF 18/07 - order is cancelled and will be reraised accordingly _x000D_3/9/2024:#Update - Address verification issue, email sent to VF 18/07 - order is cancelled and will be reraised accordingly _x000D_2/9/2024:#Update - Address verification issue, email sent to VF 18/07 - order is cancelled and will be reraised accordingly _x000D_29/8/2024:#Update - Address verification issue, email sent to VF 18/07 - order is cancelled and will be reraised accordingly _x000D_28/8/2024:#Update - Address verification issue, email sent to VF 18/07 - order is cancelled and will be reraised accordingly _x000D_Address verification issue, email sent to VF - order is cancelled and will be reraised accordingly | 9/9/2024:#Update - Address verification issue, email sent to VF 18/07 - order is cancelled and will be reraised accordingly _x000D_6/9/2024:#Update - Address verification issue, email sent to VF 18/07 - order is cancelled and will be reraised accordingly _x000D_5/9/2024:#Update - Address verification issue, email sent to VF 18/07 - order is cancelled and will be reraised accordingly _x000D_4/9/2024:#Update - Address verification issue, email sent to VF 18/07 - order is cancelled and will be reraised accordingly _x000D_3/9/2024:#Update - Address verification issue, email sent to VF 18/07 - order is cancelled and will be reraised accordingly _x000D_2/9/2024:#Update - Address verification issue, email sent to VF 18/07 - order is cancelled and will be reraised accordingly _x000D_29/8/2024:#Update - Address verification issue, email sent to VF 18/07 - order is cancelled and will be reraised accordingly _x000D_28/8/2024:#Update - Address verification issue, email sent to VF 18/07 - order is cancelled and will be reraised accordingly _x000D_Address verification issue, email sent to VF - order is cancelled and will be reraised accordingly | 0 | #Update - Address verification issue, email sent to VF 18/07 - order is cancelled and will be reraised accordingly | 2024-06-07 |  |  |  | 5.CSL | VFP2366173 | 30016831 | 1.Provisioning | AM |  |  |  |  | 0 | [11 empty] | 0
742 | 671276 | 3206 | Batch 5 Jul24 | Type 1 | SOGEA | Raj Stores Lingdale | SALTBURN-BY-THE-SEA | TS12 3DZ | 2024-06-26 | 27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 5.CSL | VFS1015472 | 30016807 | 6.Failed router install |  |  | 2024-06-25 | 2024-06-25 | 2024-06-25 | TRUE |  |  |  | 2024-07-18 |  |  |  | 2024-07-18 | 238004926119 |  | 2024-07-18 | 1
743 | 667922 | 3209 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Queens Road Grocers | LONDON | SE15 2ND | 2024-06-26 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:#Update - Pushed this one out in order to assign an OOH engineer. _x000D_21/8/2024:#Update - Pushed this one out in order to assign an OOH engineer. _x000D_20/8/2024:#Update - Pushed this one out in order to assign an OOH engineer. _x000D_19/8/2024:#Update - Pushed this one out in order to assign an OOH engineer. _x000D_19/8/2024:01452068 _x000D_16/8/2024:#Update - Pushed this one out in order to assign an OOH engineer. _x000D_15/8/2024:#Update - Pushed this one out in order to assign an OOH engineer. _x000D_14/8/2024:#Update - Pushed this one out in order to assign an OOH engineer. _x000D_13/8/2024:#Update - Pushed this one out in order to assign an OOH engineer. _x000D_12/8/2024:#Update - Pushed this one out in order to assign an OOH engineer. _x000D_9/8/2024:#Update - Pushed this one out in order to assign an OOH engineer. _x000D_8/8/2024:18/07/2024 _x000D_6/8/2024:18/07/2024 _x000D_5/8/2024:18/07/2024 _x000D_2/8/2024:18/07/2024 _x000D_1/8/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_30/7/2024:#Update - Pushed this one out in order to assign an OOH engineer. _x000D_29/7/2024:#Update - Pushed this one out in order to assign an OOH engineer. _x000D_29/7/2024:01452068 _x000D_26/7/2024:01452068 _x000D_24/7/2024:#Update - Pushed this one out in order to assign an OOH engineer. _x000D_23/7/2024:#Update - Pushed this one out in order to assign an OOH engineer. _x000D_22/7/2024:#Update - Pushed this one out in order to assign an OOH engineer. _x000D_22/7/2024:#Update - Pushed this one out in order to assign an OOH engineer. _x000D_19/7/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_18/7/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_17/7/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_16/7/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_15/7/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_12/7/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_11/7/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_10/7/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_9/7/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_4/7/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_3/7/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_27/6/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:#Update - Pushed this one out in order to assign an OOH engineer. _x000D_21/8/2024:#Update - Pushed this one out in order to assign an OOH engineer. _x000D_20/8/2024:#Update - Pushed this one out in order to assign an OOH engineer. _x000D_19/8/2024:#Update - Pushed this one out in order to assign an OOH engineer. _x000D_19/8/2024:01452068 _x000D_16/8/2024:#Update - Pushed this one out in order to assign an OOH engineer. _x000D_15/8/2024:#Update - Pushed this one out in order to assign an OOH engineer. _x000D_14/8/2024:#Update - Pushed this one out in order to assign an OOH engineer. _x000D_13/8/2024:#Update - Pushed this one out in order to assign an OOH engineer. _x000D_12/8/2024:#Update - Pushed this one out in order to assign an OOH engineer. _x000D_9/8/2024:#Update - Pushed this one out in order to assign an OOH engineer. _x000D_8/8/2024:18/07/2024 _x000D_6/8/2024:18/07/2024 _x000D_5/8/2024:18/07/2024 _x000D_2/8/2024:18/07/2024 _x000D_1/8/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_30/7/2024:#Update - Pushed this one out in order to assign an OOH engineer. _x000D_29/7/2024:#Update - Pushed this one out in order to assign an OOH engineer. _x000D_29/7/2024:01452068 _x000D_26/7/2024:01452068 _x000D_24/7/2024:#Update - Pushed this one out in order to assign an OOH engineer. _x000D_23/7/2024:#Update - Pushed this one out in order to assign an OOH engineer. _x000D_22/7/2024:#Update - Pushed this one out in order to assign an OOH engineer. _x000D_22/7/2024:#Update - Pushed this one out in order to assign an OOH engineer. _x000D_19/7/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_18/7/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_17/7/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_16/7/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_15/7/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_12/7/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_11/7/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_10/7/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_9/7/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_4/7/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_3/7/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_27/6/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | 0 | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015473 | 30016701 | 2.Commissioning | AM |  | 2024-06-25 | 2024-08-19 |  | 0 |  |  |  | 2024-09-18 | [7 empty] | 0
744 | 643440 | 3210 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Spar | Armagh | BT60 4AN | 2024-06-26 | 6/9/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_5/9/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_4/9/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_3/9/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_2/9/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_29/8/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_28/8/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_27/8/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_22/8/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_21/8/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_20/8/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_19/8/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_19/8/2024:01452523 _x000D_16/8/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_15/8/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_14/8/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_13/8/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_12/8/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_9/8/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_8/8/2024:26/06/2024 _x000D_6/8/2024:26/06/2024 _x000D_5/8/2024:26/06/2024 _x000D_2/8/2024:26/06/2024 _x000D_1/8/2024:26/06/2024 _x000D_31/7/2024:26/06/2024 _x000D_31/7/2024:26/06/2024 _x000D_30/7/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_29/7/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_29/7/2024:01452523 _x000D_26/7/2024:01452523 _x000D_24/7/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_23/7/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_22/7/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_22/7/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_6/9/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_5/9/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_4/9/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_3/9/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_2/9/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_29/8/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_28/8/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_27/8/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_22/8/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_21/8/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_20/8/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_19/8/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_19/8/2024:01452523 _x000D_16/8/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_15/8/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_14/8/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_13/8/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_12/8/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_9/8/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_8/8/2024:26/06/2024 _x000D_6/8/2024:26/06/2024 _x000D_5/8/2024:26/06/2024 _x000D_2/8/2024:26/06/2024 _x000D_1/8/2024:26/06/2024 _x000D_31/7/2024:26/06/2024 _x000D_31/7/2024:26/06/2024 _x000D_30/7/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_29/7/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_29/7/2024:01452523 _x000D_26/7/2024:01452523 _x000D_24/7/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_23/7/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_22/7/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_22/7/2024:#Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. _x000D_27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | #Update - The engineer was unable to gain access to location duct is entering the building. Duct is coming into ATM bunker room which staff are unable to give access to. This has been an issue previous when the POST OFFICE in the same property attempted to complete a fibre install. G4S security are responsible for granting access to this area. | 2024-06-07 |  |  |  | 5.CSL | VFP2366172 | 30016896 | 1.Provisioning | AM |  | 2024-06-25 | 2024-08-30 |  | 0 | [11 empty] | 0
745 | 632993 | 3211 | Batch 5 Jul24 | Type 1 | SOGEA | Stanley Bus Station Newsagents | Stanley | DH9 0NQ | 2024-06-26 | 27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015569 | 30016801 | 6.Failed router install |  |  | 2024-06-25 | 2024-06-25 | 2024-06-25 | TRUE |  |  |  | 2024-07-17 |  |  |  | 2024-07-17 | 238004926194 |  | 2024-07-17 | 1
746 | 609248 | 3215 | Batch 5 Jul24 | Type 1 | SOGEA | Spar Market | Glenrothes | KY6 2BD | 2024-06-26 | 19/7/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_18/7/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_17/7/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_16/7/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_15/7/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_12/7/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_11/7/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_10/7/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_9/7/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_4/7/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_3/7/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_27/6/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_25/6/2024:Delay on Engineer activities. Supplier will arrange new appointment _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 19/7/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_18/7/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_17/7/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_16/7/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_15/7/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_12/7/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_11/7/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_10/7/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_9/7/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_4/7/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_3/7/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_27/6/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_25/6/2024:Delay on Engineer activities. Supplier will arrange new appointment _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015567 | 30016976 | 2.Commissioning |  |  | 2024-06-25 | 2024-06-25 | 2024-06-25 | TRUE |  |  |  | 2024-07-25 | [7 empty] | 0
747 | 467032 | 3216 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Spar | Macclesfield | SK10 2HB | 2024-06-26 | 6/9/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_5/9/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_4/9/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_3/9/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_2/9/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_29/8/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_28/8/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_27/8/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_22/8/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_21/8/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_20/8/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_19/8/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_19/8/2024:01451791 _x000D_16/8/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_15/8/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_14/8/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_13/8/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_12/8/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_9/8/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_8/8/2024:25/06/2024 _x000D_6/8/2024:25/06/2024 _x000D_5/8/2024:25/06/2024 _x000D_2/8/2024:25/06/2024 _x000D_1/8/2024:25/06/2024 _x000D_31/7/2024:25/06/2024 _x000D_31/7/2024:25/06/2024 _x000D_30/7/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_29/7/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_29/7/2024:01451791 _x000D_26/7/2024:01451791 _x000D_24/7/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_23/7/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_22/7/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_22/7/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_6/9/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_5/9/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_4/9/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_3/9/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_2/9/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_29/8/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_28/8/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_27/8/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_22/8/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_21/8/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_20/8/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_19/8/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_19/8/2024:01451791 _x000D_16/8/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_15/8/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_14/8/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_13/8/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_12/8/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_9/8/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_8/8/2024:25/06/2024 _x000D_6/8/2024:25/06/2024 _x000D_5/8/2024:25/06/2024 _x000D_2/8/2024:25/06/2024 _x000D_1/8/2024:25/06/2024 _x000D_31/7/2024:25/06/2024 _x000D_31/7/2024:25/06/2024 _x000D_30/7/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_29/7/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_29/7/2024:01451791 _x000D_26/7/2024:01451791 _x000D_24/7/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_23/7/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_22/7/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_22/7/2024:#Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM _x000D_27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | #Update - Unable to access DP during opening hours. Also awaiting feedback from engineer, Action for allwyn: Confirm re-appointment for 25/07 - AM | 2024-06-07 |  |  |  | 5.CSL | VFS1015566 | 30016980 | 1.Provisioning | AM |  | 2024-06-25 | 2024-08-30 |  | 0 | [11 empty] | 0
748 | 641296 | 3218 | Batch 5 Jul24 | Type 1 | FTTP | Vivo | BELFAST | BT6 9DP | 2024-06-26 | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 10/07/2024. We will continue to provide update as they become available. _x000D_3/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 10/07/2024. We will continue to provide update as they become available. _x000D_2/7/2024:0 _x000D_1/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 10/07/2024. We will continue to provide update as they become available. _x000D_27/6/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 01/07/2024.We will continue to provide update as they become available. _x000D_25/6/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 10/07/2024. We will continue to provide update as they become available. _x000D_3/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 10/07/2024. We will continue to provide update as they become available. _x000D_2/7/2024:0 _x000D_1/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 10/07/2024. We will continue to provide update as they become available. _x000D_27/6/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 01/07/2024.We will continue to provide update as they become available. _x000D_25/6/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366171 | 30016785 | 6.Failed router install |  |  | 2024-06-25 | 2024-06-25 | 2024-06-25 | TRUE |  |  |  | 2024-07-30 |  |  |  | 2024-07-30 | 23A004952999 |  | 2024-07-31 | 1
749 | 671437 | 3219 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Premier Liscard Stop & Shop | Wallasey | CH45 4NE | 2024-06-26 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:Update: Order Amended _x000D_28/8/2024:Update: Order Amended _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:0 _x000D_20/8/2024:Your order has been delayed due to a customer missed appointment. OOH Appointment required. Please check with end user and reappoint the order if still required. _x000D_19/8/2024:Your order has been delayed due to a customer missed appointment. OOH Appointment required. Please check with end user and reappoint the order if still required. _x000D_19/8/2024:13/08/2024 16:06 _x000D_16/8/2024:Your order has been delayed due to a customer missed appointment. OOH Appointment required. Please check with end user and reappoint the order if still required. _x000D_15/8/2024:Your order has been delayed due to a customer missed appointment. OOH Appointment required. Please check with end user and reappoint the order if still required. _x000D_14/8/2024:Your order has been delayed due to a customer missed appointment. OOH Appointment required. Please check with end user and reappoint the order if still required. _x000D_13/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_12/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_18/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_17/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_16/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_15/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_12/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_11/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_10/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_9/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_27/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:Update: Order Amended _x000D_28/8/2024:Update: Order Amended _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:0 _x000D_20/8/2024:Your order has been delayed due to a customer missed appointment. OOH Appointment required. Please check with end user and reappoint the order if still required. _x000D_19/8/2024:Your order has been delayed due to a customer missed appointment. OOH Appointment required. Please check with end user and reappoint the order if still required. _x000D_19/8/2024:13/08/2024 16:06 _x000D_16/8/2024:Your order has been delayed due to a customer missed appointment. OOH Appointment required. Please check with end user and reappoint the order if still required. _x000D_15/8/2024:Your order has been delayed due to a customer missed appointment. OOH Appointment required. Please check with end user and reappoint the order if still required. _x000D_14/8/2024:Your order has been delayed due to a customer missed appointment. OOH Appointment required. Please check with end user and reappoint the order if still required. _x000D_13/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_12/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_18/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_17/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_16/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_15/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_12/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_11/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_10/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_9/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_27/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | 0 | 2024-06-07 |  |  |  | 5.CSL | VFS1065961 | 30016763 | 1.Provisioning | AM |  | 2024-06-25 | 2024-08-12 |  | 0 | [11 empty] | 0 | 671437
750 | 468817 | 3220 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Kular Stores | GATESHEAD | NE11 0AT | 2024-06-26 | 6/9/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_5/9/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_4/9/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_3/9/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_2/9/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_29/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_28/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_27/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_22/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_21/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_20/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_19/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_19/8/2024:01452551 _x000D_16/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_15/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_14/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_13/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_12/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_9/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_8/8/2024:05/07/2024 _x000D_6/8/2024:05/07/2024 _x000D_5/8/2024:05/07/2024 _x000D_2/8/2024:05/07/2024 _x000D_1/8/2024:05/07/2024 _x000D_31/7/2024:05/07/2024 _x000D_31/7/2024:05/07/2024 _x000D_30/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_29/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_29/7/2024:01452551 _x000D_26/7/2024:01452551 _x000D_24/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_23/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_22/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_22/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_6/9/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_5/9/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_4/9/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_3/9/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_2/9/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_29/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_28/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_27/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_22/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_21/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_20/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_19/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_19/8/2024:01452551 _x000D_16/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_15/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_14/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_13/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_12/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_9/8/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_8/8/2024:05/07/2024 _x000D_6/8/2024:05/07/2024 _x000D_5/8/2024:05/07/2024 _x000D_2/8/2024:05/07/2024 _x000D_1/8/2024:05/07/2024 _x000D_31/7/2024:05/07/2024 _x000D_31/7/2024:05/07/2024 _x000D_30/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_29/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_29/7/2024:01452551 _x000D_26/7/2024:01452551 _x000D_24/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_23/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_22/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_22/7/2024:#Update - ECC proposal sent to Vodafone on 05/07 _x000D_27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | #Update - ECC proposal sent to Vodafone on 05/07 | 2024-06-07 |  |  |  | 5.CSL | VFS1015469 | 30016803 | 1.Provisioning | AM |  | 2024-06-25 | 2024-08-30 |  | 0 | [11 empty] | 0
751 | 486759 | 3221 | Batch 5 Jul24 | Type 1 | SOGEA | SPAR BASSALEG ROAD | Newport | NP20 3NA | 2024-06-26 | 27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 27/6/2024:Order Completed _x000D_25/6/2024:Order Completed _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015565 | 30016680 | 2.Commissioning |  |  | 2024-06-25 | 2024-06-25 | 2024-06-25 | TRUE |  |  |  | 2024-08-01 | [7 empty] | 0
752 | 670357 | 3228 | Batch 5 Jul24 | Type 1 | FTTP | Select & Save | COVENTRY | CV6 3ES | 2024-06-26 | 19/7/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_18/7/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_17/7/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_16/7/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_15/7/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_12/7/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_11/7/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_10/7/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_9/7/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_4/7/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_3/7/2024:#Update - Customer needs to install cable trays above false ceiling for fire safety as well as remove shelving/flooring to get cable to lottery machine. Additional time and engineers is also required. CSL will update as more information become available. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Customer needs to install cable trays above false ceiling for fire safety as well as remove shelving/flooring to get cable to lottery machine. Additional time and engineers is also required. CSL will update as more information become available. _x000D_27/6/2024:#Update - Customer needs to install cable trays above false ceiling for fire safety as well as remove shelving/flooring to get cable to lottery machine. Additional time and engineers is also required. CSL will update as more information become available. _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 19/7/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_18/7/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_17/7/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_16/7/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_15/7/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_12/7/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_11/7/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_10/7/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_9/7/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_4/7/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_3/7/2024:#Update - Customer needs to install cable trays above false ceiling for fire safety as well as remove shelving/flooring to get cable to lottery machine. Additional time and engineers is also required. CSL will update as more information become available. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Customer needs to install cable trays above false ceiling for fire safety as well as remove shelving/flooring to get cable to lottery machine. Additional time and engineers is also required. CSL will update as more information become available. _x000D_27/6/2024:#Update - Customer needs to install cable trays above false ceiling for fire safety as well as remove shelving/flooring to get cable to lottery machine. Additional time and engineers is also required. CSL will update as more information become available. _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366022 | 30016714 | 2.Commissioning |  |  | 2024-06-25 | 2024-06-25 | 2024-06-25 | TRUE |  |  |  | 2024-07-17 | [7 empty] | 0
753 | 430188 | 3229 | Batch 5 Jul24 | Type 3 | FTTP/Mobile | Costcutter | COVENTRY | CV4 9EU | 2024-06-26 | 6/9/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_5/9/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_4/9/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_3/9/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_2/9/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_29/8/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_28/8/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_27/8/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_22/8/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_21/8/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_20/8/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_19/8/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_19/8/2024:01453200 _x000D_16/8/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_15/8/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_14/8/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_13/8/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_12/8/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_9/8/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_8/8/2024:04/07/2024 _x000D_6/8/2024:04/07/2024 _x000D_5/8/2024:04/07/2024 _x000D_2/8/2024:04/07/2024 _x000D_1/8/2024:04/07/2024 _x000D_31/7/2024:04/07/2024 _x000D_31/7/2024:04/07/2024 _x000D_30/7/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_29/7/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_29/7/2024:01453200 _x000D_26/7/2024:01453200 _x000D_24/7/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_23/7/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_22/7/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_22/7/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_6/9/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_5/9/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_4/9/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_3/9/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_2/9/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_29/8/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_28/8/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_27/8/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_22/8/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_21/8/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_20/8/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_19/8/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_19/8/2024:01453200 _x000D_16/8/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_15/8/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_14/8/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_13/8/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_12/8/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_9/8/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_8/8/2024:04/07/2024 _x000D_6/8/2024:04/07/2024 _x000D_5/8/2024:04/07/2024 _x000D_2/8/2024:04/07/2024 _x000D_1/8/2024:04/07/2024 _x000D_31/7/2024:04/07/2024 _x000D_31/7/2024:04/07/2024 _x000D_30/7/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_29/7/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_29/7/2024:01453200 _x000D_26/7/2024:01453200 _x000D_24/7/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_23/7/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_22/7/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_22/7/2024:#Update - ECC proposal sent to Vodafone 04/07 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | #Update - ECC proposal sent to Vodafone 04/07 | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366169 | 30016862 | 2.Commissioning | [5 empty] | 0 |  |  |  | 2024-08-16 | [7 empty] | 0
754 | 668985 | 3232 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Nisa | Lochgelly | KY5 8NR | 2024-06-26 | 6/9/2024:#Update - Retailer has confirmed 30/09 and that the retailer will clear the required shelf. _x000D_5/9/2024:#Update - Please confirm new date of 30/09- AM with the retailer and ensure that a shelf near the location of the terminal is completed empty for the engineer to work safely. _x000D_4/9/2024:#Update - Retailer is having some other electrical works completed on site. Retailer would prefer our install to happen after this other works have completed. Action for allwyn, Please can we contact the retailer and find out when the other electrician has completed their work so we can schedule the install for around then. Thanks. _x000D_3/9/2024:#Update - Retailer is having some other electrical works completed on site. Retailer would prefer our install to happen after this other works have completed. Action for allwyn, Please can we contact the retailer and find out when the other electrician has completed their work so we can schedule the install for around then. Thanks. _x000D_2/9/2024:#Update - Retailer is having some other electrical works completed on site. Retailer would prefer our install to happen after this other works have completed. Action for allwyn, Please can we contact the retailer and find out when the other electrician has completed their work so we can schedule the install for around then. Thanks. _x000D_29/8/2024:#Update - Retailer is having some other electrical works completed on site. Retailer would prefer our install to happen after this other works have completed. Action for allwyn, Please can we contact the retailer and find out when the other electrician has completed their work so we can schedule the install for around then. Thanks. _x000D_28/8/2024:#Update - Retailer is having some other electrical works completed on site. Retailer would prefer our install to happen after this other works have completed. Action for allwyn, Please can we contact the retailer and find out when the other electrician has completed their work so we can schedule the install for around then. Thanks. _x000D_27/8/2024:#Update - Retailer is having some other electrical works completed on site. Retailer would prefer our install to happen after this other works have completed. Action for allwyn, Please can we contact the retailer and find out when the other electrician has completed their work so we can schedule the install for around then. Thanks. _x000D_22/8/2024:#Update - Retailer is having some other electrical works completed on site. Retailer would prefer our install to happen after this other works have completed. Action for allwyn, Please can we contact the retailer and find out when the other electrician has completed their work so we can schedule the install for around then. Thanks. _x000D_21/8/2024:#Update - Retailer is having some other electrical works completed on site. Retailer would prefer our install to happen after this other works have completed. Action for allwyn, Please can we contact the retailer and find out when the other electrician has completed their work so we can schedule the install for around then. Thanks. _x000D_20/8/2024:#Update - Retailer is having some other electrical works completed on site. Retailer would prefer our install to happen after this other works have completed. Action for allwyn, Please can we contact the retailer and find out when the other electrician has completed their work so we can schedule the install for around then. Thanks. _x000D_19/8/2024:#Update - Retailer is having some other electrical works completed on site. Retailer would prefer our install to happen after this other works have completed. Action for allwyn, Please can we contact the retailer and find out when the other electrician has completed their work so we can schedule the install for around then. Thanks. _x000D_19/8/2024:01566652 _x000D_16/8/2024:#Update - Retailer is having some other electrical works completed on site. Retailer would prefer our install to happen after this other works have completed. Action for allwyn, Please can we contact the retailer and find out when the other electrician has completed their work so we can schedule the install for around then. Thanks. _x000D_15/8/2024:#Update - Retailer is having some other electrical works completed on site. Retailer would prefer our install to happen after this other works have completed. Action for allwyn, Please can we contact the retailer and find out when the other electrician has completed their work so we can schedule the install for around then. Thanks. _x000D_14/8/2024:Supplier Missed Appointment _x000D_13/8/2024:Supplier Missed Appointment _x000D_12/8/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 19/08/2024.We will continue to provide update as they become available. _x000D_9/8/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 13/08/2024.We will continue to provide update as they become available. _x000D_8/8/2024:Your order requires a survey due to a new network solution required. We will only contact your customer if we need to. You will receive a further update by 29-08-2024. _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:Update: Order Amended _x000D_25/6/2024:Update: Order Amended _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:#Update - Retailer has confirmed 30/09 and that the retailer will clear the required shelf. _x000D_6/9/2024:#Update - Retailer has confirmed 30/09 and that the retailer will clear the required shelf. _x000D_5/9/2024:#Update - Please confirm new date of 30/09- AM with the retailer and ensure that a shelf near the location of the terminal is completed empty for the engineer to work safely. _x000D_4/9/2024:#Update - Retailer is having some other electrical works completed on site. Retailer would prefer our install to happen after this other works have completed. Action for allwyn, Please can we contact the retailer and find out when the other electrician has completed their work so we can schedule the install for around then. Thanks. _x000D_3/9/2024:#Update - Retailer is having some other electrical works completed on site. Retailer would prefer our install to happen after this other works have completed. Action for allwyn, Please can we contact the retailer and find out when the other electrician has completed their work so we can schedule the install for around then. Thanks. _x000D_2/9/2024:#Update - Retailer is having some other electrical works completed on site. Retailer would prefer our install to happen after this other works have completed. Action for allwyn, Please can we contact the retailer and find out when the other electrician has completed their work so we can schedule the install for around then. Thanks. _x000D_29/8/2024:#Update - Retailer is having some other electrical works completed on site. Retailer would prefer our install to happen after this other works have completed. Action for allwyn, Please can we contact the retailer and find out when the other electrician has completed their work so we can schedule the install for around then. Thanks. _x000D_28/8/2024:#Update - Retailer is having some other electrical works completed on site. Retailer would prefer our install to happen after this other works have completed. Action for allwyn, Please can we contact the retailer and find out when the other electrician has completed their work so we can schedule the install for around then. Thanks. _x000D_27/8/2024:#Update - Retailer is having some other electrical works completed on site. Retailer would prefer our install to happen after this other works have completed. Action for allwyn, Please can we contact the retailer and find out when the other electrician has completed their work so we can schedule the install for around then. Thanks. _x000D_22/8/2024:#Update - Retailer is having some other electrical works completed on site. Retailer would prefer our install to happen after this other works have completed. Action for allwyn, Please can we contact the retailer and find out when the other electrician has completed their work so we can schedule the install for around then. Thanks. _x000D_21/8/2024:#Update - Retailer is having some other electrical works completed on site. Retailer would prefer our install to happen after this other works have completed. Action for allwyn, Please can we contact the retailer and find out when the other electrician has completed their work so we can schedule the install for around then. Thanks. _x000D_20/8/2024:#Update - Retailer is having some other electrical works completed on site. Retailer would prefer our install to happen after this other works have completed. Action for allwyn, Please can we contact the retailer and find out when the other electrician has completed their work so we can schedule the install for around then. Thanks. _x000D_19/8/2024:#Update - Retailer is having some other electrical works completed on site. Retailer would prefer our install to happen after this other works have completed. Action for allwyn, Please can we contact the retailer and find out when the other electrician has completed their work so we can schedule the install for around then. Thanks. _x000D_19/8/2024:01566652 _x000D_16/8/2024:#Update - Retailer is having some other electrical works completed on site. Retailer would prefer our install to happen after this other works have completed. Action for allwyn, Please can we contact the retailer and find out when the other electrician has completed their work so we can schedule the install for around then. Thanks. _x000D_15/8/2024:#Update - Retailer is having some other electrical works completed on site. Retailer would prefer our install to happen after this other works have completed. Action for allwyn, Please can we contact the retailer and find out when the other electrician has completed their work so we can schedule the install for around then. Thanks. _x000D_14/8/2024:Supplier Missed Appointment _x000D_13/8/2024:Supplier Missed Appointment _x000D_12/8/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 19/08/2024.We will continue to provide update as they become available. _x000D_9/8/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 13/08/2024.We will continue to provide update as they become available. _x000D_8/8/2024:Your order requires a survey due to a new network solution required. We will only contact your customer if we need to. You will receive a further update by 29-08-2024. _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:Update: Order Amended _x000D_25/6/2024:Update: Order Amended _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | Update: Order Amended | #Update - Retailer has confirmed 30/09 and that the retailer will clear the required shelf. | 2024-06-07 |  |  |  | 5.CSL | VFS1015464 | 30016706 | 1.Provisioning | AM |  | 2024-06-25 | 2024-08-07 |  | 0 | [11 empty] | 0
755 | 270024 | 3236 | Batch 5 Jul24 | Type 1 | FTTP | Spar | BALLYMONEY | BT53 6JD | 2024-06-26 | 27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366021 | 30016648 | 2.Commissioning |  |  | 2024-06-25 | 2024-06-25 | 2024-06-25 | TRUE |  |  |  | 2024-07-26 | [7 empty] | 0
756 | 655442 | 3237 | Batch 5 Jul24 | Type 1 | FTTP | Dulcies News Food and Wine | St Albans | AL1 3NA | 2024-06-26 | 27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366163 | 30016910 | 6.Failed router install |  |  | 2024-06-25 | 2024-06-25 | 2024-06-25 | TRUE |  |  |  | 2024-07-17 |  |  |  | 2024-07-17 | 237004907538 |  | 2024-07-18 | 1
757 | 666653 | 3239 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Willington Post Office | CROOK | DL15 0PE | 2024-06-26 | 6/9/2024:#Update - Allwyn confirmed 28th August. _x000D_5/9/2024:#Update - Allwyn confirmed 28th August. _x000D_4/9/2024:#Update - Allwyn confirmed 28th August. _x000D_3/9/2024:#Update - Allwyn confirmed 28th August. _x000D_2/9/2024:#Update - Allwyn confirmed 28th August. _x000D_29/8/2024:#Update - Allwyn confirmed 28th August. _x000D_28/8/2024:#Update - Allwyn confirmed 28th August. _x000D_27/8/2024:#Update - Allwyn confirmed 28th August. _x000D_22/8/2024:#Update - Allwyn confirmed 28th August. _x000D_21/8/2024:#Update - Allwyn confirmed 28th August. _x000D_20/8/2024:#Update - Allwyn confirmed 28th August. _x000D_19/8/2024:#Update - Allwyn confirmed 28th August. _x000D_19/8/2024:01452115 _x000D_16/8/2024:#Update - Allwyn confirmed 28th August. _x000D_15/8/2024:#Update - Allwyn confirmed 28th August. _x000D_14/8/2024:#Update - Allwyn confirmed 28th August. _x000D_13/8/2024:#Update - Allwyn confirmed 28th August. _x000D_12/8/2024:#Update - Allwyn confirmed 28th August. _x000D_9/8/2024:#Update - Allwyn confirmed 28th August. _x000D_8/8/2024:25/06/2024 _x000D_6/8/2024:25/06/2024 _x000D_5/8/2024:25/06/2024 _x000D_2/8/2024:25/06/2024 _x000D_1/8/2024:25/06/2024 _x000D_31/7/2024:25/06/2024 _x000D_31/7/2024:25/06/2024 _x000D_30/7/2024:#Update - Allwyn confirmed 28th August. _x000D_29/7/2024:#Update - Allwyn confirmed 28th August. _x000D_29/7/2024:01452115 _x000D_26/7/2024:01452115 _x000D_24/7/2024:#Update - Allwyn confirmed 28th August. _x000D_23/7/2024:#Update - Allwyn confirmed 28th August. _x000D_22/7/2024:#Update - Allwyn confirmed 28th August. _x000D_22/7/2024:#Update - Allwyn confirmed 28th August. _x000D_27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn confirmed 28th August. _x000D_6/9/2024:#Update - Allwyn confirmed 28th August. _x000D_5/9/2024:#Update - Allwyn confirmed 28th August. _x000D_4/9/2024:#Update - Allwyn confirmed 28th August. _x000D_3/9/2024:#Update - Allwyn confirmed 28th August. _x000D_2/9/2024:#Update - Allwyn confirmed 28th August. _x000D_29/8/2024:#Update - Allwyn confirmed 28th August. _x000D_28/8/2024:#Update - Allwyn confirmed 28th August. _x000D_27/8/2024:#Update - Allwyn confirmed 28th August. _x000D_22/8/2024:#Update - Allwyn confirmed 28th August. _x000D_21/8/2024:#Update - Allwyn confirmed 28th August. _x000D_20/8/2024:#Update - Allwyn confirmed 28th August. _x000D_19/8/2024:#Update - Allwyn confirmed 28th August. _x000D_19/8/2024:01452115 _x000D_16/8/2024:#Update - Allwyn confirmed 28th August. _x000D_15/8/2024:#Update - Allwyn confirmed 28th August. _x000D_14/8/2024:#Update - Allwyn confirmed 28th August. _x000D_13/8/2024:#Update - Allwyn confirmed 28th August. _x000D_12/8/2024:#Update - Allwyn confirmed 28th August. _x000D_9/8/2024:#Update - Allwyn confirmed 28th August. _x000D_8/8/2024:25/06/2024 _x000D_6/8/2024:25/06/2024 _x000D_5/8/2024:25/06/2024 _x000D_2/8/2024:25/06/2024 _x000D_1/8/2024:25/06/2024 _x000D_31/7/2024:25/06/2024 _x000D_31/7/2024:25/06/2024 _x000D_30/7/2024:#Update - Allwyn confirmed 28th August. _x000D_29/7/2024:#Update - Allwyn confirmed 28th August. _x000D_29/7/2024:01452115 _x000D_26/7/2024:01452115 _x000D_24/7/2024:#Update - Allwyn confirmed 28th August. _x000D_23/7/2024:#Update - Allwyn confirmed 28th August. _x000D_22/7/2024:#Update - Allwyn confirmed 28th August. _x000D_22/7/2024:#Update - Allwyn confirmed 28th August. _x000D_27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | Update: Order Amended | #Update - Allwyn confirmed 28th August. | 2024-06-07 |  |  |  | 5.CSL | VFP2366164 | 30016794 | 1.Provisioning | AM |  | 2024-06-25 | 2024-09-06 |  | 0 | [11 empty] | 0
758 | 467190 | 3240 | Batch 5 Jul24 | Type 1 | FTTP | Southdene News | Liverpool | L32 6QA | 2024-06-26 | 19/7/2024:#Update - Awaiting approval for ECC's _x000D_18/7/2024:#Update - Awaiting approval for ECC's _x000D_17/7/2024:#Update - Awaiting approval for ECC's _x000D_16/7/2024:#Update - Awaiting approval for ECC's _x000D_15/7/2024:#Update - Awaiting approval for ECC's _x000D_12/7/2024:#Update - Awaiting approval for ECC's _x000D_11/7/2024:#Update - Awaiting approval for ECC's _x000D_10/7/2024:#Update - Awaiting approval for ECC's _x000D_9/7/2024:#Update - Awaiting approval for ECC's _x000D_4/7/2024:#update - Awaiitng scope of additional work required from OR. _x000D_3/7/2024:#update - Awaiitng scope of additional work required from OR. _x000D_2/7/2024:0 _x000D_1/7/2024:#update - Awaiitng scope of additional work required from OR. _x000D_27/6/2024:#update - Awaiitng scope of additional work required from OR. _x000D_25/6/2024:#update - Awaiitng scope of additional work required from OR. _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 19/7/2024:#Update - Awaiting approval for ECC's _x000D_18/7/2024:#Update - Awaiting approval for ECC's _x000D_17/7/2024:#Update - Awaiting approval for ECC's _x000D_16/7/2024:#Update - Awaiting approval for ECC's _x000D_15/7/2024:#Update - Awaiting approval for ECC's _x000D_12/7/2024:#Update - Awaiting approval for ECC's _x000D_11/7/2024:#Update - Awaiting approval for ECC's _x000D_10/7/2024:#Update - Awaiting approval for ECC's _x000D_9/7/2024:#Update - Awaiting approval for ECC's _x000D_4/7/2024:#update - Awaiitng scope of additional work required from OR. _x000D_3/7/2024:#update - Awaiitng scope of additional work required from OR. _x000D_2/7/2024:0 _x000D_1/7/2024:#update - Awaiitng scope of additional work required from OR. _x000D_27/6/2024:#update - Awaiitng scope of additional work required from OR. _x000D_25/6/2024:#update - Awaiitng scope of additional work required from OR. _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366162 | 30016981 | 6.Failed router install |  |  | 2024-06-25 | 2024-06-25 | 2024-06-25 | TRUE |  |  |  | 2024-07-25 |  |  |  | 2024-07-25 | 242005008832 |  | 2024-07-26 | 1
759 | 465944 | 3241 | Batch 5 Jul24 | Type 3 | SoGEA/Mobile | SPAR ELTON | Chester | CH2 4LU | 2024-06-26 | 6/9/2024:#Update - downgraded to site type 3 _x000D_5/9/2024:#Update - downgraded to site type 3 _x000D_4/9/2024:#Update - downgraded to site type 3 _x000D_3/9/2024:#Update - downgraded to site type 3 _x000D_2/9/2024:#Update - downgraded to site type 3 _x000D_29/8/2024:#Update - Pushed out to 23/09 to allow more time for ecc approval. _x000D_28/8/2024:#Update - Pushed out to 23/09 to allow more time for ecc approval. _x000D_27/8/2024:#Update - Pushed out to 23/09 to allow more time for ecc approval. _x000D_22/8/2024:#Update - Pushed out to 23/09 to allow more time for ecc approval. _x000D_21/8/2024:#Update - Still awaiting approval- Chased 20/08 _x000D_20/8/2024:#Update - Awaiting approval for ECC's _x000D_19/8/2024:#Update - Awaiting approval for ECC's _x000D_19/8/2024:01452134 _x000D_16/8/2024:#Update - Awaiting approval for ECC's _x000D_15/8/2024:#Update - Awaiting approval for ECC's _x000D_14/8/2024:#Update - Awaiting approval for ECC's _x000D_13/8/2024:#Update - Awaiting approval for ECC's _x000D_12/8/2024:#Update - Awaiting approval for ECC's _x000D_9/8/2024:#Update - Awaiting approval for ECC's _x000D_8/8/2024:04/07/2024 _x000D_6/8/2024:04/07/2024 _x000D_5/8/2024:04/07/2024 _x000D_2/8/2024:04/07/2024 _x000D_1/8/2024:04/07/2024 _x000D_31/7/2024:04/07/2024 _x000D_31/7/2024:04/07/2024 _x000D_30/7/2024:#Update - Awaiting approval for ECC's _x000D_29/7/2024:#Update - Awaiting approval for ECC's _x000D_29/7/2024:01452134 _x000D_26/7/2024:01452134 _x000D_24/7/2024:#Update - Awaiting approval for ECC's _x000D_23/7/2024:#Update - Awaiting approval for ECC's _x000D_22/7/2024:#Update - Awaiting approval for ECC's _x000D_22/7/2024:#Update - Awaiting approval for ECC's _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:Update: Order Amended _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:Update: Order Amended _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:#Update - downgraded to site type 3 _x000D_6/9/2024:#Update - downgraded to site type 3 _x000D_5/9/2024:#Update - downgraded to site type 3 _x000D_4/9/2024:#Update - downgraded to site type 3 _x000D_3/9/2024:#Update - downgraded to site type 3 _x000D_2/9/2024:#Update - downgraded to site type 3 _x000D_29/8/2024:#Update - Pushed out to 23/09 to allow more time for ecc approval. _x000D_28/8/2024:#Update - Pushed out to 23/09 to allow more time for ecc approval. _x000D_27/8/2024:#Update - Pushed out to 23/09 to allow more time for ecc approval. _x000D_22/8/2024:#Update - Pushed out to 23/09 to allow more time for ecc approval. _x000D_21/8/2024:#Update - Still awaiting approval- Chased 20/08 _x000D_20/8/2024:#Update - Awaiting approval for ECC's _x000D_19/8/2024:#Update - Awaiting approval for ECC's _x000D_19/8/2024:01452134 _x000D_16/8/2024:#Update - Awaiting approval for ECC's _x000D_15/8/2024:#Update - Awaiting approval for ECC's _x000D_14/8/2024:#Update - Awaiting approval for ECC's _x000D_13/8/2024:#Update - Awaiting approval for ECC's _x000D_12/8/2024:#Update - Awaiting approval for ECC's _x000D_9/8/2024:#Update - Awaiting approval for ECC's _x000D_8/8/2024:04/07/2024 _x000D_6/8/2024:04/07/2024 _x000D_5/8/2024:04/07/2024 _x000D_2/8/2024:04/07/2024 _x000D_1/8/2024:04/07/2024 _x000D_31/7/2024:04/07/2024 _x000D_31/7/2024:04/07/2024 _x000D_30/7/2024:#Update - Awaiting approval for ECC's _x000D_29/7/2024:#Update - Awaiting approval for ECC's _x000D_29/7/2024:01452134 _x000D_26/7/2024:01452134 _x000D_24/7/2024:#Update - Awaiting approval for ECC's _x000D_23/7/2024:#Update - Awaiting approval for ECC's _x000D_22/7/2024:#Update - Awaiting approval for ECC's _x000D_22/7/2024:#Update - Awaiting approval for ECC's _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:Update: Order Amended _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:Update: Order Amended _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | #Update - downgraded to site type 3 | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015563 | 30016748 | 2.Commissioning | AM |  | 2024-06-25 | 2024-08-23 |  | 0 |  |  |  | 2024-08-21 | [7 empty] | 0
760 | 648701 | 3242 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Family Shopper | Leicester | LE3 9RF | 2024-08-29 | 29/8/2024:#Update - Allwyn confirmed new date of 28/08 - Am appoint. _x000D_28/8/2024:#Update - Allwyn confirmed new date of 28/08 - Am appoint. _x000D_27/8/2024:#Update - Allwyn confirmed new date of 28/08 - Am appoint. _x000D_22/8/2024:#Update - Allwyn confirmed new date of 28/08 - Am appoint. _x000D_21/8/2024:#Update - Allwyn confirmed new date of 28/08 - Am appoint. _x000D_20/8/2024:#Update - Allwyn confirmed new date of 28/08 - Am appoint. _x000D_19/8/2024:#Update - ECC'S approved. Awaiting feedback from OR _x000D_19/8/2024:01452941 _x000D_16/8/2024:#Update - Awaiting ECC approval. _x000D_15/8/2024:#Update - Awaiting ECC approval. _x000D_14/8/2024:#Update- Awaiting information regarding install date. Possible out of hours on a sunday req. Action for allwyn- Please confirm when the rest of the install can happen with the retailer and confirm with me. I will re appoint if this is possible. Awaiting the response before i submit charges for hrs on a sunday. _x000D_13/8/2024:#Update- Awaiting information regarding install date. Possible out of hours on a sunday req. Action for allwyn- Please confirm when the rest of the install can happen with the retailer and confirm with me. I will re appoint if this is possible. Awaiting the response before i submit charges for hrs on a sunday. _x000D_12/8/2024:#Update- Awaiting information regarding install date. Possible out of hours on a sunday req. Action for allwyn- Please confirm when the rest of the install can happen with the retailer and confirm with me. I will re appoint if this is possible. Awaiting the response before i submit charges for hrs on a sunday. _x000D_9/8/2024:#Update- Awaiting information regarding install date. Possible out of hours on a sunday req. Action for allwyn- Please confirm when the rest of the install can happen with the retailer and confirm with me. I will re appoint if this is possible. Awaiting the response before i submit charges for hrs on a sunday. _x000D_8/8/2024:23/07/2024 _x000D_6/8/2024:23/07/2024 _x000D_5/8/2024:23/07/2024 _x000D_2/8/2024:23/07/2024 _x000D_1/8/2024:23/07/2024 _x000D_31/7/2024:23/07/2024 _x000D_31/7/2024:23/07/2024 _x000D_30/7/2024:#Update- Awaiting information regarding install date. Possible out of hours on a sunday req. Action for allwyn- Please confirm when the rest of the install can happen with the retailer and confirm with me. I will re appoint if this is possible. Awaiting the response before i submit charges for hrs on a sunday. _x000D_29/7/2024:#Update- Awaiting information regarding install date. Possible out of hours on a sunday req. Action for allwyn- Please confirm when the rest of the install can happen with the retailer and confirm with me. I will re appoint if this is possible. Awaiting the response before i submit charges for hrs on a sunday. _x000D_29/7/2024:01452941 _x000D_26/7/2024:01452941 _x000D_24/7/2024:#Update- Awaiting information regarding install date. Possible out of hours on a sunday req. Action for allwyn- Please confirm when the rest of the install can happen with the retailer and confirm with me. I will re appoint if this is possible. Awaiting the response before i submit charges for hrs on a sunday. _x000D_23/7/2024:#Update- Awaiting information regarding install date. Possible out of hours on a sunday req. Action for allwyn- Please confirm when the rest of the install can happen with the retailer and confirm with me. I will re appoint if this is possible. Awaiting the response before i submit charges for hrs on a sunday. _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_12/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/07 AM _x000D_11/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/07 AM _x000D_10/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/07 AM _x000D_9/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/07 AM _x000D_4/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/07 AM _x000D_3/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/07 AM _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/07 AM _x000D_27/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/07 AM _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 29/8/2024:#Update - Allwyn confirmed new date of 28/08 - Am appoint. _x000D_28/8/2024:#Update - Allwyn confirmed new date of 28/08 - Am appoint. _x000D_27/8/2024:#Update - Allwyn confirmed new date of 28/08 - Am appoint. _x000D_22/8/2024:#Update - Allwyn confirmed new date of 28/08 - Am appoint. _x000D_21/8/2024:#Update - Allwyn confirmed new date of 28/08 - Am appoint. _x000D_20/8/2024:#Update - Allwyn confirmed new date of 28/08 - Am appoint. _x000D_19/8/2024:#Update - ECC'S approved. Awaiting feedback from OR _x000D_19/8/2024:01452941 _x000D_16/8/2024:#Update - Awaiting ECC approval. _x000D_15/8/2024:#Update - Awaiting ECC approval. _x000D_14/8/2024:#Update- Awaiting information regarding install date. Possible out of hours on a sunday req. Action for allwyn- Please confirm when the rest of the install can happen with the retailer and confirm with me. I will re appoint if this is possible. Awaiting the response before i submit charges for hrs on a sunday. _x000D_13/8/2024:#Update- Awaiting information regarding install date. Possible out of hours on a sunday req. Action for allwyn- Please confirm when the rest of the install can happen with the retailer and confirm with me. I will re appoint if this is possible. Awaiting the response before i submit charges for hrs on a sunday. _x000D_12/8/2024:#Update- Awaiting information regarding install date. Possible out of hours on a sunday req. Action for allwyn- Please confirm when the rest of the install can happen with the retailer and confirm with me. I will re appoint if this is possible. Awaiting the response before i submit charges for hrs on a sunday. _x000D_9/8/2024:#Update- Awaiting information regarding install date. Possible out of hours on a sunday req. Action for allwyn- Please confirm when the rest of the install can happen with the retailer and confirm with me. I will re appoint if this is possible. Awaiting the response before i submit charges for hrs on a sunday. _x000D_8/8/2024:23/07/2024 _x000D_6/8/2024:23/07/2024 _x000D_5/8/2024:23/07/2024 _x000D_2/8/2024:23/07/2024 _x000D_1/8/2024:23/07/2024 _x000D_31/7/2024:23/07/2024 _x000D_31/7/2024:23/07/2024 _x000D_30/7/2024:#Update- Awaiting information regarding install date. Possible out of hours on a sunday req. Action for allwyn- Please confirm when the rest of the install can happen with the retailer and confirm with me. I will re appoint if this is possible. Awaiting the response before i submit charges for hrs on a sunday. _x000D_29/7/2024:#Update- Awaiting information regarding install date. Possible out of hours on a sunday req. Action for allwyn- Please confirm when the rest of the install can happen with the retailer and confirm with me. I will re appoint if this is possible. Awaiting the response before i submit charges for hrs on a sunday. _x000D_29/7/2024:01452941 _x000D_26/7/2024:01452941 _x000D_24/7/2024:#Update- Awaiting information regarding install date. Possible out of hours on a sunday req. Action for allwyn- Please confirm when the rest of the install can happen with the retailer and confirm with me. I will re appoint if this is possible. Awaiting the response before i submit charges for hrs on a sunday. _x000D_23/7/2024:#Update- Awaiting information regarding install date. Possible out of hours on a sunday req. Action for allwyn- Please confirm when the rest of the install can happen with the retailer and confirm with me. I will re appoint if this is possible. Awaiting the response before i submit charges for hrs on a sunday. _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_12/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/07 AM _x000D_11/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/07 AM _x000D_10/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/07 AM _x000D_9/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/07 AM _x000D_4/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/07 AM _x000D_3/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/07 AM _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/07 AM _x000D_27/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/07 AM _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 5.CSL | VFP2366118 | 30016625 | 2.Commissioning | AM |  | 2024-06-25 | 2024-08-21 |  | 0 | [11 empty] | 0
761 | 415945 | 3247 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Anika News | LONDON | N11 3DT | 2024-07-23 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:#Update - Retailer has confirmed re-appointment, _x000D_21/8/2024:#Update - Retailer has confirmed re-appointment, _x000D_20/8/2024:#Update - Retailer has confirmed re-appointment, _x000D_19/8/2024:#Update - Retailer has confirmed re-appointment, _x000D_19/8/2024:01452055 _x000D_16/8/2024:#Update - Retailer has confirmed re-appointment, _x000D_15/8/2024:#Update - Retailer has confirmed re-appointment, _x000D_14/8/2024:#Update - Retailer has confirmed re-appointment, _x000D_13/8/2024:#Update - Retailer has confirmed re-appointment, _x000D_12/8/2024:#Update - Retailer has confirmed re-appointment, _x000D_9/8/2024:#Update - Retailer has confirmed re-appointment, _x000D_8/8/2024:23/07/2024 _x000D_6/8/2024:23/07/2024 _x000D_5/8/2024:23/07/2024 _x000D_2/8/2024:23/07/2024 _x000D_1/8/2024:23/07/2024 _x000D_31/7/2024:23/07/2024 _x000D_31/7/2024:23/07/2024 _x000D_30/7/2024:#Update - Retailer has confirmed re-appointment, _x000D_29/7/2024:#Update - Retailer has confirmed re-appointment, _x000D_29/7/2024:01452055 _x000D_26/7/2024:01452055 _x000D_24/7/2024:#Update - Retailer has confirmed re-appointment, _x000D_23/7/2024:#Update - Supplier delay. Awaiting new appointment- OR retained. _x000D_22/7/2024:#Update - Allwyn confirmed new appointment 22/07 am _x000D_22/7/2024:#Update - Allwyn confirmed new appointment 22/07 am _x000D_27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:#Update - Retailer has confirmed re-appointment, _x000D_21/8/2024:#Update - Retailer has confirmed re-appointment, _x000D_20/8/2024:#Update - Retailer has confirmed re-appointment, _x000D_19/8/2024:#Update - Retailer has confirmed re-appointment, _x000D_19/8/2024:01452055 _x000D_16/8/2024:#Update - Retailer has confirmed re-appointment, _x000D_15/8/2024:#Update - Retailer has confirmed re-appointment, _x000D_14/8/2024:#Update - Retailer has confirmed re-appointment, _x000D_13/8/2024:#Update - Retailer has confirmed re-appointment, _x000D_12/8/2024:#Update - Retailer has confirmed re-appointment, _x000D_9/8/2024:#Update - Retailer has confirmed re-appointment, _x000D_8/8/2024:23/07/2024 _x000D_6/8/2024:23/07/2024 _x000D_5/8/2024:23/07/2024 _x000D_2/8/2024:23/07/2024 _x000D_1/8/2024:23/07/2024 _x000D_31/7/2024:23/07/2024 _x000D_31/7/2024:23/07/2024 _x000D_30/7/2024:#Update - Retailer has confirmed re-appointment, _x000D_29/7/2024:#Update - Retailer has confirmed re-appointment, _x000D_29/7/2024:01452055 _x000D_26/7/2024:01452055 _x000D_24/7/2024:#Update - Retailer has confirmed re-appointment, _x000D_23/7/2024:#Update - Supplier delay. Awaiting new appointment- OR retained. _x000D_22/7/2024:#Update - Allwyn confirmed new appointment 22/07 am _x000D_22/7/2024:#Update - Allwyn confirmed new appointment 22/07 am _x000D_27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | 0 | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015463 | 30016967 | 2.Commissioning | AM |  | 2024-06-25 | 2024-08-19 |  | 0 |  |  |  | 2024-09-18 | [7 empty] | 0
762 | 417729 | 3252 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Sloans Newsagents | DUNGANNON | BT70 1AB | 2024-06-26 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 09:56 _x000D_26/7/2024:22/07/2024 09:56 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:#Update Retailer aware of the new appointment 25/07, AM. _x000D_18/7/2024:#Update Retailer aware of the new appointment 25/07, AM. _x000D_17/7/2024:#Update Retailer aware of the new appointment 25/07, AM. _x000D_16/7/2024:#Update Retailer aware of the new appointment 25/07, AM. _x000D_15/7/2024:#Update Retailer aware of the new appointment 25/07, AM. _x000D_12/7/2024:#Update Retailer aware of the new appointment 25/07, AM. _x000D_11/7/2024:#Update Retailer aware of the new appointment 25/07, AM. _x000D_10/7/2024:#Update Retailer aware of the new appointment 25/07, AM. _x000D_9/7/2024:#Update Retailer aware of the new appointment 25/07, AM. _x000D_4/7/2024:0 _x000D_3/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_2/7/2024:0 _x000D_1/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_27/6/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 09:56 _x000D_26/7/2024:22/07/2024 09:56 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:#Update Retailer aware of the new appointment 25/07, AM. _x000D_18/7/2024:#Update Retailer aware of the new appointment 25/07, AM. _x000D_17/7/2024:#Update Retailer aware of the new appointment 25/07, AM. _x000D_16/7/2024:#Update Retailer aware of the new appointment 25/07, AM. _x000D_15/7/2024:#Update Retailer aware of the new appointment 25/07, AM. _x000D_12/7/2024:#Update Retailer aware of the new appointment 25/07, AM. _x000D_11/7/2024:#Update Retailer aware of the new appointment 25/07, AM. _x000D_10/7/2024:#Update Retailer aware of the new appointment 25/07, AM. _x000D_9/7/2024:#Update Retailer aware of the new appointment 25/07, AM. _x000D_4/7/2024:0 _x000D_3/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_2/7/2024:0 _x000D_1/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_27/6/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  | 5.CSL | VFP2366114 | 30016972 | 1.Provisioning | AM |  | 2024-06-25 | 2024-09-06 |  | 0 | [11 empty] | 0
763 | 481414 | 3254 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Premier | Coventry | CV6 7EU | 2024-08-02 | 5/8/2024:05/07/2024 _x000D_2/8/2024:05/07/2024 _x000D_1/8/2024:05/07/2024 _x000D_31/7/2024:05/07/2024 _x000D_31/7/2024:05/07/2024 _x000D_30/7/2024:#Update Retailer aware of the new appointment 25/07, AM. _x000D_29/7/2024:#Update Retailer aware of the new appointment 25/07, AM. _x000D_29/7/2024:01452525 _x000D_26/7/2024:01452525 _x000D_24/7/2024:#Update Retailer aware of the new appointment 25/07, AM. _x000D_23/7/2024:#Update Retailer aware of the new appointment 25/07, AM. _x000D_22/7/2024:#Update Retailer aware of the new appointment 25/07, AM. _x000D_22/7/2024:#Update Retailer aware of the new appointment 25/07, AM. _x000D_27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 5/8/2024:05/07/2024 _x000D_2/8/2024:05/07/2024 _x000D_1/8/2024:05/07/2024 _x000D_31/7/2024:05/07/2024 _x000D_31/7/2024:05/07/2024 _x000D_30/7/2024:#Update Retailer aware of the new appointment 25/07, AM. _x000D_29/7/2024:#Update Retailer aware of the new appointment 25/07, AM. _x000D_29/7/2024:01452525 _x000D_26/7/2024:01452525 _x000D_24/7/2024:#Update Retailer aware of the new appointment 25/07, AM. _x000D_23/7/2024:#Update Retailer aware of the new appointment 25/07, AM. _x000D_22/7/2024:#Update Retailer aware of the new appointment 25/07, AM. _x000D_22/7/2024:#Update Retailer aware of the new appointment 25/07, AM. _x000D_27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366113 | 30016643 | 2.Commissioning |  |  | 2024-06-25 | 2024-08-01 | 2024-08-01 | TRUE |  |  |  | 2024-08-22 | [7 empty] | 0
764 | 670358 | 3256 | Batch 5 Jul24 | Type 1 | SOGEA | Co Op | BARNSTAPLE | EX31 3BG | 2024-06-26 | 27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015559 | 30016641 | 2.Commissioning |  |  | 2024-06-25 | 2024-06-25 | 2024-06-25 | TRUE |  |  |  | 2024-07-26 | [7 empty] | 0
765 | 421511 | 671 | Batch 3 May24 | Type 1 | FTTP/Mobile | Costsaver Supermarket | SLOUGH | SL2 1DE | 2024-06-07 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:#Update - Fourth Missed appointment - Retailer unaware. Re-appointed for 05/08 -AM - Action for Allwyn : Investigate how we can get this progressed with the retailer. Confirm with retailer 05/08 re-appointment _x000D_21/8/2024:#Update - Fourth Missed appointment - Retailer unaware. Re-appointed for 05/08 -AM - Action for Allwyn : Investigate how we can get this progressed with the retailer. Confirm with retailer 05/08 re-appointment _x000D_20/8/2024:#Update - Fourth Missed appointment - Retailer unaware. Re-appointed for 05/08 -AM - Action for Allwyn : Investigate how we can get this progressed with the retailer. Confirm with retailer 05/08 re-appointment _x000D_19/8/2024:#Update - Fourth Missed appointment - Retailer unaware. Re-appointed for 05/08 -AM - Action for Allwyn : Investigate how we can get this progressed with the retailer. Confirm with retailer 05/08 re-appointment _x000D_19/8/2024:01400388 _x000D_16/8/2024:#Update - Fourth Missed appointment - Retailer unaware. Re-appointed for 05/08 -AM - Action for Allwyn : Investigate how we can get this progressed with the retailer. Confirm with retailer 05/08 re-appointment _x000D_15/8/2024:#Update - Fourth Missed appointment - Retailer unaware. Re-appointed for 05/08 -AM - Action for Allwyn : Investigate how we can get this progressed with the retailer. Confirm with retailer 05/08 re-appointment _x000D_14/8/2024:#Update - Fourth Missed appointment - Retailer unaware. Re-appointed for 05/08 -AM - Action for Allwyn : Investigate how we can get this progressed with the retailer. Confirm with retailer 05/08 re-appointment _x000D_13/8/2024:#Update - Fourth Missed appointment - Retailer unaware. Re-appointed for 05/08 -AM - Action for Allwyn : Investigate how we can get this progressed with the retailer. Confirm with retailer 05/08 re-appointment _x000D_12/8/2024:#Update - Fourth Missed appointment - Retailer unaware. Re-appointed for 05/08 -AM - Action for Allwyn : Investigate how we can get this progressed with the retailer. Confirm with retailer 05/08 re-appointment _x000D_9/8/2024:#Update - Fourth Missed appointment - Retailer unaware. Re-appointed for 05/08 -AM - Action for Allwyn : Investigate how we can get this progressed with the retailer. Confirm with retailer 05/08 re-appointment _x000D_8/8/2024:11/07/2024 _x000D_6/8/2024:11/07/2024 _x000D_5/8/2024:11/07/2024 _x000D_2/8/2024:11/07/2024 _x000D_1/8/2024:11/07/2024 _x000D_31/7/2024:11/07/2024 _x000D_31/7/2024:11/07/2024 _x000D_30/7/2024:#Update - Fourth Missed appointment - Retailer unaware. Re-appointed for 05/08 -AM - Action for Allwyn : Investigate how we can get this progressed with the retailer. Confirm with retailer 05/08 re-appointment _x000D_29/7/2024:#Update - Fourth Missed appointment - Retailer unaware. Re-appointed for 05/08 -AM - Action for Allwyn : Investigate how we can get this progressed with the retailer. Confirm with retailer 05/08 re-appointment _x000D_29/7/2024:01400388 _x000D_26/7/2024:01400388 _x000D_24/7/2024:#Update - Fourth Missed appointment - Retailer unaware. Re-appointed for 05/08 -AM - Action for Allwyn : Investigate how we can get this progressed with the retailer. Confirm with retailer 05/08 re-appointment _x000D_23/7/2024:#Update - Fourth Missed appointment - Retailer unaware. Re-appointed for 05/08 -AM - Action for Allwyn : Investigate how we can get this progressed with the retailer. Confirm with retailer 05/08 re-appointment _x000D_22/7/2024:#Update - Fourth Missed appointment - Retailer unaware. Re-appointed for 05/08 -AM - Action for Allwyn : Investigate how we can get this progressed with the retailer. Confirm with retailer 05/08 re-appointment _x000D_22/7/2024:#Update - Fourth Missed appointment - Retailer unaware. Re-appointed for 05/08 -AM - Action for Allwyn : Investigate how we can get this progressed with the retailer. Confirm with retailer 05/08 re-appointment _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/06 AM _x000D_25/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/06 AM _x000D_24/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/06 AM _x000D_20/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/06 AM _x000D_19/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/06 AM _x000D_18/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/06 AM _x000D_17/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/06 AM _x000D_14/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/06 AM _x000D_13/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/06 AM _x000D_12/6/2024:#Update - Action for Allwyn - Installation has now been amended to 06/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 06/06 is a suitable date. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:#Update - Fourth Missed appointment - Retailer unaware. Re-appointed for 05/08 -AM - Action for Allwyn : Investigate how we can get this progressed with the retailer. Confirm with retailer 05/08 re-appointment _x000D_21/8/2024:#Update - Fourth Missed appointment - Retailer unaware. Re-appointed for 05/08 -AM - Action for Allwyn : Investigate how we can get this progressed with the retailer. Confirm with retailer 05/08 re-appointment _x000D_20/8/2024:#Update - Fourth Missed appointment - Retailer unaware. Re-appointed for 05/08 -AM - Action for Allwyn : Investigate how we can get this progressed with the retailer. Confirm with retailer 05/08 re-appointment _x000D_19/8/2024:#Update - Fourth Missed appointment - Retailer unaware. Re-appointed for 05/08 -AM - Action for Allwyn : Investigate how we can get this progressed with the retailer. Confirm with retailer 05/08 re-appointment _x000D_19/8/2024:01400388 _x000D_16/8/2024:#Update - Fourth Missed appointment - Retailer unaware. Re-appointed for 05/08 -AM - Action for Allwyn : Investigate how we can get this progressed with the retailer. Confirm with retailer 05/08 re-appointment _x000D_15/8/2024:#Update - Fourth Missed appointment - Retailer unaware. Re-appointed for 05/08 -AM - Action for Allwyn : Investigate how we can get this progressed with the retailer. Confirm with retailer 05/08 re-appointment _x000D_14/8/2024:#Update - Fourth Missed appointment - Retailer unaware. Re-appointed for 05/08 -AM - Action for Allwyn : Investigate how we can get this progressed with the retailer. Confirm with retailer 05/08 re-appointment _x000D_13/8/2024:#Update - Fourth Missed appointment - Retailer unaware. Re-appointed for 05/08 -AM - Action for Allwyn : Investigate how we can get this progressed with the retailer. Confirm with retailer 05/08 re-appointment _x000D_12/8/2024:#Update - Fourth Missed appointment - Retailer unaware. Re-appointed for 05/08 -AM - Action for Allwyn : Investigate how we can get this progressed with the retailer. Confirm with retailer 05/08 re-appointment _x000D_9/8/2024:#Update - Fourth Missed appointment - Retailer unaware. Re-appointed for 05/08 -AM - Action for Allwyn : Investigate how we can get this progressed with the retailer. Confirm with retailer 05/08 re-appointment _x000D_8/8/2024:11/07/2024 _x000D_6/8/2024:11/07/2024 _x000D_5/8/2024:11/07/2024 _x000D_2/8/2024:11/07/2024 _x000D_1/8/2024:11/07/2024 _x000D_31/7/2024:11/07/2024 _x000D_31/7/2024:11/07/2024 _x000D_30/7/2024:#Update - Fourth Missed appointment - Retailer unaware. Re-appointed for 05/08 -AM - Action for Allwyn : Investigate how we can get this progressed with the retailer. Confirm with retailer 05/08 re-appointment _x000D_29/7/2024:#Update - Fourth Missed appointment - Retailer unaware. Re-appointed for 05/08 -AM - Action for Allwyn : Investigate how we can get this progressed with the retailer. Confirm with retailer 05/08 re-appointment _x000D_29/7/2024:01400388 _x000D_26/7/2024:01400388 _x000D_24/7/2024:#Update - Fourth Missed appointment - Retailer unaware. Re-appointed for 05/08 -AM - Action for Allwyn : Investigate how we can get this progressed with the retailer. Confirm with retailer 05/08 re-appointment _x000D_23/7/2024:#Update - Fourth Missed appointment - Retailer unaware. Re-appointed for 05/08 -AM - Action for Allwyn : Investigate how we can get this progressed with the retailer. Confirm with retailer 05/08 re-appointment _x000D_22/7/2024:#Update - Fourth Missed appointment - Retailer unaware. Re-appointed for 05/08 -AM - Action for Allwyn : Investigate how we can get this progressed with the retailer. Confirm with retailer 05/08 re-appointment _x000D_22/7/2024:#Update - Fourth Missed appointment - Retailer unaware. Re-appointed for 05/08 -AM - Action for Allwyn : Investigate how we can get this progressed with the retailer. Confirm with retailer 05/08 re-appointment _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/06 AM _x000D_25/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/06 AM _x000D_24/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/06 AM _x000D_20/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/06 AM _x000D_19/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/06 AM _x000D_18/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/06 AM _x000D_17/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/06 AM _x000D_14/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/06 AM _x000D_13/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/06 AM _x000D_12/6/2024:#Update - Action for Allwyn - Installation has now been amended to 06/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 06/06 is a suitable date. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | 0 | 2024-05-20 |  |  |  | 3.Allwyn to arrange rtr install | VFP2300868 | 30013561 | 2.Commissioning | AM |  | 2024-05-17 | 2024-08-15 |  | 0 |  |  |  | 2024-09-18 | [7 empty] | 0
766 | 651852 | 1506 | Batch 4 Jun24 | Type 1 | FTTP/Mobile | Centra | Draperstown | BT45 7AA | 2024-06-07 | 6/9/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_5/9/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_4/9/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_3/9/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_2/9/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_29/8/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_28/8/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_27/8/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_22/8/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_21/8/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_20/8/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_19/8/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_19/8/2024:01453833 _x000D_16/8/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_15/8/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_14/8/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_13/8/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_12/8/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_9/8/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_8/8/2024:28/06/2024 _x000D_6/8/2024:28/06/2024 _x000D_5/8/2024:28/06/2024 _x000D_2/8/2024:28/06/2024 _x000D_1/8/2024:28/06/2024 _x000D_31/7/2024:28/06/2024 _x000D_31/7/2024:28/06/2024 _x000D_30/7/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_29/7/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_29/7/2024:01453833 _x000D_26/7/2024:01453833 _x000D_24/7/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_23/7/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_22/7/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_22/7/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_16/7/2024:#Update Upgrade and OOH sent to VF. _x000D_15/7/2024:#Update Upgrade and OOH sent to VF. _x000D_12/7/2024:#Update Upgrade and OOH sent to VF. _x000D_11/7/2024:#Update Upgrade and OOH sent to VF. _x000D_10/7/2024:#Update Upgrade and OOH sent to VF. _x000D_9/7/2024:#Update Upgrade and OOH sent to VF. _x000D_4/7/2024:#Update Upgrade and OOH sent to VF. _x000D_3/7/2024:#Update Upgrade and OOH sent to VF. _x000D_2/7/2024:0 _x000D_1/7/2024:Your order has been delayed due to our suppliers being unable to complete the job in required time frame, order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 03/07/2024 _x000D_27/6/2024:Delay on Engineer activities. Supplier will arrange new appointment _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_6/9/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_5/9/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_4/9/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_3/9/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_2/9/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_29/8/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_28/8/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_27/8/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_22/8/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_21/8/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_20/8/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_19/8/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_19/8/2024:01453833 _x000D_16/8/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_15/8/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_14/8/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_13/8/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_12/8/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_9/8/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_8/8/2024:28/06/2024 _x000D_6/8/2024:28/06/2024 _x000D_5/8/2024:28/06/2024 _x000D_2/8/2024:28/06/2024 _x000D_1/8/2024:28/06/2024 _x000D_31/7/2024:28/06/2024 _x000D_31/7/2024:28/06/2024 _x000D_30/7/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_29/7/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_29/7/2024:01453833 _x000D_26/7/2024:01453833 _x000D_24/7/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_23/7/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_22/7/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_22/7/2024:#UPDATE: Sales query. Awaiting further updates/ action from OR _x000D_16/7/2024:#Update Upgrade and OOH sent to VF. _x000D_15/7/2024:#Update Upgrade and OOH sent to VF. _x000D_12/7/2024:#Update Upgrade and OOH sent to VF. _x000D_11/7/2024:#Update Upgrade and OOH sent to VF. _x000D_10/7/2024:#Update Upgrade and OOH sent to VF. _x000D_9/7/2024:#Update Upgrade and OOH sent to VF. _x000D_4/7/2024:#Update Upgrade and OOH sent to VF. _x000D_3/7/2024:#Update Upgrade and OOH sent to VF. _x000D_2/7/2024:0 _x000D_1/7/2024:Your order has been delayed due to our suppliers being unable to complete the job in required time frame, order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 03/07/2024 _x000D_27/6/2024:Delay on Engineer activities. Supplier will arrange new appointment _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | #UPDATE: Sales query. Awaiting further updates/ action from OR | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFP2369642 | 30017053 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
767 | 486900 | 1543 | Batch 4 Jun24 | Type 1 | FTTP | Spar Stores | Birmingham | B5 4SG | 2024-06-07 | 27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:Your order has been delayed. Line plant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 14/06/2024.We will continue to provide update as they become available. CSL Note: Invalid appointme _x000D_10/6/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 11/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_7/6/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 11/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/6/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 07/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/6/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 07/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/6/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 07/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:Your order has been delayed. Line plant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 14/06/2024.We will continue to provide update as they become available. CSL Note: Invalid appointme _x000D_10/6/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 11/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_7/6/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 11/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/6/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 07/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/6/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 07/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/6/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 07/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2369643 | 30017056 | 6.Failed router install | AM |  | 2024-06-26 | 2024-06-26 | 2024-06-27 | TRUE |  |  |  | 2024-07-19 |  |  |  | 2024-07-19 | 237004907637 |  | 2024-07-23 | 1
768 | 623648 | 1852 | Batch 4 Jun24 | Type 1 | SoGEA/Mobile | Spar | Penrhyndeudraeth | LL48 6AB | 2024-06-07 | 6/9/2024:#Update - Awaiting ECC approval. _x000D_5/9/2024:#Update - Awaiting ECC approval. _x000D_4/9/2024:#Update - Awaiting ECC approval. _x000D_3/9/2024:#Update - Awaiting ECC approval. _x000D_2/9/2024:#Update - Awaiting ECC approval. _x000D_29/8/2024:#Update - Awaiting ECC approval. _x000D_28/8/2024:#Update - Awaiting ECC approval. _x000D_27/8/2024:#Update - Awaiting ECC approval. _x000D_22/8/2024:#Update - Awaiting ECC approval. _x000D_21/8/2024:#Update - Awaiting ECC approval. _x000D_20/8/2024:#Update - Awaiting ECC approval. _x000D_19/8/2024:#Update - Awaiting ECC approval. _x000D_19/8/2024:01422539 _x000D_16/8/2024:#Update - Awaiting ECC approval. _x000D_15/8/2024:#Update - Awaiting ECC approval. _x000D_14/8/2024:#Update - Awaiting ECC approval. _x000D_13/8/2024:#Update - Awaiting ECC approval. _x000D_12/8/2024:#Update - Awaiting ECC approval. _x000D_9/8/2024:#Update - Awaiting ECC approval. _x000D_8/8/2024:31/07/2024 _x000D_6/8/2024:31/07/2024 _x000D_5/8/2024:31/07/2024 _x000D_2/8/2024:31/07/2024 _x000D_1/8/2024:31/07/2024 _x000D_31/7/2024:Update: Order Amended _x000D_31/7/2024:37038 _x000D_30/7/2024:Update: Order Amended _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:25/07/2024 10:26 _x000D_26/7/2024:25/07/2024 10:26 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:Your order has been delayed due to wayleave being required and our suppliers have given us a review date of 05/07/2024. We will continue to provide update as they become available. _x000D_27/6/2024:Your order has been delayed due to wayleave being required and our suppliers have given us a review date of 05/07/2024. We will continue to provide update as they become available. _x000D_25/6/2024:Your order has been delayed due to wayleave being required and our suppliers have given us a review date of 05/07/2024. We will continue to provide update as they become available. _x000D_24/6/2024:Your order has been delayed due to wayleave being required and our suppliers have given us a review date of 25/06/2024. We will continue to provide update as they become available. _x000D_20/6/2024:Your order has been delayed due to wayleave being required and our suppliers have given us a review date of 21/06/2024. We will continue to provide update as they become available. _x000D_19/6/2024:Your order has been delayed due to wayleave being required and our suppliers have given us a review date of 21/06/2024. We will continue to provide update as they become available. _x000D_18/6/2024:Your order has been delayed due to wayleave being required and our suppliers have given us a review date of 21/06/2024. We will continue to provide update as they become available. _x000D_17/6/2024:Your order has been delayed due to wayleave being required and our suppliers have given us a review date of 21/06/2024. We will continue to provide update as they become available. _x000D_14/6/2024:Your order has been delayed due to wayleave being required and our suppliers have given us a review date of 21/06/2024. We will continue to provide update as they become available. _x000D_13/6/2024:Your order has been delayed due to wayleave being required and our suppliers have given us a review date of 14/06/2024.. We will continue to provide update as they become available. _x000D_12/6/2024:Your order has been delayed due to wayleave being required and our suppliers have given us a review date of 14/06/2024.. We will continue to provide update as they become available. _x000D_10/6/2024:0 _x000D_7/6/2024:Your order has been delayed due to wayleave being required and our suppliers have given us a review date of 12/06/2024.. We will continue to provide update as they become available. _x000D_6/6/2024:Your order has been delayed due to wayleave being required and our suppliers have given us a review date of 12/06/2024.. We will continue to provide update as they become available. _x000D_5/6/2024:Your order has been delayed due to wayleave being required and our suppliers have given us a review date of 12/06/2024.. We will continue to provide update as they become available. _x000D_4/6/2024:Your order has been delayed due to wayleave being required and our suppliers have given us a review date of 12/06/2024.. We will continue to provide update as they become available. _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 12/06/2024. We will continue to provide update as they become available. _x000D_28/5/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 12/06/2024. We will continue to provide update as they become available. _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 9/9/2024:#Update - Awaiting ECC approval. _x000D_6/9/2024:#Update - Awaiting ECC approval. _x000D_5/9/2024:#Update - Awaiting ECC approval. _x000D_4/9/2024:#Update - Awaiting ECC approval. _x000D_3/9/2024:#Update - Awaiting ECC approval. _x000D_2/9/2024:#Update - Awaiting ECC approval. _x000D_29/8/2024:#Update - Awaiting ECC approval. _x000D_28/8/2024:#Update - Awaiting ECC approval. _x000D_27/8/2024:#Update - Awaiting ECC approval. _x000D_22/8/2024:#Update - Awaiting ECC approval. _x000D_21/8/2024:#Update - Awaiting ECC approval. _x000D_20/8/2024:#Update - Awaiting ECC approval. _x000D_19/8/2024:#Update - Awaiting ECC approval. _x000D_19/8/2024:01422539 _x000D_16/8/2024:#Update - Awaiting ECC approval. _x000D_15/8/2024:#Update - Awaiting ECC approval. _x000D_14/8/2024:#Update - Awaiting ECC approval. _x000D_13/8/2024:#Update - Awaiting ECC approval. _x000D_12/8/2024:#Update - Awaiting ECC approval. _x000D_9/8/2024:#Update - Awaiting ECC approval. _x000D_8/8/2024:31/07/2024 _x000D_6/8/2024:31/07/2024 _x000D_5/8/2024:31/07/2024 _x000D_2/8/2024:31/07/2024 _x000D_1/8/2024:31/07/2024 _x000D_31/7/2024:Update: Order Amended _x000D_31/7/2024:37038 _x000D_30/7/2024:Update: Order Amended _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:25/07/2024 10:26 _x000D_26/7/2024:25/07/2024 10:26 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:Your order has been delayed due to wayleave being required and our suppliers have given us a review date of 05/07/2024. We will continue to provide update as they become available. _x000D_27/6/2024:Your order has been delayed due to wayleave being required and our suppliers have given us a review date of 05/07/2024. We will continue to provide update as they become available. _x000D_25/6/2024:Your order has been delayed due to wayleave being required and our suppliers have given us a review date of 05/07/2024. We will continue to provide update as they become available. _x000D_24/6/2024:Your order has been delayed due to wayleave being required and our suppliers have given us a review date of 25/06/2024. We will continue to provide update as they become available. _x000D_20/6/2024:Your order has been delayed due to wayleave being required and our suppliers have given us a review date of 21/06/2024. We will continue to provide update as they become available. _x000D_19/6/2024:Your order has been delayed due to wayleave being required and our suppliers have given us a review date of 21/06/2024. We will continue to provide update as they become available. _x000D_18/6/2024:Your order has been delayed due to wayleave being required and our suppliers have given us a review date of 21/06/2024. We will continue to provide update as they become available. _x000D_17/6/2024:Your order has been delayed due to wayleave being required and our suppliers have given us a review date of 21/06/2024. We will continue to provide update as they become available. _x000D_14/6/2024:Your order has been delayed due to wayleave being required and our suppliers have given us a review date of 21/06/2024. We will continue to provide update as they become available. _x000D_13/6/2024:Your order has been delayed due to wayleave being required and our suppliers have given us a review date of 14/06/2024.. We will continue to provide update as they become available. _x000D_12/6/2024:Your order has been delayed due to wayleave being required and our suppliers have given us a review date of 14/06/2024.. We will continue to provide update as they become available. _x000D_10/6/2024:0 _x000D_7/6/2024:Your order has been delayed due to wayleave being required and our suppliers have given us a review date of 12/06/2024.. We will continue to provide update as they become available. _x000D_6/6/2024:Your order has been delayed due to wayleave being required and our suppliers have given us a review date of 12/06/2024.. We will continue to provide update as they become available. _x000D_5/6/2024:Your order has been delayed due to wayleave being required and our suppliers have given us a review date of 12/06/2024.. We will continue to provide update as they become available. _x000D_4/6/2024:Your order has been delayed due to wayleave being required and our suppliers have given us a review date of 12/06/2024.. We will continue to provide update as they become available. _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 12/06/2024. We will continue to provide update as they become available. _x000D_28/5/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 12/06/2024. We will continue to provide update as they become available. _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | Update: Order Amended | #Update - Awaiting ECC approval. | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFS1022071 | 30015987 | 1.Provisioning | AM |  | 2024-06-26 | 2024-09-09 |  | 0 | [11 empty] | 0
769 | 664900 | 1735 | Batch 4 Jun24 | Type 1 | FTTP/Mobile | THE FENDER PO | Prenton | CH43 7ZJ | 2024-06-07 | 6/9/2024:#Update - permission to work form has been signed by landlord. Step-1 work is in progress as dig work is required and further updates will follow _x000D_5/9/2024:#Update - permission to work form has been signed by landlord. Step-1 work is in progress as dig work is required and further updates will follow _x000D_4/9/2024:#Update - permission to work form has been signed by landlord. Step-1 work is in progress as dig work is required and further updates will follow _x000D_3/9/2024:#Update - this order has been delayed as civil work required. We will continue to provide update as they become available. _x000D_2/9/2024:#Update - this order has been delayed as civil work required. We will continue to provide update as they become available. _x000D_29/8/2024:#Update - this order has been delayed as civil work required. We will continue to provide update as they become available. _x000D_28/8/2024:#Update - Order cancelled down as we did not receive PTW back from retailer in time. Order has been reraised and the PTW will be sent again to the retailer to authorise _x000D_27/8/2024:#Update - Order cancelled down as we did not receive PTW back from retailer in time. Order has been reraised and the PTW will be sent again to the retailer to authorise _x000D_22/8/2024:#Update - Order cancelled down as we did not receive PTW back from retailer in time. Order has been reraised and the PTW will be sent again to the retailer to authorise _x000D_21/8/2024:#Update - Order cancelled down as we did not receive PTW back from retailer in time. Order has been reraised and the PTW will be sent again to the retailer to authorise _x000D_20/8/2024:#Update - PTW form required from retailer - Allwyn deployment team are chasing this so we can progress the order _x000D_19/8/2024:#Update - PTW form required from retailer - Allwyn deployment team are chasing this so we can progress the order _x000D_19/8/2024:01419115 _x000D_16/8/2024:#Update - PTW form required from retailer - Allwyn deployment team are chasing this so we can progress the order _x000D_15/8/2024:#Update - PTW form required from retailer - Allwyn deployment team are chasing this so we can progress the order _x000D_14/8/2024:#Update - PTW form required from retailer - Allwyn deployment team are chasing this so we can progress the order _x000D_13/8/2024:#Update - PTW form required from retailer - Allwyn deployment team are chasing this so we can progress the order _x000D_12/8/2024:#Update - PTW form required from retailer - Allwyn deployment team are chasing this so we can progress the order _x000D_9/8/2024:#Update - PTW form required from retailer - Allwyn deployment team are chasing this so we can progress the order _x000D_8/8/2024:01/08/2024 _x000D_6/8/2024:01/08/2024 _x000D_5/8/2024:01/08/2024 _x000D_2/8/2024:01/08/2024 _x000D_1/8/2024:01/08/2024 _x000D_31/7/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_30/7/2024:#Update - This order requires a PTW (permission to work) to be signed. OR have attempted to contact the Grantor(s) for a signature. PTW is required: dig required outside shop to intercept duct - further updates to follow _x000D_29/7/2024:#Update - This order requires a PTW (permission to work) to be signed. OR have attempted to contact the Grantor(s) for a signature. PTW is required: dig required outside shop to intercept duct - further updates to follow _x000D_29/7/2024:01419115 _x000D_26/7/2024:01419115 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:#Update - permission to work form has been signed by landlord. Step-1 work is in progress as dig work is required and further updates will follow _x000D_6/9/2024:#Update - permission to work form has been signed by landlord. Step-1 work is in progress as dig work is required and further updates will follow _x000D_5/9/2024:#Update - permission to work form has been signed by landlord. Step-1 work is in progress as dig work is required and further updates will follow _x000D_4/9/2024:#Update - permission to work form has been signed by landlord. Step-1 work is in progress as dig work is required and further updates will follow _x000D_3/9/2024:#Update - this order has been delayed as civil work required. We will continue to provide update as they become available. _x000D_2/9/2024:#Update - this order has been delayed as civil work required. We will continue to provide update as they become available. _x000D_29/8/2024:#Update - this order has been delayed as civil work required. We will continue to provide update as they become available. _x000D_28/8/2024:#Update - Order cancelled down as we did not receive PTW back from retailer in time. Order has been reraised and the PTW will be sent again to the retailer to authorise _x000D_27/8/2024:#Update - Order cancelled down as we did not receive PTW back from retailer in time. Order has been reraised and the PTW will be sent again to the retailer to authorise _x000D_22/8/2024:#Update - Order cancelled down as we did not receive PTW back from retailer in time. Order has been reraised and the PTW will be sent again to the retailer to authorise _x000D_21/8/2024:#Update - Order cancelled down as we did not receive PTW back from retailer in time. Order has been reraised and the PTW will be sent again to the retailer to authorise _x000D_20/8/2024:#Update - PTW form required from retailer - Allwyn deployment team are chasing this so we can progress the order _x000D_19/8/2024:#Update - PTW form required from retailer - Allwyn deployment team are chasing this so we can progress the order _x000D_19/8/2024:01419115 _x000D_16/8/2024:#Update - PTW form required from retailer - Allwyn deployment team are chasing this so we can progress the order _x000D_15/8/2024:#Update - PTW form required from retailer - Allwyn deployment team are chasing this so we can progress the order _x000D_14/8/2024:#Update - PTW form required from retailer - Allwyn deployment team are chasing this so we can progress the order _x000D_13/8/2024:#Update - PTW form required from retailer - Allwyn deployment team are chasing this so we can progress the order _x000D_12/8/2024:#Update - PTW form required from retailer - Allwyn deployment team are chasing this so we can progress the order _x000D_9/8/2024:#Update - PTW form required from retailer - Allwyn deployment team are chasing this so we can progress the order _x000D_8/8/2024:01/08/2024 _x000D_6/8/2024:01/08/2024 _x000D_5/8/2024:01/08/2024 _x000D_2/8/2024:01/08/2024 _x000D_1/8/2024:01/08/2024 _x000D_31/7/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_30/7/2024:#Update - This order requires a PTW (permission to work) to be signed. OR have attempted to contact the Grantor(s) for a signature. PTW is required: dig required outside shop to intercept duct - further updates to follow _x000D_29/7/2024:#Update - This order requires a PTW (permission to work) to be signed. OR have attempted to contact the Grantor(s) for a signature. PTW is required: dig required outside shop to intercept duct - further updates to follow _x000D_29/7/2024:01419115 _x000D_26/7/2024:01419115 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | Informational - External visit has been completed | #Update - permission to work form has been signed by landlord. Step-1 work is in progress as dig work is required and further updates will follow | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFP2353446 | 30015945 | 1.Provisioning | AM |  | 2024-06-26 | 2024-08-27 |  | 0 | [11 empty] | 0
770 | 646657 | 3259 | Batch 5 Jul24 | Type 1 | FTTP | Premier Express | Norwich | NR3 1AA |  | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:Supplier Delay: KCI-3 (Order Completed) Delayed in Processing. _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:Supplier Delay: KCI-3 (Order Completed) Delayed in Processing. _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366112 | 30016688 | 2.Commissioning |  |  | 2024-06-26 | 2024-06-26 | 2024-06-27 | TRUE |  |  |  | 2024-07-17 | [7 empty] | 0
771 | 437620 | 3260 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Nisa Local | MANCHESTER | M23 1JP |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:02 _x000D_26/7/2024:22/07/2024 10:02 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:02 _x000D_26/7/2024:22/07/2024 10:02 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2366110 | 30017003 | 1.Provisioning | AM |  | 2024-06-26 | 2024-09-06 |  | 0 | [11 empty] | 0
772 | 469135 | 3261 | Batch 5 Jul24 | Type 1 | SOGEA | Go Local Extra | Rochdale | OL16 4SZ |  | 2/7/2024:0 _x000D_1/7/2024:#Update - due to this being external works where over 150m of cabling is required this will be completed by Openreach. A Line plant Survey activity has been raised - will continue to monitor this order and provide a further update accordingly _x000D_27/6/2024:Supplier Delay: Network Planning issue, please await for further details. _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 2/7/2024:0 _x000D_1/7/2024:#Update - due to this being external works where over 150m of cabling is required this will be completed by Openreach. A Line plant Survey activity has been raised - will continue to monitor this order and provide a further update accordingly _x000D_27/6/2024:Supplier Delay: Network Planning issue, please await for further details. _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015556 | 30017014 | 2.Commissioning |  |  | 2024-06-26 | 2024-06-26 | 2024-06-26 | TRUE |  |  |  | 2024-07-20 | [7 empty] | 0
773 | 654258 | 3262 | Batch 5 Jul24 | Type 1 | SOGEA | WRL Gosport | Bridgemary, Gosport | PO13 0HY |  | 27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015557 | 30016677 | 2.Commissioning |  |  | 2024-06-26 | 2024-06-26 | 2024-06-28 | TRUE |  |  |  | 2024-07-24 | [7 empty] | 0
774 | 429207 | 3266 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Spar | BANGOR | BT19 6JR |  | 6/9/2024:#Update reappointed 29/08 AM. _x000D_5/9/2024:#Update reappointed 29/08 AM. _x000D_4/9/2024:#Update reappointed 29/08 AM. _x000D_3/9/2024:#Update reappointed 29/08 AM. _x000D_2/9/2024:#Update reappointed 29/08 AM. _x000D_29/8/2024:#Update reappointed 29/08 AM. _x000D_28/8/2024:#Update reappointed 29/08 AM. _x000D_27/8/2024:#Update reappointed 29/08 AM. _x000D_22/8/2024:#Update reappointed 29/08 AM. _x000D_21/8/2024:#Update reappointed 29/08 AM. _x000D_20/8/2024:#Update reappointed 29/08 AM. _x000D_19/8/2024:#Update reappointed 29/08 AM. _x000D_19/8/2024:01453603 _x000D_16/8/2024:#Update reappointed 29/08 AM. _x000D_15/8/2024:#Update reappointed 29/08 AM. _x000D_14/8/2024:#Update reappointed 29/08 AM. _x000D_13/8/2024:#Update reappointed 29/08 AM. _x000D_12/8/2024:#Update reappointed 29/08 AM. _x000D_9/8/2024:#Update reappointed 29/08 AM. _x000D_8/8/2024:02/07/2024 _x000D_6/8/2024:02/07/2024 _x000D_5/8/2024:02/07/2024 _x000D_2/8/2024:02/07/2024 _x000D_1/8/2024:02/07/2024 _x000D_31/7/2024:02/07/2024 _x000D_31/7/2024:02/07/2024 _x000D_30/7/2024:#Update reappointed 29/08 AM. _x000D_29/7/2024:#Update reappointed 29/08 AM. _x000D_29/7/2024:01453603 _x000D_26/7/2024:01453603 _x000D_24/7/2024:#Update reappointed 29/08 AM. _x000D_23/7/2024:#Update reappointed 29/08 AM. _x000D_22/7/2024:#Update reappointed 29/08 AM. _x000D_22/7/2024:#Update reappointed 29/08 AM. _x000D_19/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_18/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_17/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_16/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_15/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_12/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_11/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_10/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_9/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_4/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_3/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_27/6/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_25/6/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_24/6/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_20/6/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_19/6/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_18/6/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:#Update reappointed 29/08 AM. _x000D_6/9/2024:#Update reappointed 29/08 AM. _x000D_5/9/2024:#Update reappointed 29/08 AM. _x000D_4/9/2024:#Update reappointed 29/08 AM. _x000D_3/9/2024:#Update reappointed 29/08 AM. _x000D_2/9/2024:#Update reappointed 29/08 AM. _x000D_29/8/2024:#Update reappointed 29/08 AM. _x000D_28/8/2024:#Update reappointed 29/08 AM. _x000D_27/8/2024:#Update reappointed 29/08 AM. _x000D_22/8/2024:#Update reappointed 29/08 AM. _x000D_21/8/2024:#Update reappointed 29/08 AM. _x000D_20/8/2024:#Update reappointed 29/08 AM. _x000D_19/8/2024:#Update reappointed 29/08 AM. _x000D_19/8/2024:01453603 _x000D_16/8/2024:#Update reappointed 29/08 AM. _x000D_15/8/2024:#Update reappointed 29/08 AM. _x000D_14/8/2024:#Update reappointed 29/08 AM. _x000D_13/8/2024:#Update reappointed 29/08 AM. _x000D_12/8/2024:#Update reappointed 29/08 AM. _x000D_9/8/2024:#Update reappointed 29/08 AM. _x000D_8/8/2024:02/07/2024 _x000D_6/8/2024:02/07/2024 _x000D_5/8/2024:02/07/2024 _x000D_2/8/2024:02/07/2024 _x000D_1/8/2024:02/07/2024 _x000D_31/7/2024:02/07/2024 _x000D_31/7/2024:02/07/2024 _x000D_30/7/2024:#Update reappointed 29/08 AM. _x000D_29/7/2024:#Update reappointed 29/08 AM. _x000D_29/7/2024:01453603 _x000D_26/7/2024:01453603 _x000D_24/7/2024:#Update reappointed 29/08 AM. _x000D_23/7/2024:#Update reappointed 29/08 AM. _x000D_22/7/2024:#Update reappointed 29/08 AM. _x000D_22/7/2024:#Update reappointed 29/08 AM. _x000D_19/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_18/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_17/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_16/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_15/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_12/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_11/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_10/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_9/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_4/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_3/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_27/6/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_25/6/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_24/6/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_20/6/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_19/6/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_18/6/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | Update: Order Amended | #Update reappointed 29/08 AM. | 2024-06-07 |  |  |  |  | VFP2366017 | 30016713 | 1.Provisioning | AM |  | 2024-06-26 | 2024-09-06 |  | 0 | [11 empty] | 0
775 | 449652 | 3272 | Batch 5 Jul24 | Type 1 | FTTP | Go Local Wybourn News and Booze | SHEFFIELD | S2 5EL |  | 19/7/2024:#Update - Awaiting understanding of Engineer notes, cannot run the line through fireproof ceiling. _x000D_18/7/2024:#Update - Awaiting understanding of Engineer notes, cannot run the line through fireproof ceiling. _x000D_17/7/2024:#Update - Awaiting understanding of Engineer notes, cannot run the line through fireproof ceiling. _x000D_16/7/2024:#Update - Awaiting understanding of Engineer notes, cannot run the line through fireproof ceiling. _x000D_15/7/2024:#Update - Awaiting understanding of Engineer notes, cannot run the line through fireproof ceiling. _x000D_12/7/2024:#Update - Awaiting understanding of Engineer notes, cannot run the line through fireproof ceiling. _x000D_11/7/2024:#Update - Awaiting understanding of Engineer notes, cannot run the line through fireproof ceiling. _x000D_10/7/2024:#Update - Awaiting understanding of Engineer notes, cannot run the line through fireproof ceiling. _x000D_9/7/2024:#Update - Awaiting understanding of Engineer notes, cannot run the line through fireproof ceiling. _x000D_4/7/2024:#Update - Awaiting understanding of Engineer notes, cannot run the line through fireproof ceiling. _x000D_3/7/2024:#Update - Awaiting understanding of Engineer notes, cannot run the line through fireproof ceiling. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Awaiting understanding of Engineer notes, cannot run the line through fireproof ceiling. _x000D_27/6/2024:Supplier Delay: Unable to complete work in the allocated appointment slot, please await further details. _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 19/7/2024:#Update - Awaiting understanding of Engineer notes, cannot run the line through fireproof ceiling. _x000D_18/7/2024:#Update - Awaiting understanding of Engineer notes, cannot run the line through fireproof ceiling. _x000D_17/7/2024:#Update - Awaiting understanding of Engineer notes, cannot run the line through fireproof ceiling. _x000D_16/7/2024:#Update - Awaiting understanding of Engineer notes, cannot run the line through fireproof ceiling. _x000D_15/7/2024:#Update - Awaiting understanding of Engineer notes, cannot run the line through fireproof ceiling. _x000D_12/7/2024:#Update - Awaiting understanding of Engineer notes, cannot run the line through fireproof ceiling. _x000D_11/7/2024:#Update - Awaiting understanding of Engineer notes, cannot run the line through fireproof ceiling. _x000D_10/7/2024:#Update - Awaiting understanding of Engineer notes, cannot run the line through fireproof ceiling. _x000D_9/7/2024:#Update - Awaiting understanding of Engineer notes, cannot run the line through fireproof ceiling. _x000D_4/7/2024:#Update - Awaiting understanding of Engineer notes, cannot run the line through fireproof ceiling. _x000D_3/7/2024:#Update - Awaiting understanding of Engineer notes, cannot run the line through fireproof ceiling. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Awaiting understanding of Engineer notes, cannot run the line through fireproof ceiling. _x000D_27/6/2024:Supplier Delay: Unable to complete work in the allocated appointment slot, please await further details. _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366108 | 30016948 | 6.Failed router install |  |  | 2024-06-26 | 2024-06-26 | 2024-06-26 | TRUE |  |  |  | 2024-07-20 |  |  |  | 2024-07-20 | 238004924228 |  | 2024-07-23 | 1
776 | 471000 | 3273 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Premier | Doncaster | DN5 0EU |  | 9/8/2024:#Update - Retailer has confirmed new date for 05/08 - Openreach have allocated the hoist for the appointment. _x000D_8/8/2024:24/07/2024 _x000D_6/8/2024:24/07/2024 _x000D_5/8/2024:24/07/2024 _x000D_2/8/2024:24/07/2024 _x000D_1/8/2024:24/07/2024 _x000D_31/7/2024:24/07/2024 _x000D_31/7/2024:24/07/2024 _x000D_30/7/2024:#Update - Retailer has confirmed new date for 05/08 - Openreach have allocated the hoist for the appointment. _x000D_29/7/2024:#Update - Retailer has confirmed new date for 05/08 - Openreach have allocated the hoist for the appointment. _x000D_29/7/2024:01454988 _x000D_26/7/2024:01454988 _x000D_24/7/2024:#Update - Retailer has confirmed new date for 05/08 - Openreach have allocated the hoist for the appointment. _x000D_23/7/2024:#Update - Awaiting understanding of Engineer notes, cannot run the line through fireproof ceiling. _x000D_22/7/2024:#Update - Awaiting understanding of Engineer notes, cannot run the line through fireproof ceiling. _x000D_22/7/2024:#Update - Awaiting understanding of Engineer notes, cannot run the line through fireproof ceiling. _x000D_27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/8/2024:#Update - Retailer has confirmed new date for 05/08 - Openreach have allocated the hoist for the appointment. _x000D_8/8/2024:24/07/2024 _x000D_6/8/2024:24/07/2024 _x000D_5/8/2024:24/07/2024 _x000D_2/8/2024:24/07/2024 _x000D_1/8/2024:24/07/2024 _x000D_31/7/2024:24/07/2024 _x000D_31/7/2024:24/07/2024 _x000D_30/7/2024:#Update - Retailer has confirmed new date for 05/08 - Openreach have allocated the hoist for the appointment. _x000D_29/7/2024:#Update - Retailer has confirmed new date for 05/08 - Openreach have allocated the hoist for the appointment. _x000D_29/7/2024:01454988 _x000D_26/7/2024:01454988 _x000D_24/7/2024:#Update - Retailer has confirmed new date for 05/08 - Openreach have allocated the hoist for the appointment. _x000D_23/7/2024:#Update - Awaiting understanding of Engineer notes, cannot run the line through fireproof ceiling. _x000D_22/7/2024:#Update - Awaiting understanding of Engineer notes, cannot run the line through fireproof ceiling. _x000D_22/7/2024:#Update - Awaiting understanding of Engineer notes, cannot run the line through fireproof ceiling. _x000D_27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015554 | 30017004 | 2.Commissioning |  |  | 2024-06-26 | 2024-08-05 | 2024-08-05 12:20 | TRUE |  |  |  | 2024-08-23 | [7 empty] | 0
777 | 648415 | 3275 | Batch 5 Jul24 | Type 1 | FTTP | Newsstand Saltcoats | Saltcoats | KA21 5ED |  | 27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366106 | 30016761 | 2.Commissioning |  |  | 2024-06-26 | 2024-06-26 | 2024-06-26 | TRUE |  |  |  | 2024-07-19 | [7 empty] | 0
778 | 616183 | 3280 | Batch 5 Jul24 | Type 1 | FTTP | St. John's Mini Market | Sittingbourne | ME10 4ND |  | 19/7/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_18/7/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_17/7/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_16/7/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_15/7/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_12/7/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_11/7/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_10/7/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_9/7/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_4/7/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_3/7/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_2/7/2024:0 _x000D_1/7/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 19/7/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_18/7/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_17/7/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_16/7/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_15/7/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_12/7/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_11/7/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_10/7/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_9/7/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_4/7/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_3/7/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_2/7/2024:0 _x000D_1/7/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366104 | 30016989 | 2.Commissioning |  |  | 2024-06-26 | 2024-06-26 | 2024-06-26 | TRUE |  |  |  | 2024-07-17 | [7 empty] | 0
779 | 433785 | 3281 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | SLAID HILL NEWS | LEEDS | LS17 8TJ |  | 6/9/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_5/9/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_4/9/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_3/9/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_2/9/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_29/8/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_28/8/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_27/8/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_22/8/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_21/8/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_20/8/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_19/8/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_19/8/2024:01453895 _x000D_16/8/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_15/8/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_14/8/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_13/8/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_12/8/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_9/8/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_8/8/2024:28/06/2024 _x000D_6/8/2024:28/06/2024 _x000D_5/8/2024:28/06/2024 _x000D_2/8/2024:28/06/2024 _x000D_1/8/2024:28/06/2024 _x000D_31/7/2024:28/06/2024 _x000D_31/7/2024:28/06/2024 _x000D_30/7/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_29/7/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_29/7/2024:01453895 _x000D_26/7/2024:01453895 _x000D_24/7/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_23/7/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_22/7/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_22/7/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_6/9/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_5/9/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_4/9/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_3/9/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_2/9/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_29/8/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_28/8/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_27/8/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_22/8/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_21/8/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_20/8/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_19/8/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_19/8/2024:01453895 _x000D_16/8/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_15/8/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_14/8/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_13/8/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_12/8/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_9/8/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_8/8/2024:28/06/2024 _x000D_6/8/2024:28/06/2024 _x000D_5/8/2024:28/06/2024 _x000D_2/8/2024:28/06/2024 _x000D_1/8/2024:28/06/2024 _x000D_31/7/2024:28/06/2024 _x000D_31/7/2024:28/06/2024 _x000D_30/7/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_29/7/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_29/7/2024:01453895 _x000D_26/7/2024:01453895 _x000D_24/7/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_23/7/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_22/7/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_22/7/2024:#UPDATE: Multi-port ONT Site pushed out to 09/08 _x000D_27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | Update: Order Amended | #UPDATE: Multi-port ONT Site pushed out to 09/08 | 2024-06-07 |  |  |  |  | VFP2366105 | 30016916 | 1.Provisioning | AM |  | 2024-06-26 | 2024-09-06 |  | 0 | [11 empty] | 0
780 | 665602 | 3283 | Batch 5 Jul24 | Type 1 | SOGEA | Bickers Newsagents | Sandwich | CT13 0HB |  | 27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015461 | 30016629 | 6.Failed router install |  |  | 2024-06-26 | 2024-06-26 | 2024-06-26 | TRUE |  |  |  | 2024-07-25 |  |  |  | 2024-07-25 | 242005008600 |  | 2024-07-29 | 1
781 | 476028 | 3286 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Haynes All Day Everyday | Doncaster | DN8 5HT |  | 6/9/2024:#Update Upgrade and OOH sent to VF. _x000D_5/9/2024:#Update Upgrade and OOH sent to VF. _x000D_4/9/2024:#Update Upgrade and OOH sent to VF. _x000D_3/9/2024:#Update Upgrade and OOH sent to VF. _x000D_2/9/2024:#Update Upgrade and OOH sent to VF. _x000D_29/8/2024:#Update Upgrade and OOH sent to VF. _x000D_28/8/2024:#Update Upgrade and OOH sent to VF. _x000D_27/8/2024:#Update Upgrade and OOH sent to VF. _x000D_22/8/2024:#Update Upgrade and OOH sent to VF. _x000D_21/8/2024:#Update Upgrade and OOH sent to VF. _x000D_20/8/2024:#Update Upgrade and OOH sent to VF. _x000D_19/8/2024:#Update Upgrade and OOH sent to VF. _x000D_19/8/2024:01454622 _x000D_16/8/2024:#Update Upgrade and OOH sent to VF. _x000D_15/8/2024:#Update Upgrade and OOH sent to VF. _x000D_14/8/2024:#Update Upgrade and OOH sent to VF. _x000D_13/8/2024:#Update Upgrade and OOH sent to VF. _x000D_12/8/2024:#Update Upgrade and OOH sent to VF. _x000D_9/8/2024:#Update Upgrade and OOH sent to VF. _x000D_8/8/2024:03/07/2024 _x000D_6/8/2024:03/07/2024 _x000D_5/8/2024:03/07/2024 _x000D_2/8/2024:03/07/2024 _x000D_1/8/2024:03/07/2024 _x000D_31/7/2024:03/07/2024 _x000D_31/7/2024:03/07/2024 _x000D_30/7/2024:#Update Upgrade and OOH sent to VF. _x000D_29/7/2024:#Update Upgrade and OOH sent to VF. _x000D_29/7/2024:01454622 _x000D_26/7/2024:01454622 _x000D_24/7/2024:#Update Upgrade and OOH sent to VF. _x000D_23/7/2024:#Update Upgrade and OOH sent to VF. _x000D_22/7/2024:#Update Upgrade and OOH sent to VF. _x000D_22/7/2024:#Update Upgrade and OOH sent to VF. _x000D_19/7/2024:#Update - Action for Allwyn - Installation has now been amended to 21/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 21/08 is a suitable date. _x000D_18/7/2024:#Update - Action for Allwyn - Installation has now been amended to 21/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 21/08 is a suitable date. _x000D_17/7/2024:#Update - Action for Allwyn - Installation has now been amended to 21/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 21/08 is a suitable date. _x000D_16/7/2024:#Update - Action for Allwyn - Installation has now been amended to 16/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 16/07 is a suitable date. _x000D_15/7/2024:#Update - Action for Allwyn - Installation has now been amended to 16/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 16/07 is a suitable date. _x000D_12/7/2024:#Update - Action for Allwyn - Installation has now been amended to 16/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 16/07 is a suitable date. _x000D_11/7/2024:#Update - Action for Allwyn - Installation has now been amended to 16/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 16/07 is a suitable date. _x000D_10/7/2024:#Update - Action for Allwyn - Installation has now been amended to 16/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 16/07 is a suitable date. _x000D_9/7/2024:#Update - Action for Allwyn - Installation has now been amended to 16/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 16/07 is a suitable date. _x000D_4/7/2024:#Update - Action for Allwyn - Installation has now been amended to 16/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 16/07 is a suitable date. _x000D_3/7/2024:#Update - Action for Allwyn - Installation has now been amended to 16/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 16/07 is a suitable date. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Action for Allwyn - Installation has now been amended to 16/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 16/07 is a suitable date. _x000D_27/6/2024:#Update - Action for Allwyn - Installation has now been amended to 16/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 16/07 is a suitable date. _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:#Update Upgrade and OOH sent to VF. _x000D_6/9/2024:#Update Upgrade and OOH sent to VF. _x000D_5/9/2024:#Update Upgrade and OOH sent to VF. _x000D_4/9/2024:#Update Upgrade and OOH sent to VF. _x000D_3/9/2024:#Update Upgrade and OOH sent to VF. _x000D_2/9/2024:#Update Upgrade and OOH sent to VF. _x000D_29/8/2024:#Update Upgrade and OOH sent to VF. _x000D_28/8/2024:#Update Upgrade and OOH sent to VF. _x000D_27/8/2024:#Update Upgrade and OOH sent to VF. _x000D_22/8/2024:#Update Upgrade and OOH sent to VF. _x000D_21/8/2024:#Update Upgrade and OOH sent to VF. _x000D_20/8/2024:#Update Upgrade and OOH sent to VF. _x000D_19/8/2024:#Update Upgrade and OOH sent to VF. _x000D_19/8/2024:01454622 _x000D_16/8/2024:#Update Upgrade and OOH sent to VF. _x000D_15/8/2024:#Update Upgrade and OOH sent to VF. _x000D_14/8/2024:#Update Upgrade and OOH sent to VF. _x000D_13/8/2024:#Update Upgrade and OOH sent to VF. _x000D_12/8/2024:#Update Upgrade and OOH sent to VF. _x000D_9/8/2024:#Update Upgrade and OOH sent to VF. _x000D_8/8/2024:03/07/2024 _x000D_6/8/2024:03/07/2024 _x000D_5/8/2024:03/07/2024 _x000D_2/8/2024:03/07/2024 _x000D_1/8/2024:03/07/2024 _x000D_31/7/2024:03/07/2024 _x000D_31/7/2024:03/07/2024 _x000D_30/7/2024:#Update Upgrade and OOH sent to VF. _x000D_29/7/2024:#Update Upgrade and OOH sent to VF. _x000D_29/7/2024:01454622 _x000D_26/7/2024:01454622 _x000D_24/7/2024:#Update Upgrade and OOH sent to VF. _x000D_23/7/2024:#Update Upgrade and OOH sent to VF. _x000D_22/7/2024:#Update Upgrade and OOH sent to VF. _x000D_22/7/2024:#Update Upgrade and OOH sent to VF. _x000D_19/7/2024:#Update - Action for Allwyn - Installation has now been amended to 21/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 21/08 is a suitable date. _x000D_18/7/2024:#Update - Action for Allwyn - Installation has now been amended to 21/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 21/08 is a suitable date. _x000D_17/7/2024:#Update - Action for Allwyn - Installation has now been amended to 21/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 21/08 is a suitable date. _x000D_16/7/2024:#Update - Action for Allwyn - Installation has now been amended to 16/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 16/07 is a suitable date. _x000D_15/7/2024:#Update - Action for Allwyn - Installation has now been amended to 16/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 16/07 is a suitable date. _x000D_12/7/2024:#Update - Action for Allwyn - Installation has now been amended to 16/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 16/07 is a suitable date. _x000D_11/7/2024:#Update - Action for Allwyn - Installation has now been amended to 16/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 16/07 is a suitable date. _x000D_10/7/2024:#Update - Action for Allwyn - Installation has now been amended to 16/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 16/07 is a suitable date. _x000D_9/7/2024:#Update - Action for Allwyn - Installation has now been amended to 16/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 16/07 is a suitable date. _x000D_4/7/2024:#Update - Action for Allwyn - Installation has now been amended to 16/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 16/07 is a suitable date. _x000D_3/7/2024:#Update - Action for Allwyn - Installation has now been amended to 16/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 16/07 is a suitable date. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Action for Allwyn - Installation has now been amended to 16/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 16/07 is a suitable date. _x000D_27/6/2024:#Update - Action for Allwyn - Installation has now been amended to 16/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 16/07 is a suitable date. _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | #Update Upgrade and OOH sent to VF. | 2024-06-07 |  |  |  |  | VFP2366100 | 30016814 | 1.Provisioning | AM |  | 2024-06-26 | 2024-09-10 |  | 0 | [11 empty] | 0
782 | 621797 | 3287 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Brixton Food & Wine | London | SW2 2TJ |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:#Update - Order has now been completed _x000D_21/8/2024:#Update - Action for Allwyn - Installation has now been amended to 21/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 21/08 is a suitable date. _x000D_20/8/2024:#Update - Action for Allwyn - Installation has now been amended to 21/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 21/08 is a suitable date. _x000D_19/8/2024:#Update - Action for Allwyn - Installation has now been amended to 21/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 21/08 is a suitable date. _x000D_19/8/2024:01453997 _x000D_16/8/2024:#Update - Action for Allwyn - Installation has now been amended to 21/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 21/08 is a suitable date. _x000D_15/8/2024:#Update - Action for Allwyn - Installation has now been amended to 21/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 21/08 is a suitable date. _x000D_14/8/2024:#Update - Action for Allwyn - Installation has now been amended to 21/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 21/08 is a suitable date. _x000D_13/8/2024:#Update - Action for Allwyn - Installation has now been amended to 21/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 21/08 is a suitable date. _x000D_12/8/2024:#Update - Action for Allwyn - Installation has now been amended to 21/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 21/08 is a suitable date. _x000D_9/8/2024:#Update - Action for Allwyn - Installation has now been amended to 21/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 21/08 is a suitable date. _x000D_8/8/2024:16/07/2024 _x000D_6/8/2024:16/07/2024 _x000D_5/8/2024:16/07/2024 _x000D_2/8/2024:16/07/2024 _x000D_1/8/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_30/7/2024:#Update - Action for Allwyn - Installation has now been amended to 21/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 21/08 is a suitable date. _x000D_29/7/2024:#Update - Action for Allwyn - Installation has now been amended to 21/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 21/08 is a suitable date. _x000D_29/7/2024:01453997 _x000D_26/7/2024:01453997 _x000D_24/7/2024:#Update - Action for Allwyn - Installation has now been amended to 21/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 21/08 is a suitable date. _x000D_23/7/2024:#Update - Action for Allwyn - Installation has now been amended to 21/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 21/08 is a suitable date. _x000D_22/7/2024:#Update - Action for Allwyn - Installation has now been amended to 21/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 21/08 is a suitable date. _x000D_22/7/2024:#Update - Action for Allwyn - Installation has now been amended to 21/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 21/08 is a suitable date. _x000D_27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:#Update - Order has now been completed _x000D_21/8/2024:#Update - Action for Allwyn - Installation has now been amended to 21/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 21/08 is a suitable date. _x000D_20/8/2024:#Update - Action for Allwyn - Installation has now been amended to 21/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 21/08 is a suitable date. _x000D_19/8/2024:#Update - Action for Allwyn - Installation has now been amended to 21/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 21/08 is a suitable date. _x000D_19/8/2024:01453997 _x000D_16/8/2024:#Update - Action for Allwyn - Installation has now been amended to 21/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 21/08 is a suitable date. _x000D_15/8/2024:#Update - Action for Allwyn - Installation has now been amended to 21/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 21/08 is a suitable date. _x000D_14/8/2024:#Update - Action for Allwyn - Installation has now been amended to 21/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 21/08 is a suitable date. _x000D_13/8/2024:#Update - Action for Allwyn - Installation has now been amended to 21/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 21/08 is a suitable date. _x000D_12/8/2024:#Update - Action for Allwyn - Installation has now been amended to 21/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 21/08 is a suitable date. _x000D_9/8/2024:#Update - Action for Allwyn - Installation has now been amended to 21/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 21/08 is a suitable date. _x000D_8/8/2024:16/07/2024 _x000D_6/8/2024:16/07/2024 _x000D_5/8/2024:16/07/2024 _x000D_2/8/2024:16/07/2024 _x000D_1/8/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_30/7/2024:#Update - Action for Allwyn - Installation has now been amended to 21/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 21/08 is a suitable date. _x000D_29/7/2024:#Update - Action for Allwyn - Installation has now been amended to 21/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 21/08 is a suitable date. _x000D_29/7/2024:01453997 _x000D_26/7/2024:01453997 _x000D_24/7/2024:#Update - Action for Allwyn - Installation has now been amended to 21/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 21/08 is a suitable date. _x000D_23/7/2024:#Update - Action for Allwyn - Installation has now been amended to 21/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 21/08 is a suitable date. _x000D_22/7/2024:#Update - Action for Allwyn - Installation has now been amended to 21/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 21/08 is a suitable date. _x000D_22/7/2024:#Update - Action for Allwyn - Installation has now been amended to 21/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 21/08 is a suitable date. _x000D_27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | 0 | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366016 | 30016622 | 2.Commissioning | AM |  | 2024-06-26 | 2024-08-21 |  | 0 |  |  |  | 2024-09-18 | [7 empty] | 0
783 | 668885 | 3289 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Londis Supermarket | Coventry | CV3 5HZ |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:Update: Order Amended _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:Update: Order Amended _x000D_31/7/2024:Update: Order Amended _x000D_31/7/2024:37912 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_18/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_17/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_16/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_15/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_12/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_11/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_10/7/2024: #Update - Allwyn confirmed Retailer has agreed to installation on 10/07 AM _x000D_9/7/2024: #Update - Allwyn confirmed Retailer has agreed to installation on 10/07 AM _x000D_4/7/2024: #Update - Allwyn confirmed Retailer has agreed to installation on 10/07 AM _x000D_3/7/2024: #Update - Allwyn confirmed Retailer has agreed to installation on 10/07 AM _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024: #Update - Allwyn confirmed Retailer has agreed to installation on 10/07 AM _x000D_27/6/2024: #Update - Allwyn confirmed Retailer has agreed to installation on 10/07 AM _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:Update: Order Amended _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:Update: Order Amended _x000D_31/7/2024:Update: Order Amended _x000D_31/7/2024:37912 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_18/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_17/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_16/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_15/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_12/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_11/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_10/7/2024: #Update - Allwyn confirmed Retailer has agreed to installation on 10/07 AM _x000D_9/7/2024: #Update - Allwyn confirmed Retailer has agreed to installation on 10/07 AM _x000D_4/7/2024: #Update - Allwyn confirmed Retailer has agreed to installation on 10/07 AM _x000D_3/7/2024: #Update - Allwyn confirmed Retailer has agreed to installation on 10/07 AM _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024: #Update - Allwyn confirmed Retailer has agreed to installation on 10/07 AM _x000D_27/6/2024: #Update - Allwyn confirmed Retailer has agreed to installation on 10/07 AM _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | 0 | 2024-06-07 |  |  |  |  | VFP2366102 | 30016710 | 1.Provisioning | AM |  | 2024-06-26 | 2024-08-29 |  | 0 | [11 empty] | 0 | 668885
784 | 670594 | 3290 | Batch 5 Jul24 | Type 1 | FTTP | Ramshead Post Office | LEEDS | LS14 1BT | 2024-07-29 | 15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_29/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_29/7/2024:01454014 _x000D_26/7/2024:01454014 _x000D_24/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_23/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_22/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_22/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_29/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_29/7/2024:01454014 _x000D_26/7/2024:01454014 _x000D_24/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_23/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_22/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_22/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFP2366101 | 30016872 | 6.Failed router install | [9 empty] | 2024-08-14 |  |  |  | 2024-08-14 | 238004926156 | 238004926156 | 2024-08-15 | 1
785 | 465312 | 3295 | Batch 5 Jul24 | Type 1 | FTTP | Avenue Food & Wine | SHEERNESS | ME12 1DS |  | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Your order has been delayed due to a customer missed appointment. FTTP advanced installation is required. Now the order got committed for 05/08/2024. _x000D_3/7/2024:Your order has been delayed due to a customer missed appointment. FTTP advanced installation is required. Now the order got committed for 05/08/2024. _x000D_2/7/2024:0 _x000D_1/7/2024:Your order has been delayed due to a customer missed appointment. FTTP advanced installation is required. Now the order got committed for 05/08/2024. _x000D_27/6/2024:Supplier Delay: KCI-3 (Order Completed) Delayed in Processing. _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Your order has been delayed due to a customer missed appointment. FTTP advanced installation is required. Now the order got committed for 05/08/2024. _x000D_3/7/2024:Your order has been delayed due to a customer missed appointment. FTTP advanced installation is required. Now the order got committed for 05/08/2024. _x000D_2/7/2024:0 _x000D_1/7/2024:Your order has been delayed due to a customer missed appointment. FTTP advanced installation is required. Now the order got committed for 05/08/2024. _x000D_27/6/2024:Supplier Delay: KCI-3 (Order Completed) Delayed in Processing. _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366099 | 30016897 | 6.Failed router install |  |  | 2024-06-26 | 2024-06-26 | 2024-06-26 | TRUE |  |  |  | 2024-07-17 |  |  |  | 2024-07-17 | 242005008580 |  | 2024-07-18 | 1
786 | 654149 | 3296 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Premier Pensarn Convenience Store | Abergele | LL22 7PS |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:48 _x000D_26/7/2024:22/07/2024 10:48 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:48 _x000D_26/7/2024:22/07/2024 10:48 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2375471 | 30016975 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
787 | 100182 | 3298 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | U Save | GLASGOW | G22 7EU |  | 6/9/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_5/9/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_4/9/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_3/9/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_2/9/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_29/8/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_28/8/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_27/8/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_22/8/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_21/8/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_20/8/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_19/8/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_19/8/2024:01453652 _x000D_16/8/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_15/8/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_14/8/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_13/8/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_12/8/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_9/8/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_8/8/2024:01/07/2024 _x000D_6/8/2024:01/07/2024 _x000D_5/8/2024:01/07/2024 _x000D_2/8/2024:01/07/2024 _x000D_1/8/2024:01/07/2024 _x000D_31/7/2024:01/07/2024 _x000D_31/7/2024:01/07/2024 _x000D_30/7/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_29/7/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_29/7/2024:01453652 _x000D_26/7/2024:01453652 _x000D_24/7/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_23/7/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_22/7/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_22/7/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_6/9/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_5/9/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_4/9/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_3/9/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_2/9/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_29/8/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_28/8/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_27/8/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_22/8/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_21/8/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_20/8/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_19/8/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_19/8/2024:01453652 _x000D_16/8/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_15/8/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_14/8/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_13/8/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_12/8/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_9/8/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_8/8/2024:01/07/2024 _x000D_6/8/2024:01/07/2024 _x000D_5/8/2024:01/07/2024 _x000D_2/8/2024:01/07/2024 _x000D_1/8/2024:01/07/2024 _x000D_31/7/2024:01/07/2024 _x000D_31/7/2024:01/07/2024 _x000D_30/7/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_29/7/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_29/7/2024:01453652 _x000D_26/7/2024:01453652 _x000D_24/7/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_23/7/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_22/7/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_22/7/2024:#Update Retailer happy with new appointment 07/08, AM. _x000D_27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | Update: Order Amended | #Update Retailer happy with new appointment 07/08, AM. | 2024-06-07 |  |  |  |  | VFP2366094 | 30016800 | 1.Provisioning | AM |  | 2024-06-26 | 2024-09-06 |  | 0 | [11 empty] | 0
788 | 630409 | 3300 | Batch 5 Jul24 | Type 1 | SOGEA | Select Convenience | Bolton | BL1 1NS |  | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_3/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_2/7/2024:0 _x000D_1/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_3/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_2/7/2024:0 _x000D_1/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015547 | 30016909 | 2.Commissioning |  |  | 2024-06-26 | 2024-06-26 | 2024-06-26 | TRUE |  |  |  | 2024-07-29 | [7 empty] | 0
789 | 232145 | 3302 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Mini Market | BARRY | CF63 2HW |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:Update: Order Amended _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:Update: Order Amended _x000D_31/7/2024:Update: Order Amended _x000D_31/7/2024:37683 _x000D_30/7/2024:Update: Order Amended _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:#Update Retailer happy with new appointment, 10/07, AM. _x000D_11/7/2024:#Update Retailer happy with new appointment, 10/07, AM. _x000D_10/7/2024:#Update Retailer happy with new appointment, 10/07, AM. _x000D_9/7/2024:#Update Retailer happy with new appointment, 10/07, AM. _x000D_4/7/2024:#Update Retailer happy with new appointment, 10/07, AM. _x000D_3/7/2024:#Update Retailer happy with new appointment, 10/07, AM. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update Retailer happy with new appointment, 10/07, AM. _x000D_27/6/2024:Update: Order Amended _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:Update: Order Amended _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:Update: Order Amended _x000D_31/7/2024:Update: Order Amended _x000D_31/7/2024:37683 _x000D_30/7/2024:Update: Order Amended _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:#Update Retailer happy with new appointment, 10/07, AM. _x000D_11/7/2024:#Update Retailer happy with new appointment, 10/07, AM. _x000D_10/7/2024:#Update Retailer happy with new appointment, 10/07, AM. _x000D_9/7/2024:#Update Retailer happy with new appointment, 10/07, AM. _x000D_4/7/2024:#Update Retailer happy with new appointment, 10/07, AM. _x000D_3/7/2024:#Update Retailer happy with new appointment, 10/07, AM. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update Retailer happy with new appointment, 10/07, AM. _x000D_27/6/2024:Update: Order Amended _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | 0 | 2024-06-07 |  |  |  |  | VFP2366092 | 30016938 | 1.Provisioning | AM |  | 2024-06-26 | 2024-08-27 |  | 0 | [11 empty] | 0
790 | 637315 | 3304 | Batch 5 Jul24 | Type 1 | FTTP | Raja Food and Wine | ILFORD | IG3 8XG |  | 27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366091 | 30016741 | 6.Failed router install |  |  | 2024-06-26 | 2024-06-26 | 2024-06-26 | TRUE |  |  |  | 2024-07-22 |  |  |  | 2024-07-22 | 242005011087 |  | 2024-07-23 | 1
791 | 272818 | 3305 | Batch 5 Jul24 | Type 1 | FTTP | The News Box | GOSPORT | PO12 3AP |  | 27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366090 | 30016888 | 2.Commissioning |  |  | 2024-06-26 | 2024-06-26 | 2024-06-26 | TRUE |  |  |  | 2024-07-17 | [7 empty] | 0
792 | 456965 | 3306 | Batch 5 Jul24 | Type 1 | FTTP | SPAR REDDITCH ROAD | BIRMINGHAM | B38 8NA |  | 27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_7/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 06/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_7/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 06/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366014 | 30017002 | 6.Failed router install |  |  | 2024-06-26 | 2024-06-26 | 2024-06-26 | TRUE |  |  |  | 2024-07-19 |  |  |  | 2024-07-19 | 237004907471 |  | 2024-07-23 | 1
793 | 627923 | 3307 | Batch 5 Jul24 | Type 1 | FTTP | Russells Food & Drink | Kircubbin | BT22 2SR |  | 19/7/2024:#Update Retailer happy with new appointment 26/07, AM. _x000D_18/7/2024:#Update Retailer happy with new appointment 26/07, AM. _x000D_17/7/2024:#Update Retailer happy with new appointment 26/07, AM. _x000D_16/7/2024:#Update Retailer happy with new appointment. _x000D_15/7/2024:#Update Retailer happy with new appointment. _x000D_12/7/2024:#Update Retailer happy with new appointment. _x000D_11/7/2024:#Update Retailer happy with new appointment. _x000D_10/7/2024:#Update Retailer happy with new appointment. _x000D_9/7/2024:#Update Retailer happy with new appointment. _x000D_4/7/2024:#Update Missed appointment, retailer unaware. Reappointed 12/07, PM. Action on Allwyn - ensure the retailer is aware. _x000D_3/7/2024:#Update Missed appointment, retailer unaware. Reappointed 12/07, PM. Action on Allwyn - ensure the retailer is aware. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update Missed appointment, retailer unaware. Reappointed 12/07, PM. Action on Allwyn - ensure the retailer is aware. _x000D_27/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:Your order requires planning validation. We may contact your customer if we need to. You will receive a further update by 20-06-2024. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/6/2024:Your order requires planning validation. We may contact your customer if we need to. You will receive a further update by 20-06-2024. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/6/2024:Your order requires planning validation. We may contact your customer if we need to. You will receive a further update by 20-06-2024. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/6/2024:Your order requires planning validation. We may contact your customer if we need to. You will receive a further update by 20-06-2024. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 19/7/2024:#Update Retailer happy with new appointment 26/07, AM. _x000D_18/7/2024:#Update Retailer happy with new appointment 26/07, AM. _x000D_17/7/2024:#Update Retailer happy with new appointment 26/07, AM. _x000D_16/7/2024:#Update Retailer happy with new appointment. _x000D_15/7/2024:#Update Retailer happy with new appointment. _x000D_12/7/2024:#Update Retailer happy with new appointment. _x000D_11/7/2024:#Update Retailer happy with new appointment. _x000D_10/7/2024:#Update Retailer happy with new appointment. _x000D_9/7/2024:#Update Retailer happy with new appointment. _x000D_4/7/2024:#Update Missed appointment, retailer unaware. Reappointed 12/07, PM. Action on Allwyn - ensure the retailer is aware. _x000D_3/7/2024:#Update Missed appointment, retailer unaware. Reappointed 12/07, PM. Action on Allwyn - ensure the retailer is aware. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update Missed appointment, retailer unaware. Reappointed 12/07, PM. Action on Allwyn - ensure the retailer is aware. _x000D_27/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:Your order requires planning validation. We may contact your customer if we need to. You will receive a further update by 20-06-2024. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/6/2024:Your order requires planning validation. We may contact your customer if we need to. You will receive a further update by 20-06-2024. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/6/2024:Your order requires planning validation. We may contact your customer if we need to. You will receive a further update by 20-06-2024. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/6/2024:Your order requires planning validation. We may contact your customer if we need to. You will receive a further update by 20-06-2024. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366011 | 30016684 | 6.Failed router install |  |  | 2024-06-26 | 2024-06-26 | 2024-06-26 | TRUE |  |  |  | 2024-07-25 |  |  |  | 2024-07-25 | 242005010446 |  | 2024-07-26 | 1
794 | 485857 | 3309 | Batch 5 Jul24 | Type 1 | FTTP | S & R News | Nottingham | NG10 1LP |  | 27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366098 | 30016851 | 6.Failed router install |  |  | 2024-06-26 | 2024-06-26 | 2024-06-27 | TRUE |  |  |  | 2024-07-22 |  |  |  | 2024-07-22 | 23A004946004 |  | 2024-07-23 | 1
795 | 669623 | 3310 | Batch 5 Jul24 | Type 1 | FTTP | SPAR LLANIDLOES PO | LLANIDLOES | SY18 6EF |  | 19/7/2024:#Update: Passed on retailer contact. Allwyn confirmed appointment. _x000D_18/7/2024:#Update: Passed on retailer contact. Allwyn confirmed appointment. _x000D_17/7/2024:#Update: Passed on retailer contact. Allwyn confirmed appointment. _x000D_16/7/2024:#Update: Passed on retailer contact. Allwyn confirmed appointment. _x000D_15/7/2024:#Update: Passed on retailer contact. Allwyn confirmed appointment. _x000D_12/7/2024:#Update: Passed on retailer contact. Allwyn confirmed appointment. _x000D_11/7/2024:#Update: Passed on retailer contact. Allwyn confirmed appointment. _x000D_10/7/2024:#Update: Passed on retailer contact. Allwyn confirmed appointment. _x000D_9/7/2024:#Update: Passed on retailer contact. Allwyn confirmed appointment. _x000D_4/7/2024:#Update: Passed on retailer contact. Allwyn confirmed appointment. _x000D_3/7/2024:#Update: Passed on retailer contact. Allwyn confirmed appointment. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Openreach have been unable to contact the retailer regarding access to the site after retaining the appointment for the next day. Contact details requested. Re-appointed for 2907 AM to retain contact with retailer. Action for allwyn: Please request contact details from retailer with permission to share this with the OR engineer. Also, Please confirm appointment for 29th with the retailer for internal works. _x000D_27/6/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:#Update: Passed on retailer contact. Allwyn confirmed appointment. _x000D_18/7/2024:#Update: Passed on retailer contact. Allwyn confirmed appointment. _x000D_17/7/2024:#Update: Passed on retailer contact. Allwyn confirmed appointment. _x000D_16/7/2024:#Update: Passed on retailer contact. Allwyn confirmed appointment. _x000D_15/7/2024:#Update: Passed on retailer contact. Allwyn confirmed appointment. _x000D_12/7/2024:#Update: Passed on retailer contact. Allwyn confirmed appointment. _x000D_11/7/2024:#Update: Passed on retailer contact. Allwyn confirmed appointment. _x000D_10/7/2024:#Update: Passed on retailer contact. Allwyn confirmed appointment. _x000D_9/7/2024:#Update: Passed on retailer contact. Allwyn confirmed appointment. _x000D_4/7/2024:#Update: Passed on retailer contact. Allwyn confirmed appointment. _x000D_3/7/2024:#Update: Passed on retailer contact. Allwyn confirmed appointment. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Openreach have been unable to contact the retailer regarding access to the site after retaining the appointment for the next day. Contact details requested. Re-appointed for 2907 AM to retain contact with retailer. Action for allwyn: Please request contact details from retailer with permission to share this with the OR engineer. Also, Please confirm appointment for 29th with the retailer for internal works. _x000D_27/6/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366089 | 30016945 | 2.Commissioning |  |  | 2024-06-26 | 2024-06-26 | 2024-06-26 | TRUE |  |  |  | 2024-07-30 | [7 empty] | 0
796 | 665146 | 3311 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Kam's News | DAVENTRY | NN11 4AA | 2024-08-16 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:#Update - Allwyn confimed appointment. Still awaiting information from OR about the cabling lengths and exact hours. Will chase Monday. _x000D_19/8/2024:01454747 _x000D_16/8/2024:#Update - Allwyn confimed appointment. Still awaiting information from OR about the cabling lengths and exact hours. Will chase Monday. _x000D_15/8/2024:#Update - Allwyn confimed appointment. Still awaiting information from OR about the cabling lengths and exact hours. Will chase Monday. _x000D_14/8/2024:#Update - Allwyn confimed appointment. Still awaiting information from OR about the cabling lengths and exact hours. Will chase Monday. _x000D_13/8/2024:#Update - Allwyn confimed appointment. Still awaiting information from OR about the cabling lengths and exact hours. Will chase Monday. _x000D_12/8/2024:#Update - Allwyn confimed appointment. Still awaiting information from OR about the cabling lengths and exact hours. Will chase Monday. _x000D_9/8/2024:#Update - Allwyn confimed appointment. Still awaiting information from OR about the cabling lengths and exact hours. Will chase Monday. _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update - Allwyn confimed appointment. Still awaiting information from OR about the cabling lengths and exact hours. Will chase Monday. _x000D_29/7/2024:#Update - Allwyn confimed appointment. Still awaiting information from OR about the cabling lengths and exact hours. Will chase Monday. _x000D_29/7/2024:01454747 _x000D_26/7/2024:01454747 _x000D_24/7/2024:#Update: Passed on retailer contact. Allwyn confirmed appointment. _x000D_23/7/2024:#Update: Passed on retailer contact. Allwyn confirmed appointment. _x000D_22/7/2024:#Update: Passed on retailer contact. Allwyn confirmed appointment. _x000D_22/7/2024:#Update: Passed on retailer contact. Allwyn confirmed appointment. _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:Your order has been delayed. Multiskilled engineer work is required. Our Suppliers have given us a review date of 03/07/2024. We will continue to provide update as they become available. _x000D_27/6/2024:Supplier Delay: Delay due to Frames Complications, please await for further details _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:#Update - Allwyn confimed appointment. Still awaiting information from OR about the cabling lengths and exact hours. Will chase Monday. _x000D_19/8/2024:01454747 _x000D_16/8/2024:#Update - Allwyn confimed appointment. Still awaiting information from OR about the cabling lengths and exact hours. Will chase Monday. _x000D_15/8/2024:#Update - Allwyn confimed appointment. Still awaiting information from OR about the cabling lengths and exact hours. Will chase Monday. _x000D_14/8/2024:#Update - Allwyn confimed appointment. Still awaiting information from OR about the cabling lengths and exact hours. Will chase Monday. _x000D_13/8/2024:#Update - Allwyn confimed appointment. Still awaiting information from OR about the cabling lengths and exact hours. Will chase Monday. _x000D_12/8/2024:#Update - Allwyn confimed appointment. Still awaiting information from OR about the cabling lengths and exact hours. Will chase Monday. _x000D_9/8/2024:#Update - Allwyn confimed appointment. Still awaiting information from OR about the cabling lengths and exact hours. Will chase Monday. _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update - Allwyn confimed appointment. Still awaiting information from OR about the cabling lengths and exact hours. Will chase Monday. _x000D_29/7/2024:#Update - Allwyn confimed appointment. Still awaiting information from OR about the cabling lengths and exact hours. Will chase Monday. _x000D_29/7/2024:01454747 _x000D_26/7/2024:01454747 _x000D_24/7/2024:#Update: Passed on retailer contact. Allwyn confirmed appointment. _x000D_23/7/2024:#Update: Passed on retailer contact. Allwyn confirmed appointment. _x000D_22/7/2024:#Update: Passed on retailer contact. Allwyn confirmed appointment. _x000D_22/7/2024:#Update: Passed on retailer contact. Allwyn confirmed appointment. _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:Your order has been delayed. Multiskilled engineer work is required. Our Suppliers have given us a review date of 03/07/2024. We will continue to provide update as they become available. _x000D_27/6/2024:Supplier Delay: Delay due to Frames Complications, please await for further details _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | 0 | 2024-06-07 |  |  |  |  | VFP2366088 | 30016667 | 2.Commissioning | AM |  | 2024-06-26 | 2024-08-15 |  | 0 |  |  |  | 2024-09-06 | [7 empty] | 0
797 | 669970 | 3312 | Batch 5 Jul24 | Type 1 | FTTP | Spar Hunts Runshaw Lane | Chorley | PR7 6AU |  | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:Update: Order Completed by Supplier _x000D_15/7/2024:Update: Order Completed by Supplier _x000D_12/7/2024:Update: Order Completed by Supplier _x000D_11/7/2024:Update: Order Completed by Supplier _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:A4 (ECC) _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:Update: Order Amended _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:Update: Order Completed by Supplier _x000D_15/7/2024:Update: Order Completed by Supplier _x000D_12/7/2024:Update: Order Completed by Supplier _x000D_11/7/2024:Update: Order Completed by Supplier _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:A4 (ECC) _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:Update: Order Amended _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFP2366013 | 30016752 | 2.Commissioning |  |  | 2024-06-26 | 2024-06-26 | 2024-07-02 | TRUE |  |  |  | 2024-07-31 | [7 empty] | 0
798 | 666574 | 3313 | Batch 5 Jul24 | Type 1 | SOGEA | Bridge Stores | Kilgetty | SA68 0UF |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Now the order got committed for 11/07/2024 _x000D_27/6/2024:Update: Order Amended _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Now the order got committed for 11/07/2024 _x000D_27/6/2024:Update: Order Amended _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | 0 | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015459 | 30016901 | 2.Commissioning | [9 empty] | 2024-08-01 | [7 empty] | 0
799 | 422706 | 3314 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Triple News | COVENTRY | CV1 4DY |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:13 _x000D_26/7/2024:22/07/2024 10:13 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_18/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_17/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_16/7/2024:#Update Reappointed to 18/07 PM due to a supplier delay. Action on Allwyn - ensure the retailer is aware. _x000D_15/7/2024:#Update Reappointed to 18/07 PM due to a supplier delay. Action on Allwyn - ensure the retailer is aware. _x000D_12/7/2024:#Update Reappointed to 18/07 PM due to a supplier delay. Action on Allwyn - ensure the retailer is aware. _x000D_11/7/2024:#Update Reappointed to 18/07 PM due to a supplier delay. Action on Allwyn - ensure the retailer is aware. _x000D_10/7/2024:#Update Reappointed to 18/07 PM due to a supplier delay. Action on Allwyn - ensure the retailer is aware. _x000D_9/7/2024:#Update Reappointed to 18/07 PM due to a supplier delay. Action on Allwyn - ensure the retailer is aware. _x000D_4/7/2024:0 _x000D_3/7/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_2/7/2024:0 _x000D_1/7/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_27/6/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:13 _x000D_26/7/2024:22/07/2024 10:13 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_18/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_17/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_16/7/2024:#Update Reappointed to 18/07 PM due to a supplier delay. Action on Allwyn - ensure the retailer is aware. _x000D_15/7/2024:#Update Reappointed to 18/07 PM due to a supplier delay. Action on Allwyn - ensure the retailer is aware. _x000D_12/7/2024:#Update Reappointed to 18/07 PM due to a supplier delay. Action on Allwyn - ensure the retailer is aware. _x000D_11/7/2024:#Update Reappointed to 18/07 PM due to a supplier delay. Action on Allwyn - ensure the retailer is aware. _x000D_10/7/2024:#Update Reappointed to 18/07 PM due to a supplier delay. Action on Allwyn - ensure the retailer is aware. _x000D_9/7/2024:#Update Reappointed to 18/07 PM due to a supplier delay. Action on Allwyn - ensure the retailer is aware. _x000D_4/7/2024:0 _x000D_3/7/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_2/7/2024:0 _x000D_1/7/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_27/6/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2366086 | 30016802 | 1.Provisioning | AM |  | 2024-06-26 | 2024-09-06 |  | 0 | [11 empty] | 0
800 | 666757 | 3315 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Shop N Save | BELLSHILL | ML4 3AA |  | 6/9/2024:#Update OR investigating. We will provide updates when they become available. _x000D_5/9/2024:#Update OR investigating. We will provide updates when they become available. _x000D_4/9/2024:#Update OR investigating. We will provide updates when they become available. _x000D_3/9/2024:#Update OR investigating. We will provide updates when they become available. _x000D_2/9/2024:#Update OR investigating. We will provide updates when they become available. _x000D_29/8/2024:#Update OR investigating. We will provide updates when they become available. _x000D_28/8/2024:#Update OR investigating. We will provide updates when they become available. _x000D_27/8/2024:#Update OR investigating. We will provide updates when they become available. _x000D_22/8/2024:#Update OR investigating. We will provide updates when they become available. _x000D_21/8/2024:#Update OR investigating. We will provide updates when they become available. _x000D_20/8/2024:#Update OR investigating. We will provide updates when they become available. _x000D_19/8/2024:#Update OR investigating. We will provide updates when they become available. _x000D_19/8/2024:01453619 _x000D_16/8/2024:#Update OR investigating. We will provide updates when they become available. _x000D_15/8/2024:#Update OR investigating. We will provide updates when they become available. _x000D_14/8/2024:#Update OR investigating. We will provide updates when they become available. _x000D_13/8/2024:#Update OR investigating. We will provide updates when they become available. _x000D_12/8/2024:#Update OR investigating. We will provide updates when they become available. _x000D_9/8/2024:#Update OR investigating. We will provide updates when they become available. _x000D_8/8/2024:25/07/2024 _x000D_6/8/2024:25/07/2024 _x000D_5/8/2024:25/07/2024 _x000D_2/8/2024:25/07/2024 _x000D_1/8/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_30/7/2024:#Update OR investigating. We will provide updates when they become available. _x000D_29/7/2024:#Update OR investigating. We will provide updates when they become available. _x000D_29/7/2024:01453619 _x000D_26/7/2024:01453619 _x000D_24/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_23/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_22/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_22/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update OR investigating. We will provide updates when they become available. _x000D_6/9/2024:#Update OR investigating. We will provide updates when they become available. _x000D_5/9/2024:#Update OR investigating. We will provide updates when they become available. _x000D_4/9/2024:#Update OR investigating. We will provide updates when they become available. _x000D_3/9/2024:#Update OR investigating. We will provide updates when they become available. _x000D_2/9/2024:#Update OR investigating. We will provide updates when they become available. _x000D_29/8/2024:#Update OR investigating. We will provide updates when they become available. _x000D_28/8/2024:#Update OR investigating. We will provide updates when they become available. _x000D_27/8/2024:#Update OR investigating. We will provide updates when they become available. _x000D_22/8/2024:#Update OR investigating. We will provide updates when they become available. _x000D_21/8/2024:#Update OR investigating. We will provide updates when they become available. _x000D_20/8/2024:#Update OR investigating. We will provide updates when they become available. _x000D_19/8/2024:#Update OR investigating. We will provide updates when they become available. _x000D_19/8/2024:01453619 _x000D_16/8/2024:#Update OR investigating. We will provide updates when they become available. _x000D_15/8/2024:#Update OR investigating. We will provide updates when they become available. _x000D_14/8/2024:#Update OR investigating. We will provide updates when they become available. _x000D_13/8/2024:#Update OR investigating. We will provide updates when they become available. _x000D_12/8/2024:#Update OR investigating. We will provide updates when they become available. _x000D_9/8/2024:#Update OR investigating. We will provide updates when they become available. _x000D_8/8/2024:25/07/2024 _x000D_6/8/2024:25/07/2024 _x000D_5/8/2024:25/07/2024 _x000D_2/8/2024:25/07/2024 _x000D_1/8/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_30/7/2024:#Update OR investigating. We will provide updates when they become available. _x000D_29/7/2024:#Update OR investigating. We will provide updates when they become available. _x000D_29/7/2024:01453619 _x000D_26/7/2024:01453619 _x000D_24/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_23/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_22/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_22/7/2024:#Update Retailer happy with new appointment 18/07, AM. _x000D_27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 09/09/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm | #Update OR investigating. We will provide updates when they become available. | 2024-06-07 |  |  |  |  | VFS1098767 | 30016840 | 1.Provisioning | AM |  | 2024-06-26 | 2024-08-22 |  | 0 | [11 empty] | 0
801 | 666466 | 3316 | Batch 5 Jul24 | Type 1 | FTTP | Perry Barr Post Office | BIRMINGHAM | B20 2QL |  | 19/7/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_18/7/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_17/7/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_16/7/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_15/7/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_12/7/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_11/7/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_10/7/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_9/7/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_4/7/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_3/7/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_27/6/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_18/7/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_17/7/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_16/7/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_15/7/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_12/7/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_11/7/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_10/7/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_9/7/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_4/7/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_3/7/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_27/6/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366087 | 30016870 | 2.Commissioning |  |  | 2024-06-26 | 2024-06-26 | 2024-06-26 | TRUE |  |  |  | 2024-07-18 | [7 empty] | 0
802 | 668919 | 3317 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Blacon News & Post Office | CHESTER | CH1 5HN |  | 6/9/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_5/9/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_4/9/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_3/9/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_2/9/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_29/8/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_28/8/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_27/8/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_22/8/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_21/8/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_20/8/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_19/8/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_19/8/2024:01453752 _x000D_16/8/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_15/8/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_14/8/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_13/8/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_12/8/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_9/8/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_8/8/2024:27/06/2024 _x000D_6/8/2024:27/06/2024 _x000D_5/8/2024:27/06/2024 _x000D_2/8/2024:27/06/2024 _x000D_1/8/2024:27/06/2024 _x000D_31/7/2024:27/06/2024 _x000D_31/7/2024:27/06/2024 _x000D_30/7/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_29/7/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_29/7/2024:01453752 _x000D_26/7/2024:01453752 _x000D_24/7/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_23/7/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_22/7/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_22/7/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_19/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_18/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_17/7/2024:#Update – proposal has been accepted. Action for Allwyn: Out of hour appointment required to remove ceiling panels, Openreach have requested that this occurs during a weekday before the shop opens. Please provide some dates/times that would work for the retailer. _x000D_16/7/2024:#Update – proposal has been accepted. Action for Allwyn: Out of hour appointment required to remove ceiling panels, Openreach have requested that this occurs during a weekday before the shop opens. Please provide some dates/times that would work for the retailer. _x000D_15/7/2024:#Update – proposal has been accepted. Action for Allwyn: Out of hour appointment required to remove ceiling panels, Openreach have requested that this occurs during a weekday before the shop opens. Please provide some dates/times that would work for the retailer. _x000D_12/7/2024:#Update – proposal has been accepted. Action for Allwyn: Out of hour appointment required to remove ceiling panels, Openreach have requested that this occurs during a weekday before the shop opens. Please provide some dates/times that would work for the retailer. _x000D_11/7/2024:#Update – proposal has been accepted. Action for Allwyn: Out of hour appointment required to remove ceiling panels, Openreach have requested that this occurs during a weekday before the shop opens. Please provide some dates/times that would work for the retailer. _x000D_10/7/2024:#Update – proposal has been accepted. Action for Allwyn: Out of hour appointment required to remove ceiling panels, Openreach have requested that this occurs during a weekday before the shop opens. Please provide some dates/times that would work for the retailer. _x000D_9/7/2024:#Update – proposal has been accepted. Action for Allwyn: Out of hour appointment required to remove ceiling panels, Openreach have requested that this occurs during a weekday before the shop opens. Please provide some dates/times that would work for the retailer. _x000D_4/7/2024:#Update – proposal has been accepted. Action for Allwyn: Out of hour appointment required to remove ceiling panels, Openreach have requested that this occurs during a weekday before the shop opens. Please provide some dates/times that would work for the retailer. _x000D_3/7/2024:#Update – proposal has been accepted. Action for Allwyn: Out of hour appointment required to remove ceiling panels, Openreach have requested that this occurs during a weekday before the shop opens. Please provide some dates/times that would work for the retailer. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update – proposal has been accepted. Action for Allwyn: Out of hour appointment required to remove ceiling panels, Openreach have requested that this occurs during a weekday before the shop opens. Please provide some dates/times that would work for the retailer. _x000D_27/6/2024:#Update – proposal has been accepted. Action for Allwyn: Out of hour appointment required to remove ceiling panels, Openreach have requested that this occurs during a weekday before the shop opens. Please provide some dates/times that would work for the retailer. _x000D_25/6/2024:#Update – proposal has been accepted. Action for Allwyn: Out of hour appointment required to remove ceiling panels, Openreach have requested that this occurs during a weekday before the shop opens. Please provide some dates/times that would work for the retailer. _x000D_24/6/2024:#Update – proposal has been accepted. Action for Allwyn: Out of hour appointment required to remove ceiling panels, Openreach have requested that this occurs during a weekday before the shop opens. Please provide some dates/times that would work for the retailer. _x000D_20/6/2024:#Update – proposal has been accepted. Action for Allwyn: Out of hour appointment required to remove ceiling panels, Openreach have requested that this occurs during a weekday before the shop opens. Please provide some dates/times that would work for the retailer. _x000D_19/6/2024:#Update – proposal has been accepted. Action for Allwyn: Out of hour appointment required to remove ceiling panels, Openreach have requested that this occurs during a weekday before the shop opens. Please provide some dates/times that would work for the retailer. _x000D_18/6/2024:#Update – proposal has been accepted. Action for Allwyn: Out of hour appointment required to remove ceiling panels, Openreach have requested that this occurs during a weekday before the shop opens. Please provide some dates/times that would work for the retailer. _x000D_17/6/2024:#Update – proposal has been accepted. Action for Allwyn: Out of hour appointment required to remove ceiling panels, Openreach have requested that this occurs during a weekday before the shop opens. Please provide some dates/times that would work for the retailer. _x000D_14/6/2024:#Update – proposal has been accepted. Action for Allwyn: Out of hour appointment required to remove ceiling panels, Openreach have requested that this occurs during a weekday before the shop opens. Please provide some dates/times that would work for the retailer. _x000D_13/6/2024:#Update – proposal has been accepted. Action for Allwyn: Out of hour appointment required to remove ceiling panels, Openreach have requested that this occurs during a weekday before the shop opens. Please provide some dates/times that would work for the retailer. _x000D_12/6/2024:#Update – proposal has been accepted. Action for Allwyn: Out of hour appointment required to remove ceiling panels, Openreach have requested that this occurs during a weekday before the shop opens. Please provide some dates/times that would work for the retailer. _x000D_11/6/2024:#Update Still awaiting Allwyn's approval for an upgrade. _x000D_ | 9/9/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_6/9/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_5/9/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_4/9/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_3/9/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_2/9/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_29/8/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_28/8/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_27/8/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_22/8/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_21/8/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_20/8/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_19/8/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_19/8/2024:01453752 _x000D_16/8/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_15/8/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_14/8/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_13/8/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_12/8/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_9/8/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_8/8/2024:27/06/2024 _x000D_6/8/2024:27/06/2024 _x000D_5/8/2024:27/06/2024 _x000D_2/8/2024:27/06/2024 _x000D_1/8/2024:27/06/2024 _x000D_31/7/2024:27/06/2024 _x000D_31/7/2024:27/06/2024 _x000D_30/7/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_29/7/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_29/7/2024:01453752 _x000D_26/7/2024:01453752 _x000D_24/7/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_23/7/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_22/7/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_22/7/2024:#Update Upgrade is needed due to complex cabling and no existing line plant. _x000D_19/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_18/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_17/7/2024:#Update – proposal has been accepted. Action for Allwyn: Out of hour appointment required to remove ceiling panels, Openreach have requested that this occurs during a weekday before the shop opens. Please provide some dates/times that would work for the retailer. _x000D_16/7/2024:#Update – proposal has been accepted. Action for Allwyn: Out of hour appointment required to remove ceiling panels, Openreach have requested that this occurs during a weekday before the shop opens. Please provide some dates/times that would work for the retailer. _x000D_15/7/2024:#Update – proposal has been accepted. Action for Allwyn: Out of hour appointment required to remove ceiling panels, Openreach have requested that this occurs during a weekday before the shop opens. Please provide some dates/times that would work for the retailer. _x000D_12/7/2024:#Update – proposal has been accepted. Action for Allwyn: Out of hour appointment required to remove ceiling panels, Openreach have requested that this occurs during a weekday before the shop opens. Please provide some dates/times that would work for the retailer. _x000D_11/7/2024:#Update – proposal has been accepted. Action for Allwyn: Out of hour appointment required to remove ceiling panels, Openreach have requested that this occurs during a weekday before the shop opens. Please provide some dates/times that would work for the retailer. _x000D_10/7/2024:#Update – proposal has been accepted. Action for Allwyn: Out of hour appointment required to remove ceiling panels, Openreach have requested that this occurs during a weekday before the shop opens. Please provide some dates/times that would work for the retailer. _x000D_9/7/2024:#Update – proposal has been accepted. Action for Allwyn: Out of hour appointment required to remove ceiling panels, Openreach have requested that this occurs during a weekday before the shop opens. Please provide some dates/times that would work for the retailer. _x000D_4/7/2024:#Update – proposal has been accepted. Action for Allwyn: Out of hour appointment required to remove ceiling panels, Openreach have requested that this occurs during a weekday before the shop opens. Please provide some dates/times that would work for the retailer. _x000D_3/7/2024:#Update – proposal has been accepted. Action for Allwyn: Out of hour appointment required to remove ceiling panels, Openreach have requested that this occurs during a weekday before the shop opens. Please provide some dates/times that would work for the retailer. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update – proposal has been accepted. Action for Allwyn: Out of hour appointment required to remove ceiling panels, Openreach have requested that this occurs during a weekday before the shop opens. Please provide some dates/times that would work for the retailer. _x000D_27/6/2024:#Update – proposal has been accepted. Action for Allwyn: Out of hour appointment required to remove ceiling panels, Openreach have requested that this occurs during a weekday before the shop opens. Please provide some dates/times that would work for the retailer. _x000D_25/6/2024:#Update – proposal has been accepted. Action for Allwyn: Out of hour appointment required to remove ceiling panels, Openreach have requested that this occurs during a weekday before the shop opens. Please provide some dates/times that would work for the retailer. _x000D_24/6/2024:#Update – proposal has been accepted. Action for Allwyn: Out of hour appointment required to remove ceiling panels, Openreach have requested that this occurs during a weekday before the shop opens. Please provide some dates/times that would work for the retailer. _x000D_20/6/2024:#Update – proposal has been accepted. Action for Allwyn: Out of hour appointment required to remove ceiling panels, Openreach have requested that this occurs during a weekday before the shop opens. Please provide some dates/times that would work for the retailer. _x000D_19/6/2024:#Update – proposal has been accepted. Action for Allwyn: Out of hour appointment required to remove ceiling panels, Openreach have requested that this occurs during a weekday before the shop opens. Please provide some dates/times that would work for the retailer. _x000D_18/6/2024:#Update – proposal has been accepted. Action for Allwyn: Out of hour appointment required to remove ceiling panels, Openreach have requested that this occurs during a weekday before the shop opens. Please provide some dates/times that would work for the retailer. _x000D_17/6/2024:#Update – proposal has been accepted. Action for Allwyn: Out of hour appointment required to remove ceiling panels, Openreach have requested that this occurs during a weekday before the shop opens. Please provide some dates/times that would work for the retailer. _x000D_14/6/2024:#Update – proposal has been accepted. Action for Allwyn: Out of hour appointment required to remove ceiling panels, Openreach have requested that this occurs during a weekday before the shop opens. Please provide some dates/times that would work for the retailer. _x000D_13/6/2024:#Update – proposal has been accepted. Action for Allwyn: Out of hour appointment required to remove ceiling panels, Openreach have requested that this occurs during a weekday before the shop opens. Please provide some dates/times that would work for the retailer. _x000D_12/6/2024:#Update – proposal has been accepted. Action for Allwyn: Out of hour appointment required to remove ceiling panels, Openreach have requested that this occurs during a weekday before the shop opens. Please provide some dates/times that would work for the retailer. _x000D_11/6/2024:#Update Still awaiting Allwyn's approval for an upgrade. _x000D_ | 0 | #Update Upgrade is needed due to complex cabling and no existing line plant. | 2024-06-07 |  |  |  |  | VFS1015458 | 30016660 | 1.Provisioning | AM |  | 2024-06-26 | 2024-08-19 |  | 0 | [11 empty] | 0
803 | 485897 | 91 | Batch 2 Apr24 | Type 1 | SoGEA/Mobile | Nunhead Mini Market | London | SE15 3QE | 2024-08-07 | 6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_19/8/2024:01342144 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_13/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_12/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_9/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_8/8/2024:18/07/2024 _x000D_6/8/2024:18/07/2024 _x000D_5/8/2024:18/07/2024 _x000D_2/8/2024:18/07/2024 _x000D_1/8/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_30/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_29/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_29/7/2024:01342144 _x000D_26/7/2024:01342144 _x000D_24/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_23/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_22/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_22/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_19/7/2024:#Update Retailer happy with new appointment. _x000D_18/7/2024:#Update Retailer happy with new appointment. _x000D_17/7/2024:#Update Retailer happy with new appointment. _x000D_16/7/2024:#Update Retailer happy with new appointment. _x000D_15/7/2024:#Update Retailer happy with new appointment. _x000D_12/7/2024:#Update Retailer happy with new appointment. _x000D_11/7/2024:#Update Retailer happy with new appointment. _x000D_10/7/2024:#Update Retailer happy with new appointment. _x000D_9/7/2024:#Update Retailer happy with new appointment. _x000D_4/7/2024:#Update Retailer happy with new appointment. _x000D_3/7/2024:#Update Retailer happy with new appointment. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update Retailer happy with new appointment. _x000D_27/6/2024:#Update Retailer happy with new appointment. _x000D_25/6/2024:#Update Retailer happy with new appointment. _x000D_24/6/2024:#Update Retailer happy with new appointment. _x000D_20/6/2024:#Update Retailer happy with new appointment. _x000D_19/6/2024:#Update Retailer happy with new appointment. _x000D_18/6/2024:#Update Retailer happy with new appointment. _x000D_17/6/2024:#Update Retailer happy with new appointment. _x000D_14/6/2024:#Update Retailer happy with new appointment. _x000D_13/6/2024:#Update Retailer happy with new appointment. _x000D_12/6/2024:#Update Retailer happy with new appointment. _x000D_11/6/2024:#Update - OR have requested CSL to await further updates as the Teletower was unavailable today for the engineer to reach the DP. OR have re-scheduled a date for the engineer to revisit the site with the correct facilities in order to complete install. Will await further updates due on 05.06 _x000D_ | 9/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_19/8/2024:01342144 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_13/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_12/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_9/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_8/8/2024:18/07/2024 _x000D_6/8/2024:18/07/2024 _x000D_5/8/2024:18/07/2024 _x000D_2/8/2024:18/07/2024 _x000D_1/8/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_30/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_29/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_29/7/2024:01342144 _x000D_26/7/2024:01342144 _x000D_24/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_23/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_22/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_22/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM _x000D_19/7/2024:#Update Retailer happy with new appointment. _x000D_18/7/2024:#Update Retailer happy with new appointment. _x000D_17/7/2024:#Update Retailer happy with new appointment. _x000D_16/7/2024:#Update Retailer happy with new appointment. _x000D_15/7/2024:#Update Retailer happy with new appointment. _x000D_12/7/2024:#Update Retailer happy with new appointment. _x000D_11/7/2024:#Update Retailer happy with new appointment. _x000D_10/7/2024:#Update Retailer happy with new appointment. _x000D_9/7/2024:#Update Retailer happy with new appointment. _x000D_4/7/2024:#Update Retailer happy with new appointment. _x000D_3/7/2024:#Update Retailer happy with new appointment. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update Retailer happy with new appointment. _x000D_27/6/2024:#Update Retailer happy with new appointment. _x000D_25/6/2024:#Update Retailer happy with new appointment. _x000D_24/6/2024:#Update Retailer happy with new appointment. _x000D_20/6/2024:#Update Retailer happy with new appointment. _x000D_19/6/2024:#Update Retailer happy with new appointment. _x000D_18/6/2024:#Update Retailer happy with new appointment. _x000D_17/6/2024:#Update Retailer happy with new appointment. _x000D_14/6/2024:#Update Retailer happy with new appointment. _x000D_13/6/2024:#Update Retailer happy with new appointment. _x000D_12/6/2024:#Update Retailer happy with new appointment. _x000D_11/6/2024:#Update - OR have requested CSL to await further updates as the Teletower was unavailable today for the engineer to reach the DP. OR have re-scheduled a date for the engineer to revisit the site with the correct facilities in order to complete install. Will await further updates due on 05.06 _x000D_ | 0 | #Update - Allwyn confirmed Retailer has agreed to installation on 06/08 at 4:30 AM | 2024-04-25 | 25/04/2024: Allwyn to make the retailer aware 11/04/2024: Allwyn to approve upgrade and ECC 08/04/2024: CSL to provide updates. 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 2.Allwyn to arrange access | VFS981292 | 30013166 | 1.Provisioning | AM |  | 2024-04-05 | 2024-08-06 |  | 0 | [11 empty] | 0
804 | 480215 | 117 | Batch 2 Apr24 | Type 1 | FTTP/Mobile | Singh Brothers Convenience Store | Doncaster | DN4 0BG | 2024-06-06 | 6/9/2024:#Update Upgrade costs sent to VF for approval. _x000D_5/9/2024:#Update Upgrade costs sent to VF for approval. _x000D_4/9/2024:#Update Upgrade costs sent to VF for approval. _x000D_3/9/2024:#Update Upgrade costs sent to VF for approval. _x000D_2/9/2024:#Update Upgrade costs sent to VF for approval. _x000D_29/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_28/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_27/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_22/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_21/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_20/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_19/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_19/8/2024:01349237 _x000D_16/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_15/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_14/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_13/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_12/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_9/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_29/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_29/7/2024:01349237 _x000D_26/7/2024:01349237 _x000D_24/7/2024:#Update Retailer happy with new appointment. _x000D_23/7/2024:#Update Retailer happy with new appointment. _x000D_22/7/2024:#Update Retailer happy with new appointment. _x000D_22/7/2024:#Update Retailer happy with new appointment. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Retailer Aware of re-appointment, 27.06 _x000D_27/6/2024:#Update - Retailer Aware of re-appointment, 27.06 _x000D_25/6/2024:#Update - Retailer Aware of re-appointment, 27.06 _x000D_24/6/2024:#Update - Retailer Aware of re-appointment, 27.06 _x000D_20/6/2024:#Update - Retailer Aware of re-appointment, 27.06 _x000D_19/6/2024:#Update - Retailer Aware of re-appointment, 27.06 _x000D_18/6/2024:#Update - Retailer Aware of re-appointment, 27.06 _x000D_17/6/2024:#Update - Retailer Aware of re-appointment, 27.06 _x000D_14/6/2024:#Update - Retailer Aware of re-appointment, 27.06 _x000D_13/6/2024:#Update - Retailer Aware of re-appointment, 27.06 _x000D_12/6/2024:#Update - Retailer Aware of re-appointment, 27.06 _x000D_0 | 9/9/2024:#Update Upgrade costs sent to VF for approval. _x000D_6/9/2024:#Update Upgrade costs sent to VF for approval. _x000D_5/9/2024:#Update Upgrade costs sent to VF for approval. _x000D_4/9/2024:#Update Upgrade costs sent to VF for approval. _x000D_3/9/2024:#Update Upgrade costs sent to VF for approval. _x000D_2/9/2024:#Update Upgrade costs sent to VF for approval. _x000D_29/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_28/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_27/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_22/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_21/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_20/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_19/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_19/8/2024:01349237 _x000D_16/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_15/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_14/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_13/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_12/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_9/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_29/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_29/7/2024:01349237 _x000D_26/7/2024:01349237 _x000D_24/7/2024:#Update Retailer happy with new appointment. _x000D_23/7/2024:#Update Retailer happy with new appointment. _x000D_22/7/2024:#Update Retailer happy with new appointment. _x000D_22/7/2024:#Update Retailer happy with new appointment. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Retailer Aware of re-appointment, 27.06 _x000D_27/6/2024:#Update - Retailer Aware of re-appointment, 27.06 _x000D_25/6/2024:#Update - Retailer Aware of re-appointment, 27.06 _x000D_24/6/2024:#Update - Retailer Aware of re-appointment, 27.06 _x000D_20/6/2024:#Update - Retailer Aware of re-appointment, 27.06 _x000D_19/6/2024:#Update - Retailer Aware of re-appointment, 27.06 _x000D_18/6/2024:#Update - Retailer Aware of re-appointment, 27.06 _x000D_17/6/2024:#Update - Retailer Aware of re-appointment, 27.06 _x000D_14/6/2024:#Update - Retailer Aware of re-appointment, 27.06 _x000D_13/6/2024:#Update - Retailer Aware of re-appointment, 27.06 _x000D_12/6/2024:#Update - Retailer Aware of re-appointment, 27.06 _x000D_0 | 0 | #Update Upgrade costs sent to VF for approval. | 2024-06-06 | 06/06/2024: CSL to provide an update 19/04/2024: Allwyn to make retailer aware of visit as per the date in column T ( confirmed ) 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 5.CSL | VFP2375492 | 30013073 | 1.Provisioning | AM |  | 2024-06-05 | 2024-09-13 |  | 0 | [11 empty] | 0
805 | 667017 | 1096 | Batch 3 May24 | Type 1 | SOGEA | Oaktree Stores and | MARLOW | SL7 3EE | 2024-06-07 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:Update: Order Amended _x000D_17/7/2024:Update: Order Amended _x000D_16/7/2024:Update: Order Amended _x000D_15/7/2024:Update: Order Amended _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:Update: Order Amended _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:Delay on Engineer activities. Supplier will arrange new appointment _x000D_13/6/2024:Delay on Engineer activities. Supplier will arrange new appointment _x000D_12/6/2024:Delay on Engineer activities. Supplier will arrange new appointment _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:Update: Order Amended _x000D_17/7/2024:Update: Order Amended _x000D_16/7/2024:Update: Order Amended _x000D_15/7/2024:Update: Order Amended _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:Update: Order Amended _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:Delay on Engineer activities. Supplier will arrange new appointment _x000D_13/6/2024:Delay on Engineer activities. Supplier will arrange new appointment _x000D_12/6/2024:Delay on Engineer activities. Supplier will arrange new appointment _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 3.Allwyn to arrange rtr install | VFP2301293 | 30013986 | 2.Commissioning | AM | [8 empty] | 2024-07-17 | [7 empty] | 0
806 | 665913 | 1188 | Batch 3 May24 | Type 1 | SoGEA/Mobile | Post Office I & E Wales Newsagents | GLASGOW | G67 4BS | 2024-06-07 | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 16:08 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 13:58 _x000D_26/7/2024:22/07/2024 13:58 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_18/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_17/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_16/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_15/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_12/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_11/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_10/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_9/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_4/7/2024:#Update - Action for Allwyn - Installation has now been amended to 27/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/06 is a suitable date. _x000D_3/7/2024:#Update - Action for Allwyn - Installation has now been amended to 27/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/06 is a suitable date. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Action for Allwyn - Installation has now been amended to 27/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/06 is a suitable date. _x000D_27/6/2024:#Update - Action for Allwyn - Installation has now been amended to 27/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/06 is a suitable date. _x000D_25/6/2024:#Update - Action for Allwyn - Installation has now been amended to 27/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/06 is a suitable date. _x000D_24/6/2024:#Update - Action for Allwyn - Installation has now been amended to 27/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/06 is a suitable date. _x000D_20/6/2024:#Update - Action for Allwyn - Installation has now been amended to 27/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/06 is a suitable date. _x000D_19/6/2024:#Update - Action for Allwyn - Installation has now been amended to 27/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/06 is a suitable date. _x000D_18/6/2024:#Update - Action for Allwyn - Installation has now been amended to 27/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/06 is a suitable date. _x000D_17/6/2024:#Update - Action for Allwyn - Installation has now been amended to 27/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/06 is a suitable date. _x000D_14/6/2024:#Update - Action for Allwyn - Installation has now been amended to 27/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/06 is a suitable date. _x000D_13/6/2024:#Update - Action for Allwyn - Installation has now been amended to 27/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/06 is a suitable date. _x000D_12/6/2024:#Update - Action for Allwyn - Installation has now been amended to 27/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/06 is a suitable date. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 16:08 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 13:58 _x000D_26/7/2024:22/07/2024 13:58 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_18/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_17/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_16/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_15/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_12/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_11/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_10/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_9/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_4/7/2024:#Update - Action for Allwyn - Installation has now been amended to 27/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/06 is a suitable date. _x000D_3/7/2024:#Update - Action for Allwyn - Installation has now been amended to 27/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/06 is a suitable date. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Action for Allwyn - Installation has now been amended to 27/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/06 is a suitable date. _x000D_27/6/2024:#Update - Action for Allwyn - Installation has now been amended to 27/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/06 is a suitable date. _x000D_25/6/2024:#Update - Action for Allwyn - Installation has now been amended to 27/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/06 is a suitable date. _x000D_24/6/2024:#Update - Action for Allwyn - Installation has now been amended to 27/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/06 is a suitable date. _x000D_20/6/2024:#Update - Action for Allwyn - Installation has now been amended to 27/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/06 is a suitable date. _x000D_19/6/2024:#Update - Action for Allwyn - Installation has now been amended to 27/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/06 is a suitable date. _x000D_18/6/2024:#Update - Action for Allwyn - Installation has now been amended to 27/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/06 is a suitable date. _x000D_17/6/2024:#Update - Action for Allwyn - Installation has now been amended to 27/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/06 is a suitable date. _x000D_14/6/2024:#Update - Action for Allwyn - Installation has now been amended to 27/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/06 is a suitable date. _x000D_13/6/2024:#Update - Action for Allwyn - Installation has now been amended to 27/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/06 is a suitable date. _x000D_12/6/2024:#Update - Action for Allwyn - Installation has now been amended to 27/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/06 is a suitable date. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 | 7/6/2024: CSL to provide an update | 5.CSL |  | 3.Allwyn to arrange rtr install | VFP2301385 | 30014078 | 2.Commissioning | AM |  | 2024-05-28 | 2024-08-16 |  | 0 |  |  |  | 2024-09-18 | [7 empty] | 0
807 | 445355 | 1213 | Batch 3 May24 | Type 3 | SoGEA/Mobile | Londis Supermarket | SPALDING | PE11 2HG | 2024-06-07 | 6/9/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_5/9/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_4/9/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_3/9/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_2/9/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_29/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_28/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_27/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_22/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_21/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_20/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_19/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_19/8/2024:01362019 _x000D_16/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_15/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_14/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_13/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_12/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_9/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_8/8/2024:08/07/2024 _x000D_6/8/2024:08/07/2024 _x000D_5/8/2024:08/07/2024 _x000D_2/8/2024:08/07/2024 _x000D_1/8/2024:08/07/2024 _x000D_31/7/2024:08/07/2024 _x000D_31/7/2024:08/07/2024 _x000D_30/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_29/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_29/7/2024:01362019 _x000D_26/7/2024:01362019 _x000D_24/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_23/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_22/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_22/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:Update: Order Amended _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:Update: Order Amended _x000D_19/6/2024:Update: Order Amended _x000D_18/6/2024:Update: Order Amended _x000D_17/6/2024:Update: Order Amended _x000D_14/6/2024:Update: Order Amended _x000D_13/6/2024:Update: Order Amended _x000D_12/6/2024:Update: Order Amended _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_6/9/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_5/9/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_4/9/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_3/9/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_2/9/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_29/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_28/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_27/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_22/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_21/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_20/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_19/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_19/8/2024:01362019 _x000D_16/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_15/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_14/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_13/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_12/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_9/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_8/8/2024:08/07/2024 _x000D_6/8/2024:08/07/2024 _x000D_5/8/2024:08/07/2024 _x000D_2/8/2024:08/07/2024 _x000D_1/8/2024:08/07/2024 _x000D_31/7/2024:08/07/2024 _x000D_31/7/2024:08/07/2024 _x000D_30/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_29/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_29/7/2024:01362019 _x000D_26/7/2024:01362019 _x000D_24/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_23/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_22/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_22/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:Update: Order Amended _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:Update: Order Amended _x000D_19/6/2024:Update: Order Amended _x000D_18/6/2024:Update: Order Amended _x000D_17/6/2024:Update: Order Amended _x000D_14/6/2024:Update: Order Amended _x000D_13/6/2024:Update: Order Amended _x000D_12/6/2024:Update: Order Amended _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update - ECC proposal sent to Vodafone on 08/07 |  |  |  |  | 3.Allwyn to arrange rtr install | VFP2301410 | 30014103 | 2.Commissioning | AM |  | 2024-08-22 | 2024-08-22 |  | 0 |  |  |  | 2024-08-22 | [7 empty] | 0
808 | 461697 | 1329 | Batch 4 Jun24 | Type 1 | SOGEA | Dels Convenience Store | SHEFFIELD | S26 4TT | 2024-06-07 | 19/7/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_18/7/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_17/7/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_16/7/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_15/7/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_12/7/2024:#Update - The order has been delayed as civil work is required. CSL will update as more information become available. _x000D_11/7/2024:#Update - The order has been delayed as civil work is required. CSL will update as more information become available. _x000D_10/7/2024:#Update - Order has been delayed as duct work is required. CSL will update as more information become available. _x000D_9/7/2024:#Update - Order has been delayed as duct work is required. CSL will update as more information become available. _x000D_4/7/2024:#Update - Order has been delayed as duct work is required. CSL will update as more information become available. _x000D_3/7/2024:#Update - Order has been delayed as duct work is required. CSL will update as more information become available. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Order has been delayed as duct work is required. CSL will update as more information become available. _x000D_27/6/2024:#Update - The order has been delayed as Traffic Management is required. The target date for this order has been updated to 27/06 to complete the remaining outdoor activities. No further engineering work is required at the retailers premises and their presence is not required. _x000D_25/6/2024:#Update - The order has been delayed as Traffic Management is required. The target date for this order has been updated to 27/06 to complete the remaining outdoor activities. No further engineering work is required at the retailers premises and their presence is not required. _x000D_24/6/2024:#Update - The order has been delayed as Traffic Management is required. The target date for this order has been updated to 27/06 to complete the remaining outdoor activities. No further engineering work is required at the retailers premises and their presence is not required. _x000D_20/6/2024:#Update - The order has been delayed as Traffic Management is required. The target date for this order has been updated to 27/06 to complete the remaining outdoor activities. No further engineering work is required at the retailers premises and their presence is not required. _x000D_19/6/2024:#Update - The order has been delayed as Traffic Management is required. The target date for this order has been updated to 27/06 to complete the remaining outdoor activities. No further engineering work is required at the retailers premises and their presence is not required. _x000D_18/6/2024:#Update - The order has been delayed as Traffic Management is required. The target date for this order has been updated to 27/06 to complete the remaining outdoor activities. No further engineering work is required at the retailers premises and their presence is not required. _x000D_17/6/2024:#Update - The order has been delayed as Traffic Management is required. The target date for this order has been updated to 27/06 to complete the remaining outdoor activities. No further engineering work is required at the retailers premises and their presence is not required. _x000D_14/6/2024:#Update - The order has been delayed as Traffic Management is required. The target date for this order has been updated to 27/06 to complete the remaining outdoor activities. No further engineering work is required at the retailers premises and their presence is not required. _x000D_13/6/2024:#Update - The order has been delayed as Traffic Management is required. The target date for this order has been updated to 27/06 to complete the remaining outdoor activities. No further engineering work is required at the retailers premises and their presence is not required. _x000D_12/6/2024:#Update - The order has been delayed as Traffic Management is required. The target date for this order has been updated to 27/06 to complete the remaining outdoor activities. No further engineering work is required at the retailers premises and their presence is not required. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_18/7/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_17/7/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_16/7/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_15/7/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_12/7/2024:#Update - The order has been delayed as civil work is required. CSL will update as more information become available. _x000D_11/7/2024:#Update - The order has been delayed as civil work is required. CSL will update as more information become available. _x000D_10/7/2024:#Update - Order has been delayed as duct work is required. CSL will update as more information become available. _x000D_9/7/2024:#Update - Order has been delayed as duct work is required. CSL will update as more information become available. _x000D_4/7/2024:#Update - Order has been delayed as duct work is required. CSL will update as more information become available. _x000D_3/7/2024:#Update - Order has been delayed as duct work is required. CSL will update as more information become available. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Order has been delayed as duct work is required. CSL will update as more information become available. _x000D_27/6/2024:#Update - The order has been delayed as Traffic Management is required. The target date for this order has been updated to 27/06 to complete the remaining outdoor activities. No further engineering work is required at the retailers premises and their presence is not required. _x000D_25/6/2024:#Update - The order has been delayed as Traffic Management is required. The target date for this order has been updated to 27/06 to complete the remaining outdoor activities. No further engineering work is required at the retailers premises and their presence is not required. _x000D_24/6/2024:#Update - The order has been delayed as Traffic Management is required. The target date for this order has been updated to 27/06 to complete the remaining outdoor activities. No further engineering work is required at the retailers premises and their presence is not required. _x000D_20/6/2024:#Update - The order has been delayed as Traffic Management is required. The target date for this order has been updated to 27/06 to complete the remaining outdoor activities. No further engineering work is required at the retailers premises and their presence is not required. _x000D_19/6/2024:#Update - The order has been delayed as Traffic Management is required. The target date for this order has been updated to 27/06 to complete the remaining outdoor activities. No further engineering work is required at the retailers premises and their presence is not required. _x000D_18/6/2024:#Update - The order has been delayed as Traffic Management is required. The target date for this order has been updated to 27/06 to complete the remaining outdoor activities. No further engineering work is required at the retailers premises and their presence is not required. _x000D_17/6/2024:#Update - The order has been delayed as Traffic Management is required. The target date for this order has been updated to 27/06 to complete the remaining outdoor activities. No further engineering work is required at the retailers premises and their presence is not required. _x000D_14/6/2024:#Update - The order has been delayed as Traffic Management is required. The target date for this order has been updated to 27/06 to complete the remaining outdoor activities. No further engineering work is required at the retailers premises and their presence is not required. _x000D_13/6/2024:#Update - The order has been delayed as Traffic Management is required. The target date for this order has been updated to 27/06 to complete the remaining outdoor activities. No further engineering work is required at the retailers premises and their presence is not required. _x000D_12/6/2024:#Update - The order has been delayed as Traffic Management is required. The target date for this order has been updated to 27/06 to complete the remaining outdoor activities. No further engineering work is required at the retailers premises and their presence is not required. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFS984897 | 30015502 | 6.Failed router install | AM |  | 2024-06-03 | 2024-07-09 | 2024-07-09 | TRUE |  |  |  | 2024-08-02 |  |  |  | 2024-08-02 | 242005008955 |  | 2024-08-06 | 1
809 | 480113 | 1347 | Batch 4 Jun24 | Type 1 | FTTP/Mobile | Newell Stores | Dungannon | BT70 1EG | 2024-06-07 | 6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 19/09 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 19/09 AM _x000D_4/9/2024:#Update - Order is still delayed due to dig work, this is awaiting permission from a third party. CSL will update as more information become available. _x000D_3/9/2024:#Update - Order is still delayed due to dig work, this is awaiting permission from a third party. CSL will update as more information become available. _x000D_2/9/2024:#Update - Order is still delayed due to dig work, this is awaiting permission from a third party. CSL will update as more information become available. _x000D_29/8/2024:#Update - Order is still delayed due to dig work, this is awaiting permission from a third party. CSL will update as more information become available. _x000D_28/8/2024:#Update - Order is still delayed due to dig work, this is awaiting permission from a third party. CSL will update as more information become available. _x000D_27/8/2024:#Update - Order is still delayed due to dig work, this is awaiting permission from a third party. CSL will update as more information become available. _x000D_22/8/2024:#Update - Order is still delayed due to dig work, this is awaiting permission from a third party. CSL will update as more information become available. _x000D_21/8/2024:#Update - Order is still delayed due to dig work, this is awaiting permission from a third party. CSL will update as more information become available. _x000D_20/8/2024:#Update - Order is still delayed due to dig work, this is awaiting permission from a third party. CSL will update as more information become available. _x000D_19/8/2024:#Update - Order is still delayed due to dig work, this is awaiting permission from a third party. CSL will update as more information become available. _x000D_19/8/2024:01424595 _x000D_16/8/2024:#Update - Order is still delayed due to dig work, this is awaiting permission from a third party. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order is still delayed due to dig work, this is awaiting permission from a third party. CSL will update as more information become available. _x000D_14/8/2024:#Update - Order is still delayed due to dig work, this is awaiting permission from a third party. CSL will update as more information become available. _x000D_13/8/2024:#Update - Order is still delayed due to dig work, this is awaiting permission from a third party. CSL will update as more information become available. _x000D_12/8/2024:#Update - Order is still delayed due to dig work, this is awaiting permission from a third party. CSL will update as more information become available. _x000D_9/8/2024:#Update - Order is still delayed due to dig work, this is awaiting permission from a third party. CSL will update as more information become available. _x000D_8/8/2024:05/08/2024 _x000D_6/8/2024:05/08/2024 _x000D_5/8/2024:05/08/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update - Order has been delayed due as dig work is required. CSL will update as more information become available. _x000D_29/7/2024:#Update - Order has been delayed due as dig work is required. CSL will update as more information become available. _x000D_29/7/2024:01424595 _x000D_26/7/2024:01424595 _x000D_24/7/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_23/7/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_22/7/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_22/7/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 19/09 AM _x000D_6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 19/09 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 19/09 AM _x000D_4/9/2024:#Update - Order is still delayed due to dig work, this is awaiting permission from a third party. CSL will update as more information become available. _x000D_3/9/2024:#Update - Order is still delayed due to dig work, this is awaiting permission from a third party. CSL will update as more information become available. _x000D_2/9/2024:#Update - Order is still delayed due to dig work, this is awaiting permission from a third party. CSL will update as more information become available. _x000D_29/8/2024:#Update - Order is still delayed due to dig work, this is awaiting permission from a third party. CSL will update as more information become available. _x000D_28/8/2024:#Update - Order is still delayed due to dig work, this is awaiting permission from a third party. CSL will update as more information become available. _x000D_27/8/2024:#Update - Order is still delayed due to dig work, this is awaiting permission from a third party. CSL will update as more information become available. _x000D_22/8/2024:#Update - Order is still delayed due to dig work, this is awaiting permission from a third party. CSL will update as more information become available. _x000D_21/8/2024:#Update - Order is still delayed due to dig work, this is awaiting permission from a third party. CSL will update as more information become available. _x000D_20/8/2024:#Update - Order is still delayed due to dig work, this is awaiting permission from a third party. CSL will update as more information become available. _x000D_19/8/2024:#Update - Order is still delayed due to dig work, this is awaiting permission from a third party. CSL will update as more information become available. _x000D_19/8/2024:01424595 _x000D_16/8/2024:#Update - Order is still delayed due to dig work, this is awaiting permission from a third party. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order is still delayed due to dig work, this is awaiting permission from a third party. CSL will update as more information become available. _x000D_14/8/2024:#Update - Order is still delayed due to dig work, this is awaiting permission from a third party. CSL will update as more information become available. _x000D_13/8/2024:#Update - Order is still delayed due to dig work, this is awaiting permission from a third party. CSL will update as more information become available. _x000D_12/8/2024:#Update - Order is still delayed due to dig work, this is awaiting permission from a third party. CSL will update as more information become available. _x000D_9/8/2024:#Update - Order is still delayed due to dig work, this is awaiting permission from a third party. CSL will update as more information become available. _x000D_8/8/2024:05/08/2024 _x000D_6/8/2024:05/08/2024 _x000D_5/8/2024:05/08/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update - Order has been delayed due as dig work is required. CSL will update as more information become available. _x000D_29/7/2024:#Update - Order has been delayed due as dig work is required. CSL will update as more information become available. _x000D_29/7/2024:01424595 _x000D_26/7/2024:01424595 _x000D_24/7/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_23/7/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_22/7/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_22/7/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | #Update - Allwyn confirmed Retailer has agreed to installation on 19/09 AM |  |  |  |  | 2.Allwyn to arrange access | VFP2338473 | 30015504 | 1.Provisioning | AM |  | 2024-06-04 | 2024-06-27 |  | 0 | [11 empty] | 0
810 | 634895 | 1378 | Batch 4 Jun24 | Type 1 | FTTP | Fairway Stores | Bedford | MK41 9HD | 2024-06-07 | 19/7/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_18/7/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_17/7/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_16/7/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_15/7/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_12/7/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_11/7/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_10/7/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:Update: Order Amended _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_18/7/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_17/7/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_16/7/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_15/7/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_12/7/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_11/7/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_10/7/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:Update: Order Amended _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | [6 empty] | 5.CSL | VFP2369635 | 30017055 | 6.Failed router install | AM |  | 2024-06-27 | 2024-06-27 | 2024-06-27 | TRUE |  |  |  | 2024-07-18 |  |  |  | 2024-07-18 | 242005008656 |  | 2024-07-19 | 1
811 | 483136 | 1396 | Batch 4 Jun24 | Type 1 | FTTP/Mobile | Fryers Convenience Store | Bristol | BS11 0AW | 2024-07-29 | 6/9/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_5/9/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_4/9/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_3/9/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_2/9/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_29/8/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_28/8/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_27/8/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_22/8/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_21/8/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_20/8/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_19/8/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_19/8/2024:01456955 _x000D_16/8/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_15/8/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_14/8/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_13/8/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_12/8/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_9/8/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_8/8/2024:10/07/2024 _x000D_6/8/2024:10/07/2024 _x000D_5/8/2024:10/07/2024 _x000D_2/8/2024:10/07/2024 _x000D_1/8/2024:10/07/2024 _x000D_31/7/2024:10/07/2024 _x000D_31/7/2024:10/07/2024 _x000D_30/7/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_29/7/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_29/7/2024:01456955 _x000D_26/7/2024:01456955 _x000D_24/7/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_23/7/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_22/7/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_22/7/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_1/7/2024:Order Completed _x000D_27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_6/9/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_5/9/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_4/9/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_3/9/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_2/9/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_29/8/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_28/8/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_27/8/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_22/8/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_21/8/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_20/8/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_19/8/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_19/8/2024:01456955 _x000D_16/8/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_15/8/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_14/8/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_13/8/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_12/8/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_9/8/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_8/8/2024:10/07/2024 _x000D_6/8/2024:10/07/2024 _x000D_5/8/2024:10/07/2024 _x000D_2/8/2024:10/07/2024 _x000D_1/8/2024:10/07/2024 _x000D_31/7/2024:10/07/2024 _x000D_31/7/2024:10/07/2024 _x000D_30/7/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_29/7/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_29/7/2024:01456955 _x000D_26/7/2024:01456955 _x000D_24/7/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_23/7/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_22/7/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_22/7/2024:#Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly _x000D_1/7/2024:Order Completed _x000D_27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update - unsuccessful install due to installation/routing issue, awaiting further update from Openreach and will share accordingly | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFP2369636 | 30017060 | 1.Provisioning | AM |  | 2024-06-27 | 2024-08-27 |  | 0 | [11 empty] | 0
812 | 632974 | 1767 | Batch 4 Jun24 | Type 1 | SoGEA/Mobile | Knights News | Manchester | M24 1AJ | 2024-06-07 | 6/9/2024:#Update - Re-appointed for 23/09 - Investigating ECC'S _x000D_5/9/2024:#Update - Re-appointed for 23/09 - Investigating ECC'S _x000D_4/9/2024:#Update - Re-appointed for 23/09 - Investigating ECC'S _x000D_3/9/2024:#Update - Re-appointed for 23/09 - Investigating ECC'S _x000D_2/9/2024:#Update - Re-appointed for 23/09 - Investigating ECC'S _x000D_29/8/2024:#Update - Re-appointed for 23/09 - Investigating ECC'S _x000D_28/8/2024:#Update - Re-appointed for 23/09 - Investigating ECC'S _x000D_27/8/2024:#Update - Re-appointed for 23/09 - Investigating ECC'S _x000D_22/8/2024:#Update - Re-appointed for 23/09 - Investigating ECC'S _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:Update: Order Amended _x000D_31/7/2024:Update: Order Amended _x000D_31/7/2024:37674 _x000D_30/7/2024:Update: Order Amended _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:29/07/2024 09:41 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:Update: Order Amended _x000D_19/6/2024:Update: Order Amended _x000D_18/6/2024:Update: Order Amended _x000D_17/6/2024:Update: Order Amended _x000D_14/6/2024:Update: Order Amended _x000D_13/6/2024:Your order has been delayed by our Suppliers due to a hoist being required to complete the installation. Please check with end user and re-appoint order for earliest date. _x000D_12/6/2024:Your order has been delayed by our Suppliers due to a hoist being required to complete the installation. Please check with end user and re-appoint order for earliest date. _x000D_10/6/2024:Delay on Engineer activities. Supplier will arrange new appointment _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 9/9/2024:#Update - Re-appointed for 23/09 - Investigating ECC'S _x000D_6/9/2024:#Update - Re-appointed for 23/09 - Investigating ECC'S _x000D_5/9/2024:#Update - Re-appointed for 23/09 - Investigating ECC'S _x000D_4/9/2024:#Update - Re-appointed for 23/09 - Investigating ECC'S _x000D_3/9/2024:#Update - Re-appointed for 23/09 - Investigating ECC'S _x000D_2/9/2024:#Update - Re-appointed for 23/09 - Investigating ECC'S _x000D_29/8/2024:#Update - Re-appointed for 23/09 - Investigating ECC'S _x000D_28/8/2024:#Update - Re-appointed for 23/09 - Investigating ECC'S _x000D_27/8/2024:#Update - Re-appointed for 23/09 - Investigating ECC'S _x000D_22/8/2024:#Update - Re-appointed for 23/09 - Investigating ECC'S _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:Update: Order Amended _x000D_31/7/2024:Update: Order Amended _x000D_31/7/2024:37674 _x000D_30/7/2024:Update: Order Amended _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:29/07/2024 09:41 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:Update: Order Amended _x000D_19/6/2024:Update: Order Amended _x000D_18/6/2024:Update: Order Amended _x000D_17/6/2024:Update: Order Amended _x000D_14/6/2024:Update: Order Amended _x000D_13/6/2024:Your order has been delayed by our Suppliers due to a hoist being required to complete the installation. Please check with end user and re-appoint order for earliest date. _x000D_12/6/2024:Your order has been delayed by our Suppliers due to a hoist being required to complete the installation. Please check with end user and re-appoint order for earliest date. _x000D_10/6/2024:Delay on Engineer activities. Supplier will arrange new appointment _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 0 | #Update - Re-appointed for 23/09 - Investigating ECC'S | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFS983301 | 30015274 | 1.Provisioning | AM |  | 2024-06-04 | 2024-08-23 |  | 0 | [11 empty] | 0
813 | 429681 | 1796 | Batch 4 Jun24 | Type 1 | SOGEA | Caerau Lane Convenience | CARDIFF | CF5 5HQ | 2024-06-10 | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:#Update - Abortive visit due to access being required to flat roof and large aggressive dog blocking ability to access DP. Couldnt contact the owner of the dog to get access _x000D_4/7/2024:#Update - Abortive visit due to access being required to flat roof and large aggressive dog blocking ability to access DP. Couldnt contact the owner of the dog to get access _x000D_3/7/2024:#Update - Abortive visit due to access being required to flat roof and large aggressive dog blocking ability to access DP. Couldnt contact the owner of the dog to get access _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:#Update - Abortive visit due to access being required to flat roof and large aggressive dog blocking ability to access DP. Couldnt contact the owner of the dog to get access _x000D_27/6/2024:#Update - Abortive visit due to access being required to flat roof and large aggressive dog blocking ability to access DP. Couldnt contact the owner of the dog to get access _x000D_25/6/2024:#Update - Abortive visit due to access being required to flat roof and large aggressive dog blocking ability to access DP. Couldnt contact the owner of the dog to get access _x000D_24/6/2024:#Update - Abortive visit due to access being required to flat roof and large aggressive dog blocking ability to access DP. Couldnt contact the owner of the dog to get access _x000D_20/6/2024:#Update - Abortive visit due to access being required to flat roof and large aggressive dog blocking ability to access DP. Couldnt contact the owner of the dog to get access _x000D_19/6/2024:#Update - Abortive visit due to access being required to flat roof and large aggressive dog blocking ability to access DP. Couldnt contact the owner of the dog to get access _x000D_18/6/2024:#Update - Abortive visit due to access being required to flat roof and large aggressive dog blocking ability to access DP. Couldnt contact the owner of the dog to get access _x000D_17/6/2024:#Update - Abortive visit due to access being required to flat roof and large aggressive dog blocking ability to access DP. Couldnt contact the owner of the dog to get access _x000D_14/6/2024:Supplier Delay: Delayed due to health and safety issues _x000D_13/6/2024:Supplier Delay: Delayed due to health and safety issues _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:#Update - Abortive visit due to access being required to flat roof and large aggressive dog blocking ability to access DP. Couldnt contact the owner of the dog to get access _x000D_4/7/2024:#Update - Abortive visit due to access being required to flat roof and large aggressive dog blocking ability to access DP. Couldnt contact the owner of the dog to get access _x000D_3/7/2024:#Update - Abortive visit due to access being required to flat roof and large aggressive dog blocking ability to access DP. Couldnt contact the owner of the dog to get access _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:#Update - Abortive visit due to access being required to flat roof and large aggressive dog blocking ability to access DP. Couldnt contact the owner of the dog to get access _x000D_27/6/2024:#Update - Abortive visit due to access being required to flat roof and large aggressive dog blocking ability to access DP. Couldnt contact the owner of the dog to get access _x000D_25/6/2024:#Update - Abortive visit due to access being required to flat roof and large aggressive dog blocking ability to access DP. Couldnt contact the owner of the dog to get access _x000D_24/6/2024:#Update - Abortive visit due to access being required to flat roof and large aggressive dog blocking ability to access DP. Couldnt contact the owner of the dog to get access _x000D_20/6/2024:#Update - Abortive visit due to access being required to flat roof and large aggressive dog blocking ability to access DP. Couldnt contact the owner of the dog to get access _x000D_19/6/2024:#Update - Abortive visit due to access being required to flat roof and large aggressive dog blocking ability to access DP. Couldnt contact the owner of the dog to get access _x000D_18/6/2024:#Update - Abortive visit due to access being required to flat roof and large aggressive dog blocking ability to access DP. Couldnt contact the owner of the dog to get access _x000D_17/6/2024:#Update - Abortive visit due to access being required to flat roof and large aggressive dog blocking ability to access DP. Couldnt contact the owner of the dog to get access _x000D_14/6/2024:Supplier Delay: Delayed due to health and safety issues _x000D_13/6/2024:Supplier Delay: Delayed due to health and safety issues _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983326 | 30015214 | 6.Failed router install | AM |  | 2024-06-07 | 2024-06-27 | 2024-06-27 | TRUE |  |  |  | 2024-08-01 |  |  |  | 2024-08-01 | 239004929556 |  | 2024-08-02 | 1
814 | 424958 | 1924 | Batch 4 Jun24 | Type 1 | SOGEA | Londis | LEIGH-ON-SEA | SS9 5XE | 2024-07-05 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_18/7/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_17/7/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_16/7/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_15/7/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_12/7/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_11/7/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_10/7/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_9/7/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_4/7/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_3/7/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_27/6/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_19/6/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_18/6/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_17/6/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_14/6/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_13/6/2024:Update: Order Amended _x000D_12/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/05/2024: New order added to report | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_18/7/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_17/7/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_16/7/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_15/7/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_12/7/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_11/7/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_10/7/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_9/7/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_4/7/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_3/7/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_27/6/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_19/6/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_18/6/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_17/6/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_14/6/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_13/6/2024:Update: Order Amended _x000D_12/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/05/2024: New order added to report | 0 | 0 | 2024-06-07 |  |  |  | 5.CSL | VFS983503 | 30015719 | 2.Commissioning | AM | [8 empty] | 2024-07-25 | [7 empty] | 0
815 | 449461 | 2371 | Batch 4 Jun24 | Type 1 | SoGEA/Mobile | Spar Stores | Fort William | PH33 6PH | 2024-06-13 | 6/9/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_5/9/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_4/9/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_3/9/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_2/9/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_29/8/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_28/8/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_27/8/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_22/8/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_21/8/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_20/8/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_19/8/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_19/8/2024:01434281 _x000D_16/8/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_15/8/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_14/8/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_13/8/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_12/8/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_9/8/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_8/8/2024:25/06/2024 _x000D_6/8/2024:25/06/2024 _x000D_5/8/2024:25/06/2024 _x000D_2/8/2024:25/06/2024 _x000D_1/8/2024:25/06/2024 _x000D_31/7/2024:25/06/2024 _x000D_31/7/2024:25/06/2024 _x000D_30/7/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_29/7/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_29/7/2024:01434281 _x000D_26/7/2024:01434281 _x000D_24/7/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_23/7/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_22/7/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_22/7/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_4/7/2024:#Update - Order has been delayed as track and locate work is required. CSL will update as more information become available. _x000D_3/7/2024:#Update - Order has been delayed as track and locate work is required. CSL will update as more information become available. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Order has been delayed as track and locate work is required. CSL will update as more information become available. _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_6/9/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_5/9/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_4/9/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_3/9/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_2/9/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_29/8/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_28/8/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_27/8/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_22/8/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_21/8/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_20/8/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_19/8/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_19/8/2024:01434281 _x000D_16/8/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_15/8/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_14/8/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_13/8/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_12/8/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_9/8/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_8/8/2024:25/06/2024 _x000D_6/8/2024:25/06/2024 _x000D_5/8/2024:25/06/2024 _x000D_2/8/2024:25/06/2024 _x000D_1/8/2024:25/06/2024 _x000D_31/7/2024:25/06/2024 _x000D_31/7/2024:25/06/2024 _x000D_30/7/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_29/7/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_29/7/2024:01434281 _x000D_26/7/2024:01434281 _x000D_24/7/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_23/7/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_22/7/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_22/7/2024:#Update Rescheduled to 30/07 AM. Awaiting OOH works decision _x000D_4/7/2024:#Update - Order has been delayed as track and locate work is required. CSL will update as more information become available. _x000D_3/7/2024:#Update - Order has been delayed as track and locate work is required. CSL will update as more information become available. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Order has been delayed as track and locate work is required. CSL will update as more information become available. _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update Rescheduled to 30/07 AM. Awaiting OOH works decision | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFS996869 | 30016092 | 1.Provisioning | AM |  | 2024-06-12 | 2024-08-28 |  | 0 | [11 empty] | 0
816 | 461636 | 3319 | Batch 5 Jul24 | Type 1 | SOGEA | Spar | COLERAINE | BT52 2BS |  | 1/7/2024:Order Completed _x000D_27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 1/7/2024:Order Completed _x000D_27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1015545 | 30016884 | 2.Commissioning |  |  | 2024-06-27 | 2024-06-27 | 2024-07-02 | TRUE |  |  |  | 2024-07-26 | [7 empty] | 0
817 | 657477 | 3320 | Batch 5 Jul24 | Type 1 | SOGEA | Londis | Oldbury | B69 1DF |  | 1/7/2024:Order Completed _x000D_27/6/2024:Update: Order Completed by Supplier _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 1/7/2024:Order Completed _x000D_27/6/2024:Update: Order Completed by Supplier _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366082 | 30016952 | 6.Failed router install |  |  | 2024-06-27 | 2024-06-27 | 2024-06-27 | TRUE |  |  |  | 2024-07-19 |  |  |  | 2024-07-19 | 237004907629 |  | 2024-07-23 | 1
818 | 657460 | 3323 | Batch 5 Jul24 | Type 1 | SOGEA | KDS Off Licence | Boldon Colliery | NE35 9AX |  | 19/7/2024:#Update not completed - supplier delay - new appointment date awaited _x000D_18/7/2024:#Update not completed - supplier delay - new appointment date awaited _x000D_17/7/2024:#Update not completed - supplier delay - new appointment date awaited _x000D_16/7/2024:#Update not completed - supplier delay - new appointment date awaited _x000D_15/7/2024:#Update not completed - supplier delay - new appointment date awaited _x000D_12/7/2024:#Update not completed - supplier delay - new appointment date awaited _x000D_11/7/2024:#Update not completed - supplier delay - new appointment date awaited _x000D_10/7/2024:#Update not completed - supplier delay - new appointment date awaited _x000D_9/7/2024:#Update not completed - supplier delay - new appointment date awaited _x000D_4/7/2024:#Update not completed - supplier delay - new appointment date awaited _x000D_3/7/2024:#Update not completed - supplier delay - new appointment date awaited _x000D_2/7/2024:0 _x000D_1/7/2024:#Update not completed - supplier delay - new appointment date awaited _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:#Update not completed - supplier delay - new appointment date awaited _x000D_18/7/2024:#Update not completed - supplier delay - new appointment date awaited _x000D_17/7/2024:#Update not completed - supplier delay - new appointment date awaited _x000D_16/7/2024:#Update not completed - supplier delay - new appointment date awaited _x000D_15/7/2024:#Update not completed - supplier delay - new appointment date awaited _x000D_12/7/2024:#Update not completed - supplier delay - new appointment date awaited _x000D_11/7/2024:#Update not completed - supplier delay - new appointment date awaited _x000D_10/7/2024:#Update not completed - supplier delay - new appointment date awaited _x000D_9/7/2024:#Update not completed - supplier delay - new appointment date awaited _x000D_4/7/2024:#Update not completed - supplier delay - new appointment date awaited _x000D_3/7/2024:#Update not completed - supplier delay - new appointment date awaited _x000D_2/7/2024:0 _x000D_1/7/2024:#Update not completed - supplier delay - new appointment date awaited _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015543 | 30016702 | 6.Failed router install |  |  | 2024-06-27 | 2024-06-27 | 2024-06-27 | TRUE |  |  |  | 2024-07-17 |  |  |  | 2024-07-17 | 238004926190 |  | 2024-07-17 | 1
819 | 637269 | 3327 | Batch 5 Jul24 | Type 1 | SOGEA | Premier Oval Convenience Store | Woodlands, Donaster | DN6 7UA |  | 1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015553 | 30016858 | 6.Failed router install |  |  | 2024-06-27 | 2024-06-27 | 2024-06-27 | TRUE |  |  |  | 2024-07-19 |  |  |  | 2024-07-19 | 242005008793 |  | 2024-07-23 | 1
820 | 659134 | 3328 | Batch 5 Jul24 | Type 1 | FTTP | SRA News Lifestyle Express | Birmingham | B43 7BN |  | 1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366080 | 30016731 | 6.Failed router install |  |  | 2024-06-27 | 2024-06-27 | 2024-06-27 | TRUE |  |  |  | 2024-07-19 |  |  |  | 2024-07-19 | 237004907635 |  | 2024-07-23 | 1
821 | 647170 | 3331 | Batch 5 Jul24 | Type 1 | FTTP | Paper Chase | Craigavon | BT66 6DB |  | 19/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 08/08 AM _x000D_18/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 18/07 AM _x000D_17/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 18/07 AM _x000D_16/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 18/07 AM _x000D_15/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 18/07 AM _x000D_12/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 18/07 AM _x000D_11/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 18/07 AM _x000D_10/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 18/07 AM _x000D_9/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 18/07 AM _x000D_4/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 18/07 AM _x000D_3/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 18/07 AM _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 18/07 AM _x000D_27/6/2024:#Update - Action for Allwyn - Installation has now been amended to 18/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 18/07 is a suitable date. _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 08/08 AM _x000D_18/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 18/07 AM _x000D_17/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 18/07 AM _x000D_16/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 18/07 AM _x000D_15/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 18/07 AM _x000D_12/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 18/07 AM _x000D_11/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 18/07 AM _x000D_10/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 18/07 AM _x000D_9/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 18/07 AM _x000D_4/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 18/07 AM _x000D_3/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 18/07 AM _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 18/07 AM _x000D_27/6/2024:#Update - Action for Allwyn - Installation has now been amended to 18/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 18/07 is a suitable date. _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366079 | 30016812 | 6.Failed router install |  |  | 2024-06-27 | 2024-06-27 | 2024-06-27 | TRUE |  |  |  | 2024-07-29 |  |  |  | 2024-07-29 | 23A004952888 |  | 2024-07-30 | 1
822 | 649119 | 3334 | Batch 5 Jul24 | Type 1 | FTTP | Premier Store | RUSHDEN | NN10 0BT |  | 19/7/2024:#Update - NFA - Allwyn confirmed new installation date 25/07 with retailer _x000D_18/7/2024:#Update - NFA - Allwyn confirmed new installation date 25/07 with retailer _x000D_17/7/2024:#Update - NFA - Allwyn confirmed new installation date 25/07 with retailer _x000D_16/7/2024:#Update - NFA - Allwyn confirmed new installation date 25/07 with retailer _x000D_15/7/2024:#Update - NFA - Allwyn confirmed new installation date 25/07 with retailer _x000D_12/7/2024:#Update - NFA - Allwyn confirmed new installation date 25/07 with retailer _x000D_11/7/2024:#Update - retailer's family member has passed away and requested we rearrange, so this install has been rearranged for 07/08. _x000D_10/7/2024:#Update - retailer's family member has passed away and requested we rearrange, so this install has been rearranged for 07/08. _x000D_9/7/2024:#Update - retailer's family member has passed away and requested we rearrange, so this install has been rearranged for 07/08. _x000D_4/7/2024:#Update - retailer's family member has passed away and requested we rearrange, so this install has been rearranged for 07/08. _x000D_3/7/2024:#Update - retailer's family member has passed away and requested we rearrange, so this install has been rearranged for 07/08. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - retailer's family member has passed away and requested we rearrange, so this install has been rearranged for 07/08. _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:#Update - NFA - Allwyn confirmed new installation date 25/07 with retailer _x000D_18/7/2024:#Update - NFA - Allwyn confirmed new installation date 25/07 with retailer _x000D_17/7/2024:#Update - NFA - Allwyn confirmed new installation date 25/07 with retailer _x000D_16/7/2024:#Update - NFA - Allwyn confirmed new installation date 25/07 with retailer _x000D_15/7/2024:#Update - NFA - Allwyn confirmed new installation date 25/07 with retailer _x000D_12/7/2024:#Update - NFA - Allwyn confirmed new installation date 25/07 with retailer _x000D_11/7/2024:#Update - retailer's family member has passed away and requested we rearrange, so this install has been rearranged for 07/08. _x000D_10/7/2024:#Update - retailer's family member has passed away and requested we rearrange, so this install has been rearranged for 07/08. _x000D_9/7/2024:#Update - retailer's family member has passed away and requested we rearrange, so this install has been rearranged for 07/08. _x000D_4/7/2024:#Update - retailer's family member has passed away and requested we rearrange, so this install has been rearranged for 07/08. _x000D_3/7/2024:#Update - retailer's family member has passed away and requested we rearrange, so this install has been rearranged for 07/08. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - retailer's family member has passed away and requested we rearrange, so this install has been rearranged for 07/08. _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366074 | 30016983 | 6.Failed router install |  |  | 2024-06-27 | 2024-06-27 | 2024-06-28 | TRUE |  |  |  | 2024-07-31 |  |  |  | 2024-07-24 | 23A004946019 |  | 2024-07-30 | 1
823 | 260518 | 3335 | Batch 5 Jul24 | Type 1 | SOGEA | Hills Newspoint | LONDON | E11 4RD | 2024-07-29 | 29/7/2024:#Update - NFA - Allwyn confirmed new installation date 25/07 with retailer _x000D_29/7/2024:01456441 _x000D_26/7/2024:01456441 _x000D_24/7/2024:#Update - NFA - Allwyn confirmed new installation date 25/07 with retailer _x000D_23/7/2024:#Update - NFA - Allwyn confirmed new installation date 25/07 with retailer _x000D_22/7/2024:#Update - NFA - Allwyn confirmed new installation date 25/07 with retailer _x000D_22/7/2024:#Update - NFA - Allwyn confirmed new installation date 25/07 with retailer _x000D_1/7/2024:Order Completed _x000D_27/6/2024:Update: Order Completed by Supplier _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 29/7/2024:#Update - NFA - Allwyn confirmed new installation date 25/07 with retailer _x000D_29/7/2024:01456441 _x000D_26/7/2024:01456441 _x000D_24/7/2024:#Update - NFA - Allwyn confirmed new installation date 25/07 with retailer _x000D_23/7/2024:#Update - NFA - Allwyn confirmed new installation date 25/07 with retailer _x000D_22/7/2024:#Update - NFA - Allwyn confirmed new installation date 25/07 with retailer _x000D_22/7/2024:#Update - NFA - Allwyn confirmed new installation date 25/07 with retailer _x000D_1/7/2024:Order Completed _x000D_27/6/2024:Update: Order Completed by Supplier _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1015541 | 30016958 | 6.Failed router install |  |  | 2024-06-27 | 2024-07-25 | 2024-07-25 | TRUE |  |  |  | 2024-08-16 |  |  |  | 2024-08-16 | 242005008581 | 242005008581 | 2024-08-19 | 1
824 | 463834 | 3336 | Batch 5 Jul24 | Type 1 | SOGEA | Spar | MoneyMore Co Derry | BT45 7UL |  | 3/7/2024:#Update Reallocation required because engineer received higher priority instruction from the control. Will continue to update as they come in _x000D_2/7/2024:0 _x000D_1/7/2024:#Update Reallocation required because engineer received higher priority instruction from the control. Will continue to update as they come in _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 3/7/2024:#Update Reallocation required because engineer received higher priority instruction from the control. Will continue to update as they come in _x000D_2/7/2024:0 _x000D_1/7/2024:#Update Reallocation required because engineer received higher priority instruction from the control. Will continue to update as they come in _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015540 | 30016746 | 2.Commissioning |  |  | 2024-06-27 | 2024-06-27 | 2024-06-27 | TRUE |  |  |  | 2024-07-26 | [7 empty] | 0
825 | 637456 | 3339 | Batch 5 Jul24 | Type 1 | SOGEA | Go local Extra | DONCASTER | DN11 0PF |  | 4/7/2024:#Update - this order is delayed due to third party supplier frames complications - further update to follow _x000D_3/7/2024:#Update - this order is delayed due to third party supplier frames complications - further update to follow _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - this order is delayed due to third party supplier frames complications - further update to follow _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 4/7/2024:#Update - this order is delayed due to third party supplier frames complications - further update to follow _x000D_3/7/2024:#Update - this order is delayed due to third party supplier frames complications - further update to follow _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - this order is delayed due to third party supplier frames complications - further update to follow _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015539 | 30016820 | 6.Failed router install |  |  | 2024-06-27 | 2024-06-27 | 2024-06-27 | TRUE |  |  |  | 2024-07-19 |  |  |  | 2024-07-19 | 242005008792 |  | 2024-07-23 | 1
826 | 261182 | 3341 | Batch 5 Jul24 | Type 1 | FTTP | Premier Balne Lane Convenience Stor | WAKEFIELD | WF2 0DL | 2024-07-04 | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Your order has been delayed due to a customer missed appointment. Incorrect Order type, Now order got re-appointed for 05/08/2024. _x000D_3/7/2024:Your order has been delayed due to a customer missed appointment. Incorrect Order type, Now order got re-appointed for 05/08/2024. _x000D_2/7/2024:0 _x000D_1/7/2024:Your order has been delayed due to a customer missed appointment. Incorrect Order type, Now order got re-appointed for 05/08/2024. _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Your order has been delayed due to a customer missed appointment. Incorrect Order type, Now order got re-appointed for 05/08/2024. _x000D_3/7/2024:Your order has been delayed due to a customer missed appointment. Incorrect Order type, Now order got re-appointed for 05/08/2024. _x000D_2/7/2024:0 _x000D_1/7/2024:Your order has been delayed due to a customer missed appointment. Incorrect Order type, Now order got re-appointed for 05/08/2024. _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFP2366072 | 30016949 | 6.Failed router install |  |  | 2024-06-27 | 2024-06-27 | 2024-07-03 | TRUE |  |  |  | 2024-07-26 |  |  |  | 2024-07-26 | 242005013374 |  | 2024-07-29 | 1
827 | 654365 | 3342 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Kennys Food Fayre | Newtownabbey | BT36 4SP |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 11:03 _x000D_26/7/2024:22/07/2024 11:03 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Missed appointment due to the stock still being in the way and the engineer being unable to work safely. Needs OOH appointment. Reached out to OR for the total hours and awaiting Allwyn to advise on when this will be removed/appropriate times for the retailer to retain access to the rear of the shop/out of hours appointment _x000D_18/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 19/07 AM _x000D_17/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 19/07 AM _x000D_16/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 19/07 AM _x000D_15/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 19/07 AM _x000D_12/7/2024:#Update - Action for Allwyn - Installation has now been amended to 19/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 19/07 is a suitable date. _x000D_11/7/2024:#Update - Action for Allwyn - Installation has now been amended to 19/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 19/07 is a suitable date. _x000D_10/7/2024:#Update - Action for Allwyn - Installation has now been amended to 19/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 19/07 is a suitable date. _x000D_9/7/2024:#Update - Action for Allwyn - Installation has now been amended to 19/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 19/07 is a suitable date. _x000D_4/7/2024:#Update - Action for Allwyn - Installation has now been amended to 19/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 19/07 is a suitable date. _x000D_3/7/2024:#Update - Action for Allwyn - Installation has now been amended to 19/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 19/07 is a suitable date. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Action for Allwyn - Installation has now been amended to 19/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 19/07 is a suitable date. _x000D_27/6/2024:#Update - Action for Allwyn - Installation has now been amended to 19/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 19/07 is a suitable date. _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 11:03 _x000D_26/7/2024:22/07/2024 11:03 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Missed appointment due to the stock still being in the way and the engineer being unable to work safely. Needs OOH appointment. Reached out to OR for the total hours and awaiting Allwyn to advise on when this will be removed/appropriate times for the retailer to retain access to the rear of the shop/out of hours appointment _x000D_18/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 19/07 AM _x000D_17/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 19/07 AM _x000D_16/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 19/07 AM _x000D_15/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 19/07 AM _x000D_12/7/2024:#Update - Action for Allwyn - Installation has now been amended to 19/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 19/07 is a suitable date. _x000D_11/7/2024:#Update - Action for Allwyn - Installation has now been amended to 19/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 19/07 is a suitable date. _x000D_10/7/2024:#Update - Action for Allwyn - Installation has now been amended to 19/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 19/07 is a suitable date. _x000D_9/7/2024:#Update - Action for Allwyn - Installation has now been amended to 19/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 19/07 is a suitable date. _x000D_4/7/2024:#Update - Action for Allwyn - Installation has now been amended to 19/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 19/07 is a suitable date. _x000D_3/7/2024:#Update - Action for Allwyn - Installation has now been amended to 19/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 19/07 is a suitable date. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Action for Allwyn - Installation has now been amended to 19/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 19/07 is a suitable date. _x000D_27/6/2024:#Update - Action for Allwyn - Installation has now been amended to 19/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 19/07 is a suitable date. _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2366008 | 30016905 | 1.Provisioning | AM |  | 2024-06-27 | 2024-09-06 |  | 0 | [11 empty] | 0
828 | 632556 | 3344 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Coras | Hartlepool | TS25 1TU |  | 6/9/2024:#Update - Awaiting feedback from OR regarding approved OOH appointment. Will confirm date ASAP _x000D_5/9/2024:#Update - Awaiting feedback from OR regarding approved OOH appointment. Will confirm date ASAP _x000D_4/9/2024:#Update - Awaiting feedback from OR regarding approved OOH appointment. Will confirm date ASAP _x000D_3/9/2024:#Update - Awaiting feedback from OR regarding approved OOH appointment. Will confirm date ASAP _x000D_2/9/2024:#Update - Awaiting feedback from OR regarding approved OOH appointment. Will confirm date ASAP _x000D_29/8/2024:#Update - Awaiting feedback from OR regarding approved OOH appointment. Will confirm date ASAP _x000D_28/8/2024:#Update - Awaiting feedback from OR regarding approved OOH appointment. Will confirm date ASAP _x000D_27/8/2024:#Update - Awaiting feedback from OR regarding approved OOH appointment. Will confirm date ASAP _x000D_22/8/2024:#Update - Awaiting response from Openreach about arranging the OOH appointment. - May take a while given the opening times for this store- Hoping to hear back about when the engineer can attend _x000D_21/8/2024:#Update - Awaiting response from Openreach about arranging the OOH appointment. - May take a while given the opening times for this store- Hoping to hear back about when the engineer can attend _x000D_20/8/2024:#Update - Awaiting ECCS approval. _x000D_19/8/2024:#Update - Awaiting ECCS approval. _x000D_19/8/2024:01455549 _x000D_16/8/2024:#Update - Awaiting ECCS approval. _x000D_15/8/2024:#Update - Awaiting ECCS approval. _x000D_14/8/2024:#Update - Awaiting ECCS approval. _x000D_13/8/2024:#Update - Awaiting ECCS approval. _x000D_12/8/2024:#Update - Awaiting ECCS approval. _x000D_9/8/2024:#Update - Awaiting ECCS approval. _x000D_8/8/2024:30/07/2024 _x000D_6/8/2024:30/07/2024 _x000D_5/8/2024:30/07/2024 _x000D_2/8/2024:30/07/2024 _x000D_1/8/2024:30/07/2024 _x000D_31/7/2024:30/07/2024 _x000D_31/7/2024:30/07/2024 _x000D_30/7/2024:#Update - Awaiting ECCS approval. _x000D_29/7/2024:#Update - Missed appointment due to the stock still being in the way and the engineer being unable to work safely. Needs OOH appointment. Reached out to OR for the total hours and awaiting Allwyn to advise on when this will be removed/appropriate times for the retailer to retain access to the rear of the shop/out of hours appointment _x000D_29/7/2024:01455549 _x000D_26/7/2024:01455549 _x000D_24/7/2024:#Update - Missed appointment due to the stock still being in the way and the engineer being unable to work safely. Needs OOH appointment. Reached out to OR for the total hours and awaiting Allwyn to advise on when this will be removed/appropriate times for the retailer to retain access to the rear of the shop/out of hours appointment _x000D_23/7/2024:#Update - Missed appointment due to the stock still being in the way and the engineer being unable to work safely. Needs OOH appointment. Reached out to OR for the total hours and awaiting Allwyn to advise on when this will be removed/appropriate times for the retailer to retain access to the rear of the shop/out of hours appointment _x000D_22/7/2024:#Update - Missed appointment due to the stock still being in the way and the engineer being unable to work safely. Needs OOH appointment. Reached out to OR for the total hours and awaiting Allwyn to advise on when this will be removed/appropriate times for the retailer to retain access to the rear of the shop/out of hours appointment _x000D_22/7/2024:#Update - Missed appointment due to the stock still being in the way and the engineer being unable to work safely. Needs OOH appointment. Reached out to OR for the total hours and awaiting Allwyn to advise on when this will be removed/appropriate times for the retailer to retain access to the rear of the shop/out of hours appointment _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - Awaiting feedback from OR regarding approved OOH appointment. Will confirm date ASAP _x000D_6/9/2024:#Update - Awaiting feedback from OR regarding approved OOH appointment. Will confirm date ASAP _x000D_5/9/2024:#Update - Awaiting feedback from OR regarding approved OOH appointment. Will confirm date ASAP _x000D_4/9/2024:#Update - Awaiting feedback from OR regarding approved OOH appointment. Will confirm date ASAP _x000D_3/9/2024:#Update - Awaiting feedback from OR regarding approved OOH appointment. Will confirm date ASAP _x000D_2/9/2024:#Update - Awaiting feedback from OR regarding approved OOH appointment. Will confirm date ASAP _x000D_29/8/2024:#Update - Awaiting feedback from OR regarding approved OOH appointment. Will confirm date ASAP _x000D_28/8/2024:#Update - Awaiting feedback from OR regarding approved OOH appointment. Will confirm date ASAP _x000D_27/8/2024:#Update - Awaiting feedback from OR regarding approved OOH appointment. Will confirm date ASAP _x000D_22/8/2024:#Update - Awaiting response from Openreach about arranging the OOH appointment. - May take a while given the opening times for this store- Hoping to hear back about when the engineer can attend _x000D_21/8/2024:#Update - Awaiting response from Openreach about arranging the OOH appointment. - May take a while given the opening times for this store- Hoping to hear back about when the engineer can attend _x000D_20/8/2024:#Update - Awaiting ECCS approval. _x000D_19/8/2024:#Update - Awaiting ECCS approval. _x000D_19/8/2024:01455549 _x000D_16/8/2024:#Update - Awaiting ECCS approval. _x000D_15/8/2024:#Update - Awaiting ECCS approval. _x000D_14/8/2024:#Update - Awaiting ECCS approval. _x000D_13/8/2024:#Update - Awaiting ECCS approval. _x000D_12/8/2024:#Update - Awaiting ECCS approval. _x000D_9/8/2024:#Update - Awaiting ECCS approval. _x000D_8/8/2024:30/07/2024 _x000D_6/8/2024:30/07/2024 _x000D_5/8/2024:30/07/2024 _x000D_2/8/2024:30/07/2024 _x000D_1/8/2024:30/07/2024 _x000D_31/7/2024:30/07/2024 _x000D_31/7/2024:30/07/2024 _x000D_30/7/2024:#Update - Awaiting ECCS approval. _x000D_29/7/2024:#Update - Missed appointment due to the stock still being in the way and the engineer being unable to work safely. Needs OOH appointment. Reached out to OR for the total hours and awaiting Allwyn to advise on when this will be removed/appropriate times for the retailer to retain access to the rear of the shop/out of hours appointment _x000D_29/7/2024:01455549 _x000D_26/7/2024:01455549 _x000D_24/7/2024:#Update - Missed appointment due to the stock still being in the way and the engineer being unable to work safely. Needs OOH appointment. Reached out to OR for the total hours and awaiting Allwyn to advise on when this will be removed/appropriate times for the retailer to retain access to the rear of the shop/out of hours appointment _x000D_23/7/2024:#Update - Missed appointment due to the stock still being in the way and the engineer being unable to work safely. Needs OOH appointment. Reached out to OR for the total hours and awaiting Allwyn to advise on when this will be removed/appropriate times for the retailer to retain access to the rear of the shop/out of hours appointment _x000D_22/7/2024:#Update - Missed appointment due to the stock still being in the way and the engineer being unable to work safely. Needs OOH appointment. Reached out to OR for the total hours and awaiting Allwyn to advise on when this will be removed/appropriate times for the retailer to retain access to the rear of the shop/out of hours appointment _x000D_22/7/2024:#Update - Missed appointment due to the stock still being in the way and the engineer being unable to work safely. Needs OOH appointment. Reached out to OR for the total hours and awaiting Allwyn to advise on when this will be removed/appropriate times for the retailer to retain access to the rear of the shop/out of hours appointment _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update - Awaiting feedback from OR regarding approved OOH appointment. Will confirm date ASAP | 2024-06-07 |  |  |  |  | VFP2366073 | 30016757 | 1.Provisioning | AM |  | 2024-06-27 | 2024-09-16 |  | 0 | [11 empty] | 0
829 | 445258 | 3345 | Batch 5 Jul24 | Type 1 | SOGEA | Premier Abbey News | WREXHAM | LL13 8YH |  | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Your order has been delayed due to a customer missed appointment. Customer not received router. Please check with end user and reappoint the order if still required. _x000D_3/7/2024:Your order has been delayed due to a customer missed appointment. Customer not received router. Please check with end user and reappoint the order if still required. _x000D_2/7/2024:0 _x000D_1/7/2024:Your order has been delayed due to a customer missed appointment. Customer not received router. Please check with end user and reappoint the order if still required. _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Your order has been delayed due to a customer missed appointment. Customer not received router. Please check with end user and reappoint the order if still required. _x000D_3/7/2024:Your order has been delayed due to a customer missed appointment. Customer not received router. Please check with end user and reappoint the order if still required. _x000D_2/7/2024:0 _x000D_1/7/2024:Your order has been delayed due to a customer missed appointment. Customer not received router. Please check with end user and reappoint the order if still required. _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015537 | 30016887 | 6.Failed router install |  |  | 2024-06-27 | 2024-06-27 | 2024-06-27 | TRUE |  |  |  | 2024-07-30 |  |  |  | 2024-07-30 | 242005008946 |  | 2024-07-30 | 1
830 | 640327 | 3346 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Premier CH Brown | BIRMINGHAM | B33 9LZ |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 11:27 _x000D_26/7/2024:22/07/2024 11:27 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update – The installation could not be completed as shelving and stock is in the way of the cable entry point (BT80). The engineer has advised that the work will need to be completed in a quieter time when they are able move this. Additionally, to progress the engineer would need permission to drill tetra in the adjacent shop to run the line to the DP. And there is also scaffolding currently blocking the front of the shop so they cannot proceed until this has been removed. _x000D_18/7/2024:#Update – The installation could not be completed as shelving and stock is in the way of the cable entry point (BT80). The engineer has advised that the work will need to be completed in a quieter time when they are able move this. Additionally, to progress the engineer would need permission to drill tetra in the adjacent shop to run the line to the DP. And there is also scaffolding currently blocking the front of the shop so they cannot proceed until this has been removed. _x000D_17/7/2024:#Update – The installation could not be completed as shelving and stock is in the way of the cable entry point (BT80). The engineer has advised that the work will need to be completed in a quieter time when they are able move this. Additionally, to progress the engineer would need permission to drill tetra in the adjacent shop to run the line to the DP. And there is also scaffolding currently blocking the front of the shop so they cannot proceed until this has been removed. _x000D_16/7/2024:#Update – The installation could not be completed as shelving and stock is in the way of the cable entry point (BT80). The engineer has advised that the work will need to be completed in a quieter time when they are able move this. Additionally, to progress the engineer would need permission to drill tetra in the adjacent shop to run the line to the DP. And there is also scaffolding currently blocking the front of the shop so they cannot proceed until this has been removed. _x000D_15/7/2024:#Update – The installation could not be completed as shelving and stock is in the way of the cable entry point (BT80). The engineer has advised that the work will need to be completed in a quieter time when they are able move this. Additionally, to progress the engineer would need permission to drill tetra in the adjacent shop to run the line to the DP. And there is also scaffolding currently blocking the front of the shop so they cannot proceed until this has been removed. _x000D_12/7/2024:#Update – The installation could not be completed as shelving and stock is in the way of the cable entry point (BT80). The engineer has advised that the work will need to be completed in a quieter time when they are able move this. Additionally, to progress the engineer would need permission to drill tetra in the adjacent shop to run the line to the DP. And there is also scaffolding currently blocking the front of the shop so they cannot proceed until this has been removed. _x000D_11/7/2024:#Update – The installation could not be completed as shelving and stock is in the way of the cable entry point (BT80). The engineer has advised that the work will need to be completed in a quieter time when they are able move this. Additionally, to progress the engineer would need permission to drill tetra in the adjacent shop to run the line to the DP. And there is also scaffolding currently blocking the front of the shop so they cannot proceed until this has been removed. _x000D_10/7/2024:#Update – The installation could not be completed as shelving and stock is in the way of the cable entry point (BT80). The engineer has advised that the work will need to be completed in a quieter time when they are able move this. Additionally, to progress the engineer would need permission to drill tetra in the adjacent shop to run the line to the DP. And there is also scaffolding currently blocking the front of the shop so they cannot proceed until this has been removed. _x000D_9/7/2024:#Update - Awaiting for more information for Openreach. CSL will update as more information become available. _x000D_4/7/2024:#Update - Awaiting for more information for Openreach. CSL will update as more information become available. _x000D_3/7/2024:#Update - Awaiting for more information for Openreach. CSL will update as more information become available. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Awaiting for more information for Openreach. CSL will update as more information become available. _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 11:27 _x000D_26/7/2024:22/07/2024 11:27 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update – The installation could not be completed as shelving and stock is in the way of the cable entry point (BT80). The engineer has advised that the work will need to be completed in a quieter time when they are able move this. Additionally, to progress the engineer would need permission to drill tetra in the adjacent shop to run the line to the DP. And there is also scaffolding currently blocking the front of the shop so they cannot proceed until this has been removed. _x000D_18/7/2024:#Update – The installation could not be completed as shelving and stock is in the way of the cable entry point (BT80). The engineer has advised that the work will need to be completed in a quieter time when they are able move this. Additionally, to progress the engineer would need permission to drill tetra in the adjacent shop to run the line to the DP. And there is also scaffolding currently blocking the front of the shop so they cannot proceed until this has been removed. _x000D_17/7/2024:#Update – The installation could not be completed as shelving and stock is in the way of the cable entry point (BT80). The engineer has advised that the work will need to be completed in a quieter time when they are able move this. Additionally, to progress the engineer would need permission to drill tetra in the adjacent shop to run the line to the DP. And there is also scaffolding currently blocking the front of the shop so they cannot proceed until this has been removed. _x000D_16/7/2024:#Update – The installation could not be completed as shelving and stock is in the way of the cable entry point (BT80). The engineer has advised that the work will need to be completed in a quieter time when they are able move this. Additionally, to progress the engineer would need permission to drill tetra in the adjacent shop to run the line to the DP. And there is also scaffolding currently blocking the front of the shop so they cannot proceed until this has been removed. _x000D_15/7/2024:#Update – The installation could not be completed as shelving and stock is in the way of the cable entry point (BT80). The engineer has advised that the work will need to be completed in a quieter time when they are able move this. Additionally, to progress the engineer would need permission to drill tetra in the adjacent shop to run the line to the DP. And there is also scaffolding currently blocking the front of the shop so they cannot proceed until this has been removed. _x000D_12/7/2024:#Update – The installation could not be completed as shelving and stock is in the way of the cable entry point (BT80). The engineer has advised that the work will need to be completed in a quieter time when they are able move this. Additionally, to progress the engineer would need permission to drill tetra in the adjacent shop to run the line to the DP. And there is also scaffolding currently blocking the front of the shop so they cannot proceed until this has been removed. _x000D_11/7/2024:#Update – The installation could not be completed as shelving and stock is in the way of the cable entry point (BT80). The engineer has advised that the work will need to be completed in a quieter time when they are able move this. Additionally, to progress the engineer would need permission to drill tetra in the adjacent shop to run the line to the DP. And there is also scaffolding currently blocking the front of the shop so they cannot proceed until this has been removed. _x000D_10/7/2024:#Update – The installation could not be completed as shelving and stock is in the way of the cable entry point (BT80). The engineer has advised that the work will need to be completed in a quieter time when they are able move this. Additionally, to progress the engineer would need permission to drill tetra in the adjacent shop to run the line to the DP. And there is also scaffolding currently blocking the front of the shop so they cannot proceed until this has been removed. _x000D_9/7/2024:#Update - Awaiting for more information for Openreach. CSL will update as more information become available. _x000D_4/7/2024:#Update - Awaiting for more information for Openreach. CSL will update as more information become available. _x000D_3/7/2024:#Update - Awaiting for more information for Openreach. CSL will update as more information become available. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Awaiting for more information for Openreach. CSL will update as more information become available. _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2366070 | 30016806 | 1.Provisioning | AM |  | 2024-06-27 | 2024-09-06 |  | 0 | [11 empty] | 0
831 | 654635 | 3351 | Batch 5 Jul24 | Type 1 | FTTP | Child Avenue Convenience Store | Bilston | WV14 9XB |  | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366009 | 30016889 | 6.Failed router install |  |  | 2024-06-27 | 2024-06-27 | 2024-06-27 | TRUE |  |  |  | 2024-07-18 |  |  |  | 2024-07-18 | 237004907638 |  | 2024-07-19 | 1
832 | 664484 | 3352 | Batch 5 Jul24 | Type 1 | FTTP | Whitburn Post Office | Whitburn | EH47 0RD |  | 23/7/2024:#Update - Completed 19/07 _x000D_22/7/2024:#Update - Completed 19/07 _x000D_22/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 23/7/2024:#Update - Completed 19/07 _x000D_22/7/2024:#Update - Completed 19/07 _x000D_22/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366071 | 30016753 | 6.Failed router install |  |  | 2024-06-27 | 2024-07-19 | 2024-07-19 | TRUE |  |  |  | 2024-08-09 |  |  |  | 2024-08-09 | 239004929625 |  | 2024-08-12 | 1
833 | 667421 | 3355 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Ladybrook Lane Post Office | MANSFIELD | NG18 5JP |  | 6/9/2024:#Update - Awaiting for allwyn to confirm if the retailer has resolved power outlet issue near the lotto terminal _x000D_5/9/2024:#Update - Awaiting for allwyn to confirm if the retailer has resolved power outlet issue near the lotto terminal _x000D_4/9/2024:#Update - Awaiting for allwyn to confirm if the retailer has resolved power outlet issue near the lotto terminal _x000D_3/9/2024:#Update - Awaiting for allwyn to confirm if the retailer has resolved power outlet issue near the lotto terminal _x000D_2/9/2024:#Update - Awaiting for allwyn to confirm if the retailer has resolved power outlet issue near the lotto terminal _x000D_29/8/2024:#Update - Awaiting for allwyn to confirm if the retailer has resolved power outlet issue near the lotto terminal _x000D_28/8/2024:#Update - Awaiting for allwyn to confirm if the retailer has resolved power outlet issue near the lotto terminal _x000D_27/8/2024:#Update - Awaiting for allwyn to confirm if the retailer has resolved power outlet issue near the lotto terminal _x000D_22/8/2024:#Update - Awaiting for allwyn to confirm if the retailer has resolved power outlet issue near the lotto terminal _x000D_21/8/2024:#Update - Awaiting for allwyn to confirm if the retailer has resolved power outlet issue near the lotto terminal _x000D_20/8/2024:#Update - Awaiting for allwyn to confirm if the retailer has resolved power outlet issue near the lotto terminal _x000D_19/8/2024:#Update - Awaiting for allwyn to confirm if the retailer has resolved power outlet issue near the lotto terminal _x000D_19/8/2024:01457078 _x000D_16/8/2024:#Update - Awaiting for allwyn to confirm if the retailer has resolved power outlet issue near the lotto terminal _x000D_15/8/2024:#Update - Awaiting for allwyn to confirm if the retailer has resolved power outlet issue near the lotto terminal _x000D_14/8/2024:#Update - Awaiting for allwyn to confirm if the retailer has resolved power outlet issue near the lotto terminal _x000D_13/8/2024:#Update - Awaiting for allwyn to confirm if the retailer has resolved power outlet issue near the lotto terminal _x000D_12/8/2024:#Update - Awaiting for allwyn to confirm if the retailer has resolved power outlet issue near the lotto terminal _x000D_9/8/2024:#Update - Awaiting for allwyn to confirm if the retailer has resolved power outlet issue near the lotto terminal _x000D_8/8/2024:29/07/2024 _x000D_6/8/2024:29/07/2024 _x000D_5/8/2024:29/07/2024 _x000D_2/8/2024:29/07/2024 _x000D_1/8/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_30/7/2024:#Update - Awaiting for allwyn to confirm if the retailer has resolved power outlet issue near the lotto terminal _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_3/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_2/7/2024:0 _x000D_1/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - Awaiting for allwyn to confirm if the retailer has resolved power outlet issue near the lotto terminal _x000D_6/9/2024:#Update - Awaiting for allwyn to confirm if the retailer has resolved power outlet issue near the lotto terminal _x000D_5/9/2024:#Update - Awaiting for allwyn to confirm if the retailer has resolved power outlet issue near the lotto terminal _x000D_4/9/2024:#Update - Awaiting for allwyn to confirm if the retailer has resolved power outlet issue near the lotto terminal _x000D_3/9/2024:#Update - Awaiting for allwyn to confirm if the retailer has resolved power outlet issue near the lotto terminal _x000D_2/9/2024:#Update - Awaiting for allwyn to confirm if the retailer has resolved power outlet issue near the lotto terminal _x000D_29/8/2024:#Update - Awaiting for allwyn to confirm if the retailer has resolved power outlet issue near the lotto terminal _x000D_28/8/2024:#Update - Awaiting for allwyn to confirm if the retailer has resolved power outlet issue near the lotto terminal _x000D_27/8/2024:#Update - Awaiting for allwyn to confirm if the retailer has resolved power outlet issue near the lotto terminal _x000D_22/8/2024:#Update - Awaiting for allwyn to confirm if the retailer has resolved power outlet issue near the lotto terminal _x000D_21/8/2024:#Update - Awaiting for allwyn to confirm if the retailer has resolved power outlet issue near the lotto terminal _x000D_20/8/2024:#Update - Awaiting for allwyn to confirm if the retailer has resolved power outlet issue near the lotto terminal _x000D_19/8/2024:#Update - Awaiting for allwyn to confirm if the retailer has resolved power outlet issue near the lotto terminal _x000D_19/8/2024:01457078 _x000D_16/8/2024:#Update - Awaiting for allwyn to confirm if the retailer has resolved power outlet issue near the lotto terminal _x000D_15/8/2024:#Update - Awaiting for allwyn to confirm if the retailer has resolved power outlet issue near the lotto terminal _x000D_14/8/2024:#Update - Awaiting for allwyn to confirm if the retailer has resolved power outlet issue near the lotto terminal _x000D_13/8/2024:#Update - Awaiting for allwyn to confirm if the retailer has resolved power outlet issue near the lotto terminal _x000D_12/8/2024:#Update - Awaiting for allwyn to confirm if the retailer has resolved power outlet issue near the lotto terminal _x000D_9/8/2024:#Update - Awaiting for allwyn to confirm if the retailer has resolved power outlet issue near the lotto terminal _x000D_8/8/2024:29/07/2024 _x000D_6/8/2024:29/07/2024 _x000D_5/8/2024:29/07/2024 _x000D_2/8/2024:29/07/2024 _x000D_1/8/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_30/7/2024:#Update - Awaiting for allwyn to confirm if the retailer has resolved power outlet issue near the lotto terminal _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_3/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_2/7/2024:0 _x000D_1/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update - Awaiting for allwyn to confirm if the retailer has resolved power outlet issue near the lotto terminal | 2024-06-07 |  |  |  |  | VFP2366069 | 30016826 | 1.Provisioning | AM |  | 2024-06-27 | 2024-08-27 |  | 0 | [11 empty] | 0
834 | 663656 | 3356 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Easington Village News Ltd | PETERLEE | SR8 3AU |  | 6/9/2024:#Update - Awaiting engineer to be allocated for a sunday appoint. _x000D_5/9/2024:#Update - Awaiting engineer to be allocated for a sunday appoint. _x000D_4/9/2024:#Update - Awaiting engineer to be allocated for a sunday appoint. _x000D_3/9/2024:#Update - Awaiting engineer to be allocated for a sunday appoint. _x000D_2/9/2024:#Update - Awaiting engineer to be allocated for a sunday appoint. _x000D_29/8/2024:#Update - Awaiting engineer to be allocated for a sunday appoint. _x000D_28/8/2024:#Update - Awaiting engineer to be allocated for a sunday appoint. _x000D_27/8/2024:#Update - Awaiting engineer to be allocated for a sunday appoint. _x000D_22/8/2024:#Update - Awaiting engineer to be allocated for a sunday appoint. _x000D_21/8/2024:#Update - Awaiting engineer to be allocated for a sunday appoint. _x000D_20/8/2024:#Update - Awaiting engineer to be allocated for a sunday appoint. _x000D_19/8/2024:#Update - Awaiting engineer to be allocated for a sunday appoint. _x000D_19/8/2024:01458475 _x000D_16/8/2024:#Update - Awaiting engineer to be allocated for a sunday appoint. _x000D_15/8/2024:#Update - Awaiting engineer to be allocated for a sunday appoint. _x000D_14/8/2024:#Update - Awaiting engineer to be allocated for a sunday appoint. _x000D_13/8/2024:#Update - Awaiting engineer to be allocated for a sunday appoint. _x000D_12/8/2024:#Update - Awaiting engineer to be allocated for a sunday appoint. _x000D_9/8/2024:#Update - Awaiting engineer to be allocated for a sunday appoint. _x000D_8/8/2024:31/07/2024 _x000D_6/8/2024:31/07/2024 _x000D_5/8/2024:31/07/2024 _x000D_2/8/2024:31/07/2024 _x000D_1/8/2024:31/07/2024 _x000D_31/7/2024:30/07/2024 _x000D_31/7/2024:30/07/2024 _x000D_30/7/2024:#Update - Awaiting ECC approval. _x000D_29/7/2024:#Update - Awaiting ECC approval. _x000D_29/7/2024:01458475 _x000D_26/7/2024:01458475 _x000D_24/7/2024:#Update - Awaiting ECC approval. _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - Awaiting engineer to be allocated for a sunday appoint. _x000D_6/9/2024:#Update - Awaiting engineer to be allocated for a sunday appoint. _x000D_5/9/2024:#Update - Awaiting engineer to be allocated for a sunday appoint. _x000D_4/9/2024:#Update - Awaiting engineer to be allocated for a sunday appoint. _x000D_3/9/2024:#Update - Awaiting engineer to be allocated for a sunday appoint. _x000D_2/9/2024:#Update - Awaiting engineer to be allocated for a sunday appoint. _x000D_29/8/2024:#Update - Awaiting engineer to be allocated for a sunday appoint. _x000D_28/8/2024:#Update - Awaiting engineer to be allocated for a sunday appoint. _x000D_27/8/2024:#Update - Awaiting engineer to be allocated for a sunday appoint. _x000D_22/8/2024:#Update - Awaiting engineer to be allocated for a sunday appoint. _x000D_21/8/2024:#Update - Awaiting engineer to be allocated for a sunday appoint. _x000D_20/8/2024:#Update - Awaiting engineer to be allocated for a sunday appoint. _x000D_19/8/2024:#Update - Awaiting engineer to be allocated for a sunday appoint. _x000D_19/8/2024:01458475 _x000D_16/8/2024:#Update - Awaiting engineer to be allocated for a sunday appoint. _x000D_15/8/2024:#Update - Awaiting engineer to be allocated for a sunday appoint. _x000D_14/8/2024:#Update - Awaiting engineer to be allocated for a sunday appoint. _x000D_13/8/2024:#Update - Awaiting engineer to be allocated for a sunday appoint. _x000D_12/8/2024:#Update - Awaiting engineer to be allocated for a sunday appoint. _x000D_9/8/2024:#Update - Awaiting engineer to be allocated for a sunday appoint. _x000D_8/8/2024:31/07/2024 _x000D_6/8/2024:31/07/2024 _x000D_5/8/2024:31/07/2024 _x000D_2/8/2024:31/07/2024 _x000D_1/8/2024:31/07/2024 _x000D_31/7/2024:30/07/2024 _x000D_31/7/2024:30/07/2024 _x000D_30/7/2024:#Update - Awaiting ECC approval. _x000D_29/7/2024:#Update - Awaiting ECC approval. _x000D_29/7/2024:01458475 _x000D_26/7/2024:01458475 _x000D_24/7/2024:#Update - Awaiting ECC approval. _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update - Awaiting engineer to be allocated for a sunday appoint. | 2024-06-07 |  |  |  |  | VFP2366005 | 30016906 | 1.Provisioning | AM |  | 2024-08-06 | 2024-08-19 |  | 0 | [11 empty] | 0
835 | 410517 | 3359 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Budgens | SELBY | YO8 5XA |  | 22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_19/8/2024:01457230 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_13/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_12/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_9/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_8/8/2024:18/07/2024 _x000D_6/8/2024:18/07/2024 _x000D_5/8/2024:18/07/2024 _x000D_2/8/2024:18/07/2024 _x000D_1/8/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_30/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_29/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_29/7/2024:01457230 _x000D_26/7/2024:01457230 _x000D_24/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_23/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_22/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_22/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_19/8/2024:01457230 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_13/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_12/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_9/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_8/8/2024:18/07/2024 _x000D_6/8/2024:18/07/2024 _x000D_5/8/2024:18/07/2024 _x000D_2/8/2024:18/07/2024 _x000D_1/8/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_30/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_29/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_29/7/2024:01457230 _x000D_26/7/2024:01457230 _x000D_24/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_23/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_22/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_22/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/08 AM _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1057045 | 30021846 | 6.Failed router install | [9 empty] | 2024-08-23 |  |  |  | 2024-08-23 | 23A004948614 | 23A004948614 | 2024-08-23 | 1
836 | 465501 | 3362 | Batch 5 Jul24 | Type 1 | FTTP | Johns News | ILKESTON | DE7 8AH | 2024-07-02 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:Update: Order Amended _x000D_17/7/2024:Update: Order Amended _x000D_16/7/2024:Update: Order Amended _x000D_15/7/2024:Update: Order Amended _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:Update: Order Amended _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:Update: Order Amended _x000D_17/7/2024:Update: Order Amended _x000D_16/7/2024:Update: Order Amended _x000D_15/7/2024:Update: Order Amended _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:Update: Order Amended _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | 0 | 2024-06-07 |  |  |  |  | VFP2366076 | 30016835 | 2.Commissioning | [9 empty] | 2024-07-25 | [7 empty] | 0
837 | 618265 | 3363 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Nisa Local | Walton-On-Thames | KT12 2BL |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:30/07/2024 _x000D_1/8/2024:30/07/2024 _x000D_31/7/2024:30/07/2024 _x000D_31/7/2024:30/07/2024 _x000D_30/7/2024:#Update - Installation completed. _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:Update: Order Amended _x000D_1/7/2024:Order Completed _x000D_27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:30/07/2024 _x000D_1/8/2024:30/07/2024 _x000D_31/7/2024:30/07/2024 _x000D_31/7/2024:30/07/2024 _x000D_30/7/2024:#Update - Installation completed. _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:Update: Order Amended _x000D_1/7/2024:Order Completed _x000D_27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | 0 | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366066 | 30016902 | 2.Commissioning | [9 empty] | 2024-08-21 | [7 empty] | 0
838 | 609803 | 3366 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Normans News | Northampton | NN5 5LE |  | 6/9/2024:#Update - The Openreach notes state that the external works have been completed however the engineer was unable to find a route to get the cable inside. The only route possible is in the upper left corner of the shop above the metal shutters but this route is blocked by an internal case holder for the metal shutter and is only accessible behind the shelving units behind the tills. There are also electric power cables running in this area making it unsafe to drill without removing the case to identify where they go. The engineer has said that to progress the retailer needs to remove the shelving to provide a route inside or provide an alternative option _x000D_5/9/2024:#Update - The Openreach notes state that the external works have been completed however the engineer was unable to find a route to get the cable inside. The only route possible is in the upper left corner of the shop above the metal shutters but this route is blocked by an internal case holder for the metal shutter and is only accessible behind the shelving units behind the tills. There are also electric power cables running in this area making it unsafe to drill without removing the case to identify where they go. The engineer has said that to progress the retailer needs to remove the shelving to provide a route inside or provide an alternative option _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/08 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/08 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/08 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/08 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/08 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/08 AM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/08 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/08 AM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/08 AM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/08 AM _x000D_19/8/2024:01456736 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/08 AM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/08 AM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/08 AM _x000D_13/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/08 AM _x000D_12/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/08 AM _x000D_9/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/08 AM _x000D_8/8/2024:01/08/2024 _x000D_6/8/2024:01/08/2024 _x000D_5/8/2024:01/08/2024 _x000D_2/8/2024:01/08/2024 _x000D_1/8/2024:01/08/2024 _x000D_31/7/2024:17/07/2024 _x000D_31/7/2024:17/07/2024 _x000D_30/7/2024:#Update - Action for Allwyn - Installation has now been amended to 12/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 10/08 is a suitable date. _x000D_29/7/2024:#Update - Action for Allwyn - Installation has now been amended to 12/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 10/08 is a suitable date. _x000D_29/7/2024:01456736 _x000D_26/7/2024:01456736 _x000D_24/7/2024:#Update - Action for Allwyn - Installation has now been amended to 12/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 10/08 is a suitable date. _x000D_23/7/2024:#Update - Action for Allwyn - Installation has now been amended to 12/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 10/08 is a suitable date. _x000D_22/7/2024:#Update - Action for Allwyn - Installation has now been amended to 12/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 10/08 is a suitable date. _x000D_22/7/2024:#Update - Action for Allwyn - Installation has now been amended to 12/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 10/08 is a suitable date. _x000D_1/7/2024:Order Completed _x000D_27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - The Openreach notes state that the external works have been completed however the engineer was unable to find a route to get the cable inside. The only route possible is in the upper left corner of the shop above the metal shutters but this route is blocked by an internal case holder for the metal shutter and is only accessible behind the shelving units behind the tills. There are also electric power cables running in this area making it unsafe to drill without removing the case to identify where they go. The engineer has said that to progress the retailer needs to remove the shelving to provide a route inside or provide an alternative option _x000D_6/9/2024:#Update - The Openreach notes state that the external works have been completed however the engineer was unable to find a route to get the cable inside. The only route possible is in the upper left corner of the shop above the metal shutters but this route is blocked by an internal case holder for the metal shutter and is only accessible behind the shelving units behind the tills. There are also electric power cables running in this area making it unsafe to drill without removing the case to identify where they go. The engineer has said that to progress the retailer needs to remove the shelving to provide a route inside or provide an alternative option _x000D_5/9/2024:#Update - The Openreach notes state that the external works have been completed however the engineer was unable to find a route to get the cable inside. The only route possible is in the upper left corner of the shop above the metal shutters but this route is blocked by an internal case holder for the metal shutter and is only accessible behind the shelving units behind the tills. There are also electric power cables running in this area making it unsafe to drill without removing the case to identify where they go. The engineer has said that to progress the retailer needs to remove the shelving to provide a route inside or provide an alternative option _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/08 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/08 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/08 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/08 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/08 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/08 AM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/08 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/08 AM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/08 AM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/08 AM _x000D_19/8/2024:01456736 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/08 AM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/08 AM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/08 AM _x000D_13/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/08 AM _x000D_12/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/08 AM _x000D_9/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/08 AM _x000D_8/8/2024:01/08/2024 _x000D_6/8/2024:01/08/2024 _x000D_5/8/2024:01/08/2024 _x000D_2/8/2024:01/08/2024 _x000D_1/8/2024:01/08/2024 _x000D_31/7/2024:17/07/2024 _x000D_31/7/2024:17/07/2024 _x000D_30/7/2024:#Update - Action for Allwyn - Installation has now been amended to 12/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 10/08 is a suitable date. _x000D_29/7/2024:#Update - Action for Allwyn - Installation has now been amended to 12/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 10/08 is a suitable date. _x000D_29/7/2024:01456736 _x000D_26/7/2024:01456736 _x000D_24/7/2024:#Update - Action for Allwyn - Installation has now been amended to 12/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 10/08 is a suitable date. _x000D_23/7/2024:#Update - Action for Allwyn - Installation has now been amended to 12/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 10/08 is a suitable date. _x000D_22/7/2024:#Update - Action for Allwyn - Installation has now been amended to 12/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 10/08 is a suitable date. _x000D_22/7/2024:#Update - Action for Allwyn - Installation has now been amended to 12/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 10/08 is a suitable date. _x000D_1/7/2024:Order Completed _x000D_27/6/2024:Order Completed _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | #Update - The Openreach notes state that the external works have been completed however the engineer was unable to find a route to get the cable inside. The only route possible is in the upper left corner of the shop above the metal shutters but this route is blocked by an internal case holder for the metal shutter and is only accessible behind the shelving units behind the tills. There are also electric power cables running in this area making it unsafe to drill without removing the case to identify where they go. The engineer has said that to progress the retailer needs to remove the shelving to provide a route inside or provide an alternative option | 2024-06-07 |  |  |  |  | VFP2366065 | 30016866 | 1.Provisioning | AM |  | 2024-06-27 | 2024-08-21 |  | 0 | [11 empty] | 0
839 | 664721 | 3367 | Batch 5 Jul24 | Type 1 | FTTP | Wilson Road PO & Store | Cardiff | CF23 9PL |  | 1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366004 | 30016644 | 2.Commissioning |  |  | 2024-06-27 | 2024-06-27 | 2024-06-27 | TRUE |  |  |  | 2024-07-30 | [7 empty] | 0
840 | 448154 | 3372 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Mckee Convenience Store | BELFAST | BT12 7JE |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 15:13 _x000D_26/7/2024:22/07/2024 15:13 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:Update: Order Amended _x000D_15/7/2024:Update: Order Amended _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 16/07/2024.We will continue to provide update as they become available. _x000D_4/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 16/07/2024.We will continue to provide update as they become available. _x000D_3/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 16/07/2024.We will continue to provide update as they become available. _x000D_2/7/2024:0 _x000D_1/7/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 15:13 _x000D_26/7/2024:22/07/2024 15:13 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:Update: Order Amended _x000D_15/7/2024:Update: Order Amended _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 16/07/2024.We will continue to provide update as they become available. _x000D_4/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 16/07/2024.We will continue to provide update as they become available. _x000D_3/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 16/07/2024.We will continue to provide update as they become available. _x000D_2/7/2024:0 _x000D_1/7/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2366062 | 30016724 | 1.Provisioning | AM |  | 2024-06-27 | 2024-09-06 |  | 0 | [11 empty] | 0
841 | 427320 | 3373 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Nisa Extra | Willenhall | WV12 4HA |  | 6/9/2024:#Update - Awaiting ECC approval, _x000D_5/9/2024:#Update - Awaiting ECC approval, _x000D_4/9/2024:#Update - Awaiting ECC approval, _x000D_3/9/2024:#Update - Awaiting ECC approval, _x000D_2/9/2024:#Update - Awaiting ECC approval, _x000D_29/8/2024:#Update - Awaiting ECC approval, _x000D_28/8/2024:#Update - Awaiting ECC approval, _x000D_27/8/2024:#Update - Awaiting ECC approval, _x000D_22/8/2024:#Update - Awaiting ECC approval, _x000D_21/8/2024:#Update - Awaiting ECC approval, _x000D_20/8/2024:#Update - Awaiting ECC approval, _x000D_19/8/2024:#Update - Awaiting ECC approval, _x000D_19/8/2024:01457051 _x000D_16/8/2024:#Update - Awaiting ECC approval, _x000D_15/8/2024:#Update - Awaiting ECC approval, _x000D_14/8/2024:#Update - Awaiting ECC approval, _x000D_13/8/2024:#Update - Awaiting ECC approval, _x000D_12/8/2024:#Update - Awaiting ECC approval, _x000D_9/8/2024:#Update - Awaiting ECC approval, _x000D_8/8/2024:23/07/2024 _x000D_6/8/2024:23/07/2024 _x000D_5/8/2024:23/07/2024 _x000D_2/8/2024:23/07/2024 _x000D_1/8/2024:23/07/2024 _x000D_31/7/2024:23/07/2024 _x000D_31/7/2024:23/07/2024 _x000D_30/7/2024:#Update - Awaiting ECC approval, _x000D_29/7/2024:#Update - Awaiting ECC approval, _x000D_29/7/2024:01457051 _x000D_26/7/2024:01457051 _x000D_24/7/2024:#Update - Awaiting ECC approval, _x000D_23/7/2024:#Update - Awaiting ECC approval, _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:Update: Order Amended _x000D_16/7/2024:Update: Order Amended _x000D_15/7/2024:Update: Order Amended _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:0 _x000D_4/7/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_3/7/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_2/7/2024:0 _x000D_1/7/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_27/6/2024:End User Missed appointment. Action required _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - Awaiting ECC approval, _x000D_6/9/2024:#Update - Awaiting ECC approval, _x000D_5/9/2024:#Update - Awaiting ECC approval, _x000D_4/9/2024:#Update - Awaiting ECC approval, _x000D_3/9/2024:#Update - Awaiting ECC approval, _x000D_2/9/2024:#Update - Awaiting ECC approval, _x000D_29/8/2024:#Update - Awaiting ECC approval, _x000D_28/8/2024:#Update - Awaiting ECC approval, _x000D_27/8/2024:#Update - Awaiting ECC approval, _x000D_22/8/2024:#Update - Awaiting ECC approval, _x000D_21/8/2024:#Update - Awaiting ECC approval, _x000D_20/8/2024:#Update - Awaiting ECC approval, _x000D_19/8/2024:#Update - Awaiting ECC approval, _x000D_19/8/2024:01457051 _x000D_16/8/2024:#Update - Awaiting ECC approval, _x000D_15/8/2024:#Update - Awaiting ECC approval, _x000D_14/8/2024:#Update - Awaiting ECC approval, _x000D_13/8/2024:#Update - Awaiting ECC approval, _x000D_12/8/2024:#Update - Awaiting ECC approval, _x000D_9/8/2024:#Update - Awaiting ECC approval, _x000D_8/8/2024:23/07/2024 _x000D_6/8/2024:23/07/2024 _x000D_5/8/2024:23/07/2024 _x000D_2/8/2024:23/07/2024 _x000D_1/8/2024:23/07/2024 _x000D_31/7/2024:23/07/2024 _x000D_31/7/2024:23/07/2024 _x000D_30/7/2024:#Update - Awaiting ECC approval, _x000D_29/7/2024:#Update - Awaiting ECC approval, _x000D_29/7/2024:01457051 _x000D_26/7/2024:01457051 _x000D_24/7/2024:#Update - Awaiting ECC approval, _x000D_23/7/2024:#Update - Awaiting ECC approval, _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:Update: Order Amended _x000D_16/7/2024:Update: Order Amended _x000D_15/7/2024:Update: Order Amended _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:0 _x000D_4/7/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_3/7/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_2/7/2024:0 _x000D_1/7/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_27/6/2024:End User Missed appointment. Action required _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update - Awaiting ECC approval, | 2024-06-07 |  |  |  |  | VFP2366060 | 30016843 | 1.Provisioning | AM |  | 2024-06-27 | 2024-08-29 |  | 0 | [11 empty] | 0
842 | 623567 | 3375 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Veer Food and Wine | Southall | UB1 1ND |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:Update: Order Amended _x000D_28/8/2024:Update: Order Amended _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:Update: Order Completed by Supplier _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:Update: Order Amended _x000D_28/8/2024:Update: Order Amended _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:Update: Order Completed by Supplier _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | 0 | 2024-06-07 |  |  |  |  | VFS1015640 | 30016695 | 1.Provisioning | AM |  | 2024-06-27 | 2024-08-30 |  | 0 | [11 empty] | 0
843 | 664480 | 3378 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Premier Blackhall | Peterlee | TS27 4EA |  | 6/9/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_5/9/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_4/9/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_3/9/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_2/9/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_29/8/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_28/8/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_27/8/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_22/8/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_21/8/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_20/8/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_19/8/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_19/8/2024:01456335 _x000D_16/8/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_15/8/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_14/8/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_13/8/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_12/8/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_9/8/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_8/8/2024:27/06/2024 _x000D_6/8/2024:27/06/2024 _x000D_5/8/2024:27/06/2024 _x000D_2/8/2024:27/06/2024 _x000D_1/8/2024:27/06/2024 _x000D_31/7/2024:27/06/2024 _x000D_31/7/2024:27/06/2024 _x000D_30/7/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_29/7/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_29/7/2024:01456335 _x000D_26/7/2024:01456335 _x000D_24/7/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_23/7/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_22/7/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_22/7/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Allwyn confirmed reappointed install date with retailer _x000D_27/6/2024:#Update - Allwyn confirmed reappointed install date with retailer _x000D_25/6/2024:#Update - Allwyn confirmed reappointed install date with retailer _x000D_24/6/2024:#Update - Allwyn confirmed reappointed install date with retailer _x000D_20/6/2024:#Update - Allwyn confirmed reappointed install date with retailer _x000D_19/6/2024:#Update - Allwyn confirmed reappointed install date with retailer _x000D_18/6/2024:#Update - Allwyn confirmed reappointed install date with retailer _x000D_17/6/2024:#Update - Allwyn confirmed reappointed install date with retailer _x000D_14/6/2024:#Update - Allwyn confirmed reappointed install date with retailer _x000D_13/6/2024:#Update - Allwyn confirmed reappointed install date with retailer _x000D_12/6/2024:#Update - Allwyn confirmed reappointed install date with retailer _x000D_11/6/2024:0 _x000D_ | 9/9/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_6/9/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_5/9/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_4/9/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_3/9/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_2/9/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_29/8/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_28/8/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_27/8/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_22/8/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_21/8/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_20/8/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_19/8/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_19/8/2024:01456335 _x000D_16/8/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_15/8/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_14/8/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_13/8/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_12/8/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_9/8/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_8/8/2024:27/06/2024 _x000D_6/8/2024:27/06/2024 _x000D_5/8/2024:27/06/2024 _x000D_2/8/2024:27/06/2024 _x000D_1/8/2024:27/06/2024 _x000D_31/7/2024:27/06/2024 _x000D_31/7/2024:27/06/2024 _x000D_30/7/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_29/7/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_29/7/2024:01456335 _x000D_26/7/2024:01456335 _x000D_24/7/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_23/7/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_22/7/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_22/7/2024:#Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Allwyn confirmed reappointed install date with retailer _x000D_27/6/2024:#Update - Allwyn confirmed reappointed install date with retailer _x000D_25/6/2024:#Update - Allwyn confirmed reappointed install date with retailer _x000D_24/6/2024:#Update - Allwyn confirmed reappointed install date with retailer _x000D_20/6/2024:#Update - Allwyn confirmed reappointed install date with retailer _x000D_19/6/2024:#Update - Allwyn confirmed reappointed install date with retailer _x000D_18/6/2024:#Update - Allwyn confirmed reappointed install date with retailer _x000D_17/6/2024:#Update - Allwyn confirmed reappointed install date with retailer _x000D_14/6/2024:#Update - Allwyn confirmed reappointed install date with retailer _x000D_13/6/2024:#Update - Allwyn confirmed reappointed install date with retailer _x000D_12/6/2024:#Update - Allwyn confirmed reappointed install date with retailer _x000D_11/6/2024:0 _x000D_ | 0 | #Update Order delayed - Out of hours required - details awaited from supplier before arranging ECC | 2024-06-07 |  |  |  |  | VFS1015639 | 30016762 | 1.Provisioning | AM |  | 2024-06-27 | 2024-08-30 |  | 0 | [11 empty] | 0
844 | 661495 | 248 | Batch 2 Apr24 | Type 1 | SOGEA | Mithurja Convenience Store | Mitcham | CR4 2JB | 2024-05-30 | 6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_18/7/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_17/7/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_16/7/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_15/7/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_12/7/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_11/7/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_10/7/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_9/7/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_4/7/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_3/7/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_27/6/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_25/6/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_24/6/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_20/6/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_19/6/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_18/6/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_17/6/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_14/6/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_13/6/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_12/6/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_11/6/2024:0 _x000D_ | 6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_18/7/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_17/7/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_16/7/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_15/7/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_12/7/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_11/7/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_10/7/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_9/7/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_4/7/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_3/7/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_27/6/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_25/6/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_24/6/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_20/6/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_19/6/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_18/6/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_17/6/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_14/6/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_13/6/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_12/6/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_11/6/2024:0 _x000D_ |  |  | 2024-04-25 | 25/04/2024: Allwyn to make retailer aware of visit as per the date in column T 25/04/2024: Allwyn to check with the retailer how CSL should proccess 18/04/2024: Date confirmed on 25/04 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS939540 | 30013281 | 6.Failed router install | AM |  | 2024-06-03 | 2024-07-12 | 2024-07-12 | TRUE |  |  |  | 2024-08-02 |  |  |  | 2024-08-02 | 242005011001 |  | 2024-08-06 | 1
845 | 636226 | 322 | Batch 2 Apr24 | Type 1 | SoGEA/Mobile | Sparken Supermarket - Premier | Bradford | BD6 3LX | 2024-05-30 | 6/9/2024:#Update - changing to Site Type 3 _x000D_5/9/2024:#Update - changing to Site Type 3 _x000D_4/9/2024:#Update - changing to Site Type 3 _x000D_3/9/2024:#Update - changing to Site Type 3 _x000D_2/9/2024:#Update - changing to Site Type 3 _x000D_29/8/2024:#Update - changing to Site Type 3 _x000D_28/8/2024:#Update - changing to Site Type 3 _x000D_27/8/2024:#Update - changing to Site Type 3 _x000D_22/8/2024:#Update - awaiting ECC approval - proposal sent to VF 22/05 _x000D_21/8/2024:#Update - with customer to confirm how to proceed - site requires OOH appointment but store manager not prepared to accommodate appointment and close site _x000D_20/8/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_19/8/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_19/8/2024:01355095 _x000D_16/8/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_15/8/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_14/8/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_13/8/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_12/8/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_9/8/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_8/8/2024:20/05/2024 _x000D_6/8/2024:20/05/2024 _x000D_5/8/2024:20/05/2024 _x000D_2/8/2024:20/05/2024 _x000D_1/8/2024:20/05/2024 _x000D_31/7/2024:20/05/2024 _x000D_31/7/2024:20/05/2024 _x000D_30/7/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_29/7/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_29/7/2024:01355095 _x000D_26/7/2024:01355095 _x000D_24/7/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_23/7/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_22/7/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_22/7/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Allwyn requested date to be pushed out, have re-appointed for 03/06. Allwyn to confirm with the retailer that this date suits with the retailer. _x000D_27/6/2024:#Update - Allwyn requested date to be pushed out, have re-appointed for 03/06. Allwyn to confirm with the retailer that this date suits with the retailer. _x000D_25/6/2024:#Update - Allwyn requested date to be pushed out, have re-appointed for 03/06. Allwyn to confirm with the retailer that this date suits with the retailer. _x000D_24/6/2024:#Update - Allwyn requested date to be pushed out, have re-appointed for 03/06. Allwyn to confirm with the retailer that this date suits with the retailer. _x000D_20/6/2024:#Update - Allwyn requested date to be pushed out, have re-appointed for 03/06. Allwyn to confirm with the retailer that this date suits with the retailer. _x000D_19/6/2024:#Update - Allwyn requested date to be pushed out, have re-appointed for 03/06. Allwyn to confirm with the retailer that this date suits with the retailer. _x000D_18/6/2024:#Update - Allwyn requested date to be pushed out, have re-appointed for 03/06. Allwyn to confirm with the retailer that this date suits with the retailer. _x000D_17/6/2024:#Update - Allwyn requested date to be pushed out, have re-appointed for 03/06. Allwyn to confirm with the retailer that this date suits with the retailer. _x000D_14/6/2024:#Update - Allwyn requested date to be pushed out, have re-appointed for 03/06. Allwyn to confirm with the retailer that this date suits with the retailer. _x000D_13/6/2024:#Update - Allwyn requested date to be pushed out, have re-appointed for 03/06. Allwyn to confirm with the retailer that this date suits with the retailer. _x000D_12/6/2024:#Update - Allwyn requested date to be pushed out, have re-appointed for 03/06. Allwyn to confirm with the retailer that this date suits with the retailer. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 9/9/2024:#Update - changing to Site Type 3 _x000D_6/9/2024:#Update - changing to Site Type 3 _x000D_5/9/2024:#Update - changing to Site Type 3 _x000D_4/9/2024:#Update - changing to Site Type 3 _x000D_3/9/2024:#Update - changing to Site Type 3 _x000D_2/9/2024:#Update - changing to Site Type 3 _x000D_29/8/2024:#Update - changing to Site Type 3 _x000D_28/8/2024:#Update - changing to Site Type 3 _x000D_27/8/2024:#Update - changing to Site Type 3 _x000D_22/8/2024:#Update - awaiting ECC approval - proposal sent to VF 22/05 _x000D_21/8/2024:#Update - with customer to confirm how to proceed - site requires OOH appointment but store manager not prepared to accommodate appointment and close site _x000D_20/8/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_19/8/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_19/8/2024:01355095 _x000D_16/8/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_15/8/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_14/8/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_13/8/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_12/8/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_9/8/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_8/8/2024:20/05/2024 _x000D_6/8/2024:20/05/2024 _x000D_5/8/2024:20/05/2024 _x000D_2/8/2024:20/05/2024 _x000D_1/8/2024:20/05/2024 _x000D_31/7/2024:20/05/2024 _x000D_31/7/2024:20/05/2024 _x000D_30/7/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_29/7/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_29/7/2024:01355095 _x000D_26/7/2024:01355095 _x000D_24/7/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_23/7/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_22/7/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_22/7/2024:#Update - Openreach have advised excess works to complete order. Going to push out to accommodate these works. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Allwyn requested date to be pushed out, have re-appointed for 03/06. Allwyn to confirm with the retailer that this date suits with the retailer. _x000D_27/6/2024:#Update - Allwyn requested date to be pushed out, have re-appointed for 03/06. Allwyn to confirm with the retailer that this date suits with the retailer. _x000D_25/6/2024:#Update - Allwyn requested date to be pushed out, have re-appointed for 03/06. Allwyn to confirm with the retailer that this date suits with the retailer. _x000D_24/6/2024:#Update - Allwyn requested date to be pushed out, have re-appointed for 03/06. Allwyn to confirm with the retailer that this date suits with the retailer. _x000D_20/6/2024:#Update - Allwyn requested date to be pushed out, have re-appointed for 03/06. Allwyn to confirm with the retailer that this date suits with the retailer. _x000D_19/6/2024:#Update - Allwyn requested date to be pushed out, have re-appointed for 03/06. Allwyn to confirm with the retailer that this date suits with the retailer. _x000D_18/6/2024:#Update - Allwyn requested date to be pushed out, have re-appointed for 03/06. Allwyn to confirm with the retailer that this date suits with the retailer. _x000D_17/6/2024:#Update - Allwyn requested date to be pushed out, have re-appointed for 03/06. Allwyn to confirm with the retailer that this date suits with the retailer. _x000D_14/6/2024:#Update - Allwyn requested date to be pushed out, have re-appointed for 03/06. Allwyn to confirm with the retailer that this date suits with the retailer. _x000D_13/6/2024:#Update - Allwyn requested date to be pushed out, have re-appointed for 03/06. Allwyn to confirm with the retailer that this date suits with the retailer. _x000D_12/6/2024:#Update - Allwyn requested date to be pushed out, have re-appointed for 03/06. Allwyn to confirm with the retailer that this date suits with the retailer. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 0 | #Update - changing to Site Type 3 | 2024-04-30 | 30/04/2024: Allwyn to make the retaile aware. 16/04/2024: Allwyn to make the retaile aware. 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 2.Allwyn to arrange access | VFS939527 | 30013226 | 1.Provisioning | AM |  | 2024-04-15 | 2024-09-04 |  | 0 | [11 empty] | 0
846 | 665435 | 1154 | Batch 3 May24 | Type 1 | SOGEA | Premier Gills Food and Wine | NEWCASTLE UPON TYNE | NE5 3JE | 2024-06-07 | 19/7/2024:#Update - installation unsuccessful, OOH required due to H&S issues/many customers in store. CSL liaising with OR for scope of work / hours required and will update accordingly _x000D_18/7/2024:#Update - installation unsuccessful, OOH required due to H&S issues/many customers in store. CSL liaising with OR for scope of work / hours required and will update accordingly _x000D_17/7/2024:#Update - installation unsuccessful, OOH required due to H&S issues/many customers in store. CSL liaising with OR for scope of work / hours required and will update accordingly _x000D_16/7/2024:#Update - installation unsuccessful, OOH required due to H&S issues/many customers in store. CSL liaising with OR for scope of work / hours required and will update accordingly _x000D_15/7/2024:#Update - installation unsuccessful, OOH required due to H&S issues/many customers in store. CSL liaising with OR for scope of work / hours required and will update accordingly _x000D_12/7/2024:#Update - installation unsuccessful, OOH required due to H&S issues/many customers in store. CSL liaising with OR for scope of work / hours required and will update accordingly _x000D_11/7/2024:#Update - installation unsuccessful, OOH required due to H&S issues/many customers in store. CSL liaising with OR for scope of work / hours required and will update accordingly _x000D_10/7/2024:#Update - installation unsuccessful, OOH required due to H&S issues/many customers in store. CSL liaising with OR for scope of work / hours required and will update accordingly _x000D_9/7/2024:#Update - installation unsuccessful, OOH required due to H&S issues/many customers in store. CSL liaising with OR for scope of work / hours required and will update accordingly _x000D_4/7/2024:#Update - installation unsuccessful, OOH required due to H&S issues/many customers in store. CSL liaising with OR for scope of work / hours required and will update accordingly _x000D_3/7/2024:#Update - installation unsuccessful, OOH required due to H&S issues/many customers in store. CSL liaising with OR for scope of work / hours required and will update accordingly _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - installation unsuccessful, OOH required due to H&S issues/many customers in store. CSL liaising with OR for scope of work / hours required and will update accordingly _x000D_27/6/2024:#Update - installation unsuccessful, OOH required due to H&S issues/many customers in store. CSL liaising with OR for scope of work / hours required and will update accordingly _x000D_25/6/2024:#Update - installation unsuccessful, OOH required due to H&S issues/many customers in store. CSL liaising with OR for scope of work / hours required and will update accordingly _x000D_24/6/2024:#Update - installation unsuccessful, OOH required due to H&S issues/many customers in store. CSL liaising with OR for scope of work / hours required and will update accordingly _x000D_20/6/2024:#Update - installation unsuccessful, OOH required due to H&S issues/many customers in store. CSL liaising with OR for scope of work / hours required and will update accordingly _x000D_19/6/2024:#Update - installation unsuccessful, OOH required due to H&S issues/many customers in store. CSL liaising with OR for scope of work / hours required and will update accordingly _x000D_18/6/2024:#Update - installation unsuccessful, OOH required due to H&S issues/many customers in store. CSL liaising with OR for scope of work / hours required and will update accordingly _x000D_17/6/2024:#Update - installation unsuccessful, OOH required due to H&S issues/many customers in store. CSL liaising with OR for scope of work / hours required and will update accordingly _x000D_14/6/2024:#Update - installation unsuccessful, OOH required due to H&S issues/many customers in store. CSL liaising with OR for scope of work / hours required and will update accordingly _x000D_13/6/2024:#Update - installation unsuccessful, OOH required due to H&S issues/many customers in store. CSL liaising with OR for scope of work / hours required and will update accordingly _x000D_12/6/2024:#Update - installation unsuccessful, OOH required due to H&S issues/many customers in store. CSL liaising with OR for scope of work / hours required and will update accordingly _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:#Update - installation unsuccessful, OOH required due to H&S issues/many customers in store. CSL liaising with OR for scope of work / hours required and will update accordingly _x000D_18/7/2024:#Update - installation unsuccessful, OOH required due to H&S issues/many customers in store. CSL liaising with OR for scope of work / hours required and will update accordingly _x000D_17/7/2024:#Update - installation unsuccessful, OOH required due to H&S issues/many customers in store. CSL liaising with OR for scope of work / hours required and will update accordingly _x000D_16/7/2024:#Update - installation unsuccessful, OOH required due to H&S issues/many customers in store. CSL liaising with OR for scope of work / hours required and will update accordingly _x000D_15/7/2024:#Update - installation unsuccessful, OOH required due to H&S issues/many customers in store. CSL liaising with OR for scope of work / hours required and will update accordingly _x000D_12/7/2024:#Update - installation unsuccessful, OOH required due to H&S issues/many customers in store. CSL liaising with OR for scope of work / hours required and will update accordingly _x000D_11/7/2024:#Update - installation unsuccessful, OOH required due to H&S issues/many customers in store. CSL liaising with OR for scope of work / hours required and will update accordingly _x000D_10/7/2024:#Update - installation unsuccessful, OOH required due to H&S issues/many customers in store. CSL liaising with OR for scope of work / hours required and will update accordingly _x000D_9/7/2024:#Update - installation unsuccessful, OOH required due to H&S issues/many customers in store. CSL liaising with OR for scope of work / hours required and will update accordingly _x000D_4/7/2024:#Update - installation unsuccessful, OOH required due to H&S issues/many customers in store. CSL liaising with OR for scope of work / hours required and will update accordingly _x000D_3/7/2024:#Update - installation unsuccessful, OOH required due to H&S issues/many customers in store. CSL liaising with OR for scope of work / hours required and will update accordingly _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - installation unsuccessful, OOH required due to H&S issues/many customers in store. CSL liaising with OR for scope of work / hours required and will update accordingly _x000D_27/6/2024:#Update - installation unsuccessful, OOH required due to H&S issues/many customers in store. CSL liaising with OR for scope of work / hours required and will update accordingly _x000D_25/6/2024:#Update - installation unsuccessful, OOH required due to H&S issues/many customers in store. CSL liaising with OR for scope of work / hours required and will update accordingly _x000D_24/6/2024:#Update - installation unsuccessful, OOH required due to H&S issues/many customers in store. CSL liaising with OR for scope of work / hours required and will update accordingly _x000D_20/6/2024:#Update - installation unsuccessful, OOH required due to H&S issues/many customers in store. CSL liaising with OR for scope of work / hours required and will update accordingly _x000D_19/6/2024:#Update - installation unsuccessful, OOH required due to H&S issues/many customers in store. CSL liaising with OR for scope of work / hours required and will update accordingly _x000D_18/6/2024:#Update - installation unsuccessful, OOH required due to H&S issues/many customers in store. CSL liaising with OR for scope of work / hours required and will update accordingly _x000D_17/6/2024:#Update - installation unsuccessful, OOH required due to H&S issues/many customers in store. CSL liaising with OR for scope of work / hours required and will update accordingly _x000D_14/6/2024:#Update - installation unsuccessful, OOH required due to H&S issues/many customers in store. CSL liaising with OR for scope of work / hours required and will update accordingly _x000D_13/6/2024:#Update - installation unsuccessful, OOH required due to H&S issues/many customers in store. CSL liaising with OR for scope of work / hours required and will update accordingly _x000D_12/6/2024:#Update - installation unsuccessful, OOH required due to H&S issues/many customers in store. CSL liaising with OR for scope of work / hours required and will update accordingly _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301351 | 30014044 | 2.Commissioning | AM |  | 2024-05-24 | 2024-06-28 | 2024-06-28 | TRUE |  |  |  | 2024-07-24 | [7 empty] | 0
847 | 668024 | 1178 | Batch 3 May24 | Type 1 | SOGEA | Ankaran Food and Wine | LONDON | W12 0BP | 2024-06-07 | 22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | [6 empty] | 5.CSL | VFP2301375 | 30014068 | 6.Failed router install | AM | [8 empty] | 2024-07-30 |  |  |  | 2024-08-21 | 242005010983 | 242005010983 | 2024-08-23 | 1
848 | 651841 | 1503 | Batch 4 Jun24 | Type 1 | SOGEA | Centra | Londonderry | BT48 8LB | 2024-06-07 | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:#Update - Missed appointment - customer wants an 80/20 circuit so engineer left site due to 'incorrect product'. Customer wants 80/20 not 40/10 _x000D_4/7/2024:#Update - Missed appointment - customer wants an 80/20 circuit so engineer left site due to 'incorrect product'. Customer wants 80/20 not 40/10 _x000D_3/7/2024:#Update - Missed appointment - customer wants an 80/20 circuit so engineer left site due to 'incorrect product'. Customer wants 80/20 not 40/10 _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:#Update - Missed appointment - customer wants an 80/20 circuit so engineer left site due to 'incorrect product'. Customer wants 80/20 not 40/10 _x000D_27/6/2024:#Update - Missed appointment - customer wants an 80/20 circuit so engineer left site due to 'incorrect product'. Customer wants 80/20 not 40/10 _x000D_25/6/2024:#Update - Missed appointment - customer wants an 80/20 circuit so engineer left site due to 'incorrect product'. Customer wants 80/20 not 40/10 _x000D_24/6/2024:#Update - Missed appointment - customer wants an 80/20 circuit so engineer left site due to 'incorrect product'. Customer wants 80/20 not 40/10 _x000D_20/6/2024:#Update - Missed appointment - customer wants an 80/20 circuit so engineer left site due to 'incorrect product'. Customer wants 80/20 not 40/10 _x000D_19/6/2024:#Update - Missed appointment - customer wants an 80/20 circuit so engineer left site due to 'incorrect product'. Customer wants 80/20 not 40/10 _x000D_18/6/2024:#Update - Missed appointment - customer wants an 80/20 circuit so engineer left site due to 'incorrect product'. Customer wants 80/20 not 40/10 _x000D_17/6/2024:#Update - Missed appointment - customer wants an 80/20 circuit so engineer left site due to 'incorrect product'. Customer wants 80/20 not 40/10 _x000D_14/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect Product. Please check with end user and reappoint the order if still required. _x000D_13/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:#Update - Missed appointment - customer wants an 80/20 circuit so engineer left site due to 'incorrect product'. Customer wants 80/20 not 40/10 _x000D_4/7/2024:#Update - Missed appointment - customer wants an 80/20 circuit so engineer left site due to 'incorrect product'. Customer wants 80/20 not 40/10 _x000D_3/7/2024:#Update - Missed appointment - customer wants an 80/20 circuit so engineer left site due to 'incorrect product'. Customer wants 80/20 not 40/10 _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:#Update - Missed appointment - customer wants an 80/20 circuit so engineer left site due to 'incorrect product'. Customer wants 80/20 not 40/10 _x000D_27/6/2024:#Update - Missed appointment - customer wants an 80/20 circuit so engineer left site due to 'incorrect product'. Customer wants 80/20 not 40/10 _x000D_25/6/2024:#Update - Missed appointment - customer wants an 80/20 circuit so engineer left site due to 'incorrect product'. Customer wants 80/20 not 40/10 _x000D_24/6/2024:#Update - Missed appointment - customer wants an 80/20 circuit so engineer left site due to 'incorrect product'. Customer wants 80/20 not 40/10 _x000D_20/6/2024:#Update - Missed appointment - customer wants an 80/20 circuit so engineer left site due to 'incorrect product'. Customer wants 80/20 not 40/10 _x000D_19/6/2024:#Update - Missed appointment - customer wants an 80/20 circuit so engineer left site due to 'incorrect product'. Customer wants 80/20 not 40/10 _x000D_18/6/2024:#Update - Missed appointment - customer wants an 80/20 circuit so engineer left site due to 'incorrect product'. Customer wants 80/20 not 40/10 _x000D_17/6/2024:#Update - Missed appointment - customer wants an 80/20 circuit so engineer left site due to 'incorrect product'. Customer wants 80/20 not 40/10 _x000D_14/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect Product. Please check with end user and reappoint the order if still required. _x000D_13/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984751 | 30015333 | 6.Failed router install | AM |  | 2024-06-28 | 2024-06-28 | 2024-06-28 | TRUE |  |  |  | 2024-07-26 |  |  |  | 2024-07-26 | 23A004952958 |  | 2024-07-29 | 1
849 | 482341 | 1912 | Batch 4 Jun24 | Type 1 | SOGEA | Kumar Stores | Neath | SA11 5EU | 2024-06-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_18/7/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_17/7/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_16/7/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_15/7/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_12/7/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_11/7/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_10/7/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_9/7/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_4/7/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_3/7/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_27/6/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_25/6/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_24/6/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_20/6/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_19/6/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_18/6/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_17/6/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_14/6/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. _x000D_13/6/2024:EU Missed Appointment. Supplier engineer has been unable to gain access. _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_18/7/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_17/7/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_16/7/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_15/7/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_12/7/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_11/7/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_10/7/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_9/7/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_4/7/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_3/7/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_27/6/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_25/6/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_24/6/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_20/6/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_19/6/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_18/6/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_17/6/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_14/6/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. _x000D_13/6/2024:EU Missed Appointment. Supplier engineer has been unable to gain access. _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 0 | 0 | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFS983494 | 30015744 | 2.Commissioning | AM | [8 empty] | 2024-07-25 | [7 empty] | 0
850 | 627039 | 1915 | Batch 4 Jun24 | Type 3 | FTTP/Mobile | The Three Singhs | Selby | YO8 9BY | 2024-06-14 | 6/9/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_5/9/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_4/9/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_3/9/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_2/9/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_29/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_28/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_27/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_22/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_21/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_20/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_19/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_19/8/2024:01436098 _x000D_16/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_15/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_14/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_13/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_12/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_9/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_8/8/2024:05/08/2024 _x000D_6/8/2024:05/08/2024 _x000D_5/8/2024:05/08/2024 _x000D_2/8/2024:14/06/2024 _x000D_1/8/2024:14/06/2024 _x000D_31/7/2024:14/06/2024 _x000D_31/7/2024:14/06/2024 _x000D_30/7/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_29/7/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_29/7/2024:01436098 _x000D_26/7/2024:01436098 _x000D_24/7/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_23/7/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_22/7/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_22/7/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_19/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_18/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_17/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_16/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_15/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_12/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_11/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_10/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_9/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_4/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_3/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Action for Allwyn - Installation has now been amended to 28/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 28/06 is a suitable date _x000D_27/6/2024:#Update - Action for Allwyn - Installation has now been amended to 28/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 28/06 is a suitable date _x000D_25/6/2024:#Update - Action for Allwyn - Installation has now been amended to 28/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 28/06 is a suitable date _x000D_24/6/2024:#Update - Action for Allwyn - Installation has now been amended to 28/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 28/06 is a suitable date _x000D_20/6/2024:#Update - Action for Allwyn - Installation has now been amended to 28/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 28/06 is a suitable date _x000D_19/6/2024:#Update - Action for Allwyn - Installation has now been amended to 28/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 28/06 is a suitable date _x000D_18/6/2024:#Update - Action for Allwyn - Installation has now been amended to 28/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 28/06 is a suitable date _x000D_17/6/2024:#Update - Action for Allwyn - Installation has now been amended to 28/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 28/06 is a suitable date _x000D_14/6/2024:#Update - Action for Allwyn - Installation has now been amended to 28/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 28/06 is a suitable date _x000D_13/6/2024:#Update - Action for Allwyn - Installation has now been amended to 28/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 28/06 is a suitable date _x000D_12/6/2024:#Update - Action for Allwyn - Installation has now been amended to 28/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 28/06 is a suitable date _x000D_10/6/2024:#Update - Action for Allwyn - Installation has now been amended to 28/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 28/06 is a suitable date _x000D_7/6/2024:#Update - Action for Allwyn - Installation has now been amended to 28/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 28/06 is a suitable date _x000D_6/6/2024:#Update - Action for Allwyn - Installation has now been amended to 28/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 28/06 is a suitable date _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 9/9/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_6/9/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_5/9/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_4/9/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_3/9/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_2/9/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_29/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_28/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_27/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_22/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_21/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_20/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_19/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_19/8/2024:01436098 _x000D_16/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_15/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_14/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_13/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_12/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_9/8/2024:#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_8/8/2024:05/08/2024 _x000D_6/8/2024:05/08/2024 _x000D_5/8/2024:05/08/2024 _x000D_2/8/2024:14/06/2024 _x000D_1/8/2024:14/06/2024 _x000D_31/7/2024:14/06/2024 _x000D_31/7/2024:14/06/2024 _x000D_30/7/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_29/7/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_29/7/2024:01436098 _x000D_26/7/2024:01436098 _x000D_24/7/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_23/7/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_22/7/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_22/7/2024:#Update Customer missed appointment due to customer not allowing access. Rescheduled to 28/06 PM. _x000D_19/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_18/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_17/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_16/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_15/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_12/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_11/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_10/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_9/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_4/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_3/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Action for Allwyn - Installation has now been amended to 28/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 28/06 is a suitable date _x000D_27/6/2024:#Update - Action for Allwyn - Installation has now been amended to 28/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 28/06 is a suitable date _x000D_25/6/2024:#Update - Action for Allwyn - Installation has now been amended to 28/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 28/06 is a suitable date _x000D_24/6/2024:#Update - Action for Allwyn - Installation has now been amended to 28/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 28/06 is a suitable date _x000D_20/6/2024:#Update - Action for Allwyn - Installation has now been amended to 28/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 28/06 is a suitable date _x000D_19/6/2024:#Update - Action for Allwyn - Installation has now been amended to 28/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 28/06 is a suitable date _x000D_18/6/2024:#Update - Action for Allwyn - Installation has now been amended to 28/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 28/06 is a suitable date _x000D_17/6/2024:#Update - Action for Allwyn - Installation has now been amended to 28/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 28/06 is a suitable date _x000D_14/6/2024:#Update - Action for Allwyn - Installation has now been amended to 28/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 28/06 is a suitable date _x000D_13/6/2024:#Update - Action for Allwyn - Installation has now been amended to 28/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 28/06 is a suitable date _x000D_12/6/2024:#Update - Action for Allwyn - Installation has now been amended to 28/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 28/06 is a suitable date _x000D_10/6/2024:#Update - Action for Allwyn - Installation has now been amended to 28/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 28/06 is a suitable date _x000D_7/6/2024:#Update - Action for Allwyn - Installation has now been amended to 28/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 28/06 is a suitable date _x000D_6/6/2024:#Update - Action for Allwyn - Installation has now been amended to 28/06 AM. Please speak with the retailer regarding installation details and confirm to CSL if 28/06 is a suitable date _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 0 | #Update - this site has changed to a site type 3 / mobile only as per customer request | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2337374 | 30015676 | 2.Commissioning | AM |  |  |  |  | 0 |  |  |  | 2024-08-23 | [7 empty] | 0
851 | 667642 | 1527 | Batch 4 Jun24 | Type 1 | FTTP | Premier | Manchester | M18 8SZ | 2024-07-23 | 12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:01425186 _x000D_24/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_23/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_22/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_22/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:Update: Order Amended _x000D_17/7/2024:0 _x000D_16/7/2024:Update: Order Amended _x000D_15/7/2024:Update: Order Amended _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:Update: Order Amended _x000D_20/6/2024:Update: Order Amended _x000D_19/6/2024:Update: Order Amended _x000D_18/6/2024:Update: Order Amended _x000D_17/6/2024:Your order has been delayed by our Suppliers due to unable to access distribution point within customer premises. Now order got re-appointed for 28/06/2024. _x000D_14/6/2024:Your order has been delayed by our Suppliers due to unable to access distribution point within customer premises. Now order got re-appointed for 28/06/2024. _x000D_13/6/2024:Your order has been delayed by our Suppliers due to unable to access distribution point within customer premises. Now order got re-appointed for 28/06/2024. _x000D_12/6/2024:Your order has been delayed by our Suppliers due to unable to access distribution point within customer premises. Now order got re-appointed for 28/06/2024. _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:01425186 _x000D_24/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_23/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_22/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_22/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:Update: Order Amended _x000D_17/7/2024:0 _x000D_16/7/2024:Update: Order Amended _x000D_15/7/2024:Update: Order Amended _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:Update: Order Amended _x000D_20/6/2024:Update: Order Amended _x000D_19/6/2024:Update: Order Amended _x000D_18/6/2024:Update: Order Amended _x000D_17/6/2024:Your order has been delayed by our Suppliers due to unable to access distribution point within customer premises. Now order got re-appointed for 28/06/2024. _x000D_14/6/2024:Your order has been delayed by our Suppliers due to unable to access distribution point within customer premises. Now order got re-appointed for 28/06/2024. _x000D_13/6/2024:Your order has been delayed by our Suppliers due to unable to access distribution point within customer premises. Now order got re-appointed for 28/06/2024. _x000D_12/6/2024:Your order has been delayed by our Suppliers due to unable to access distribution point within customer premises. Now order got re-appointed for 28/06/2024. _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFP2353435 | 30015960 | 6.Failed router install | AM |  | 2024-06-05 | 2024-07-22 | 2024-07-22 | TRUE |  |  |  | 2024-08-09 |  |  |  | 2024-08-09 | 23A004948345 |  | 2024-08-12 | 1
852 | 642082 | 1889 | Batch 4 Jun24 | Type 3 | SoGEA/Mobile | Gilletts Callington Ltd | Weston-super-Mare | BS23 1HN | 2024-06-11 | 6/9/2024:#Update - Allwyn changed to site type 3 _x000D_5/9/2024:#Update - Allwyn changed to site type 3 _x000D_4/9/2024:#Update - Allwyn changed to site type 3 _x000D_3/9/2024:#Update - Allwyn changed to site type 3 _x000D_2/9/2024:#Update - Allwyn changed to site type 3 _x000D_29/8/2024:#Update - Allwyn changed to site type 3 _x000D_28/8/2024:#Update - Allwyn changed to site type 3 _x000D_27/8/2024:#Update - Allwyn changed to site type 3 _x000D_22/8/2024:#Update - Allwyn changed to site type 3 _x000D_21/8/2024:#Update - Allwyn changed to site type 3 _x000D_20/8/2024:#Update - Allwyn changed to site type 3 _x000D_19/8/2024:#Update - Allwyn changed to site type 3 _x000D_19/8/2024:01430452 _x000D_16/8/2024:#Update - Allwyn changed to site type 3 _x000D_15/8/2024:#Update - Allwyn changed to site type 3 _x000D_14/8/2024:#Update - Allwyn changed to site type 3 _x000D_13/8/2024:#Update - Allwyn changed to site type 3 _x000D_12/8/2024:#Update - Allwyn changed to site type 3 _x000D_9/8/2024:#Update - Allwyn changed to site type 3 _x000D_8/8/2024:30/07/2024 _x000D_6/8/2024:30/07/2024 _x000D_5/8/2024:30/07/2024 _x000D_2/8/2024:30/07/2024 _x000D_1/8/2024:30/07/2024 _x000D_31/7/2024:30/07/2024 _x000D_31/7/2024:30/07/2024 _x000D_30/7/2024:End User Missed appointment. Action required _x000D_29/7/2024:End User Missed appointment. Action required _x000D_29/7/2024:29/07/2024 09:34 _x000D_26/7/2024:24/07/2024 23:03 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn changed to site type 3 _x000D_6/9/2024:#Update - Allwyn changed to site type 3 _x000D_5/9/2024:#Update - Allwyn changed to site type 3 _x000D_4/9/2024:#Update - Allwyn changed to site type 3 _x000D_3/9/2024:#Update - Allwyn changed to site type 3 _x000D_2/9/2024:#Update - Allwyn changed to site type 3 _x000D_29/8/2024:#Update - Allwyn changed to site type 3 _x000D_28/8/2024:#Update - Allwyn changed to site type 3 _x000D_27/8/2024:#Update - Allwyn changed to site type 3 _x000D_22/8/2024:#Update - Allwyn changed to site type 3 _x000D_21/8/2024:#Update - Allwyn changed to site type 3 _x000D_20/8/2024:#Update - Allwyn changed to site type 3 _x000D_19/8/2024:#Update - Allwyn changed to site type 3 _x000D_19/8/2024:01430452 _x000D_16/8/2024:#Update - Allwyn changed to site type 3 _x000D_15/8/2024:#Update - Allwyn changed to site type 3 _x000D_14/8/2024:#Update - Allwyn changed to site type 3 _x000D_13/8/2024:#Update - Allwyn changed to site type 3 _x000D_12/8/2024:#Update - Allwyn changed to site type 3 _x000D_9/8/2024:#Update - Allwyn changed to site type 3 _x000D_8/8/2024:30/07/2024 _x000D_6/8/2024:30/07/2024 _x000D_5/8/2024:30/07/2024 _x000D_2/8/2024:30/07/2024 _x000D_1/8/2024:30/07/2024 _x000D_31/7/2024:30/07/2024 _x000D_31/7/2024:30/07/2024 _x000D_30/7/2024:End User Missed appointment. Action required _x000D_29/7/2024:End User Missed appointment. Action required _x000D_29/7/2024:29/07/2024 09:34 _x000D_26/7/2024:24/07/2024 23:03 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | #Update - Allwyn changed to site type 3 | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996837 | 30016105 | 2.Commissioning | AM |  | 2024-07-29 | 2024-07-29 |  | 0 |  |  |  | 2024-09-02 | [7 empty] | 0
853 | 649093 | 3379 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Shema Londis | White City | W12 7DA |  | 12/8/2024:Order Completed _x000D_9/8/2024:Order Completed _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:Your order has been delayed due to a customer missed appointment. Customer not received router. Please check with end user and reappoint the order if still required. _x000D_31/7/2024:Your order has been delayed due to a customer missed appointment. Customer not received router. Please check with end user and reappoint the order if still required. _x000D_31/7/2024:37098 _x000D_30/7/2024:Your order has been delayed due to a customer missed appointment. Customer not received router. Please check with end user and reappoint the order if still required. _x000D_29/7/2024:Your order has been delayed due to a customer missed appointment. Customer not received router. Please check with end user and reappoint the order if still required. _x000D_29/7/2024:25/07/2024 15:17 _x000D_26/7/2024:25/07/2024 15:17 _x000D_24/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 12/8/2024:Order Completed _x000D_9/8/2024:Order Completed _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:Your order has been delayed due to a customer missed appointment. Customer not received router. Please check with end user and reappoint the order if still required. _x000D_31/7/2024:Your order has been delayed due to a customer missed appointment. Customer not received router. Please check with end user and reappoint the order if still required. _x000D_31/7/2024:37098 _x000D_30/7/2024:Your order has been delayed due to a customer missed appointment. Customer not received router. Please check with end user and reappoint the order if still required. _x000D_29/7/2024:Your order has been delayed due to a customer missed appointment. Customer not received router. Please check with end user and reappoint the order if still required. _x000D_29/7/2024:25/07/2024 15:17 _x000D_26/7/2024:25/07/2024 15:17 _x000D_24/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015530 | 30016697 | 2.Commissioning |  |  | 2024-06-28 | 2024-08-08 | 2024-08-08 11:30 | TRUE |  |  |  | 2024-08-29 | [7 empty] | 0
854 | 651384 | 3380 | Batch 5 Jul24 | Type 1 | SOGEA | SPAR Kincorth | Aberdeen | AB12 5BT |  | 19/7/2024:#Update Customer unaware, reappointed 12/07, PM. Action on Allwyn - ensure the retailer is aware of new appointment. _x000D_18/7/2024:#Update Customer unaware, reappointed 12/07, PM. Action on Allwyn - ensure the retailer is aware of new appointment. _x000D_17/7/2024:#Update Customer unaware, reappointed 12/07, PM. Action on Allwyn - ensure the retailer is aware of new appointment. _x000D_16/7/2024:#Update Customer unaware, reappointed 12/07, PM. Action on Allwyn - ensure the retailer is aware of new appointment. _x000D_15/7/2024:#Update Customer unaware, reappointed 12/07, PM. Action on Allwyn - ensure the retailer is aware of new appointment. _x000D_12/7/2024:#Update Customer unaware, reappointed 12/07, PM. Action on Allwyn - ensure the retailer is aware of new appointment. _x000D_11/7/2024:#Update Customer unaware, reappointed 12/07, PM. Action on Allwyn - ensure the retailer is aware of new appointment. _x000D_10/7/2024:#Update Customer unaware, reappointed 12/07, PM. Action on Allwyn - ensure the retailer is aware of new appointment. _x000D_9/7/2024:#Update Customer unaware, reappointed 12/07, PM. Action on Allwyn - ensure the retailer is aware of new appointment. _x000D_4/7/2024:#Update Customer unaware, reappointed 12/07, PM. Action on Allwyn - ensure the retailer is aware of new appointment. _x000D_3/7/2024:#Update Customer unaware, reappointed 12/07, PM. Action on Allwyn - ensure the retailer is aware of new appointment. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:#Update Customer unaware, reappointed 12/07, PM. Action on Allwyn - ensure the retailer is aware of new appointment. _x000D_18/7/2024:#Update Customer unaware, reappointed 12/07, PM. Action on Allwyn - ensure the retailer is aware of new appointment. _x000D_17/7/2024:#Update Customer unaware, reappointed 12/07, PM. Action on Allwyn - ensure the retailer is aware of new appointment. _x000D_16/7/2024:#Update Customer unaware, reappointed 12/07, PM. Action on Allwyn - ensure the retailer is aware of new appointment. _x000D_15/7/2024:#Update Customer unaware, reappointed 12/07, PM. Action on Allwyn - ensure the retailer is aware of new appointment. _x000D_12/7/2024:#Update Customer unaware, reappointed 12/07, PM. Action on Allwyn - ensure the retailer is aware of new appointment. _x000D_11/7/2024:#Update Customer unaware, reappointed 12/07, PM. Action on Allwyn - ensure the retailer is aware of new appointment. _x000D_10/7/2024:#Update Customer unaware, reappointed 12/07, PM. Action on Allwyn - ensure the retailer is aware of new appointment. _x000D_9/7/2024:#Update Customer unaware, reappointed 12/07, PM. Action on Allwyn - ensure the retailer is aware of new appointment. _x000D_4/7/2024:#Update Customer unaware, reappointed 12/07, PM. Action on Allwyn - ensure the retailer is aware of new appointment. _x000D_3/7/2024:#Update Customer unaware, reappointed 12/07, PM. Action on Allwyn - ensure the retailer is aware of new appointment. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015529 | 30017025 | 2.Commissioning |  |  | 2024-06-28 | 2024-06-28 | 2024-06-28 | TRUE | [11 empty] | 0
855 | 652039 | 3381 | Batch 5 Jul24 | Type 1 | SOGEA | Strawberry local | Hounslow | TW4 7DJ | 2024-07-18 | 9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:#Update Customer unaware, reappointed 12/07, PM. Action on Allwyn - ensure the retailer is aware of new appointment. _x000D_2/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:#Update Customer unaware, reappointed 12/07, PM. Action on Allwyn - ensure the retailer is aware of new appointment. _x000D_2/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1015638 | 30016860 | 6.Failed router install |  |  | 2024-06-28 | 2024-07-12 | 2024-07-17 | TRUE |  |  |  | 2024-08-07 |  |  |  | 2024-08-07 | 242005008504 |  | 2024-08-09 | 1
856 | 251903 | 3382 | Batch 5 Jul24 | Type 1 | FTTP | Fournews | Belfast | BT8 6LX |  | 2/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 2/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366061 | 30016903 | 6.Failed router install |  |  | 2024-06-28 | 2024-06-28 | 2024-06-28 | TRUE |  |  |  | 2024-07-25 |  |  |  | 2024-07-25 | 23A004952900 |  | 2024-07-26 | 1
857 | 661299 | 3390 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Premier Store | Leeds | LS9 6AP |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:03 _x000D_26/7/2024:22/07/2024 10:03 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:03 _x000D_26/7/2024:22/07/2024 10:03 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2366055 | 30016788 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
858 | 485127 | 3392 | Batch 5 Jul24 | Type 1 | FTTP | Cornish News | Derby | DE24 0LX |  | 2/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 2/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366057 | 30016789 | 6.Failed router install |  |  | 2024-06-28 | 2024-06-28 | 2024-06-28 | TRUE |  |  |  | 2024-07-25 |  |  |  | 2024-07-25 | 23A004946015 |  | 2024-07-26 | 1
859 | 486438 | 3399 | Batch 5 Jul24 | Type 1 | SOGEA | SPAR NEW ROMNEY | NEW ROMNEY | TN28 8BZ |  | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015527 | 30016743 | 2.Commissioning |  |  | 2024-06-28 | 2024-06-28 | 2024-06-28 | TRUE |  |  |  | 2024-07-25 | [7 empty] | 0
860 | 667958 | 3404 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Shop Daily | Maidenhead | SL6 2SZ |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 16/08 AM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 16/08 AM _x000D_19/8/2024:01457812 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 16/08 AM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 16/08 AM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 16/08 AM _x000D_13/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 16/08 AM _x000D_12/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 16/08 AM _x000D_9/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 16/08 AM _x000D_8/8/2024:17/07/2024 _x000D_6/8/2024:17/07/2024 _x000D_5/8/2024:17/07/2024 _x000D_2/8/2024:17/07/2024 _x000D_1/8/2024:17/07/2024 _x000D_31/7/2024:17/07/2024 _x000D_31/7/2024:17/07/2024 _x000D_30/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 16/08 AM _x000D_29/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 16/08 AM _x000D_29/7/2024:01457812 _x000D_26/7/2024:01457812 _x000D_24/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 16/08 AM _x000D_23/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 16/08 AM _x000D_22/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 16/08 AM _x000D_22/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 16/08 AM _x000D_2/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 16/08 AM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 16/08 AM _x000D_19/8/2024:01457812 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 16/08 AM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 16/08 AM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 16/08 AM _x000D_13/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 16/08 AM _x000D_12/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 16/08 AM _x000D_9/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 16/08 AM _x000D_8/8/2024:17/07/2024 _x000D_6/8/2024:17/07/2024 _x000D_5/8/2024:17/07/2024 _x000D_2/8/2024:17/07/2024 _x000D_1/8/2024:17/07/2024 _x000D_31/7/2024:17/07/2024 _x000D_31/7/2024:17/07/2024 _x000D_30/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 16/08 AM _x000D_29/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 16/08 AM _x000D_29/7/2024:01457812 _x000D_26/7/2024:01457812 _x000D_24/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 16/08 AM _x000D_23/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 16/08 AM _x000D_22/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 16/08 AM _x000D_22/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 16/08 AM _x000D_2/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | 0 | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015524 | 30016640 | 2.Commissioning | AM |  | 2024-06-28 | 2024-08-16 |  | 0 |  |  |  | 2024-09-18 | [7 empty] | 0
861 | 671768 | 3406 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Th&i Family Store | Gateshead | NE11 0XE |  | 6/9/2024:#Update Costs with VF for approval _x000D_5/9/2024:#Update Costs with VF for approval _x000D_4/9/2024:#Update Costs with VF for approval _x000D_3/9/2024:#Update Costs with VF for approval _x000D_2/9/2024:#Update Costs with VF for approval _x000D_29/8/2024:#Update Costs with VF for approval _x000D_28/8/2024:#Update Costs with VF for approval _x000D_27/8/2024:#Update Costs with VF for approval _x000D_22/8/2024:#Update Costs with VF for approval _x000D_21/8/2024:#Update Costs with VF for approval _x000D_20/8/2024:#Update Costs with VF for approval _x000D_19/8/2024:#Update Costs with VF for approval _x000D_19/8/2024:01413716 _x000D_16/8/2024:#Update Costs with VF for approval _x000D_15/8/2024:#Update Costs with VF for approval _x000D_14/8/2024:#Update Costs with VF for approval _x000D_13/8/2024:#Update Costs with VF for approval _x000D_12/8/2024:#Update Costs with VF for approval _x000D_9/8/2024:#Update Costs with VF for approval _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update Costs with VF for approval _x000D_29/7/2024:#Update Costs with VF for approval _x000D_29/7/2024:01413716 _x000D_26/7/2024:01413716 _x000D_24/7/2024:#Update Upgrade and OOH sent to VF to approve. _x000D_23/7/2024:#Update Upgrade and OOH sent to VF to approve. _x000D_22/7/2024:#Update Upgrade and OOH sent to VF to approve. _x000D_22/7/2024:#Update Upgrade and OOH sent to VF to approve. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update Costs with VF for approval _x000D_6/9/2024:#Update Costs with VF for approval _x000D_5/9/2024:#Update Costs with VF for approval _x000D_4/9/2024:#Update Costs with VF for approval _x000D_3/9/2024:#Update Costs with VF for approval _x000D_2/9/2024:#Update Costs with VF for approval _x000D_29/8/2024:#Update Costs with VF for approval _x000D_28/8/2024:#Update Costs with VF for approval _x000D_27/8/2024:#Update Costs with VF for approval _x000D_22/8/2024:#Update Costs with VF for approval _x000D_21/8/2024:#Update Costs with VF for approval _x000D_20/8/2024:#Update Costs with VF for approval _x000D_19/8/2024:#Update Costs with VF for approval _x000D_19/8/2024:01413716 _x000D_16/8/2024:#Update Costs with VF for approval _x000D_15/8/2024:#Update Costs with VF for approval _x000D_14/8/2024:#Update Costs with VF for approval _x000D_13/8/2024:#Update Costs with VF for approval _x000D_12/8/2024:#Update Costs with VF for approval _x000D_9/8/2024:#Update Costs with VF for approval _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update Costs with VF for approval _x000D_29/7/2024:#Update Costs with VF for approval _x000D_29/7/2024:01413716 _x000D_26/7/2024:01413716 _x000D_24/7/2024:#Update Upgrade and OOH sent to VF to approve. _x000D_23/7/2024:#Update Upgrade and OOH sent to VF to approve. _x000D_22/7/2024:#Update Upgrade and OOH sent to VF to approve. _x000D_22/7/2024:#Update Upgrade and OOH sent to VF to approve. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | #Update Costs with VF for approval | 2024-06-07 |  |  |  |  | VFS1015523 | 30016971 | 1.Provisioning | AM |  | 2024-06-28 | 2024-09-11 |  | 0 | [11 empty] | 0 | 671768
862 | 413843 | 3408 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Plessey Newsagents | BLYTH | NE24 3LB |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:14 _x000D_26/7/2024:22/07/2024 10:14 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:14 _x000D_26/7/2024:22/07/2024 10:14 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2366052 | 30016838 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
863 | 471707 | 3411 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Spar Canniford Loxton Road | Weston Super Mare | BS23 4QX |  | 6/9/2024:#Update - Retailer has confirmed appointment to occur during standard hours of 23/09 _x000D_5/9/2024:#Update - Retailer has confirmed appointment to occur during standard hours of 23/09 _x000D_4/9/2024:#Update - Retailer has confirmed appointment to occur during standard hours of 23/09 _x000D_3/9/2024:#Update - Retailer has confirmed appointment to occur during standard hours of 23/09 _x000D_2/9/2024:#Update - Retailer has confirmed appointment to occur during standard hours of 23/09 _x000D_29/8/2024:#Update - Retailer has confirmed appointment to occur during standard hours of 23/09 _x000D_28/8/2024:#Update - Retailer confirmed new date of 23/08 _x000D_27/8/2024:#Update - Retailer confirmed new date of 23/08 _x000D_22/8/2024:#Update - Retailer confirmed new date of 23/08 _x000D_21/8/2024:#Update - Retailer confirmed new date of 23/08 _x000D_20/8/2024:#Update - Retailer confirmed new date of 23/08 _x000D_19/8/2024:#Update - Retailer confirmed new date of 23/08 _x000D_19/8/2024:01457704 _x000D_16/8/2024:#Update - Retailer confirmed new date of 23/08 _x000D_15/8/2024:#Update - Retailer confirmed new date of 23/08 _x000D_14/8/2024:#Update - Retailer confirmed new date of 23/08 _x000D_13/8/2024:#Update - Retailer confirmed new date of 23/08 _x000D_12/8/2024:#Update - Retailer confirmed new date of 23/08 _x000D_9/8/2024:#Update - Retailer confirmed new date of 23/08 _x000D_8/8/2024:31/07/2024 _x000D_6/8/2024:31/07/2024 _x000D_5/8/2024:31/07/2024 _x000D_2/8/2024:31/07/2024 _x000D_1/8/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_30/7/2024:#Update - Pushed out for 23/08 - AM _x000D_29/7/2024:#Update - Pushed out for 23/08 - AM _x000D_29/7/2024:01457704 _x000D_26/7/2024:01457704 _x000D_24/7/2024:#Update - Pushed out for 23/08 - AM _x000D_23/7/2024:#Update - Pushed out for 23/08 - AM _x000D_22/7/2024:0 _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:Update: Order Amended _x000D_15/7/2024:Update: Order Amended _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:Your order has been delayed by our Suppliers due to a hoist / ladder being required to complete the installation. Please check with end user and re-appoint order for earliest date. _x000D_3/7/2024:Your order has been delayed by our Suppliers due to a hoist / ladder being required to complete the installation. Please check with end user and re-appoint order for earliest date. _x000D_2/7/2024:0 _x000D_1/7/2024:Supplier Delay: Delayed due to health and safety issues _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - Retailer has confirmed appointment to occur during standard hours of 23/09 _x000D_6/9/2024:#Update - Retailer has confirmed appointment to occur during standard hours of 23/09 _x000D_5/9/2024:#Update - Retailer has confirmed appointment to occur during standard hours of 23/09 _x000D_4/9/2024:#Update - Retailer has confirmed appointment to occur during standard hours of 23/09 _x000D_3/9/2024:#Update - Retailer has confirmed appointment to occur during standard hours of 23/09 _x000D_2/9/2024:#Update - Retailer has confirmed appointment to occur during standard hours of 23/09 _x000D_29/8/2024:#Update - Retailer has confirmed appointment to occur during standard hours of 23/09 _x000D_28/8/2024:#Update - Retailer confirmed new date of 23/08 _x000D_27/8/2024:#Update - Retailer confirmed new date of 23/08 _x000D_22/8/2024:#Update - Retailer confirmed new date of 23/08 _x000D_21/8/2024:#Update - Retailer confirmed new date of 23/08 _x000D_20/8/2024:#Update - Retailer confirmed new date of 23/08 _x000D_19/8/2024:#Update - Retailer confirmed new date of 23/08 _x000D_19/8/2024:01457704 _x000D_16/8/2024:#Update - Retailer confirmed new date of 23/08 _x000D_15/8/2024:#Update - Retailer confirmed new date of 23/08 _x000D_14/8/2024:#Update - Retailer confirmed new date of 23/08 _x000D_13/8/2024:#Update - Retailer confirmed new date of 23/08 _x000D_12/8/2024:#Update - Retailer confirmed new date of 23/08 _x000D_9/8/2024:#Update - Retailer confirmed new date of 23/08 _x000D_8/8/2024:31/07/2024 _x000D_6/8/2024:31/07/2024 _x000D_5/8/2024:31/07/2024 _x000D_2/8/2024:31/07/2024 _x000D_1/8/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_30/7/2024:#Update - Pushed out for 23/08 - AM _x000D_29/7/2024:#Update - Pushed out for 23/08 - AM _x000D_29/7/2024:01457704 _x000D_26/7/2024:01457704 _x000D_24/7/2024:#Update - Pushed out for 23/08 - AM _x000D_23/7/2024:#Update - Pushed out for 23/08 - AM _x000D_22/7/2024:0 _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:Update: Order Amended _x000D_15/7/2024:Update: Order Amended _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:Your order has been delayed by our Suppliers due to a hoist / ladder being required to complete the installation. Please check with end user and re-appoint order for earliest date. _x000D_3/7/2024:Your order has been delayed by our Suppliers due to a hoist / ladder being required to complete the installation. Please check with end user and re-appoint order for earliest date. _x000D_2/7/2024:0 _x000D_1/7/2024:Supplier Delay: Delayed due to health and safety issues _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update - Retailer has confirmed appointment to occur during standard hours of 23/09 | 2024-06-07 |  |  |  |  | VFS1015634 | 30016749 | 1.Provisioning | AM |  | 2024-06-28 | 2024-08-23 |  | 0 | [11 empty] | 0
864 | 659931 | 3412 | Batch 5 Jul24 | Type 3 | SoGEA/Mobile | Foregate News and Offlicence | Chester | CH1 1HE |  | 6/9/2024:#Update Retailer happy with appointment, 30/07, AM _x000D_5/9/2024:#Update Retailer happy with appointment, 30/07, AM _x000D_4/9/2024:#Update Retailer happy with appointment, 30/07, AM _x000D_3/9/2024:#Update Retailer happy with appointment, 30/07, AM _x000D_2/9/2024:#Update Retailer happy with appointment, 30/07, AM _x000D_29/8/2024:#Update Retailer happy with appointment, 30/07, AM _x000D_28/8/2024:#Update Retailer happy with appointment, 30/07, AM _x000D_27/8/2024:#Update Retailer happy with appointment, 30/07, AM _x000D_22/8/2024:#Update Retailer happy with appointment, 30/07, AM _x000D_21/8/2024:#Update Retailer happy with appointment, 30/07, AM _x000D_20/8/2024:#Update Retailer happy with appointment, 30/07, AM _x000D_19/8/2024:#Update Retailer happy with appointment, 30/07, AM _x000D_19/8/2024:01459602 _x000D_16/8/2024:#Update Retailer happy with appointment, 30/07, AM _x000D_15/8/2024:#Update Retailer happy with appointment, 30/07, AM _x000D_14/8/2024:#Update Retailer happy with appointment, 30/07, AM _x000D_13/8/2024:#Update Retailer happy with appointment, 30/07, AM _x000D_12/8/2024:#Update Retailer happy with appointment, 30/07, AM _x000D_9/8/2024:#Update Retailer happy with appointment, 30/07, AM _x000D_8/8/2024:24/07/2024 _x000D_6/8/2024:24/07/2024 _x000D_5/8/2024:24/07/2024 _x000D_2/8/2024:24/07/2024 _x000D_1/8/2024:24/07/2024 _x000D_31/7/2024:24/07/2024 _x000D_31/7/2024:24/07/2024 _x000D_30/7/2024:#Update Retailer happy with appointment, 30/07, AM _x000D_29/7/2024:#Update Retailer happy with appointment, 30/07, AM _x000D_29/7/2024:01459602 _x000D_26/7/2024:01459602 _x000D_24/7/2024:#Update Retailer happy with appointment, 30/07, AM _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:Your order requires planning validation. We may contact your customer if we need to. You will receive a further update by 20-06-2024. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/6/2024:Your order requires planning validation. We may contact your customer if we need to. You will receive a further update by 20-06-2024. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/6/2024:Your order requires planning validation. We may contact your customer if we need to. You will receive a further update by 20-06-2024. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/6/2024:Your order requires planning validation. We may contact your customer if we need to. You will receive a further update by 20-06-2024. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 9/9/2024:#Update Retailer happy with appointment, 30/07, AM _x000D_6/9/2024:#Update Retailer happy with appointment, 30/07, AM _x000D_5/9/2024:#Update Retailer happy with appointment, 30/07, AM _x000D_4/9/2024:#Update Retailer happy with appointment, 30/07, AM _x000D_3/9/2024:#Update Retailer happy with appointment, 30/07, AM _x000D_2/9/2024:#Update Retailer happy with appointment, 30/07, AM _x000D_29/8/2024:#Update Retailer happy with appointment, 30/07, AM _x000D_28/8/2024:#Update Retailer happy with appointment, 30/07, AM _x000D_27/8/2024:#Update Retailer happy with appointment, 30/07, AM _x000D_22/8/2024:#Update Retailer happy with appointment, 30/07, AM _x000D_21/8/2024:#Update Retailer happy with appointment, 30/07, AM _x000D_20/8/2024:#Update Retailer happy with appointment, 30/07, AM _x000D_19/8/2024:#Update Retailer happy with appointment, 30/07, AM _x000D_19/8/2024:01459602 _x000D_16/8/2024:#Update Retailer happy with appointment, 30/07, AM _x000D_15/8/2024:#Update Retailer happy with appointment, 30/07, AM _x000D_14/8/2024:#Update Retailer happy with appointment, 30/07, AM _x000D_13/8/2024:#Update Retailer happy with appointment, 30/07, AM _x000D_12/8/2024:#Update Retailer happy with appointment, 30/07, AM _x000D_9/8/2024:#Update Retailer happy with appointment, 30/07, AM _x000D_8/8/2024:24/07/2024 _x000D_6/8/2024:24/07/2024 _x000D_5/8/2024:24/07/2024 _x000D_2/8/2024:24/07/2024 _x000D_1/8/2024:24/07/2024 _x000D_31/7/2024:24/07/2024 _x000D_31/7/2024:24/07/2024 _x000D_30/7/2024:#Update Retailer happy with appointment, 30/07, AM _x000D_29/7/2024:#Update Retailer happy with appointment, 30/07, AM _x000D_29/7/2024:01459602 _x000D_26/7/2024:01459602 _x000D_24/7/2024:#Update Retailer happy with appointment, 30/07, AM _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:Your order requires planning validation. We may contact your customer if we need to. You will receive a further update by 20-06-2024. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/6/2024:Your order requires planning validation. We may contact your customer if we need to. You will receive a further update by 20-06-2024. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/6/2024:Your order requires planning validation. We may contact your customer if we need to. You will receive a further update by 20-06-2024. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/6/2024:Your order requires planning validation. We may contact your customer if we need to. You will receive a further update by 20-06-2024. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 0 | #Update Retailer happy with appointment, 30/07, AM | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015522 | 30016823 | 2.Commissioning | [9 empty] | 2024-09-05 | [7 empty] | 0
865 | 621817 | 3416 | Batch 5 Jul24 | Type 1 | FTTP | Premier | Durham | DL1 4SQ |  | 2/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 2/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366049 | 30016782 | 6.Failed router install |  |  | 2024-06-28 | 2024-06-28 | 2024-06-28 | TRUE |  |  |  | 2024-07-25 |  |  |  | 2024-07-25 | 242005013664 |  | 2024-07-26 | 1
866 | 646282 | 3417 | Batch 5 Jul24 | Type 1 | SOGEA | Central | BELFAST | BT1 5HD |  | 19/7/2024:#Update Failed install, Shop is in the process of moving existing cabling and plant. Shop has refused install as they do not want any of the existing cabling to be used. Shop will speak to their electricians and decide if they want to run new cabling to lottery machine, or agree another solution _x000D_18/7/2024:#Update Failed install, Shop is in the process of moving existing cabling and plant. Shop has refused install as they do not want any of the existing cabling to be used. Shop will speak to their electricians and decide if they want to run new cabling to lottery machine, or agree another solution _x000D_17/7/2024:#Update Failed install, Shop is in the process of moving existing cabling and plant. Shop has refused install as they do not want any of the existing cabling to be used. Shop will speak to their electricians and decide if they want to run new cabling to lottery machine, or agree another solution _x000D_16/7/2024:#Update Failed install, Shop is in the process of moving existing cabling and plant. Shop has refused install as they do not want any of the existing cabling to be used. Shop will speak to their electricians and decide if they want to run new cabling to lottery machine, or agree another solution _x000D_15/7/2024:#Update Failed install, Shop is in the process of moving existing cabling and plant. Shop has refused install as they do not want any of the existing cabling to be used. Shop will speak to their electricians and decide if they want to run new cabling to lottery machine, or agree another solution _x000D_12/7/2024:#Update Failed install, Shop is in the process of moving existing cabling and plant. Shop has refused install as they do not want any of the existing cabling to be used. Shop will speak to their electricians and decide if they want to run new cabling to lottery machine, or agree another solution _x000D_11/7/2024:#Update Failed install, Shop is in the process of moving existing cabling and plant. Shop has refused install as they do not want any of the existing cabling to be used. Shop will speak to their electricians and decide if they want to run new cabling to lottery machine, or agree another solution _x000D_10/7/2024:#Update Failed install, Shop is in the process of moving existing cabling and plant. Shop has refused install as they do not want any of the existing cabling to be used. Shop will speak to their electricians and decide if they want to run new cabling to lottery machine, or agree another solution _x000D_9/7/2024:#Update Failed install, Shop is in the process of moving existing cabling and plant. Shop has refused install as they do not want any of the existing cabling to be used. Shop will speak to their electricians and decide if they want to run new cabling to lottery machine, or agree another solution _x000D_4/7/2024:#Update Failed install, Shop is in the process of moving existing cabling and plant. Shop has refused install as they do not want any of the existing cabling to be used. Shop will speak to their electricians and decide if they want to run new cabling to lottery machine, or agree another solution _x000D_3/7/2024:#Update Failed install, Shop is in the process of moving existing cabling and plant. Shop has refused install as they do not want any of the existing cabling to be used. Shop will speak to their electricians and decide if they want to run new cabling to lottery machine, or agree another solution _x000D_2/7/2024:0 _x000D_1/7/2024:End User Missed appointment. Action required _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:#Update Failed install, Shop is in the process of moving existing cabling and plant. Shop has refused install as they do not want any of the existing cabling to be used. Shop will speak to their electricians and decide if they want to run new cabling to lottery machine, or agree another solution _x000D_18/7/2024:#Update Failed install, Shop is in the process of moving existing cabling and plant. Shop has refused install as they do not want any of the existing cabling to be used. Shop will speak to their electricians and decide if they want to run new cabling to lottery machine, or agree another solution _x000D_17/7/2024:#Update Failed install, Shop is in the process of moving existing cabling and plant. Shop has refused install as they do not want any of the existing cabling to be used. Shop will speak to their electricians and decide if they want to run new cabling to lottery machine, or agree another solution _x000D_16/7/2024:#Update Failed install, Shop is in the process of moving existing cabling and plant. Shop has refused install as they do not want any of the existing cabling to be used. Shop will speak to their electricians and decide if they want to run new cabling to lottery machine, or agree another solution _x000D_15/7/2024:#Update Failed install, Shop is in the process of moving existing cabling and plant. Shop has refused install as they do not want any of the existing cabling to be used. Shop will speak to their electricians and decide if they want to run new cabling to lottery machine, or agree another solution _x000D_12/7/2024:#Update Failed install, Shop is in the process of moving existing cabling and plant. Shop has refused install as they do not want any of the existing cabling to be used. Shop will speak to their electricians and decide if they want to run new cabling to lottery machine, or agree another solution _x000D_11/7/2024:#Update Failed install, Shop is in the process of moving existing cabling and plant. Shop has refused install as they do not want any of the existing cabling to be used. Shop will speak to their electricians and decide if they want to run new cabling to lottery machine, or agree another solution _x000D_10/7/2024:#Update Failed install, Shop is in the process of moving existing cabling and plant. Shop has refused install as they do not want any of the existing cabling to be used. Shop will speak to their electricians and decide if they want to run new cabling to lottery machine, or agree another solution _x000D_9/7/2024:#Update Failed install, Shop is in the process of moving existing cabling and plant. Shop has refused install as they do not want any of the existing cabling to be used. Shop will speak to their electricians and decide if they want to run new cabling to lottery machine, or agree another solution _x000D_4/7/2024:#Update Failed install, Shop is in the process of moving existing cabling and plant. Shop has refused install as they do not want any of the existing cabling to be used. Shop will speak to their electricians and decide if they want to run new cabling to lottery machine, or agree another solution _x000D_3/7/2024:#Update Failed install, Shop is in the process of moving existing cabling and plant. Shop has refused install as they do not want any of the existing cabling to be used. Shop will speak to their electricians and decide if they want to run new cabling to lottery machine, or agree another solution _x000D_2/7/2024:0 _x000D_1/7/2024:End User Missed appointment. Action required _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015519 | 30016882 | 2.Commissioning |  |  | 2024-06-28 | 2024-06-28 | 2024-06-28 | TRUE |  |  |  | 2024-07-24 | [7 empty] | 0
867 | 486815 | 3421 | Batch 5 Jul24 | Type 3 | FTTP/Mobile | Premier | Lowestoft | NR32 2BS |  | 6/9/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_5/9/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_4/9/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_3/9/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_2/9/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_29/8/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_28/8/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_27/8/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_22/8/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_21/8/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_20/8/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_19/8/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_19/8/2024:01457916 _x000D_16/8/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_15/8/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_14/8/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_13/8/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_12/8/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_9/8/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_8/8/2024:28/06/2024 _x000D_6/8/2024:28/06/2024 _x000D_5/8/2024:28/06/2024 _x000D_2/8/2024:28/06/2024 _x000D_1/8/2024:28/06/2024 _x000D_31/7/2024:28/06/2024 _x000D_31/7/2024:28/06/2024 _x000D_30/7/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_29/7/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_29/7/2024:01457916 _x000D_26/7/2024:01457916 _x000D_24/7/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_23/7/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_22/7/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_22/7/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_2/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_6/9/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_5/9/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_4/9/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_3/9/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_2/9/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_29/8/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_28/8/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_27/8/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_22/8/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_21/8/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_20/8/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_19/8/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_19/8/2024:01457916 _x000D_16/8/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_15/8/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_14/8/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_13/8/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_12/8/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_9/8/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_8/8/2024:28/06/2024 _x000D_6/8/2024:28/06/2024 _x000D_5/8/2024:28/06/2024 _x000D_2/8/2024:28/06/2024 _x000D_1/8/2024:28/06/2024 _x000D_31/7/2024:28/06/2024 _x000D_31/7/2024:28/06/2024 _x000D_30/7/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_29/7/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_29/7/2024:01457916 _x000D_26/7/2024:01457916 _x000D_24/7/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_23/7/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_22/7/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_22/7/2024:#Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed _x000D_2/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update - unsuccessful installation - complex routing required through ductwork, possible OOH, CSL are liaising with OR to obtain scope of work / possible upgrade and we will forward to VF once confirmed | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366051 | 30016616 | 2.Commissioning | AM |  |  |  |  | 0 |  |  |  | 2024-08-21 | [7 empty] | 0
868 | 425699 | 3423 | Batch 5 Jul24 | Type 1 | FTTP | Cheshunt News | WALTHAM CROSS | EN8 0LJ | 2024-07-18 | 12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFP2366047 | 30016886 | 6.Failed router install |  |  | 2024-06-28 | 2024-07-17 | 2024-07-17 | TRUE |  |  |  | 2024-08-07 |  |  |  | 2024-08-07 | 242005008501 |  | 2024-08-12 | 1
869 | 658988 | 3427 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | John's Convenience Store Premier | Maldon | CM9 6DZ |  | 6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_19/8/2024:01454670 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_13/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_12/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_9/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_8/8/2024:27/06/2024 _x000D_6/8/2024:27/06/2024 _x000D_5/8/2024:27/06/2024 _x000D_2/8/2024:27/06/2024 _x000D_1/8/2024:27/06/2024 _x000D_31/7/2024:27/06/2024 _x000D_31/7/2024:27/06/2024 _x000D_30/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_29/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_29/7/2024:01454670 _x000D_26/7/2024:01454670 _x000D_24/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_23/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_22/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_22/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_2/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_19/8/2024:01454670 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_13/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_12/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_9/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_8/8/2024:27/06/2024 _x000D_6/8/2024:27/06/2024 _x000D_5/8/2024:27/06/2024 _x000D_2/8/2024:27/06/2024 _x000D_1/8/2024:27/06/2024 _x000D_31/7/2024:27/06/2024 _x000D_31/7/2024:27/06/2024 _x000D_30/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_29/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_29/7/2024:01454670 _x000D_26/7/2024:01454670 _x000D_24/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_23/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_22/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_22/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM _x000D_2/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | #Update - Allwyn confirmed Retailer has agreed to installation on 22/07 AM | 2024-06-07 |  |  |  |  | VFP2366046 | 30016735 | 1.Provisioning | AM |  | 2024-06-28 | 2024-09-06 |  | 0 | [11 empty] | 0
870 | 665014 | 3429 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Thorrington Stores | COLCHESTER | CO7 8JP |  | 6/9/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_5/9/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_4/9/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_3/9/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_2/9/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_29/8/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_28/8/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_27/8/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_22/8/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_21/8/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_20/8/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_19/8/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_19/8/2024:01458377 _x000D_16/8/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_15/8/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_14/8/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_13/8/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_12/8/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_9/8/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_8/8/2024:02/07/2024 _x000D_6/8/2024:02/07/2024 _x000D_5/8/2024:02/07/2024 _x000D_2/8/2024:02/07/2024 _x000D_1/8/2024:02/07/2024 _x000D_31/7/2024:02/07/2024 _x000D_31/7/2024:02/07/2024 _x000D_30/7/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_29/7/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_29/7/2024:01458377 _x000D_26/7/2024:01458377 _x000D_24/7/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_23/7/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_22/7/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_22/7/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_2/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_6/9/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_5/9/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_4/9/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_3/9/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_2/9/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_29/8/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_28/8/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_27/8/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_22/8/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_21/8/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_20/8/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_19/8/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_19/8/2024:01458377 _x000D_16/8/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_15/8/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_14/8/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_13/8/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_12/8/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_9/8/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_8/8/2024:02/07/2024 _x000D_6/8/2024:02/07/2024 _x000D_5/8/2024:02/07/2024 _x000D_2/8/2024:02/07/2024 _x000D_1/8/2024:02/07/2024 _x000D_31/7/2024:02/07/2024 _x000D_31/7/2024:02/07/2024 _x000D_30/7/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_29/7/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_29/7/2024:01458377 _x000D_26/7/2024:01458377 _x000D_24/7/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_23/7/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_22/7/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_22/7/2024:#Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. _x000D_2/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update Missed appointment. Premier shop owner does not want cable running up from counter where lottery machine is and would like time to source conduit from Counter to false ceiling. OOHs also required due to access to false ceiling. | 2024-06-07 |  |  |  |  | VFP2365997 | 30016631 | 1.Provisioning | AM |  | 2024-06-28 | 2024-08-29 |  | 0 | [11 empty] | 0
871 | 450130 | 3433 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | SPAR ST NEOTS | St. Neots | PE19 1PX |  | 6/9/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_5/9/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_4/9/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_3/9/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_2/9/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_29/8/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_28/8/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_27/8/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_22/8/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_21/8/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_20/8/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_19/8/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_19/8/2024:01458105 _x000D_16/8/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_15/8/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_14/8/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_13/8/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_12/8/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_9/8/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_8/8/2024:01/07/2024 _x000D_6/8/2024:01/07/2024 _x000D_5/8/2024:01/07/2024 _x000D_2/8/2024:01/07/2024 _x000D_1/8/2024:01/07/2024 _x000D_31/7/2024:01/07/2024 _x000D_31/7/2024:01/07/2024 _x000D_30/7/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_29/7/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_29/7/2024:01458105 _x000D_26/7/2024:01458105 _x000D_24/7/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_23/7/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_22/7/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_22/7/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Advanced upgrade required due to complexity of install/routing; proposal sent to VF to approve _x000D_27/6/2024:#Update - Advanced upgrade required due to complexity of install/routing; proposal sent to VF to approve _x000D_25/6/2024:#Update - Advanced upgrade required due to complexity of install/routing; proposal sent to VF to approve _x000D_24/6/2024:#Update - Advanced upgrade required due to complexity of install/routing; proposal sent to VF to approve _x000D_20/6/2024:#Update - Advanced upgrade required due to complexity of install/routing; proposal sent to VF to approve _x000D_19/6/2024:#Update - Advanced upgrade required due to complexity of install/routing; proposal sent to VF to approve _x000D_18/6/2024:#Update - Advanced upgrade required due to complexity of install/routing; proposal sent to VF to approve _x000D_17/6/2024:#Update - Advanced upgrade required due to complexity of install/routing; proposal sent to VF to approve _x000D_14/6/2024:#Update - Advanced upgrade required due to complexity of install/routing; proposal sent to VF to approve _x000D_13/6/2024:#Update - Advanced upgrade required due to complexity of install/routing; proposal sent to VF to approve _x000D_12/6/2024:#Update - Advanced upgrade required due to complexity of install/routing; proposal sent to VF to approve _x000D_10/6/2024:#Update - Advanced upgrade required due to complexity of install/routing; proposal sent to VF to approve _x000D_7/6/2024:#Update - Advanced upgrade required due to complexity of install/routing; proposal sent to VF to approve _x000D_6/6/2024:#Update - Advanced upgrade required due to complexity of install/routing; proposal sent to VF to approve _x000D_5/6/2024:#Update - Advanced upgrade required due to complexity of install/routing; proposal sent to VF to approve _x000D_4/6/2024:#Update - Advanced upgrade required due to complexity of install/routing; proposal sent to VF to approve _x000D_ | 9/9/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_6/9/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_5/9/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_4/9/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_3/9/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_2/9/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_29/8/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_28/8/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_27/8/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_22/8/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_21/8/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_20/8/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_19/8/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_19/8/2024:01458105 _x000D_16/8/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_15/8/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_14/8/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_13/8/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_12/8/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_9/8/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_8/8/2024:01/07/2024 _x000D_6/8/2024:01/07/2024 _x000D_5/8/2024:01/07/2024 _x000D_2/8/2024:01/07/2024 _x000D_1/8/2024:01/07/2024 _x000D_31/7/2024:01/07/2024 _x000D_31/7/2024:01/07/2024 _x000D_30/7/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_29/7/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_29/7/2024:01458105 _x000D_26/7/2024:01458105 _x000D_24/7/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_23/7/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_22/7/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_22/7/2024:#Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Advanced upgrade required due to complexity of install/routing; proposal sent to VF to approve _x000D_27/6/2024:#Update - Advanced upgrade required due to complexity of install/routing; proposal sent to VF to approve _x000D_25/6/2024:#Update - Advanced upgrade required due to complexity of install/routing; proposal sent to VF to approve _x000D_24/6/2024:#Update - Advanced upgrade required due to complexity of install/routing; proposal sent to VF to approve _x000D_20/6/2024:#Update - Advanced upgrade required due to complexity of install/routing; proposal sent to VF to approve _x000D_19/6/2024:#Update - Advanced upgrade required due to complexity of install/routing; proposal sent to VF to approve _x000D_18/6/2024:#Update - Advanced upgrade required due to complexity of install/routing; proposal sent to VF to approve _x000D_17/6/2024:#Update - Advanced upgrade required due to complexity of install/routing; proposal sent to VF to approve _x000D_14/6/2024:#Update - Advanced upgrade required due to complexity of install/routing; proposal sent to VF to approve _x000D_13/6/2024:#Update - Advanced upgrade required due to complexity of install/routing; proposal sent to VF to approve _x000D_12/6/2024:#Update - Advanced upgrade required due to complexity of install/routing; proposal sent to VF to approve _x000D_10/6/2024:#Update - Advanced upgrade required due to complexity of install/routing; proposal sent to VF to approve _x000D_7/6/2024:#Update - Advanced upgrade required due to complexity of install/routing; proposal sent to VF to approve _x000D_6/6/2024:#Update - Advanced upgrade required due to complexity of install/routing; proposal sent to VF to approve _x000D_5/6/2024:#Update - Advanced upgrade required due to complexity of install/routing; proposal sent to VF to approve _x000D_4/6/2024:#Update - Advanced upgrade required due to complexity of install/routing; proposal sent to VF to approve _x000D_ | 0 | #Update - Address verification required - The address provided on the order form is 200 Cambridge Street, St. Neots PE19 1PX however Openreach advise the correct address is Unit 1 2 steeple court, Cambridge Street, St. Neots PE19 1QB. | 2024-06-07 |  |  |  |  | VFS1015630 | 30016879 | 1.Provisioning | AM |  | 2024-06-28 | 2024-06-28 |  | 0 | [11 empty] | 0
872 | 110591 | 3434 | Batch 5 Jul24 | Type 1 | SOGEA | Nisa Local | LUTON | LU1 5RD |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | 0 | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015629 | 30016855 | 2.Commissioning | [9 empty] | 2024-07-26 | [7 empty] | 0
873 | 637541 | 3438 | Batch 5 Jul24 | Type 1 | SOGEA | Spar Maxol | ANTRIM | BT41 4JG |  | 19/7/2024:#Update - Recieved clarification on OOH - This site does not need OOH appointment. This can simply go ahead for the 05/08 with a normal standard appointment, and a Hoist will be deployed for this date. _x000D_18/7/2024:#Update - Recieved clarification on OOH - This site does not need OOH appointment. This can simply go ahead for the 05/08 with a normal standard appointment, and a Hoist will be deployed for this date. _x000D_17/7/2024:#Update - Recieved clarification on OOH - This site does not need OOH appointment. This can simply go ahead for the 05/08 with a normal standard appointment, and a Hoist will be deployed for this date. _x000D_16/7/2024:#Update - Recieved clarification on OOH - This site does not need OOH appointment. This can simply go ahead for the 05/08 with a normal standard appointment, and a Hoist will be deployed for this date. _x000D_15/7/2024:#Update - Recieved clarification on OOH - This site does not need OOH appointment. This can simply go ahead for the 05/08 with a normal standard appointment, and a Hoist will be deployed for this date. _x000D_12/7/2024:#Update - Awaiting information regarding OOH - I have pushed this to 05/08 , and the retailer has confirmed this appoint. _x000D_11/7/2024:#Update - Engineer has retained this for Tuesday - Will check hud for then. _x000D_10/7/2024:#Update - Engineer has retained this for Tuesday - Will check hud for then. _x000D_9/7/2024:#Update - Engineer has retained this for Tuesday - Will check hud for then. _x000D_4/7/2024:#Update - Engineer has retained this for Tuesday - Will check hud for then. _x000D_3/7/2024:#Update - Engineer has retained this for Tuesday - Will check hud for then. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Engineer has retained this for Tuesday - Will check hud for then. _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:#Update - Recieved clarification on OOH - This site does not need OOH appointment. This can simply go ahead for the 05/08 with a normal standard appointment, and a Hoist will be deployed for this date. _x000D_18/7/2024:#Update - Recieved clarification on OOH - This site does not need OOH appointment. This can simply go ahead for the 05/08 with a normal standard appointment, and a Hoist will be deployed for this date. _x000D_17/7/2024:#Update - Recieved clarification on OOH - This site does not need OOH appointment. This can simply go ahead for the 05/08 with a normal standard appointment, and a Hoist will be deployed for this date. _x000D_16/7/2024:#Update - Recieved clarification on OOH - This site does not need OOH appointment. This can simply go ahead for the 05/08 with a normal standard appointment, and a Hoist will be deployed for this date. _x000D_15/7/2024:#Update - Recieved clarification on OOH - This site does not need OOH appointment. This can simply go ahead for the 05/08 with a normal standard appointment, and a Hoist will be deployed for this date. _x000D_12/7/2024:#Update - Awaiting information regarding OOH - I have pushed this to 05/08 , and the retailer has confirmed this appoint. _x000D_11/7/2024:#Update - Engineer has retained this for Tuesday - Will check hud for then. _x000D_10/7/2024:#Update - Engineer has retained this for Tuesday - Will check hud for then. _x000D_9/7/2024:#Update - Engineer has retained this for Tuesday - Will check hud for then. _x000D_4/7/2024:#Update - Engineer has retained this for Tuesday - Will check hud for then. _x000D_3/7/2024:#Update - Engineer has retained this for Tuesday - Will check hud for then. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Engineer has retained this for Tuesday - Will check hud for then. _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366043 | 30016742 | 6.Failed router install |  |  | 2024-06-28 | 2024-06-28 | 2024-06-28 | TRUE |  |  |  | 2024-07-25 |  |  |  | 2024-07-25 | 242005010431 |  | 2024-07-26 | 1
874 | 478898 | 98 | Batch 2 Apr24 | Type 1 | FTTP | Seaford News | Seaford | BN25 1LX | 2024-07-02 | 4/7/2024:#Update - Reappointed for 31.05- AM. Action for Allwyn - Please confirm with retailer. _x000D_3/7/2024:#Update - Reappointed for 31.05- AM. Action for Allwyn - Please confirm with retailer. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Reappointed for 31.05- AM. Action for Allwyn - Please confirm with retailer. _x000D_27/6/2024:#Update - Reappointed for 31.05- AM. Action for Allwyn - Please confirm with retailer. _x000D_25/6/2024:#Update - Reappointed for 31.05- AM. Action for Allwyn - Please confirm with retailer. _x000D_24/6/2024:#Update - Reappointed for 31.05- AM. Action for Allwyn - Please confirm with retailer. _x000D_20/6/2024:#Update - Reappointed for 31.05- AM. Action for Allwyn - Please confirm with retailer. _x000D_19/6/2024:#Update - Reappointed for 31.05- AM. Action for Allwyn - Please confirm with retailer. _x000D_18/6/2024:#Update - Reappointed for 31.05- AM. Action for Allwyn - Please confirm with retailer. _x000D_17/6/2024:#Update - Reappointed for 31.05- AM. Action for Allwyn - Please confirm with retailer. _x000D_14/6/2024:#Update - Reappointed for 31.05- AM. Action for Allwyn - Please confirm with retailer. _x000D_13/6/2024:#Update - Reappointed for 31.05- AM. Action for Allwyn - Please confirm with retailer. _x000D_12/6/2024:#Update - Reappointed for 31.05- AM. Action for Allwyn - Please confirm with retailer. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:Your order has been delayed due to a sales query raised by our supplier. There are several existing line at premises. Please confirm with end user that a new line is required to progress the order further. CSL Note: Invalid appointment slot received CSL N _x000D_31/5/2024:Your order has been delayed due to a sales query raised by our supplier. There are several existing line at premises. Please confirm with end user that a new line is required to progress the order further. CSL Note: Invalid appointment slot received CSL N _x000D_30/5/2024:Your order has been delayed due to a sales query raised by our supplier. There are several existing line at premises. Please confirm with end user that a new line is required to progress the order further. CSL Note: Invalid appointment slot received CSL N _x000D_29/5/2024:Your order has been delayed due to a sales query raised by our supplier. There are several existing line at premises. Please confirm with end user that a new line is required to progress the order further. CSL Note: Invalid appointment slot received CSL N _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 4/7/2024:#Update - Reappointed for 31.05- AM. Action for Allwyn - Please confirm with retailer. _x000D_3/7/2024:#Update - Reappointed for 31.05- AM. Action for Allwyn - Please confirm with retailer. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Reappointed for 31.05- AM. Action for Allwyn - Please confirm with retailer. _x000D_27/6/2024:#Update - Reappointed for 31.05- AM. Action for Allwyn - Please confirm with retailer. _x000D_25/6/2024:#Update - Reappointed for 31.05- AM. Action for Allwyn - Please confirm with retailer. _x000D_24/6/2024:#Update - Reappointed for 31.05- AM. Action for Allwyn - Please confirm with retailer. _x000D_20/6/2024:#Update - Reappointed for 31.05- AM. Action for Allwyn - Please confirm with retailer. _x000D_19/6/2024:#Update - Reappointed for 31.05- AM. Action for Allwyn - Please confirm with retailer. _x000D_18/6/2024:#Update - Reappointed for 31.05- AM. Action for Allwyn - Please confirm with retailer. _x000D_17/6/2024:#Update - Reappointed for 31.05- AM. Action for Allwyn - Please confirm with retailer. _x000D_14/6/2024:#Update - Reappointed for 31.05- AM. Action for Allwyn - Please confirm with retailer. _x000D_13/6/2024:#Update - Reappointed for 31.05- AM. Action for Allwyn - Please confirm with retailer. _x000D_12/6/2024:#Update - Reappointed for 31.05- AM. Action for Allwyn - Please confirm with retailer. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:Your order has been delayed due to a sales query raised by our supplier. There are several existing line at premises. Please confirm with end user that a new line is required to progress the order further. CSL Note: Invalid appointment slot received CSL N _x000D_31/5/2024:Your order has been delayed due to a sales query raised by our supplier. There are several existing line at premises. Please confirm with end user that a new line is required to progress the order further. CSL Note: Invalid appointment slot received CSL N _x000D_30/5/2024:Your order has been delayed due to a sales query raised by our supplier. There are several existing line at premises. Please confirm with end user that a new line is required to progress the order further. CSL Note: Invalid appointment slot received CSL N _x000D_29/5/2024:Your order has been delayed due to a sales query raised by our supplier. There are several existing line at premises. Please confirm with end user that a new line is required to progress the order further. CSL Note: Invalid appointment slot received CSL N _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-04-04 | 05/04/2024: Allwyn to make the retailer know. 22/03/24: Action- Allwyn to give the retailer a heads up 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 2.Allwyn to arrange access | VFP2303084 | 30013175 | 6.Failed router install | AM |  | 2024-07-01 | 2024-07-01 | 2024-07-01 | TRUE |  |  |  | 2024-07-25 |  |  |  | 2024-07-25 | 23A004948638 |  | 2024-07-29 | 1
875 | 605905 | 562 | Batch 3 May24 | Type 1 | SOGEA | Premier Ivor Hale Supermarket | Llwynpia | CF40 2JJ | 2024-06-07 | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_3/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_27/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_25/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_24/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_20/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_19/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_18/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_17/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_14/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_13/6/2024:#Update - Action for Allwyn - Installation has now been amended to 01/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 01/07 is a suitable date. _x000D_12/6/2024:#Update - Missed Appointment - The retailer was unaware of the order and therefore refused entry. Additionally the engineer has been advised that the shop will be undergoing a refurbishment in the near future. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_3/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_27/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_25/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_24/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_20/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_19/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_18/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_17/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_14/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_13/6/2024:#Update - Action for Allwyn - Installation has now been amended to 01/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 01/07 is a suitable date. _x000D_12/6/2024:#Update - Missed Appointment - The retailer was unaware of the order and therefore refused entry. Additionally the engineer has been advised that the shop will be undergoing a refurbishment in the near future. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300759 | 30013452 | 6.Failed router install | AM |  | 2024-05-23 | 2024-07-09 | 2024-07-09 | TRUE |  |  |  | 2024-08-05 |  |  |  | 2024-08-05 | 239004929415 |  | 2024-08-06 | 1
876 | 631985 | 703 | Batch 3 May24 | Type 1 | SOGEA | Walworth Road Food & Wine | London | SE17 2TE | 2024-07-02 | 29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_4/7/2024:#Update The retailer is happy with the new appointment on 03/07, AM. _x000D_3/7/2024:#Update The retailer is happy with the new appointment on 03/07, AM. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update Upgrade and OOH approved, scheduled for 03/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_27/6/2024:#Update Upgrade and OOH approved, scheduled for 03/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_25/6/2024:#Update Upgrade and OOH approved, scheduled for 03/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_24/6/2024:#Update Still awaiting Allwyn's approval for an upgrade. _x000D_20/6/2024:#Update Still awaiting Allwyn's approval for an upgrade. _x000D_19/6/2024:#Update Still awaiting Allwyn's approval for an upgrade. _x000D_18/6/2024:#Update Still awaiting Allwyn's approval for an upgrade. _x000D_17/6/2024:#Update Still awaiting Allwyn's approval for an upgrade. _x000D_14/6/2024:#Update Still awaiting Allwyn's approval for an upgrade. _x000D_13/6/2024:#Update Still awaiting Allwyn's approval for an upgrade. _x000D_12/6/2024:#Update Still awaiting Allwyn's approval for an upgrade. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_4/7/2024:#Update The retailer is happy with the new appointment on 03/07, AM. _x000D_3/7/2024:#Update The retailer is happy with the new appointment on 03/07, AM. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update Upgrade and OOH approved, scheduled for 03/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_27/6/2024:#Update Upgrade and OOH approved, scheduled for 03/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_25/6/2024:#Update Upgrade and OOH approved, scheduled for 03/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_24/6/2024:#Update Still awaiting Allwyn's approval for an upgrade. _x000D_20/6/2024:#Update Still awaiting Allwyn's approval for an upgrade. _x000D_19/6/2024:#Update Still awaiting Allwyn's approval for an upgrade. _x000D_18/6/2024:#Update Still awaiting Allwyn's approval for an upgrade. _x000D_17/6/2024:#Update Still awaiting Allwyn's approval for an upgrade. _x000D_14/6/2024:#Update Still awaiting Allwyn's approval for an upgrade. _x000D_13/6/2024:#Update Still awaiting Allwyn's approval for an upgrade. _x000D_12/6/2024:#Update Still awaiting Allwyn's approval for an upgrade. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-05-09 | 09/05/2024: Allwyn to make the retailer aware in the date in column U |  |  | 2.Allwyn to arrange access | VFP2300900 | 30013593 | 6.Failed router install | AM |  | 2024-05-08 | 2024-07-01 | 2024-07-01 | TRUE |  |  |  | 2024-07-25 |  |  |  | 2024-07-25 | 242005011169 |  | 2024-07-29 | 1
877 | 625028 | 704 | Batch 3 May24 | Type 1 | SOGEA | Newsforce | Whitley Bay | NE26 2SS | 2024-07-04 | 19/7/2024:Update: Order Amended _x000D_18/7/2024:Update: Order Amended _x000D_17/7/2024:Update: Order Amended _x000D_16/7/2024:Update: Order Amended _x000D_15/7/2024:Update: Order Amended _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 19/7/2024:Update: Order Amended _x000D_18/7/2024:Update: Order Amended _x000D_17/7/2024:Update: Order Amended _x000D_16/7/2024:Update: Order Amended _x000D_15/7/2024:Update: Order Amended _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-05-09 | 09/05/2024: CSL to provide an update |  |  | 2.Allwyn to arrange access | VFP2300901 | 30013594 | 2.Commissioning | AM |  | 2024-05-08 | 2024-07-03 | 2024-07-03 | TRUE |  |  |  | 2024-07-24 | [7 empty] | 0
878 | 660075 | 900 | Batch 3 May24 | Type 1 | SoGEA/Mobile | Belvoir News | Coalville | LE67 3XF | 2024-09-03 | 6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:Order Completed _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:Update: Order Amended _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_12/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_9/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_8/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_6/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_5/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_18/7/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_17/7/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_16/7/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_15/7/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_12/7/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_11/7/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_10/7/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_9/7/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_4/7/2024:#Update - missed appointment - no site contact / shop closed Action on Allwyn to confirm reappointed install date _x000D_3/7/2024:#Update - missed appointment - no site contact / shop closed Action on Allwyn to confirm reappointed install date _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - missed appointment - no site contact / shop closed Action on Allwyn to confirm reappointed install date _x000D_27/6/2024:#Update - missed appointment - no site contact / shop closed Action on Allwyn to confirm reappointed install date _x000D_25/6/2024:#Update - missed appointment - no site contact / shop closed Action on Allwyn to confirm reappointed install date _x000D_24/6/2024:#Update - missed appointment - no site contact / shop closed Action on Allwyn to confirm reappointed install date _x000D_20/6/2024:#Update - missed appointment - no site contact / shop closed Action on Allwyn to confirm reappointed install date _x000D_19/6/2024:#Update - missed appointment - no site contact / shop closed Action on Allwyn to confirm reappointed install date _x000D_18/6/2024:#Update - missed appointment - no site contact / shop closed Action on Allwyn to confirm reappointed install date _x000D_17/6/2024:#Update - missed appointment - no site contact / shop closed Action on Allwyn to confirm reappointed install date _x000D_14/6/2024:#Update - missed appointment - no site contact / shop closed Action on Allwyn to confirm reappointed install date _x000D_13/6/2024:#Update - missed appointment - no site contact / shop closed Action on Allwyn to confirm reappointed install date _x000D_12/6/2024:#Update - missed appointment - no site contact / shop closed Action on Allwyn to confirm reappointed install date _x000D_0 | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:Order Completed _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:Update: Order Amended _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_12/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_9/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_8/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_6/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_5/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_18/7/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_17/7/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_16/7/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_15/7/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_12/7/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_11/7/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_10/7/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_9/7/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_4/7/2024:#Update - missed appointment - no site contact / shop closed Action on Allwyn to confirm reappointed install date _x000D_3/7/2024:#Update - missed appointment - no site contact / shop closed Action on Allwyn to confirm reappointed install date _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - missed appointment - no site contact / shop closed Action on Allwyn to confirm reappointed install date _x000D_27/6/2024:#Update - missed appointment - no site contact / shop closed Action on Allwyn to confirm reappointed install date _x000D_25/6/2024:#Update - missed appointment - no site contact / shop closed Action on Allwyn to confirm reappointed install date _x000D_24/6/2024:#Update - missed appointment - no site contact / shop closed Action on Allwyn to confirm reappointed install date _x000D_20/6/2024:#Update - missed appointment - no site contact / shop closed Action on Allwyn to confirm reappointed install date _x000D_19/6/2024:#Update - missed appointment - no site contact / shop closed Action on Allwyn to confirm reappointed install date _x000D_18/6/2024:#Update - missed appointment - no site contact / shop closed Action on Allwyn to confirm reappointed install date _x000D_17/6/2024:#Update - missed appointment - no site contact / shop closed Action on Allwyn to confirm reappointed install date _x000D_14/6/2024:#Update - missed appointment - no site contact / shop closed Action on Allwyn to confirm reappointed install date _x000D_13/6/2024:#Update - missed appointment - no site contact / shop closed Action on Allwyn to confirm reappointed install date _x000D_12/6/2024:#Update - missed appointment - no site contact / shop closed Action on Allwyn to confirm reappointed install date _x000D_0 | Order Completed | 0 | 2024-05-20 | 20/05/24: CSL to provide update |  |  | 5.CSL | VFS975491 | 30013790 | 2.Commissioning | AM |  | 2024-05-17 | 2024-09-02 |  | 0 | [11 empty] | 0
879 | 664615 | 1049 | Batch 3 May24 | Type 1 | FTTP/Mobile | Centra | BELFAST | BT15 3HE | 2024-06-07 | 6/9/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_5/9/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_4/9/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_3/9/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_2/9/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_29/8/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_28/8/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_27/8/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_22/8/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_21/8/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_20/8/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_19/8/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_19/8/2024:01425783 _x000D_16/8/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_15/8/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_14/8/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_13/8/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_12/8/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_9/8/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_8/8/2024:05/07/2024 _x000D_6/8/2024:05/07/2024 _x000D_5/8/2024:05/07/2024 _x000D_2/8/2024:05/07/2024 _x000D_1/8/2024:05/07/2024 _x000D_31/7/2024:05/07/2024 _x000D_31/7/2024:05/07/2024 _x000D_30/7/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_29/7/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_29/7/2024:01425783 _x000D_26/7/2024:01425783 _x000D_24/7/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_23/7/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_22/7/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_22/7/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:#Update - Reappointed date confirmed with retailer 01/07-AM _x000D_3/7/2024:#Update - Reappointed date confirmed with retailer 01/07-AM _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Reappointed date confirmed with retailer 01/07-AM _x000D_27/6/2024:#Update - Reappointed date confirmed with retailer 01/07-AM _x000D_25/6/2024:#Update - Reappointed date confirmed with retailer 01/07-AM _x000D_24/6/2024:#Update - Reappointed date confirmed with retailer 01/07-AM _x000D_20/6/2024:#Update - Reappointed date confirmed with retailer 01/07-AM _x000D_19/6/2024:#Update - Reappointed date confirmed with retailer 01/07-AM _x000D_18/6/2024:#Update - Reappointed date confirmed with retailer 01/07-AM _x000D_17/6/2024:#Update - Reappointed date confirmed with retailer 01/07-AM _x000D_14/6/2024:#Update - Reappointed date confirmed with retailer 01/07-AM _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_6/9/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_5/9/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_4/9/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_3/9/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_2/9/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_29/8/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_28/8/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_27/8/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_22/8/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_21/8/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_20/8/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_19/8/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_19/8/2024:01425783 _x000D_16/8/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_15/8/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_14/8/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_13/8/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_12/8/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_9/8/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_8/8/2024:05/07/2024 _x000D_6/8/2024:05/07/2024 _x000D_5/8/2024:05/07/2024 _x000D_2/8/2024:05/07/2024 _x000D_1/8/2024:05/07/2024 _x000D_31/7/2024:05/07/2024 _x000D_31/7/2024:05/07/2024 _x000D_30/7/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_29/7/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_29/7/2024:01425783 _x000D_26/7/2024:01425783 _x000D_24/7/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_23/7/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_22/7/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_22/7/2024:#UPDATE: Multi-Port ONT site. Install pushed to 05/08 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:#Update - Reappointed date confirmed with retailer 01/07-AM _x000D_3/7/2024:#Update - Reappointed date confirmed with retailer 01/07-AM _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Reappointed date confirmed with retailer 01/07-AM _x000D_27/6/2024:#Update - Reappointed date confirmed with retailer 01/07-AM _x000D_25/6/2024:#Update - Reappointed date confirmed with retailer 01/07-AM _x000D_24/6/2024:#Update - Reappointed date confirmed with retailer 01/07-AM _x000D_20/6/2024:#Update - Reappointed date confirmed with retailer 01/07-AM _x000D_19/6/2024:#Update - Reappointed date confirmed with retailer 01/07-AM _x000D_18/6/2024:#Update - Reappointed date confirmed with retailer 01/07-AM _x000D_17/6/2024:#Update - Reappointed date confirmed with retailer 01/07-AM _x000D_14/6/2024:#Update - Reappointed date confirmed with retailer 01/07-AM _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #UPDATE: Multi-Port ONT site. Install pushed to 05/08 |  |  |  |  | 2.Allwyn to arrange access | VFP2376428 | 30013939 | 1.Provisioning | AM |  | 2024-05-22 | 2024-09-06 |  | 0 | [11 empty] | 0
880 | 665974 | 1095 | Batch 3 May24 | Type 1 | SOGEA | Green Lane Post Office | THORNTON HEATH | CR7 8BB | 2024-07-02 | 29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_18/7/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_17/7/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_16/7/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_15/7/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_12/7/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_11/7/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_10/7/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_9/7/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_4/7/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_3/7/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_27/6/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_25/6/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_24/6/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_20/6/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_19/6/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_18/6/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_17/6/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_14/6/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_13/6/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_12/6/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_18/7/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_17/7/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_16/7/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_15/7/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_12/7/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_11/7/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_10/7/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_9/7/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_4/7/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_3/7/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_27/6/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_25/6/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_24/6/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_20/6/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_19/6/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_18/6/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_17/6/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_14/6/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_13/6/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_12/6/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFP2301292 | 30013985 | 6.Failed router install | AM |  | 2024-05-23 | 2024-07-01 | 2024-07-01 | TRUE |  |  |  | 2024-07-25 |  |  |  | 2024-07-25 | 242005011163 |  | 2024-07-29 | 1
881 | 665276 | 1118 | Batch 3 May24 | Type 3 | SoGEA/Mobile | ORFORD AVENUE SPSO | NOTTINGHAM | NG11 8GY | 2024-07-29 | 6/9/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_5/9/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_4/9/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_3/9/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_2/9/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_29/8/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_28/8/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_27/8/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_22/8/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_21/8/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_20/8/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_19/8/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_19/8/2024:01408679 _x000D_16/8/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_15/8/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_14/8/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_13/8/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_12/8/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_9/8/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_8/8/2024:24/05/2024 _x000D_6/8/2024:24/05/2024 _x000D_5/8/2024:24/05/2024 _x000D_2/8/2024:24/05/2024 _x000D_1/8/2024:24/05/2024 _x000D_31/7/2024:24/05/2024 _x000D_31/7/2024:24/05/2024 _x000D_30/7/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_29/7/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_29/7/2024:01408679 _x000D_26/7/2024:01408679 _x000D_24/7/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_23/7/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_22/7/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_22/7/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_4/7/2024:#Update order has been re-raised for 01/07/2024 (AM slot) - awaiting TRC approval from Allwyn _x000D_3/7/2024:#Update order has been re-raised for 01/07/2024 (AM slot) - awaiting TRC approval from Allwyn _x000D_2/7/2024:0 _x000D_1/7/2024:#Update order has been re-raised for 01/07/2024 (AM slot) - awaiting TRC approval from Allwyn _x000D_27/6/2024:#Update order has been re-raised for 01/07/2024 (AM slot) - awaiting TRC approval from Allwyn _x000D_25/6/2024:#Update order has been re-raised for 01/07/2024 (AM slot) - awaiting TRC approval from Allwyn _x000D_24/6/2024:#Update order has been re-raised for 01/07/2024 (AM slot) - awaiting TRC approval from Allwyn _x000D_20/6/2024:#Update order has been re-raised for 01/07/2024 (AM slot) - awaiting TRC approval from Allwyn _x000D_19/6/2024:#Update order has been re-raised for 01/07/2024 (AM slot) - awaiting TRC approval from Allwyn _x000D_18/6/2024:#Update order has been re-raised for 01/07/2024 (AM slot) - awaiting TRC approval from Allwyn _x000D_17/6/2024:#Update order has been re-raised for 01/07/2024 (AM slot) - awaiting TRC approval from Allwyn _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_6/9/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_5/9/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_4/9/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_3/9/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_2/9/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_29/8/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_28/8/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_27/8/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_22/8/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_21/8/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_20/8/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_19/8/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_19/8/2024:01408679 _x000D_16/8/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_15/8/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_14/8/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_13/8/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_12/8/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_9/8/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_8/8/2024:24/05/2024 _x000D_6/8/2024:24/05/2024 _x000D_5/8/2024:24/05/2024 _x000D_2/8/2024:24/05/2024 _x000D_1/8/2024:24/05/2024 _x000D_31/7/2024:24/05/2024 _x000D_31/7/2024:24/05/2024 _x000D_30/7/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_29/7/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_29/7/2024:01408679 _x000D_26/7/2024:01408679 _x000D_24/7/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_23/7/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_22/7/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_22/7/2024:#Update Installation 24/05/2024 failed, drilling will be required _x000D_4/7/2024:#Update order has been re-raised for 01/07/2024 (AM slot) - awaiting TRC approval from Allwyn _x000D_3/7/2024:#Update order has been re-raised for 01/07/2024 (AM slot) - awaiting TRC approval from Allwyn _x000D_2/7/2024:0 _x000D_1/7/2024:#Update order has been re-raised for 01/07/2024 (AM slot) - awaiting TRC approval from Allwyn _x000D_27/6/2024:#Update order has been re-raised for 01/07/2024 (AM slot) - awaiting TRC approval from Allwyn _x000D_25/6/2024:#Update order has been re-raised for 01/07/2024 (AM slot) - awaiting TRC approval from Allwyn _x000D_24/6/2024:#Update order has been re-raised for 01/07/2024 (AM slot) - awaiting TRC approval from Allwyn _x000D_20/6/2024:#Update order has been re-raised for 01/07/2024 (AM slot) - awaiting TRC approval from Allwyn _x000D_19/6/2024:#Update order has been re-raised for 01/07/2024 (AM slot) - awaiting TRC approval from Allwyn _x000D_18/6/2024:#Update order has been re-raised for 01/07/2024 (AM slot) - awaiting TRC approval from Allwyn _x000D_17/6/2024:#Update order has been re-raised for 01/07/2024 (AM slot) - awaiting TRC approval from Allwyn _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update Installation 24/05/2024 failed, drilling will be required |  |  |  |  | 3.Allwyn to arrange rtr install | VFS978134 | 30014008 | 2.Commissioning | AM |  | 2024-07-26 | 2024-07-26 |  | 0 |  |  |  | 2024-08-27 | [7 empty] | 0
882 | 431292 | 1314 | Batch 3 May24 | Type 3 | SOGEA | Nisa Local | LONDON | E14 3HW | 2024-06-07 | 6/9/2024:#Update order has been re-raised for 01/07/2024 (AM slot) - awaiting TRC approval from Allwyn _x000D_5/9/2024:#Update order has been re-raised for 01/07/2024 (AM slot) - awaiting TRC approval from Allwyn _x000D_4/9/2024:#Update order has been re-raised for 01/07/2024 (AM slot) - awaiting TRC approval from Allwyn _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Now order got re-appointed for 01/07/2024 _x000D_13/6/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Now order got re-appointed for 01/07/2024 _x000D_12/6/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Now order got re-appointed for 01/07/2024 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update order has been re-raised for 01/07/2024 (AM slot) - awaiting TRC approval from Allwyn _x000D_6/9/2024:#Update order has been re-raised for 01/07/2024 (AM slot) - awaiting TRC approval from Allwyn _x000D_5/9/2024:#Update order has been re-raised for 01/07/2024 (AM slot) - awaiting TRC approval from Allwyn _x000D_4/9/2024:#Update order has been re-raised for 01/07/2024 (AM slot) - awaiting TRC approval from Allwyn _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Now order got re-appointed for 01/07/2024 _x000D_13/6/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Now order got re-appointed for 01/07/2024 _x000D_12/6/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Now order got re-appointed for 01/07/2024 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update order has been re-raised for 01/07/2024 (AM slot) - awaiting TRC approval from Allwyn |  |  |  |  | 3.Allwyn to arrange rtr install | VFP2301511 | 30014204 | 2.Commissioning | AM |  |  |  |  | Not Applicable |  |  |  | 2024-07-24 | [7 empty] | 0
883 | 461425 | 1420 | Batch 4 Jun24 | Type 1 | SOGEA | Premier Court Road Supermarket | ORPINGTON | BR6 9DA | 2024-07-02 | 19/7/2024:#Update - The install has been passed back to Openreach as the engineer was unable to run ca able through false ceiling due to fire regulations. Complex network solution is required. CSL will update as more information becomes available _x000D_18/7/2024:#Update - The install has been passed back to Openreach as the engineer was unable to run ca able through false ceiling due to fire regulations. Complex network solution is required. CSL will update as more information becomes available _x000D_17/7/2024:#Update - The install has been passed back to Openreach as the engineer was unable to run ca able through false ceiling due to fire regulations. Complex network solution is required. CSL will update as more information becomes available _x000D_16/7/2024:#Update - The install has been passed back to Openreach as the engineer was unable to run ca able through false ceiling due to fire regulations. Complex network solution is required. CSL will update as more information becomes available _x000D_15/7/2024:#Update - The install has been passed back to Openreach as the engineer was unable to run ca able through false ceiling due to fire regulations. Complex network solution is required. CSL will update as more information becomes available _x000D_12/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_11/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_10/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_9/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_4/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_3/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_27/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_25/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_24/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_20/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_19/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_18/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_17/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_14/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_13/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_12/6/2024:#Update - Missed Appointment - The installation requires internal cabling ran through ceiling tiles to the back of the shop where the distribution point is located. The retailer refused to close an isle to allow the work to be carried out. _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 19/7/2024:#Update - The install has been passed back to Openreach as the engineer was unable to run ca able through false ceiling due to fire regulations. Complex network solution is required. CSL will update as more information becomes available _x000D_18/7/2024:#Update - The install has been passed back to Openreach as the engineer was unable to run ca able through false ceiling due to fire regulations. Complex network solution is required. CSL will update as more information becomes available _x000D_17/7/2024:#Update - The install has been passed back to Openreach as the engineer was unable to run ca able through false ceiling due to fire regulations. Complex network solution is required. CSL will update as more information becomes available _x000D_16/7/2024:#Update - The install has been passed back to Openreach as the engineer was unable to run ca able through false ceiling due to fire regulations. Complex network solution is required. CSL will update as more information becomes available _x000D_15/7/2024:#Update - The install has been passed back to Openreach as the engineer was unable to run ca able through false ceiling due to fire regulations. Complex network solution is required. CSL will update as more information becomes available _x000D_12/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_11/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_10/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_9/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_4/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_3/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_27/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_25/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_24/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_20/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_19/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_18/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_17/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_14/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_13/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 01/07 AM _x000D_12/6/2024:#Update - Missed Appointment - The installation requires internal cabling ran through ceiling tiles to the back of the shop where the distribution point is located. The retailer refused to close an isle to allow the work to be carried out. _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 | 7/6/2024: CSL to provide an update |  |  | 5.CSL | VFS984690 | 30015377 | 6.Failed router install | AM |  | 2024-06-06 | 2024-07-01 | 2024-07-01 | TRUE |  |  |  | 2024-07-24 |  |  |  | 2024-07-24 | 242005011083 |  | 2024-08-01 | 1
884 | 672507 | 1819 | Batch 4 Jun24 | Type 1 | SoGEA/Mobile | Annan Convenience Store | Annan | DG12 6DW | 2024-08-28 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:#Update - An engineer is attending site on 26/08 to complete external works. _x000D_28/8/2024:#Update - An engineer is attending site on 26/08 to complete external works. _x000D_27/8/2024:#Update - An engineer is attending site on 26/08 to complete external works. _x000D_22/8/2024:#Update - The engineer attended site however the retailer does not want to close an isle to carry out the cabling work, the internal cable needs to run through ceiling tiles to back of the shop to get to external DP. _x000D_21/8/2024:#Update - The engineer attended site however the retailer does not want to close an isle to carry out the cabling work, the internal cable needs to run through ceiling tiles to back of the shop to get to external DP. _x000D_20/8/2024:#Update - The engineer attended site however the retailer does not want to close an isle to carry out the cabling work, the internal cable needs to run through ceiling tiles to back of the shop to get to external DP. _x000D_19/8/2024:#Update - The engineer attended site however the retailer does not want to close an isle to carry out the cabling work, the internal cable needs to run through ceiling tiles to back of the shop to get to external DP. _x000D_19/8/2024:01431847 _x000D_16/8/2024:#Update - The engineer attended site however the retailer does not want to close an isle to carry out the cabling work, the internal cable needs to run through ceiling tiles to back of the shop to get to external DP. _x000D_15/8/2024:#Update - The engineer attended site however the retailer does not want to close an isle to carry out the cabling work, the internal cable needs to run through ceiling tiles to back of the shop to get to external DP. _x000D_14/8/2024:#Update - The engineer attended site however the retailer does not want to close an isle to carry out the cabling work, the internal cable needs to run through ceiling tiles to back of the shop to get to external DP. _x000D_13/8/2024:#Update - The engineer attended site however the retailer does not want to close an isle to carry out the cabling work, the internal cable needs to run through ceiling tiles to back of the shop to get to external DP. _x000D_12/8/2024:#Update - The engineer attended site however the retailer does not want to close an isle to carry out the cabling work, the internal cable needs to run through ceiling tiles to back of the shop to get to external DP. _x000D_9/8/2024:#Update - The engineer attended site however the retailer does not want to close an isle to carry out the cabling work, the internal cable needs to run through ceiling tiles to back of the shop to get to external DP. _x000D_8/8/2024:02/08/2024 _x000D_6/8/2024:02/08/2024 _x000D_5/8/2024:02/08/2024 _x000D_2/8/2024:02/08/2024 _x000D_1/8/2024:23/07/2024 _x000D_31/7/2024:23/07/2024 _x000D_31/7/2024:23/07/2024 _x000D_30/7/2024:#Update - Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 31/07/2024 _x000D_29/7/2024:#Update - Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 31/07/2024 _x000D_29/7/2024:01431847 _x000D_26/7/2024:01431847 _x000D_24/7/2024:#Update - Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 31/07/2024 _x000D_23/7/2024:#Update - The install has been passed back to Openreach as the engineer was unable to run ca able through false ceiling due to fire regulations. Complex network solution is required. CSL will update as more information becomes available _x000D_22/7/2024:#Update - The install has been passed back to Openreach as the engineer was unable to run ca able through false ceiling due to fire regulations. Complex network solution is required. CSL will update as more information becomes available _x000D_22/7/2024:#Update - The install has been passed back to Openreach as the engineer was unable to run ca able through false ceiling due to fire regulations. Complex network solution is required. CSL will update as more information becomes available _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:Order Completed _x000D_15/7/2024:Order Completed _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Now order got re-appointed for 12/07/2024. _x000D_2/7/2024:A4 (ECC) _x000D_1/7/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Now order got re-appointed for 12/07/2024. _x000D_27/6/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Now order got re-appointed for 12/07/2024. _x000D_25/6/2024:End User Missed appointment. Action required _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 10-06-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/6/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 10-06-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/6/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 10-06-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_7/6/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 10-06-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:#Update - An engineer is attending site on 26/08 to complete external works. _x000D_28/8/2024:#Update - An engineer is attending site on 26/08 to complete external works. _x000D_27/8/2024:#Update - An engineer is attending site on 26/08 to complete external works. _x000D_22/8/2024:#Update - The engineer attended site however the retailer does not want to close an isle to carry out the cabling work, the internal cable needs to run through ceiling tiles to back of the shop to get to external DP. _x000D_21/8/2024:#Update - The engineer attended site however the retailer does not want to close an isle to carry out the cabling work, the internal cable needs to run through ceiling tiles to back of the shop to get to external DP. _x000D_20/8/2024:#Update - The engineer attended site however the retailer does not want to close an isle to carry out the cabling work, the internal cable needs to run through ceiling tiles to back of the shop to get to external DP. _x000D_19/8/2024:#Update - The engineer attended site however the retailer does not want to close an isle to carry out the cabling work, the internal cable needs to run through ceiling tiles to back of the shop to get to external DP. _x000D_19/8/2024:01431847 _x000D_16/8/2024:#Update - The engineer attended site however the retailer does not want to close an isle to carry out the cabling work, the internal cable needs to run through ceiling tiles to back of the shop to get to external DP. _x000D_15/8/2024:#Update - The engineer attended site however the retailer does not want to close an isle to carry out the cabling work, the internal cable needs to run through ceiling tiles to back of the shop to get to external DP. _x000D_14/8/2024:#Update - The engineer attended site however the retailer does not want to close an isle to carry out the cabling work, the internal cable needs to run through ceiling tiles to back of the shop to get to external DP. _x000D_13/8/2024:#Update - The engineer attended site however the retailer does not want to close an isle to carry out the cabling work, the internal cable needs to run through ceiling tiles to back of the shop to get to external DP. _x000D_12/8/2024:#Update - The engineer attended site however the retailer does not want to close an isle to carry out the cabling work, the internal cable needs to run through ceiling tiles to back of the shop to get to external DP. _x000D_9/8/2024:#Update - The engineer attended site however the retailer does not want to close an isle to carry out the cabling work, the internal cable needs to run through ceiling tiles to back of the shop to get to external DP. _x000D_8/8/2024:02/08/2024 _x000D_6/8/2024:02/08/2024 _x000D_5/8/2024:02/08/2024 _x000D_2/8/2024:02/08/2024 _x000D_1/8/2024:23/07/2024 _x000D_31/7/2024:23/07/2024 _x000D_31/7/2024:23/07/2024 _x000D_30/7/2024:#Update - Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 31/07/2024 _x000D_29/7/2024:#Update - Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 31/07/2024 _x000D_29/7/2024:01431847 _x000D_26/7/2024:01431847 _x000D_24/7/2024:#Update - Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 31/07/2024 _x000D_23/7/2024:#Update - The install has been passed back to Openreach as the engineer was unable to run ca able through false ceiling due to fire regulations. Complex network solution is required. CSL will update as more information becomes available _x000D_22/7/2024:#Update - The install has been passed back to Openreach as the engineer was unable to run ca able through false ceiling due to fire regulations. Complex network solution is required. CSL will update as more information becomes available _x000D_22/7/2024:#Update - The install has been passed back to Openreach as the engineer was unable to run ca able through false ceiling due to fire regulations. Complex network solution is required. CSL will update as more information becomes available _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:Order Completed _x000D_15/7/2024:Order Completed _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Now order got re-appointed for 12/07/2024. _x000D_2/7/2024:A4 (ECC) _x000D_1/7/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Now order got re-appointed for 12/07/2024. _x000D_27/6/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Now order got re-appointed for 12/07/2024. _x000D_25/6/2024:End User Missed appointment. Action required _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 10-06-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/6/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 10-06-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/6/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 10-06-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_7/6/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 10-06-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | 0 | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFS983344 | 30015223 | 2.Commissioning | AM |  | 2024-06-11 | 2024-07-01 |  | 0 | [11 empty] | 0 | 672507
885 | 427568 | 3418 | Batch 5 Jul24 | Type 1 | SOGEA | Mckenzies General Store | LONDON | N7 8RE | 2024-07-02 | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1012853 | 30016495 | 6.Failed router install |  |  | 2024-07-01 | 2024-07-01 | 2024-07-01 | TRUE |  |  |  | 2024-07-29 |  |  |  | 2024-07-29 | 242005011167 |  | 2024-07-30 | 1
886 | 466432 | 3439 | Batch 5 Jul24 | Type 1 | SOGEA | Esso Manby Road Express | IMMINGHAM | DN40 2LG | 2024-07-02 | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1015516 | 30016915 | 6.Failed router install |  |  | 2024-07-01 | 2024-07-01 | 2024-07-01 | TRUE |  |  |  | 2024-07-27 |  |  |  | 2024-07-23 | 23A004948653 |  | 2024-07-23 | 1
887 | 666328 | 3440 | Batch 5 Jul24 | Type 1 | FTTP | Ravenscliffe Post Office | Bradford | BD10 0JJ | 2024-07-02 | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFP2363556 | 30016296 | 2.Commissioning |  |  | 2024-07-01 | 2024-07-01 | 2024-07-01 | TRUE |  |  |  | 2024-07-26 | [7 empty] | 0
888 | 665043 | 3444 | Batch 5 Jul24 | Type 1 | FTTP | Mulkerns Eurospar | Newry | BT35 8QY | 2024-07-02 | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFP2363553 | 30016259 | 2.Commissioning |  |  | 2024-07-01 | 2024-07-01 | 2024-07-01 | TRUE |  |  |  | 2024-07-24 | [7 empty] | 0
889 | 657817 | 3445 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Premier | Coventry | CV6 2FG |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:46 _x000D_26/7/2024:22/07/2024 10:46 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Awaiting approval for OOH. Pushed out for 19/08 - AM _x000D_18/7/2024:#Update - Awaiting approval for OOH. Pushed out for 19/08 - AM _x000D_17/7/2024:#Update - Awaiting approval for OOH. Pushed out for 19/08 - AM _x000D_16/7/2024:#Update - Reappointed for 12/08- AM to account for ECC approval. _x000D_15/7/2024:#Update - Reappointed for 12/08- AM to account for ECC approval. _x000D_12/7/2024:#Update - Awaiting OOH approval, _x000D_11/7/2024:#Update - Awaiting OOH approval, _x000D_10/7/2024:#Update - Awaiting OOH approval, _x000D_9/7/2024:#Update - Awaiting OOH approval, _x000D_4/7/2024:#Update - Awaiting OOH approval, _x000D_3/7/2024:#Update - Awaiting OOH approval, _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:46 _x000D_26/7/2024:22/07/2024 10:46 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Awaiting approval for OOH. Pushed out for 19/08 - AM _x000D_18/7/2024:#Update - Awaiting approval for OOH. Pushed out for 19/08 - AM _x000D_17/7/2024:#Update - Awaiting approval for OOH. Pushed out for 19/08 - AM _x000D_16/7/2024:#Update - Reappointed for 12/08- AM to account for ECC approval. _x000D_15/7/2024:#Update - Reappointed for 12/08- AM to account for ECC approval. _x000D_12/7/2024:#Update - Awaiting OOH approval, _x000D_11/7/2024:#Update - Awaiting OOH approval, _x000D_10/7/2024:#Update - Awaiting OOH approval, _x000D_9/7/2024:#Update - Awaiting OOH approval, _x000D_4/7/2024:#Update - Awaiting OOH approval, _x000D_3/7/2024:#Update - Awaiting OOH approval, _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2363551 | 30016231 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
890 | 471477 | 3446 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | COSTCUTTER | MALTON | YO17 9HX | 2024-07-02 | 6/9/2024:#Update = Pushed out for 09.09 to allow time for appointment engineer allocation. _x000D_5/9/2024:#Update = Pushed out for 09.09 to allow time for appointment engineer allocation. _x000D_4/9/2024:#Update = Pushed out for 09.09 to allow time for appointment engineer allocation. _x000D_3/9/2024:#Update = Pushed out for 09.09 to allow time for appointment engineer allocation. _x000D_2/9/2024:#Update = Pushed out for 09.09 to allow time for appointment engineer allocation. _x000D_29/8/2024:#Update = Pushed out for 09.09 to allow time for appointment engineer allocation. _x000D_28/8/2024:#Update = Pushed out for 09.09 to allow time for appointment engineer allocation. _x000D_27/8/2024:#Update = Pushed out for 09.09 to allow time for appointment engineer allocation. _x000D_22/8/2024:#Update = Pushed out for 09.09 to allow time for appointment engineer allocation. _x000D_21/8/2024:#Update = Pushed out for 09.09 to allow time for appointment engineer allocation. _x000D_20/8/2024:#Update = Pushed out for 09.09 to allow time for appointment engineer allocation. _x000D_19/8/2024:#Update = Pushed out for 09.09 to allow time for appointment engineer allocation. _x000D_19/8/2024:01461266 _x000D_16/8/2024:#Update - Charges approved. Awaiting confimation for sundaydate with OR _x000D_15/8/2024:#Update - Upgrade ECCS need ot be approved. Adjusted to suit the sunday request from the retailer. _x000D_14/8/2024:#Update - Upgrade ECCS need ot be approved. Adjusted to suit the sunday request from the retailer. _x000D_13/8/2024:#Update - Upgrade ECCS need ot be approved. Adjusted to suit the sunday request from the retailer. _x000D_12/8/2024:#Update - Upgrade ECCS need ot be approved. Adjusted to suit the sunday request from the retailer. _x000D_9/8/2024:#Update - Upgrade ECCS need ot be approved. Adjusted to suit the sunday request from the retailer. _x000D_8/8/2024:23/07/2024 _x000D_6/8/2024:23/07/2024 _x000D_5/8/2024:23/07/2024 _x000D_2/8/2024:23/07/2024 _x000D_1/8/2024:23/07/2024 _x000D_31/7/2024:23/07/2024 _x000D_31/7/2024:23/07/2024 _x000D_30/7/2024:#Update - Upgrade ECCS need ot be approved. Adjusted to suit the sunday request from the retailer. _x000D_29/7/2024:#Update - Upgrade ECCS need ot be approved. Adjusted to suit the sunday request from the retailer. _x000D_29/7/2024:01461266 _x000D_26/7/2024:01461266 _x000D_24/7/2024:#Update - Upgrade ECCS need ot be approved. Adjusted to suit the sunday request from the retailer. _x000D_23/7/2024:#Update - Awaiting approval for OOH. Pushed out for 19/08 - AM _x000D_22/7/2024:#Update - Awaiting approval for OOH. Pushed out for 19/08 - AM _x000D_22/7/2024:#Update - Awaiting approval for OOH. Pushed out for 19/08 - AM _x000D_19/7/2024:#Update - Awaiting approval on ECC's _x000D_18/7/2024:#Update - Awaiting approval on ECC's _x000D_17/7/2024:#Update - Awaiting approval on ECC's _x000D_16/7/2024:#Update - Awaiting approval on ECC's _x000D_15/7/2024:#Update - Awaiting approval on ECC's _x000D_12/7/2024:#Update - Awaiting approval on ECC's _x000D_11/7/2024:#Update - Awaiting approval on ECC's _x000D_10/7/2024:#Update - Awaiting approval on ECC's _x000D_9/7/2024:#Update - Awaiting approval on ECC's _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:EU Missed Appointment. Supplier engineer has been unable to gain access. _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update = Pushed out for 09.09 to allow time for appointment engineer allocation. _x000D_6/9/2024:#Update = Pushed out for 09.09 to allow time for appointment engineer allocation. _x000D_5/9/2024:#Update = Pushed out for 09.09 to allow time for appointment engineer allocation. _x000D_4/9/2024:#Update = Pushed out for 09.09 to allow time for appointment engineer allocation. _x000D_3/9/2024:#Update = Pushed out for 09.09 to allow time for appointment engineer allocation. _x000D_2/9/2024:#Update = Pushed out for 09.09 to allow time for appointment engineer allocation. _x000D_29/8/2024:#Update = Pushed out for 09.09 to allow time for appointment engineer allocation. _x000D_28/8/2024:#Update = Pushed out for 09.09 to allow time for appointment engineer allocation. _x000D_27/8/2024:#Update = Pushed out for 09.09 to allow time for appointment engineer allocation. _x000D_22/8/2024:#Update = Pushed out for 09.09 to allow time for appointment engineer allocation. _x000D_21/8/2024:#Update = Pushed out for 09.09 to allow time for appointment engineer allocation. _x000D_20/8/2024:#Update = Pushed out for 09.09 to allow time for appointment engineer allocation. _x000D_19/8/2024:#Update = Pushed out for 09.09 to allow time for appointment engineer allocation. _x000D_19/8/2024:01461266 _x000D_16/8/2024:#Update - Charges approved. Awaiting confimation for sundaydate with OR _x000D_15/8/2024:#Update - Upgrade ECCS need ot be approved. Adjusted to suit the sunday request from the retailer. _x000D_14/8/2024:#Update - Upgrade ECCS need ot be approved. Adjusted to suit the sunday request from the retailer. _x000D_13/8/2024:#Update - Upgrade ECCS need ot be approved. Adjusted to suit the sunday request from the retailer. _x000D_12/8/2024:#Update - Upgrade ECCS need ot be approved. Adjusted to suit the sunday request from the retailer. _x000D_9/8/2024:#Update - Upgrade ECCS need ot be approved. Adjusted to suit the sunday request from the retailer. _x000D_8/8/2024:23/07/2024 _x000D_6/8/2024:23/07/2024 _x000D_5/8/2024:23/07/2024 _x000D_2/8/2024:23/07/2024 _x000D_1/8/2024:23/07/2024 _x000D_31/7/2024:23/07/2024 _x000D_31/7/2024:23/07/2024 _x000D_30/7/2024:#Update - Upgrade ECCS need ot be approved. Adjusted to suit the sunday request from the retailer. _x000D_29/7/2024:#Update - Upgrade ECCS need ot be approved. Adjusted to suit the sunday request from the retailer. _x000D_29/7/2024:01461266 _x000D_26/7/2024:01461266 _x000D_24/7/2024:#Update - Upgrade ECCS need ot be approved. Adjusted to suit the sunday request from the retailer. _x000D_23/7/2024:#Update - Awaiting approval for OOH. Pushed out for 19/08 - AM _x000D_22/7/2024:#Update - Awaiting approval for OOH. Pushed out for 19/08 - AM _x000D_22/7/2024:#Update - Awaiting approval for OOH. Pushed out for 19/08 - AM _x000D_19/7/2024:#Update - Awaiting approval on ECC's _x000D_18/7/2024:#Update - Awaiting approval on ECC's _x000D_17/7/2024:#Update - Awaiting approval on ECC's _x000D_16/7/2024:#Update - Awaiting approval on ECC's _x000D_15/7/2024:#Update - Awaiting approval on ECC's _x000D_12/7/2024:#Update - Awaiting approval on ECC's _x000D_11/7/2024:#Update - Awaiting approval on ECC's _x000D_10/7/2024:#Update - Awaiting approval on ECC's _x000D_9/7/2024:#Update - Awaiting approval on ECC's _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:EU Missed Appointment. Supplier engineer has been unable to gain access. _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | #Update = Pushed out for 09.09 to allow time for appointment engineer allocation. | 2024-06-07 |  |  |  |  | VFP2363552 | 30016387 | 1.Provisioning | AM |  | 2024-07-01 | 2024-08-19 |  | 0 | [11 empty] | 0
891 | 633320 | 3448 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Gostwick Road Convenience Store | Bedford | MK42 9XD | 2024-07-02 | 6/9/2024:#Update - Awaiting approval on ECC's _x000D_5/9/2024:#Update - Awaiting approval on ECC's _x000D_4/9/2024:#Update - Awaiting approval on ECC's _x000D_3/9/2024:#Update - Awaiting approval on ECC's _x000D_2/9/2024:#Update - Awaiting approval on ECC's _x000D_29/8/2024:#Update - Awaiting approval on ECC's _x000D_28/8/2024:#Update - Awaiting approval on ECC's _x000D_27/8/2024:#Update - Awaiting approval on ECC's _x000D_22/8/2024:#Update - Awaiting approval on ECC's _x000D_21/8/2024:#Update - Awaiting approval on ECC's _x000D_20/8/2024:#Update - Awaiting approval on ECC's _x000D_19/8/2024:#Update - Awaiting approval on ECC's _x000D_19/8/2024:01460942 _x000D_16/8/2024:#Update - Awaiting approval on ECC's _x000D_15/8/2024:#Update - Awaiting approval on ECC's _x000D_14/8/2024:#Update - Awaiting approval on ECC's _x000D_13/8/2024:#Update - Awaiting approval on ECC's _x000D_12/8/2024:#Update - Awaiting approval on ECC's _x000D_9/8/2024:#Update - Awaiting approval on ECC's _x000D_8/8/2024:09/07/2024 _x000D_6/8/2024:09/07/2024 _x000D_5/8/2024:09/07/2024 _x000D_2/8/2024:09/07/2024 _x000D_1/8/2024:09/07/2024 _x000D_31/7/2024:09/07/2024 _x000D_31/7/2024:09/07/2024 _x000D_30/7/2024:#Update - Awaiting approval on ECC's _x000D_29/7/2024:#Update - Awaiting approval on ECC's _x000D_29/7/2024:01460942 _x000D_26/7/2024:01460942 _x000D_24/7/2024:#Update - Awaiting approval on ECC's _x000D_23/7/2024:#Update - Awaiting approval on ECC's _x000D_22/7/2024:#Update - Awaiting approval on ECC's _x000D_22/7/2024:#Update - Awaiting approval on ECC's _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - Awaiting approval on ECC's _x000D_6/9/2024:#Update - Awaiting approval on ECC's _x000D_5/9/2024:#Update - Awaiting approval on ECC's _x000D_4/9/2024:#Update - Awaiting approval on ECC's _x000D_3/9/2024:#Update - Awaiting approval on ECC's _x000D_2/9/2024:#Update - Awaiting approval on ECC's _x000D_29/8/2024:#Update - Awaiting approval on ECC's _x000D_28/8/2024:#Update - Awaiting approval on ECC's _x000D_27/8/2024:#Update - Awaiting approval on ECC's _x000D_22/8/2024:#Update - Awaiting approval on ECC's _x000D_21/8/2024:#Update - Awaiting approval on ECC's _x000D_20/8/2024:#Update - Awaiting approval on ECC's _x000D_19/8/2024:#Update - Awaiting approval on ECC's _x000D_19/8/2024:01460942 _x000D_16/8/2024:#Update - Awaiting approval on ECC's _x000D_15/8/2024:#Update - Awaiting approval on ECC's _x000D_14/8/2024:#Update - Awaiting approval on ECC's _x000D_13/8/2024:#Update - Awaiting approval on ECC's _x000D_12/8/2024:#Update - Awaiting approval on ECC's _x000D_9/8/2024:#Update - Awaiting approval on ECC's _x000D_8/8/2024:09/07/2024 _x000D_6/8/2024:09/07/2024 _x000D_5/8/2024:09/07/2024 _x000D_2/8/2024:09/07/2024 _x000D_1/8/2024:09/07/2024 _x000D_31/7/2024:09/07/2024 _x000D_31/7/2024:09/07/2024 _x000D_30/7/2024:#Update - Awaiting approval on ECC's _x000D_29/7/2024:#Update - Awaiting approval on ECC's _x000D_29/7/2024:01460942 _x000D_26/7/2024:01460942 _x000D_24/7/2024:#Update - Awaiting approval on ECC's _x000D_23/7/2024:#Update - Awaiting approval on ECC's _x000D_22/7/2024:#Update - Awaiting approval on ECC's _x000D_22/7/2024:#Update - Awaiting approval on ECC's _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | #Update - Awaiting approval on ECC's | 2024-06-07 |  |  |  |  | VFP2363550 | 30016370 | 1.Provisioning | AM |  | 2024-07-01 | 2024-09-12 |  | 0 | [11 empty] | 0
892 | 110865 | 3449 | Batch 5 Jul24 | Type 1 | SOGEA | D & M Fraser Nisa Local | THURSO | KW14 7NB | 2024-07-02 | 19/7/2024:#Update - site requires OOH appointment. ECC raised and with Allwyn to approve _x000D_18/7/2024:#Update - Supplier Delay: Network Planning issues. Please await for further updates _x000D_17/7/2024:#Update - Supplier Delay: Network Planning issues. Please await for further updates _x000D_16/7/2024:#Update - Supplier Delay: Network Planning issues. Please await for further updates _x000D_15/7/2024:#Update - Supplier Delay: Network Planning issues. Please await for further updates _x000D_12/7/2024:#Update - Supplier Delay: Network Planning issues. Please await for further updates _x000D_11/7/2024:#Update - Supplier Delay: Network Planning issues. Please await for further updates _x000D_10/7/2024:#Update - Supplier Delay: Network Planning issues. Please await for further updates _x000D_9/7/2024:#Update - Supplier Delay: Network Planning issues. Please await for further updates _x000D_4/7/2024:#Update - Supplier Delay: Network Planning issues. Please await for further updates _x000D_3/7/2024:#Update - Supplier Delay: Network Planning issues. Please await for further updates _x000D_2/7/2024:0 _x000D_1/7/2024:End User Missed appointment. Action required _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_19/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_18/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_17/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_14/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_13/6/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/6/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/6/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_7/6/2024:0 _x000D_ | 19/7/2024:#Update - site requires OOH appointment. ECC raised and with Allwyn to approve _x000D_18/7/2024:#Update - Supplier Delay: Network Planning issues. Please await for further updates _x000D_17/7/2024:#Update - Supplier Delay: Network Planning issues. Please await for further updates _x000D_16/7/2024:#Update - Supplier Delay: Network Planning issues. Please await for further updates _x000D_15/7/2024:#Update - Supplier Delay: Network Planning issues. Please await for further updates _x000D_12/7/2024:#Update - Supplier Delay: Network Planning issues. Please await for further updates _x000D_11/7/2024:#Update - Supplier Delay: Network Planning issues. Please await for further updates _x000D_10/7/2024:#Update - Supplier Delay: Network Planning issues. Please await for further updates _x000D_9/7/2024:#Update - Supplier Delay: Network Planning issues. Please await for further updates _x000D_4/7/2024:#Update - Supplier Delay: Network Planning issues. Please await for further updates _x000D_3/7/2024:#Update - Supplier Delay: Network Planning issues. Please await for further updates _x000D_2/7/2024:0 _x000D_1/7/2024:End User Missed appointment. Action required _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_19/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_18/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_17/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_14/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_13/6/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/6/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/6/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1013107 | 30016498 | 2.Commissioning |  |  | 2024-07-01 | 2024-07-01 | 2024-07-01 | TRUE | [11 empty] | 0
893 | 668207 | 3450 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Glyncoch PO | PONTYPRIDD | CF37 3DD | 2024-07-02 | 6/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 14/07 _x000D_5/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 14/07 _x000D_4/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 14/07 _x000D_3/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 14/07 _x000D_2/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 14/07 _x000D_29/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 14/07 _x000D_28/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 14/07 _x000D_27/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 14/07 _x000D_22/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 14/07 _x000D_21/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 14/07 _x000D_20/8/2024:#Update - site requires OOH appointment. ECC raised and with Allwyn to approve _x000D_19/8/2024:#Update - site requires OOH appointment. ECC raised and with Allwyn to approve _x000D_19/8/2024:01409570 _x000D_16/8/2024:#Update - site requires OOH appointment. ECC raised and with Allwyn to approve _x000D_15/8/2024:#Update - site requires OOH appointment. ECC raised and with Allwyn to approve _x000D_14/8/2024:#Update - site requires OOH appointment. ECC raised and with Allwyn to approve _x000D_13/8/2024:#Update - site requires OOH appointment. ECC raised and with Allwyn to approve _x000D_12/8/2024:#Update - site requires OOH appointment. ECC raised and with Allwyn to approve _x000D_9/8/2024:#Update - site requires OOH appointment. ECC raised and with Allwyn to approve _x000D_8/8/2024:19/07/2024 _x000D_6/8/2024:19/07/2024 _x000D_5/8/2024:19/07/2024 _x000D_2/8/2024:19/07/2024 _x000D_1/8/2024:19/07/2024 _x000D_31/7/2024:19/07/2024 _x000D_31/7/2024:19/07/2024 _x000D_30/7/2024:#Update - site requires OOH appointment. ECC raised and with Allwyn to approve _x000D_29/7/2024:#Update - site requires OOH appointment. ECC raised and with Allwyn to approve _x000D_29/7/2024:01409570 _x000D_26/7/2024:01409570 _x000D_24/7/2024:#Update - site requires OOH appointment. ECC raised and with Allwyn to approve _x000D_23/7/2024:#Update - site requires OOH appointment. ECC raised and with Allwyn to approve _x000D_22/7/2024:#Update - site requires OOH appointment. ECC raised and with Allwyn to approve _x000D_22/7/2024:#Update - site requires OOH appointment. ECC raised and with Allwyn to approve _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 14/07 _x000D_6/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 14/07 _x000D_5/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 14/07 _x000D_4/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 14/07 _x000D_3/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 14/07 _x000D_2/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 14/07 _x000D_29/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 14/07 _x000D_28/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 14/07 _x000D_27/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 14/07 _x000D_22/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 14/07 _x000D_21/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 14/07 _x000D_20/8/2024:#Update - site requires OOH appointment. ECC raised and with Allwyn to approve _x000D_19/8/2024:#Update - site requires OOH appointment. ECC raised and with Allwyn to approve _x000D_19/8/2024:01409570 _x000D_16/8/2024:#Update - site requires OOH appointment. ECC raised and with Allwyn to approve _x000D_15/8/2024:#Update - site requires OOH appointment. ECC raised and with Allwyn to approve _x000D_14/8/2024:#Update - site requires OOH appointment. ECC raised and with Allwyn to approve _x000D_13/8/2024:#Update - site requires OOH appointment. ECC raised and with Allwyn to approve _x000D_12/8/2024:#Update - site requires OOH appointment. ECC raised and with Allwyn to approve _x000D_9/8/2024:#Update - site requires OOH appointment. ECC raised and with Allwyn to approve _x000D_8/8/2024:19/07/2024 _x000D_6/8/2024:19/07/2024 _x000D_5/8/2024:19/07/2024 _x000D_2/8/2024:19/07/2024 _x000D_1/8/2024:19/07/2024 _x000D_31/7/2024:19/07/2024 _x000D_31/7/2024:19/07/2024 _x000D_30/7/2024:#Update - site requires OOH appointment. ECC raised and with Allwyn to approve _x000D_29/7/2024:#Update - site requires OOH appointment. ECC raised and with Allwyn to approve _x000D_29/7/2024:01409570 _x000D_26/7/2024:01409570 _x000D_24/7/2024:#Update - site requires OOH appointment. ECC raised and with Allwyn to approve _x000D_23/7/2024:#Update - site requires OOH appointment. ECC raised and with Allwyn to approve _x000D_22/7/2024:#Update - site requires OOH appointment. ECC raised and with Allwyn to approve _x000D_22/7/2024:#Update - site requires OOH appointment. ECC raised and with Allwyn to approve _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update - awaiting ECC approval from customer - proposal sent to VF 14/07 | 2024-06-07 |  |  |  |  | VFS1013103 | 30016400 | 1.Provisioning | AM |  | 2024-07-01 | 2024-08-30 |  | 0 | [11 empty] | 0
894 | 481108 | 3451 | Batch 5 Jul24 | Type 1 | SOGEA | New Cross Kiosk | London | SE14 6LD | 2024-07-02 | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1013104 | 30016459 | 6.Failed router install |  |  | 2024-07-01 | 2024-07-01 | 2024-07-01 | TRUE |  |  |  | 2024-07-25 |  |  |  | 2024-07-25 | 242005008624 |  | 2024-07-26 | 1
895 | 649705 | 3453 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Shell | Northants | NN18 8AR | 2024-07-02 | 6/9/2024:#Update - Openreach - 04/09 - Contract engineer unable to complete the task due to SD engineer visit required. The task raised for Openreach engineer with required skills to complete the work and are trying our best to complete this work as early as possible. Our Next review will follow on 11/09/2024 However we will notify you again if any new information is received before the next review date. _x000D_5/9/2024:#Update - Pushed out to 02/09 - Still seeking local knowledge to locate JRC - Chased OR 31/07 _x000D_4/9/2024:#Update - Pushed out to 02/09 - Still seeking local knowledge to locate JRC - Chased OR 31/07 _x000D_3/9/2024:#Update - Pushed out to 02/09 - Still seeking local knowledge to locate JRC - Chased OR 31/07 _x000D_2/9/2024:#Update - Pushed out to 02/09 - Still seeking local knowledge to locate JRC - Chased OR 31/07 _x000D_29/8/2024:#Update - Pushed out to 02/09 - Still seeking local knowledge to locate JRC - Chased OR 31/07 _x000D_28/8/2024:#Update - Pushed out to 02/09 - Still seeking local knowledge to locate JRC - Chased OR 31/07 _x000D_27/8/2024:#Update - Pushed out to 02/09 - Still seeking local knowledge to locate JRC - Chased OR 31/07 _x000D_22/8/2024:#Update - Pushed out to 02/09 - Still seeking local knowledge to locate JRC - Chased OR 31/07 _x000D_21/8/2024:#Update - Pushed out to 02/09 - Still seeking local knowledge to locate JRC - Chased OR 31/07 _x000D_20/8/2024:#Update - Pushed out to 02/09 - Still seeking local knowledge to locate JRC - Chased OR 31/07 _x000D_19/8/2024:#Update - Pushed out to 02/09 - Still seeking local knowledge to locate JRC - Chased OR 31/07 _x000D_19/8/2024:01463383 _x000D_16/8/2024:#Update - Pushed out to 02/09 - Still seeking local knowledge to locate JRC - Chased OR 31/07 _x000D_15/8/2024:#Update - Pushed out to 02/09 - Still seeking local knowledge to locate JRC - Chased OR 31/07 _x000D_14/8/2024:#Update - Pushed out to 02/09 - Still seeking local knowledge to locate JRC - Chased OR 31/07 _x000D_13/8/2024:#Update - Pushed out to 02/09 - Still seeking local knowledge to locate JRC - Chased OR 31/07 _x000D_12/8/2024:#Update - Pushed out to 02/09 - Still seeking local knowledge to locate JRC - Chased OR 31/07 _x000D_9/8/2024:#Update - Pushed out to 02/09 - Still seeking local knowledge to locate JRC - Chased OR 31/07 _x000D_8/8/2024:31/07/2024 _x000D_6/8/2024:31/07/2024 _x000D_5/8/2024:31/07/2024 _x000D_2/8/2024:31/07/2024 _x000D_1/8/2024:31/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_30/7/2024:#Update - Chasing OR about this one _x000D_29/7/2024:#Update - Chasing OR about this one _x000D_29/7/2024:01463383 _x000D_26/7/2024:01463383 _x000D_24/7/2024:#Update, Supplier delay. Unable to locate JRC /CBT - Review date of 04/07 _x000D_23/7/2024:#Update, Supplier delay. Unable to locate JRC /CBT - Review date of 04/07 _x000D_22/7/2024:#Update, Supplier delay. Unable to locate JRC /CBT - Review date of 04/07 _x000D_22/7/2024:#Update, Supplier delay. Unable to locate JRC /CBT - Review date of 04/07 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - Openreach - 04/09 - Contract engineer unable to complete the task due to SD engineer visit required. The task raised for Openreach engineer with required skills to complete the work and are trying our best to complete this work as early as possible. Our Next review will follow on 11/09/2024 However we will notify you again if any new information is received before the next review date. _x000D_6/9/2024:#Update - Openreach - 04/09 - Contract engineer unable to complete the task due to SD engineer visit required. The task raised for Openreach engineer with required skills to complete the work and are trying our best to complete this work as early as possible. Our Next review will follow on 11/09/2024 However we will notify you again if any new information is received before the next review date. _x000D_5/9/2024:#Update - Pushed out to 02/09 - Still seeking local knowledge to locate JRC - Chased OR 31/07 _x000D_4/9/2024:#Update - Pushed out to 02/09 - Still seeking local knowledge to locate JRC - Chased OR 31/07 _x000D_3/9/2024:#Update - Pushed out to 02/09 - Still seeking local knowledge to locate JRC - Chased OR 31/07 _x000D_2/9/2024:#Update - Pushed out to 02/09 - Still seeking local knowledge to locate JRC - Chased OR 31/07 _x000D_29/8/2024:#Update - Pushed out to 02/09 - Still seeking local knowledge to locate JRC - Chased OR 31/07 _x000D_28/8/2024:#Update - Pushed out to 02/09 - Still seeking local knowledge to locate JRC - Chased OR 31/07 _x000D_27/8/2024:#Update - Pushed out to 02/09 - Still seeking local knowledge to locate JRC - Chased OR 31/07 _x000D_22/8/2024:#Update - Pushed out to 02/09 - Still seeking local knowledge to locate JRC - Chased OR 31/07 _x000D_21/8/2024:#Update - Pushed out to 02/09 - Still seeking local knowledge to locate JRC - Chased OR 31/07 _x000D_20/8/2024:#Update - Pushed out to 02/09 - Still seeking local knowledge to locate JRC - Chased OR 31/07 _x000D_19/8/2024:#Update - Pushed out to 02/09 - Still seeking local knowledge to locate JRC - Chased OR 31/07 _x000D_19/8/2024:01463383 _x000D_16/8/2024:#Update - Pushed out to 02/09 - Still seeking local knowledge to locate JRC - Chased OR 31/07 _x000D_15/8/2024:#Update - Pushed out to 02/09 - Still seeking local knowledge to locate JRC - Chased OR 31/07 _x000D_14/8/2024:#Update - Pushed out to 02/09 - Still seeking local knowledge to locate JRC - Chased OR 31/07 _x000D_13/8/2024:#Update - Pushed out to 02/09 - Still seeking local knowledge to locate JRC - Chased OR 31/07 _x000D_12/8/2024:#Update - Pushed out to 02/09 - Still seeking local knowledge to locate JRC - Chased OR 31/07 _x000D_9/8/2024:#Update - Pushed out to 02/09 - Still seeking local knowledge to locate JRC - Chased OR 31/07 _x000D_8/8/2024:31/07/2024 _x000D_6/8/2024:31/07/2024 _x000D_5/8/2024:31/07/2024 _x000D_2/8/2024:31/07/2024 _x000D_1/8/2024:31/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_30/7/2024:#Update - Chasing OR about this one _x000D_29/7/2024:#Update - Chasing OR about this one _x000D_29/7/2024:01463383 _x000D_26/7/2024:01463383 _x000D_24/7/2024:#Update, Supplier delay. Unable to locate JRC /CBT - Review date of 04/07 _x000D_23/7/2024:#Update, Supplier delay. Unable to locate JRC /CBT - Review date of 04/07 _x000D_22/7/2024:#Update, Supplier delay. Unable to locate JRC /CBT - Review date of 04/07 _x000D_22/7/2024:#Update, Supplier delay. Unable to locate JRC /CBT - Review date of 04/07 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Your order has been delayed. Multiskilled engineer work is required. Our Suppliers have given us a review date of 12/09/2024. We will continue to provide update as they become available. | #Update - Openreach - 04/09 - Contract engineer unable to complete the task due to SD engineer visit required. The task raised for Openreach engineer with required skills to complete the work and are trying our best to complete this work as early as possible. Our Next review will follow on 11/09/2024 However we will notify you again if any new information is received before the next review date. | 2024-06-07 |  |  |  |  | VFP2363549 | 30016209 | 1.Provisioning | AM |  | 2024-07-01 | 2024-09-02 |  | 0 | [11 empty] | 0
896 | 650082 | 3454 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Station Newsagents | Rhyl, Denbighshire | LL18 1AT |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:52 _x000D_26/7/2024:22/07/2024 10:52 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:52 _x000D_26/7/2024:22/07/2024 10:52 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2363546 | 30016280 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
897 | 475899 | 3455 | Batch 5 Jul24 | Type 1 | FTTP | Day Today | Leven | KY8 2HA | 2024-07-02 | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFP2363545 | 30016299 | 6.Failed router install |  |  | 2024-07-01 | 2024-07-01 | 2024-07-01 | TRUE |  |  |  | 2024-07-25 |  |  |  | 2024-07-25 | 23A004948497 |  | 2024-07-26 | 1
898 | 457857 | 3456 | Batch 5 Jul24 | Type 1 | SOGEA | Your Local Costcutter | LONDON | E6 3PD | 2024-07-02 | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1012382 | 30016613 | 6.Failed router install |  |  | 2024-07-01 | 2024-07-01 | 2024-07-01 | TRUE |  |  |  | 2024-07-24 |  |  |  | 2024-07-24 | 242005011081 |  | 2024-07-25 | 1
899 | 445677 | 3457 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | LONDIS | MITCHAM | CR4 1RB |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:34 _x000D_26/7/2024:22/07/2024 10:34 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:34 _x000D_26/7/2024:22/07/2024 10:34 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2363547 | 30016367 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
900 | 664946 | 3459 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Budget | WISBECH | PE14 8RG | 2024-07-18 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:#Update - Order has been delayed as Track and locate work is required. CSL will update as more information becomes available. _x000D_9/8/2024:#Update - Order has been delayed as Track and locate work is required. CSL will update as more information becomes available. _x000D_8/8/2024:29/07/2024 _x000D_6/8/2024:29/07/2024 _x000D_5/8/2024:29/07/2024 _x000D_2/8/2024:29/07/2024 _x000D_1/8/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_30/7/2024:#Update - Order has been delayed as Track and locate work is required. CSL will update as more information becomes available. _x000D_29/7/2024:#Update Retailer happy with new appointment 17/07, AM. _x000D_29/7/2024:01460932 _x000D_26/7/2024:01460932 _x000D_24/7/2024:#Update Retailer happy with new appointment 17/07, AM. _x000D_23/7/2024:#Update Retailer happy with new appointment 17/07, AM. _x000D_22/7/2024:#Update Retailer happy with new appointment 17/07, AM. _x000D_22/7/2024:#Update Retailer happy with new appointment 17/07, AM. _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:#Update - Order has been delayed as Track and locate work is required. CSL will update as more information becomes available. _x000D_9/8/2024:#Update - Order has been delayed as Track and locate work is required. CSL will update as more information becomes available. _x000D_8/8/2024:29/07/2024 _x000D_6/8/2024:29/07/2024 _x000D_5/8/2024:29/07/2024 _x000D_2/8/2024:29/07/2024 _x000D_1/8/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_30/7/2024:#Update - Order has been delayed as Track and locate work is required. CSL will update as more information becomes available. _x000D_29/7/2024:#Update Retailer happy with new appointment 17/07, AM. _x000D_29/7/2024:01460932 _x000D_26/7/2024:01460932 _x000D_24/7/2024:#Update Retailer happy with new appointment 17/07, AM. _x000D_23/7/2024:#Update Retailer happy with new appointment 17/07, AM. _x000D_22/7/2024:#Update Retailer happy with new appointment 17/07, AM. _x000D_22/7/2024:#Update Retailer happy with new appointment 17/07, AM. _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | 0 | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1013101 | 30016602 | 2.Commissioning | [9 empty] | 2024-08-07 | [7 empty] | 0
901 | 474737 | 3460 | Batch 5 Jul24 | Type 1 | SOGEA | Express Food & Wine | Luton | LU2 9JS | 2024-07-02 | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1013102 | 30016503 | 6.Failed router install |  |  | 2024-07-01 | 2024-07-01 | 2024-07-01 | TRUE |  |  |  | 2024-07-26 |  |  |  | 2024-07-26 | 242005011165 |  | 2024-07-29 | 1
902 | 444511 | 3461 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Spar | MAGHERAFELT | BT45 6HF |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:36 _x000D_26/7/2024:22/07/2024 10:36 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:36 _x000D_26/7/2024:22/07/2024 10:36 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2363544 | 30016245 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
903 | 654931 | 3462 | Batch 5 Jul24 | Type 1 | SOGEA | Avon Road Convenience Premier | Essex | RM14 1RQ | 2024-07-02 | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1013099 | 30016505 | 6.Failed router install |  |  | 2024-07-01 | 2024-07-01 | 2024-07-02 | TRUE |  |  |  | 2024-07-31 |  |  |  | 2024-07-31 | 242005011157 |  | 2024-08-01 | 1
904 | 670397 | 3463 | Batch 5 Jul24 | Type 1 | FTTP | BALLYMAGORRY SPSO & CENTRA | STRABANE | BT82 0AT | 2024-07-02 | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFP2363543 | 30016248 | 2.Commissioning |  |  | 2024-07-01 | 2024-07-01 | 2024-07-01 | TRUE |  |  |  | 2024-07-26 | [7 empty] | 0
905 | 486455 | 3464 | Batch 5 Jul24 | Type 1 | FTTP | Good News | Kettering | NN16 8SX | 2024-07-02 | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFP2363542 | 30016293 | 6.Failed router install |  |  | 2024-07-01 | 2024-07-01 | 2024-07-02 | TRUE |  |  |  | 2024-07-24 |  |  |  | 2024-07-24 | 23A004946014 |  | 2024-07-25 | 1
906 | 667814 | 3466 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Thames View Post Office | BARKING | IG11 0NY | 2024-07-23 | 6/9/2024:#Update Awaiting further info from OR _x000D_5/9/2024:#Update Awaiting further info from OR _x000D_4/9/2024:#Update Awaiting further info from OR _x000D_3/9/2024:#Update Awaiting further info from OR _x000D_2/9/2024:#Update Awaiting further info from OR _x000D_29/8/2024:#Update Awaiting further info from OR _x000D_28/8/2024:#Update Awaiting further info from OR _x000D_27/8/2024:#Update Awaiting further info from OR _x000D_22/8/2024:#Update Awaiting further info from OR _x000D_21/8/2024:#Update Awaiting further info from OR _x000D_20/8/2024:#Update Awaiting further info from OR _x000D_19/8/2024:#Update Awaiting further info from OR _x000D_19/8/2024:01461454 _x000D_16/8/2024:#Update Awaiting further info from OR _x000D_15/8/2024:#Update Awaiting further info from OR _x000D_14/8/2024:#Update Awaiting further info from OR _x000D_13/8/2024:#Update Awaiting further info from OR _x000D_12/8/2024:#Update Awaiting further info from OR _x000D_9/8/2024:#Update Awaiting further info from OR _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update Awaiting further info from OR _x000D_29/7/2024:#Update Awaiting further info from OR _x000D_29/7/2024:01461454 _x000D_26/7/2024:01461454 _x000D_24/7/2024:#Update Retailer happy with new appointment 22/07, AM. _x000D_23/7/2024:#Update Retailer happy with new appointment 22/07, AM. _x000D_22/7/2024:#Update Retailer happy with new appointment 22/07, AM. _x000D_22/7/2024:#Update Retailer happy with new appointment 22/07, AM. _x000D_19/7/2024:#Update - Allwyn confirmed new appoint. _x000D_18/7/2024:#Update - Allwyn confirmed new appoint. _x000D_17/7/2024:#Update - Allwyn confirmed new appoint. _x000D_16/7/2024:#Update - Allwyn confirmed new appoint. _x000D_15/7/2024:#Update - Allwyn confirmed new appoint. _x000D_12/7/2024:#Update - Allwyn confirmed new appoint. _x000D_11/7/2024:#Update - Allwyn confirmed new appoint. _x000D_10/7/2024:#Update - Allwyn confirmed new appoint. _x000D_9/7/2024:#Update - Allwyn confirmed new appoint. _x000D_4/7/2024:#Update - Allwyn confirmed new appoint. _x000D_3/7/2024:#Update - Allwyn confirmed new appoint. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update Awaiting further info from OR _x000D_6/9/2024:#Update Awaiting further info from OR _x000D_5/9/2024:#Update Awaiting further info from OR _x000D_4/9/2024:#Update Awaiting further info from OR _x000D_3/9/2024:#Update Awaiting further info from OR _x000D_2/9/2024:#Update Awaiting further info from OR _x000D_29/8/2024:#Update Awaiting further info from OR _x000D_28/8/2024:#Update Awaiting further info from OR _x000D_27/8/2024:#Update Awaiting further info from OR _x000D_22/8/2024:#Update Awaiting further info from OR _x000D_21/8/2024:#Update Awaiting further info from OR _x000D_20/8/2024:#Update Awaiting further info from OR _x000D_19/8/2024:#Update Awaiting further info from OR _x000D_19/8/2024:01461454 _x000D_16/8/2024:#Update Awaiting further info from OR _x000D_15/8/2024:#Update Awaiting further info from OR _x000D_14/8/2024:#Update Awaiting further info from OR _x000D_13/8/2024:#Update Awaiting further info from OR _x000D_12/8/2024:#Update Awaiting further info from OR _x000D_9/8/2024:#Update Awaiting further info from OR _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update Awaiting further info from OR _x000D_29/7/2024:#Update Awaiting further info from OR _x000D_29/7/2024:01461454 _x000D_26/7/2024:01461454 _x000D_24/7/2024:#Update Retailer happy with new appointment 22/07, AM. _x000D_23/7/2024:#Update Retailer happy with new appointment 22/07, AM. _x000D_22/7/2024:#Update Retailer happy with new appointment 22/07, AM. _x000D_22/7/2024:#Update Retailer happy with new appointment 22/07, AM. _x000D_19/7/2024:#Update - Allwyn confirmed new appoint. _x000D_18/7/2024:#Update - Allwyn confirmed new appoint. _x000D_17/7/2024:#Update - Allwyn confirmed new appoint. _x000D_16/7/2024:#Update - Allwyn confirmed new appoint. _x000D_15/7/2024:#Update - Allwyn confirmed new appoint. _x000D_12/7/2024:#Update - Allwyn confirmed new appoint. _x000D_11/7/2024:#Update - Allwyn confirmed new appoint. _x000D_10/7/2024:#Update - Allwyn confirmed new appoint. _x000D_9/7/2024:#Update - Allwyn confirmed new appoint. _x000D_4/7/2024:#Update - Allwyn confirmed new appoint. _x000D_3/7/2024:#Update - Allwyn confirmed new appoint. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | #Update Awaiting further info from OR | 2024-06-07 |  |  |  |  | VFS1013098 | 30016463 | 1.Provisioning | AM |  | 2024-07-01 | 2024-09-06 |  | 0 | [11 empty] | 0
907 | 657191 | 3467 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Spar | Strabane | BT82 9DB | 2024-09-03 | 6/9/2024:#Update - Completed - 02/09/2024 10:40 _x000D_5/9/2024:#Update - Completed - 02/09/2024 10:40 _x000D_4/9/2024:#Update - Completed - 02/09/2024 10:40 _x000D_3/9/2024:#Update - Completed - 02/09/2024 10:40 _x000D_2/9/2024:#Update - Completed - 02/09/2024 10:40 _x000D_29/8/2024:#Update - Allwyn confirmed new appoint. _x000D_28/8/2024:#Update - Allwyn confirmed new appoint. _x000D_27/8/2024:#Update - Allwyn confirmed new appoint. _x000D_22/8/2024:#Update - Allwyn confirmed new appoint. _x000D_21/8/2024:#Update - Allwyn confirmed new appoint. _x000D_20/8/2024:#Update - Allwyn confirmed new appoint. _x000D_19/8/2024:#Update - Allwyn confirmed new appoint. _x000D_19/8/2024:01461201 _x000D_16/8/2024:#Update - Allwyn confirmed new appoint. _x000D_15/8/2024:#Update - Allwyn confirmed new appoint. _x000D_14/8/2024:#Update - Allwyn confirmed new appoint. _x000D_13/8/2024:#Update - Allwyn confirmed new appoint. _x000D_12/8/2024:#Update - Allwyn confirmed new appoint. _x000D_9/8/2024:#Update - Allwyn confirmed new appoint. _x000D_8/8/2024:02/07/2024 _x000D_6/8/2024:02/07/2024 _x000D_5/8/2024:02/07/2024 _x000D_2/8/2024:02/07/2024 _x000D_1/8/2024:02/07/2024 _x000D_31/7/2024:02/07/2024 _x000D_31/7/2024:02/07/2024 _x000D_30/7/2024:#Update - Allwyn confirmed new appoint. _x000D_29/7/2024:#Update - Allwyn confirmed new appoint. _x000D_29/7/2024:01461201 _x000D_26/7/2024:01461201 _x000D_24/7/2024:#Update - Allwyn confirmed new appoint. _x000D_23/7/2024:#Update - Allwyn confirmed new appoint. _x000D_22/7/2024:#Update - Allwyn confirmed new appoint. _x000D_22/7/2024:#Update - Allwyn confirmed new appoint. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:End User Missed appointment. Action required _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - Completed - 02/09/2024 10:40 _x000D_6/9/2024:#Update - Completed - 02/09/2024 10:40 _x000D_5/9/2024:#Update - Completed - 02/09/2024 10:40 _x000D_4/9/2024:#Update - Completed - 02/09/2024 10:40 _x000D_3/9/2024:#Update - Completed - 02/09/2024 10:40 _x000D_2/9/2024:#Update - Completed - 02/09/2024 10:40 _x000D_29/8/2024:#Update - Allwyn confirmed new appoint. _x000D_28/8/2024:#Update - Allwyn confirmed new appoint. _x000D_27/8/2024:#Update - Allwyn confirmed new appoint. _x000D_22/8/2024:#Update - Allwyn confirmed new appoint. _x000D_21/8/2024:#Update - Allwyn confirmed new appoint. _x000D_20/8/2024:#Update - Allwyn confirmed new appoint. _x000D_19/8/2024:#Update - Allwyn confirmed new appoint. _x000D_19/8/2024:01461201 _x000D_16/8/2024:#Update - Allwyn confirmed new appoint. _x000D_15/8/2024:#Update - Allwyn confirmed new appoint. _x000D_14/8/2024:#Update - Allwyn confirmed new appoint. _x000D_13/8/2024:#Update - Allwyn confirmed new appoint. _x000D_12/8/2024:#Update - Allwyn confirmed new appoint. _x000D_9/8/2024:#Update - Allwyn confirmed new appoint. _x000D_8/8/2024:02/07/2024 _x000D_6/8/2024:02/07/2024 _x000D_5/8/2024:02/07/2024 _x000D_2/8/2024:02/07/2024 _x000D_1/8/2024:02/07/2024 _x000D_31/7/2024:02/07/2024 _x000D_31/7/2024:02/07/2024 _x000D_30/7/2024:#Update - Allwyn confirmed new appoint. _x000D_29/7/2024:#Update - Allwyn confirmed new appoint. _x000D_29/7/2024:01461201 _x000D_26/7/2024:01461201 _x000D_24/7/2024:#Update - Allwyn confirmed new appoint. _x000D_23/7/2024:#Update - Allwyn confirmed new appoint. _x000D_22/7/2024:#Update - Allwyn confirmed new appoint. _x000D_22/7/2024:#Update - Allwyn confirmed new appoint. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:End User Missed appointment. Action required _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Order Completed | #Update - Completed - 02/09/2024 10:40 | 2024-06-07 |  |  |  |  | VFP2363538 | 30016226 | 2.Commissioning | AM |  | 2024-07-01 | 2024-08-29 |  | 0 | [11 empty] | 0
908 | 627592 | 3470 | Batch 5 Jul24 | Type 1 | SOGEA | Nimika Best Food and Wine | Borehamwood | WD6 1AT | 2024-07-02 | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1012371 | 30016611 | 6.Failed router install |  |  | 2024-07-01 | 2024-07-01 | 2024-07-01 | TRUE |  |  |  | 2024-07-26 |  |  |  | 2024-07-26 | 242005011152 |  | 2024-07-29 | 1
909 | 644102 | 3473 | Batch 5 Jul24 | Type 1 | SOGEA | Hills Harrington Road | Workington | CA14 3UJ | 2024-07-02 | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1013095 | 30016438 | 6.Failed router install |  |  | 2024-07-01 | 2024-07-01 | 2024-07-01 | TRUE |  |  |  | 2024-07-29 |  |  |  | 2024-07-29 | 242005008816 |  | 2024-07-30 | 1
910 | 667758 | 3474 | Batch 5 Jul24 | Type 1 | SOGEA | Todays Extra | Bradford | BD2 3LW | 2024-07-02 | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFP2363536 | 30016210 | 6.Failed router install |  |  | 2024-07-01 | 2024-07-01 | 2024-07-01 | TRUE |  |  |  | 2024-07-26 |  |  |  | 2024-07-26 | 23A004948655 |  | 2024-07-29 | 1
911 | 627499 | 3476 | Batch 5 Jul24 | Type 1 | FTTP | Nisa Tynemouth Road | Howden | NE28 0BA | 2024-07-02 | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFP2363537 | 30016316 | 2.Commissioning |  |  | 2024-07-01 | 2024-07-01 | 2024-07-01 | TRUE |  |  |  | 2024-07-24 | [7 empty] | 0
912 | 449368 | 3477 | Batch 5 Jul24 | Type 1 | SOGEA | H Robertson Convenience Store | SOUTH SHIELDS | NE33 4QX | 2024-07-02 | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1013089 | 30016461 | 6.Failed router install |  |  | 2024-07-01 | 2024-07-01 | 2024-07-01 | TRUE |  |  |  | 2024-07-24 |  |  |  | 2024-07-24 | 242005013471 |  | 2024-07-25 | 1
913 | 650756 | 3479 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Day Today | Belfast | BT13 3LB |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 11:17 _x000D_26/7/2024:22/07/2024 11:17 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing ONT at premises. Please confirm with end user that a second line on same ONT is required to progress the order further. _x000D_22/7/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing ONT at premises. Please confirm with end user that a second line on same ONT is required to progress the order further. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 11:17 _x000D_26/7/2024:22/07/2024 11:17 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing ONT at premises. Please confirm with end user that a second line on same ONT is required to progress the order further. _x000D_22/7/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing ONT at premises. Please confirm with end user that a second line on same ONT is required to progress the order further. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2363535 | 30016337 | 1.Provisioning | AM |  | 2024-07-01 | 2024-09-06 |  | 0 | [11 empty] | 0
914 | 642807 | 3480 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Bramley Park Road Premier | Sheffield | S13 8UA |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:38 _x000D_26/7/2024:22/07/2024 10:38 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:38 _x000D_26/7/2024:22/07/2024 10:38 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2363532 | 30016298 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
915 | 472574 | 3482 | Batch 5 Jul24 | Type 1 | SOGEA | SPAR WHITESTONE | Nuneaton | CV11 6PF | 2024-07-02 | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFP2363531 | 30016192 | 6.Failed router install |  |  | 2024-07-01 | 2024-07-01 | 2024-07-01 | TRUE |  |  |  | 2024-07-29 |  |  |  | 2024-07-29 | 23A004945905 |  | 2024-07-30 | 1
916 | 652286 | 3485 | Batch 5 Jul24 | Type 1 | FTTP | Nearbuy | Belfast | BT11 8BG | 2024-07-02 | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Completed by Supplier _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Completed by Supplier _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFP2363528 | 30016284 | 2.Commissioning |  |  | 2024-07-01 | 2024-07-01 | 2024-07-01 | TRUE |  |  |  | 2024-07-29 | [7 empty] | 0
917 | 100794 | 3486 | Batch 5 Jul24 | Type 1 | FTTP | Londis | MANCHESTER | M19 1AJ | 2024-07-02 | 19/7/2024:#Update Customer missed appointment - rescheduled to 16/07 AM. Customer to be made aware _x000D_18/7/2024:#Update Customer missed appointment - rescheduled to 16/07 AM. Customer to be made aware _x000D_17/7/2024:#Update Customer missed appointment - rescheduled to 16/07 AM. Customer to be made aware _x000D_16/7/2024:#Update Customer missed appointment - rescheduled to 16/07 AM. Customer to be made aware _x000D_15/7/2024:#Update Customer missed appointment - rescheduled to 16/07 AM. Customer to be made aware _x000D_12/7/2024:#Update Customer missed appointment - rescheduled to 16/07 AM. Customer to be made aware _x000D_11/7/2024:#Update Customer missed appointment - rescheduled to 16/07 AM. Customer to be made aware _x000D_10/7/2024:#Update Customer missed appointment - rescheduled to 16/07 AM. Customer to be made aware _x000D_9/7/2024:#Update Customer missed appointment - rescheduled to 16/07 AM. Customer to be made aware _x000D_4/7/2024:#Update Customer missed appointment - rescheduled to 16/07 AM. Customer to be made aware _x000D_3/7/2024:#Update Customer missed appointment - rescheduled to 16/07 AM. Customer to be made aware _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:End User Missed appointment. Action required _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:#Update Customer missed appointment - rescheduled to 16/07 AM. Customer to be made aware _x000D_18/7/2024:#Update Customer missed appointment - rescheduled to 16/07 AM. Customer to be made aware _x000D_17/7/2024:#Update Customer missed appointment - rescheduled to 16/07 AM. Customer to be made aware _x000D_16/7/2024:#Update Customer missed appointment - rescheduled to 16/07 AM. Customer to be made aware _x000D_15/7/2024:#Update Customer missed appointment - rescheduled to 16/07 AM. Customer to be made aware _x000D_12/7/2024:#Update Customer missed appointment - rescheduled to 16/07 AM. Customer to be made aware _x000D_11/7/2024:#Update Customer missed appointment - rescheduled to 16/07 AM. Customer to be made aware _x000D_10/7/2024:#Update Customer missed appointment - rescheduled to 16/07 AM. Customer to be made aware _x000D_9/7/2024:#Update Customer missed appointment - rescheduled to 16/07 AM. Customer to be made aware _x000D_4/7/2024:#Update Customer missed appointment - rescheduled to 16/07 AM. Customer to be made aware _x000D_3/7/2024:#Update Customer missed appointment - rescheduled to 16/07 AM. Customer to be made aware _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:End User Missed appointment. Action required _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFP2363527 | 30016348 | 2.Commissioning |  |  | 2024-07-01 | 2024-07-01 | 2024-07-01 | TRUE |  |  |  | 2024-08-06 | [7 empty] | 0
918 | 485220 | 3488 | Batch 5 Jul24 | Type 1 | FTTP | Spar Gillett | Dorchester | DT1 2LW | 2024-07-02 | 19/7/2024:#Update - Awaiting ECC approval. _x000D_18/7/2024:#Update - Awaiting ECC approval. _x000D_17/7/2024:#Update - Awaiting ECC approval. _x000D_16/7/2024:#Update - Awaiting ECC approval. _x000D_15/7/2024:#Update - Awaiting ECC approval. _x000D_12/7/2024:#Update - Awaiting ECC approval. _x000D_11/7/2024:#Update - Awaiting ECC approval. _x000D_10/7/2024:#Update - Awaiting feedback from engineer. _x000D_9/7/2024:#Update - Awaiting feedback from engineer. _x000D_4/7/2024:#Update - Awaiting feedback from engineer. _x000D_3/7/2024:#Update - Awaiting feedback from engineer. _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:#Update - Awaiting ECC approval. _x000D_18/7/2024:#Update - Awaiting ECC approval. _x000D_17/7/2024:#Update - Awaiting ECC approval. _x000D_16/7/2024:#Update - Awaiting ECC approval. _x000D_15/7/2024:#Update - Awaiting ECC approval. _x000D_12/7/2024:#Update - Awaiting ECC approval. _x000D_11/7/2024:#Update - Awaiting ECC approval. _x000D_10/7/2024:#Update - Awaiting feedback from engineer. _x000D_9/7/2024:#Update - Awaiting feedback from engineer. _x000D_4/7/2024:#Update - Awaiting feedback from engineer. _x000D_3/7/2024:#Update - Awaiting feedback from engineer. _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFP2363526 | 30016288 | 2.Commissioning |  |  | 2024-07-01 | 2024-07-01 | 2024-07-01 | TRUE |  |  |  | 2024-07-25 | [7 empty] | 0
919 | 647087 | 3490 | Batch 5 Jul24 | Type 3 | FTTP/Mobile | Nisa Local Southfield Drive | Peterborough | PE2 8PX | 2024-07-02 | 6/9/2024:#Update - Awaiting ECC approval. _x000D_5/9/2024:#Update - Awaiting ECC approval. _x000D_4/9/2024:#Update - Awaiting ECC approval. _x000D_3/9/2024:#Update - Awaiting ECC approval. _x000D_2/9/2024:#Update - Awaiting ECC approval. _x000D_29/8/2024:#Update - Awaiting ECC approval. _x000D_28/8/2024:#Update - Awaiting ECC approval. _x000D_27/8/2024:#Update - Awaiting ECC approval. _x000D_22/8/2024:#Update - Awaiting ECC approval. _x000D_21/8/2024:#Update - Awaiting ECC approval. _x000D_20/8/2024:#Update - Awaiting ECC approval. _x000D_19/8/2024:#Update - Awaiting ECC approval. _x000D_19/8/2024:01462090 _x000D_16/8/2024:#Update - Awaiting ECC approval. _x000D_15/8/2024:#Update - Awaiting ECC approval. _x000D_14/8/2024:#Update - Awaiting ECC approval. _x000D_13/8/2024:#Update - Awaiting ECC approval. _x000D_12/8/2024:#Update - Awaiting ECC approval. _x000D_9/8/2024:#Update - Awaiting ECC approval. _x000D_8/8/2024:10/07/2024 _x000D_6/8/2024:10/07/2024 _x000D_5/8/2024:10/07/2024 _x000D_2/8/2024:10/07/2024 _x000D_1/8/2024:10/07/2024 _x000D_31/7/2024:10/07/2024 _x000D_31/7/2024:10/07/2024 _x000D_30/7/2024:#Update - Awaiting ECC approval. _x000D_29/7/2024:#Update - Awaiting ECC approval. _x000D_29/7/2024:01462090 _x000D_26/7/2024:01462090 _x000D_24/7/2024:#Update - Awaiting ECC approval. _x000D_23/7/2024:#Update - Awaiting ECC approval. _x000D_22/7/2024:#Update - Awaiting ECC approval. _x000D_22/7/2024:#Update - Awaiting ECC approval. _x000D_19/7/2024:#Update Retailer aware of new appointment 31/07, AM. _x000D_18/7/2024:#Update Retailer aware of new appointment 31/07, AM. _x000D_17/7/2024:#Update Missed appointment as retailer unaware. Reappointed for 31/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_16/7/2024:#Update Missed appointment as retailer unaware. Reappointed for 17/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_15/7/2024:#Update Missed appointment as retailer unaware. Reappointed for 17/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_12/7/2024:#Update Missed appointment as retailer unaware. Reappointed for 17/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_11/7/2024:#Update Missed appointment as retailer unaware. Reappointed for 17/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_10/7/2024:#Update Missed appointment as retailer unaware. Reappointed for 17/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_9/7/2024:#Update Missed appointment as retailer unaware. Reappointed for 17/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_4/7/2024:#Update Missed appointment as retailer unaware. Reappointed for 17/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_3/7/2024:#Update Missed appointment as retailer unaware. Reappointed for 17/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - Awaiting ECC approval. _x000D_6/9/2024:#Update - Awaiting ECC approval. _x000D_5/9/2024:#Update - Awaiting ECC approval. _x000D_4/9/2024:#Update - Awaiting ECC approval. _x000D_3/9/2024:#Update - Awaiting ECC approval. _x000D_2/9/2024:#Update - Awaiting ECC approval. _x000D_29/8/2024:#Update - Awaiting ECC approval. _x000D_28/8/2024:#Update - Awaiting ECC approval. _x000D_27/8/2024:#Update - Awaiting ECC approval. _x000D_22/8/2024:#Update - Awaiting ECC approval. _x000D_21/8/2024:#Update - Awaiting ECC approval. _x000D_20/8/2024:#Update - Awaiting ECC approval. _x000D_19/8/2024:#Update - Awaiting ECC approval. _x000D_19/8/2024:01462090 _x000D_16/8/2024:#Update - Awaiting ECC approval. _x000D_15/8/2024:#Update - Awaiting ECC approval. _x000D_14/8/2024:#Update - Awaiting ECC approval. _x000D_13/8/2024:#Update - Awaiting ECC approval. _x000D_12/8/2024:#Update - Awaiting ECC approval. _x000D_9/8/2024:#Update - Awaiting ECC approval. _x000D_8/8/2024:10/07/2024 _x000D_6/8/2024:10/07/2024 _x000D_5/8/2024:10/07/2024 _x000D_2/8/2024:10/07/2024 _x000D_1/8/2024:10/07/2024 _x000D_31/7/2024:10/07/2024 _x000D_31/7/2024:10/07/2024 _x000D_30/7/2024:#Update - Awaiting ECC approval. _x000D_29/7/2024:#Update - Awaiting ECC approval. _x000D_29/7/2024:01462090 _x000D_26/7/2024:01462090 _x000D_24/7/2024:#Update - Awaiting ECC approval. _x000D_23/7/2024:#Update - Awaiting ECC approval. _x000D_22/7/2024:#Update - Awaiting ECC approval. _x000D_22/7/2024:#Update - Awaiting ECC approval. _x000D_19/7/2024:#Update Retailer aware of new appointment 31/07, AM. _x000D_18/7/2024:#Update Retailer aware of new appointment 31/07, AM. _x000D_17/7/2024:#Update Missed appointment as retailer unaware. Reappointed for 31/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_16/7/2024:#Update Missed appointment as retailer unaware. Reappointed for 17/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_15/7/2024:#Update Missed appointment as retailer unaware. Reappointed for 17/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_12/7/2024:#Update Missed appointment as retailer unaware. Reappointed for 17/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_11/7/2024:#Update Missed appointment as retailer unaware. Reappointed for 17/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_10/7/2024:#Update Missed appointment as retailer unaware. Reappointed for 17/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_9/7/2024:#Update Missed appointment as retailer unaware. Reappointed for 17/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_4/7/2024:#Update Missed appointment as retailer unaware. Reappointed for 17/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_3/7/2024:#Update Missed appointment as retailer unaware. Reappointed for 17/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update - Awaiting ECC approval. | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2363525 | 30016289 | 2.Commissioning | AM |  |  |  |  | 0 |  |  |  | 2024-08-21 | [7 empty] | 0
920 | 663203 | 3491 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Premier King Street Stores | Telford | TF4 2AH | 2024-07-02 | 6/9/2024:#Update Retailer not ready for appointment, reappointed for 18/09, AM. Action on Allwyn - ensure the retailer is aware. _x000D_5/9/2024:#Update Retailer not ready for appointment, reappointed for 18/09, AM. Action on Allwyn - ensure the retailer is aware. _x000D_4/9/2024:#Update Retailer not ready for appointment, reappointed for 18/09, AM. Action on Allwyn - ensure the retailer is aware. _x000D_3/9/2024:#Update Retailer not ready for appointment, reappointed for 18/09, AM. Action on Allwyn - ensure the retailer is aware. _x000D_2/9/2024:#Update Retailer not ready for appointment, reappointed for 18/09, AM. Action on Allwyn - ensure the retailer is aware. _x000D_29/8/2024:#Update Retailer not ready for appointment, reappointed for 18/09, AM. Action on Allwyn - ensure the retailer is aware. _x000D_28/8/2024:#Update Retailer not ready for appointment, reappointed for 18/09, AM. Action on Allwyn - ensure the retailer is aware. _x000D_27/8/2024:#Update Retailer not ready for appointment, reappointed for 18/09, AM. Action on Allwyn - ensure the retailer is aware. _x000D_22/8/2024:#Update Retailer not ready for appointment, reappointed for 18/09, AM. Action on Allwyn - ensure the retailer is aware. _x000D_21/8/2024:#Update Retailer aware of new appointment 31/07, AM. _x000D_20/8/2024:#Update Retailer aware of new appointment 31/07, AM. _x000D_19/8/2024:#Update Retailer aware of new appointment 31/07, AM. _x000D_19/8/2024:01462364 _x000D_16/8/2024:#Update Retailer aware of new appointment 31/07, AM. _x000D_15/8/2024:#Update Retailer aware of new appointment 31/07, AM. _x000D_14/8/2024:#Update Retailer aware of new appointment 31/07, AM. _x000D_13/8/2024:#Update Retailer aware of new appointment 31/07, AM. _x000D_12/8/2024:#Update Retailer aware of new appointment 31/07, AM. _x000D_9/8/2024:#Update Retailer aware of new appointment 31/07, AM. _x000D_8/8/2024:17/07/2024 _x000D_6/8/2024:17/07/2024 _x000D_5/8/2024:17/07/2024 _x000D_2/8/2024:17/07/2024 _x000D_1/8/2024:17/07/2024 _x000D_31/7/2024:17/07/2024 _x000D_31/7/2024:17/07/2024 _x000D_30/7/2024:#Update Retailer aware of new appointment 31/07, AM. _x000D_29/7/2024:#Update Retailer aware of new appointment 31/07, AM. _x000D_29/7/2024:01462364 _x000D_26/7/2024:01462364 _x000D_24/7/2024:#Update Retailer aware of new appointment 31/07, AM. _x000D_23/7/2024:#Update Retailer aware of new appointment 31/07, AM. _x000D_22/7/2024:#Update Retailer aware of new appointment 31/07, AM. _x000D_22/7/2024:#Update Retailer aware of new appointment 31/07, AM. _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update Retailer not ready for appointment, reappointed for 18/09, AM. Action on Allwyn - ensure the retailer is aware. _x000D_6/9/2024:#Update Retailer not ready for appointment, reappointed for 18/09, AM. Action on Allwyn - ensure the retailer is aware. _x000D_5/9/2024:#Update Retailer not ready for appointment, reappointed for 18/09, AM. Action on Allwyn - ensure the retailer is aware. _x000D_4/9/2024:#Update Retailer not ready for appointment, reappointed for 18/09, AM. Action on Allwyn - ensure the retailer is aware. _x000D_3/9/2024:#Update Retailer not ready for appointment, reappointed for 18/09, AM. Action on Allwyn - ensure the retailer is aware. _x000D_2/9/2024:#Update Retailer not ready for appointment, reappointed for 18/09, AM. Action on Allwyn - ensure the retailer is aware. _x000D_29/8/2024:#Update Retailer not ready for appointment, reappointed for 18/09, AM. Action on Allwyn - ensure the retailer is aware. _x000D_28/8/2024:#Update Retailer not ready for appointment, reappointed for 18/09, AM. Action on Allwyn - ensure the retailer is aware. _x000D_27/8/2024:#Update Retailer not ready for appointment, reappointed for 18/09, AM. Action on Allwyn - ensure the retailer is aware. _x000D_22/8/2024:#Update Retailer not ready for appointment, reappointed for 18/09, AM. Action on Allwyn - ensure the retailer is aware. _x000D_21/8/2024:#Update Retailer aware of new appointment 31/07, AM. _x000D_20/8/2024:#Update Retailer aware of new appointment 31/07, AM. _x000D_19/8/2024:#Update Retailer aware of new appointment 31/07, AM. _x000D_19/8/2024:01462364 _x000D_16/8/2024:#Update Retailer aware of new appointment 31/07, AM. _x000D_15/8/2024:#Update Retailer aware of new appointment 31/07, AM. _x000D_14/8/2024:#Update Retailer aware of new appointment 31/07, AM. _x000D_13/8/2024:#Update Retailer aware of new appointment 31/07, AM. _x000D_12/8/2024:#Update Retailer aware of new appointment 31/07, AM. _x000D_9/8/2024:#Update Retailer aware of new appointment 31/07, AM. _x000D_8/8/2024:17/07/2024 _x000D_6/8/2024:17/07/2024 _x000D_5/8/2024:17/07/2024 _x000D_2/8/2024:17/07/2024 _x000D_1/8/2024:17/07/2024 _x000D_31/7/2024:17/07/2024 _x000D_31/7/2024:17/07/2024 _x000D_30/7/2024:#Update Retailer aware of new appointment 31/07, AM. _x000D_29/7/2024:#Update Retailer aware of new appointment 31/07, AM. _x000D_29/7/2024:01462364 _x000D_26/7/2024:01462364 _x000D_24/7/2024:#Update Retailer aware of new appointment 31/07, AM. _x000D_23/7/2024:#Update Retailer aware of new appointment 31/07, AM. _x000D_22/7/2024:#Update Retailer aware of new appointment 31/07, AM. _x000D_22/7/2024:#Update Retailer aware of new appointment 31/07, AM. _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update Retailer not ready for appointment, reappointed for 18/09, AM. Action on Allwyn - ensure the retailer is aware. | 2024-06-07 |  |  |  |  | VFS1013086 | 30016393 | 1.Provisioning | AM |  | 2024-07-01 | 2024-08-13 |  | 0 | [11 empty] | 0
921 | 663288 | 3492 | Batch 5 Jul24 | Type 1 | SOGEA | Leeming Food & Wine | Borehamwood | WD6 4DU | 2024-07-02 | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1013087 | 30016405 | 6.Failed router install |  |  | 2024-07-01 | 2024-07-01 | 2024-07-01 | TRUE |  |  |  | 2024-07-26 |  |  |  | 2024-07-26 | 242005011151 |  | 2024-07-30 | 1
922 | 652161 | 3494 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Premier Eccles Old Road | Salford | M6 8HA |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:52 _x000D_26/7/2024:22/07/2024 10:52 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:52 _x000D_26/7/2024:22/07/2024 10:52 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2363522 | 30016195 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
923 | 485000 | 3496 | Batch 5 Jul24 | Type 1 | SOGEA | Premier | Alfreton | DE55 6JA | 2024-07-02 | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1013085 | 30016416 | 6.Failed router install |  |  | 2024-07-01 | 2024-07-01 | 2024-07-02 | TRUE |  |  |  | 2024-07-31 |  |  |  | 2024-07-31 | 23A004945909 |  | 2024-08-01 | 1
924 | 467140 | 401 | Batch 3 May24 | Type 1 | SoGEA/Mobile | Athavan Superstore | Harrow | HA2 9SG | 2024-08-16 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:Order Completed _x000D_19/8/2024:15/08/2024 12:59 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:Update: Order Amended _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:03 _x000D_26/7/2024:22/07/2024 10:03 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:Update: Order Amended _x000D_14/6/2024:Update: Order Amended _x000D_13/6/2024:Update: Order Amended _x000D_12/6/2024:Update: Order Amended _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:Order Completed _x000D_19/8/2024:15/08/2024 12:59 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:Update: Order Amended _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:03 _x000D_26/7/2024:22/07/2024 10:03 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:Update: Order Amended _x000D_14/6/2024:Update: Order Amended _x000D_13/6/2024:Update: Order Amended _x000D_12/6/2024:Update: Order Amended _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2300598 | 30013291 | 2.Commissioning | AM |  | 2024-05-02 | 2024-08-15 |  | 0 |  |  |  | 2024-09-06 | [7 empty] | 0
925 | 652573 | 911 | Batch 3 May24 | Type 1 | SOGEA | Choc N News | Harlow | CM20 1BL | 2024-07-03 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_18/7/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_17/7/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_16/7/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_15/7/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_12/7/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_11/7/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_10/7/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_9/7/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_4/7/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:Update: Order Amended _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:Update: Order Amended _x000D_17/6/2024:Update: Order Amended _x000D_14/6/2024:Update: Order Amended _x000D_13/6/2024:Update: Order Amended _x000D_12/6/2024:Update: Order Amended _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_18/7/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_17/7/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_16/7/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_15/7/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_12/7/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_11/7/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_10/7/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_9/7/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_4/7/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:Update: Order Amended _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:Update: Order Amended _x000D_17/6/2024:Update: Order Amended _x000D_14/6/2024:Update: Order Amended _x000D_13/6/2024:Update: Order Amended _x000D_12/6/2024:Update: Order Amended _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2301108 | 30013801 | 2.Commissioning | AM | [8 empty] | 2024-07-24 | [7 empty] | 0
926 | 461795 | 1322 | Batch 3 May24 | Type 3 | SoGEA/Mobile | Nisa Local | LUTON | LU3 3AH | 2024-06-07 | 6/9/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_5/9/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_4/9/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_3/9/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_2/9/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_29/8/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_28/8/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_27/8/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_22/8/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_21/8/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_20/8/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_19/8/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_19/8/2024:01418651 _x000D_16/8/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_15/8/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_14/8/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_13/8/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_12/8/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_9/8/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_8/8/2024:03/07/2024 _x000D_6/8/2024:03/07/2024 _x000D_5/8/2024:03/07/2024 _x000D_2/8/2024:03/07/2024 _x000D_1/8/2024:03/07/2024 _x000D_31/7/2024:03/07/2024 _x000D_31/7/2024:03/07/2024 _x000D_30/7/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_29/7/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_29/7/2024:01418651 _x000D_26/7/2024:01418651 _x000D_24/7/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_23/7/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_22/7/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_22/7/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_19/7/2024:#Update - Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 08/07/2024. We will continue to provide update as they become available. _x000D_18/7/2024:#Update - Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 08/07/2024. We will continue to provide update as they become available. _x000D_17/7/2024:#Update - Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 08/07/2024. We will continue to provide update as they become available. _x000D_16/7/2024:#Update - Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 08/07/2024. We will continue to provide update as they become available. _x000D_15/7/2024:#Update - Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 08/07/2024. We will continue to provide update as they become available. _x000D_12/7/2024:#Update - Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 08/07/2024. We will continue to provide update as they become available. _x000D_11/7/2024:#Update - Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 08/07/2024. We will continue to provide update as they become available. _x000D_10/7/2024:#Update - Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 08/07/2024. We will continue to provide update as they become available. _x000D_9/7/2024:#Update - Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 08/07/2024. We will continue to provide update as they become available. _x000D_4/7/2024:#Update - Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 08/07/2024. We will continue to provide update as they become available. _x000D_3/7/2024:#Update - Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 08/07/2024. We will continue to provide update as they become available. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 08/07/2024. We will continue to provide update as they become available. _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 26/06/2024.We will continue to provide update as they become available. _x000D_17/6/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 26/06/2024.We will continue to provide update as they become available. _x000D_14/6/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 26/06/2024.We will continue to provide update as they become available. _x000D_13/6/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 26/06/2024.We will continue to provide update as they become available. _x000D_12/6/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 26/06/2024.We will continue to provide update as they become available. _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 9/9/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_6/9/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_5/9/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_4/9/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_3/9/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_2/9/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_29/8/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_28/8/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_27/8/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_22/8/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_21/8/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_20/8/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_19/8/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_19/8/2024:01418651 _x000D_16/8/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_15/8/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_14/8/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_13/8/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_12/8/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_9/8/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_8/8/2024:03/07/2024 _x000D_6/8/2024:03/07/2024 _x000D_5/8/2024:03/07/2024 _x000D_2/8/2024:03/07/2024 _x000D_1/8/2024:03/07/2024 _x000D_31/7/2024:03/07/2024 _x000D_31/7/2024:03/07/2024 _x000D_30/7/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_29/7/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_29/7/2024:01418651 _x000D_26/7/2024:01418651 _x000D_24/7/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_23/7/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_22/7/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_22/7/2024:#Update OR notes sent to Allwyn to decide how to proceed. _x000D_19/7/2024:#Update - Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 08/07/2024. We will continue to provide update as they become available. _x000D_18/7/2024:#Update - Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 08/07/2024. We will continue to provide update as they become available. _x000D_17/7/2024:#Update - Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 08/07/2024. We will continue to provide update as they become available. _x000D_16/7/2024:#Update - Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 08/07/2024. We will continue to provide update as they become available. _x000D_15/7/2024:#Update - Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 08/07/2024. We will continue to provide update as they become available. _x000D_12/7/2024:#Update - Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 08/07/2024. We will continue to provide update as they become available. _x000D_11/7/2024:#Update - Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 08/07/2024. We will continue to provide update as they become available. _x000D_10/7/2024:#Update - Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 08/07/2024. We will continue to provide update as they become available. _x000D_9/7/2024:#Update - Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 08/07/2024. We will continue to provide update as they become available. _x000D_4/7/2024:#Update - Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 08/07/2024. We will continue to provide update as they become available. _x000D_3/7/2024:#Update - Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 08/07/2024. We will continue to provide update as they become available. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 08/07/2024. We will continue to provide update as they become available. _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 26/06/2024.We will continue to provide update as they become available. _x000D_17/6/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 26/06/2024.We will continue to provide update as they become available. _x000D_14/6/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 26/06/2024.We will continue to provide update as they become available. _x000D_13/6/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 26/06/2024.We will continue to provide update as they become available. _x000D_12/6/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 26/06/2024.We will continue to provide update as they become available. _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 0 | #Update OR notes sent to Allwyn to decide how to proceed. |  |  |  |  | 3.Allwyn to arrange rtr install | VFP2301519 | 30014212 | 2.Commissioning | AM |  | 2024-08-15 | 2024-08-15 |  | 0 |  |  |  | 2024-08-29 | [7 empty] | 0
927 | 665144 | 2539 | Batch 4 Jun24 | Type 1 | SoGEA/Mobile | Stowmarket Store Ltd | Stowmarket | IP14 1AH | 2024-07-03 | 6/9/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_5/9/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_4/9/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_3/9/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_2/9/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_29/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_28/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_27/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_22/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_21/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_20/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_19/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_19/8/2024:01435851 _x000D_16/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_15/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_14/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_13/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_12/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_9/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_8/8/2024:08/07/2024 _x000D_6/8/2024:08/07/2024 _x000D_5/8/2024:08/07/2024 _x000D_2/8/2024:08/07/2024 _x000D_1/8/2024:08/07/2024 _x000D_31/7/2024:08/07/2024 _x000D_31/7/2024:08/07/2024 _x000D_30/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_29/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_29/7/2024:01435851 _x000D_26/7/2024:01435851 _x000D_24/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_23/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_22/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_22/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_6/9/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_5/9/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_4/9/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_3/9/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_2/9/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_29/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_28/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_27/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_22/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_21/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_20/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_19/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_19/8/2024:01435851 _x000D_16/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_15/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_14/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_13/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_12/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_9/8/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_8/8/2024:08/07/2024 _x000D_6/8/2024:08/07/2024 _x000D_5/8/2024:08/07/2024 _x000D_2/8/2024:08/07/2024 _x000D_1/8/2024:08/07/2024 _x000D_31/7/2024:08/07/2024 _x000D_31/7/2024:08/07/2024 _x000D_30/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_29/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_29/7/2024:01435851 _x000D_26/7/2024:01435851 _x000D_24/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_23/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_22/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_22/7/2024:#Update - ECC proposal sent to Vodafone on 08/07 _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | #Update - ECC proposal sent to Vodafone on 08/07 | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFS996913 | 30016118 | 1.Provisioning | AM |  | 2024-06-13 | 2024-08-30 |  | 0 | [11 empty] | 0
928 | 660896 | 3500 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Sham News | Leeds | LS9 9JD |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:40 _x000D_26/7/2024:22/07/2024 10:40 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:#Update customer missed appointment due to being unaware of order. This has been pushed to 17/07 AM _x000D_18/7/2024:#Update customer missed appointment due to being unaware of order. This has been pushed to 17/07 AM _x000D_17/7/2024:#Update customer missed appointment due to being unaware of order. This has been pushed to 17/07 AM _x000D_16/7/2024:#Update customer missed appointment due to being unaware of order. This has been pushed to 17/07 AM _x000D_15/7/2024:#Update customer missed appointment due to being unaware of order. This has been pushed to 17/07 AM _x000D_12/7/2024:#Update customer missed appointment due to being unaware of order. This has been pushed to 17/07 AM _x000D_11/7/2024:#Update customer missed appointment due to being unaware of order. This has been pushed to 17/07 AM _x000D_10/7/2024:#Update customer missed appointment due to being unaware of order. This has been pushed to 17/07 AM _x000D_9/7/2024:#Update customer missed appointment due to being unaware of order. This has been pushed to 17/07 AM _x000D_4/7/2024:#Update customer missed appointment due to being unaware of order. This has been pushed to 17/07 AM _x000D_3/7/2024:#Update customer missed appointment due to being unaware of order. This has been pushed to 17/07 AM _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:40 _x000D_26/7/2024:22/07/2024 10:40 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:#Update customer missed appointment due to being unaware of order. This has been pushed to 17/07 AM _x000D_18/7/2024:#Update customer missed appointment due to being unaware of order. This has been pushed to 17/07 AM _x000D_17/7/2024:#Update customer missed appointment due to being unaware of order. This has been pushed to 17/07 AM _x000D_16/7/2024:#Update customer missed appointment due to being unaware of order. This has been pushed to 17/07 AM _x000D_15/7/2024:#Update customer missed appointment due to being unaware of order. This has been pushed to 17/07 AM _x000D_12/7/2024:#Update customer missed appointment due to being unaware of order. This has been pushed to 17/07 AM _x000D_11/7/2024:#Update customer missed appointment due to being unaware of order. This has been pushed to 17/07 AM _x000D_10/7/2024:#Update customer missed appointment due to being unaware of order. This has been pushed to 17/07 AM _x000D_9/7/2024:#Update customer missed appointment due to being unaware of order. This has been pushed to 17/07 AM _x000D_4/7/2024:#Update customer missed appointment due to being unaware of order. This has been pushed to 17/07 AM _x000D_3/7/2024:#Update customer missed appointment due to being unaware of order. This has been pushed to 17/07 AM _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2363520 | 30016317 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
929 | 632625 | 3503 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Day Today Express | Johnstone | PA5 8RD | 2024-07-03 | 6/9/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_5/9/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_4/9/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_3/9/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_2/9/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_29/8/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_28/8/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_27/8/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_22/8/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_21/8/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_20/8/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_19/8/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_19/8/2024:01463455 _x000D_16/8/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_15/8/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_14/8/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_13/8/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_12/8/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_9/8/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_8/8/2024:04/07/2024 _x000D_6/8/2024:04/07/2024 _x000D_5/8/2024:04/07/2024 _x000D_2/8/2024:04/07/2024 _x000D_1/8/2024:04/07/2024 _x000D_31/7/2024:04/07/2024 _x000D_31/7/2024:04/07/2024 _x000D_30/7/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_29/7/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_29/7/2024:01463455 _x000D_26/7/2024:01463455 _x000D_24/7/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_23/7/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_22/7/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_22/7/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_6/9/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_5/9/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_4/9/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_3/9/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_2/9/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_29/8/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_28/8/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_27/8/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_22/8/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_21/8/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_20/8/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_19/8/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_19/8/2024:01463455 _x000D_16/8/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_15/8/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_14/8/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_13/8/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_12/8/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_9/8/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_8/8/2024:04/07/2024 _x000D_6/8/2024:04/07/2024 _x000D_5/8/2024:04/07/2024 _x000D_2/8/2024:04/07/2024 _x000D_1/8/2024:04/07/2024 _x000D_31/7/2024:04/07/2024 _x000D_31/7/2024:04/07/2024 _x000D_30/7/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_29/7/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_29/7/2024:01463455 _x000D_26/7/2024:01463455 _x000D_24/7/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_23/7/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_22/7/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_22/7/2024:#Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update – The engineer could not identify where the lead is, they can locate the wiring going in but can't find in the store. The manager is away therefore couldn’t assist and the staff where unaware of where this could be located. They suggested it may be in the loft however there is a lot of stock. | 2024-06-07 |  |  |  |  | VFS1013079 | 30016390 | 1.Provisioning | AM |  | 2024-07-02 | 2024-09-02 |  | 0 | [11 empty] | 0
930 | 437766 | 3504 | Batch 5 Jul24 | Type 1 | SOGEA | Tindale Crescent Newsagent | BISHOP AUCKLAND | DL14 9TE | 2024-07-03 | 16/7/2024:Order Completed _x000D_15/7/2024:Order Completed _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 16/7/2024:Order Completed _x000D_15/7/2024:Order Completed _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1013080 | 30016502 | 2.Commissioning |  |  | 2024-07-02 | 2024-07-02 | 2024-07-02 | TRUE |  |  |  | 2024-07-25 | [7 empty] | 0
931 | 655534 | 3506 | Batch 5 Jul24 | Type 1 | FTTP | Costcutter Drumgor | Craigavon | BT65 5BW | 2024-07-03 | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFP2363517 | 30016347 | 2.Commissioning |  |  | 2024-07-02 | 2024-07-02 | 2024-07-02 | TRUE |  |  |  | 2024-07-24 | [7 empty] | 0
932 | 465509 | 3509 | Batch 5 Jul24 | Type 3 | SoGEA/Mobile | Spar | BRIDGWATER | TA5 2HE | 2024-07-03 | 6/9/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_5/9/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_4/9/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_3/9/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_2/9/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_29/8/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_28/8/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_27/8/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_22/8/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_21/8/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_20/8/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_19/8/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_19/8/2024:01465720 _x000D_16/8/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_15/8/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_14/8/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_13/8/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_12/8/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_9/8/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_8/8/2024:16/07/2024 _x000D_6/8/2024:16/07/2024 _x000D_5/8/2024:16/07/2024 _x000D_2/8/2024:16/07/2024 _x000D_1/8/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_30/7/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_29/7/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_29/7/2024:01465720 _x000D_26/7/2024:01465720 _x000D_24/7/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_23/7/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_22/7/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_22/7/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_6/9/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_5/9/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_4/9/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_3/9/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_2/9/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_29/8/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_28/8/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_27/8/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_22/8/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_21/8/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_20/8/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_19/8/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_19/8/2024:01465720 _x000D_16/8/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_15/8/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_14/8/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_13/8/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_12/8/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_9/8/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_8/8/2024:16/07/2024 _x000D_6/8/2024:16/07/2024 _x000D_5/8/2024:16/07/2024 _x000D_2/8/2024:16/07/2024 _x000D_1/8/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_30/7/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_29/7/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_29/7/2024:01465720 _x000D_26/7/2024:01465720 _x000D_24/7/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_23/7/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_22/7/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_22/7/2024:#Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update - unsuccessful installation - this site does not meet Openreach fire standards and no work will be done until these are met. Allwyn liaising with the retailer and will update CSL accordingly | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1013075 | 30016396 | 2.Commissioning | AM |  |  |  |  | 0 |  |  |  | 2024-09-03 | [7 empty] | 0
933 | 625773 | 3510 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Spar | Londonderry | BT48 8AB |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 11:01 _x000D_26/7/2024:22/07/2024 11:01 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 11:01 _x000D_26/7/2024:22/07/2024 11:01 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2363516 | 30016365 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
934 | 665000 | 3513 | Batch 5 Jul24 | Type 1 | SOGEA | Silverton Newsagents | DUMBARTON | G82 2NZ | 2024-07-03 | 19/7/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_18/7/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_17/7/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_16/7/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_15/7/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_12/7/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_11/7/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_10/7/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_9/7/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_4/7/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_3/7/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_18/7/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_17/7/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_16/7/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_15/7/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_12/7/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_11/7/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_10/7/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_9/7/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_4/7/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_3/7/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1013073 | 30016514 | 2.Commissioning |  |  | 2024-07-02 | 2024-07-02 | 2024-07-02 | TRUE |  |  |  | 2024-07-24 | [7 empty] | 0
935 | 672387 | 3514 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Spar | Devon | EX14 1JW | 2024-07-03 | 6/9/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_5/9/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_4/9/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_3/9/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_2/9/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_29/8/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_28/8/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_27/8/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_22/8/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_21/8/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_20/8/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_19/8/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_19/8/2024:01463429 _x000D_16/8/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_15/8/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_14/8/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_13/8/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_12/8/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_9/8/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_8/8/2024:03/07/2024 _x000D_6/8/2024:03/07/2024 _x000D_5/8/2024:03/07/2024 _x000D_2/8/2024:03/07/2024 _x000D_1/8/2024:03/07/2024 _x000D_31/7/2024:03/07/2024 _x000D_31/7/2024:03/07/2024 _x000D_30/7/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_29/7/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_29/7/2024:01463429 _x000D_26/7/2024:01463429 _x000D_24/7/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_23/7/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_22/7/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_22/7/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_19/7/2024:#Update Retailer happy with new appointment 23/07, AM. _x000D_18/7/2024:#Update Retailer happy with new appointment 23/07, AM. _x000D_17/7/2024:#Update Retailer happy with new appointment 23/07, AM. _x000D_16/7/2024:#Update Retailer happy with new appointment 23/07, AM. _x000D_15/7/2024:#Update Retailer happy with new appointment 23/07, AM. _x000D_12/7/2024:#Update Retailer happy with new appointment 23/07, AM. _x000D_11/7/2024:#Update Retailer happy with new appointment 23/07, AM. _x000D_10/7/2024:#Update Retailer happy with new appointment 23/07, AM. _x000D_9/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 16/07/2024.We will continue to provide update as they become available. _x000D_4/7/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_3/7/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_6/9/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_5/9/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_4/9/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_3/9/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_2/9/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_29/8/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_28/8/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_27/8/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_22/8/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_21/8/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_20/8/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_19/8/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_19/8/2024:01463429 _x000D_16/8/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_15/8/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_14/8/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_13/8/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_12/8/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_9/8/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_8/8/2024:03/07/2024 _x000D_6/8/2024:03/07/2024 _x000D_5/8/2024:03/07/2024 _x000D_2/8/2024:03/07/2024 _x000D_1/8/2024:03/07/2024 _x000D_31/7/2024:03/07/2024 _x000D_31/7/2024:03/07/2024 _x000D_30/7/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_29/7/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_29/7/2024:01463429 _x000D_26/7/2024:01463429 _x000D_24/7/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_23/7/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_22/7/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_22/7/2024:#Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM _x000D_19/7/2024:#Update Retailer happy with new appointment 23/07, AM. _x000D_18/7/2024:#Update Retailer happy with new appointment 23/07, AM. _x000D_17/7/2024:#Update Retailer happy with new appointment 23/07, AM. _x000D_16/7/2024:#Update Retailer happy with new appointment 23/07, AM. _x000D_15/7/2024:#Update Retailer happy with new appointment 23/07, AM. _x000D_12/7/2024:#Update Retailer happy with new appointment 23/07, AM. _x000D_11/7/2024:#Update Retailer happy with new appointment 23/07, AM. _x000D_10/7/2024:#Update Retailer happy with new appointment 23/07, AM. _x000D_9/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 16/07/2024.We will continue to provide update as they become available. _x000D_4/7/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_3/7/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update Missed appointment due to customer not being aware. This has been rescheduled to 18/07 AM | 2024-06-07 |  |  |  |  | VFP2363514 | 30016305 | 1.Provisioning | AM |  | 2024-07-02 | 2024-08-27 |  | 0 | [11 empty] | 0 | 672387
936 | 458994 | 3516 | Batch 5 Jul24 | Type 1 | SOGEA | Budgens | BLANDFORD FORUM | DT11 7LP | 2024-07-03 | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1013070 | 30016492 | 2.Commissioning |  |  | 2024-07-02 | 2024-07-02 | 2024-07-02 | TRUE |  |  |  | 2024-07-25 | [7 empty] | 0
937 | 487440 | 3517 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Nisa Local | Fife | KY8 3HR |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:46 _x000D_26/7/2024:22/07/2024 10:46 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:46 _x000D_26/7/2024:22/07/2024 10:46 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2363513 | 30016275 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
938 | 438884 | 3518 | Batch 5 Jul24 | Type 1 | FTTP | TJs Premier | LONDON | SE18 5NQ | 2024-07-03 | 19/7/2024:#Update - Allwyn have confirmed new appoint with retailer for 29/07 AM. _x000D_18/7/2024:#Update - Allwyn have confirmed new appoint with retailer for 29/07 AM. _x000D_17/7/2024:#Update - Allwyn have confirmed new appoint with retailer for 29/07 AM. _x000D_16/7/2024:#Update - Allwyn have confirmed new appoint with retailer for 29/07 AM. _x000D_15/7/2024:#Update - Allwyn have confirmed new appoint with retailer for 29/07 AM. _x000D_12/7/2024:#Update - Allwyn have confirmed new appoint with retailer for 29/07 AM. _x000D_11/7/2024:#Update - Allwyn have confirmed new appoint with retailer for 29/07 AM. _x000D_10/7/2024:#Update - Allwyn have confirmed new appoint with retailer for 29/07 AM. _x000D_9/7/2024:#Update - Allwyn have confirmed new appoint with retailer for 29/07 AM. _x000D_4/7/2024:#Update - Allwyn have confirmed new appoint with retailer for 29/07 AM. _x000D_3/7/2024:#Update - Allwyn have confirmed new appoint with retailer for 29/07 AM. _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:#Update - Allwyn have confirmed new appoint with retailer for 29/07 AM. _x000D_18/7/2024:#Update - Allwyn have confirmed new appoint with retailer for 29/07 AM. _x000D_17/7/2024:#Update - Allwyn have confirmed new appoint with retailer for 29/07 AM. _x000D_16/7/2024:#Update - Allwyn have confirmed new appoint with retailer for 29/07 AM. _x000D_15/7/2024:#Update - Allwyn have confirmed new appoint with retailer for 29/07 AM. _x000D_12/7/2024:#Update - Allwyn have confirmed new appoint with retailer for 29/07 AM. _x000D_11/7/2024:#Update - Allwyn have confirmed new appoint with retailer for 29/07 AM. _x000D_10/7/2024:#Update - Allwyn have confirmed new appoint with retailer for 29/07 AM. _x000D_9/7/2024:#Update - Allwyn have confirmed new appoint with retailer for 29/07 AM. _x000D_4/7/2024:#Update - Allwyn have confirmed new appoint with retailer for 29/07 AM. _x000D_3/7/2024:#Update - Allwyn have confirmed new appoint with retailer for 29/07 AM. _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFP2363512 | 30016311 | 2.Commissioning |  |  | 2024-07-02 | 2024-07-02 | 2024-07-02 | TRUE |  |  |  | 2024-07-25 | [7 empty] | 0
939 | 666758 | 3520 | Batch 5 Jul24 | Type 3 | SoGEA/Mobile | Smart News Food And Wine | Southall | UB1 2LF | 2024-07-03 | 6/9/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_5/9/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_4/9/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_3/9/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_2/9/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_29/8/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_28/8/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_27/8/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_22/8/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_21/8/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_20/8/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_19/8/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_19/8/2024:01465816 _x000D_16/8/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_15/8/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_14/8/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_13/8/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_12/8/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_9/8/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_8/8/2024:05/07/2024 _x000D_6/8/2024:05/07/2024 _x000D_5/8/2024:05/07/2024 _x000D_2/8/2024:05/07/2024 _x000D_1/8/2024:05/07/2024 _x000D_31/7/2024:05/07/2024 _x000D_31/7/2024:05/07/2024 _x000D_30/7/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_29/7/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_29/7/2024:01465816 _x000D_26/7/2024:01465816 _x000D_24/7/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_23/7/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_22/7/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_22/7/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_6/9/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_5/9/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_4/9/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_3/9/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_2/9/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_29/8/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_28/8/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_27/8/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_22/8/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_21/8/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_20/8/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_19/8/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_19/8/2024:01465816 _x000D_16/8/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_15/8/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_14/8/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_13/8/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_12/8/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_9/8/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_8/8/2024:05/07/2024 _x000D_6/8/2024:05/07/2024 _x000D_5/8/2024:05/07/2024 _x000D_2/8/2024:05/07/2024 _x000D_1/8/2024:05/07/2024 _x000D_31/7/2024:05/07/2024 _x000D_31/7/2024:05/07/2024 _x000D_30/7/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_29/7/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_29/7/2024:01465816 _x000D_26/7/2024:01465816 _x000D_24/7/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_23/7/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_22/7/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_22/7/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1013068 | 30016599 | 2.Commissioning | AM |  |  |  |  | 0 |  |  |  | 2024-08-21 | [7 empty] | 0
940 | 655057 | 3522 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Best One | Luton | LU3 2QQ | 2024-07-03 | 6/9/2024:#Update Address query, with VF to advise _x000D_5/9/2024:#Update Address query, with VF to advise _x000D_4/9/2024:#Update Address query, with VF to advise _x000D_3/9/2024:#Update Address query, with VF to advise _x000D_2/9/2024:#Update Address query, with VF to advise _x000D_29/8/2024:#Update Address query, with VF to advise _x000D_28/8/2024:#Update Address query, with VF to advise _x000D_27/8/2024:#Update Address query, with VF to advise _x000D_22/8/2024:#Update Address query, with VF to advise _x000D_21/8/2024:#Update Address query, with VF to advise _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update Address query, with VF to advise _x000D_6/9/2024:#Update Address query, with VF to advise _x000D_5/9/2024:#Update Address query, with VF to advise _x000D_4/9/2024:#Update Address query, with VF to advise _x000D_3/9/2024:#Update Address query, with VF to advise _x000D_2/9/2024:#Update Address query, with VF to advise _x000D_29/8/2024:#Update Address query, with VF to advise _x000D_28/8/2024:#Update Address query, with VF to advise _x000D_27/8/2024:#Update Address query, with VF to advise _x000D_22/8/2024:#Update Address query, with VF to advise _x000D_21/8/2024:#Update Address query, with VF to advise _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update Address query, with VF to advise | 2024-06-07 |  |  |  |  | VFP2363511 | 30016250 | 1.Provisioning | AM |  |  |  |  | 0 | [11 empty] | 0
941 | 655408 | 3523 | Batch 5 Jul24 | Type 1 | SOGEA | Go Local Extra | Manchester | M16 0HU | 2024-07-03 | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1013066 | 30016588 | 6.Failed router install |  |  | 2024-07-02 | 2024-07-02 | 2024-07-02 | TRUE |  |  |  | 2024-07-29 |  |  |  | 2024-08-06 | 23A004948712 |  | 2024-08-07 | 1
942 | 461713 | 3524 | Batch 5 Jul24 | Type 1 | SOGEA | Premier Supermarket | HUNTINGDON | PE29 7HN | 2024-07-03 | 4/7/2024:Supplier Delay: Provision of service will be delayed by a scheduled service outage _x000D_3/7/2024:Supplier Delay: Provision of service will be delayed by a scheduled service outage _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 4/7/2024:Supplier Delay: Provision of service will be delayed by a scheduled service outage _x000D_3/7/2024:Supplier Delay: Provision of service will be delayed by a scheduled service outage _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1013063 | 30016403 | 6.Failed router install |  |  | 2024-07-02 | 2024-07-02 | 2024-07-02 | TRUE |  |  |  | 2024-07-24 |  |  |  | 2024-08-27 | 237004907614 | 237004907614 | 2024-08-29 | 1
943 | 462789 | 3526 | Batch 5 Jul24 | Type 1 | FTTP | ALTA SUPER NEWS | LIVERPOOL | L13 5UR | 2024-07-03 | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFP2363510 | 30016205 | 2.Commissioning |  |  | 2024-07-02 | 2024-07-02 | 2024-07-04 | TRUE |  |  |  | 2024-08-02 | [7 empty] | 0
944 | 614593 | 3528 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Costcutter | Mansfield | NG18 2HG | 2024-07-03 | 6/9/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_5/9/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_4/9/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_3/9/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_2/9/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_29/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_28/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_27/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_22/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_21/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_20/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_19/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_19/8/2024:01463212 _x000D_16/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_15/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_14/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_13/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_12/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_9/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_8/8/2024:01/08/2024 _x000D_6/8/2024:01/08/2024 _x000D_5/8/2024:01/08/2024 _x000D_2/8/2024:01/08/2024 _x000D_1/8/2024:01/08/2024 _x000D_31/7/2024:05/07/2024 _x000D_31/7/2024:05/07/2024 _x000D_30/7/2024:#Update - Action for Allwyn - Installation has now been amended to 23/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 23/07 is a suitable date. _x000D_29/7/2024:#Update - Action for Allwyn - Installation has now been amended to 23/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 23/07 is a suitable date. _x000D_29/7/2024:01463212 _x000D_26/7/2024:01463212 _x000D_24/7/2024:#Update - Action for Allwyn - Installation has now been amended to 23/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 23/07 is a suitable date. _x000D_23/7/2024:#Update - Action for Allwyn - Installation has now been amended to 23/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 23/07 is a suitable date. _x000D_22/7/2024:#Update - Action for Allwyn - Installation has now been amended to 23/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 23/07 is a suitable date. _x000D_22/7/2024:#Update - Action for Allwyn - Installation has now been amended to 23/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 23/07 is a suitable date. _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_6/9/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_5/9/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_4/9/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_3/9/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_2/9/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_29/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_28/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_27/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_22/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_21/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_20/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_19/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_19/8/2024:01463212 _x000D_16/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_15/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_14/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_13/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_12/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_9/8/2024:#Update - ECC proposal sent to Vodafone on 01/08 _x000D_8/8/2024:01/08/2024 _x000D_6/8/2024:01/08/2024 _x000D_5/8/2024:01/08/2024 _x000D_2/8/2024:01/08/2024 _x000D_1/8/2024:01/08/2024 _x000D_31/7/2024:05/07/2024 _x000D_31/7/2024:05/07/2024 _x000D_30/7/2024:#Update - Action for Allwyn - Installation has now been amended to 23/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 23/07 is a suitable date. _x000D_29/7/2024:#Update - Action for Allwyn - Installation has now been amended to 23/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 23/07 is a suitable date. _x000D_29/7/2024:01463212 _x000D_26/7/2024:01463212 _x000D_24/7/2024:#Update - Action for Allwyn - Installation has now been amended to 23/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 23/07 is a suitable date. _x000D_23/7/2024:#Update - Action for Allwyn - Installation has now been amended to 23/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 23/07 is a suitable date. _x000D_22/7/2024:#Update - Action for Allwyn - Installation has now been amended to 23/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 23/07 is a suitable date. _x000D_22/7/2024:#Update - Action for Allwyn - Installation has now been amended to 23/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 23/07 is a suitable date. _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update - ECC proposal sent to Vodafone on 01/08 | 2024-06-07 |  |  |  |  | VFP2363507 | 30016216 | 1.Provisioning | AM |  | 2024-07-02 | 2024-08-30 |  | 0 | [11 empty] | 0
945 | 486329 | 3530 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | SPAR PONTHIR | NEWPORT | NP18 3NY | 2024-07-18 | 6/9/2024:#Update - installation unsuccessful due to complexity of job and additional cabling required; CSL currently waiting for OR feedback regarding upgrade requirement and OOH scope of work _x000D_5/9/2024:#Update - installation unsuccessful due to complexity of job and additional cabling required; CSL currently waiting for OR feedback regarding upgrade requirement and OOH scope of work _x000D_4/9/2024:#Update - installation unsuccessful due to complexity of job and additional cabling required; CSL currently waiting for OR feedback regarding upgrade requirement and OOH scope of work _x000D_3/9/2024:#Update - Appointment confirmed with allwyn. _x000D_2/9/2024:#Update - Appointment confirmed with allwyn. _x000D_29/8/2024:#Update - Appointment confirmed with allwyn. _x000D_28/8/2024:#Update - Appointment confirmed with allwyn. _x000D_27/8/2024:#Update - Appointment confirmed with allwyn. _x000D_22/8/2024:#Update - Appointment confirmed with allwyn. _x000D_21/8/2024:#Update - Appointment confirmed with allwyn. _x000D_20/8/2024:#Update - Appointment confirmed with allwyn. _x000D_19/8/2024:#Update - Appointment confirmed with allwyn. _x000D_19/8/2024:01463382 _x000D_16/8/2024:#Update - Appointment confirmed with allwyn. _x000D_15/8/2024:#Update - Appointment confirmed with allwyn. _x000D_14/8/2024:#Update - Appointment confirmed with allwyn. _x000D_13/8/2024:#Update - Appointment confirmed with allwyn. _x000D_12/8/2024:#Update - Appointment confirmed with allwyn. _x000D_9/8/2024:#Update - Appointment confirmed with allwyn. _x000D_8/8/2024:23/07/2024 _x000D_6/8/2024:23/07/2024 _x000D_5/8/2024:23/07/2024 _x000D_2/8/2024:23/07/2024 _x000D_1/8/2024:23/07/2024 _x000D_31/7/2024:23/07/2024 _x000D_31/7/2024:23/07/2024 _x000D_30/7/2024:#Update - Appointment confirmed with allwyn. _x000D_29/7/2024:#Update - Appointment confirmed with allwyn. _x000D_29/7/2024:01463382 _x000D_26/7/2024:01463382 _x000D_24/7/2024:#Update - Appointment confirmed with allwyn. _x000D_23/7/2024:#Update - Appointment confirmed with allwyn. _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_18/7/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_17/7/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_16/7/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_15/7/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_12/7/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_11/7/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_10/7/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_9/7/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_4/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_3/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - installation unsuccessful due to complexity of job and additional cabling required; CSL currently waiting for OR feedback regarding upgrade requirement and OOH scope of work _x000D_6/9/2024:#Update - installation unsuccessful due to complexity of job and additional cabling required; CSL currently waiting for OR feedback regarding upgrade requirement and OOH scope of work _x000D_5/9/2024:#Update - installation unsuccessful due to complexity of job and additional cabling required; CSL currently waiting for OR feedback regarding upgrade requirement and OOH scope of work _x000D_4/9/2024:#Update - installation unsuccessful due to complexity of job and additional cabling required; CSL currently waiting for OR feedback regarding upgrade requirement and OOH scope of work _x000D_3/9/2024:#Update - Appointment confirmed with allwyn. _x000D_2/9/2024:#Update - Appointment confirmed with allwyn. _x000D_29/8/2024:#Update - Appointment confirmed with allwyn. _x000D_28/8/2024:#Update - Appointment confirmed with allwyn. _x000D_27/8/2024:#Update - Appointment confirmed with allwyn. _x000D_22/8/2024:#Update - Appointment confirmed with allwyn. _x000D_21/8/2024:#Update - Appointment confirmed with allwyn. _x000D_20/8/2024:#Update - Appointment confirmed with allwyn. _x000D_19/8/2024:#Update - Appointment confirmed with allwyn. _x000D_19/8/2024:01463382 _x000D_16/8/2024:#Update - Appointment confirmed with allwyn. _x000D_15/8/2024:#Update - Appointment confirmed with allwyn. _x000D_14/8/2024:#Update - Appointment confirmed with allwyn. _x000D_13/8/2024:#Update - Appointment confirmed with allwyn. _x000D_12/8/2024:#Update - Appointment confirmed with allwyn. _x000D_9/8/2024:#Update - Appointment confirmed with allwyn. _x000D_8/8/2024:23/07/2024 _x000D_6/8/2024:23/07/2024 _x000D_5/8/2024:23/07/2024 _x000D_2/8/2024:23/07/2024 _x000D_1/8/2024:23/07/2024 _x000D_31/7/2024:23/07/2024 _x000D_31/7/2024:23/07/2024 _x000D_30/7/2024:#Update - Appointment confirmed with allwyn. _x000D_29/7/2024:#Update - Appointment confirmed with allwyn. _x000D_29/7/2024:01463382 _x000D_26/7/2024:01463382 _x000D_24/7/2024:#Update - Appointment confirmed with allwyn. _x000D_23/7/2024:#Update - Appointment confirmed with allwyn. _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_18/7/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_17/7/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_16/7/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_15/7/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_12/7/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_11/7/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_10/7/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_9/7/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_4/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_3/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Completed by Supplier | #Update - installation unsuccessful due to complexity of job and additional cabling required; CSL currently waiting for OR feedback regarding upgrade requirement and OOH scope of work | 2024-06-07 |  |  |  |  | VFS1013060 | 30016529 | 1.Provisioning | AM |  | 2024-07-02 | 2024-09-06 |  | 0 | [11 empty] | 0
946 | 666464 | 3531 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Family Shopper | BOURNEMOUTH | BH9 2AQ | 2024-07-03 | 6/9/2024:#Update Retailer confirmed OOH appointment 08/09 at 10am. _x000D_5/9/2024:#Update Retailer confirmed OOH appointment 08/09 at 10am. _x000D_4/9/2024:#Update Retailer confirmed OOH appointment 08/09 at 10am. _x000D_3/9/2024:#Update Retailer confirmed OOH appointment 08/09 at 10am. _x000D_2/9/2024:#Update Retailer confirmed OOH appointment 08/09 at 10am. _x000D_29/8/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_28/8/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_27/8/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_22/8/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_21/8/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_20/8/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_19/8/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_19/8/2024:01465852 _x000D_16/8/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_15/8/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_14/8/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_13/8/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_12/8/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_9/8/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_8/8/2024:09/07/2024 _x000D_6/8/2024:09/07/2024 _x000D_5/8/2024:09/07/2024 _x000D_2/8/2024:09/07/2024 _x000D_1/8/2024:09/07/2024 _x000D_31/7/2024:09/07/2024 _x000D_31/7/2024:09/07/2024 _x000D_30/7/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_29/7/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_29/7/2024:01465852 _x000D_26/7/2024:01465852 _x000D_24/7/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_23/7/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_22/7/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_22/7/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update Retailer confirmed OOH appointment 08/09 at 10am. _x000D_6/9/2024:#Update Retailer confirmed OOH appointment 08/09 at 10am. _x000D_5/9/2024:#Update Retailer confirmed OOH appointment 08/09 at 10am. _x000D_4/9/2024:#Update Retailer confirmed OOH appointment 08/09 at 10am. _x000D_3/9/2024:#Update Retailer confirmed OOH appointment 08/09 at 10am. _x000D_2/9/2024:#Update Retailer confirmed OOH appointment 08/09 at 10am. _x000D_29/8/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_28/8/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_27/8/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_22/8/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_21/8/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_20/8/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_19/8/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_19/8/2024:01465852 _x000D_16/8/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_15/8/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_14/8/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_13/8/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_12/8/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_9/8/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_8/8/2024:09/07/2024 _x000D_6/8/2024:09/07/2024 _x000D_5/8/2024:09/07/2024 _x000D_2/8/2024:09/07/2024 _x000D_1/8/2024:09/07/2024 _x000D_31/7/2024:09/07/2024 _x000D_31/7/2024:09/07/2024 _x000D_30/7/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_29/7/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_29/7/2024:01465852 _x000D_26/7/2024:01465852 _x000D_24/7/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_23/7/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_22/7/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_22/7/2024:#Update Upgrade and OOH sent to VF for approval. _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update Retailer confirmed OOH appointment 08/09 at 10am. | 2024-06-07 |  |  |  |  | VFP2363506 | 30016386 | 1.Provisioning | AM |  | 2024-07-02 | 2024-08-22 |  | 0 | [11 empty] | 0
947 | 672624 | 3540 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Spar Shop | ST. AUSTELL | PL26 8AB |  | 6/9/2024:#Update - Multiport order _x000D_5/9/2024:#Update - Multiport order _x000D_4/9/2024:#Update - Multiport order _x000D_3/9/2024:#Update - Multiport order _x000D_2/9/2024:#Update - Multiport order _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:47 _x000D_26/7/2024:22/07/2024 10:47 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - Multiport order _x000D_6/9/2024:#Update - Multiport order _x000D_5/9/2024:#Update - Multiport order _x000D_4/9/2024:#Update - Multiport order _x000D_3/9/2024:#Update - Multiport order _x000D_2/9/2024:#Update - Multiport order _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:47 _x000D_26/7/2024:22/07/2024 10:47 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | #Update - Multiport order | 2024-06-07 |  |  |  |  | VFP2363501 | 30016385 | 1.Provisioning |  |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
948 | 445054 | 3541 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Go Local Crayford Stores | DERBY | DE24 0HL |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:37 _x000D_26/7/2024:22/07/2024 10:37 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:37 _x000D_26/7/2024:22/07/2024 10:37 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2363496 | 30016369 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
949 | 635152 | 3543 | Batch 5 Jul24 | Type 1 | SOGEA | Bargain Booze | Newport | PO30 1TP | 2024-07-03 | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1013054 | 30016583 | 2.Commissioning |  |  | 2024-07-02 | 2024-07-02 | 2024-07-02 | TRUE |  |  |  | 2024-07-18 | [7 empty] | 0
950 | 480823 | 3548 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Village Convenience Store | Lancing | BN15 9TP | 2024-08-28 | 29/8/2024:#Update - Retailer has been made aware of new appointment _x000D_28/8/2024:#Update - Retailer has been made aware of new appointment _x000D_27/8/2024:#Update - Retailer has been made aware of new appointment _x000D_22/8/2024:#Update - Retailer has been made aware of new appointment _x000D_21/8/2024:#Update - Retailer has been made aware of new appointment _x000D_20/8/2024:#Update - Retailer has been made aware of new appointment _x000D_19/8/2024:#Update - Retailer has been made aware of new appointment _x000D_19/8/2024:01540511 _x000D_16/8/2024:#Update - Retailer has been made aware of new appointment _x000D_15/8/2024:#Update Action to arrange suitable time with customer for shop to be closed - frame ladder required to reach side walls to fire proof cleat along the right side of wall _x000D_14/8/2024:#Update Action to arrange suitable time with customer for shop to be closed - frame ladder required to reach side walls to fire proof cleat along the right side of wall _x000D_13/8/2024:#Update Action to arrange suitable time with customer for shop to be closed - frame ladder required to reach side walls to fire proof cleat along the right side of wall _x000D_12/8/2024:#Update Action to arrange suitable time with customer for shop to be closed - frame ladder required to reach side walls to fire proof cleat along the right side of wall _x000D_9/8/2024:#Update Action to arrange suitable time with customer for shop to be closed - frame ladder required to reach side walls to fire proof cleat along the right side of wall _x000D_8/8/2024:03/07/2024 _x000D_6/8/2024:03/07/2024 _x000D_5/8/2024:03/07/2024 _x000D_2/8/2024:03/07/2024 _x000D_1/8/2024:03/07/2024 _x000D_31/7/2024:03/07/2024 _x000D_31/7/2024:03/07/2024 _x000D_30/7/2024:#Update Action to arrange suitable time with customer for shop to be closed - frame ladder required to reach side walls to fire proof cleat along the right side of wall _x000D_29/7/2024:#Update Action to arrange suitable time with customer for shop to be closed - frame ladder required to reach side walls to fire proof cleat along the right side of wall _x000D_29/7/2024:01463440 _x000D_26/7/2024:01463440 _x000D_24/7/2024:#Update Action to arrange suitable time with customer for shop to be closed - frame ladder required to reach side walls to fire proof cleat along the right side of wall _x000D_23/7/2024:#Update Action to arrange suitable time with customer for shop to be closed - frame ladder required to reach side walls to fire proof cleat along the right side of wall _x000D_22/7/2024:#Update Action to arrange suitable time with customer for shop to be closed - frame ladder required to reach side walls to fire proof cleat along the right side of wall _x000D_22/7/2024:#Update Action to arrange suitable time with customer for shop to be closed - frame ladder required to reach side walls to fire proof cleat along the right side of wall _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 29/8/2024:#Update - Retailer has been made aware of new appointment _x000D_28/8/2024:#Update - Retailer has been made aware of new appointment _x000D_27/8/2024:#Update - Retailer has been made aware of new appointment _x000D_22/8/2024:#Update - Retailer has been made aware of new appointment _x000D_21/8/2024:#Update - Retailer has been made aware of new appointment _x000D_20/8/2024:#Update - Retailer has been made aware of new appointment _x000D_19/8/2024:#Update - Retailer has been made aware of new appointment _x000D_19/8/2024:01540511 _x000D_16/8/2024:#Update - Retailer has been made aware of new appointment _x000D_15/8/2024:#Update Action to arrange suitable time with customer for shop to be closed - frame ladder required to reach side walls to fire proof cleat along the right side of wall _x000D_14/8/2024:#Update Action to arrange suitable time with customer for shop to be closed - frame ladder required to reach side walls to fire proof cleat along the right side of wall _x000D_13/8/2024:#Update Action to arrange suitable time with customer for shop to be closed - frame ladder required to reach side walls to fire proof cleat along the right side of wall _x000D_12/8/2024:#Update Action to arrange suitable time with customer for shop to be closed - frame ladder required to reach side walls to fire proof cleat along the right side of wall _x000D_9/8/2024:#Update Action to arrange suitable time with customer for shop to be closed - frame ladder required to reach side walls to fire proof cleat along the right side of wall _x000D_8/8/2024:03/07/2024 _x000D_6/8/2024:03/07/2024 _x000D_5/8/2024:03/07/2024 _x000D_2/8/2024:03/07/2024 _x000D_1/8/2024:03/07/2024 _x000D_31/7/2024:03/07/2024 _x000D_31/7/2024:03/07/2024 _x000D_30/7/2024:#Update Action to arrange suitable time with customer for shop to be closed - frame ladder required to reach side walls to fire proof cleat along the right side of wall _x000D_29/7/2024:#Update Action to arrange suitable time with customer for shop to be closed - frame ladder required to reach side walls to fire proof cleat along the right side of wall _x000D_29/7/2024:01463440 _x000D_26/7/2024:01463440 _x000D_24/7/2024:#Update Action to arrange suitable time with customer for shop to be closed - frame ladder required to reach side walls to fire proof cleat along the right side of wall _x000D_23/7/2024:#Update Action to arrange suitable time with customer for shop to be closed - frame ladder required to reach side walls to fire proof cleat along the right side of wall _x000D_22/7/2024:#Update Action to arrange suitable time with customer for shop to be closed - frame ladder required to reach side walls to fire proof cleat along the right side of wall _x000D_22/7/2024:#Update Action to arrange suitable time with customer for shop to be closed - frame ladder required to reach side walls to fire proof cleat along the right side of wall _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFP2424205 | 30016278 | 2.Commissioning | AM |  | 2024-07-02 | 2024-08-27 |  | 0 | [11 empty] | 0
951 | 641766 | 3549 | Batch 5 Jul24 | Type 1 | SOGEA | Premier Express Leazes Convenience | Newcastle Upon Tyne | NE16 6JE | 2024-07-03 | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1013048 | 30016589 | 6.Failed router install |  |  | 2024-07-02 | 2024-07-02 | 2024-07-02 | TRUE |  |  |  | 2024-07-24 |  |  |  | 2024-07-24 | 242005013660 |  | 2024-07-24 | 1
952 | 656304 | 3551 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Spar | Merthyr Tudful | CF47 8NN |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:42 _x000D_26/7/2024:22/07/2024 10:42 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Pushed out until 5th August- Allwyn will confirm if obstruction/rubbish has been cleared away and will confirm appointment date when that has happened. _x000D_18/7/2024:#Update - Pushed out until 5th August- Allwyn will confirm if obstruction/rubbish has been cleared away and will confirm appointment date when that has happened. _x000D_17/7/2024:#Update - Pushed out until 5th August- Allwyn will confirm if obstruction/rubbish has been cleared away and will confirm appointment date when that has happened. _x000D_16/7/2024:#Update - Pushed out until 5th August- Allwyn will confirm if obstruction/rubbish has been cleared away and will confirm appointment date when that has happened. _x000D_15/7/2024:#Update - Pushed out until 5th August- Allwyn will confirm if obstruction/rubbish has been cleared away and will confirm appointment date when that has happened. _x000D_12/7/2024:#Update - Pushed out until 5th August- Allwyn will confirm if obstruction/rubbish has been cleared away and will confirm appointment date when that has happened. _x000D_11/7/2024:#Update - Pushed out until 5th August- Allwyn will confirm if obstruction/rubbish has been cleared away and will confirm appointment date when that has happened. _x000D_10/7/2024:#Update - Pushed out until 5th August- Allwyn will confirm if obstruction/rubbish has been cleared away and will confirm appointment date when that has happened. _x000D_9/7/2024:Your order has been delayed. The appointment has been delayed due to a Hazard owned by Thirdparty. Our suppliers team will contact you to get the available date for installation. We will provide the further updates on 06/07/2024. _x000D_4/7/2024:Your order has been delayed. The appointment has been delayed due to a Hazard owned by Thirdparty. Our suppliers team will contact you to get the available date for installation. We will provide the further updates on 06/07/2024. _x000D_3/7/2024:Your order has been delayed. The appointment has been delayed due to a Hazard owned by Thirdparty. Our suppliers team will contact you to get the available date for installation. We will provide the further updates on 06/07/2024. _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:42 _x000D_26/7/2024:22/07/2024 10:42 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Pushed out until 5th August- Allwyn will confirm if obstruction/rubbish has been cleared away and will confirm appointment date when that has happened. _x000D_18/7/2024:#Update - Pushed out until 5th August- Allwyn will confirm if obstruction/rubbish has been cleared away and will confirm appointment date when that has happened. _x000D_17/7/2024:#Update - Pushed out until 5th August- Allwyn will confirm if obstruction/rubbish has been cleared away and will confirm appointment date when that has happened. _x000D_16/7/2024:#Update - Pushed out until 5th August- Allwyn will confirm if obstruction/rubbish has been cleared away and will confirm appointment date when that has happened. _x000D_15/7/2024:#Update - Pushed out until 5th August- Allwyn will confirm if obstruction/rubbish has been cleared away and will confirm appointment date when that has happened. _x000D_12/7/2024:#Update - Pushed out until 5th August- Allwyn will confirm if obstruction/rubbish has been cleared away and will confirm appointment date when that has happened. _x000D_11/7/2024:#Update - Pushed out until 5th August- Allwyn will confirm if obstruction/rubbish has been cleared away and will confirm appointment date when that has happened. _x000D_10/7/2024:#Update - Pushed out until 5th August- Allwyn will confirm if obstruction/rubbish has been cleared away and will confirm appointment date when that has happened. _x000D_9/7/2024:Your order has been delayed. The appointment has been delayed due to a Hazard owned by Thirdparty. Our suppliers team will contact you to get the available date for installation. We will provide the further updates on 06/07/2024. _x000D_4/7/2024:Your order has been delayed. The appointment has been delayed due to a Hazard owned by Thirdparty. Our suppliers team will contact you to get the available date for installation. We will provide the further updates on 06/07/2024. _x000D_3/7/2024:Your order has been delayed. The appointment has been delayed due to a Hazard owned by Thirdparty. Our suppliers team will contact you to get the available date for installation. We will provide the further updates on 06/07/2024. _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2363493 | 30016243 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
953 | 651784 | 3552 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Cough and Candy News | Manchester | M34 3JU | 2024-09-02 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:#Update - NFA - Allwyn have confirmed with retailer for 30/08 _x000D_2/9/2024:#Update - NFA - Allwyn have confirmed with retailer for 30/08 _x000D_29/8/2024:#Update - NFA - Allwyn have confirmed with retailer for 30/08 _x000D_28/8/2024:#Update - NFA - Allwyn have confirmed with retailer for 30/08 _x000D_27/8/2024:#Update - NFA - Allwyn have confirmed with retailer for 30/08 _x000D_22/8/2024:#Update - NFA - Allwyn have confirmed with retailer for 30/08 _x000D_21/8/2024:#Update - NFA - Allwyn have confirmed with retailer for 30/08 _x000D_20/8/2024:#Update - NFA - Allwyn have confirmed with retailer for 30/08 _x000D_19/8/2024:#Update - NFA - Allwyn have confirmed with retailer for 30/08 _x000D_19/8/2024:01464669 _x000D_16/8/2024:#Update - Rubbish has been cleared away. Appointment for 05/08 has been approved. _x000D_15/8/2024:#Update - Rubbish has been cleared away. Appointment for 05/08 has been approved. _x000D_14/8/2024:#Update - Rubbish has been cleared away. Appointment for 05/08 has been approved. _x000D_13/8/2024:#Update - Rubbish has been cleared away. Appointment for 05/08 has been approved. _x000D_12/8/2024:#Update - Rubbish has been cleared away. Appointment for 05/08 has been approved. _x000D_9/8/2024:#Update - Rubbish has been cleared away. Appointment for 05/08 has been approved. _x000D_8/8/2024:31/07/2024 _x000D_6/8/2024:31/07/2024 _x000D_5/8/2024:31/07/2024 _x000D_2/8/2024:31/07/2024 _x000D_1/8/2024:31/07/2024 _x000D_31/7/2024:09/07/2024 _x000D_31/7/2024:09/07/2024 _x000D_30/7/2024:#Update - Pushed out until 5th August- Allwyn will confirm if obstruction/rubbish has been cleared away and will confirm appointment date when that has happened. _x000D_29/7/2024:#Update - Pushed out until 5th August- Allwyn will confirm if obstruction/rubbish has been cleared away and will confirm appointment date when that has happened. _x000D_29/7/2024:01464669 _x000D_26/7/2024:01464669 _x000D_24/7/2024:#Update - Pushed out until 5th August- Allwyn will confirm if obstruction/rubbish has been cleared away and will confirm appointment date when that has happened. _x000D_23/7/2024:#Update - Pushed out until 5th August- Allwyn will confirm if obstruction/rubbish has been cleared away and will confirm appointment date when that has happened. _x000D_22/7/2024:#Update - Pushed out until 5th August- Allwyn will confirm if obstruction/rubbish has been cleared away and will confirm appointment date when that has happened. _x000D_22/7/2024:#Update - Pushed out until 5th August- Allwyn will confirm if obstruction/rubbish has been cleared away and will confirm appointment date when that has happened. _x000D_9/7/2024:Order Completed _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:This is a delay message. We are currently unable to complete all engineering activities required to fulfil this order. Further indoor and outdoor work is required. End User presence will be required. _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:#Update - NFA - Allwyn have confirmed with retailer for 30/08 _x000D_2/9/2024:#Update - NFA - Allwyn have confirmed with retailer for 30/08 _x000D_29/8/2024:#Update - NFA - Allwyn have confirmed with retailer for 30/08 _x000D_28/8/2024:#Update - NFA - Allwyn have confirmed with retailer for 30/08 _x000D_27/8/2024:#Update - NFA - Allwyn have confirmed with retailer for 30/08 _x000D_22/8/2024:#Update - NFA - Allwyn have confirmed with retailer for 30/08 _x000D_21/8/2024:#Update - NFA - Allwyn have confirmed with retailer for 30/08 _x000D_20/8/2024:#Update - NFA - Allwyn have confirmed with retailer for 30/08 _x000D_19/8/2024:#Update - NFA - Allwyn have confirmed with retailer for 30/08 _x000D_19/8/2024:01464669 _x000D_16/8/2024:#Update - Rubbish has been cleared away. Appointment for 05/08 has been approved. _x000D_15/8/2024:#Update - Rubbish has been cleared away. Appointment for 05/08 has been approved. _x000D_14/8/2024:#Update - Rubbish has been cleared away. Appointment for 05/08 has been approved. _x000D_13/8/2024:#Update - Rubbish has been cleared away. Appointment for 05/08 has been approved. _x000D_12/8/2024:#Update - Rubbish has been cleared away. Appointment for 05/08 has been approved. _x000D_9/8/2024:#Update - Rubbish has been cleared away. Appointment for 05/08 has been approved. _x000D_8/8/2024:31/07/2024 _x000D_6/8/2024:31/07/2024 _x000D_5/8/2024:31/07/2024 _x000D_2/8/2024:31/07/2024 _x000D_1/8/2024:31/07/2024 _x000D_31/7/2024:09/07/2024 _x000D_31/7/2024:09/07/2024 _x000D_30/7/2024:#Update - Pushed out until 5th August- Allwyn will confirm if obstruction/rubbish has been cleared away and will confirm appointment date when that has happened. _x000D_29/7/2024:#Update - Pushed out until 5th August- Allwyn will confirm if obstruction/rubbish has been cleared away and will confirm appointment date when that has happened. _x000D_29/7/2024:01464669 _x000D_26/7/2024:01464669 _x000D_24/7/2024:#Update - Pushed out until 5th August- Allwyn will confirm if obstruction/rubbish has been cleared away and will confirm appointment date when that has happened. _x000D_23/7/2024:#Update - Pushed out until 5th August- Allwyn will confirm if obstruction/rubbish has been cleared away and will confirm appointment date when that has happened. _x000D_22/7/2024:#Update - Pushed out until 5th August- Allwyn will confirm if obstruction/rubbish has been cleared away and will confirm appointment date when that has happened. _x000D_22/7/2024:#Update - Pushed out until 5th August- Allwyn will confirm if obstruction/rubbish has been cleared away and will confirm appointment date when that has happened. _x000D_9/7/2024:Order Completed _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:This is a delay message. We are currently unable to complete all engineering activities required to fulfil this order. Further indoor and outdoor work is required. End User presence will be required. _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | 0 | 2024-06-07 |  |  |  |  | VFP2363492 | 30016211 | 2.Commissioning | AM |  | 2024-07-02 | 2024-08-30 |  | 0 | [11 empty] | 0
954 | 461569 | 3556 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Londis | ORPINGTON | BR5 3NJ |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:48 _x000D_26/7/2024:22/07/2024 10:48 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:48 _x000D_26/7/2024:22/07/2024 10:48 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_4/7/2024:Order Completed _x000D_3/7/2024:Order Completed _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2363490 | 30016343 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
955 | 661750 | 3558 | Batch 5 Jul24 | Type 1 | SOGEA | Singhs Premier | Sheffield | S5 7HA | 2024-07-03 | 19/7/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_18/7/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_17/7/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_16/7/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_15/7/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_12/7/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_11/7/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_10/7/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_9/7/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_4/7/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_3/7/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_27/6/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_25/6/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_24/6/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_20/6/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_19/6/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_18/6/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_17/6/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_14/6/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_13/6/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_12/6/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_11/6/2024:#Update Retailer happy with new appointment 12/06, AM. _x000D_ | 19/7/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_18/7/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_17/7/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_16/7/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_15/7/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_12/7/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_11/7/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_10/7/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_9/7/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_4/7/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_3/7/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_27/6/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_25/6/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_24/6/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_20/6/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_19/6/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_18/6/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_17/6/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_14/6/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_13/6/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_12/6/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_11/6/2024:#Update Retailer happy with new appointment 12/06, AM. _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1013045 | 30016454 | 6.Failed router install |  |  | 2024-07-02 | 2024-07-02 | 2024-07-02 | TRUE |  |  |  | 2024-07-26 |  |  |  | 2024-07-26 | 23A004948658 |  | 2024-07-29 | 1
956 | 615105 | 74 | Batch 2 Apr24 | Type 1 | SoGEA/Mobile | Mall News | Dagenham | RM10 8RE | 2024-09-03 | 6/9/2024:#Update - NFA - Allwyn confirmed new installation date with retailer 02/09 _x000D_5/9/2024:#Update - NFA - Allwyn confirmed new installation date with retailer 02/09 _x000D_4/9/2024:#Update - NFA - Allwyn confirmed new installation date with retailer 02/09 _x000D_3/9/2024:#Update - NFA - Allwyn confirmed new installation date with retailer 02/09 _x000D_2/9/2024:#Update - NFA - Allwyn confirmed new installation date with retailer 02/09 _x000D_29/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer 02/09 _x000D_28/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer 02/09 _x000D_27/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer 02/09 _x000D_22/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer 02/09 _x000D_21/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer 02/09 _x000D_20/8/2024:#Update - Order Delay - Survey Required- further updates to follow _x000D_19/8/2024:#Update - Order Delay - Survey Required- further updates to follow _x000D_19/8/2024:01339318 _x000D_16/8/2024:#Update - Order Delay - Survey Required- further updates to follow _x000D_15/8/2024:#Update - Order Delay - Survey Required- further updates to follow _x000D_14/8/2024:#Update - Order Delay - Survey Required- further updates to follow _x000D_13/8/2024:#Update - Order Delay - Survey Required- further updates to follow _x000D_12/8/2024:#Update - Order Delay - Survey Required- further updates to follow _x000D_9/8/2024:#Update - Order Delay - Survey Required- further updates to follow _x000D_8/8/2024:29/07/2024 _x000D_6/8/2024:29/07/2024 _x000D_5/8/2024:29/07/2024 _x000D_2/8/2024:29/07/2024 _x000D_1/8/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_30/7/2024:#Update - Order Delay - Survey Required- further updates to follow _x000D_29/7/2024:#Update - installation unsuccessful - incorrect routing identified, with Openreach to update and they will provide further updates accordingly _x000D_29/7/2024:01339318 _x000D_26/7/2024:01339318 _x000D_24/7/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_23/7/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_22/7/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_22/7/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_19/7/2024:#Update - NFA - Allwyn have confirmed new install date 19/07 - AM with retailer _x000D_18/7/2024:#Update - NFA - Allwyn have confirmed new install date 19/07 - AM with retailer _x000D_17/7/2024:#Update - NFA - Allwyn have confirmed new install date 19/07 - AM with retailer _x000D_16/7/2024:#Update - NFA - Allwyn have confirmed new install date 19/07 - AM with retailer _x000D_15/7/2024:#Update - NFA - Allwyn have confirmed new install date 19/07 - AM with retailer _x000D_12/7/2024:#Update - NFA - Allwyn have confirmed new install date 19/07 - AM with retailer _x000D_11/7/2024:#Update - NFA - Allwyn have confirmed new install date 19/07 - AM with retailer _x000D_10/7/2024:#Update - NFA - Allwyn have confirmed new install date 19/07 - AM with retailer _x000D_9/7/2024:#Update - NFA - Allwyn have confirmed new install date 19/07 - AM with retailer _x000D_4/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_3/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_27/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_25/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_24/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_20/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_19/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_18/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_17/6/2024:#Update - reappointed for 14/06 AM Action on Allwyn to confirm rescheduled installation date with retailer _x000D_14/6/2024:#Update - reappointed for 14/06 AM Action on Allwyn to confirm rescheduled installation date with retailer _x000D_13/6/2024:#Update - reappointed for 14/06 AM Action on Allwyn to confirm rescheduled installation date with retailer _x000D_12/6/2024:#Update - reappointed for 14/06 AM Action on Allwyn to confirm rescheduled installation date with retailer _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:#Update - NFA - Allwyn confirmed new installation date with retailer 02/09 _x000D_6/9/2024:#Update - NFA - Allwyn confirmed new installation date with retailer 02/09 _x000D_5/9/2024:#Update - NFA - Allwyn confirmed new installation date with retailer 02/09 _x000D_4/9/2024:#Update - NFA - Allwyn confirmed new installation date with retailer 02/09 _x000D_3/9/2024:#Update - NFA - Allwyn confirmed new installation date with retailer 02/09 _x000D_2/9/2024:#Update - NFA - Allwyn confirmed new installation date with retailer 02/09 _x000D_29/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer 02/09 _x000D_28/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer 02/09 _x000D_27/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer 02/09 _x000D_22/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer 02/09 _x000D_21/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer 02/09 _x000D_20/8/2024:#Update - Order Delay - Survey Required- further updates to follow _x000D_19/8/2024:#Update - Order Delay - Survey Required- further updates to follow _x000D_19/8/2024:01339318 _x000D_16/8/2024:#Update - Order Delay - Survey Required- further updates to follow _x000D_15/8/2024:#Update - Order Delay - Survey Required- further updates to follow _x000D_14/8/2024:#Update - Order Delay - Survey Required- further updates to follow _x000D_13/8/2024:#Update - Order Delay - Survey Required- further updates to follow _x000D_12/8/2024:#Update - Order Delay - Survey Required- further updates to follow _x000D_9/8/2024:#Update - Order Delay - Survey Required- further updates to follow _x000D_8/8/2024:29/07/2024 _x000D_6/8/2024:29/07/2024 _x000D_5/8/2024:29/07/2024 _x000D_2/8/2024:29/07/2024 _x000D_1/8/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_30/7/2024:#Update - Order Delay - Survey Required- further updates to follow _x000D_29/7/2024:#Update - installation unsuccessful - incorrect routing identified, with Openreach to update and they will provide further updates accordingly _x000D_29/7/2024:01339318 _x000D_26/7/2024:01339318 _x000D_24/7/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_23/7/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_22/7/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_22/7/2024:#Update - Allwyn attempting contact with retailer and will update CSL accordingly _x000D_19/7/2024:#Update - NFA - Allwyn have confirmed new install date 19/07 - AM with retailer _x000D_18/7/2024:#Update - NFA - Allwyn have confirmed new install date 19/07 - AM with retailer _x000D_17/7/2024:#Update - NFA - Allwyn have confirmed new install date 19/07 - AM with retailer _x000D_16/7/2024:#Update - NFA - Allwyn have confirmed new install date 19/07 - AM with retailer _x000D_15/7/2024:#Update - NFA - Allwyn have confirmed new install date 19/07 - AM with retailer _x000D_12/7/2024:#Update - NFA - Allwyn have confirmed new install date 19/07 - AM with retailer _x000D_11/7/2024:#Update - NFA - Allwyn have confirmed new install date 19/07 - AM with retailer _x000D_10/7/2024:#Update - NFA - Allwyn have confirmed new install date 19/07 - AM with retailer _x000D_9/7/2024:#Update - NFA - Allwyn have confirmed new install date 19/07 - AM with retailer _x000D_4/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_3/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_27/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_25/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_24/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_20/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_19/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_18/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_17/6/2024:#Update - reappointed for 14/06 AM Action on Allwyn to confirm rescheduled installation date with retailer _x000D_14/6/2024:#Update - reappointed for 14/06 AM Action on Allwyn to confirm rescheduled installation date with retailer _x000D_13/6/2024:#Update - reappointed for 14/06 AM Action on Allwyn to confirm rescheduled installation date with retailer _x000D_12/6/2024:#Update - reappointed for 14/06 AM Action on Allwyn to confirm rescheduled installation date with retailer _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | Order Completed | #Update - NFA - Allwyn confirmed new installation date with retailer 02/09 | 2024-04-29 | 29/04/2024: Allwyn to make retailer aware of visit as per the date in column T 08/04/2024: Allwyn to Please advise the store that a new service is required and the existing line can not be used. (Colsed ) 04/04/2024: CSL to provide updates. 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 2.Allwyn to arrange access | VFS939385 | 30013151 | 2.Commissioning | AM |  | 2024-04-03 | 2024-09-02 |  | 0 | [11 empty] | 0
957 | 658951 | 807 | Batch 3 May24 | Type 1 | SoGEA/Mobile | Monks Newsagents | Wembley | HA9 6PL | 2024-07-04 | 6/9/2024:#Update - requires upgrade to Premium managed install due to cabling requirements - with VF to approve _x000D_5/9/2024:#Update - requires upgrade to Premium managed install due to cabling requirements - with VF to approve _x000D_4/9/2024:#Update - requires upgrade to Premium managed install due to cabling requirements - with VF to approve _x000D_3/9/2024:#Update - requires upgrade to Premium managed install due to cabling requirements - with VF to approve _x000D_2/9/2024:#Update - requires upgrade to Premium managed install due to cabling requirements - with VF to approve _x000D_29/8/2024:#Update - requires upgrade to Premium managed install due to cabling requirements - with VF to approve _x000D_28/8/2024:#Update - requires upgrade to Premium managed install due to cabling requirements - with VF to approve _x000D_27/8/2024:#Update - requires upgrade to Premium managed install due to cabling requirements - with VF to approve _x000D_22/8/2024:#Update - requires upgrade to Premium managed install due to cabling requirements - with VF to approve _x000D_21/8/2024:#Update - requires upgrade to Premium managed install due to cabling requirements - with VF to approve _x000D_20/8/2024:#Update - requires upgrade to Premium managed install due to cabling requirements - with VF to approve _x000D_19/8/2024:#Update - requires upgrade to Premium managed install due to cabling requirements - with VF to approve _x000D_19/8/2024:01390453 _x000D_16/8/2024:#Update - requires upgrade to Premium managed install due to cabling requirements - with VF to approve _x000D_15/8/2024:#Update - requires upgrade to Premium managed install due to cabling requirements - with VF to approve _x000D_14/8/2024:#Update - requires upgrade to Premium managed install due to cabling requirements - with VF to approve _x000D_13/8/2024:#Update - requires upgrade to Premium managed install due to cabling requirements - with VF to approve _x000D_12/8/2024:#Update - requires upgrade to Premium managed install due to cabling requirements - with VF to approve _x000D_9/8/2024:#Update - requires upgrade to Premium managed install due to cabling requirements - with VF to approve _x000D_8/8/2024:07/08/2024 _x000D_6/8/2024:05/07/2024 _x000D_5/8/2024:05/07/2024 _x000D_2/8/2024:05/07/2024 _x000D_1/8/2024:05/07/2024 _x000D_31/7/2024:05/07/2024 _x000D_31/7/2024:05/07/2024 _x000D_30/7/2024:#Update - NFA - Allwyn have confirmed new install date 19/07 - AM with retailer _x000D_29/7/2024:#Update - NFA - Allwyn have confirmed new install date 19/07 - AM with retailer _x000D_29/7/2024:01390453 _x000D_26/7/2024:01390453 _x000D_24/7/2024:#Update - NFA - Allwyn have confirmed new install date 19/07 - AM with retailer _x000D_23/7/2024:#Update - NFA - Allwyn have confirmed new install date 19/07 - AM with retailer _x000D_22/7/2024:#Update - NFA - Allwyn have confirmed new install date 19/07 - AM with retailer _x000D_22/7/2024:#Update - NFA - Allwyn have confirmed new install date 19/07 - AM with retailer _x000D_19/7/2024:#Update - NFA - Allwyn confirmed new installation date 02/08 PM _x000D_18/7/2024:#Update - NFA - Allwyn confirmed new installation date 02/08 PM _x000D_17/7/2024:#Update - NFA - Allwyn confirmed new installation date 02/08 PM _x000D_16/7/2024:#Update - NFA - Allwyn confirmed new installation date 02/08 PM _x000D_15/7/2024:#Update - NFA - Allwyn confirmed new installation date 02/08 PM _x000D_12/7/2024:#Update - NFA - Allwyn confirmed new installation date 02/08 PM _x000D_11/7/2024:#Update - NFA - Allwyn confirmed new installation date 02/08 PM _x000D_10/7/2024:#Update - NFA - Allwyn confirmed new installation date 02/08 PM _x000D_9/7/2024:#Update - NFA - Allwyn confirmed new installation date 02/08 PM _x000D_4/7/2024:#Update - NFA - Allwyn confirmed new installation date 02/08 PM _x000D_3/7/2024:#Update - NFA - Allwyn confirmed new installation date 02/08 PM _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:#Update - NFA - retailer agreed to rescheduled install date with Allwyn, _x000D_27/6/2024:#Update - NFA - retailer agreed to rescheduled install date with Allwyn, _x000D_25/6/2024:#Update - NFA - retailer agreed to rescheduled install date with Allwyn, _x000D_24/6/2024:#Update - NFA - retailer agreed to rescheduled install date with Allwyn, _x000D_20/6/2024:#Update - NFA - retailer agreed to rescheduled install date with Allwyn, _x000D_19/6/2024:#Update - NFA - retailer agreed to rescheduled install date with Allwyn, _x000D_18/6/2024:#Update - NFA - retailer agreed to rescheduled install date with Allwyn, _x000D_17/6/2024:#Update - NFA - retailer agreed to rescheduled install date with Allwyn, _x000D_14/6/2024:#Update - NFA - retailer agreed to rescheduled install date with Allwyn, _x000D_13/6/2024:#Update - NFA - retailer agreed to rescheduled install date with Allwyn, _x000D_12/6/2024:#Update - NFA - retailer agreed to rescheduled install date with Allwyn, _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - requires upgrade to Premium managed install due to cabling requirements - with VF to approve _x000D_6/9/2024:#Update - requires upgrade to Premium managed install due to cabling requirements - with VF to approve _x000D_5/9/2024:#Update - requires upgrade to Premium managed install due to cabling requirements - with VF to approve _x000D_4/9/2024:#Update - requires upgrade to Premium managed install due to cabling requirements - with VF to approve _x000D_3/9/2024:#Update - requires upgrade to Premium managed install due to cabling requirements - with VF to approve _x000D_2/9/2024:#Update - requires upgrade to Premium managed install due to cabling requirements - with VF to approve _x000D_29/8/2024:#Update - requires upgrade to Premium managed install due to cabling requirements - with VF to approve _x000D_28/8/2024:#Update - requires upgrade to Premium managed install due to cabling requirements - with VF to approve _x000D_27/8/2024:#Update - requires upgrade to Premium managed install due to cabling requirements - with VF to approve _x000D_22/8/2024:#Update - requires upgrade to Premium managed install due to cabling requirements - with VF to approve _x000D_21/8/2024:#Update - requires upgrade to Premium managed install due to cabling requirements - with VF to approve _x000D_20/8/2024:#Update - requires upgrade to Premium managed install due to cabling requirements - with VF to approve _x000D_19/8/2024:#Update - requires upgrade to Premium managed install due to cabling requirements - with VF to approve _x000D_19/8/2024:01390453 _x000D_16/8/2024:#Update - requires upgrade to Premium managed install due to cabling requirements - with VF to approve _x000D_15/8/2024:#Update - requires upgrade to Premium managed install due to cabling requirements - with VF to approve _x000D_14/8/2024:#Update - requires upgrade to Premium managed install due to cabling requirements - with VF to approve _x000D_13/8/2024:#Update - requires upgrade to Premium managed install due to cabling requirements - with VF to approve _x000D_12/8/2024:#Update - requires upgrade to Premium managed install due to cabling requirements - with VF to approve _x000D_9/8/2024:#Update - requires upgrade to Premium managed install due to cabling requirements - with VF to approve _x000D_8/8/2024:07/08/2024 _x000D_6/8/2024:05/07/2024 _x000D_5/8/2024:05/07/2024 _x000D_2/8/2024:05/07/2024 _x000D_1/8/2024:05/07/2024 _x000D_31/7/2024:05/07/2024 _x000D_31/7/2024:05/07/2024 _x000D_30/7/2024:#Update - NFA - Allwyn have confirmed new install date 19/07 - AM with retailer _x000D_29/7/2024:#Update - NFA - Allwyn have confirmed new install date 19/07 - AM with retailer _x000D_29/7/2024:01390453 _x000D_26/7/2024:01390453 _x000D_24/7/2024:#Update - NFA - Allwyn have confirmed new install date 19/07 - AM with retailer _x000D_23/7/2024:#Update - NFA - Allwyn have confirmed new install date 19/07 - AM with retailer _x000D_22/7/2024:#Update - NFA - Allwyn have confirmed new install date 19/07 - AM with retailer _x000D_22/7/2024:#Update - NFA - Allwyn have confirmed new install date 19/07 - AM with retailer _x000D_19/7/2024:#Update - NFA - Allwyn confirmed new installation date 02/08 PM _x000D_18/7/2024:#Update - NFA - Allwyn confirmed new installation date 02/08 PM _x000D_17/7/2024:#Update - NFA - Allwyn confirmed new installation date 02/08 PM _x000D_16/7/2024:#Update - NFA - Allwyn confirmed new installation date 02/08 PM _x000D_15/7/2024:#Update - NFA - Allwyn confirmed new installation date 02/08 PM _x000D_12/7/2024:#Update - NFA - Allwyn confirmed new installation date 02/08 PM _x000D_11/7/2024:#Update - NFA - Allwyn confirmed new installation date 02/08 PM _x000D_10/7/2024:#Update - NFA - Allwyn confirmed new installation date 02/08 PM _x000D_9/7/2024:#Update - NFA - Allwyn confirmed new installation date 02/08 PM _x000D_4/7/2024:#Update - NFA - Allwyn confirmed new installation date 02/08 PM _x000D_3/7/2024:#Update - NFA - Allwyn confirmed new installation date 02/08 PM _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:#Update - NFA - retailer agreed to rescheduled install date with Allwyn, _x000D_27/6/2024:#Update - NFA - retailer agreed to rescheduled install date with Allwyn, _x000D_25/6/2024:#Update - NFA - retailer agreed to rescheduled install date with Allwyn, _x000D_24/6/2024:#Update - NFA - retailer agreed to rescheduled install date with Allwyn, _x000D_20/6/2024:#Update - NFA - retailer agreed to rescheduled install date with Allwyn, _x000D_19/6/2024:#Update - NFA - retailer agreed to rescheduled install date with Allwyn, _x000D_18/6/2024:#Update - NFA - retailer agreed to rescheduled install date with Allwyn, _x000D_17/6/2024:#Update - NFA - retailer agreed to rescheduled install date with Allwyn, _x000D_14/6/2024:#Update - NFA - retailer agreed to rescheduled install date with Allwyn, _x000D_13/6/2024:#Update - NFA - retailer agreed to rescheduled install date with Allwyn, _x000D_12/6/2024:#Update - NFA - retailer agreed to rescheduled install date with Allwyn, _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update - requires upgrade to Premium managed install due to cabling requirements - with VF to approve | 2024-05-13 | 13/05/2024: Allwyn to provide a time/date |  |  | 2.Allwyn to arrange access | VFS1069647 | 30013697 | 1.Provisioning | AM |  | 2024-05-10 | 2024-09-13 |  | 0 | [11 empty] | 0
958 | 665008 | 1160 | Batch 3 May24 | Type 1 | FTTP/Mobile | Shelley's Budgens (Old name:Post Office) | HORSHAM | RH12 5FN | 2024-06-13 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:03/07/2024 _x000D_5/8/2024:03/07/2024 _x000D_2/8/2024:03/07/2024 _x000D_1/8/2024:03/07/2024 _x000D_31/7/2024:03/07/2024 _x000D_31/7/2024:03/07/2024 _x000D_30/7/2024:#Update - NFA - Allwyn confirmed new installation date 02/08 PM _x000D_29/7/2024:#Update - NFA - Allwyn confirmed new installation date 02/08 PM _x000D_29/7/2024:01409661 _x000D_26/7/2024:01409661 _x000D_24/7/2024:#Update - NFA - Allwyn confirmed new installation date 02/08 PM _x000D_23/7/2024:#Update - NFA - Allwyn confirmed new installation date 02/08 PM _x000D_22/7/2024:#Update - NFA - Allwyn confirmed new installation date 02/08 PM _x000D_22/7/2024:#Update - NFA - Allwyn confirmed new installation date 02/08 PM _x000D_4/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/07 AM _x000D_3/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/07 AM _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/07 AM _x000D_27/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/07 AM _x000D_25/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/07 AM _x000D_24/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/07 AM _x000D_20/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/07 AM _x000D_19/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/07 AM _x000D_18/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/07 AM _x000D_17/6/2024:#Update - Openreach were unable to assign an engineer to site on the proposed install date. CSL to reappoint the installation and update with a committed date. _x000D_14/6/2024:#Update - Openreach were unable to assign an engineer to site on the proposed install date. CSL to reappoint the installation and update with a committed date. _x000D_13/6/2024:#Update - Openreach were unable to assign an engineer to site on the proposed install date. CSL to reappoint the installation and update with a committed date. _x000D_12/6/2024:#Update - Openreach were unable to assign an engineer to site on the proposed install date. CSL to reappoint the installation and update with a committed date. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:03/07/2024 _x000D_5/8/2024:03/07/2024 _x000D_2/8/2024:03/07/2024 _x000D_1/8/2024:03/07/2024 _x000D_31/7/2024:03/07/2024 _x000D_31/7/2024:03/07/2024 _x000D_30/7/2024:#Update - NFA - Allwyn confirmed new installation date 02/08 PM _x000D_29/7/2024:#Update - NFA - Allwyn confirmed new installation date 02/08 PM _x000D_29/7/2024:01409661 _x000D_26/7/2024:01409661 _x000D_24/7/2024:#Update - NFA - Allwyn confirmed new installation date 02/08 PM _x000D_23/7/2024:#Update - NFA - Allwyn confirmed new installation date 02/08 PM _x000D_22/7/2024:#Update - NFA - Allwyn confirmed new installation date 02/08 PM _x000D_22/7/2024:#Update - NFA - Allwyn confirmed new installation date 02/08 PM _x000D_4/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/07 AM _x000D_3/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/07 AM _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/07 AM _x000D_27/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/07 AM _x000D_25/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/07 AM _x000D_24/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/07 AM _x000D_20/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/07 AM _x000D_19/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/07 AM _x000D_18/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/07 AM _x000D_17/6/2024:#Update - Openreach were unable to assign an engineer to site on the proposed install date. CSL to reappoint the installation and update with a committed date. _x000D_14/6/2024:#Update - Openreach were unable to assign an engineer to site on the proposed install date. CSL to reappoint the installation and update with a committed date. _x000D_13/6/2024:#Update - Openreach were unable to assign an engineer to site on the proposed install date. CSL to reappoint the installation and update with a committed date. _x000D_12/6/2024:#Update - Openreach were unable to assign an engineer to site on the proposed install date. CSL to reappoint the installation and update with a committed date. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 3.Allwyn to arrange rtr install | VFP2301357 | 30014050 | 2.Commissioning | AM | [5 empty] | 1 |  |  | 2024-08-30 | [7 empty] | 0
959 | 469467 | 1327 | Batch 4 Jun24 | Type 1 | SOGEA | Nisa Local | CHELMSFORD | CM2 6DF | 2024-07-04 | 4/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/07 AM _x000D_3/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/07 AM _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/07 AM _x000D_27/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/07 AM _x000D_25/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/07 AM _x000D_24/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/07 AM _x000D_20/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/07 AM _x000D_19/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/07 AM _x000D_18/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/07 AM _x000D_17/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/07 AM _x000D_14/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/07 AM _x000D_13/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/07 AM _x000D_12/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/07 AM _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 4/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/07 AM _x000D_3/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/07 AM _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/07 AM _x000D_27/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/07 AM _x000D_25/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/07 AM _x000D_24/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/07 AM _x000D_20/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/07 AM _x000D_19/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/07 AM _x000D_18/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/07 AM _x000D_17/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/07 AM _x000D_14/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/07 AM _x000D_13/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/07 AM _x000D_12/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/07 AM _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS984894 | 30015306 | 2.Commissioning | AM |  | 2024-06-03 | 2024-07-03 | 2024-07-03 | TRUE |  |  |  | 2024-07-24 | [7 empty] | 0
960 | 667253 | 1405 | Batch 4 Jun24 | Type 1 | FTTP | Singh's Premier | Sheffield | S2 1LB | 2024-07-04 | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:#Update: Allwyn requested a Wednesday in July so order has been reappointed 03/07/24 _x000D_3/7/2024:#Update: Allwyn requested a Wednesday in July so order has been reappointed 03/07/24 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update: Allwyn requested a Wednesday in July so order has been reappointed 03/07/24 _x000D_27/6/2024:#Update: Allwyn requested a Wednesday in July so order has been reappointed 03/07/24 _x000D_25/6/2024:#Update: Allwyn requested a Wednesday in July so order has been reappointed 03/07/24 _x000D_24/6/2024:#Update: Allwyn requested a Wednesday in July so order has been reappointed 03/07/24 _x000D_20/6/2024:#Update: Allwyn requested a Wednesday in July so order has been reappointed 03/07/24 _x000D_19/6/2024:#Update: Allwyn requested a Wednesday in July so order has been reappointed 03/07/24 _x000D_18/6/2024:#Update: Allwyn requested a Wednesday in July so order has been reappointed 03/07/24 _x000D_17/6/2024:#Update: Allwyn requested a Wednesday in July so order has been reappointed 03/07/24 _x000D_14/6/2024:Update: Order Amended _x000D_13/6/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_12/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:#Update: Allwyn requested a Wednesday in July so order has been reappointed 03/07/24 _x000D_3/7/2024:#Update: Allwyn requested a Wednesday in July so order has been reappointed 03/07/24 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update: Allwyn requested a Wednesday in July so order has been reappointed 03/07/24 _x000D_27/6/2024:#Update: Allwyn requested a Wednesday in July so order has been reappointed 03/07/24 _x000D_25/6/2024:#Update: Allwyn requested a Wednesday in July so order has been reappointed 03/07/24 _x000D_24/6/2024:#Update: Allwyn requested a Wednesday in July so order has been reappointed 03/07/24 _x000D_20/6/2024:#Update: Allwyn requested a Wednesday in July so order has been reappointed 03/07/24 _x000D_19/6/2024:#Update: Allwyn requested a Wednesday in July so order has been reappointed 03/07/24 _x000D_18/6/2024:#Update: Allwyn requested a Wednesday in July so order has been reappointed 03/07/24 _x000D_17/6/2024:#Update: Allwyn requested a Wednesday in July so order has been reappointed 03/07/24 _x000D_14/6/2024:Update: Order Amended _x000D_13/6/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_12/6/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 | 7/6/2024: CSL to provide an update |  |  | 3.Allwyn to arrange rtr install | VFP2338499 | 30015546 | 6.Failed router install | AM |  | 2024-06-06 | 2024-07-03 | 2024-07-03 | TRUE |  |  |  | 2024-07-26 |  |  |  | 2024-07-26 | 242005013379 |  | 2024-08-02 | 1 | 667253
961 | 642985 | 1837 | Batch 4 Jun24 | Type 1 | SOGEA | Lakenheath news | Suffolk | IP27 9DS | 2024-07-04 | 29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:Update: Order Amended _x000D_15/7/2024:Update: Order Amended _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:Supplier Delay: KCI-3 (Order Completed) Delayed in Processing. _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:Update: Order Amended _x000D_15/7/2024:Update: Order Amended _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:Supplier Delay: KCI-3 (Order Completed) Delayed in Processing. _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFS983363 | 30015262 | 6.Failed router install | AM |  | 2024-06-12 | 2024-07-03 | 2024-07-03 | TRUE |  |  |  | 2024-07-26 |  |  |  | 2024-07-26 | 23A004945248 |  | 2024-07-29 | 1
962 | 108783 | 3560 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Nisa Local | PONTYPROIDD | CF38 2FF | 2024-08-29 | 29/8/2024:#Update - Traffic management work required. Our Suppliers have given us a review date of 03/09/2024 _x000D_28/8/2024:#Update - Traffic management work required. Our Suppliers have given us a review date of 03/09/2024 _x000D_27/8/2024:#Update - Traffic management work required. Our Suppliers have given us a review date of 03/09/2024 _x000D_22/8/2024:#Update - Traffic management work required. Our Suppliers have given us a review date of 03/09/2024 _x000D_21/8/2024:#Update - Traffic management work required. Our Suppliers have given us a review date of 03/09/2024 _x000D_20/8/2024:#Update - Traffic management work required. Our Suppliers have given us a review date of 03/09/2024 _x000D_19/8/2024:#Update - Traffic management work required. Our Suppliers have given us a review date of 03/09/2024 _x000D_19/8/2024:01477869 _x000D_16/8/2024:#Update - Traffic management work required. Our Suppliers have given us a review date of 03/09/2024 _x000D_15/8/2024:#Update - Traffic management work required. Our Suppliers have given us a review date of 03/09/2024 _x000D_14/8/2024:#Update - Multiskilled engineer work is required, Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available _x000D_13/8/2024:#Update - Multiskilled engineer work is required, Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available _x000D_12/8/2024:#Update - Multiskilled engineer work is required, Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available _x000D_9/8/2024:#Update - Multiskilled engineer work is required, Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available _x000D_8/8/2024:31/07/2024 _x000D_6/8/2024:31/07/2024 _x000D_5/8/2024:31/07/2024 _x000D_2/8/2024:31/07/2024 _x000D_1/8/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_30/7/2024:#Update - Supplier delay - Multiskilled engineer work is required, Our Suppliers have given us a review date of 25/07/2024. We will continue to provide update as they become available. _x000D_29/7/2024:#Update - Supplier delay - Multiskilled engineer work is required, Our Suppliers have given us a review date of 25/07/2024. We will continue to provide update as they become available. _x000D_29/7/2024:01477869 _x000D_26/7/2024:01477869 _x000D_24/7/2024:#Update - Supplier delay - Multiskilled engineer work is required, Our Suppliers have given us a review date of 25/07/2024. We will continue to provide update as they become available. _x000D_23/7/2024:#Update - Supplier delay - Multiskilled engineer work is required, Our Suppliers have given us a review date of 25/07/2024. We will continue to provide update as they become available. _x000D_22/7/2024:#Update Supplier delay - frames complications, HUD notes "More time needed because engineer ran out of time on this job. Details of work remaining Fit completed from CBT to OnT" _x000D_22/7/2024:#Update Supplier delay - frames complications, HUD notes "More time needed because engineer ran out of time on this job. Details of work remaining Fit completed from CBT to OnT" _x000D_19/7/2024:#Update - Civil work required. Our Suppliers have given us a review date of 22/07/2024. We will continue to provide update as they become available. _x000D_18/7/2024:#Update - Civil work required. Our Suppliers have given us a review date of 22/07/2024. We will continue to provide update as they become available. _x000D_17/7/2024:#Update - Civil work required. Our Suppliers have given us a review date of 22/07/2024. We will continue to provide update as they become available. _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 18/07/2024.We will continue to provide update as they become available. _x000D_10/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 18/07/2024.We will continue to provide update as they become available. _x000D_9/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 18/07/2024.We will continue to provide update as they become available. _x000D_4/7/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 29/8/2024:#Update - Traffic management work required. Our Suppliers have given us a review date of 03/09/2024 _x000D_28/8/2024:#Update - Traffic management work required. Our Suppliers have given us a review date of 03/09/2024 _x000D_27/8/2024:#Update - Traffic management work required. Our Suppliers have given us a review date of 03/09/2024 _x000D_22/8/2024:#Update - Traffic management work required. Our Suppliers have given us a review date of 03/09/2024 _x000D_21/8/2024:#Update - Traffic management work required. Our Suppliers have given us a review date of 03/09/2024 _x000D_20/8/2024:#Update - Traffic management work required. Our Suppliers have given us a review date of 03/09/2024 _x000D_19/8/2024:#Update - Traffic management work required. Our Suppliers have given us a review date of 03/09/2024 _x000D_19/8/2024:01477869 _x000D_16/8/2024:#Update - Traffic management work required. Our Suppliers have given us a review date of 03/09/2024 _x000D_15/8/2024:#Update - Traffic management work required. Our Suppliers have given us a review date of 03/09/2024 _x000D_14/8/2024:#Update - Multiskilled engineer work is required, Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available _x000D_13/8/2024:#Update - Multiskilled engineer work is required, Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available _x000D_12/8/2024:#Update - Multiskilled engineer work is required, Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available _x000D_9/8/2024:#Update - Multiskilled engineer work is required, Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available _x000D_8/8/2024:31/07/2024 _x000D_6/8/2024:31/07/2024 _x000D_5/8/2024:31/07/2024 _x000D_2/8/2024:31/07/2024 _x000D_1/8/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_30/7/2024:#Update - Supplier delay - Multiskilled engineer work is required, Our Suppliers have given us a review date of 25/07/2024. We will continue to provide update as they become available. _x000D_29/7/2024:#Update - Supplier delay - Multiskilled engineer work is required, Our Suppliers have given us a review date of 25/07/2024. We will continue to provide update as they become available. _x000D_29/7/2024:01477869 _x000D_26/7/2024:01477869 _x000D_24/7/2024:#Update - Supplier delay - Multiskilled engineer work is required, Our Suppliers have given us a review date of 25/07/2024. We will continue to provide update as they become available. _x000D_23/7/2024:#Update - Supplier delay - Multiskilled engineer work is required, Our Suppliers have given us a review date of 25/07/2024. We will continue to provide update as they become available. _x000D_22/7/2024:#Update Supplier delay - frames complications, HUD notes "More time needed because engineer ran out of time on this job. Details of work remaining Fit completed from CBT to OnT" _x000D_22/7/2024:#Update Supplier delay - frames complications, HUD notes "More time needed because engineer ran out of time on this job. Details of work remaining Fit completed from CBT to OnT" _x000D_19/7/2024:#Update - Civil work required. Our Suppliers have given us a review date of 22/07/2024. We will continue to provide update as they become available. _x000D_18/7/2024:#Update - Civil work required. Our Suppliers have given us a review date of 22/07/2024. We will continue to provide update as they become available. _x000D_17/7/2024:#Update - Civil work required. Our Suppliers have given us a review date of 22/07/2024. We will continue to provide update as they become available. _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 18/07/2024.We will continue to provide update as they become available. _x000D_10/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 18/07/2024.We will continue to provide update as they become available. _x000D_9/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 18/07/2024.We will continue to provide update as they become available. _x000D_4/7/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 5.CSL | VFP2363489 | 30016255 | 2.Commissioning | AM |  | 2024-07-03 | 2024-07-03 |  | 0 | [11 empty] | 0
963 | 446789 | 3561 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Spar | DUNGANNON | BT71 5HY | 2024-08-14 | 16/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 04/08/2024.We will continue to provide update as they become available. _x000D_15/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 04/08/2024.We will continue to provide update as they become available. _x000D_14/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 04/08/2024.We will continue to provide update as they become available. _x000D_13/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 04/08/2024.We will continue to provide update as they become available. _x000D_12/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 04/08/2024.We will continue to provide update as they become available. _x000D_9/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 04/08/2024.We will continue to provide update as they become available. _x000D_8/8/2024:22/07/2024 _x000D_6/8/2024:22/07/2024 _x000D_5/8/2024:22/07/2024 _x000D_2/8/2024:22/07/2024 _x000D_1/8/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_30/7/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 04/08/2024.We will continue to provide update as they become available. _x000D_29/7/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 04/08/2024.We will continue to provide update as they become available. _x000D_29/7/2024:01466911 _x000D_26/7/2024:01466911 _x000D_24/7/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 04/08/2024.We will continue to provide update as they become available. _x000D_23/7/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 04/08/2024.We will continue to provide update as they become available. _x000D_22/7/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 04/08/2024.We will continue to provide update as they become available. _x000D_22/7/2024:#Update - Civil work required. Our Suppliers have given us a review date of 22/07/2024. We will continue to provide update as they become available. _x000D_4/7/2024:Order Completed _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 16/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 04/08/2024.We will continue to provide update as they become available. _x000D_15/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 04/08/2024.We will continue to provide update as they become available. _x000D_14/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 04/08/2024.We will continue to provide update as they become available. _x000D_13/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 04/08/2024.We will continue to provide update as they become available. _x000D_12/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 04/08/2024.We will continue to provide update as they become available. _x000D_9/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 04/08/2024.We will continue to provide update as they become available. _x000D_8/8/2024:22/07/2024 _x000D_6/8/2024:22/07/2024 _x000D_5/8/2024:22/07/2024 _x000D_2/8/2024:22/07/2024 _x000D_1/8/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_30/7/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 04/08/2024.We will continue to provide update as they become available. _x000D_29/7/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 04/08/2024.We will continue to provide update as they become available. _x000D_29/7/2024:01466911 _x000D_26/7/2024:01466911 _x000D_24/7/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 04/08/2024.We will continue to provide update as they become available. _x000D_23/7/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 04/08/2024.We will continue to provide update as they become available. _x000D_22/7/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 04/08/2024.We will continue to provide update as they become available. _x000D_22/7/2024:#Update - Civil work required. Our Suppliers have given us a review date of 22/07/2024. We will continue to provide update as they become available. _x000D_4/7/2024:Order Completed _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 5.CSL | VFP2363488 | 30016356 | 3.In life | AM |  | 2024-07-03 | 2024-08-13 | 2024-08-13 09:59 | 1 |  |  |  | 2024-09-04 |  |  |  | 2024-09-04 | 238004925788 | 238004925788 | 2024-09-05 | 1
964 | 662062 | 3562 | Batch 5 Jul24 | Type 1 | SOGEA | Jala News | Wellington | TA21 8AA | 2024-07-04 | 9/7/2024:Order Completed _x000D_4/7/2024:Supplier Delay: Network Planning issue, please await for further details. _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/7/2024:Order Completed _x000D_4/7/2024:Supplier Delay: Network Planning issue, please await for further details. _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1013044 | 30016489 | 2.Commissioning |  |  | 2024-07-03 | 2024-07-03 | 2024-07-03 | TRUE |  |  |  | 2024-07-25 | [7 empty] | 0
965 | 431532 | 3563 | Batch 5 Jul24 | Type 1 | SOGEA | Westwood Convenience Store | PETERBOROUGH | PE3 7JB | 2024-07-04 | 6/9/2024:#Update - Order is committed for 12/09 - DP needs to be exposed and premium charge approved prior to visit. VF / Allwyn aware. _x000D_5/9/2024:#Update - Order is committed for 12/09 - DP needs to be exposed and premium charge approved prior to visit. VF / Allwyn aware. _x000D_4/9/2024:#Update - Order is committed for 12/09 - DP needs to be exposed and premium charge approved prior to visit. VF / Allwyn aware. _x000D_3/9/2024:#Update - Order is committed for 12/09 - DP needs to be exposed and premium charge approved prior to visit. VF / Allwyn aware. _x000D_2/9/2024:#Update - Order is committed for 12/09 - DP needs to be exposed and premium charge approved prior to visit. VF / Allwyn aware. _x000D_29/8/2024:#Update - Order is committed for 12/09 - DP needs to be exposed and premium charge approved prior to visit. VF / Allwyn aware. _x000D_28/8/2024:#Update - Order is committed for 12/09 - DP needs to be exposed and premium charge approved prior to visit. VF / Allwyn aware. _x000D_27/8/2024:#Update - order to be reraised but customer will need to expose DP in order to complete. Allwyn to be notified. _x000D_22/8/2024:#Update - order to be reraised but customer will need to expose DP in order to complete. Allwyn to be notified. _x000D_4/7/2024:Order Completed _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - Order is committed for 12/09 - DP needs to be exposed and premium charge approved prior to visit. VF / Allwyn aware. _x000D_6/9/2024:#Update - Order is committed for 12/09 - DP needs to be exposed and premium charge approved prior to visit. VF / Allwyn aware. _x000D_5/9/2024:#Update - Order is committed for 12/09 - DP needs to be exposed and premium charge approved prior to visit. VF / Allwyn aware. _x000D_4/9/2024:#Update - Order is committed for 12/09 - DP needs to be exposed and premium charge approved prior to visit. VF / Allwyn aware. _x000D_3/9/2024:#Update - Order is committed for 12/09 - DP needs to be exposed and premium charge approved prior to visit. VF / Allwyn aware. _x000D_2/9/2024:#Update - Order is committed for 12/09 - DP needs to be exposed and premium charge approved prior to visit. VF / Allwyn aware. _x000D_29/8/2024:#Update - Order is committed for 12/09 - DP needs to be exposed and premium charge approved prior to visit. VF / Allwyn aware. _x000D_28/8/2024:#Update - Order is committed for 12/09 - DP needs to be exposed and premium charge approved prior to visit. VF / Allwyn aware. _x000D_27/8/2024:#Update - order to be reraised but customer will need to expose DP in order to complete. Allwyn to be notified. _x000D_22/8/2024:#Update - order to be reraised but customer will need to expose DP in order to complete. Allwyn to be notified. _x000D_4/7/2024:Order Completed _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | #Update - Order is committed for 12/09 - DP needs to be exposed and premium charge approved prior to visit. VF / Allwyn aware. | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1092299 | 30016496 | 2.Commissioning |  |  | 2024-07-03 | 2024-07-03 | 2024-07-05 | TRUE |  |  |  | 2024-08-01 | [7 empty] | 0
966 | 231199 | 3564 | Batch 5 Jul24 | Type 1 | FTTP | Keystore JS Khun Khun | KILMARNOCK | KA3 1NT | 2024-07-04 | 16/7/2024:#Update VF to approve site survey charge. _x000D_15/7/2024:#Update VF to approve site survey charge. _x000D_12/7/2024:#Update VF to approve site survey charge. _x000D_11/7/2024:#Update VF to approve site survey charge. _x000D_10/7/2024:#Update VF to approve site survey charge. _x000D_9/7/2024:#Update VF to approve site survey charge. _x000D_4/7/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 16/7/2024:#Update VF to approve site survey charge. _x000D_15/7/2024:#Update VF to approve site survey charge. _x000D_12/7/2024:#Update VF to approve site survey charge. _x000D_11/7/2024:#Update VF to approve site survey charge. _x000D_10/7/2024:#Update VF to approve site survey charge. _x000D_9/7/2024:#Update VF to approve site survey charge. _x000D_4/7/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFP2363487 | 30016290 | 2.Commissioning |  |  | 2024-07-03 | 2024-07-03 | 2024-07-03 | TRUE |  |  |  | 2024-07-24 | [7 empty] | 0
967 | 664562 | 3566 | Batch 5 Jul24 | Type 1 | SOGEA | Nisa | Birmingham | B14 4LJ | 2024-07-04 | 19/7/2024:#Update customer missed appointment due to them not being aware of appointment. Rescheduled for 25/07 AM _x000D_18/7/2024:#Update customer missed appointment due to them not being aware of appointment. Rescheduled for 25/07 AM _x000D_17/7/2024:#Update customer missed appointment due to them not being aware of appointment. Rescheduled for 25/07 AM _x000D_16/7/2024:#Update customer missed appointment due to them not being aware of appointment. Rescheduled for 25/07 AM _x000D_15/7/2024:#Update customer missed appointment due to them not being aware of appointment. Rescheduled for 25/07 AM _x000D_12/7/2024:#Update customer missed appointment due to them not being aware of appointment. Rescheduled for 25/07 AM _x000D_11/7/2024:#Update customer missed appointment due to them not being aware of appointment. Rescheduled for 25/07 AM _x000D_10/7/2024:#Update customer missed appointment due to them not being aware of appointment. Rescheduled for 25/07 AM _x000D_9/7/2024:#Update customer missed appointment due to them not being aware of appointment. Rescheduled for 25/07 AM _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:#Update customer missed appointment due to them not being aware of appointment. Rescheduled for 25/07 AM _x000D_18/7/2024:#Update customer missed appointment due to them not being aware of appointment. Rescheduled for 25/07 AM _x000D_17/7/2024:#Update customer missed appointment due to them not being aware of appointment. Rescheduled for 25/07 AM _x000D_16/7/2024:#Update customer missed appointment due to them not being aware of appointment. Rescheduled for 25/07 AM _x000D_15/7/2024:#Update customer missed appointment due to them not being aware of appointment. Rescheduled for 25/07 AM _x000D_12/7/2024:#Update customer missed appointment due to them not being aware of appointment. Rescheduled for 25/07 AM _x000D_11/7/2024:#Update customer missed appointment due to them not being aware of appointment. Rescheduled for 25/07 AM _x000D_10/7/2024:#Update customer missed appointment due to them not being aware of appointment. Rescheduled for 25/07 AM _x000D_9/7/2024:#Update customer missed appointment due to them not being aware of appointment. Rescheduled for 25/07 AM _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1013040 | 30016575 | 6.Failed router install |  |  | 2024-07-03 | 2024-07-03 | 2024-07-03 | TRUE |  |  |  | 2024-07-26 |  |  |  | 2024-07-26 | 237004907580 |  | 2024-07-29 | 1
968 | 471189 | 3568 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Premier Express | Llanelli | SA15 3BD | 2024-07-04 | 6/9/2024:#Update - retailer out of country and cannot confirm access - install date pushed out; customer to liaise with retailer when they return and feedback to CSL _x000D_5/9/2024:#Update - retailer out of country and cannot confirm access - install date pushed out; customer to liaise with retailer when they return and feedback to CSL _x000D_4/9/2024:#Update - retailer out of country and cannot confirm access - install date pushed out; customer to liaise with retailer when they return and feedback to CSL _x000D_3/9/2024:#Update - retailer out of country and cannot confirm access - install date pushed out; customer to liaise with retailer when they return and feedback to CSL _x000D_2/9/2024:#Update - retailer out of country and cannot confirm access - install date pushed out; customer to liaise with retailer when they return and feedback to CSL _x000D_29/8/2024:#Update - retailer out of country and cannot confirm access - install date pushed out; customer to liaise with retailer when they return and feedback to CSL _x000D_28/8/2024:#Update - retailer out of country and cannot confirm access - install date pushed out; customer to liaise with retailer when they return and feedback to CSL _x000D_27/8/2024:#Update - retailer out of country and cannot confirm access - install date pushed out; customer to liaise with retailer when they return and feedback to CSL _x000D_22/8/2024:#Update - retailer out of country and cannot confirm access - install date pushed out; customer to liaise with retailer when they return and feedback to CSL _x000D_21/8/2024:#Update - retailer out of country and cannot confirm access - install date pushed out; customer to liaise with retailer when they return and feedback to CSL _x000D_20/8/2024:#Update - installation unsuccessful: Line plant access issue needs to be resolved to complete this job. Unable to access Beyond the DP. Openreach requested PTW from third party/EU and will provide further updates accordingly _x000D_19/8/2024:#Update - installation unsuccessful: Line plant access issue needs to be resolved to complete this job. Unable to access Beyond the DP. Openreach requested PTW from third party/EU and will provide further updates accordingly _x000D_19/8/2024:01465564 _x000D_16/8/2024:#Update - installation unsuccessful: Line plant access issue needs to be resolved to complete this job. Unable to access Beyond the DP. Openreach requested PTW from third party/EU and will provide further updates accordingly _x000D_15/8/2024:#Update - installation unsuccessful: Line plant access issue needs to be resolved to complete this job. Unable to access Beyond the DP. Openreach requested PTW from third party/EU and will provide further updates accordingly _x000D_14/8/2024:#Update - installation unsuccessful: Line plant access issue needs to be resolved to complete this job. Unable to access Beyond the DP. Openreach requested PTW from third party/EU and will provide further updates accordingly _x000D_13/8/2024:#Update - installation unsuccessful: Line plant access issue needs to be resolved to complete this job. Unable to access Beyond the DP. Openreach requested PTW from third party/EU and will provide further updates accordingly _x000D_12/8/2024:#Update - installation unsuccessful: Line plant access issue needs to be resolved to complete this job. Unable to access Beyond the DP. Openreach requested PTW from third party/EU and will provide further updates accordingly _x000D_9/8/2024:#Update - installation unsuccessful: Line plant access issue needs to be resolved to complete this job. Unable to access Beyond the DP. Openreach requested PTW from third party/EU and will provide further updates accordingly _x000D_8/8/2024:25/07/2024 _x000D_6/8/2024:25/07/2024 _x000D_5/8/2024:25/07/2024 _x000D_2/8/2024:25/07/2024 _x000D_1/8/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_30/7/2024:#Update - installation unsuccessful: Line plant access issue needs to be resolved to complete this job. Unable to access Beyond the DP. Openreach requested PTW from third party/EU and will provide further updates accordingly _x000D_29/7/2024:#Update - installation unsuccessful: Line plant access issue needs to be resolved to complete this job. Unable to access Beyond the DP. Openreach requested PTW from third party/EU and will provide further updates accordingly _x000D_29/7/2024:01465564 _x000D_26/7/2024:01465564 _x000D_24/7/2024:#Update - NFA - Allwyn confirmed new install date 19/07 with retailer _x000D_23/7/2024:#Update - NFA - Allwyn confirmed new install date 19/07 with retailer _x000D_22/7/2024:#Update - NFA - Allwyn confirmed new install date 19/07 with retailer _x000D_22/7/2024:#Update - NFA - Allwyn confirmed new install date 19/07 with retailer _x000D_4/7/2024:Order Completed _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - retailer out of country and cannot confirm access - install date pushed out; customer to liaise with retailer when they return and feedback to CSL _x000D_6/9/2024:#Update - retailer out of country and cannot confirm access - install date pushed out; customer to liaise with retailer when they return and feedback to CSL _x000D_5/9/2024:#Update - retailer out of country and cannot confirm access - install date pushed out; customer to liaise with retailer when they return and feedback to CSL _x000D_4/9/2024:#Update - retailer out of country and cannot confirm access - install date pushed out; customer to liaise with retailer when they return and feedback to CSL _x000D_3/9/2024:#Update - retailer out of country and cannot confirm access - install date pushed out; customer to liaise with retailer when they return and feedback to CSL _x000D_2/9/2024:#Update - retailer out of country and cannot confirm access - install date pushed out; customer to liaise with retailer when they return and feedback to CSL _x000D_29/8/2024:#Update - retailer out of country and cannot confirm access - install date pushed out; customer to liaise with retailer when they return and feedback to CSL _x000D_28/8/2024:#Update - retailer out of country and cannot confirm access - install date pushed out; customer to liaise with retailer when they return and feedback to CSL _x000D_27/8/2024:#Update - retailer out of country and cannot confirm access - install date pushed out; customer to liaise with retailer when they return and feedback to CSL _x000D_22/8/2024:#Update - retailer out of country and cannot confirm access - install date pushed out; customer to liaise with retailer when they return and feedback to CSL _x000D_21/8/2024:#Update - retailer out of country and cannot confirm access - install date pushed out; customer to liaise with retailer when they return and feedback to CSL _x000D_20/8/2024:#Update - installation unsuccessful: Line plant access issue needs to be resolved to complete this job. Unable to access Beyond the DP. Openreach requested PTW from third party/EU and will provide further updates accordingly _x000D_19/8/2024:#Update - installation unsuccessful: Line plant access issue needs to be resolved to complete this job. Unable to access Beyond the DP. Openreach requested PTW from third party/EU and will provide further updates accordingly _x000D_19/8/2024:01465564 _x000D_16/8/2024:#Update - installation unsuccessful: Line plant access issue needs to be resolved to complete this job. Unable to access Beyond the DP. Openreach requested PTW from third party/EU and will provide further updates accordingly _x000D_15/8/2024:#Update - installation unsuccessful: Line plant access issue needs to be resolved to complete this job. Unable to access Beyond the DP. Openreach requested PTW from third party/EU and will provide further updates accordingly _x000D_14/8/2024:#Update - installation unsuccessful: Line plant access issue needs to be resolved to complete this job. Unable to access Beyond the DP. Openreach requested PTW from third party/EU and will provide further updates accordingly _x000D_13/8/2024:#Update - installation unsuccessful: Line plant access issue needs to be resolved to complete this job. Unable to access Beyond the DP. Openreach requested PTW from third party/EU and will provide further updates accordingly _x000D_12/8/2024:#Update - installation unsuccessful: Line plant access issue needs to be resolved to complete this job. Unable to access Beyond the DP. Openreach requested PTW from third party/EU and will provide further updates accordingly _x000D_9/8/2024:#Update - installation unsuccessful: Line plant access issue needs to be resolved to complete this job. Unable to access Beyond the DP. Openreach requested PTW from third party/EU and will provide further updates accordingly _x000D_8/8/2024:25/07/2024 _x000D_6/8/2024:25/07/2024 _x000D_5/8/2024:25/07/2024 _x000D_2/8/2024:25/07/2024 _x000D_1/8/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_30/7/2024:#Update - installation unsuccessful: Line plant access issue needs to be resolved to complete this job. Unable to access Beyond the DP. Openreach requested PTW from third party/EU and will provide further updates accordingly _x000D_29/7/2024:#Update - installation unsuccessful: Line plant access issue needs to be resolved to complete this job. Unable to access Beyond the DP. Openreach requested PTW from third party/EU and will provide further updates accordingly _x000D_29/7/2024:01465564 _x000D_26/7/2024:01465564 _x000D_24/7/2024:#Update - NFA - Allwyn confirmed new install date 19/07 with retailer _x000D_23/7/2024:#Update - NFA - Allwyn confirmed new install date 19/07 with retailer _x000D_22/7/2024:#Update - NFA - Allwyn confirmed new install date 19/07 with retailer _x000D_22/7/2024:#Update - NFA - Allwyn confirmed new install date 19/07 with retailer _x000D_4/7/2024:Order Completed _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update - retailer out of country and cannot confirm access - install date pushed out; customer to liaise with retailer when they return and feedback to CSL | 2024-06-07 |  |  |  | 5.CSL | VFS1013041 | 30016422 | 1.Provisioning | AM |  | 2024-07-03 | 2024-08-23 |  | 0 | [11 empty] | 0
969 | 624618 | 3570 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Windmill Stores Premier | London | SE16 3JU |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:40 _x000D_26/7/2024:22/07/2024 10:40 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_4/7/2024:Order Completed _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:40 _x000D_26/7/2024:22/07/2024 10:40 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_4/7/2024:Order Completed _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2363485 | 30016313 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
970 | 460576 | 3572 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | FreshGo | LONDON | SE19 1QL | 2024-07-04 | 6/9/2024:#Update - install unsuccessful - no access, no site contact present _x000D_5/9/2024:#Update - hard dig required. New ducting required and heavy lifter required. This order is with our third party supplier and we will provide updates accordingly _x000D_4/9/2024:#Update - hard dig required. New ducting required and heavy lifter required. This order is with our third party supplier and we will provide updates accordingly _x000D_3/9/2024:#Update - hard dig required. New ducting required and heavy lifter required. This order is with our third party supplier and we will provide updates accordingly _x000D_2/9/2024:#Update - hard dig required. New ducting required and heavy lifter required. This order is with our third party supplier and we will provide updates accordingly _x000D_29/8/2024:#Update - hard dig required. New ducting required and heavy lifter required. This order is with our third party supplier and we will provide updates accordingly _x000D_28/8/2024:#Update - hard dig required. New ducting required and heavy lifter required. This order is with our third party supplier and we will provide updates accordingly _x000D_27/8/2024:#Update - hard dig required. New ducting required and heavy lifter required. This order is with our third party supplier and we will provide updates accordingly _x000D_22/8/2024:#Update - hard dig required. New ducting required and heavy lifter required. This order is with our third party supplier and we will provide updates accordingly _x000D_21/8/2024:#Update - hard dig required. New ducting required and heavy lifter required. This order is with our third party supplier and we will provide updates accordingly _x000D_20/8/2024:#Update - hard dig required. New ducting required and heavy lifter required. This order is with our third party supplier and we will provide updates accordingly _x000D_19/8/2024:#Update - hard dig required. New ducting required and heavy lifter required. This order is with our third party supplier and we will provide updates accordingly _x000D_19/8/2024:01467052 _x000D_16/8/2024:#Update - hard dig required. New ducting required and heavy lifter required. This order is with our third party supplier and we will provide updates accordingly _x000D_15/8/2024:#Update - hard dig required. New ducting required and heavy lifter required. This order is with our third party supplier and we will provide updates accordingly _x000D_14/8/2024:#Update - hard dig required. New ducting required and heavy lifter required. This order is with our third party supplier and we will provide updates accordingly _x000D_13/8/2024:#Update - hard dig required. New ducting required and heavy lifter required. This order is with our third party supplier and we will provide updates accordingly _x000D_12/8/2024:#Update - hard dig required. New ducting required and heavy lifter required. This order is with our third party supplier and we will provide updates accordingly _x000D_9/8/2024:#Update - hard dig required. New ducting required and heavy lifter required. This order is with our third party supplier and we will provide updates accordingly _x000D_8/8/2024:23/07/2024 _x000D_6/8/2024:23/07/2024 _x000D_5/8/2024:23/07/2024 _x000D_2/8/2024:23/07/2024 _x000D_1/8/2024:23/07/2024 _x000D_31/7/2024:23/07/2024 _x000D_31/7/2024:23/07/2024 _x000D_30/7/2024:#Update - hard dig required. New ducting required and heavy lifter required. This order is with our third party supplier and we will provide updates accordingly _x000D_29/7/2024:#Update - hard dig required. New ducting required and heavy lifter required. This order is with our third party supplier and we will provide updates accordingly _x000D_29/7/2024:01467052 _x000D_26/7/2024:01467052 _x000D_24/7/2024:#Update - hard dig required. New ducting required and heavy lifter required. This order is with our third party supplier and we will provide updates accordingly _x000D_23/7/2024:#Update - hard dig required. New ducting required and heavy lifter required. This order is with our third party supplier and we will provide updates accordingly _x000D_22/7/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_22/7/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_4/7/2024:Order Completed _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - install unsuccessful - no access, no site contact present _x000D_6/9/2024:#Update - install unsuccessful - no access, no site contact present _x000D_5/9/2024:#Update - hard dig required. New ducting required and heavy lifter required. This order is with our third party supplier and we will provide updates accordingly _x000D_4/9/2024:#Update - hard dig required. New ducting required and heavy lifter required. This order is with our third party supplier and we will provide updates accordingly _x000D_3/9/2024:#Update - hard dig required. New ducting required and heavy lifter required. This order is with our third party supplier and we will provide updates accordingly _x000D_2/9/2024:#Update - hard dig required. New ducting required and heavy lifter required. This order is with our third party supplier and we will provide updates accordingly _x000D_29/8/2024:#Update - hard dig required. New ducting required and heavy lifter required. This order is with our third party supplier and we will provide updates accordingly _x000D_28/8/2024:#Update - hard dig required. New ducting required and heavy lifter required. This order is with our third party supplier and we will provide updates accordingly _x000D_27/8/2024:#Update - hard dig required. New ducting required and heavy lifter required. This order is with our third party supplier and we will provide updates accordingly _x000D_22/8/2024:#Update - hard dig required. New ducting required and heavy lifter required. This order is with our third party supplier and we will provide updates accordingly _x000D_21/8/2024:#Update - hard dig required. New ducting required and heavy lifter required. This order is with our third party supplier and we will provide updates accordingly _x000D_20/8/2024:#Update - hard dig required. New ducting required and heavy lifter required. This order is with our third party supplier and we will provide updates accordingly _x000D_19/8/2024:#Update - hard dig required. New ducting required and heavy lifter required. This order is with our third party supplier and we will provide updates accordingly _x000D_19/8/2024:01467052 _x000D_16/8/2024:#Update - hard dig required. New ducting required and heavy lifter required. This order is with our third party supplier and we will provide updates accordingly _x000D_15/8/2024:#Update - hard dig required. New ducting required and heavy lifter required. This order is with our third party supplier and we will provide updates accordingly _x000D_14/8/2024:#Update - hard dig required. New ducting required and heavy lifter required. This order is with our third party supplier and we will provide updates accordingly _x000D_13/8/2024:#Update - hard dig required. New ducting required and heavy lifter required. This order is with our third party supplier and we will provide updates accordingly _x000D_12/8/2024:#Update - hard dig required. New ducting required and heavy lifter required. This order is with our third party supplier and we will provide updates accordingly _x000D_9/8/2024:#Update - hard dig required. New ducting required and heavy lifter required. This order is with our third party supplier and we will provide updates accordingly _x000D_8/8/2024:23/07/2024 _x000D_6/8/2024:23/07/2024 _x000D_5/8/2024:23/07/2024 _x000D_2/8/2024:23/07/2024 _x000D_1/8/2024:23/07/2024 _x000D_31/7/2024:23/07/2024 _x000D_31/7/2024:23/07/2024 _x000D_30/7/2024:#Update - hard dig required. New ducting required and heavy lifter required. This order is with our third party supplier and we will provide updates accordingly _x000D_29/7/2024:#Update - hard dig required. New ducting required and heavy lifter required. This order is with our third party supplier and we will provide updates accordingly _x000D_29/7/2024:01467052 _x000D_26/7/2024:01467052 _x000D_24/7/2024:#Update - hard dig required. New ducting required and heavy lifter required. This order is with our third party supplier and we will provide updates accordingly _x000D_23/7/2024:#Update - hard dig required. New ducting required and heavy lifter required. This order is with our third party supplier and we will provide updates accordingly _x000D_22/7/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_22/7/2024:#Update - NFA - Allwyn confirmed new installation date of 19/07 with retailer _x000D_4/7/2024:Order Completed _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | #Update - install unsuccessful - no access, no site contact present | 2024-06-07 |  |  |  | 5.CSL | VFP2363484 | 30016241 | 1.Provisioning | AM |  | 2024-07-03 | 2024-07-19 |  | 0 | [11 empty] | 0
971 | 436979 | 3576 | Batch 5 Jul24 | Type 1 | SOGEA | Spar Sanco Badsey | EVESHAM | WR11 7EW | 2024-07-04 | 19/7/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_18/7/2024:#Update - Supplier Delay: Network Planning - this order has been sent to the survey group - further updates to follow _x000D_17/7/2024:#Update - Supplier Delay: Network Planning - this order has been sent to the survey group - further updates to follow _x000D_16/7/2024:#Update - Supplier Delay: Network Planning - this order has been sent to the survey group - further updates to follow _x000D_15/7/2024:#Update - Supplier Delay: Network Planning - this order has been sent to the survey group - further updates to follow _x000D_12/7/2024:#Update - Supplier Delay: Network Planning - this order has been sent to the survey group - further updates to follow _x000D_11/7/2024:#Update - Supplier Delay: Network Planning - this order has been sent to the survey group - further updates to follow _x000D_10/7/2024:#Update - Supplier Delay: Network Planning - this order has been sent to the survey group - further updates to follow _x000D_9/7/2024:#Update - Supplier Delay: Network Planning - this order has been sent to the survey group - further updates to follow _x000D_4/7/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_3/7/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_18/7/2024:#Update - Supplier Delay: Network Planning - this order has been sent to the survey group - further updates to follow _x000D_17/7/2024:#Update - Supplier Delay: Network Planning - this order has been sent to the survey group - further updates to follow _x000D_16/7/2024:#Update - Supplier Delay: Network Planning - this order has been sent to the survey group - further updates to follow _x000D_15/7/2024:#Update - Supplier Delay: Network Planning - this order has been sent to the survey group - further updates to follow _x000D_12/7/2024:#Update - Supplier Delay: Network Planning - this order has been sent to the survey group - further updates to follow _x000D_11/7/2024:#Update - Supplier Delay: Network Planning - this order has been sent to the survey group - further updates to follow _x000D_10/7/2024:#Update - Supplier Delay: Network Planning - this order has been sent to the survey group - further updates to follow _x000D_9/7/2024:#Update - Supplier Delay: Network Planning - this order has been sent to the survey group - further updates to follow _x000D_4/7/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_3/7/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1013033 | 30016543 | 6.Failed router install |  |  | 2024-07-03 | 2024-07-03 | 2024-07-03 | TRUE |  |  |  | 2024-07-25 |  |  |  | 2024-07-25 | 239004929547 |  | 2024-07-26 | 1
972 | 479672 | 3577 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Budgens | MINSTER ON SEA | ME12 3QN | 2024-07-04 | 6/9/2024:#Update - order delayed due to build work required. We will continue to provide updates as they become available. _x000D_5/9/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_4/9/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_3/9/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_2/9/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_29/8/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_28/8/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_27/8/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_22/8/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_21/8/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_20/8/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_19/8/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_19/8/2024:01465598 _x000D_16/8/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_15/8/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_14/8/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_13/8/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_12/8/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_9/8/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_8/8/2024:18/07/2024 _x000D_6/8/2024:18/07/2024 _x000D_5/8/2024:18/07/2024 _x000D_2/8/2024:18/07/2024 _x000D_1/8/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_30/7/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_29/7/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_29/7/2024:01465598 _x000D_26/7/2024:01465598 _x000D_24/7/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_23/7/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_22/7/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_22/7/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_4/7/2024:Order Completed _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - order delayed due to build work required. We will continue to provide updates as they become available. _x000D_6/9/2024:#Update - order delayed due to build work required. We will continue to provide updates as they become available. _x000D_5/9/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_4/9/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_3/9/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_2/9/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_29/8/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_28/8/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_27/8/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_22/8/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_21/8/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_20/8/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_19/8/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_19/8/2024:01465598 _x000D_16/8/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_15/8/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_14/8/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_13/8/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_12/8/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_9/8/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_8/8/2024:18/07/2024 _x000D_6/8/2024:18/07/2024 _x000D_5/8/2024:18/07/2024 _x000D_2/8/2024:18/07/2024 _x000D_1/8/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_30/7/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_29/7/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_29/7/2024:01465598 _x000D_26/7/2024:01465598 _x000D_24/7/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_23/7/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_22/7/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_22/7/2024:#Update - order is delayed as build work required. Our Suppliers have given us a review date of 13/08 - we will continue to provide update accordingly _x000D_4/7/2024:Order Completed _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Your order has been delayed due to Build work required. Our Suppliers have given us a estimate completion date of 25/09/2024 and given us a review date of 12/09/2024. We will continue to provide update as they become available. | #Update - order delayed due to build work required. We will continue to provide updates as they become available. | 2024-06-07 |  |  |  | 5.CSL | VFP2363483 | 30016329 | 1.Provisioning | AM |  | 2024-07-03 | 2024-07-03 |  | 0 | [11 empty] | 0
973 | 486008 | 3579 | Batch 5 Jul24 | Type 1 | SOGEA | Costcutter | Paisley | PA3 4RL | 2024-07-04 | 4/7/2024:Order Completed _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 4/7/2024:Order Completed _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1013035 | 30016434 | 6.Failed router install |  |  | 2024-07-03 | 2024-07-03 | 2024-07-03 | TRUE |  |  |  | 2024-07-25 |  |  |  | 2024-07-25 | 23A004948499 |  | 2024-07-26 | 1
974 | 621073 | 3582 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Costcutter | Manchester | M26 4HD |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 11:29 _x000D_26/7/2024:22/07/2024 11:29 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 10/07/2024.We will continue to provide update as they become available. _x000D_10/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 10/07/2024.We will continue to provide update as they become available. _x000D_9/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 10/07/2024.We will continue to provide update as they become available. _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 11:29 _x000D_26/7/2024:22/07/2024 11:29 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 10/07/2024.We will continue to provide update as they become available. _x000D_10/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 10/07/2024.We will continue to provide update as they become available. _x000D_9/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 10/07/2024.We will continue to provide update as they become available. _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2363482 | 30016335 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
975 | 670578 | 3583 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Nisa Local | Peterborough | PE7 3RF | 2024-07-04 | 6/9/2024:#Update - Awaiting Approval for ECCS _x000D_5/9/2024:#Update - Awaiting Approval for ECCS _x000D_4/9/2024:#Update - Awaiting Approval for ECCS _x000D_3/9/2024:#Update - Awaiting Approval for ECCS _x000D_2/9/2024:#Update - Awaiting Approval for ECCS _x000D_29/8/2024:#Update - Awaiting Approval for ECCS _x000D_28/8/2024:#Update - Awaiting Approval for ECCS _x000D_27/8/2024:#Update - Awaiting Approval for ECCS _x000D_22/8/2024:#Update - Awaiting Approval for ECCS _x000D_21/8/2024:#Update - Awaiting Approval for ECCS _x000D_20/8/2024:#Update - Awaiting Approval for ECCS _x000D_19/8/2024:#Update - Awaiting Approval for ECCS _x000D_19/8/2024:01467610 _x000D_16/8/2024:#Update - Awaiting Approval for ECCS _x000D_15/8/2024:#Update - Awaiting Approval for ECCS _x000D_14/8/2024:#Update - Awaiting Approval for ECCS _x000D_13/8/2024:#Update - Awaiting Approval for ECCS _x000D_12/8/2024:#Update - Awaiting Approval for ECCS _x000D_9/8/2024:#Update - Awaiting Approval for ECCS _x000D_8/8/2024:23/07/2024 _x000D_6/8/2024:23/07/2024 _x000D_5/8/2024:23/07/2024 _x000D_2/8/2024:23/07/2024 _x000D_1/8/2024:23/07/2024 _x000D_31/7/2024:23/07/2024 _x000D_31/7/2024:23/07/2024 _x000D_30/7/2024:#Update - Awaiting Approval for ECCS _x000D_29/7/2024:#Update - Awaiting Approval for ECCS _x000D_29/7/2024:01467610 _x000D_26/7/2024:01467610 _x000D_24/7/2024:#Update - Awaiting Approval for ECCS _x000D_23/7/2024:#Update - Awaiting Approval for ECCS _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_4/7/2024:Order Completed _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - Awaiting Approval for ECCS _x000D_6/9/2024:#Update - Awaiting Approval for ECCS _x000D_5/9/2024:#Update - Awaiting Approval for ECCS _x000D_4/9/2024:#Update - Awaiting Approval for ECCS _x000D_3/9/2024:#Update - Awaiting Approval for ECCS _x000D_2/9/2024:#Update - Awaiting Approval for ECCS _x000D_29/8/2024:#Update - Awaiting Approval for ECCS _x000D_28/8/2024:#Update - Awaiting Approval for ECCS _x000D_27/8/2024:#Update - Awaiting Approval for ECCS _x000D_22/8/2024:#Update - Awaiting Approval for ECCS _x000D_21/8/2024:#Update - Awaiting Approval for ECCS _x000D_20/8/2024:#Update - Awaiting Approval for ECCS _x000D_19/8/2024:#Update - Awaiting Approval for ECCS _x000D_19/8/2024:01467610 _x000D_16/8/2024:#Update - Awaiting Approval for ECCS _x000D_15/8/2024:#Update - Awaiting Approval for ECCS _x000D_14/8/2024:#Update - Awaiting Approval for ECCS _x000D_13/8/2024:#Update - Awaiting Approval for ECCS _x000D_12/8/2024:#Update - Awaiting Approval for ECCS _x000D_9/8/2024:#Update - Awaiting Approval for ECCS _x000D_8/8/2024:23/07/2024 _x000D_6/8/2024:23/07/2024 _x000D_5/8/2024:23/07/2024 _x000D_2/8/2024:23/07/2024 _x000D_1/8/2024:23/07/2024 _x000D_31/7/2024:23/07/2024 _x000D_31/7/2024:23/07/2024 _x000D_30/7/2024:#Update - Awaiting Approval for ECCS _x000D_29/7/2024:#Update - Awaiting Approval for ECCS _x000D_29/7/2024:01467610 _x000D_26/7/2024:01467610 _x000D_24/7/2024:#Update - Awaiting Approval for ECCS _x000D_23/7/2024:#Update - Awaiting Approval for ECCS _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_4/7/2024:Order Completed _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update - Awaiting Approval for ECCS | 2024-06-07 |  |  |  | 5.CSL | VFP2363481 | 30016338 | 1.Provisioning | AM |  | 2024-07-03 | 2024-08-29 |  | 0 | [11 empty] | 0
976 | 668022 | 3587 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | PREMIER KEELE ROAD STORES | NEWCASTLE | ST5 2JX | 2024-07-04 | 6/9/2024:#Update - Looks like the engineer needs certail fixtures removed or moved out of the way in order to complete. Re-appointed for 30/09. Awaiting info from allwyn, in order to proceed. May need a possible upgrade? _x000D_5/9/2024:#Update - Looks like the engineer needs certail fixtures removed or moved out of the way in order to complete. Re-appointed for 30/09. Awaiting info from allwyn, in order to proceed. May need a possible upgrade? _x000D_4/9/2024:#Update - Pushed this out for 27/08 - Allwyn unable to contact retailer yet _x000D_3/9/2024:#Update - Pushed this out for 27/08 - Allwyn unable to contact retailer yet _x000D_2/9/2024:#Update - Pushed this out for 27/08 - Allwyn unable to contact retailer yet _x000D_29/8/2024:#Update - Pushed this out for 27/08 - Allwyn unable to contact retailer yet _x000D_28/8/2024:#Update - Pushed this out for 27/08 - Allwyn unable to contact retailer yet _x000D_27/8/2024:#Update - Pushed this out for 27/08 - Allwyn unable to contact retailer yet _x000D_22/8/2024:#Update - Pushed this out for 27/08 - Allwyn unable to contact retailer yet _x000D_21/8/2024:#Update - Pushed this out for 27/08 - Allwyn unable to contact retailer yet _x000D_20/8/2024:#Update - Pushed this out for 27/08 - Allwyn unable to contact retailer yet _x000D_19/8/2024:#Update - Pushed this out for 27/08 - Allwyn unable to contact retailer yet _x000D_19/8/2024:01466942 _x000D_16/8/2024:#Update - Pushed this out for 27/08 - Allwyn unable to contact retailer yet _x000D_15/8/2024:#Update - Pushed this out for 27/08 - Allwyn unable to contact retailer yet _x000D_14/8/2024:#Update - Pushed this out for 27/08 - Allwyn unable to contact retailer yet _x000D_13/8/2024:#Update - Pushed this out for 27/08 - Allwyn unable to contact retailer yet _x000D_12/8/2024:#Update - Pushed this out for 27/08 - Allwyn unable to contact retailer yet _x000D_9/8/2024:#Update - Pushed this out for 27/08 - Allwyn unable to contact retailer yet _x000D_8/8/2024:31/07/2024 _x000D_6/8/2024:31/07/2024 _x000D_5/8/2024:31/07/2024 _x000D_2/8/2024:31/07/2024 _x000D_1/8/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_30/7/2024:#Update - Allwyn have emailed the retailer. Date TBC- May have to push this out. Awaiting retailer confirmation and they will let me know once thats recieved, _x000D_29/7/2024:#Update - Retailer unaware - Action for allwyn: Please confirm reappoint for 29/07 am. _x000D_29/7/2024:01466942 _x000D_26/7/2024:01466942 _x000D_24/7/2024:#Update - Retailer unaware - Action for allwyn: Please confirm reappoint for 29/07 am. _x000D_23/7/2024:#Update - Retailer unaware - Action for allwyn: Please confirm reappoint for 29/07 am. _x000D_22/7/2024:#Update - Retailer unaware - Action for allwyn: Please confirm reappoint for 29/07 am. _x000D_22/7/2024:#Update - Retailer unaware - Action for allwyn: Please confirm reappoint for 29/07 am. _x000D_4/7/2024:Order Completed _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - Looks like the engineer needs certail fixtures removed or moved out of the way in order to complete. Re-appointed for 30/09. Awaiting info from allwyn, in order to proceed. May need a possible upgrade? _x000D_6/9/2024:#Update - Looks like the engineer needs certail fixtures removed or moved out of the way in order to complete. Re-appointed for 30/09. Awaiting info from allwyn, in order to proceed. May need a possible upgrade? _x000D_5/9/2024:#Update - Looks like the engineer needs certail fixtures removed or moved out of the way in order to complete. Re-appointed for 30/09. Awaiting info from allwyn, in order to proceed. May need a possible upgrade? _x000D_4/9/2024:#Update - Pushed this out for 27/08 - Allwyn unable to contact retailer yet _x000D_3/9/2024:#Update - Pushed this out for 27/08 - Allwyn unable to contact retailer yet _x000D_2/9/2024:#Update - Pushed this out for 27/08 - Allwyn unable to contact retailer yet _x000D_29/8/2024:#Update - Pushed this out for 27/08 - Allwyn unable to contact retailer yet _x000D_28/8/2024:#Update - Pushed this out for 27/08 - Allwyn unable to contact retailer yet _x000D_27/8/2024:#Update - Pushed this out for 27/08 - Allwyn unable to contact retailer yet _x000D_22/8/2024:#Update - Pushed this out for 27/08 - Allwyn unable to contact retailer yet _x000D_21/8/2024:#Update - Pushed this out for 27/08 - Allwyn unable to contact retailer yet _x000D_20/8/2024:#Update - Pushed this out for 27/08 - Allwyn unable to contact retailer yet _x000D_19/8/2024:#Update - Pushed this out for 27/08 - Allwyn unable to contact retailer yet _x000D_19/8/2024:01466942 _x000D_16/8/2024:#Update - Pushed this out for 27/08 - Allwyn unable to contact retailer yet _x000D_15/8/2024:#Update - Pushed this out for 27/08 - Allwyn unable to contact retailer yet _x000D_14/8/2024:#Update - Pushed this out for 27/08 - Allwyn unable to contact retailer yet _x000D_13/8/2024:#Update - Pushed this out for 27/08 - Allwyn unable to contact retailer yet _x000D_12/8/2024:#Update - Pushed this out for 27/08 - Allwyn unable to contact retailer yet _x000D_9/8/2024:#Update - Pushed this out for 27/08 - Allwyn unable to contact retailer yet _x000D_8/8/2024:31/07/2024 _x000D_6/8/2024:31/07/2024 _x000D_5/8/2024:31/07/2024 _x000D_2/8/2024:31/07/2024 _x000D_1/8/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_30/7/2024:#Update - Allwyn have emailed the retailer. Date TBC- May have to push this out. Awaiting retailer confirmation and they will let me know once thats recieved, _x000D_29/7/2024:#Update - Retailer unaware - Action for allwyn: Please confirm reappoint for 29/07 am. _x000D_29/7/2024:01466942 _x000D_26/7/2024:01466942 _x000D_24/7/2024:#Update - Retailer unaware - Action for allwyn: Please confirm reappoint for 29/07 am. _x000D_23/7/2024:#Update - Retailer unaware - Action for allwyn: Please confirm reappoint for 29/07 am. _x000D_22/7/2024:#Update - Retailer unaware - Action for allwyn: Please confirm reappoint for 29/07 am. _x000D_22/7/2024:#Update - Retailer unaware - Action for allwyn: Please confirm reappoint for 29/07 am. _x000D_4/7/2024:Order Completed _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update - Looks like the engineer needs certail fixtures removed or moved out of the way in order to complete. Re-appointed for 30/09. Awaiting info from allwyn, in order to proceed. May need a possible upgrade? | 2024-06-07 |  |  |  | 5.CSL | VFP2363478 | 30016224 | 1.Provisioning | AM |  | 2024-07-03 | 2024-08-27 |  | 0 | [11 empty] | 0
977 | 655949 | 3588 | Batch 5 Jul24 | Type 1 | FTTP | Londis Bainsford | Falkirk | FK2 7PA | 2024-07-04 | 4/7/2024:Order Completed _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 4/7/2024:Order Completed _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFP2363476 | 30016279 | 6.Failed router install |  |  | 2024-07-03 | 2024-07-03 | 2024-07-03 | TRUE |  |  |  | 2024-07-24 |  |  |  | 2024-07-24 | 242005008952 |  | 2024-07-25 | 1
978 | 637706 | 3590 | Batch 5 Jul24 | Type 1 | FTTP | Premier CJs Supermarket | Grimsby | DN32 8BJ | 2024-07-04 | 6/9/2024:#Update - Supplier system delay, review date of 04/09/2024 _x000D_19/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_18/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_17/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_16/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_15/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_12/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_11/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_10/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_9/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_4/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_3/7/2024:End User Missed appointment. Action required _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - Supplier system delay, review date of 04/09/2024 _x000D_6/9/2024:#Update - Supplier system delay, review date of 04/09/2024 _x000D_19/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_18/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_17/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_16/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_15/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_12/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_11/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_10/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_9/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_4/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_3/7/2024:End User Missed appointment. Action required _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update - Supplier system delay, review date of 04/09/2024 | 2024-06-07 |  |  |  |  | VFS1029985 | 30016352 | 2.Commissioning |  |  | 2024-07-03 | 2024-07-03 | 2024-07-03 | TRUE |  |  |  | 2024-07-23 | [7 empty] | 0
979 | 472358 | 3593 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | VG Stores Premier | Ardrossan | KA22 8EZ |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:56 _x000D_26/7/2024:22/07/2024 10:56 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Retailer aware of new appointment for 24/07 - AM _x000D_18/7/2024:#Update - Retailer aware of new appointment for 24/07 - AM _x000D_17/7/2024:#Update - Retailer aware of new appointment for 24/07 - AM _x000D_16/7/2024:#Update - Re-appointed for 24/07. Action for allwyn : Please confirm new appointment of 24/07 AM _x000D_15/7/2024:#Update - Re-appointed for 24/07. Action for allwyn : Please confirm new appointment of 24/07 AM _x000D_12/7/2024:#Update - Re-appointed for 24/07. Action for allwyn : Please confirm new appointment of 24/07 AM _x000D_11/7/2024:#Update - Re-appointed for 24/07. Action for allwyn : Please confirm new appointment of 24/07 AM _x000D_10/7/2024:#Update - Re-appointed for 24/07. Action for allwyn : Please confirm new appointment of 24/07 AM _x000D_9/7/2024:#Update - Re-appointed for 24/07. Action for allwyn : Please confirm new appointment of 24/07 AM _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:56 _x000D_26/7/2024:22/07/2024 10:56 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Retailer aware of new appointment for 24/07 - AM _x000D_18/7/2024:#Update - Retailer aware of new appointment for 24/07 - AM _x000D_17/7/2024:#Update - Retailer aware of new appointment for 24/07 - AM _x000D_16/7/2024:#Update - Re-appointed for 24/07. Action for allwyn : Please confirm new appointment of 24/07 AM _x000D_15/7/2024:#Update - Re-appointed for 24/07. Action for allwyn : Please confirm new appointment of 24/07 AM _x000D_12/7/2024:#Update - Re-appointed for 24/07. Action for allwyn : Please confirm new appointment of 24/07 AM _x000D_11/7/2024:#Update - Re-appointed for 24/07. Action for allwyn : Please confirm new appointment of 24/07 AM _x000D_10/7/2024:#Update - Re-appointed for 24/07. Action for allwyn : Please confirm new appointment of 24/07 AM _x000D_9/7/2024:#Update - Re-appointed for 24/07. Action for allwyn : Please confirm new appointment of 24/07 AM _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2363475 | 30016193 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
980 | 658791 | 3595 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | St Margarets Express | Leicester | LE1 3AG | 2024-07-04 | 6/9/2024:#Update - address verification issues, VF raised with Allwyn 28/08 - will reraise order when resolved _x000D_5/9/2024:#Update - address verification issues, VF raised with Allwyn 28/08 - will reraise order when resolved _x000D_4/9/2024:#Update - address verification issues, VF raised with Allwyn 28/08 - will reraise order when resolved _x000D_3/9/2024:#Update - address verification issues, VF raised with Allwyn 28/08 - will reraise order when resolved _x000D_2/9/2024:#Update - address verification issues, VF raised with Allwyn 28/08 - will reraise order when resolved _x000D_29/8/2024:#Update - address verification issues, VF raised with Allwyn 28/08 - will reraise order when resolved _x000D_28/8/2024:#Update - address verification issues, VF raised with Allwyn 28/08 - will reraise order when resolved _x000D_27/8/2024:#Update - address verification required, retailer confirmed they will register their address with Royal Mail. Once this has been done the order can progress _x000D_22/8/2024:#Update - address verification required, retailer confirmed they will register their address with Royal Mail. Once this has been done the order can progress _x000D_21/8/2024:#Update - address verification required, retailer confirmed they will register their address with Royal Mail. Once this has been done the order can progress _x000D_20/8/2024:#Update - DP behind partition wall, engineer unable to gain access to DP to complete install - Allwyn to confirm with retailer that access will be available on the rescheduled install date of 23/08 - AM _x000D_19/8/2024:#Update - DP behind partition wall, engineer unable to gain access to DP to complete install - Allwyn to confirm with retailer that access will be available on the rescheduled install date of 23/08 - AM _x000D_19/8/2024:01503264 _x000D_16/8/2024:#Update - DP behind partition wall, engineer unable to gain access to DP to complete install - Allwyn to confirm with retailer that access will be available on the rescheduled install date of 23/08 - AM _x000D_15/8/2024:#Update - DP behind partition wall, engineer unable to gain access to DP to complete install - Allwyn to confirm with retailer that access will be available on the rescheduled install date of 23/08 - AM _x000D_14/8/2024:#Update - DP behind partition wall, engineer unable to gain access to DP to complete install - Allwyn to confirm with retailer that access will be available on the rescheduled install date of 23/08 - AM _x000D_13/8/2024:#Update - DP behind partition wall, engineer unable to gain access to DP to complete install - Allwyn to confirm with retailer that access will be available on the rescheduled install date of 23/08 - AM _x000D_12/8/2024:#Update - DP behind partition wall, engineer unable to gain access to DP to complete install - Allwyn to confirm with retailer that access will be available on the rescheduled install date of 23/08 - AM _x000D_9/8/2024:#Update - DP behind partition wall, engineer unable to gain access to DP to complete install - Allwyn to confirm with retailer that access will be available on the rescheduled install date of 23/08 - AM _x000D_8/8/2024:05/08/2024 _x000D_6/8/2024:05/08/2024 _x000D_5/8/2024:22/07/2024 _x000D_2/8/2024:22/07/2024 _x000D_1/8/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_30/7/2024:#Update - NFA - Allwyn have confirmed rescheduled installation date 02/08 with retailer _x000D_29/7/2024:#Update - NFA - Allwyn have confirmed rescheduled installation date 02/08 with retailer _x000D_29/7/2024:01503264 _x000D_26/7/2024:01503264 _x000D_24/7/2024:#Update - NFA - Allwyn have confirmed rescheduled installation date 02/08 with retailer _x000D_23/7/2024:#Update - NFA - Allwyn have confirmed rescheduled installation date 02/08 with retailer _x000D_22/7/2024:#Update - NFA - Allwyn have confirmed rescheduled installation date 02/08 with retailer _x000D_22/7/2024:End User Missed appointment. Action required _x000D_19/7/2024:#Update - NFA - Allwyn have confirmed new installation date with retailer of 19/07 - AM _x000D_18/7/2024:#Update - NFA - Allwyn have confirmed new installation date with retailer of 19/07 - AM _x000D_17/7/2024:#Update - NFA - Allwyn have confirmed new installation date with retailer of 19/07 - AM _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_10/7/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_9/7/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - address verification issues, VF raised with Allwyn 28/08 - will reraise order when resolved _x000D_6/9/2024:#Update - address verification issues, VF raised with Allwyn 28/08 - will reraise order when resolved _x000D_5/9/2024:#Update - address verification issues, VF raised with Allwyn 28/08 - will reraise order when resolved _x000D_4/9/2024:#Update - address verification issues, VF raised with Allwyn 28/08 - will reraise order when resolved _x000D_3/9/2024:#Update - address verification issues, VF raised with Allwyn 28/08 - will reraise order when resolved _x000D_2/9/2024:#Update - address verification issues, VF raised with Allwyn 28/08 - will reraise order when resolved _x000D_29/8/2024:#Update - address verification issues, VF raised with Allwyn 28/08 - will reraise order when resolved _x000D_28/8/2024:#Update - address verification issues, VF raised with Allwyn 28/08 - will reraise order when resolved _x000D_27/8/2024:#Update - address verification required, retailer confirmed they will register their address with Royal Mail. Once this has been done the order can progress _x000D_22/8/2024:#Update - address verification required, retailer confirmed they will register their address with Royal Mail. Once this has been done the order can progress _x000D_21/8/2024:#Update - address verification required, retailer confirmed they will register their address with Royal Mail. Once this has been done the order can progress _x000D_20/8/2024:#Update - DP behind partition wall, engineer unable to gain access to DP to complete install - Allwyn to confirm with retailer that access will be available on the rescheduled install date of 23/08 - AM _x000D_19/8/2024:#Update - DP behind partition wall, engineer unable to gain access to DP to complete install - Allwyn to confirm with retailer that access will be available on the rescheduled install date of 23/08 - AM _x000D_19/8/2024:01503264 _x000D_16/8/2024:#Update - DP behind partition wall, engineer unable to gain access to DP to complete install - Allwyn to confirm with retailer that access will be available on the rescheduled install date of 23/08 - AM _x000D_15/8/2024:#Update - DP behind partition wall, engineer unable to gain access to DP to complete install - Allwyn to confirm with retailer that access will be available on the rescheduled install date of 23/08 - AM _x000D_14/8/2024:#Update - DP behind partition wall, engineer unable to gain access to DP to complete install - Allwyn to confirm with retailer that access will be available on the rescheduled install date of 23/08 - AM _x000D_13/8/2024:#Update - DP behind partition wall, engineer unable to gain access to DP to complete install - Allwyn to confirm with retailer that access will be available on the rescheduled install date of 23/08 - AM _x000D_12/8/2024:#Update - DP behind partition wall, engineer unable to gain access to DP to complete install - Allwyn to confirm with retailer that access will be available on the rescheduled install date of 23/08 - AM _x000D_9/8/2024:#Update - DP behind partition wall, engineer unable to gain access to DP to complete install - Allwyn to confirm with retailer that access will be available on the rescheduled install date of 23/08 - AM _x000D_8/8/2024:05/08/2024 _x000D_6/8/2024:05/08/2024 _x000D_5/8/2024:22/07/2024 _x000D_2/8/2024:22/07/2024 _x000D_1/8/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_30/7/2024:#Update - NFA - Allwyn have confirmed rescheduled installation date 02/08 with retailer _x000D_29/7/2024:#Update - NFA - Allwyn have confirmed rescheduled installation date 02/08 with retailer _x000D_29/7/2024:01503264 _x000D_26/7/2024:01503264 _x000D_24/7/2024:#Update - NFA - Allwyn have confirmed rescheduled installation date 02/08 with retailer _x000D_23/7/2024:#Update - NFA - Allwyn have confirmed rescheduled installation date 02/08 with retailer _x000D_22/7/2024:#Update - NFA - Allwyn have confirmed rescheduled installation date 02/08 with retailer _x000D_22/7/2024:End User Missed appointment. Action required _x000D_19/7/2024:#Update - NFA - Allwyn have confirmed new installation date with retailer of 19/07 - AM _x000D_18/7/2024:#Update - NFA - Allwyn have confirmed new installation date with retailer of 19/07 - AM _x000D_17/7/2024:#Update - NFA - Allwyn have confirmed new installation date with retailer of 19/07 - AM _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_10/7/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_9/7/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update - address verification issues, VF raised with Allwyn 28/08 - will reraise order when resolved | 2024-06-07 |  |  |  | 5.CSL | VFS1013026 | 30016570 | 1.Provisioning | AM |  | 2024-07-03 | 2024-08-23 |  | 0 | [11 empty] | 0
981 | 659005 | 3599 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Walker Post Office | Newcastle upon Tyne | NE6 3DJ | 2024-08-14 | 16/8/2024:#Update With OR, potential dig works involved. _x000D_15/8/2024:#Update With OR, potential dig works involved. _x000D_14/8/2024:#Update With OR, potential dig works involved. _x000D_13/8/2024:#Update With OR, potential dig works involved. _x000D_12/8/2024:#Update With OR, potential dig works involved. _x000D_9/8/2024:#Update With OR, potential dig works involved. _x000D_8/8/2024:04/07/2024 _x000D_6/8/2024:04/07/2024 _x000D_5/8/2024:04/07/2024 _x000D_2/8/2024:04/07/2024 _x000D_1/8/2024:04/07/2024 _x000D_31/7/2024:04/07/2024 _x000D_31/7/2024:04/07/2024 _x000D_30/7/2024:#Update With OR, potential dig works involved. _x000D_29/7/2024:#Update With OR, potential dig works involved. _x000D_29/7/2024:01466922 _x000D_26/7/2024:01466922 _x000D_24/7/2024:#Update With OR, potential dig works involved. _x000D_23/7/2024:#Update With OR, potential dig works involved. _x000D_22/7/2024:#Update With OR, potential dig works involved. _x000D_22/7/2024:#Update With OR, potential dig works involved. _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:Update: Order Amended _x000D_17/7/2024:Update: Order Amended _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:Your order has been delayed due to our suppliers being unable to complete the job in required time frame. Please check with the end user and book a new appointment. _x000D_10/7/2024:Your order has been delayed due to our suppliers being unable to complete the job in required time frame. Please check with the end user and book a new appointment. _x000D_9/7/2024:Your order has been delayed due to our suppliers being unable to complete the job in required time frame. Please check with the end user and book a new appointment. _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_19/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_18/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_17/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_14/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_13/6/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/6/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/6/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_7/6/2024:0 _x000D_ | 16/8/2024:#Update With OR, potential dig works involved. _x000D_15/8/2024:#Update With OR, potential dig works involved. _x000D_14/8/2024:#Update With OR, potential dig works involved. _x000D_13/8/2024:#Update With OR, potential dig works involved. _x000D_12/8/2024:#Update With OR, potential dig works involved. _x000D_9/8/2024:#Update With OR, potential dig works involved. _x000D_8/8/2024:04/07/2024 _x000D_6/8/2024:04/07/2024 _x000D_5/8/2024:04/07/2024 _x000D_2/8/2024:04/07/2024 _x000D_1/8/2024:04/07/2024 _x000D_31/7/2024:04/07/2024 _x000D_31/7/2024:04/07/2024 _x000D_30/7/2024:#Update With OR, potential dig works involved. _x000D_29/7/2024:#Update With OR, potential dig works involved. _x000D_29/7/2024:01466922 _x000D_26/7/2024:01466922 _x000D_24/7/2024:#Update With OR, potential dig works involved. _x000D_23/7/2024:#Update With OR, potential dig works involved. _x000D_22/7/2024:#Update With OR, potential dig works involved. _x000D_22/7/2024:#Update With OR, potential dig works involved. _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:Update: Order Amended _x000D_17/7/2024:Update: Order Amended _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:Your order has been delayed due to our suppliers being unable to complete the job in required time frame. Please check with the end user and book a new appointment. _x000D_10/7/2024:Your order has been delayed due to our suppliers being unable to complete the job in required time frame. Please check with the end user and book a new appointment. _x000D_9/7/2024:Your order has been delayed due to our suppliers being unable to complete the job in required time frame. Please check with the end user and book a new appointment. _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_19/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_18/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_17/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_14/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_13/6/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/6/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/6/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 5.CSL | VFP2363469 | 30016203 | 2.Commissioning | AM |  | 2024-07-03 | 2024-08-02 | 2024-08-13 09:20 | 1 | [11 empty] | 0 | 659005
982 | 615912 | 3600 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Spar | Inverness | IV2 7SU | 2024-07-04 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | 0 | 2024-06-07 |  |  |  | 5.CSL | VFS1012852 | 30016601 | 1.Provisioning | AM |  | 2024-07-03 | 2024-08-27 |  | 0 | [11 empty] | 0
983 | 632923 | 3601 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Sholebroke News | Leeds | LS7 3JG |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 19/07 _x000D_18/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 19/07 _x000D_17/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 19/07 _x000D_16/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 19/07 _x000D_15/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 19/07 _x000D_12/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 19/07 _x000D_11/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 19/07 _x000D_10/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 19/07 _x000D_9/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 19/07 _x000D_4/7/2024:End User Missed appointment. Action required _x000D_3/7/2024:End User Missed appointment. Action required _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 19/07 _x000D_18/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 19/07 _x000D_17/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 19/07 _x000D_16/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 19/07 _x000D_15/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 19/07 _x000D_12/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 19/07 _x000D_11/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 19/07 _x000D_10/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 19/07 _x000D_9/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer of 19/07 _x000D_4/7/2024:End User Missed appointment. Action required _x000D_3/7/2024:End User Missed appointment. Action required _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2363470 | 30016332 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
984 | 639041 | 3603 | Batch 5 Jul24 | Type 1 | SOGEA | Tavistock Convenience Store | Manchester | M9 5RD | 2024-07-04 | 4/7/2024:#Update - Order was delayed due to step-1 work. This has now been resolved and appointed for 03/07 AM _x000D_3/7/2024:#Update - Order was delayed due to step-1 work. This has now been resolved and appointed for 03/07 AM _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Order was delayed due to step-1 work. This has now been resolved and appointed for 03/07 AM _x000D_27/6/2024:#Update - Order was delayed due to step-1 work. This has now been resolved and appointed for 03/07 AM _x000D_25/6/2024:#Update - Order was delayed due to step-1 work. This has now been resolved and appointed for 03/07 AM _x000D_24/6/2024:#Update - Order was delayed due to step-1 work. This has now been resolved and appointed for 03/07 AM _x000D_20/6/2024:#Update - Order was delayed due to step-1 work. This has now been resolved and appointed for 03/07 AM _x000D_19/6/2024:#Update - Order was delayed due to step-1 work. This has now been resolved and appointed for 03/07 AM _x000D_18/6/2024:#Update - Order was delayed due to step-1 work. This has now been resolved and appointed for 03/07 AM _x000D_17/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_14/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 24/06/2024. We will continue to provide update as they become available CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_13/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 14/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 14/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/6/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 10/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_7/6/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 10/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_6/6/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 10/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_5/6/2024:0 _x000D_4/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 05/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 4/7/2024:#Update - Order was delayed due to step-1 work. This has now been resolved and appointed for 03/07 AM _x000D_3/7/2024:#Update - Order was delayed due to step-1 work. This has now been resolved and appointed for 03/07 AM _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Order was delayed due to step-1 work. This has now been resolved and appointed for 03/07 AM _x000D_27/6/2024:#Update - Order was delayed due to step-1 work. This has now been resolved and appointed for 03/07 AM _x000D_25/6/2024:#Update - Order was delayed due to step-1 work. This has now been resolved and appointed for 03/07 AM _x000D_24/6/2024:#Update - Order was delayed due to step-1 work. This has now been resolved and appointed for 03/07 AM _x000D_20/6/2024:#Update - Order was delayed due to step-1 work. This has now been resolved and appointed for 03/07 AM _x000D_19/6/2024:#Update - Order was delayed due to step-1 work. This has now been resolved and appointed for 03/07 AM _x000D_18/6/2024:#Update - Order was delayed due to step-1 work. This has now been resolved and appointed for 03/07 AM _x000D_17/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_14/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 24/06/2024. We will continue to provide update as they become available CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_13/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 14/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 14/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/6/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 10/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_7/6/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 10/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_6/6/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 10/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_5/6/2024:0 _x000D_4/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 05/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1013024 | 30016560 | 2.Commissioning |  |  | 2024-07-03 | 2024-07-03 | 2024-07-03 | TRUE |  |  |  | 2024-08-06 | [7 empty] | 0
985 | 668928 | 3604 | Batch 5 Jul24 | Type 1 | FTTP | Canley Family Shopper | Coventry | CV4 8DA | 2024-07-04 | 4/7/2024:Order Completed _x000D_3/7/2024:Update: Order Completed by Supplier _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 4/7/2024:Order Completed _x000D_3/7/2024:Update: Order Completed by Supplier _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFP2363466 | 30016218 | 2.Commissioning |  |  | 2024-07-03 | 2024-07-03 | 2024-07-03 | TRUE |  |  |  | 2024-07-30 | [7 empty] | 0
986 | 642211 | 3605 | Batch 5 Jul24 | Type 1 | SOGEA | Premier | Norfolk | NR5 8DF | 2024-07-04 | 4/7/2024:Order Completed _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 4/7/2024:Order Completed _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1013021 | 30016568 | 2.Commissioning |  |  | 2024-07-03 | 2024-07-03 | 2024-07-03 | TRUE |  |  |  | 2024-07-24 | [7 empty] | 0
987 | 603718 | 3607 | Batch 5 Jul24 | Type 1 | SOGEA | HJ Foodstores | Sunderland | SR4 6NQ | 2024-07-04 | 19/7/2024:#Update - Allwyn have confirmed re-appointment for 19/08 _x000D_18/7/2024:#Update - Confirmed notes, this is a simple re-appointment. No need for additional hours. Action for Allwyn: Please confirm re-appointment date of 19/08 with the retailer. _x000D_17/7/2024:#Update - Confirmed notes, this is a simple re-appointment. No need for additional hours. Action for Allwyn: Please confirm re-appointment date of 19/08 with the retailer. _x000D_16/7/2024:#Update - order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 10/07/2024. _x000D_15/7/2024:#Update - order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 10/07/2024. _x000D_12/7/2024:#Update - order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 10/07/2024. _x000D_11/7/2024:#Update - order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 10/07/2024. _x000D_10/7/2024:#Update - order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 10/07/2024. _x000D_9/7/2024:#Update - order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 10/07/2024. _x000D_4/7/2024:Supplier Delay: KCI-3 (Order Completed) Delayed in Processing. _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:#Update - Allwyn have confirmed re-appointment for 19/08 _x000D_18/7/2024:#Update - Confirmed notes, this is a simple re-appointment. No need for additional hours. Action for Allwyn: Please confirm re-appointment date of 19/08 with the retailer. _x000D_17/7/2024:#Update - Confirmed notes, this is a simple re-appointment. No need for additional hours. Action for Allwyn: Please confirm re-appointment date of 19/08 with the retailer. _x000D_16/7/2024:#Update - order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 10/07/2024. _x000D_15/7/2024:#Update - order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 10/07/2024. _x000D_12/7/2024:#Update - order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 10/07/2024. _x000D_11/7/2024:#Update - order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 10/07/2024. _x000D_10/7/2024:#Update - order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 10/07/2024. _x000D_9/7/2024:#Update - order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 10/07/2024. _x000D_4/7/2024:Supplier Delay: KCI-3 (Order Completed) Delayed in Processing. _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1013022 | 30016424 | 2.Commissioning |  |  | 2024-07-03 | 2024-07-03 | 2024-07-03 | TRUE |  |  |  | 2024-07-25 | [7 empty] | 0
988 | 438580 | 3609 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Nisa Local | COVENTRY | CV2 2GG | 2024-07-04 | 6/9/2024:#Update - Allwyn having trouble reaching out to retailer - may need to be pushed out again _x000D_5/9/2024:#Update - Allwyn having trouble reaching out to retailer - may need to be pushed out again _x000D_4/9/2024:#Update - Allwyn having trouble reaching out to retailer - may need to be pushed out again _x000D_3/9/2024:#Update - Allwyn having trouble reaching out to retailer - may need to be pushed out again _x000D_2/9/2024:#Update - Allwyn having trouble reaching out to retailer - may need to be pushed out again _x000D_29/8/2024:#Update - Allwyn having trouble reaching out to retailer - may need to be pushed out again _x000D_28/8/2024:#Update - Allwyn having trouble reaching out to retailer - may need to be pushed out again _x000D_27/8/2024:#Update - Allwyn having trouble reaching out to retailer - may need to be pushed out again _x000D_22/8/2024:#Update - Allwyn having trouble reaching out to retailer - may need to be pushed out again _x000D_21/8/2024:#Update - Allwyn have confirmed re-appointment for 19/08 _x000D_20/8/2024:#Update - Allwyn have confirmed re-appointment for 19/08 _x000D_19/8/2024:#Update - Allwyn have confirmed re-appointment for 19/08 _x000D_19/8/2024:01467228 _x000D_16/8/2024:#Update - Allwyn have confirmed re-appointment for 19/08 _x000D_15/8/2024:#Update - Allwyn have confirmed re-appointment for 19/08 _x000D_14/8/2024:#Update - Allwyn have confirmed re-appointment for 19/08 _x000D_13/8/2024:#Update - Allwyn have confirmed re-appointment for 19/08 _x000D_12/8/2024:#Update - Allwyn have confirmed re-appointment for 19/08 _x000D_9/8/2024:#Update - Allwyn have confirmed re-appointment for 19/08 _x000D_8/8/2024:19/07/2024 _x000D_6/8/2024:19/07/2024 _x000D_5/8/2024:19/07/2024 _x000D_2/8/2024:19/07/2024 _x000D_1/8/2024:19/07/2024 _x000D_31/7/2024:19/07/2024 _x000D_31/7/2024:19/07/2024 _x000D_30/7/2024:#Update - Allwyn have confirmed re-appointment for 19/08 _x000D_29/7/2024:#Update - Allwyn have confirmed re-appointment for 19/08 _x000D_29/7/2024:01467228 _x000D_26/7/2024:01467228 _x000D_24/7/2024:#Update - Allwyn have confirmed re-appointment for 19/08 _x000D_23/7/2024:#Update - Allwyn have confirmed re-appointment for 19/08 _x000D_22/7/2024:#Update - Allwyn have confirmed re-appointment for 19/08 _x000D_22/7/2024:#Update - Allwyn have confirmed re-appointment for 19/08 _x000D_19/7/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_18/7/2024:Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 19/07/2024 for further updates. _x000D_17/7/2024:Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 19/07/2024 for further updates. _x000D_16/7/2024:EU Missed Appointment. Supplier engineer has been unable to gain access. _x000D_15/7/2024:EU Missed Appointment. Supplier engineer has been unable to gain access. _x000D_12/7/2024:EU Missed Appointment. Supplier engineer has been unable to gain access. _x000D_11/7/2024:0 _x000D_10/7/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_9/7/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_4/7/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_3/7/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn having trouble reaching out to retailer - may need to be pushed out again _x000D_6/9/2024:#Update - Allwyn having trouble reaching out to retailer - may need to be pushed out again _x000D_5/9/2024:#Update - Allwyn having trouble reaching out to retailer - may need to be pushed out again _x000D_4/9/2024:#Update - Allwyn having trouble reaching out to retailer - may need to be pushed out again _x000D_3/9/2024:#Update - Allwyn having trouble reaching out to retailer - may need to be pushed out again _x000D_2/9/2024:#Update - Allwyn having trouble reaching out to retailer - may need to be pushed out again _x000D_29/8/2024:#Update - Allwyn having trouble reaching out to retailer - may need to be pushed out again _x000D_28/8/2024:#Update - Allwyn having trouble reaching out to retailer - may need to be pushed out again _x000D_27/8/2024:#Update - Allwyn having trouble reaching out to retailer - may need to be pushed out again _x000D_22/8/2024:#Update - Allwyn having trouble reaching out to retailer - may need to be pushed out again _x000D_21/8/2024:#Update - Allwyn have confirmed re-appointment for 19/08 _x000D_20/8/2024:#Update - Allwyn have confirmed re-appointment for 19/08 _x000D_19/8/2024:#Update - Allwyn have confirmed re-appointment for 19/08 _x000D_19/8/2024:01467228 _x000D_16/8/2024:#Update - Allwyn have confirmed re-appointment for 19/08 _x000D_15/8/2024:#Update - Allwyn have confirmed re-appointment for 19/08 _x000D_14/8/2024:#Update - Allwyn have confirmed re-appointment for 19/08 _x000D_13/8/2024:#Update - Allwyn have confirmed re-appointment for 19/08 _x000D_12/8/2024:#Update - Allwyn have confirmed re-appointment for 19/08 _x000D_9/8/2024:#Update - Allwyn have confirmed re-appointment for 19/08 _x000D_8/8/2024:19/07/2024 _x000D_6/8/2024:19/07/2024 _x000D_5/8/2024:19/07/2024 _x000D_2/8/2024:19/07/2024 _x000D_1/8/2024:19/07/2024 _x000D_31/7/2024:19/07/2024 _x000D_31/7/2024:19/07/2024 _x000D_30/7/2024:#Update - Allwyn have confirmed re-appointment for 19/08 _x000D_29/7/2024:#Update - Allwyn have confirmed re-appointment for 19/08 _x000D_29/7/2024:01467228 _x000D_26/7/2024:01467228 _x000D_24/7/2024:#Update - Allwyn have confirmed re-appointment for 19/08 _x000D_23/7/2024:#Update - Allwyn have confirmed re-appointment for 19/08 _x000D_22/7/2024:#Update - Allwyn have confirmed re-appointment for 19/08 _x000D_22/7/2024:#Update - Allwyn have confirmed re-appointment for 19/08 _x000D_19/7/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_18/7/2024:Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 19/07/2024 for further updates. _x000D_17/7/2024:Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 19/07/2024 for further updates. _x000D_16/7/2024:EU Missed Appointment. Supplier engineer has been unable to gain access. _x000D_15/7/2024:EU Missed Appointment. Supplier engineer has been unable to gain access. _x000D_12/7/2024:EU Missed Appointment. Supplier engineer has been unable to gain access. _x000D_11/7/2024:0 _x000D_10/7/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_9/7/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_4/7/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_3/7/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update - Allwyn having trouble reaching out to retailer - may need to be pushed out again | 2024-06-07 |  |  |  | 5.CSL | VFS1013020 | 30016519 | 1.Provisioning | AM |  | 2024-07-03 | 2024-08-19 |  | 0 | [11 empty] | 0
989 | 629224 | 3610 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Centra | Belfast | BT7 3GL | 2024-07-04 | 6/9/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_5/9/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_4/9/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_3/9/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_2/9/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_29/8/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_28/8/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_27/8/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_22/8/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_21/8/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_20/8/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_19/8/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_19/8/2024:01501573 _x000D_16/8/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_15/8/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_14/8/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_13/8/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_12/8/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_9/8/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_8/8/2024:18/07/2024 _x000D_6/8/2024:18/07/2024 _x000D_5/8/2024:18/07/2024 _x000D_2/8/2024:18/07/2024 _x000D_1/8/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_30/7/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_29/7/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_29/7/2024:01501573 _x000D_26/7/2024:01501573 _x000D_24/7/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_23/7/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_22/7/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_22/7/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:Update: Order Amended _x000D_15/7/2024:Update: Order Amended _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_6/9/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_5/9/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_4/9/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_3/9/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_2/9/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_29/8/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_28/8/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_27/8/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_22/8/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_21/8/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_20/8/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_19/8/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_19/8/2024:01501573 _x000D_16/8/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_15/8/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_14/8/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_13/8/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_12/8/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_9/8/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_8/8/2024:18/07/2024 _x000D_6/8/2024:18/07/2024 _x000D_5/8/2024:18/07/2024 _x000D_2/8/2024:18/07/2024 _x000D_1/8/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_30/7/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_29/7/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_29/7/2024:01501573 _x000D_26/7/2024:01501573 _x000D_24/7/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_23/7/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_22/7/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_22/7/2024:#Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:Update: Order Amended _x000D_15/7/2024:Update: Order Amended _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 24/07/2024 for further updates. | 2024-06-07 |  |  |  | 5.CSL | VFP2363463 | 30016381 | 1.Provisioning | AM |  | 2024-07-03 | 2024-07-03 |  | 0 | [11 empty] | 0
990 | 631352 | 3611 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Rams News and Off Licence | RAMSGATE | CT12 6PP | 2024-08-07 | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 5.CSL | VFP2363464 | 30016215 | 3.In life |  |  | 2024-07-03 | 2024-08-06 | 2024-08-06 11:25 | TRUE |  |  |  | 2024-09-05 |  |  |  | 2024-09-05 | 242005011073 | 242005011073 | 2024-09-06 | 1
991 | 657181 | 3612 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | SI News and Off Licence | Coventry | CV3 1EN |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 11:33 _x000D_26/7/2024:22/07/2024 11:33 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_4/7/2024:Order Completed _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 11:33 _x000D_26/7/2024:22/07/2024 11:33 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_4/7/2024:Order Completed _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2363465 | 30016185 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
992 | 438683 | 3613 | Batch 5 Jul24 | Type 1 | SOGEA | Lotus Convenience Store | Romford | RM6 6YU | 2024-07-04 | 4/7/2024:Order Completed _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 4/7/2024:Order Completed _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1013018 | 30016540 | 2.Commissioning |  |  | 2024-07-03 | 2024-07-03 | 2024-07-03 | TRUE |  |  |  | 2024-07-31 | [7 empty] | 0
993 | 459839 | 3615 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Premier Coombe Valley Food and Wine | DOVER | CT17 0HG | 2024-07-04 | 6/9/2024:#Update - Awaiting ECC approval for 2hrs out of hours , 2 Sunday engineers. _x000D_5/9/2024:#Update - engineer assessed the site and said that it needs to be upgraded. I have emailed allwyn with a prospective date. Finding out from OR the exact specs for the job and then i will submit for ECC approval. _x000D_4/9/2024:#Update - engineer assessed the site and said that it needs to be upgraded. I have emailed allwyn with a prospective date. Finding out from OR the exact specs for the job and then i will submit for ECC approval. _x000D_3/9/2024:#Update - engineer assessed the site and said that it needs to be upgraded. I have emailed allwyn with a prospective date. Finding out from OR the exact specs for the job and then i will submit for ECC approval. _x000D_2/9/2024:#Update - engineer assessed the site and said that it needs to be upgraded. I have emailed allwyn with a prospective date. Finding out from OR the exact specs for the job and then i will submit for ECC approval. _x000D_29/8/2024:#Update - engineer assessed the site and said that it needs to be upgraded. I have emailed allwyn with a prospective date. Finding out from OR the exact specs for the job and then i will submit for ECC approval. _x000D_28/8/2024:#Update - engineer assessed the site and said that it needs to be upgraded. I have emailed allwyn with a prospective date. Finding out from OR the exact specs for the job and then i will submit for ECC approval. _x000D_27/8/2024:#Update - engineer assessed the site and said that it needs to be upgraded. I have emailed allwyn with a prospective date. Finding out from OR the exact specs for the job and then i will submit for ECC approval. _x000D_22/8/2024:#Update - engineer assessed the site and said that it needs to be upgraded. I have emailed allwyn with a prospective date. Finding out from OR the exact specs for the job and then i will submit for ECC approval. _x000D_21/8/2024:#Update - engineer assessed the site and said that it needs to be upgraded. I have emailed allwyn with a prospective date. Finding out from OR the exact specs for the job and then i will submit for ECC approval. _x000D_20/8/2024:#Update - engineer assessed the site and said that it needs to be upgraded. I have emailed allwyn with a prospective date. Finding out from OR the exact specs for the job and then i will submit for ECC approval. _x000D_19/8/2024:#Update - engineer assessed the site and said that it needs to be upgraded. I have emailed allwyn with a prospective date. Finding out from OR the exact specs for the job and then i will submit for ECC approval. _x000D_19/8/2024:01466935 _x000D_16/8/2024:#Update - engineer assessed the site and said that it needs to be upgraded. I have emailed allwyn with a prospective date. Finding out from OR the exact specs for the job and then i will submit for ECC approval. _x000D_15/8/2024:#Update - engineer assessed the site and said that it needs to be upgraded. I have emailed allwyn with a prospective date. Finding out from OR the exact specs for the job and then i will submit for ECC approval. _x000D_14/8/2024:#Update - engineer assessed the site and said that it needs to be upgraded. I have emailed allwyn with a prospective date. Finding out from OR the exact specs for the job and then i will submit for ECC approval. _x000D_13/8/2024:#Update - engineer assessed the site and said that it needs to be upgraded. I have emailed allwyn with a prospective date. Finding out from OR the exact specs for the job and then i will submit for ECC approval. _x000D_12/8/2024:#Update - engineer assessed the site and said that it needs to be upgraded. I have emailed allwyn with a prospective date. Finding out from OR the exact specs for the job and then i will submit for ECC approval. _x000D_9/8/2024:#Update - engineer assessed the site and said that it needs to be upgraded. I have emailed allwyn with a prospective date. Finding out from OR the exact specs for the job and then i will submit for ECC approval. _x000D_8/8/2024:29/07/2024 _x000D_6/8/2024:29/07/2024 _x000D_5/8/2024:29/07/2024 _x000D_2/8/2024:29/07/2024 _x000D_1/8/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_30/7/2024:#Update - engineer assessed the site and said that it needs to be upgraded. I have emailed allwyn with a prospective date. Finding out from OR the exact specs for the job and then i will submit for ECC approval. _x000D_29/7/2024:#Update - Allwyn confirmed new appoint of 29/07 with the retailer. _x000D_29/7/2024:01466935 _x000D_26/7/2024:01466935 _x000D_24/7/2024:#Update - Allwyn confirmed new appoint of 29/07 with the retailer. _x000D_23/7/2024:#Update - Allwyn confirmed new appoint of 29/07 with the retailer. _x000D_22/7/2024:#Update - Allwyn confirmed new appoint of 29/07 with the retailer. _x000D_22/7/2024:#Update - Allwyn confirmed new appoint of 29/07 with the retailer. _x000D_19/7/2024:#Update Retailer happy with new appointment 24/07, AM. _x000D_18/7/2024:#Update Retailer happy with new appointment 24/07, AM. _x000D_17/7/2024:#Update Retailer happy with new appointment 24/07, AM. _x000D_16/7/2024:#Update Retailer happy with new appointment 24/07, AM. _x000D_15/7/2024:#Update Retailer happy with new appointment 24/07, AM. _x000D_12/7/2024:#Update Retailer happy with new appointment 24/07, AM. _x000D_11/7/2024:#Update Retailer happy with new appointment 24/07, AM. _x000D_10/7/2024:#Update Retailer happy with new appointment 24/07, AM. _x000D_9/7/2024:Your order has been delayed. Our suppliers are raising the required external work, they have given us a review date of 10/07/2024.We will continue to provide update as they become available. _x000D_4/7/2024:Your order has been delayed. Our suppliers are raising the required external work, they have given us a review date of 10/07/2024.We will continue to provide update as they become available. _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - Awaiting ECC approval for 2hrs out of hours , 2 Sunday engineers. _x000D_6/9/2024:#Update - Awaiting ECC approval for 2hrs out of hours , 2 Sunday engineers. _x000D_5/9/2024:#Update - engineer assessed the site and said that it needs to be upgraded. I have emailed allwyn with a prospective date. Finding out from OR the exact specs for the job and then i will submit for ECC approval. _x000D_4/9/2024:#Update - engineer assessed the site and said that it needs to be upgraded. I have emailed allwyn with a prospective date. Finding out from OR the exact specs for the job and then i will submit for ECC approval. _x000D_3/9/2024:#Update - engineer assessed the site and said that it needs to be upgraded. I have emailed allwyn with a prospective date. Finding out from OR the exact specs for the job and then i will submit for ECC approval. _x000D_2/9/2024:#Update - engineer assessed the site and said that it needs to be upgraded. I have emailed allwyn with a prospective date. Finding out from OR the exact specs for the job and then i will submit for ECC approval. _x000D_29/8/2024:#Update - engineer assessed the site and said that it needs to be upgraded. I have emailed allwyn with a prospective date. Finding out from OR the exact specs for the job and then i will submit for ECC approval. _x000D_28/8/2024:#Update - engineer assessed the site and said that it needs to be upgraded. I have emailed allwyn with a prospective date. Finding out from OR the exact specs for the job and then i will submit for ECC approval. _x000D_27/8/2024:#Update - engineer assessed the site and said that it needs to be upgraded. I have emailed allwyn with a prospective date. Finding out from OR the exact specs for the job and then i will submit for ECC approval. _x000D_22/8/2024:#Update - engineer assessed the site and said that it needs to be upgraded. I have emailed allwyn with a prospective date. Finding out from OR the exact specs for the job and then i will submit for ECC approval. _x000D_21/8/2024:#Update - engineer assessed the site and said that it needs to be upgraded. I have emailed allwyn with a prospective date. Finding out from OR the exact specs for the job and then i will submit for ECC approval. _x000D_20/8/2024:#Update - engineer assessed the site and said that it needs to be upgraded. I have emailed allwyn with a prospective date. Finding out from OR the exact specs for the job and then i will submit for ECC approval. _x000D_19/8/2024:#Update - engineer assessed the site and said that it needs to be upgraded. I have emailed allwyn with a prospective date. Finding out from OR the exact specs for the job and then i will submit for ECC approval. _x000D_19/8/2024:01466935 _x000D_16/8/2024:#Update - engineer assessed the site and said that it needs to be upgraded. I have emailed allwyn with a prospective date. Finding out from OR the exact specs for the job and then i will submit for ECC approval. _x000D_15/8/2024:#Update - engineer assessed the site and said that it needs to be upgraded. I have emailed allwyn with a prospective date. Finding out from OR the exact specs for the job and then i will submit for ECC approval. _x000D_14/8/2024:#Update - engineer assessed the site and said that it needs to be upgraded. I have emailed allwyn with a prospective date. Finding out from OR the exact specs for the job and then i will submit for ECC approval. _x000D_13/8/2024:#Update - engineer assessed the site and said that it needs to be upgraded. I have emailed allwyn with a prospective date. Finding out from OR the exact specs for the job and then i will submit for ECC approval. _x000D_12/8/2024:#Update - engineer assessed the site and said that it needs to be upgraded. I have emailed allwyn with a prospective date. Finding out from OR the exact specs for the job and then i will submit for ECC approval. _x000D_9/8/2024:#Update - engineer assessed the site and said that it needs to be upgraded. I have emailed allwyn with a prospective date. Finding out from OR the exact specs for the job and then i will submit for ECC approval. _x000D_8/8/2024:29/07/2024 _x000D_6/8/2024:29/07/2024 _x000D_5/8/2024:29/07/2024 _x000D_2/8/2024:29/07/2024 _x000D_1/8/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_30/7/2024:#Update - engineer assessed the site and said that it needs to be upgraded. I have emailed allwyn with a prospective date. Finding out from OR the exact specs for the job and then i will submit for ECC approval. _x000D_29/7/2024:#Update - Allwyn confirmed new appoint of 29/07 with the retailer. _x000D_29/7/2024:01466935 _x000D_26/7/2024:01466935 _x000D_24/7/2024:#Update - Allwyn confirmed new appoint of 29/07 with the retailer. _x000D_23/7/2024:#Update - Allwyn confirmed new appoint of 29/07 with the retailer. _x000D_22/7/2024:#Update - Allwyn confirmed new appoint of 29/07 with the retailer. _x000D_22/7/2024:#Update - Allwyn confirmed new appoint of 29/07 with the retailer. _x000D_19/7/2024:#Update Retailer happy with new appointment 24/07, AM. _x000D_18/7/2024:#Update Retailer happy with new appointment 24/07, AM. _x000D_17/7/2024:#Update Retailer happy with new appointment 24/07, AM. _x000D_16/7/2024:#Update Retailer happy with new appointment 24/07, AM. _x000D_15/7/2024:#Update Retailer happy with new appointment 24/07, AM. _x000D_12/7/2024:#Update Retailer happy with new appointment 24/07, AM. _x000D_11/7/2024:#Update Retailer happy with new appointment 24/07, AM. _x000D_10/7/2024:#Update Retailer happy with new appointment 24/07, AM. _x000D_9/7/2024:Your order has been delayed. Our suppliers are raising the required external work, they have given us a review date of 10/07/2024.We will continue to provide update as they become available. _x000D_4/7/2024:Your order has been delayed. Our suppliers are raising the required external work, they have given us a review date of 10/07/2024.We will continue to provide update as they become available. _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | #Update - Awaiting ECC approval for 2hrs out of hours , 2 Sunday engineers. | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFP2363462 | 30016249 | 1.Provisioning | AM |  | 2024-07-03 | 2024-09-09 |  | 0 | [11 empty] | 0
994 | 636021 | 3617 | Batch 5 Jul24 | Type 1 | SOGEA | St News Supermarket | DONCASTER | DN1 3BB | 2024-07-04 | 19/7/2024:#Update - NFA - Allwyn confirmed new installation date 19/07 with retailer _x000D_18/7/2024:#Update - unsuccessful installation - EU, Site Manager and and shop worker unaware, reappointed for 19/07 _x000D_17/7/2024:#Update - unsuccessful installation - EU, Site Manager and and shop worker unaware, reappointed for 19/07 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:#Update - NFA - Allwyn confirmed new installation date 19/07 with retailer _x000D_18/7/2024:#Update - unsuccessful installation - EU, Site Manager and and shop worker unaware, reappointed for 19/07 _x000D_17/7/2024:#Update - unsuccessful installation - EU, Site Manager and and shop worker unaware, reappointed for 19/07 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1013017 | 30016587 | 2.Commissioning |  |  | 2024-07-03 | 2024-07-03 | 2024-07-03 | TRUE |  |  |  | 2024-07-23 | [7 empty] | 0
995 | 468847 | 3618 | Batch 5 Jul24 | Type 1 | SOGEA | Spar | Oxford | OX3 9LU | 2024-07-04 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:#Update - NFA - Allwyn confirmed new installation date 19/07 with retailer _x000D_22/7/2024:#Update - NFA - Allwyn confirmed new installation date 19/07 with retailer _x000D_22/7/2024:#Update - NFA - Allwyn confirmed new installation date 19/07 with retailer _x000D_19/7/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_18/7/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_17/7/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_16/7/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_15/7/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_12/7/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_11/7/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_10/7/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_9/7/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_4/7/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_3/7/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_27/6/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_25/6/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_24/6/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_20/6/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_19/6/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_18/6/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_17/6/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_14/6/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_13/6/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_12/6/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_11/6/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_10/6/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_7/6/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_6/6/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_5/6/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_4/6/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_31/5/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_30/5/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_29/5/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_28/5/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_10/5/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_08/04/2024: CSL and OR advised that the order need to be upgraded to Advanced as internal and external work is needed wih 8 hours + 3 Engineers. 02/04/2024: Abortive charges to be raised on 27/03/2024. Issue regarding the existing cable in the store and new dropwire needs to be installed ( it will take time ). The only suitable sitme for the retailer to complete the external and internal work is on Sunday. One engineer can completed the work, but it will be better to have 2 engineers and 1 hoist driver. 28/03/2024: Appointment rescheduled for 22/04/2024. Abortive visit, Engineer was not given access to the site on 27/03/2024 and abortive visits charge to be raised. 18/03/24: Access confirmed for the 27/03 1200-1400 15/03/24: Customer advised that retailer would like Openreach to attend post 6PM. However, Openreach have flagged that a flat roof engineer is required and wouldn't be able to access the flat roof in the dark. Allwyn are investigating with the retailer if they can attend on the 27/03 during the store closing time in the afternoon around 2PM. CSL are also investigating if this is possible with Openreach. If the work cannot be done earlier as required appointment might need to move into April as there is more daylight. (after clk change) 14/03/24: CSL to provide OoH slot date to complete provide and OoH charges. 12/03/24: Further abortive visit charge to be raised to Allwyn due to failed visit on the 05/03. 06/03/24: OR attended site 05/03, did not get access to complete, shop was extremely busy, shop owner advised they didn't want new cables and drilling and said the shop needs to be closed to complete works. Allwyn stated that this order might be downgraded to type 3 due to difficulties in trying to arrange works - tba. 14/02/24: Your order has been delayed by our Suppliers due to unable to access distribution point within customer premises. Please check with end user and re-appoint order once access arranged. VF to raise Abortive visit charge - closed 05/03 charge approved by Allwyn. 09/02/24: Need to access flat above, they are the landlord of building. Need to access BT66 through bedroom window and find internal connection point connecting from the shop to the cable to BT66z landlords away. Have left a message but no response. Employees will speak to them when they're back and arrange a suitable time to reappoint. NTE fitted. | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:#Update - NFA - Allwyn confirmed new installation date 19/07 with retailer _x000D_22/7/2024:#Update - NFA - Allwyn confirmed new installation date 19/07 with retailer _x000D_22/7/2024:#Update - NFA - Allwyn confirmed new installation date 19/07 with retailer _x000D_19/7/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_18/7/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_17/7/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_16/7/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_15/7/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_12/7/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_11/7/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_10/7/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_9/7/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_4/7/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_3/7/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_27/6/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_25/6/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_24/6/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_20/6/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_19/6/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_18/6/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_17/6/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_14/6/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_13/6/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_12/6/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_11/6/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_10/6/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_7/6/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_6/6/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_5/6/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_4/6/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_31/5/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_30/5/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_29/5/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_28/5/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_10/5/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_08/04/2024: CSL and OR advised that the order need to be upgraded to Advanced as internal and external work is needed wih 8 hours + 3 Engineers. 02/04/2024: Abortive charges to be raised on 27/03/2024. Issue regarding the existing cable in the store and new dropwire needs to be installed ( it will take time ). The only suitable sitme for the retailer to complete the external and internal work is on Sunday. One engineer can completed the work, but it will be better to have 2 engineers and 1 hoist driver. 28/03/2024: Appointment rescheduled for 22/04/2024. Abortive visit, Engineer was not given access to the site on 27/03/2024 and abortive visits charge to be raised. 18/03/24: Access confirmed for the 27/03 1200-1400 15/03/24: Customer advised that retailer would like Openreach to attend post 6PM. However, Openreach have flagged that a flat roof engineer is required and wouldn't be able to access the flat roof in the dark. Allwyn are investigating with the retailer if they can attend on the 27/03 during the store closing time in the afternoon around 2PM. CSL are also investigating if this is possible with Openreach. If the work cannot be done earlier as required appointment might need to move into April as there is more daylight. (after clk change) 14/03/24: CSL to provide OoH slot date to complete provide and OoH charges. 12/03/24: Further abortive visit charge to be raised to Allwyn due to failed visit on the 05/03. 06/03/24: OR attended site 05/03, did not get access to complete, shop was extremely busy, shop owner advised they didn't want new cables and drilling and said the shop needs to be closed to complete works. Allwyn stated that this order might be downgraded to type 3 due to difficulties in trying to arrange works - tba. 14/02/24: Your order has been delayed by our Suppliers due to unable to access distribution point within customer premises. Please check with end user and re-appoint order once access arranged. VF to raise Abortive visit charge - closed 05/03 charge approved by Allwyn. 09/02/24: Need to access flat above, they are the landlord of building. Need to access BT66 through bedroom window and find internal connection point connecting from the shop to the cable to BT66z landlords away. Have left a message but no response. Employees will speak to them when they're back and arrange a suitable time to reappoint. NTE fitted. | 0 | 0 | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1013016 | 30016555 | 2.Commissioning | [17 empty] | 0
996 | 462577 | 11 | Batch 1 Feb24 | Type 1 | SoGEA/Mobile | Cross Stores | Stroud | GL6 9BN | 2024-05-30 | 6/9/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_5/9/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_4/9/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_3/9/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_2/9/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_29/8/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_28/8/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_27/8/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_22/8/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_21/8/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_20/8/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_19/8/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_19/8/2024:01280018 _x000D_16/8/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_15/8/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_14/8/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_13/8/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_12/8/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_9/8/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_8/8/2024:09/05/2024 _x000D_6/8/2024:09/05/2024 _x000D_5/8/2024:09/05/2024 _x000D_2/8/2024:09/05/2024 _x000D_1/8/2024:09/05/2024 _x000D_31/7/2024:09/05/2024 _x000D_31/7/2024:09/05/2024 _x000D_30/7/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_29/7/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_29/7/2024:01280018 _x000D_26/7/2024:01280018 _x000D_24/7/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_23/7/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_22/7/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_22/7/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_19/7/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_18/7/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_17/7/2024:#Update - this order is delayed as site survey is required. This has been sent to the survey engineers. We will continue to provide update as they become available. _x000D_16/7/2024:#Update - this order is delayed as site survey is required. This has been sent to the survey engineers. We will continue to provide update as they become available. _x000D_15/7/2024:#Update - this order is delayed as site survey is required. This has been sent to the survey engineers. We will continue to provide update as they become available. _x000D_12/7/2024:#Update - this order is delayed as site survey is required. This has been sent to the survey engineers. We will continue to provide update as they become available. _x000D_11/7/2024:#Update - this order is delayed as site survey is required. This has been sent to the survey engineers. We will continue to provide update as they become available. _x000D_10/7/2024:#Update - this order is delayed as site survey is required. This has been sent to the survey engineers. We will continue to provide update as they become available. _x000D_9/7/2024:#Update - this order is delayed as site survey is required. This has been sent to the survey engineers. We will continue to provide update as they become available. _x000D_4/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_3/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_27/6/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_25/6/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_24/6/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_20/6/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_19/6/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_18/6/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_17/6/2024:#Update - delayed due to third party estimate required - a final installation date will be appointed when this stage is complete. Further update to follow after 10/06 _x000D_14/6/2024:#Update - delayed due to third party estimate required - a final installation date will be appointed when this stage is complete. Further update to follow after 10/06 _x000D_13/6/2024:#Update - delayed due to third party estimate required - a final installation date will be appointed when this stage is complete. Further update to follow after 10/06 _x000D_12/6/2024:#Update - delayed due to third party estimate required - a final installation date will be appointed when this stage is complete. Further update to follow after 10/06 _x000D_11/6/2024:Update: Order Completed by Supplier _x000D_ | 9/9/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_6/9/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_5/9/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_4/9/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_3/9/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_2/9/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_29/8/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_28/8/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_27/8/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_22/8/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_21/8/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_20/8/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_19/8/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_19/8/2024:01280018 _x000D_16/8/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_15/8/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_14/8/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_13/8/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_12/8/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_9/8/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_8/8/2024:09/05/2024 _x000D_6/8/2024:09/05/2024 _x000D_5/8/2024:09/05/2024 _x000D_2/8/2024:09/05/2024 _x000D_1/8/2024:09/05/2024 _x000D_31/7/2024:09/05/2024 _x000D_31/7/2024:09/05/2024 _x000D_30/7/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_29/7/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_29/7/2024:01280018 _x000D_26/7/2024:01280018 _x000D_24/7/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_23/7/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_22/7/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_22/7/2024:#Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly _x000D_19/7/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_18/7/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_17/7/2024:#Update - this order is delayed as site survey is required. This has been sent to the survey engineers. We will continue to provide update as they become available. _x000D_16/7/2024:#Update - this order is delayed as site survey is required. This has been sent to the survey engineers. We will continue to provide update as they become available. _x000D_15/7/2024:#Update - this order is delayed as site survey is required. This has been sent to the survey engineers. We will continue to provide update as they become available. _x000D_12/7/2024:#Update - this order is delayed as site survey is required. This has been sent to the survey engineers. We will continue to provide update as they become available. _x000D_11/7/2024:#Update - this order is delayed as site survey is required. This has been sent to the survey engineers. We will continue to provide update as they become available. _x000D_10/7/2024:#Update - this order is delayed as site survey is required. This has been sent to the survey engineers. We will continue to provide update as they become available. _x000D_9/7/2024:#Update - this order is delayed as site survey is required. This has been sent to the survey engineers. We will continue to provide update as they become available. _x000D_4/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_3/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_27/6/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_25/6/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_24/6/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_20/6/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_19/6/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_18/6/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_17/6/2024:#Update - delayed due to third party estimate required - a final installation date will be appointed when this stage is complete. Further update to follow after 10/06 _x000D_14/6/2024:#Update - delayed due to third party estimate required - a final installation date will be appointed when this stage is complete. Further update to follow after 10/06 _x000D_13/6/2024:#Update - delayed due to third party estimate required - a final installation date will be appointed when this stage is complete. Further update to follow after 10/06 _x000D_12/6/2024:#Update - delayed due to third party estimate required - a final installation date will be appointed when this stage is complete. Further update to follow after 10/06 _x000D_11/6/2024:Update: Order Completed by Supplier _x000D_ | 0 | #Update - awaiting OOH resource availability update from Openreach, CSL chasing and will update accordingly | 2024-04-08 | 28/03/2024:Allwyn to approve upgrade - Allwyn to aprove OOH work - Allwyn to make sure retailer is aware of new appointment on 22/04/2024 15/03/24: Action Allwyn to check if retailer will allow appointment earlier in the afternoon on the 27/03? - closed 18/03/24 Access confirmed for the 27/03 1200-1400 12/03/24: Action Allwyn to advise on out-of-hours appointment slot. - closed. 01/03/24: Order date amended to 05/03 as per discussion with Allwyn. OR engineer cannot attend after 10am for a AM app on the 04/03. - closed 06/03 29/02/24 PM: Allwyn advise that access is available in flat on original date of 04/03. Action CSL investigating if appointment can be moved from 13/03 back to 04/03. 29/02/24 AM: CSL advise that engineer cannot attend before 10am on the 04/03. CSL have rescheduled appointment for 13/03 PM. Action Allwyn to arrnage access with end user on given date. Action Allwyn to discuss with retailer on how to proceed. 15/02/24: OR requesting revisit on the 04/03 if Allwyn can arrange site access. |  | 14/03 - Allwyn have advised that retailer has agreed visit can take place after 1800 weekdays. - closed 15/03. 11/03/24 SL: Cross Store downgraded to Type 2 due to lack of mobile signal. 08/03/24: Downgrade to Type 3. 26/02/2024 - spoken to Brian Powell (owner), he will arrange access for 4th March but the engineer cannot attend before 10am closed 29/02 access to be re-arranged for the 13/03 PM. | 1.Allwyn to approve additional charges | VFS874903 | 30012227 | 1.Provisioning | AM |  | 2024-03-27 | 2024-09-16 |  | 0 | [11 empty] | 0
997 | 635701 | 246 | Batch 2 Apr24 | Type 1 | FTTP/Mobile | Texaco Petrol Station | Cardiff | CF14 2FF | 2024-07-05 | 6/9/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_5/9/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_4/9/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_3/9/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_2/9/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_29/8/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_28/8/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_27/8/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_22/8/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_21/8/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_20/8/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_19/8/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_19/8/2024:01351857 _x000D_16/8/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_15/8/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_14/8/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_13/8/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_12/8/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_9/8/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_8/8/2024:18/07/2024 _x000D_6/8/2024:18/07/2024 _x000D_5/8/2024:18/07/2024 _x000D_2/8/2024:18/07/2024 _x000D_1/8/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_30/7/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_29/7/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_29/7/2024:01351857 _x000D_26/7/2024:01351857 _x000D_24/7/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_23/7/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_22/7/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_22/7/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_19/7/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_18/7/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_17/7/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_16/7/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_15/7/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_12/7/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_11/7/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_10/7/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_9/7/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_4/7/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_3/7/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_27/6/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_25/6/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_24/6/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_20/6/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_19/6/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_18/6/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_17/6/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_14/6/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_13/6/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_12/6/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_6/9/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_5/9/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_4/9/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_3/9/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_2/9/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_29/8/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_28/8/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_27/8/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_22/8/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_21/8/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_20/8/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_19/8/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_19/8/2024:01351857 _x000D_16/8/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_15/8/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_14/8/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_13/8/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_12/8/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_9/8/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_8/8/2024:18/07/2024 _x000D_6/8/2024:18/07/2024 _x000D_5/8/2024:18/07/2024 _x000D_2/8/2024:18/07/2024 _x000D_1/8/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_30/7/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_29/7/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_29/7/2024:01351857 _x000D_26/7/2024:01351857 _x000D_24/7/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_23/7/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_22/7/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_22/7/2024:#Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly _x000D_19/7/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_18/7/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_17/7/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_16/7/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_15/7/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_12/7/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_11/7/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_10/7/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_9/7/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_4/7/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_3/7/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_27/6/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_25/6/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_24/6/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_20/6/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_19/6/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_18/6/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_17/6/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_14/6/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_13/6/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_12/6/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update - installation unsuccessful due to a routing issue - further update and reschedule to follow accordingly | 2024-04-12 | 12/04/2024: Allwyn confirmed the new date with the retailer. 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 2.Allwyn to arrange access | VFP2421087 | 30013280 | 1.Provisioning | AM |  | 2024-04-11 |  |  | 0 | [11 empty] | 0
998 | 671843 | 1392 | Batch 4 Jun24 | Type 1 | FTTP/Mobile | Riks Convenience | LONDON | E11 1EA | 2024-06-07 | 6/9/2024:#Update - ECC approved (OOH) - awaiting Engineer availability to schedule appointment _x000D_5/9/2024:#Update - ECC approved (OOH) - awaiting Engineer availability to schedule appointment _x000D_4/9/2024:#Update - ECC approved (OOH) - awaiting Engineer availability to schedule appointment _x000D_3/9/2024:#Update - ECC approved (OOH) - awaiting Engineer availability to schedule appointment _x000D_2/9/2024:#Update - ECC approved (OOH) - awaiting Engineer availability to schedule appointment _x000D_29/8/2024:#Update - ECC approved (OOH) - awaiting Engineer availability to schedule appointment _x000D_28/8/2024:#Update - ECC approved (OOH) - awaiting Engineer availability to schedule appointment _x000D_27/8/2024:#Update - ECC approved (OOH) - awaiting Engineer availability to schedule appointment _x000D_22/8/2024:#Update - ECC approved (OOH) - awaiting Engineer availability to schedule appointment _x000D_21/8/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_20/8/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_19/8/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_19/8/2024:01406128 _x000D_16/8/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_15/8/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_14/8/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_13/8/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_12/8/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_9/8/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_8/8/2024:23/05/2024 _x000D_6/8/2024:23/05/2024 _x000D_5/8/2024:23/05/2024 _x000D_2/8/2024:23/05/2024 _x000D_1/8/2024:23/05/2024 _x000D_31/7/2024:23/05/2024 _x000D_31/7/2024:23/05/2024 _x000D_30/7/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_29/7/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_29/7/2024:01406128 _x000D_26/7/2024:01406128 _x000D_24/7/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_23/7/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_22/7/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_22/7/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Your order has been delayed. Multiskilled engineer work is required for NCF work, Our Suppliers have given us a review date of 12/07/2024. We will continue to provide update as they become available. _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:Update: Order Amended _x000D_20/6/2024:Update: Order Amended _x000D_19/6/2024:Update: Order Amended _x000D_18/6/2024:Update: Order Amended _x000D_17/6/2024:Update: Order Amended _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:Update: Order Amended _x000D_7/6/2024:Update: Order Amended _x000D_6/6/2024:Update: Order Amended _x000D_5/6/2024:Update: Order Amended _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 9/9/2024:#Update - ECC approved (OOH) - awaiting Engineer availability to schedule appointment _x000D_6/9/2024:#Update - ECC approved (OOH) - awaiting Engineer availability to schedule appointment _x000D_5/9/2024:#Update - ECC approved (OOH) - awaiting Engineer availability to schedule appointment _x000D_4/9/2024:#Update - ECC approved (OOH) - awaiting Engineer availability to schedule appointment _x000D_3/9/2024:#Update - ECC approved (OOH) - awaiting Engineer availability to schedule appointment _x000D_2/9/2024:#Update - ECC approved (OOH) - awaiting Engineer availability to schedule appointment _x000D_29/8/2024:#Update - ECC approved (OOH) - awaiting Engineer availability to schedule appointment _x000D_28/8/2024:#Update - ECC approved (OOH) - awaiting Engineer availability to schedule appointment _x000D_27/8/2024:#Update - ECC approved (OOH) - awaiting Engineer availability to schedule appointment _x000D_22/8/2024:#Update - ECC approved (OOH) - awaiting Engineer availability to schedule appointment _x000D_21/8/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_20/8/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_19/8/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_19/8/2024:01406128 _x000D_16/8/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_15/8/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_14/8/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_13/8/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_12/8/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_9/8/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_8/8/2024:23/05/2024 _x000D_6/8/2024:23/05/2024 _x000D_5/8/2024:23/05/2024 _x000D_2/8/2024:23/05/2024 _x000D_1/8/2024:23/05/2024 _x000D_31/7/2024:23/05/2024 _x000D_31/7/2024:23/05/2024 _x000D_30/7/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_29/7/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_29/7/2024:01406128 _x000D_26/7/2024:01406128 _x000D_24/7/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_23/7/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_22/7/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_22/7/2024:#Update - #Update - OOH is required as scaffolding is needed; pedestrians walking past unable to use ladders and deploy tetra as this will be an obstruction. Internal works will need to be completed OOH as shop too busy. CSL liaising with Openreach to obtain estimation of hours required. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Your order has been delayed. Multiskilled engineer work is required for NCF work, Our Suppliers have given us a review date of 12/07/2024. We will continue to provide update as they become available. _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:Update: Order Amended _x000D_20/6/2024:Update: Order Amended _x000D_19/6/2024:Update: Order Amended _x000D_18/6/2024:Update: Order Amended _x000D_17/6/2024:Update: Order Amended _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:Update: Order Amended _x000D_7/6/2024:Update: Order Amended _x000D_6/6/2024:Update: Order Amended _x000D_5/6/2024:Update: Order Amended _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | Update: Order Amended | #Update - ECC approved (OOH) - awaiting Engineer availability to schedule appointment |  |  |  |  | 2.Allwyn to arrange access | VFP2338496 | 30015442 | 1.Provisioning | AM |  | 2024-05-22 | 2024-09-04 |  | 0 | [11 empty] | 0 | 671843
999 | 618253 | 1764 | Batch 4 Jun24 | Type 1 | FTTP | News Spot 2 | MANCHESTER | SK14 2QU | 2024-07-05 | 12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:Update: Order Amended _x000D_13/6/2024:Update: Order Amended _x000D_12/6/2024:Update: Order Amended _x000D_10/6/2024:Update: Order Amended _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:Update: Order Amended _x000D_13/6/2024:Update: Order Amended _x000D_12/6/2024:Update: Order Amended _x000D_10/6/2024:Update: Order Amended _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2337306 | 30015145 | 6.Failed router install | AM |  | 2024-06-04 | 2024-07-04 | 2024-07-09 | TRUE |  |  |  | 2024-08-09 |  |  |  | 2024-08-09 | 23A004948563 |  | 2024-08-12 | 1
1000 | 646754 | 1790 | Batch 4 Jun24 | Type 1 | FTTP/Mobile | Pra Lateshop Premier | Llanelli | SA15 1BU | 2024-06-07 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 15:13 _x000D_26/7/2024:22/07/2024 15:13 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_18/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_17/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_16/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_15/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_12/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_11/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_10/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_9/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_4/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_3/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_27/6/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:Update: Order Amended _x000D_19/6/2024:Update: Order Amended _x000D_18/6/2024:Update: Order Amended _x000D_17/6/2024:Update: Order Amended _x000D_14/6/2024:Update: Order Amended _x000D_13/6/2024:Update: Order Amended _x000D_12/6/2024:Delay on Engineer activities. Supplier will arrange new appointment _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 15:13 _x000D_26/7/2024:22/07/2024 15:13 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_18/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_17/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_16/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_15/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_12/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_11/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_10/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_9/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_4/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_3/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_27/6/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:Update: Order Amended _x000D_19/6/2024:Update: Order Amended _x000D_18/6/2024:Update: Order Amended _x000D_17/6/2024:Update: Order Amended _x000D_14/6/2024:Update: Order Amended _x000D_13/6/2024:Update: Order Amended _x000D_12/6/2024:Delay on Engineer activities. Supplier will arrange new appointment _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 0 | 0 | 2024-06-07 | 7/6/2024: CSL to provide an update |  |  | 5.CSL | VFP2383804 | 30015143 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
1001 | 655752 | 1834 | Batch 4 Jun24 | Type 1 | SoGEA/Mobile | Chapel News | Worthing | BN11 1EY | 2024-07-05 | 6/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 02/08 _x000D_5/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 02/08 _x000D_4/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 02/08 _x000D_3/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 02/08 _x000D_2/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 02/08 _x000D_29/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 02/08 _x000D_28/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 02/08 _x000D_27/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 02/08 _x000D_22/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 02/08 _x000D_21/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 02/08 _x000D_20/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_19/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_19/8/2024:01433910 _x000D_16/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_15/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_14/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_13/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_12/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_9/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_8/8/2024:27/06/2024 _x000D_6/8/2024:27/06/2024 _x000D_5/8/2024:27/06/2024 _x000D_2/8/2024:27/06/2024 _x000D_1/8/2024:27/06/2024 _x000D_31/7/2024:27/06/2024 _x000D_31/7/2024:27/06/2024 _x000D_30/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_29/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_29/7/2024:01433910 _x000D_26/7/2024:01433910 _x000D_24/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_23/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_22/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_22/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_4/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/07 AM _x000D_3/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/07 AM _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/07 AM _x000D_27/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/07 AM _x000D_25/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/07 AM _x000D_24/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/07 AM _x000D_20/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/07 AM _x000D_19/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/07 AM _x000D_18/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/07 AM _x000D_17/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/07 AM _x000D_14/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/07 AM _x000D_13/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/07 AM _x000D_12/6/2024:#Update - Allwyn have requested to change the date of the installation as the retailer is closed on 24/06 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_4/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_ | 9/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 02/08 _x000D_6/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 02/08 _x000D_5/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 02/08 _x000D_4/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 02/08 _x000D_3/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 02/08 _x000D_2/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 02/08 _x000D_29/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 02/08 _x000D_28/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 02/08 _x000D_27/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 02/08 _x000D_22/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 02/08 _x000D_21/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 02/08 _x000D_20/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_19/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_19/8/2024:01433910 _x000D_16/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_15/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_14/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_13/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_12/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_9/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_8/8/2024:27/06/2024 _x000D_6/8/2024:27/06/2024 _x000D_5/8/2024:27/06/2024 _x000D_2/8/2024:27/06/2024 _x000D_1/8/2024:27/06/2024 _x000D_31/7/2024:27/06/2024 _x000D_31/7/2024:27/06/2024 _x000D_30/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_29/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_29/7/2024:01433910 _x000D_26/7/2024:01433910 _x000D_24/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_23/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_22/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_22/7/2024:#Update - NFA - Allwyn confirmed new installation date with retailer _x000D_4/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/07 AM _x000D_3/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/07 AM _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/07 AM _x000D_27/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/07 AM _x000D_25/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/07 AM _x000D_24/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/07 AM _x000D_20/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/07 AM _x000D_19/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/07 AM _x000D_18/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/07 AM _x000D_17/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/07 AM _x000D_14/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/07 AM _x000D_13/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/07 AM _x000D_12/6/2024:#Update - Allwyn have requested to change the date of the installation as the retailer is closed on 24/06 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_4/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_ | 0 | #Update - awaiting ECC approval from customer - proposal sent to VF 02/08 | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFS983358 | 30015205 | 1.Provisioning | AM |  | 2024-06-12 | 2024-08-29 |  | 0 | [11 empty] | 0
1002 | 463898 | 3619 | Batch 5 Jul24 | Type 1 | SOGEA | B & K News Convenience Store | MILTON KEYNES | MK14 7AH | 2024-07-05 | 4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1013015 | 30016585 | 2.Commissioning |  |  | 2024-07-04 | 2024-07-04 | 2024-07-04 | TRUE |  |  |  | 2024-07-29 | [7 empty] | 0
1003 | 486401 | 3621 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | SPAR SEDBURY | CHEPSTOW | NP16 7AA |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 11:02 _x000D_26/7/2024:22/07/2024 11:02 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 11:02 _x000D_26/7/2024:22/07/2024 11:02 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2363458 | 30016297 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
1004 | 470720 | 3622 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | SPAR WATTON | Carbrooke | IP25 6XU |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 11:25 _x000D_26/7/2024:22/07/2024 11:25 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 11:25 _x000D_26/7/2024:22/07/2024 11:25 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2363459 | 30016312 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
1005 | 649129 | 3623 | Batch 5 Jul24 | Type 1 | FTTP | Costcutter | Tweedmouth | TD15 2AA | 2024-07-05 | 4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFP2363457 | 30016191 | 6.Failed router install |  |  | 2024-07-04 | 2024-07-04 | 2024-07-04 | TRUE |  |  |  | 2024-07-25 |  |  |  | 2024-07-25 | 242005013476 |  | 2024-07-26 | 1
1006 | 483769 | 3625 | Batch 5 Jul24 | Type 1 | SOGEA | SPAR BATCHLEY | Redditch | B97 6JB | 2024-07-05 | 4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1013012 | 30016593 | 6.Failed router install |  |  | 2024-07-04 | 2024-07-04 | 2024-07-04 | TRUE |  |  |  | 2024-07-26 |  |  |  | 2024-07-26 | 237004907586 |  | 2024-07-30 | 1
1007 | 633938 | 3628 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Gills Store | Cardiff | CF5 4DD |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 11:04 _x000D_26/7/2024:22/07/2024 11:04 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 11:04 _x000D_26/7/2024:22/07/2024 11:04 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2363453 | 30016306 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
1008 | 650222 | 3629 | Batch 5 Jul24 | Type 1 | FTTP | Chris's Premier | Sittingbourne | ME10 3LB | 2024-07-05 | 19/7/2024:#Update Retailer is happy with the new appointment on 31/07, AM. _x000D_18/7/2024:Update: Order Amended _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:#Update Retailer is happy with the new appointment on 31/07, AM. _x000D_18/7/2024:Update: Order Amended _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFP2363454 | 30016376 | 6.Failed router install |  |  | 2024-07-04 | 2024-07-04 | 2024-07-04 | TRUE |  |  |  | 2024-07-24 |  |  |  | 2024-07-24 | 242005008539 |  | 2024-07-29 | 1
1009 | 459893 | 3631 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Daves Convenience Lifestyle | WALSALL | WS2 7JY |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 11:13 _x000D_26/7/2024:22/07/2024 11:13 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_4/7/2024:Update: Order Completed by Supplier _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 11:13 _x000D_26/7/2024:22/07/2024 11:13 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_4/7/2024:Update: Order Completed by Supplier _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2363451 | 30016304 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
1010 | 645366 | 3632 | Batch 5 Jul24 | Type 1 | SOGEA | Londis Ruabon | WREXHAM | LL14 6EQ | 2024-07-05 | 4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1013011 | 30016407 | 2.Commissioning |  |  | 2024-07-04 | 2024-07-04 | 2024-07-04 | TRUE |  |  |  | 2024-08-06 | [7 empty] | 0
1011 | 662459 | 3634 | Batch 5 Jul24 | Type 1 | FTTP | A1 News & Wine | Ilford | IG1 2RZ | 2024-07-05 | 19/7/2024:#Update - Civil Work required. Completion date - 05/08. _x000D_18/7/2024:#Update - Civil Work required. Completion date - 05/08. _x000D_17/7/2024:#Update - Civil Work required. Completion date - 05/08. _x000D_16/7/2024:#Update - Civil Work required. Completion date - 05/08. _x000D_15/7/2024:#Update - Civil Work required. Completion date - 05/08. _x000D_12/7/2024:#Update - Duct work required. Supplier delay. Will provide update for 15/07 _x000D_11/7/2024:#Update - Duct work required. Supplier delay. Will provide update for 15/07 _x000D_10/7/2024:#Update - Duct work required. Supplier delay. Will provide update for 15/07 _x000D_9/7/2024:#Update - Duct work required. Supplier delay. Will provide update for 15/07 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:#Update - Civil Work required. Completion date - 05/08. _x000D_18/7/2024:#Update - Civil Work required. Completion date - 05/08. _x000D_17/7/2024:#Update - Civil Work required. Completion date - 05/08. _x000D_16/7/2024:#Update - Civil Work required. Completion date - 05/08. _x000D_15/7/2024:#Update - Civil Work required. Completion date - 05/08. _x000D_12/7/2024:#Update - Duct work required. Supplier delay. Will provide update for 15/07 _x000D_11/7/2024:#Update - Duct work required. Supplier delay. Will provide update for 15/07 _x000D_10/7/2024:#Update - Duct work required. Supplier delay. Will provide update for 15/07 _x000D_9/7/2024:#Update - Duct work required. Supplier delay. Will provide update for 15/07 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFP2363446 | 30016229 | 2.Commissioning |  |  | 2024-07-04 | 2024-07-04 | 2024-07-04 | TRUE |  |  |  | 2024-07-31 | [7 empty] | 0
1012 | 665927 | 3635 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Premier News | Luton | LU4 9PG | 2024-07-05 | 6/9/2024:#Update - still experiencing contractor delay and has been escalated by our supplier. They have given us a review date of 29/08/2024. _x000D_5/9/2024:#Update - still experiencing contractor delay and has been escalated by our supplier. They have given us a review date of 29/08/2024. _x000D_4/9/2024:#Update - still experiencing contractor delay and has been escalated by our supplier. They have given us a review date of 29/08/2024. _x000D_3/9/2024:#Update - still experiencing contractor delay and has been escalated by our supplier. They have given us a review date of 29/08/2024. _x000D_2/9/2024:#Update - still experiencing contractor delay and has been escalated by our supplier. They have given us a review date of 29/08/2024. _x000D_29/8/2024:#Update - still experiencing contractor delay and has been escalated by our supplier. They have given us a review date of 29/08/2024. _x000D_28/8/2024:#Update - still experiencing contractor delay and has been escalated by our supplier. They have given us a review date of 29/08/2024. _x000D_27/8/2024:#Update - still experiencing contractor delay and has been escalated by our supplier. They have given us a review date of 29/08/2024. _x000D_22/8/2024:#Update - still experiencing contractor delay and has been escalated by our supplier. They have given us a review date of 29/08/2024. _x000D_21/8/2024:#Update - still experiencing contractor delay and has been escalated by our supplier. They have given us a review date of 29/08/2024. _x000D_20/8/2024:#Update - still experiencing contractor delay and has been escalated by our supplier. They have given us a review date of 29/08/2024. _x000D_19/8/2024:#Update - still experiencing contractor delay and has been escalated by our supplier. They have given us a review date of 29/08/2024. _x000D_19/8/2024:01488204 _x000D_16/8/2024:#Update - Your order has been delayed. Civil work required. We will continue to provide update as they become available _x000D_15/8/2024:#Update - Your order has been delayed. Civil work required. We will continue to provide update as they become available _x000D_14/8/2024:#Update - Your order has been delayed. Civil work required. We will continue to provide update as they become available _x000D_13/8/2024:#Update - Your order has been delayed. Civil work required. We will continue to provide update as they become available _x000D_12/8/2024:#Update - Your order has been delayed. Civil work required. We will continue to provide update as they become available _x000D_9/8/2024:#Update - Your order has been delayed. Civil work required. We will continue to provide update as they become available _x000D_8/8/2024:25/07/2024 _x000D_6/8/2024:25/07/2024 _x000D_5/8/2024:25/07/2024 _x000D_2/8/2024:25/07/2024 _x000D_1/8/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_30/7/2024:#Update - Your order has been delayed. Civil work required. We will continue to provide update as they become available _x000D_29/7/2024:#Update - Your order has been delayed. Civil work required. We will continue to provide update as they become available _x000D_29/7/2024:01488204 _x000D_26/7/2024:01488204 _x000D_24/7/2024:#Update - Civil Work required. Completion date - 05/08. _x000D_23/7/2024:#Update - Civil Work required. Completion date - 05/08. _x000D_22/7/2024:#Update - Civil Work required. Completion date - 05/08. _x000D_22/7/2024:#Update - Civil Work required. Completion date - 05/08. _x000D_4/7/2024:Order Completed _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - still experiencing contractor delay and has been escalated by our supplier. They have given us a review date of 29/08/2024. _x000D_6/9/2024:#Update - still experiencing contractor delay and has been escalated by our supplier. They have given us a review date of 29/08/2024. _x000D_5/9/2024:#Update - still experiencing contractor delay and has been escalated by our supplier. They have given us a review date of 29/08/2024. _x000D_4/9/2024:#Update - still experiencing contractor delay and has been escalated by our supplier. They have given us a review date of 29/08/2024. _x000D_3/9/2024:#Update - still experiencing contractor delay and has been escalated by our supplier. They have given us a review date of 29/08/2024. _x000D_2/9/2024:#Update - still experiencing contractor delay and has been escalated by our supplier. They have given us a review date of 29/08/2024. _x000D_29/8/2024:#Update - still experiencing contractor delay and has been escalated by our supplier. They have given us a review date of 29/08/2024. _x000D_28/8/2024:#Update - still experiencing contractor delay and has been escalated by our supplier. They have given us a review date of 29/08/2024. _x000D_27/8/2024:#Update - still experiencing contractor delay and has been escalated by our supplier. They have given us a review date of 29/08/2024. _x000D_22/8/2024:#Update - still experiencing contractor delay and has been escalated by our supplier. They have given us a review date of 29/08/2024. _x000D_21/8/2024:#Update - still experiencing contractor delay and has been escalated by our supplier. They have given us a review date of 29/08/2024. _x000D_20/8/2024:#Update - still experiencing contractor delay and has been escalated by our supplier. They have given us a review date of 29/08/2024. _x000D_19/8/2024:#Update - still experiencing contractor delay and has been escalated by our supplier. They have given us a review date of 29/08/2024. _x000D_19/8/2024:01488204 _x000D_16/8/2024:#Update - Your order has been delayed. Civil work required. We will continue to provide update as they become available _x000D_15/8/2024:#Update - Your order has been delayed. Civil work required. We will continue to provide update as they become available _x000D_14/8/2024:#Update - Your order has been delayed. Civil work required. We will continue to provide update as they become available _x000D_13/8/2024:#Update - Your order has been delayed. Civil work required. We will continue to provide update as they become available _x000D_12/8/2024:#Update - Your order has been delayed. Civil work required. We will continue to provide update as they become available _x000D_9/8/2024:#Update - Your order has been delayed. Civil work required. We will continue to provide update as they become available _x000D_8/8/2024:25/07/2024 _x000D_6/8/2024:25/07/2024 _x000D_5/8/2024:25/07/2024 _x000D_2/8/2024:25/07/2024 _x000D_1/8/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_30/7/2024:#Update - Your order has been delayed. Civil work required. We will continue to provide update as they become available _x000D_29/7/2024:#Update - Your order has been delayed. Civil work required. We will continue to provide update as they become available _x000D_29/7/2024:01488204 _x000D_26/7/2024:01488204 _x000D_24/7/2024:#Update - Civil Work required. Completion date - 05/08. _x000D_23/7/2024:#Update - Civil Work required. Completion date - 05/08. _x000D_22/7/2024:#Update - Civil Work required. Completion date - 05/08. _x000D_22/7/2024:#Update - Civil Work required. Completion date - 05/08. _x000D_4/7/2024:Order Completed _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Your order has been delayed by our Suppliers due to Assistance being required to complete the installation. Please check with end user and re-appoint order for earliest date. | #Update - still experiencing contractor delay and has been escalated by our supplier. They have given us a review date of 29/08/2024. | 2024-06-07 |  |  |  | 5.CSL | VFP2363445 | 30016360 | 1.Provisioning | AM |  | 2024-07-04 | 2024-07-04 |  | 0 | [11 empty] | 0
1013 | 470249 | 3637 | Batch 5 Jul24 | Type 1 | SOGEA | Dash and Cox | GOSPORT | PO12 1SE | 2024-07-05 | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:Update: Order Amended _x000D_15/7/2024:Update: Order Amended _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:Update: Order Amended _x000D_15/7/2024:Update: Order Amended _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1013010 | 30016433 | 2.Commissioning |  |  | 2024-07-04 | 2024-07-04 | 2024-07-04 | TRUE |  |  |  | 2024-07-24 | [7 empty] | 0
1014 | 478074 | 3638 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Nairns | Duns | TD11 3BY | 2024-07-05 | 6/9/2024:#Update Advised by OR to cancel this order as there is no fibre available. They will advise when fibre becomes available and we will reraise. _x000D_5/9/2024:#Update Advised by OR to cancel this order as there is no fibre available. They will advise when fibre becomes available and we will reraise. _x000D_4/9/2024:#Update Advised by OR to cancel this order as there is no fibre available. They will advise when fibre becomes available and we will reraise. _x000D_3/9/2024:#Update Advised by OR to cancel this order as there is no fibre available. They will advise when fibre becomes available and we will reraise. _x000D_2/9/2024:#Update Advised by OR to cancel this order as there is no fibre available. They will advise when fibre becomes available and we will reraise. _x000D_29/8/2024:#Update Advised by OR to cancel this order as there is no fibre available. They will advise when fibre becomes available and we will reraise. _x000D_28/8/2024:#Update Advised by OR to cancel this order as there is no fibre available. They will advise when fibre becomes available and we will reraise. _x000D_27/8/2024:#Update Advised by OR to cancel this order as there is no fibre available. They will advise when fibre becomes available and we will reraise. _x000D_22/8/2024:#Update Advised by OR to cancel this order as there is no fibre available. They will advise when fibre becomes available and we will reraise. _x000D_21/8/2024:#Update Advised by OR to cancel this order as there is no fibre available. They will advise when fibre becomes available and we will reraise. _x000D_20/8/2024:#Update Advised by OR to cancel this order as there is no fibre available. They will advise when fibre becomes available and we will reraise. _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update Advised by OR to cancel this order as there is no fibre available. They will advise when fibre becomes available and we will reraise. _x000D_6/9/2024:#Update Advised by OR to cancel this order as there is no fibre available. They will advise when fibre becomes available and we will reraise. _x000D_5/9/2024:#Update Advised by OR to cancel this order as there is no fibre available. They will advise when fibre becomes available and we will reraise. _x000D_4/9/2024:#Update Advised by OR to cancel this order as there is no fibre available. They will advise when fibre becomes available and we will reraise. _x000D_3/9/2024:#Update Advised by OR to cancel this order as there is no fibre available. They will advise when fibre becomes available and we will reraise. _x000D_2/9/2024:#Update Advised by OR to cancel this order as there is no fibre available. They will advise when fibre becomes available and we will reraise. _x000D_29/8/2024:#Update Advised by OR to cancel this order as there is no fibre available. They will advise when fibre becomes available and we will reraise. _x000D_28/8/2024:#Update Advised by OR to cancel this order as there is no fibre available. They will advise when fibre becomes available and we will reraise. _x000D_27/8/2024:#Update Advised by OR to cancel this order as there is no fibre available. They will advise when fibre becomes available and we will reraise. _x000D_22/8/2024:#Update Advised by OR to cancel this order as there is no fibre available. They will advise when fibre becomes available and we will reraise. _x000D_21/8/2024:#Update Advised by OR to cancel this order as there is no fibre available. They will advise when fibre becomes available and we will reraise. _x000D_20/8/2024:#Update Advised by OR to cancel this order as there is no fibre available. They will advise when fibre becomes available and we will reraise. _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update Advised by OR to cancel this order as there is no fibre available. They will advise when fibre becomes available and we will reraise. | 2024-06-07 |  |  |  | 5.CSL | VFS1013009 | 30016449 | 1.Provisioning | AM |  | 2024-07-04 | 2024-08-28 |  | 0 | [11 empty] | 0
1015 | 672650 | 3640 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Spar | LISKEARD | PL14 6LJ | 2024-07-05 | 6/9/2024:#Update Moving to ST3 as the retailer does not want to do OOH & close shop. Costs on ECC _x000D_5/9/2024:#Update Moving to ST3 as the retailer does not want to do OOH & close shop. Costs on ECC _x000D_4/9/2024:#Update Moving to ST3 as the retailer does not want to do OOH & close shop. Costs on ECC _x000D_3/9/2024:#Update Moving to ST3 as the retailer does not want to do OOH & close shop. Costs on ECC _x000D_2/9/2024:#Update Moving to ST3 as the retailer does not want to do OOH & close shop. Costs on ECC _x000D_29/8/2024:#Update Moving to ST3 as the retailer does not want to do OOH & close shop. Costs on ECC _x000D_28/8/2024:#Update Moving to ST3 as the retailer does not want to do OOH & close shop. Costs on ECC _x000D_27/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_22/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_21/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_20/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_13/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_12/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_9/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_8/8/2024:22/07/2024 _x000D_6/8/2024:22/07/2024 _x000D_5/8/2024:22/07/2024 _x000D_2/8/2024:22/07/2024 _x000D_1/8/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_30/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_29/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_29/7/2024:01468509 _x000D_26/7/2024:01468509 _x000D_24/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_23/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_4/7/2024:Update: Order Completed by Supplier _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update Moving to ST3 as the retailer does not want to do OOH & close shop. Costs on ECC _x000D_6/9/2024:#Update Moving to ST3 as the retailer does not want to do OOH & close shop. Costs on ECC _x000D_5/9/2024:#Update Moving to ST3 as the retailer does not want to do OOH & close shop. Costs on ECC _x000D_4/9/2024:#Update Moving to ST3 as the retailer does not want to do OOH & close shop. Costs on ECC _x000D_3/9/2024:#Update Moving to ST3 as the retailer does not want to do OOH & close shop. Costs on ECC _x000D_2/9/2024:#Update Moving to ST3 as the retailer does not want to do OOH & close shop. Costs on ECC _x000D_29/8/2024:#Update Moving to ST3 as the retailer does not want to do OOH & close shop. Costs on ECC _x000D_28/8/2024:#Update Moving to ST3 as the retailer does not want to do OOH & close shop. Costs on ECC _x000D_27/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_22/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_21/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_20/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_13/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_12/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_9/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_8/8/2024:22/07/2024 _x000D_6/8/2024:22/07/2024 _x000D_5/8/2024:22/07/2024 _x000D_2/8/2024:22/07/2024 _x000D_1/8/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_30/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_29/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_29/7/2024:01468509 _x000D_26/7/2024:01468509 _x000D_24/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_23/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_4/7/2024:Update: Order Completed by Supplier _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update Moving to ST3 as the retailer does not want to do OOH & close shop. Costs on ECC | 2024-06-07 |  |  |  | 5.CSL | VFS1013008 | 30016531 | 1.Provisioning |  |  | 2024-07-04 | 2024-08-30 |  | 0 | [11 empty] | 0
1016 | 670422 | 3641 | Batch 5 Jul24 | Type 1 | FTTP | Geralds Supermarket | Dawlish | EX7 0PQ | 2024-07-05 | 19/7/2024:Update: Order Amended _x000D_18/7/2024:Update: Order Amended _x000D_17/7/2024:Update: Order Amended _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_11/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_10/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_9/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:Update: Order Amended _x000D_18/7/2024:Update: Order Amended _x000D_17/7/2024:Update: Order Amended _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_11/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_10/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_9/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1012393 | 30016608 | 6.Failed router install |  |  | 2024-07-04 | 2024-07-04 | 2024-07-04 | TRUE |  |  |  | 2024-07-26 |  |  |  | 2024-07-26 | 242005010467 |  |  | 1
1017 | 669546 | 3642 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | HASLAND SPSO & SPAR HASLAND | CHESTERFIELD | S41 0JF | 2024-07-05 | 6/9/2024:#Update Upgrade costs sent to VF for approval. _x000D_5/9/2024:#Update Upgrade costs sent to VF for approval. _x000D_4/9/2024:#Update Upgrade costs sent to VF for approval. _x000D_3/9/2024:#Update Upgrade costs sent to VF for approval. _x000D_2/9/2024:#Update Upgrade costs sent to VF for approval. _x000D_29/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_28/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_27/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_22/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_21/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_20/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_19/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_19/8/2024:01469094 _x000D_16/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_15/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_14/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_13/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_12/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_9/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_8/8/2024:22/07/2024 _x000D_6/8/2024:22/07/2024 _x000D_5/8/2024:22/07/2024 _x000D_2/8/2024:22/07/2024 _x000D_1/8/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_30/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_29/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_29/7/2024:01469094 _x000D_26/7/2024:01469094 _x000D_24/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_23/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update Upgrade costs sent to VF for approval. _x000D_6/9/2024:#Update Upgrade costs sent to VF for approval. _x000D_5/9/2024:#Update Upgrade costs sent to VF for approval. _x000D_4/9/2024:#Update Upgrade costs sent to VF for approval. _x000D_3/9/2024:#Update Upgrade costs sent to VF for approval. _x000D_2/9/2024:#Update Upgrade costs sent to VF for approval. _x000D_29/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_28/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_27/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_22/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_21/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_20/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_19/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_19/8/2024:01469094 _x000D_16/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_15/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_14/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_13/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_12/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_9/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_8/8/2024:22/07/2024 _x000D_6/8/2024:22/07/2024 _x000D_5/8/2024:22/07/2024 _x000D_2/8/2024:22/07/2024 _x000D_1/8/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_30/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_29/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_29/7/2024:01469094 _x000D_26/7/2024:01469094 _x000D_24/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_23/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update Upgrade costs sent to VF for approval. | 2024-06-07 |  |  |  | 5.CSL | VFP2363444 | 30016187 | 1.Provisioning | AM |  | 2024-07-04 | 2024-08-30 |  | 0 | [11 empty] | 0
1018 | 661758 | 3645 | Batch 5 Jul24 | Type 3 | FTTP | Singhs Premier | SHEFFIELD | S5 8TT | 2024-07-05 | 6/9/2024:#Update - Allwyn have requested for this site to move from a site type 1 to site type 3 _x000D_5/9/2024:#Update - Allwyn have requested for this site to move from a site type 1 to site type 3 _x000D_4/9/2024:#Update - Allwyn have requested for this site to move from a site type 1 to site type 3 _x000D_3/9/2024:#Update - Allwyn have requested for this site to move from a site type 1 to site type 3 _x000D_2/9/2024:#Update - Allwyn have requested for this site to move from a site type 1 to site type 3 _x000D_29/8/2024:#Update - Allwyn have requested for this site to move from a site type 1 to site type 3 _x000D_28/8/2024:#Update - Allwyn have requested for this site to move from a site type 1 to site type 3 _x000D_27/8/2024:#Update - Allwyn have requested for this site to move from a site type 1 to site type 3 _x000D_22/8/2024:#Update - Allwyn have requested for this site to move from a site type 1 to site type 3 _x000D_21/8/2024:#Update - Allwyn have requested for this site to move from a site type 1 to site type 3 _x000D_20/8/2024:#Update - Allwyn have requested for this site to move from a site type 1 to site type 3 _x000D_19/8/2024:#Update - Allwyn have requested for this site to move from a site type 1 to site type 3 _x000D_19/8/2024:01468340 _x000D_16/8/2024:#Update - Allwyn have requested for this site to move from a site type 1 to site type 3 _x000D_15/8/2024:#Update - Allwyn have requested for this site to move from a site type 1 to site type 3 _x000D_14/8/2024:#Update - Allwyn have requested for this site to move from a site type 1 to site type 3 _x000D_13/8/2024:#Update - Allwyn have requested for this site to move from a site type 1 to site type 3 _x000D_12/8/2024:#Update - Allwyn have requested for this site to move from a site type 1 to site type 3 _x000D_9/8/2024:#Update - Allwyn have requested for this site to move from a site type 1 to site type 3 _x000D_8/8/2024:25/07/2024 _x000D_6/8/2024:25/07/2024 _x000D_5/8/2024:25/07/2024 _x000D_2/8/2024:25/07/2024 _x000D_1/8/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_30/7/2024:#Update - Allwyn have requested for this site to move from a site type 1 to site type 3 _x000D_29/7/2024:#Update - Allwyn have requested for this site to move from a site type 1 to site type 3 _x000D_29/7/2024:01468340 _x000D_26/7/2024:01468340 _x000D_24/7/2024:#Update - ECC proposal sent to Vodafone on 11/07 _x000D_23/7/2024:#Update - ECC proposal sent to Vodafone on 11/07 _x000D_22/7/2024:#Update - ECC proposal sent to Vodafone on 11/07 _x000D_22/7/2024:#Update - ECC proposal sent to Vodafone on 11/07 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:Your order has been delayed due to a customer missed appointment. Incorrect Address Please check with end user and reappoint the order if still required. _x000D_11/7/2024:Your order has been delayed due to a customer missed appointment. Incorrect Address Please check with end user and reappoint the order if still required. _x000D_10/7/2024:Your order has been delayed due to a customer missed appointment. Incorrect Address Please check with end user and reappoint the order if still required. _x000D_9/7/2024:Your order has been delayed due to a customer missed appointment. Incorrect Address Please check with end user and reappoint the order if still required. _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn have requested for this site to move from a site type 1 to site type 3 _x000D_6/9/2024:#Update - Allwyn have requested for this site to move from a site type 1 to site type 3 _x000D_5/9/2024:#Update - Allwyn have requested for this site to move from a site type 1 to site type 3 _x000D_4/9/2024:#Update - Allwyn have requested for this site to move from a site type 1 to site type 3 _x000D_3/9/2024:#Update - Allwyn have requested for this site to move from a site type 1 to site type 3 _x000D_2/9/2024:#Update - Allwyn have requested for this site to move from a site type 1 to site type 3 _x000D_29/8/2024:#Update - Allwyn have requested for this site to move from a site type 1 to site type 3 _x000D_28/8/2024:#Update - Allwyn have requested for this site to move from a site type 1 to site type 3 _x000D_27/8/2024:#Update - Allwyn have requested for this site to move from a site type 1 to site type 3 _x000D_22/8/2024:#Update - Allwyn have requested for this site to move from a site type 1 to site type 3 _x000D_21/8/2024:#Update - Allwyn have requested for this site to move from a site type 1 to site type 3 _x000D_20/8/2024:#Update - Allwyn have requested for this site to move from a site type 1 to site type 3 _x000D_19/8/2024:#Update - Allwyn have requested for this site to move from a site type 1 to site type 3 _x000D_19/8/2024:01468340 _x000D_16/8/2024:#Update - Allwyn have requested for this site to move from a site type 1 to site type 3 _x000D_15/8/2024:#Update - Allwyn have requested for this site to move from a site type 1 to site type 3 _x000D_14/8/2024:#Update - Allwyn have requested for this site to move from a site type 1 to site type 3 _x000D_13/8/2024:#Update - Allwyn have requested for this site to move from a site type 1 to site type 3 _x000D_12/8/2024:#Update - Allwyn have requested for this site to move from a site type 1 to site type 3 _x000D_9/8/2024:#Update - Allwyn have requested for this site to move from a site type 1 to site type 3 _x000D_8/8/2024:25/07/2024 _x000D_6/8/2024:25/07/2024 _x000D_5/8/2024:25/07/2024 _x000D_2/8/2024:25/07/2024 _x000D_1/8/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_30/7/2024:#Update - Allwyn have requested for this site to move from a site type 1 to site type 3 _x000D_29/7/2024:#Update - Allwyn have requested for this site to move from a site type 1 to site type 3 _x000D_29/7/2024:01468340 _x000D_26/7/2024:01468340 _x000D_24/7/2024:#Update - ECC proposal sent to Vodafone on 11/07 _x000D_23/7/2024:#Update - ECC proposal sent to Vodafone on 11/07 _x000D_22/7/2024:#Update - ECC proposal sent to Vodafone on 11/07 _x000D_22/7/2024:#Update - ECC proposal sent to Vodafone on 11/07 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:Your order has been delayed due to a customer missed appointment. Incorrect Address Please check with end user and reappoint the order if still required. _x000D_11/7/2024:Your order has been delayed due to a customer missed appointment. Incorrect Address Please check with end user and reappoint the order if still required. _x000D_10/7/2024:Your order has been delayed due to a customer missed appointment. Incorrect Address Please check with end user and reappoint the order if still required. _x000D_9/7/2024:Your order has been delayed due to a customer missed appointment. Incorrect Address Please check with end user and reappoint the order if still required. _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update - Allwyn have requested for this site to move from a site type 1 to site type 3 | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | Order Cancelled | Order Cancelled | 2.Commissioning | [9 empty] | 2024-08-15 | [7 empty] | 0
1019 | 624910 | 3646 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Our Supermarket | Croydon | CR0 3JL | 2024-09-04 | 6/9/2024:#Update Retailer happy with new appointment 03/09, AM. _x000D_5/9/2024:#Update Retailer happy with new appointment 03/09, AM. _x000D_4/9/2024:#Update Retailer happy with new appointment 03/09, AM. _x000D_3/9/2024:#Update Retailer happy with new appointment 03/09, AM. _x000D_2/9/2024:#Update Retailer happy with new appointment 03/09, AM. _x000D_29/8/2024:#Update Retailer happy with new appointment 03/09, AM. _x000D_28/8/2024:#Update Retailer happy with new appointment 03/09, AM. _x000D_27/8/2024:#Update Retailer happy with new appointment 03/09, AM. _x000D_22/8/2024:#Update Retailer happy with new appointment 03/09, AM. _x000D_21/8/2024:#Update Retailer happy with new appointment 03/09, AM. _x000D_20/8/2024:#Update Retailer happy with new appointment 03/09, AM. _x000D_19/8/2024:#Update Retailer happy with new appointment 03/09, AM. _x000D_19/8/2024:01468793 _x000D_16/8/2024:#Update Retailer happy with new appointment 03/09, AM. _x000D_15/8/2024:#Update Retailer happy with new appointment 03/09, AM. _x000D_14/8/2024:#Update Retailer happy with new appointment 03/09, AM. _x000D_13/8/2024:#Update Retailer happy with new appointment 03/09, AM. _x000D_12/8/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update Retailer happy with new appointment 03/09, AM. _x000D_6/9/2024:#Update Retailer happy with new appointment 03/09, AM. _x000D_5/9/2024:#Update Retailer happy with new appointment 03/09, AM. _x000D_4/9/2024:#Update Retailer happy with new appointment 03/09, AM. _x000D_3/9/2024:#Update Retailer happy with new appointment 03/09, AM. _x000D_2/9/2024:#Update Retailer happy with new appointment 03/09, AM. _x000D_29/8/2024:#Update Retailer happy with new appointment 03/09, AM. _x000D_28/8/2024:#Update Retailer happy with new appointment 03/09, AM. _x000D_27/8/2024:#Update Retailer happy with new appointment 03/09, AM. _x000D_22/8/2024:#Update Retailer happy with new appointment 03/09, AM. _x000D_21/8/2024:#Update Retailer happy with new appointment 03/09, AM. _x000D_20/8/2024:#Update Retailer happy with new appointment 03/09, AM. _x000D_19/8/2024:#Update Retailer happy with new appointment 03/09, AM. _x000D_19/8/2024:01468793 _x000D_16/8/2024:#Update Retailer happy with new appointment 03/09, AM. _x000D_15/8/2024:#Update Retailer happy with new appointment 03/09, AM. _x000D_14/8/2024:#Update Retailer happy with new appointment 03/09, AM. _x000D_13/8/2024:#Update Retailer happy with new appointment 03/09, AM. _x000D_12/8/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Order Completed | #Update Retailer happy with new appointment 03/09, AM. | 2024-06-07 |  |  |  | 5.CSL | VFP2431357 | 30016239 | 2.Commissioning | AM |  | 2024-07-04 | 2024-09-03 |  | 0 | [11 empty] | 0
1020 | 446123 | 3647 | Batch 5 Jul24 | Type 1 | SOGEA | Spar | ARMAGH | BT61 7QX | 2024-07-05 | 4/7/2024:Order Completed _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 4/7/2024:Order Completed _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1013006 | 30016582 | 6.Failed router install |  |  | 2024-07-04 | 2024-07-04 | 2024-07-04 | TRUE |  |  |  | 2024-07-24 |  |  |  | 2024-07-24 | 242005010432 |  | 2024-07-25 | 1
1021 | 633025 | 3648 | Batch 5 Jul24 | Type 1 | FTTP | Lifestyle Express | Hemsworth | WF9 4AS | 2024-07-05 | 19/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_18/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_17/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_16/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_15/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_12/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_11/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_10/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_9/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_18/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_17/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_16/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_15/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_12/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_11/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_10/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_9/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFP2363440 | 30016301 | 6.Failed router install |  |  | 2024-07-04 | 2024-07-04 | 2024-07-04 | TRUE |  |  |  | 2024-07-26 |  |  |  | 2024-07-26 | 238004924263 |  | 2024-07-29 | 1
1022 | 466464 | 3649 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Mjs Nisa Local | SHEFFIELD | S5 9FL | 2024-07-05 | 6/9/2024:#Update Retailer confirmed 03/09, AM. _x000D_5/9/2024:#Update Retailer confirmed 03/09, AM. _x000D_4/9/2024:#Update Retailer confirmed 03/09, AM. _x000D_3/9/2024:#Update Retailer confirmed 03/09, AM. _x000D_2/9/2024:#Update Retailer confirmed 03/09, AM. _x000D_29/8/2024:#Update Retailer confirmed 03/09, AM. _x000D_28/8/2024:#Update Retailer confirmed 03/09, AM. _x000D_27/8/2024:#Update Retailer confirmed 03/09, AM. _x000D_22/8/2024:#Update Retailer confirmed 03/09, AM. _x000D_21/8/2024:#Update Retailer confirmed 03/09, AM. _x000D_20/8/2024:#Update Retailer confirmed 03/09, AM. _x000D_19/8/2024:#Update VF to approve upgrade charge _x000D_19/8/2024:01467589 _x000D_16/8/2024:#Update VF to approve upgrade charge _x000D_15/8/2024:#Update VF to approve upgrade charge _x000D_14/8/2024:#Update VF to approve upgrade charge _x000D_13/8/2024:#Update VF to approve upgrade charge _x000D_12/8/2024:#Update VF to approve upgrade charge _x000D_9/8/2024:#Update VF to approve upgrade charge _x000D_8/8/2024:25/07/2024 _x000D_6/8/2024:25/07/2024 _x000D_5/8/2024:25/07/2024 _x000D_2/8/2024:25/07/2024 _x000D_1/8/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_30/7/2024:#Update VF to approve upgrade charge _x000D_29/7/2024:#Update VF to approve upgrade charge _x000D_29/7/2024:01467589 _x000D_26/7/2024:01467589 _x000D_24/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_23/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_22/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_22/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:Update: Order Amended _x000D_25/6/2024:Update: Order Amended _x000D_24/6/2024:Update: Order Amended _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update Retailer confirmed 03/09, AM. _x000D_6/9/2024:#Update Retailer confirmed 03/09, AM. _x000D_5/9/2024:#Update Retailer confirmed 03/09, AM. _x000D_4/9/2024:#Update Retailer confirmed 03/09, AM. _x000D_3/9/2024:#Update Retailer confirmed 03/09, AM. _x000D_2/9/2024:#Update Retailer confirmed 03/09, AM. _x000D_29/8/2024:#Update Retailer confirmed 03/09, AM. _x000D_28/8/2024:#Update Retailer confirmed 03/09, AM. _x000D_27/8/2024:#Update Retailer confirmed 03/09, AM. _x000D_22/8/2024:#Update Retailer confirmed 03/09, AM. _x000D_21/8/2024:#Update Retailer confirmed 03/09, AM. _x000D_20/8/2024:#Update Retailer confirmed 03/09, AM. _x000D_19/8/2024:#Update VF to approve upgrade charge _x000D_19/8/2024:01467589 _x000D_16/8/2024:#Update VF to approve upgrade charge _x000D_15/8/2024:#Update VF to approve upgrade charge _x000D_14/8/2024:#Update VF to approve upgrade charge _x000D_13/8/2024:#Update VF to approve upgrade charge _x000D_12/8/2024:#Update VF to approve upgrade charge _x000D_9/8/2024:#Update VF to approve upgrade charge _x000D_8/8/2024:25/07/2024 _x000D_6/8/2024:25/07/2024 _x000D_5/8/2024:25/07/2024 _x000D_2/8/2024:25/07/2024 _x000D_1/8/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_30/7/2024:#Update VF to approve upgrade charge _x000D_29/7/2024:#Update VF to approve upgrade charge _x000D_29/7/2024:01467589 _x000D_26/7/2024:01467589 _x000D_24/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_23/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_22/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_22/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:Update: Order Amended _x000D_25/6/2024:Update: Order Amended _x000D_24/6/2024:Update: Order Amended _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update Retailer confirmed 03/09, AM. | 2024-06-07 |  |  |  | 5.CSL | VFP2363439 | 30016351 | 1.Provisioning | AM |  | 2024-07-04 | 2024-08-28 |  | 0 | [11 empty] | 0
1023 | 633644 | 3650 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Premier | MANCHESTER | M9 6RG | 2024-08-28 | 29/8/2024:Order Completed _x000D_28/8/2024:Order Completed _x000D_27/8/2024:Order Completed _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:Update: Order Amended _x000D_31/7/2024:36899 _x000D_30/7/2024:Update: Order Amended _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:24/07/2024 08:06 _x000D_26/7/2024:24/07/2024 08:06 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Order Completed _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 17/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_15/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 17/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_12/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 17/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_11/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 17/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_10/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 17/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_9/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 10/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_4/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 08-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 29/8/2024:Order Completed _x000D_28/8/2024:Order Completed _x000D_27/8/2024:Order Completed _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:Update: Order Amended _x000D_31/7/2024:36899 _x000D_30/7/2024:Update: Order Amended _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:24/07/2024 08:06 _x000D_26/7/2024:24/07/2024 08:06 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Order Completed _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 17/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_15/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 17/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_12/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 17/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_11/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 17/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_10/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 17/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_9/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 10/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_4/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 08-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1013005 | 30016425 | 2.Commissioning | AM |  | 2024-08-28 | 2024-08-27 |  | 0 | [11 empty] | 0
1024 | 487321 | 3653 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Budgens | Brandon | IP27 0QW |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 11:25 _x000D_26/7/2024:22/07/2024 11:25 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_4/7/2024:Order Completed _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 11:25 _x000D_26/7/2024:22/07/2024 11:25 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_4/7/2024:Order Completed _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2363438 | 30016228 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
1025 | 461747 | 3658 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | VIVO ESSENTIALS | BELFAST | BT13 3RQ | 2024-08-29 | 29/8/2024:#Update - Order has been delayed as civils work is required. CSL will update as more information become available. _x000D_28/8/2024:#Update - Order has been delayed as civils work is required. CSL will update as more information become available. _x000D_27/8/2024:#Update - Order has been delayed as civils work is required. CSL will update as more information become available. _x000D_22/8/2024:#Update - Order has been delayed as civils work is required. CSL will update as more information become available. _x000D_21/8/2024:#Update - Order has been delayed as civils work is required. CSL will update as more information become available. _x000D_20/8/2024:#Update - Order has been delayed as civils work is required. CSL will update as more information become available. _x000D_19/8/2024:#Update - Order has been delayed as civils work is required. CSL will update as more information become available. _x000D_19/8/2024:01579129 _x000D_16/8/2024:#Update - Order has been delayed as civils work is required. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order has been delayed as civils work is required. CSL will update as more information become available. _x000D_14/8/2024:#Update - Order has been delayed as civils work is required. CSL will update as more information become available. _x000D_13/8/2024:#Update - Order has been delayed as civils work is required. CSL will update as more information become available. _x000D_12/8/2024:Your order is still experiencing contractor delay and has been escalated by our supplier. They have given us a review date of 12/08/2024. We will continue to provide updates as they become available. _x000D_9/8/2024:Your order is still experiencing contractor delay and has been escalated by our supplier. They have given us a review date of 12/08/2024. We will continue to provide updates as they become available. _x000D_8/8/2024:Your order is still experiencing contractor delay and has been escalated by our supplier. They have given us a review date of 12/08/2024. We will continue to provide updates as they become available. _x000D_6/8/2024:Your order is still experiencing contractor delay and has been escalated by our supplier. They have given us a review date of 12/08/2024. We will continue to provide updates as they become available. _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Your order has been delayed. Civils work required. Our Suppliers have given us a review date of 05/08/2024. We will continue to provide update as they become available. _x000D_23/7/2024:Your order has been delayed. Civils work required. Our Suppliers have given us a review date of 05/08/2024. We will continue to provide update as they become available. _x000D_22/7/2024:Your order has been delayed. Civils work required. Our Suppliers have given us a review date of 05/08/2024. We will continue to provide update as they become available. _x000D_22/7/2024:Your order has been delayed. Civils work required. Our Suppliers have given us a review date of 05/08/2024. We will continue to provide update as they become available. _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 29/8/2024:#Update - Order has been delayed as civils work is required. CSL will update as more information become available. _x000D_28/8/2024:#Update - Order has been delayed as civils work is required. CSL will update as more information become available. _x000D_27/8/2024:#Update - Order has been delayed as civils work is required. CSL will update as more information become available. _x000D_22/8/2024:#Update - Order has been delayed as civils work is required. CSL will update as more information become available. _x000D_21/8/2024:#Update - Order has been delayed as civils work is required. CSL will update as more information become available. _x000D_20/8/2024:#Update - Order has been delayed as civils work is required. CSL will update as more information become available. _x000D_19/8/2024:#Update - Order has been delayed as civils work is required. CSL will update as more information become available. _x000D_19/8/2024:01579129 _x000D_16/8/2024:#Update - Order has been delayed as civils work is required. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order has been delayed as civils work is required. CSL will update as more information become available. _x000D_14/8/2024:#Update - Order has been delayed as civils work is required. CSL will update as more information become available. _x000D_13/8/2024:#Update - Order has been delayed as civils work is required. CSL will update as more information become available. _x000D_12/8/2024:Your order is still experiencing contractor delay and has been escalated by our supplier. They have given us a review date of 12/08/2024. We will continue to provide updates as they become available. _x000D_9/8/2024:Your order is still experiencing contractor delay and has been escalated by our supplier. They have given us a review date of 12/08/2024. We will continue to provide updates as they become available. _x000D_8/8/2024:Your order is still experiencing contractor delay and has been escalated by our supplier. They have given us a review date of 12/08/2024. We will continue to provide updates as they become available. _x000D_6/8/2024:Your order is still experiencing contractor delay and has been escalated by our supplier. They have given us a review date of 12/08/2024. We will continue to provide updates as they become available. _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Your order has been delayed. Civils work required. Our Suppliers have given us a review date of 05/08/2024. We will continue to provide update as they become available. _x000D_23/7/2024:Your order has been delayed. Civils work required. Our Suppliers have given us a review date of 05/08/2024. We will continue to provide update as they become available. _x000D_22/7/2024:Your order has been delayed. Civils work required. Our Suppliers have given us a review date of 05/08/2024. We will continue to provide update as they become available. _x000D_22/7/2024:Your order has been delayed. Civils work required. Our Suppliers have given us a review date of 05/08/2024. We will continue to provide update as they become available. _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 5.CSL | VFP2363435 | 30016247 | 2.Commissioning | AM |  | 2024-07-04 | 2024-07-04 |  | 0 | [11 empty] | 0
1026 | 460373 | 3659 | Batch 5 Jul24 | Type 1 | FTTP | Rubys Londis | BEXLEYHEATH | DA7 5HD | 2024-07-05 | 4/7/2024:Update: Order Completed by Supplier _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 4/7/2024:Update: Order Completed by Supplier _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFP2363433 | 30016382 | 2.Commissioning |  |  | 2024-07-04 | 2024-07-04 | 2024-07-04 | TRUE |  |  |  | 2024-07-24 | [7 empty] | 0
1027 | 458538 | 3665 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Nisa Local | MOTHERWELL | ML1 2LS |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 11:27 _x000D_26/7/2024:22/07/2024 11:27 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_4/7/2024:Order Completed _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 11:27 _x000D_26/7/2024:22/07/2024 11:27 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_4/7/2024:Order Completed _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2363430 | 30016257 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
1028 | 653924 | 3670 | Batch 5 Jul24 | Type 1 | SOGEA | Morrisons Daily | Bradford | BD9 5EP | 2024-07-05 | 4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1012995 | 30016408 | 6.Failed router install |  |  | 2024-07-04 | 2024-07-04 | 2024-07-04 | TRUE |  |  |  | 2024-07-26 |  |  |  | 2024-07-26 | 23A004948656 |  | 2024-07-29 | 1
1029 | 660169 | 3672 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Spar | Dungannon | BT71 4AA | 2024-07-05 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:#Update - delayed by our Suppliers due to Traffic Management being required to complete the installation. Order now re-appointed for 20/08/2024 AM slot. _x000D_21/8/2024:#Update - delayed by our Suppliers due to Traffic Management being required to complete the installation. Order now re-appointed for 20/08/2024 AM slot. _x000D_20/8/2024:#Update - delayed by our Suppliers due to Traffic Management being required to complete the installation. Order now re-appointed for 20/08/2024 AM slot. _x000D_19/8/2024:#Update - delayed by our Suppliers due to Traffic Management being required to complete the installation. Order now re-appointed for 20/08/2024 AM slot. _x000D_19/8/2024:01467759 _x000D_16/8/2024:#Update - delayed by our Suppliers due to Traffic Management being required to complete the installation. Order now re-appointed for 20/08/2024 AM slot. _x000D_15/8/2024:#Update - delayed by our Suppliers due to Traffic Management being required to complete the installation. Order now re-appointed for 20/08/2024 AM slot. _x000D_14/8/2024:#Update - delayed by our Suppliers due to Traffic Management being required to complete the installation. Order now re-appointed for 20/08/2024 AM slot. _x000D_13/8/2024:#Update - delayed by our Suppliers due to Traffic Management being required to complete the installation. Order now re-appointed for 20/08/2024 AM slot. _x000D_12/8/2024:#Update - delayed by our Suppliers due to Traffic Management being required to complete the installation. Order now re-appointed for 20/08/2024 AM slot. _x000D_9/8/2024:#Update - delayed by our Suppliers due to Traffic Management being required to complete the installation. Order now re-appointed for 20/08/2024 AM slot. _x000D_8/8/2024:31/07/2024 _x000D_6/8/2024:31/07/2024 _x000D_5/8/2024:31/07/2024 _x000D_2/8/2024:31/07/2024 _x000D_1/8/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_30/7/2024:#Update - Appointment has been confirmed, hopefully this new appoint goes smoothly. _x000D_29/7/2024:#Update - Appointment has been confirmed, hopefully this new appoint goes smoothly. _x000D_29/7/2024:01467759 _x000D_26/7/2024:01467759 _x000D_24/7/2024:#Update - Appointment has been confirmed, hopefully this new appoint goes smoothly. _x000D_23/7/2024:#Update - Appointment has been confirmed, hopefully this new appoint goes smoothly. _x000D_22/7/2024:#Update - Appointment has been confirmed, hopefully this new appoint goes smoothly. _x000D_22/7/2024:#Update - Appointment has been confirmed, hopefully this new appoint goes smoothly. _x000D_19/7/2024:#Update customer missed appointment due to being unaware of visit. Rescheduled for 18/07 AM _x000D_18/7/2024:#Update customer missed appointment due to being unaware of visit. Rescheduled for 18/07 AM _x000D_17/7/2024:#Update customer missed appointment due to being unaware of visit. Rescheduled for 18/07 AM _x000D_16/7/2024:#Update customer missed appointment due to being unaware of visit. Rescheduled for 18/07 AM _x000D_15/7/2024:#Update customer missed appointment due to being unaware of visit. Rescheduled for 18/07 AM _x000D_12/7/2024:#Update customer missed appointment due to being unaware of visit. Rescheduled for 18/07 AM _x000D_11/7/2024:#Update customer missed appointment due to being unaware of visit. Rescheduled for 18/07 AM _x000D_10/7/2024:#Update customer missed appointment due to being unaware of visit. Rescheduled for 18/07 AM _x000D_9/7/2024:#Update customer missed appointment due to being unaware of visit. Rescheduled for 18/07 AM _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:#Update - delayed by our Suppliers due to Traffic Management being required to complete the installation. Order now re-appointed for 20/08/2024 AM slot. _x000D_21/8/2024:#Update - delayed by our Suppliers due to Traffic Management being required to complete the installation. Order now re-appointed for 20/08/2024 AM slot. _x000D_20/8/2024:#Update - delayed by our Suppliers due to Traffic Management being required to complete the installation. Order now re-appointed for 20/08/2024 AM slot. _x000D_19/8/2024:#Update - delayed by our Suppliers due to Traffic Management being required to complete the installation. Order now re-appointed for 20/08/2024 AM slot. _x000D_19/8/2024:01467759 _x000D_16/8/2024:#Update - delayed by our Suppliers due to Traffic Management being required to complete the installation. Order now re-appointed for 20/08/2024 AM slot. _x000D_15/8/2024:#Update - delayed by our Suppliers due to Traffic Management being required to complete the installation. Order now re-appointed for 20/08/2024 AM slot. _x000D_14/8/2024:#Update - delayed by our Suppliers due to Traffic Management being required to complete the installation. Order now re-appointed for 20/08/2024 AM slot. _x000D_13/8/2024:#Update - delayed by our Suppliers due to Traffic Management being required to complete the installation. Order now re-appointed for 20/08/2024 AM slot. _x000D_12/8/2024:#Update - delayed by our Suppliers due to Traffic Management being required to complete the installation. Order now re-appointed for 20/08/2024 AM slot. _x000D_9/8/2024:#Update - delayed by our Suppliers due to Traffic Management being required to complete the installation. Order now re-appointed for 20/08/2024 AM slot. _x000D_8/8/2024:31/07/2024 _x000D_6/8/2024:31/07/2024 _x000D_5/8/2024:31/07/2024 _x000D_2/8/2024:31/07/2024 _x000D_1/8/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_30/7/2024:#Update - Appointment has been confirmed, hopefully this new appoint goes smoothly. _x000D_29/7/2024:#Update - Appointment has been confirmed, hopefully this new appoint goes smoothly. _x000D_29/7/2024:01467759 _x000D_26/7/2024:01467759 _x000D_24/7/2024:#Update - Appointment has been confirmed, hopefully this new appoint goes smoothly. _x000D_23/7/2024:#Update - Appointment has been confirmed, hopefully this new appoint goes smoothly. _x000D_22/7/2024:#Update - Appointment has been confirmed, hopefully this new appoint goes smoothly. _x000D_22/7/2024:#Update - Appointment has been confirmed, hopefully this new appoint goes smoothly. _x000D_19/7/2024:#Update customer missed appointment due to being unaware of visit. Rescheduled for 18/07 AM _x000D_18/7/2024:#Update customer missed appointment due to being unaware of visit. Rescheduled for 18/07 AM _x000D_17/7/2024:#Update customer missed appointment due to being unaware of visit. Rescheduled for 18/07 AM _x000D_16/7/2024:#Update customer missed appointment due to being unaware of visit. Rescheduled for 18/07 AM _x000D_15/7/2024:#Update customer missed appointment due to being unaware of visit. Rescheduled for 18/07 AM _x000D_12/7/2024:#Update customer missed appointment due to being unaware of visit. Rescheduled for 18/07 AM _x000D_11/7/2024:#Update customer missed appointment due to being unaware of visit. Rescheduled for 18/07 AM _x000D_10/7/2024:#Update customer missed appointment due to being unaware of visit. Rescheduled for 18/07 AM _x000D_9/7/2024:#Update customer missed appointment due to being unaware of visit. Rescheduled for 18/07 AM _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | 0 | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2363429 | 30016222 | 2.Commissioning | AM |  | 2024-07-04 | 2024-08-20 |  | 0 |  |  |  | 2024-09-27 | [7 empty] | 0
1030 | 647612 | 3675 | Batch 5 Jul24 | Type 1 | FTTP | Key Store Premier | Goole | DN14 5UN | 2024-07-05 | 4/7/2024:Update: Order Completed by Supplier _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 4/7/2024:Update: Order Completed by Supplier _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFP2363431 | 30016262 | 6.Failed router install |  |  | 2024-07-04 | 2024-07-04 | 2024-07-04 | TRUE |  |  |  | 2024-07-27 |  |  |  | 2024-07-23 | 242005013479 |  | 2024-07-24 | 1
1031 | 665286 | 1067 | Batch 3 May24 | Type 1 | SoGEA/Mobile | Post Office | BARNSLEY | S70 5AB | 2024-06-07 | 6/9/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_5/9/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_4/9/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_3/9/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_2/9/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_29/8/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_28/8/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_27/8/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_22/8/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_21/8/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_20/8/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_19/8/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_19/8/2024:01405739 _x000D_16/8/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_15/8/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_14/8/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_13/8/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_12/8/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_9/8/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_8/8/2024:30/05/2024 _x000D_6/8/2024:30/05/2024 _x000D_5/8/2024:30/05/2024 _x000D_2/8/2024:30/05/2024 _x000D_1/8/2024:30/05/2024 _x000D_31/7/2024:30/05/2024 _x000D_31/7/2024:30/05/2024 _x000D_30/7/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_29/7/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_29/7/2024:01405739 _x000D_26/7/2024:01405739 _x000D_24/7/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_23/7/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_22/7/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_22/7/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_6/9/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_5/9/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_4/9/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_3/9/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_2/9/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_29/8/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_28/8/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_27/8/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_22/8/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_21/8/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_20/8/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_19/8/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_19/8/2024:01405739 _x000D_16/8/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_15/8/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_14/8/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_13/8/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_12/8/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_9/8/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_8/8/2024:30/05/2024 _x000D_6/8/2024:30/05/2024 _x000D_5/8/2024:30/05/2024 _x000D_2/8/2024:30/05/2024 _x000D_1/8/2024:30/05/2024 _x000D_31/7/2024:30/05/2024 _x000D_31/7/2024:30/05/2024 _x000D_30/7/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_29/7/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_29/7/2024:01405739 _x000D_26/7/2024:01405739 _x000D_24/7/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_23/7/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_22/7/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_22/7/2024:#Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update:- Difficult install, currently awaiting clarification on the scope from OR. Likely will need to be upgraded or TRC's applied. | 2024-05-23 | 23/05/24: Allwyn to arrange access on the new date |  |  | 2.Allwyn to arrange access | VFS978354 | 30013957 | 1.Provisioning | AM |  | 2024-05-22 | 2024-07-16 |  | 0 | [11 empty] | 0
1032 | 472233 | 3679 | Batch 5 Jul24 | Type 1 | FTTP | Premier | Rotherham | S63 0HD |  | 19/7/2024:Update: Order Amended _x000D_18/7/2024:Update: Order Amended _x000D_17/7/2024:Update: Order Amended _x000D_16/7/2024:Your order has been delayed due to multiskilled engineer work is required, order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 11/07/2024. _x000D_15/7/2024:Your order has been delayed due to multiskilled engineer work is required, order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 11/07/2024. _x000D_12/7/2024:Your order has been delayed due to multiskilled engineer work is required, order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 11/07/2024. _x000D_11/7/2024:Your order has been delayed due to multiskilled engineer work is required, order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 11/07/2024. _x000D_10/7/2024:Your order has been delayed due to multiskilled engineer work is required, order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 11/07/2024. _x000D_9/7/2024:Your order has been delayed due to multiskilled engineer work is required, order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 11/07/2024. _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:Update: Order Amended _x000D_18/7/2024:Update: Order Amended _x000D_17/7/2024:Update: Order Amended _x000D_16/7/2024:Your order has been delayed due to multiskilled engineer work is required, order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 11/07/2024. _x000D_15/7/2024:Your order has been delayed due to multiskilled engineer work is required, order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 11/07/2024. _x000D_12/7/2024:Your order has been delayed due to multiskilled engineer work is required, order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 11/07/2024. _x000D_11/7/2024:Your order has been delayed due to multiskilled engineer work is required, order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 11/07/2024. _x000D_10/7/2024:Your order has been delayed due to multiskilled engineer work is required, order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 11/07/2024. _x000D_9/7/2024:Your order has been delayed due to multiskilled engineer work is required, order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 11/07/2024. _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFP2363427 | 30016379 | 6.Failed router install |  |  | 2024-07-05 | 2024-07-05 |  | TRUE |  |  |  | 2024-07-26 |  |  |  | 2024-07-26 | 242005013371 |  | 2024-07-26 | 1
1033 | 652080 | 3680 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Thrisftys | St. Helens | WA9 5QW |  | 6/9/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_5/9/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_4/9/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_3/9/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_2/9/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_29/8/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_28/8/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_27/8/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_22/8/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_21/8/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_20/8/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_19/8/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_19/8/2024:01473748 _x000D_16/8/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_15/8/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_14/8/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_13/8/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_12/8/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_9/8/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_8/8/2024:22/07/2024 _x000D_6/8/2024:22/07/2024 _x000D_5/8/2024:22/07/2024 _x000D_2/8/2024:22/07/2024 _x000D_1/8/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_30/7/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_29/7/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_29/7/2024:01473748 _x000D_26/7/2024:01473748 _x000D_24/7/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_23/7/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_6/9/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_5/9/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_4/9/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_3/9/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_2/9/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_29/8/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_28/8/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_27/8/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_22/8/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_21/8/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_20/8/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_19/8/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_19/8/2024:01473748 _x000D_16/8/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_15/8/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_14/8/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_13/8/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_12/8/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_9/8/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_8/8/2024:22/07/2024 _x000D_6/8/2024:22/07/2024 _x000D_5/8/2024:22/07/2024 _x000D_2/8/2024:22/07/2024 _x000D_1/8/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_30/7/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_29/7/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_29/7/2024:01473748 _x000D_26/7/2024:01473748 _x000D_24/7/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_23/7/2024:#Update Upgrade & OOH sent to VF for approval. _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update Upgrade & OOH sent to VF for approval. | 2024-06-07 |  |  |  |  | VFP2363426 | 30016318 | 1.Provisioning | AM |  | 2024-07-05 | 2024-08-30 |  | 0 | [11 empty] | 0
1034 | 435409 | 3681 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | M N S Late Shop | Glannau Dyfrdwy | CH5 3BS | 2024-07-29 | 6/9/2024:#Update 2 hour install required thus TRC's will need to be added. Currently waiting for the deployment team to inform me if this retailer will require an OOH appointment Order timed out while waiting and will need to be reraised _x000D_5/9/2024:#Update 2 hour install required thus TRC's will need to be added. Currently waiting for the deployment team to inform me if this retailer will require an OOH appointment Order timed out while waiting and will need to be reraised _x000D_4/9/2024:#Update 2 hour install required thus TRC's will need to be added. Currently waiting for the deployment team to inform me if this retailer will require an OOH appointment Order timed out while waiting and will need to be reraised _x000D_3/9/2024:#Update 2 hour install required thus TRC's will need to be added. Currently waiting for the deployment team to inform me if this retailer will require an OOH appointment Order timed out while waiting and will need to be reraised _x000D_2/9/2024:#Update 2 hour install required thus TRC's will need to be added. Currently waiting for the deployment team to inform me if this retailer will require an OOH appointment Order timed out while waiting and will need to be reraised _x000D_29/8/2024:#Update 2 hour install required thus TRC's will need to be added. Currently waiting for the deployment team to inform me if this retailer will require an OOH appointment Order timed out while waiting and will need to be reraised _x000D_28/8/2024:#Update 2 hour install required thus TRC's will need to be added. Currently waiting for the deployment team to inform me if this retailer will require an OOH appointment Order timed out while waiting and will need to be reraised _x000D_27/8/2024:#Update 2 hour install required thus TRC's will need to be added. Currently waiting for the deployment team to inform me if this retailer will require an OOH appointment Order timed out while waiting and will need to be reraised _x000D_22/8/2024:#Update 2 hour install required thus TRC's will need to be added. Currently waiting for the deployment team to inform me if this retailer will require an OOH appointment Order timed out while waiting and will need to be reraised _x000D_21/8/2024:#Update 2 hour install required thus TRC's will need to be added. Currently waiting for the deployment team to inform me if this retailer will require an OOH appointment Order timed out while waiting and will need to be reraised _x000D_20/8/2024:#Update 2 hour install required thus TRC's will need to be added. Currently waiting for the deployment team to inform me if this retailer will require an OOH appointment Order timed out while waiting and will need to be reraised _x000D_19/8/2024:#Update 2 hour install required thus TRC's will need to be added. Currently waiting for the deployment team to inform me if this retailer will require an OOH appointment Order timed out while waiting and will need to be reraised _x000D_19/8/2024:01470781 _x000D_16/8/2024:#Update 2 hour install required thus TRC's will need to be added. Currently waiting for the deployment team to inform me if this retailer will require an OOH appointment Order timed out while waiting and will need to be reraised _x000D_15/8/2024:#Update 2 hour install required thus TRC's will need to be added. Currently waiting for the deployment team to inform me if this retailer will require an OOH appointment Order timed out while waiting and will need to be reraised _x000D_14/8/2024:#Update 2 hour install required thus TRC's will need to be added. Currently waiting for the deployment team to inform me if this retailer will require an OOH appointment Order timed out while waiting and will need to be reraised _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:Your order has been delayed due to a customer missed appointment. OOH appointment required. Please check with end user and reappoint the order if still required. _x000D_2/8/2024:Your order has been delayed due to a customer missed appointment. OOH appointment required. Please check with end user and reappoint the order if still required. _x000D_1/8/2024:Your order has been delayed due to a customer missed appointment. OOH appointment required. Please check with end user and reappoint the order if still required. _x000D_31/7/2024:Your order has been delayed due to a customer missed appointment. OOH appointment required. Please check with end user and reappoint the order if still required. _x000D_31/7/2024:37709 _x000D_30/7/2024:Your order has been delayed due to a customer missed appointment. OOH appointment required. Please check with end user and reappoint the order if still required. _x000D_29/7/2024:EU Missed Appointment. Supplier engineer has been unable to gain access. _x000D_29/7/2024:26/07/2024 07:38 _x000D_26/7/2024:26/07/2024 07:38 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update 2 hour install required thus TRC's will need to be added. Currently waiting for the deployment team to inform me if this retailer will require an OOH appointment Order timed out while waiting and will need to be reraised _x000D_6/9/2024:#Update 2 hour install required thus TRC's will need to be added. Currently waiting for the deployment team to inform me if this retailer will require an OOH appointment Order timed out while waiting and will need to be reraised _x000D_5/9/2024:#Update 2 hour install required thus TRC's will need to be added. Currently waiting for the deployment team to inform me if this retailer will require an OOH appointment Order timed out while waiting and will need to be reraised _x000D_4/9/2024:#Update 2 hour install required thus TRC's will need to be added. Currently waiting for the deployment team to inform me if this retailer will require an OOH appointment Order timed out while waiting and will need to be reraised _x000D_3/9/2024:#Update 2 hour install required thus TRC's will need to be added. Currently waiting for the deployment team to inform me if this retailer will require an OOH appointment Order timed out while waiting and will need to be reraised _x000D_2/9/2024:#Update 2 hour install required thus TRC's will need to be added. Currently waiting for the deployment team to inform me if this retailer will require an OOH appointment Order timed out while waiting and will need to be reraised _x000D_29/8/2024:#Update 2 hour install required thus TRC's will need to be added. Currently waiting for the deployment team to inform me if this retailer will require an OOH appointment Order timed out while waiting and will need to be reraised _x000D_28/8/2024:#Update 2 hour install required thus TRC's will need to be added. Currently waiting for the deployment team to inform me if this retailer will require an OOH appointment Order timed out while waiting and will need to be reraised _x000D_27/8/2024:#Update 2 hour install required thus TRC's will need to be added. Currently waiting for the deployment team to inform me if this retailer will require an OOH appointment Order timed out while waiting and will need to be reraised _x000D_22/8/2024:#Update 2 hour install required thus TRC's will need to be added. Currently waiting for the deployment team to inform me if this retailer will require an OOH appointment Order timed out while waiting and will need to be reraised _x000D_21/8/2024:#Update 2 hour install required thus TRC's will need to be added. Currently waiting for the deployment team to inform me if this retailer will require an OOH appointment Order timed out while waiting and will need to be reraised _x000D_20/8/2024:#Update 2 hour install required thus TRC's will need to be added. Currently waiting for the deployment team to inform me if this retailer will require an OOH appointment Order timed out while waiting and will need to be reraised _x000D_19/8/2024:#Update 2 hour install required thus TRC's will need to be added. Currently waiting for the deployment team to inform me if this retailer will require an OOH appointment Order timed out while waiting and will need to be reraised _x000D_19/8/2024:01470781 _x000D_16/8/2024:#Update 2 hour install required thus TRC's will need to be added. Currently waiting for the deployment team to inform me if this retailer will require an OOH appointment Order timed out while waiting and will need to be reraised _x000D_15/8/2024:#Update 2 hour install required thus TRC's will need to be added. Currently waiting for the deployment team to inform me if this retailer will require an OOH appointment Order timed out while waiting and will need to be reraised _x000D_14/8/2024:#Update 2 hour install required thus TRC's will need to be added. Currently waiting for the deployment team to inform me if this retailer will require an OOH appointment Order timed out while waiting and will need to be reraised _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:Your order has been delayed due to a customer missed appointment. OOH appointment required. Please check with end user and reappoint the order if still required. _x000D_2/8/2024:Your order has been delayed due to a customer missed appointment. OOH appointment required. Please check with end user and reappoint the order if still required. _x000D_1/8/2024:Your order has been delayed due to a customer missed appointment. OOH appointment required. Please check with end user and reappoint the order if still required. _x000D_31/7/2024:Your order has been delayed due to a customer missed appointment. OOH appointment required. Please check with end user and reappoint the order if still required. _x000D_31/7/2024:37709 _x000D_30/7/2024:Your order has been delayed due to a customer missed appointment. OOH appointment required. Please check with end user and reappoint the order if still required. _x000D_29/7/2024:EU Missed Appointment. Supplier engineer has been unable to gain access. _x000D_29/7/2024:26/07/2024 07:38 _x000D_26/7/2024:26/07/2024 07:38 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update 2 hour install required thus TRC's will need to be added. Currently waiting for the deployment team to inform me if this retailer will require an OOH appointment Order timed out while waiting and will need to be reraised | 2024-06-07 |  |  |  |  | VFP2363425 | 30016264 | 1.Provisioning | AM |  | 2024-07-05 | 2024-07-26 |  | 0 | [11 empty] | 0
1035 | 666824 | 3682 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Dumpton Post Office | BROADSTAIRS | CT10 2EW |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 11:24 _x000D_26/7/2024:22/07/2024 11:24 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 11:24 _x000D_26/7/2024:22/07/2024 11:24 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2363424 | 30016265 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
1036 | 665166 | 3685 | Batch 5 Jul24 | Type 1 | FTTP | Go Local | WALLASEY | CH44 2AG |  | 9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFP2363423 | 30016320 | 6.Failed router install |  |  | 2024-07-05 | 2024-07-05 |  | TRUE |  |  |  | 2024-08-02 |  |  |  | 2024-08-02 | 23A004948496 |  | 2024-08-06 | 1
1037 | 657245 | 3687 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | One Stop Working With Merlin Stores | BRIDGEND | CF31 4ES |  | 6/9/2024:#Update Retailer confirmed 23/09, AM. _x000D_5/9/2024:#Update Retailer confirmed 23/09, AM. _x000D_4/9/2024:#Update Retailer confirmed 23/09, AM. _x000D_3/9/2024:#Update Retailer confirmed 23/09, AM. _x000D_2/9/2024:#Update Retailer confirmed 23/09, AM. _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update Retailer confirmed 23/09, AM. _x000D_6/9/2024:#Update Retailer confirmed 23/09, AM. _x000D_5/9/2024:#Update Retailer confirmed 23/09, AM. _x000D_4/9/2024:#Update Retailer confirmed 23/09, AM. _x000D_3/9/2024:#Update Retailer confirmed 23/09, AM. _x000D_2/9/2024:#Update Retailer confirmed 23/09, AM. _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update Retailer confirmed 23/09, AM. | 2024-06-07 |  |  |  |  | VFS1098745 | 30016197 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
1038 | 428956 | 3688 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | SPAR DRUMMOND ROAD | SKEGNESS | PE25 3ES |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2363421 | 30016308 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
1039 | 650901 | 3691 | Batch 5 Jul24 | Type 1 | SOGEA | Welcome Co Op | Sittingbourne | ME10 1TH |  | 9/7/2024:Openreach Delay : Automated testing has identified a potential fault _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/7/2024:Openreach Delay : Automated testing has identified a potential fault _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1012986 | 30016451 | 6.Failed router install |  |  | 2024-07-05 | 2024-07-05 |  | TRUE |  |  |  | 2024-07-24 |  |  |  | 2024-07-24 | 242005008531 |  | 2024-07-29 | 1
1040 | 664040 | 3692 | Batch 5 Jul24 | Type 1 | FTTP | Go Local Extra | BIRMINGHAM | B34 6QU |  | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFP2363420 | 30016364 | 6.Failed router install |  |  | 2024-07-05 | 2024-07-05 |  | TRUE |  |  |  | 2024-07-29 |  |  |  | 2024-07-29 | 237004907579 |  | 2024-07-30 | 1
1041 | 441904 | 3693 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Mayfair Convenience Store | DAGENHAM | RM10 7XD |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 15:13 _x000D_26/7/2024:22/07/2024 15:13 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 15:13 _x000D_26/7/2024:22/07/2024 15:13 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2363419 | 30016258 | 1.Provisioning | AM |  | 2024-09-06 | 2024-09-06 |  | 0 | [11 empty] | 0
1042 | 665127 | 3697 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Lewis Llandrinio | Llanymynech | SY22 6SB |  | 6/9/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_5/9/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_4/9/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_3/9/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_2/9/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_29/8/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_28/8/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_27/8/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_22/8/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_21/8/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_20/8/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_19/8/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_19/8/2024:01409204 _x000D_16/8/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_15/8/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_14/8/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_13/8/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_12/8/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_9/8/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_8/8/2024:18/06/2024 _x000D_6/8/2024:18/06/2024 _x000D_5/8/2024:18/06/2024 _x000D_2/8/2024:18/06/2024 _x000D_1/8/2024:18/06/2024 _x000D_31/7/2024:18/06/2024 _x000D_31/7/2024:18/06/2024 _x000D_30/7/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_29/7/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_29/7/2024:01409204 _x000D_26/7/2024:01409204 _x000D_24/7/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_23/7/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_22/7/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_22/7/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_6/9/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_5/9/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_4/9/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_3/9/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_2/9/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_29/8/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_28/8/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_27/8/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_22/8/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_21/8/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_20/8/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_19/8/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_19/8/2024:01409204 _x000D_16/8/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_15/8/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_14/8/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_13/8/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_12/8/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_9/8/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_8/8/2024:18/06/2024 _x000D_6/8/2024:18/06/2024 _x000D_5/8/2024:18/06/2024 _x000D_2/8/2024:18/06/2024 _x000D_1/8/2024:18/06/2024 _x000D_31/7/2024:18/06/2024 _x000D_31/7/2024:18/06/2024 _x000D_30/7/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_29/7/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_29/7/2024:01409204 _x000D_26/7/2024:01409204 _x000D_24/7/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_23/7/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_22/7/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_22/7/2024:#Update- Chasing information from Engineer about this one. Will inform as updates become available. _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | #Update- Chasing information from Engineer about this one. Will inform as updates become available. | 2024-06-07 |  |  |  |  | VFP2363418 | 30016374 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
1043 | 639228 | 3698 | Batch 5 Jul24 | Type 1 | SOGEA | One Stop Valley Store & Off Licence | Nottingham | NG5 1HW |  | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1012983 | 30016546 | 2.Commissioning |  |  | 2024-07-05 | 2024-07-05 |  | TRUE |  |  |  | 2024-07-25 | [7 empty] | 0
1044 | 664421 | 3699 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Supervalu Richhill | ARMAGH | BT61 9PW |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:30 _x000D_26/7/2024:22/07/2024 10:30 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:30 _x000D_26/7/2024:22/07/2024 10:30 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2363416 | 30016281 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
1045 | 450126 | 3700 | Batch 5 Jul24 | Type 1 | FTTP | SPAR ABBOTS LANGLEY | ABBOTS LANGLEY | WD5 0LA |  | 9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFP2363415 | 30016303 | 6.Failed router install |  |  | 2024-07-05 | 2024-07-05 |  | TRUE |  |  |  | 2024-07-26 |  |  |  | 2024-07-26 | 242005011161 |  | 2024-07-29 | 1
1046 | 615353 | 3701 | Batch 5 Jul24 | Type 1 | SOGEA | Singh Stores | West Chirton | NE29 7DR |  | 19/7/2024:Update: Order Completed by Supplier _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:Update: Order Completed by Supplier _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1012981 | 30016595 | 6.Failed router install |  |  | 2024-07-05 | 2024-07-05 |  | TRUE |  |  |  | 2024-07-24 |  |  |  | 2024-07-24 | 242005013669 |  | 2024-07-25 | 1
1047 | 635153 | 3703 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Bargain Booze | Newport | PO30 5LE |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:#Update Retailer happy with new appointment 31/07, AM. _x000D_21/8/2024:#Update Retailer happy with new appointment 31/07, AM. _x000D_20/8/2024:#Update Retailer happy with new appointment 31/07, AM. _x000D_19/8/2024:#Update Retailer happy with new appointment 31/07, AM. _x000D_19/8/2024:01472045 _x000D_16/8/2024:#Update Retailer happy with new appointment 31/07, AM. _x000D_15/8/2024:#Update Retailer happy with new appointment 31/07, AM. _x000D_14/8/2024:#Update Retailer happy with new appointment 31/07, AM. _x000D_13/8/2024:#Update Retailer happy with new appointment 31/07, AM. _x000D_12/8/2024:#Update Retailer happy with new appointment 31/07, AM. _x000D_9/8/2024:#Update Retailer happy with new appointment 31/07, AM. _x000D_8/8/2024:17/07/2024 _x000D_6/8/2024:17/07/2024 _x000D_5/8/2024:17/07/2024 _x000D_2/8/2024:17/07/2024 _x000D_1/8/2024:17/07/2024 _x000D_31/7/2024:17/07/2024 _x000D_31/7/2024:17/07/2024 _x000D_30/7/2024:#Update Retailer happy with new appointment 31/07, AM. _x000D_29/7/2024:#Update Retailer happy with new appointment 31/07, AM. _x000D_29/7/2024:01472045 _x000D_26/7/2024:01472045 _x000D_24/7/2024:#Update Retailer happy with new appointment 31/07, AM. _x000D_23/7/2024:#Update Retailer happy with new appointment 31/07, AM. _x000D_22/7/2024:#Update Retailer happy with new appointment 31/07, AM. _x000D_22/7/2024:#Update Retailer happy with new appointment 31/07, AM. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:#Update Retailer happy with new appointment 31/07, AM. _x000D_21/8/2024:#Update Retailer happy with new appointment 31/07, AM. _x000D_20/8/2024:#Update Retailer happy with new appointment 31/07, AM. _x000D_19/8/2024:#Update Retailer happy with new appointment 31/07, AM. _x000D_19/8/2024:01472045 _x000D_16/8/2024:#Update Retailer happy with new appointment 31/07, AM. _x000D_15/8/2024:#Update Retailer happy with new appointment 31/07, AM. _x000D_14/8/2024:#Update Retailer happy with new appointment 31/07, AM. _x000D_13/8/2024:#Update Retailer happy with new appointment 31/07, AM. _x000D_12/8/2024:#Update Retailer happy with new appointment 31/07, AM. _x000D_9/8/2024:#Update Retailer happy with new appointment 31/07, AM. _x000D_8/8/2024:17/07/2024 _x000D_6/8/2024:17/07/2024 _x000D_5/8/2024:17/07/2024 _x000D_2/8/2024:17/07/2024 _x000D_1/8/2024:17/07/2024 _x000D_31/7/2024:17/07/2024 _x000D_31/7/2024:17/07/2024 _x000D_30/7/2024:#Update Retailer happy with new appointment 31/07, AM. _x000D_29/7/2024:#Update Retailer happy with new appointment 31/07, AM. _x000D_29/7/2024:01472045 _x000D_26/7/2024:01472045 _x000D_24/7/2024:#Update Retailer happy with new appointment 31/07, AM. _x000D_23/7/2024:#Update Retailer happy with new appointment 31/07, AM. _x000D_22/7/2024:#Update Retailer happy with new appointment 31/07, AM. _x000D_22/7/2024:#Update Retailer happy with new appointment 31/07, AM. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | 0 | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1012982 | 30016542 | 2.Commissioning | AM |  | 2024-07-05 | 2024-08-19 |  | 0 | [11 empty] | 0
1048 | 620178 | 3704 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Maxol Spar | Bangor | BT20 3RQ |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:16 _x000D_26/7/2024:22/07/2024 10:16 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_9/7/2024:Openreach Delay : Automated testing has identified a potential fault _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:16 _x000D_26/7/2024:22/07/2024 10:16 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_9/7/2024:Openreach Delay : Automated testing has identified a potential fault _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2363413 | 30016340 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
1049 | 669391 | 3705 | Batch 5 Jul24 | Type 1 | SOGEA | SPAR TETNEY POST OFFICE | GRIMSBY | DN36 5JE |  | 19/7/2024:#Update - Retailer confirmed new appointment for 05/08 - Am _x000D_18/7/2024:#Update - Retailer confirmed new appointment for 05/08 - Am _x000D_17/7/2024:#Update - Retailer confirmed new appointment for 05/08 - Am _x000D_16/7/2024:#Update - Retailer unaware, Reappointed for 05/08 - Action for allwyn, Please confirm new appointment of 05/08 _x000D_15/7/2024:#Update - Retailer unaware, Reappointed for 05/08 - Action for allwyn, Please confirm new appointment of 05/08 _x000D_12/7/2024:#Update - Retailer unaware, Reappointed for 05/08 - Action for allwyn, Please confirm new appointment of 05/08 _x000D_11/7/2024:#Update - Retailer unaware, Reappointed for 05/08 - Action for allwyn, Please confirm new appointment of 05/08 _x000D_10/7/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_9/7/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:#Update - Retailer confirmed new appointment for 05/08 - Am _x000D_18/7/2024:#Update - Retailer confirmed new appointment for 05/08 - Am _x000D_17/7/2024:#Update - Retailer confirmed new appointment for 05/08 - Am _x000D_16/7/2024:#Update - Retailer unaware, Reappointed for 05/08 - Action for allwyn, Please confirm new appointment of 05/08 _x000D_15/7/2024:#Update - Retailer unaware, Reappointed for 05/08 - Action for allwyn, Please confirm new appointment of 05/08 _x000D_12/7/2024:#Update - Retailer unaware, Reappointed for 05/08 - Action for allwyn, Please confirm new appointment of 05/08 _x000D_11/7/2024:#Update - Retailer unaware, Reappointed for 05/08 - Action for allwyn, Please confirm new appointment of 05/08 _x000D_10/7/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_9/7/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1012978 | 30016419 | 6.Failed router install |  |  | 2024-07-05 | 2024-07-05 |  | TRUE |  |  |  | 2024-07-31 |  |  |  | 2024-07-31 | 238004926080 |  | 2024-08-01 | 1
1050 | 668424 | 3711 | Batch 5 Jul24 | Type 1 | FTTP | Premier Stores & Post Office | EBBW VALE | NP23 5TA |  | 19/7/2024:#Update Customer unaware, reappointed 19/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_18/7/2024:#Update Customer unaware, reappointed 19/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_17/7/2024:#Update Customer unaware, reappointed 19/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_16/7/2024:#Update Customer unaware, reappointed 19/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_15/7/2024:#Update Customer unaware, reappointed 19/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_12/7/2024:#Update Customer unaware, reappointed 19/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_11/7/2024:#Update Customer unaware, reappointed 19/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_10/7/2024:#Update Customer unaware, reappointed 19/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_9/7/2024:#Update Customer unaware, reappointed 19/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:#Update Customer unaware, reappointed 19/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_18/7/2024:#Update Customer unaware, reappointed 19/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_17/7/2024:#Update Customer unaware, reappointed 19/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_16/7/2024:#Update Customer unaware, reappointed 19/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_15/7/2024:#Update Customer unaware, reappointed 19/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_12/7/2024:#Update Customer unaware, reappointed 19/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_11/7/2024:#Update Customer unaware, reappointed 19/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_10/7/2024:#Update Customer unaware, reappointed 19/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_9/7/2024:#Update Customer unaware, reappointed 19/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFP2363411 | 30016287 | 2.Commissioning |  |  | 2024-07-05 | 2024-07-05 |  | TRUE |  |  |  | 2024-07-26 | [7 empty] | 0
1051 | 431028 | 3712 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Bipinns News | WALSALL | WS1 4LA |  | 6/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 22/07 _x000D_5/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 22/07 _x000D_4/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 22/07 _x000D_3/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 22/07 _x000D_2/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 22/07 _x000D_29/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 22/07 _x000D_28/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 22/07 _x000D_27/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 22/07 _x000D_22/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 22/07 _x000D_21/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 22/07 _x000D_20/8/2024:#Update Upgrade sent to VF for approval. _x000D_19/8/2024:#Update Upgrade sent to VF for approval. _x000D_19/8/2024:01470601 _x000D_16/8/2024:#Update Upgrade sent to VF for approval. _x000D_15/8/2024:#Update Upgrade sent to VF for approval. _x000D_14/8/2024:#Update Upgrade sent to VF for approval. _x000D_13/8/2024:#Update Upgrade sent to VF for approval. _x000D_12/8/2024:#Update Upgrade sent to VF for approval. _x000D_9/8/2024:#Update Upgrade sent to VF for approval. _x000D_8/8/2024:22/07/2024 _x000D_6/8/2024:22/07/2024 _x000D_5/8/2024:22/07/2024 _x000D_2/8/2024:22/07/2024 _x000D_1/8/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_30/7/2024:#Update Upgrade sent to VF for approval. _x000D_29/7/2024:#Update Upgrade sent to VF for approval. _x000D_29/7/2024:01470601 _x000D_26/7/2024:01470601 _x000D_24/7/2024:#Update Upgrade sent to VF for approval. _x000D_23/7/2024:#Update Upgrade sent to VF for approval. _x000D_22/7/2024:#Update Customer unaware, reappointed 19/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_22/7/2024:#Update Customer unaware, reappointed 19/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 22/07 _x000D_6/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 22/07 _x000D_5/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 22/07 _x000D_4/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 22/07 _x000D_3/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 22/07 _x000D_2/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 22/07 _x000D_29/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 22/07 _x000D_28/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 22/07 _x000D_27/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 22/07 _x000D_22/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 22/07 _x000D_21/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 22/07 _x000D_20/8/2024:#Update Upgrade sent to VF for approval. _x000D_19/8/2024:#Update Upgrade sent to VF for approval. _x000D_19/8/2024:01470601 _x000D_16/8/2024:#Update Upgrade sent to VF for approval. _x000D_15/8/2024:#Update Upgrade sent to VF for approval. _x000D_14/8/2024:#Update Upgrade sent to VF for approval. _x000D_13/8/2024:#Update Upgrade sent to VF for approval. _x000D_12/8/2024:#Update Upgrade sent to VF for approval. _x000D_9/8/2024:#Update Upgrade sent to VF for approval. _x000D_8/8/2024:22/07/2024 _x000D_6/8/2024:22/07/2024 _x000D_5/8/2024:22/07/2024 _x000D_2/8/2024:22/07/2024 _x000D_1/8/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_30/7/2024:#Update Upgrade sent to VF for approval. _x000D_29/7/2024:#Update Upgrade sent to VF for approval. _x000D_29/7/2024:01470601 _x000D_26/7/2024:01470601 _x000D_24/7/2024:#Update Upgrade sent to VF for approval. _x000D_23/7/2024:#Update Upgrade sent to VF for approval. _x000D_22/7/2024:#Update Customer unaware, reappointed 19/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_22/7/2024:#Update Customer unaware, reappointed 19/07, AM. Action on Allwyn - ensure the retailer is aware. _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update - awaiting ECC approval from customer - proposal sent to VF 22/07 | 2024-06-07 |  |  |  |  | VFS1012974 | 30016392 | 1.Provisioning | AM |  | 2024-07-05 | 2024-08-30 |  | 0 | [11 empty] | 0
1052 | 666858 | 3715 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Freshway | CHELMSFORD | CM3 6AH |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:17 _x000D_26/7/2024:22/07/2024 10:17 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:#Update - Awaiting ECC approval. _x000D_18/7/2024:#Update - Awaiting ECC approval. _x000D_17/7/2024:#Update - Awaiting ECC approval. _x000D_16/7/2024:#Update - Awaiting ECC approval. _x000D_15/7/2024:#Update - Awaiting ECC approval. _x000D_12/7/2024:#Update - Awaiting ECC approval. _x000D_11/7/2024:#Update - Awaiting ECC approval. _x000D_10/7/2024:#Update - Awaiting ECC approval. _x000D_9/7/2024:#Update - Confirming scope of additional works with OR - Will send details over for approval when I get them. Action for allwyn : Please confirm availability from the retailer for re-appointment. Needs shelves to be cleared of stock, on a Monday AM when the store is quiet. Possible OOH? X2 Engineers - Awaiting confirmation. _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:17 _x000D_26/7/2024:22/07/2024 10:17 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:#Update - Awaiting ECC approval. _x000D_18/7/2024:#Update - Awaiting ECC approval. _x000D_17/7/2024:#Update - Awaiting ECC approval. _x000D_16/7/2024:#Update - Awaiting ECC approval. _x000D_15/7/2024:#Update - Awaiting ECC approval. _x000D_12/7/2024:#Update - Awaiting ECC approval. _x000D_11/7/2024:#Update - Awaiting ECC approval. _x000D_10/7/2024:#Update - Awaiting ECC approval. _x000D_9/7/2024:#Update - Confirming scope of additional works with OR - Will send details over for approval when I get them. Action for allwyn : Please confirm availability from the retailer for re-appointment. Needs shelves to be cleared of stock, on a Monday AM when the store is quiet. Possible OOH? X2 Engineers - Awaiting confirmation. _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2363409 | 30016292 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
1053 | 100047 | 3716 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Best One Marsden News | NELSON | BB9 9NP |  | 22/8/2024:#Update - Retailer confirmed new appointment of 09/09 _x000D_21/8/2024:#Update - Retailer confirmed new appointment of 09/09 _x000D_20/8/2024:#Update - Retailer confirmed new appointment of 09/09 _x000D_19/8/2024:#Update - Retailer confirmed new appointment of 09/09 _x000D_19/8/2024:01477761 _x000D_16/8/2024:#Update - Awaiting ECC approval. _x000D_15/8/2024:#Update - Awaiting ECC approval. _x000D_14/8/2024:#Update - Awaiting ECC approval. _x000D_13/8/2024:#Update - Awaiting ECC approval. _x000D_12/8/2024:#Update - Awaiting ECC approval. _x000D_9/8/2024:#Update - Awaiting ECC approval. _x000D_8/8/2024:10/07/2024 _x000D_6/8/2024:10/07/2024 _x000D_5/8/2024:10/07/2024 _x000D_2/8/2024:10/07/2024 _x000D_1/8/2024:10/07/2024 _x000D_31/7/2024:10/07/2024 _x000D_31/7/2024:10/07/2024 _x000D_30/7/2024:#Update - Awaiting ECC approval. _x000D_29/7/2024:#Update - Awaiting ECC approval. _x000D_29/7/2024:01477761 _x000D_26/7/2024:01477761 _x000D_24/7/2024:#Update - Awaiting ECC approval. _x000D_23/7/2024:#Update - Awaiting ECC approval. _x000D_22/7/2024:#Update - Awaiting ECC approval. _x000D_22/7/2024:#Update - Awaiting ECC approval. _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 22/8/2024:#Update - Retailer confirmed new appointment of 09/09 _x000D_21/8/2024:#Update - Retailer confirmed new appointment of 09/09 _x000D_20/8/2024:#Update - Retailer confirmed new appointment of 09/09 _x000D_19/8/2024:#Update - Retailer confirmed new appointment of 09/09 _x000D_19/8/2024:01477761 _x000D_16/8/2024:#Update - Awaiting ECC approval. _x000D_15/8/2024:#Update - Awaiting ECC approval. _x000D_14/8/2024:#Update - Awaiting ECC approval. _x000D_13/8/2024:#Update - Awaiting ECC approval. _x000D_12/8/2024:#Update - Awaiting ECC approval. _x000D_9/8/2024:#Update - Awaiting ECC approval. _x000D_8/8/2024:10/07/2024 _x000D_6/8/2024:10/07/2024 _x000D_5/8/2024:10/07/2024 _x000D_2/8/2024:10/07/2024 _x000D_1/8/2024:10/07/2024 _x000D_31/7/2024:10/07/2024 _x000D_31/7/2024:10/07/2024 _x000D_30/7/2024:#Update - Awaiting ECC approval. _x000D_29/7/2024:#Update - Awaiting ECC approval. _x000D_29/7/2024:01477761 _x000D_26/7/2024:01477761 _x000D_24/7/2024:#Update - Awaiting ECC approval. _x000D_23/7/2024:#Update - Awaiting ECC approval. _x000D_22/7/2024:#Update - Awaiting ECC approval. _x000D_22/7/2024:#Update - Awaiting ECC approval. _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2363408 | 30016355 | 2.Commissioning | AM |  | 2024-07-07 | 2024-08-05 | 2024-09-19 10:14 | 1 |  |  |  | 2024-09-18 | [7 empty] | 0
1054 | 487062 | 3720 | Batch 5 Jul24 | Type 1 | FTTP | S&S Convenience Store Premier | Corby | NN18 0RQ |  | 27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:23/07/2024 13:23 _x000D_24/7/2024:Order Completed _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:Update: Order Amended _x000D_16/7/2024:Update: Order Amended _x000D_15/7/2024:Update: Order Amended _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Your order has been delayed due to a routing issue at our suppliers. The order has now been passed to a backend team to update. They have given us a review date of 09/07/2024. Please check back on 11/07/2024 for further updates. _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:23/07/2024 13:23 _x000D_24/7/2024:Order Completed _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:Update: Order Amended _x000D_16/7/2024:Update: Order Amended _x000D_15/7/2024:Update: Order Amended _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Your order has been delayed due to a routing issue at our suppliers. The order has now been passed to a backend team to update. They have given us a review date of 09/07/2024. Please check back on 11/07/2024 for further updates. _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2363407 | 30016310 | 6.Failed router install | [9 empty] | 2024-08-14 |  |  |  | 2024-08-22 | 23A004945992 | 23A004945992 | 2024-08-27 | 1
1055 | 463452 | 3721 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Londis | REDRUTH | TR16 5JU |  | 2/8/2024:Order Completed _x000D_1/8/2024:Order Completed _x000D_31/7/2024:Order Completed _x000D_31/7/2024:37657 _x000D_30/7/2024:Order Completed _x000D_29/7/2024:Order Completed _x000D_29/7/2024:29/07/2024 08:49 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 2/8/2024:Order Completed _x000D_1/8/2024:Order Completed _x000D_31/7/2024:Order Completed _x000D_31/7/2024:37657 _x000D_30/7/2024:Order Completed _x000D_29/7/2024:Order Completed _x000D_29/7/2024:29/07/2024 08:49 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1012971 | 30016557 | 2.Commissioning |  |  | 2024-07-05 | 2024-07-29 | 2024-07-29 | TRUE | [11 empty] | 0
1056 | 473250 | 3730 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Bargain Booze | Barrow in Furness | LA14 3BZ |  | 6/9/2024:#Update - Address verification issue, email sent to VF 24/07 - order is cancelled and will be reraised accordingly _x000D_5/9/2024:#Update - Address verification issue, email sent to VF 24/07 - order is cancelled and will be reraised accordingly _x000D_4/9/2024:#Update - Address verification issue, email sent to VF 24/07 - order is cancelled and will be reraised accordingly _x000D_3/9/2024:#Update - Address verification issue, email sent to VF 24/07 - order is cancelled and will be reraised accordingly _x000D_2/9/2024:#Update - Address verification issue, email sent to VF 24/07 - order is cancelled and will be reraised accordingly _x000D_29/8/2024:#Update - Address verification issue, email sent to VF 24/07 - order is cancelled and will be reraised accordingly _x000D_28/8/2024:#Update - Address verification issue, email sent to VF 24/07 - order is cancelled and will be reraised accordingly _x000D_Address verification issue, email sent to VF - order is cancelled and will be reraised accordingly | 9/9/2024:#Update - Address verification issue, email sent to VF 24/07 - order is cancelled and will be reraised accordingly _x000D_6/9/2024:#Update - Address verification issue, email sent to VF 24/07 - order is cancelled and will be reraised accordingly _x000D_5/9/2024:#Update - Address verification issue, email sent to VF 24/07 - order is cancelled and will be reraised accordingly _x000D_4/9/2024:#Update - Address verification issue, email sent to VF 24/07 - order is cancelled and will be reraised accordingly _x000D_3/9/2024:#Update - Address verification issue, email sent to VF 24/07 - order is cancelled and will be reraised accordingly _x000D_2/9/2024:#Update - Address verification issue, email sent to VF 24/07 - order is cancelled and will be reraised accordingly _x000D_29/8/2024:#Update - Address verification issue, email sent to VF 24/07 - order is cancelled and will be reraised accordingly _x000D_28/8/2024:#Update - Address verification issue, email sent to VF 24/07 - order is cancelled and will be reraised accordingly _x000D_Address verification issue, email sent to VF - order is cancelled and will be reraised accordingly | 0 | #Update - Address verification issue, email sent to VF 24/07 - order is cancelled and will be reraised accordingly | 2024-06-07 |  |  |  |  | VFS1012965 | 30016389 | 1.Provisioning | AM |  | 2024-07-05 | 2024-07-05 |  | 0 | [11 empty] | 0
1057 | 632835 | 3731 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Premier | Redruth | TR15 3XJ |  | 6/9/2024:#Update - This installation was not completed as the store manager is still away on holiday, action with Allwyn to contact the retailer to obtain availability _x000D_5/9/2024:#Update - This installation was not completed as the store manager is still away on holiday, action with Allwyn to contact the retailer to obtain availability _x000D_4/9/2024:#Update - This installation was not completed as the store manager is still away on holiday, action with Allwyn to contact the retailer to obtain availability _x000D_3/9/2024:#Update - This installation was not completed as the store manager is still away on holiday, action with Allwyn to contact the retailer to obtain availability _x000D_2/9/2024:#Update - This installation was not completed as the store manager is still away on holiday, action with Allwyn to contact the retailer to obtain availability _x000D_29/8/2024:#Update - This installation was not completed as the store manager is still away on holiday, action with Allwyn to contact the retailer to obtain availability _x000D_28/8/2024:#Update - This installation was not completed as the store manager is still away on holiday, action with Allwyn to contact the retailer to obtain availability _x000D_Store manager is on holiday, no reply from Allwyn, chased 27/08 - order is cancelled and will be reraised accordingly | 9/9/2024:#Update - This installation was not completed as the store manager is still away on holiday, action with Allwyn to contact the retailer to obtain availability _x000D_6/9/2024:#Update - This installation was not completed as the store manager is still away on holiday, action with Allwyn to contact the retailer to obtain availability _x000D_5/9/2024:#Update - This installation was not completed as the store manager is still away on holiday, action with Allwyn to contact the retailer to obtain availability _x000D_4/9/2024:#Update - This installation was not completed as the store manager is still away on holiday, action with Allwyn to contact the retailer to obtain availability _x000D_3/9/2024:#Update - This installation was not completed as the store manager is still away on holiday, action with Allwyn to contact the retailer to obtain availability _x000D_2/9/2024:#Update - This installation was not completed as the store manager is still away on holiday, action with Allwyn to contact the retailer to obtain availability _x000D_29/8/2024:#Update - This installation was not completed as the store manager is still away on holiday, action with Allwyn to contact the retailer to obtain availability _x000D_28/8/2024:#Update - This installation was not completed as the store manager is still away on holiday, action with Allwyn to contact the retailer to obtain availability _x000D_Store manager is on holiday, no reply from Allwyn, chased 27/08 - order is cancelled and will be reraised accordingly | 0 | #Update - This installation was not completed as the store manager is still away on holiday, action with Allwyn to contact the retailer to obtain availability | 2024-06-07 |  |  |  |  | VFS1012966 | 30016415 | 1.Provisioning | AM |  | 2024-07-22 | 2024-07-05 |  | 0 | [11 empty] | 0
1058 | 446675 | 3733 | Batch 5 Jul24 | Type 1 | SOGEA | VJs News | MANCHESTER | M24 6FL |  | 9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1012961 | 30016547 | 6.Failed router install |  |  | 2024-07-05 | 2024-07-05 |  | TRUE |  |  |  | 2024-08-06 |  |  |  | 2024-08-06 | 23A004948562 |  | 2024-08-07 | 1
1059 | 661888 | 3737 | Batch 5 Jul24 | Type 1 | SOGEA | Holyhead Post Office | Holyhead | LL65 1HG |  | 19/7/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_18/7/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_17/7/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_16/7/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_15/7/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_12/7/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_11/7/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_10/7/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_9/7/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_4/7/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_3/7/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_27/6/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_25/6/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_24/6/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_20/6/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_19/6/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_18/6/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_17/6/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_14/6/2024:#Update - Retailer to arrange access for engineer for the below reappointment date, 08/07 am. Action for allwyn : Confirm new date and ensure retailer has access for Engineer, _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 19/7/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_18/7/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_17/7/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_16/7/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_15/7/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_12/7/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_11/7/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_10/7/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_9/7/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_4/7/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_3/7/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_27/6/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_25/6/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_24/6/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_20/6/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_19/6/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_18/6/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_17/6/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_14/6/2024:#Update - Retailer to arrange access for engineer for the below reappointment date, 08/07 am. Action for allwyn : Confirm new date and ensure retailer has access for Engineer, _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  |  | VFS1012958 | 30016563 | 6.Failed router install |  |  | 2024-07-05 | 2024-07-05 |  | TRUE |  |  |  | 2024-08-07 |  |  |  | 2024-08-07 | 242005008917 |  | 2024-08-08 | 1
1060 | 650229 | 1949 | Batch 4 Jun24 | Type 1 | FTTP/Mobile | Today Express | Belfast | BT14 6JZ | 2024-06-07 | 6/9/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_5/9/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_4/9/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_3/9/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_2/9/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_29/8/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_28/8/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_27/8/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_22/8/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_21/8/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_20/8/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_19/8/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_19/8/2024:01437335 _x000D_16/8/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_15/8/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_14/8/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_13/8/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_12/8/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_9/8/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_8/8/2024:17/06/2024 _x000D_6/8/2024:17/06/2024 _x000D_5/8/2024:17/06/2024 _x000D_2/8/2024:17/06/2024 _x000D_1/8/2024:17/06/2024 _x000D_31/7/2024:17/06/2024 _x000D_31/7/2024:17/06/2024 _x000D_30/7/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_29/7/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_29/7/2024:01437335 _x000D_26/7/2024:01437335 _x000D_24/7/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_23/7/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_22/7/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_22/7/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_12/7/2024:#Update due to address issue order had to be reraised. Now scheduled for 08/07 AM _x000D_11/7/2024:#Update due to address issue order had to be reraised. Now scheduled for 08/07 AM _x000D_10/7/2024:#Update due to address issue order had to be reraised. Now scheduled for 08/07 AM _x000D_9/7/2024:#Update due to address issue order had to be reraised. Now scheduled for 08/07 AM _x000D_4/7/2024:#Update due to address issue order had to be reraised. Now scheduled for 08/07 AM _x000D_3/7/2024:#Update due to address issue order had to be reraised. Now scheduled for 08/07 AM _x000D_2/7/2024:0 _x000D_1/7/2024:#Update due to address issue order had to be reraised. Now scheduled for 08/07 AM _x000D_27/6/2024:#Update due to address issue order had to be reraised. Now scheduled for 08/07 AM _x000D_25/6/2024:#Update due to address issue order had to be reraised. Now scheduled for 08/07 AM _x000D_24/6/2024:#Update due to address issue order had to be reraised. Now scheduled for 08/07 AM _x000D_20/6/2024:#Update due to address issue order had to be reraised. Now scheduled for 08/07 AM _x000D_19/6/2024:#Update due to address issue order had to be reraised. Now scheduled for 08/07 AM _x000D_18/6/2024:#Update due to address issue order had to be reraised. Now scheduled for 08/07 AM _x000D_17/6/2024:#Update due to address issue order had to be reraised. Now scheduled for 08/07 AM _x000D_14/6/2024:#Update due to address issue order had to be reraised. Now scheduled for 08/07 AM _x000D_13/6/2024:#Update due to address issue order had to be reraised. Now scheduled for 08/07 AM _x000D_12/6/2024:#Update due to address issue order had to be reraised. Now scheduled for 08/07 AM _x000D_10/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect Address Please check with end user and reappoint the order if still required. _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 9/9/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_6/9/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_5/9/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_4/9/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_3/9/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_2/9/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_29/8/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_28/8/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_27/8/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_22/8/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_21/8/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_20/8/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_19/8/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_19/8/2024:01437335 _x000D_16/8/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_15/8/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_14/8/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_13/8/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_12/8/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_9/8/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_8/8/2024:17/06/2024 _x000D_6/8/2024:17/06/2024 _x000D_5/8/2024:17/06/2024 _x000D_2/8/2024:17/06/2024 _x000D_1/8/2024:17/06/2024 _x000D_31/7/2024:17/06/2024 _x000D_31/7/2024:17/06/2024 _x000D_30/7/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_29/7/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_29/7/2024:01437335 _x000D_26/7/2024:01437335 _x000D_24/7/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_23/7/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_22/7/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_22/7/2024:#Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. _x000D_12/7/2024:#Update due to address issue order had to be reraised. Now scheduled for 08/07 AM _x000D_11/7/2024:#Update due to address issue order had to be reraised. Now scheduled for 08/07 AM _x000D_10/7/2024:#Update due to address issue order had to be reraised. Now scheduled for 08/07 AM _x000D_9/7/2024:#Update due to address issue order had to be reraised. Now scheduled for 08/07 AM _x000D_4/7/2024:#Update due to address issue order had to be reraised. Now scheduled for 08/07 AM _x000D_3/7/2024:#Update due to address issue order had to be reraised. Now scheduled for 08/07 AM _x000D_2/7/2024:0 _x000D_1/7/2024:#Update due to address issue order had to be reraised. Now scheduled for 08/07 AM _x000D_27/6/2024:#Update due to address issue order had to be reraised. Now scheduled for 08/07 AM _x000D_25/6/2024:#Update due to address issue order had to be reraised. Now scheduled for 08/07 AM _x000D_24/6/2024:#Update due to address issue order had to be reraised. Now scheduled for 08/07 AM _x000D_20/6/2024:#Update due to address issue order had to be reraised. Now scheduled for 08/07 AM _x000D_19/6/2024:#Update due to address issue order had to be reraised. Now scheduled for 08/07 AM _x000D_18/6/2024:#Update due to address issue order had to be reraised. Now scheduled for 08/07 AM _x000D_17/6/2024:#Update due to address issue order had to be reraised. Now scheduled for 08/07 AM _x000D_14/6/2024:#Update due to address issue order had to be reraised. Now scheduled for 08/07 AM _x000D_13/6/2024:#Update due to address issue order had to be reraised. Now scheduled for 08/07 AM _x000D_12/6/2024:#Update due to address issue order had to be reraised. Now scheduled for 08/07 AM _x000D_10/6/2024:Your order has been delayed due to a customer missed appointment. Incorrect Address Please check with end user and reappoint the order if still required. _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 0 | #Update - Retailer confirmed 8th July AM appointment, retailer contact detailed retained by openreach. | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFP2337382 | 30015673 | 1.Provisioning | AM |  | 2024-06-14 | 2024-07-08 |  | 0 | [11 empty] | 0
1061 | 668071 | 1625 | Batch 4 Jun24 | Type 1 | FTTP | SPAR | Newry | BT34 5UH | 2024-06-07 | 19/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_18/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_17/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_16/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_15/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_12/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_11/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_10/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_9/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_4/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_3/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_27/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_25/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_24/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_20/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_19/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_18/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_17/6/2024:Update: Order Amended _x000D_14/6/2024:Update: Order Amended _x000D_13/6/2024:Update: Order Amended _x000D_12/6/2024:Update: Order Amended _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 19/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_18/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_17/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_16/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_15/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_12/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_11/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_10/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_9/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_4/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_3/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_27/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_25/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_24/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_20/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_19/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_18/6/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_17/6/2024:Update: Order Amended _x000D_14/6/2024:Update: Order Amended _x000D_13/6/2024:Update: Order Amended _x000D_12/6/2024:Update: Order Amended _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 | 7/6/2024: CSL to provide an update |  |  | 3.Allwyn to arrange rtr install | VFS1027731 | 30015949 | 6.Failed router install | AM |  | 2024-06-06 | 2024-07-08 | 2024-07-08 | TRUE |  |  |  | 2024-08-01 |  |  |  | 2024-08-01 | 23A004952891 |  | 2024-08-02 | 1
1062 | 486180 | 3158 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Cyclon Food & Wine | Slough | SL1 1DH |  | 6/9/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_5/9/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_4/9/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_3/9/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_2/9/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_29/8/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_28/8/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_27/8/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_22/8/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_21/8/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_20/8/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_19/8/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_19/8/2024:01431745 _x000D_16/8/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_15/8/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_14/8/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_13/8/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_12/8/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_9/8/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_8/8/2024:17/06/2024 _x000D_6/8/2024:17/06/2024 _x000D_5/8/2024:17/06/2024 _x000D_2/8/2024:17/06/2024 _x000D_1/8/2024:17/06/2024 _x000D_31/7/2024:17/06/2024 _x000D_31/7/2024:17/06/2024 _x000D_30/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_29/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_29/7/2024:01431745 _x000D_26/7/2024:01431745 _x000D_24/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_23/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_22/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_22/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_6/9/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_5/9/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_4/9/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_3/9/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_2/9/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_29/8/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_28/8/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_27/8/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_22/8/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_21/8/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_20/8/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_19/8/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_19/8/2024:01431745 _x000D_16/8/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_15/8/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_14/8/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_13/8/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_12/8/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_9/8/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_8/8/2024:17/06/2024 _x000D_6/8/2024:17/06/2024 _x000D_5/8/2024:17/06/2024 _x000D_2/8/2024:17/06/2024 _x000D_1/8/2024:17/06/2024 _x000D_31/7/2024:17/06/2024 _x000D_31/7/2024:17/06/2024 _x000D_30/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_29/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_29/7/2024:01431745 _x000D_26/7/2024:01431745 _x000D_24/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_23/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_22/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_22/7/2024:#Update - NFA - Allwyn confirmed new install date with retailer _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update - NFA - Allwyn confirmed new install date with retailer | 2024-06-07 |  |  |  |  | VFP2366186 | 30016939 | 1.Provisioning | AM |  | 2024-07-08 | 2024-09-02 |  | 0 | [11 empty] | 0
1063 | 455131 | 3744 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Spar | SALISBURY | SP2 9HJ |  | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:19/07/2024 13:58 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:19/07/2024 13:58 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | 0 | 2024-06-07 |  |  |  |  | VFP2424795 | 30016322 | 1.Provisioning | AM |  | 2024-07-08 | 2024-09-06 |  | 0 | [11 empty] | 0
1064 | 665140 | 3746 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Crick Post Office & Stores | NORTHAMPTON | NN6 7TX |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:37 _x000D_26/7/2024:22/07/2024 10:37 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:37 _x000D_26/7/2024:22/07/2024 10:37 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2363398 | 30016219 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
1065 | 659303 | 3747 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Rogers Newsagents | Wrexham | LL14 3YE |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:33 _x000D_26/7/2024:22/07/2024 10:33 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_18/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_17/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_16/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_15/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_12/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_11/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_10/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_9/7/2024:#Update - Action for Allwyn - Installation has now been amended to 26/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 26/07 is a suitable date. _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:33 _x000D_26/7/2024:22/07/2024 10:33 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_18/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_17/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_16/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_15/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_12/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_11/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_10/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_9/7/2024:#Update - Action for Allwyn - Installation has now been amended to 26/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 26/07 is a suitable date. _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2363397 | 30016196 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
1066 | 480934 | 3748 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Chandra Off Licence | London | SW16 2ND | 2024-08-23 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/08 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/08 AM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/08 AM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/08 AM _x000D_19/8/2024:01477014 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/08 AM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/08 AM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/08 AM _x000D_13/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/08 AM _x000D_12/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/08 AM _x000D_9/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/08 AM _x000D_8/8/2024:01/08/2024 _x000D_6/8/2024:01/08/2024 _x000D_5/8/2024:01/08/2024 _x000D_2/8/2024:01/08/2024 _x000D_1/8/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_30/7/2024:#Update - Action for Allwyn - Installation has now been amended to 16/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 16/08 is a suitable date. _x000D_29/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_29/7/2024:01477014 _x000D_26/7/2024:01477014 _x000D_24/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_23/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_22/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_22/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/08 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/08 AM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/08 AM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/08 AM _x000D_19/8/2024:01477014 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/08 AM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/08 AM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/08 AM _x000D_13/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/08 AM _x000D_12/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/08 AM _x000D_9/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/08 AM _x000D_8/8/2024:01/08/2024 _x000D_6/8/2024:01/08/2024 _x000D_5/8/2024:01/08/2024 _x000D_2/8/2024:01/08/2024 _x000D_1/8/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_30/7/2024:#Update - Action for Allwyn - Installation has now been amended to 16/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 16/08 is a suitable date. _x000D_29/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_29/7/2024:01477014 _x000D_26/7/2024:01477014 _x000D_24/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_23/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_22/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_22/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 26/07 AM _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | 0 | 2024-06-07 |  |  |  |  | VFS1012951 | 30016517 | 2.Commissioning | AM |  | 2024-07-08 | 2024-08-22 |  | 0 | [11 empty] | 0
1067 | 468618 | 3752 | Batch 5 Jul24 | Type 1 | FTTP | Go Local | Manchester | M19 1SQ |  | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:Your order has been delayed due to a customer missed appointment. Customer need out of hours appointment. And the order got re-appointed for 06/08/2024. _x000D_15/7/2024:Your order has been delayed due to a customer missed appointment. Customer need out of hours appointment. And the order got re-appointed for 06/08/2024. _x000D_12/7/2024:Your order has been delayed due to a customer missed appointment. Customer need out of hours appointment. And the order got re-appointed for 06/08/2024. _x000D_11/7/2024:Your order has been delayed due to a customer missed appointment. Customer need out of hours appointment. And the order got re-appointed for 06/08/2024. _x000D_10/7/2024:Your order has been delayed due to a customer missed appointment. Customer need out of hours appointment. And the order got re-appointed for 06/08/2024. _x000D_9/7/2024:Your order has been delayed due to a customer missed appointment. Customer need out of hours appointment. And the order got re-appointed for 06/08/2024. _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:Your order has been delayed due to a customer missed appointment. Customer need out of hours appointment. And the order got re-appointed for 06/08/2024. _x000D_15/7/2024:Your order has been delayed due to a customer missed appointment. Customer need out of hours appointment. And the order got re-appointed for 06/08/2024. _x000D_12/7/2024:Your order has been delayed due to a customer missed appointment. Customer need out of hours appointment. And the order got re-appointed for 06/08/2024. _x000D_11/7/2024:Your order has been delayed due to a customer missed appointment. Customer need out of hours appointment. And the order got re-appointed for 06/08/2024. _x000D_10/7/2024:Your order has been delayed due to a customer missed appointment. Customer need out of hours appointment. And the order got re-appointed for 06/08/2024. _x000D_9/7/2024:Your order has been delayed due to a customer missed appointment. Customer need out of hours appointment. And the order got re-appointed for 06/08/2024. _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2363396 | 30016295 | 2.Commissioning |  |  | 2024-07-08 | 2024-07-08 | 2024-07-08 | TRUE |  |  |  | 2024-08-08 | [7 empty] | 0
1068 | 649887 | 3753 | Batch 5 Jul24 | Type 3 | SoGEA/Mobile | Premier Hill Top News | TELFORD | TF7 5HU |  | 6/9/2024:#Update - Awaiting update from OR regarding alternate route, _x000D_5/9/2024:#Update - Awaiting update from OR regarding alternate route, _x000D_4/9/2024:#Update - Awaiting update from OR regarding alternate route, _x000D_3/9/2024:#Update - Awaiting update from OR regarding alternate route, _x000D_2/9/2024:#Update - Awaiting update from OR regarding alternate route, _x000D_29/8/2024:#Update - Awaiting update from OR regarding alternate route, _x000D_28/8/2024:#Update - Awaiting update from OR regarding alternate route, _x000D_27/8/2024:#Update - Awaiting update from OR regarding alternate route, _x000D_22/8/2024:#Update - Awaiting update from OR regarding alternate route, _x000D_21/8/2024:#Update - Awaiting update from OR regarding alternate route, _x000D_20/8/2024:#Update - Awaiting update from OR regarding alternate route, _x000D_19/8/2024:#Update - Awaiting update from OR regarding alternate route, _x000D_19/8/2024:01476310 _x000D_16/8/2024:#Update - Awaiting update from OR regarding alternate route, _x000D_15/8/2024:#Update - Awaiting update from OR regarding alternate route, _x000D_14/8/2024:#Update - Awaiting update from OR regarding alternate route, _x000D_13/8/2024:#Update - Awaiting update from OR regarding alternate route, _x000D_12/8/2024:#Update - Awaiting update from OR regarding alternate route, _x000D_9/8/2024:#Update - Awaiting update from OR regarding alternate route, _x000D_8/8/2024:30/07/2024 _x000D_6/8/2024:30/07/2024 _x000D_5/8/2024:30/07/2024 _x000D_2/8/2024:30/07/2024 _x000D_1/8/2024:30/07/2024 _x000D_31/7/2024:30/07/2024 _x000D_31/7/2024:30/07/2024 _x000D_30/7/2024:#Update - Awaiting update from OR regarding alternate route, _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - Awaiting update from OR regarding alternate route, _x000D_6/9/2024:#Update - Awaiting update from OR regarding alternate route, _x000D_5/9/2024:#Update - Awaiting update from OR regarding alternate route, _x000D_4/9/2024:#Update - Awaiting update from OR regarding alternate route, _x000D_3/9/2024:#Update - Awaiting update from OR regarding alternate route, _x000D_2/9/2024:#Update - Awaiting update from OR regarding alternate route, _x000D_29/8/2024:#Update - Awaiting update from OR regarding alternate route, _x000D_28/8/2024:#Update - Awaiting update from OR regarding alternate route, _x000D_27/8/2024:#Update - Awaiting update from OR regarding alternate route, _x000D_22/8/2024:#Update - Awaiting update from OR regarding alternate route, _x000D_21/8/2024:#Update - Awaiting update from OR regarding alternate route, _x000D_20/8/2024:#Update - Awaiting update from OR regarding alternate route, _x000D_19/8/2024:#Update - Awaiting update from OR regarding alternate route, _x000D_19/8/2024:01476310 _x000D_16/8/2024:#Update - Awaiting update from OR regarding alternate route, _x000D_15/8/2024:#Update - Awaiting update from OR regarding alternate route, _x000D_14/8/2024:#Update - Awaiting update from OR regarding alternate route, _x000D_13/8/2024:#Update - Awaiting update from OR regarding alternate route, _x000D_12/8/2024:#Update - Awaiting update from OR regarding alternate route, _x000D_9/8/2024:#Update - Awaiting update from OR regarding alternate route, _x000D_8/8/2024:30/07/2024 _x000D_6/8/2024:30/07/2024 _x000D_5/8/2024:30/07/2024 _x000D_2/8/2024:30/07/2024 _x000D_1/8/2024:30/07/2024 _x000D_31/7/2024:30/07/2024 _x000D_31/7/2024:30/07/2024 _x000D_30/7/2024:#Update - Awaiting update from OR regarding alternate route, _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update - Awaiting update from OR regarding alternate route, | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1012947 | 30016485 | 2.Commissioning | AM |  |  |  |  | 0 |  |  |  | 2024-08-26 | [7 empty] | 0
1069 | 669012 | 3754 | Batch 5 Jul24 | Type 1 | FTTP | The Village Store | Strabane | BT82 0HN |  | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2363395 | 30016326 | 2.Commissioning |  |  | 2024-07-08 | 2024-07-08 | 2024-07-08 | TRUE |  |  |  | 2024-08-02 | [7 empty] | 0
1070 | 462038 | 3757 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Premier K and T Food and Wine | CREWE | CW1 3NF |  | 6/9/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_5/9/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_4/9/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_3/9/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_2/9/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_29/8/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_28/8/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_27/8/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_22/8/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_21/8/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_20/8/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_19/8/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_19/8/2024:01476388 _x000D_16/8/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_15/8/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_14/8/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_13/8/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_12/8/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_9/8/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_8/8/2024:09/07/2024 _x000D_6/8/2024:09/07/2024 _x000D_5/8/2024:09/07/2024 _x000D_2/8/2024:09/07/2024 _x000D_1/8/2024:09/07/2024 _x000D_31/7/2024:09/07/2024 _x000D_31/7/2024:09/07/2024 _x000D_30/7/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_29/7/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_29/7/2024:01476388 _x000D_26/7/2024:01476388 _x000D_24/7/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_23/7/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_22/7/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_22/7/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_6/9/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_5/9/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_4/9/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_3/9/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_2/9/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_29/8/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_28/8/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_27/8/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_22/8/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_21/8/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_20/8/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_19/8/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_19/8/2024:01476388 _x000D_16/8/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_15/8/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_14/8/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_13/8/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_12/8/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_9/8/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_8/8/2024:09/07/2024 _x000D_6/8/2024:09/07/2024 _x000D_5/8/2024:09/07/2024 _x000D_2/8/2024:09/07/2024 _x000D_1/8/2024:09/07/2024 _x000D_31/7/2024:09/07/2024 _x000D_31/7/2024:09/07/2024 _x000D_30/7/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_29/7/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_29/7/2024:01476388 _x000D_26/7/2024:01476388 _x000D_24/7/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_23/7/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_22/7/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_22/7/2024:#Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update - Engineer thinks this install is not possible even with an advanced upgrade. Asking openreach to include more information regarding this being a good candidate for mobile options to submit to allwyn. | 2024-06-07 |  |  |  |  | VFS1012944 | 30016399 | 1.Provisioning | AM |  | 2024-07-08 | 2024-08-12 |  | 0 | [11 empty] | 0
1071 | 432122 | 3761 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | SPAR | LANCASTER | LA1 4AQ |  | 6/9/2024:#Update - awaiting ECC approval - proposal sent to VF 11/07 _x000D_5/9/2024:#Update - awaiting ECC approval - proposal sent to VF 11/07 _x000D_4/9/2024:#Update - awaiting ECC approval - proposal sent to VF 11/07 _x000D_3/9/2024:#Update - awaiting ECC approval - proposal sent to VF 11/07 _x000D_2/9/2024:#Update - awaiting ECC approval - proposal sent to VF 11/07 _x000D_29/8/2024:#Update - awaiting ECC approval - proposal sent to VF 11/07 _x000D_28/8/2024:#Update - awaiting ECC approval - proposal sent to VF 11/07 _x000D_Awaiting ECC approval premium upgrade - proposal sent to VF 11/07 | 9/9/2024:#Update - awaiting ECC approval - proposal sent to VF 11/07 _x000D_6/9/2024:#Update - awaiting ECC approval - proposal sent to VF 11/07 _x000D_5/9/2024:#Update - awaiting ECC approval - proposal sent to VF 11/07 _x000D_4/9/2024:#Update - awaiting ECC approval - proposal sent to VF 11/07 _x000D_3/9/2024:#Update - awaiting ECC approval - proposal sent to VF 11/07 _x000D_2/9/2024:#Update - awaiting ECC approval - proposal sent to VF 11/07 _x000D_29/8/2024:#Update - awaiting ECC approval - proposal sent to VF 11/07 _x000D_28/8/2024:#Update - awaiting ECC approval - proposal sent to VF 11/07 _x000D_Awaiting ECC approval premium upgrade - proposal sent to VF 11/07 | 0 | #Update - awaiting ECC approval - proposal sent to VF 11/07 | 2024-06-07 |  |  |  |  | VFP2363394 | 30016221 | 1.Provisioning | AM |  | 2024-07-08 | 2024-07-08 |  | 0 | [11 empty] | 0
1072 | 486348 | 3762 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | SPAR LLANISHEN FACH | CARDIFF | CF14 6LB |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:50 _x000D_26/7/2024:22/07/2024 10:50 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:50 _x000D_26/7/2024:22/07/2024 10:50 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2363391 | 30016233 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
1073 | 650490 | 3766 | Batch 5 Jul24 | Type 1 | FTTP | Costcutter | Birmingham | B32 4AG |  | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2363388 | 30016373 | 6.Failed router install |  |  | 2024-07-08 | 2024-07-08 | 2024-07-08 | TRUE |  |  |  | 2024-08-08 |  |  |  | 2024-08-08 | 23A004948346 |  | 2024-08-09 | 1
1074 | 664425 | 3769 | Batch 5 Jul24 | Type 1 | SOGEA | Llanfachraeth Spso | HOLYHEAD | LL65 4UL |  | 29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1065489 | 30021962 | 2.Commissioning |  |  | 2024-07-08 | 2024-07-08 | 2024-07-08 | TRUE |  |  |  | 2024-08-14 | [7 empty] | 0
1075 | 260583 | 3770 | Batch 5 Jul24 | Type 1 | SOGEA | Beaumout News | LEICESTER | LE4 1EF |  | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1012936 | 30016432 | 6.Failed router install |  |  | 2024-07-08 | 2024-07-08 | 2024-07-08 | TRUE |  |  |  | 2024-08-02 |  |  |  | 2024-08-02 | 242005008654 |  | 2024-08-06 | 1
1076 | 630180 | 3775 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Nisa Local | Saffron Walden | CB11 4BE |  | 6/9/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_5/9/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_4/9/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_3/9/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_2/9/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_29/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_28/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_27/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_22/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_21/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_20/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_19/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_19/8/2024:01479408 _x000D_16/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_15/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_14/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_13/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_12/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_9/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_8/8/2024:16/07/2024 _x000D_6/8/2024:16/07/2024 _x000D_5/8/2024:16/07/2024 _x000D_2/8/2024:16/07/2024 _x000D_1/8/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_30/7/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_29/7/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_29/7/2024:01479408 _x000D_26/7/2024:01479408 _x000D_24/7/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_23/7/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_22/7/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_22/7/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_15/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_12/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_11/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_10/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_9/7/2024:Supplier Delay: KCI-3 (Order Completed) Delayed in Processing. _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_6/9/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_5/9/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_4/9/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_3/9/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_2/9/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_29/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_28/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_27/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_22/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_21/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_20/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_19/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_19/8/2024:01479408 _x000D_16/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_15/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_14/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_13/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_12/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_9/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_8/8/2024:16/07/2024 _x000D_6/8/2024:16/07/2024 _x000D_5/8/2024:16/07/2024 _x000D_2/8/2024:16/07/2024 _x000D_1/8/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_30/7/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_29/7/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_29/7/2024:01479408 _x000D_26/7/2024:01479408 _x000D_24/7/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_23/7/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_22/7/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_22/7/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_15/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_12/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_11/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_10/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_9/7/2024:Supplier Delay: KCI-3 (Order Completed) Delayed in Processing. _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 | 2024-06-07 |  |  |  |  | VFS1012935 | 30016545 | 1.Provisioning | AM |  | 2024-07-08 | 2024-08-30 |  | 0 | [11 empty] | 0
1077 | 465421 | 3776 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Londis Starthill Service Station | ROCHFORD | SS4 1RF |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:Update: Order Amended _x000D_19/8/2024:Update: Order Amended _x000D_19/8/2024:13/08/2024 15:15 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:19/07/2024 09:38 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:Update: Order Amended _x000D_19/8/2024:Update: Order Amended _x000D_19/8/2024:13/08/2024 15:15 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:19/07/2024 09:38 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2363383 | 30016346 | 1.Provisioning | AM |  | 2024-07-08 | 2024-09-10 |  | 0 | [11 empty] | 0
1078 | 209673 | 3781 | Batch 5 Jul24 | Type 1 | SOGEA | Spar | PORTSMOUTH | PO1 5PL |  | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_15/7/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_12/7/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_11/7/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_10/7/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_9/7/2024:End User Missed appointment. Action required _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_15/7/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_12/7/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_11/7/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_10/7/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_9/7/2024:End User Missed appointment. Action required _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1012931 | 30016465 | 6.Failed router install |  |  | 2024-07-08 | 2024-07-08 | 2024-07-08 | TRUE |  |  |  | 2024-08-09 |  |  |  | 2024-08-09 | 242005010993 |  | 2024-08-12 | 1
1079 | 670572 | 3782 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Birchwood Post Office | WARRINGTON | WA3 7PG |  | 6/9/2024:#Update - The site above has failed its second appointment due to the engineer being unable to gain access to the site. Security clearance is required to access line plant in the post office. The engineer was told security is handled by Grapevine (03456034004) FAD code 1544349. Allwyn to discuss the above with the retailer and advise if they can arrange access with the security company. _x000D_5/9/2024:#Update - The site above has failed its second appointment due to the engineer being unable to gain access to the site. Security clearance is required to access line plant in the post office. The engineer was told security is handled by Grapevine (03456034004) FAD code 1544349. Allwyn to discuss the above with the retailer and advise if they can arrange access with the security company. _x000D_4/9/2024:#Update - The site above has failed its second appointment due to the engineer being unable to gain access to the site. Security clearance is required to access line plant in the post office. The engineer was told security is handled by Grapevine (03456034004) FAD code 1544349. Allwyn to discuss the above with the retailer and advise if they can arrange access with the security company. _x000D_3/9/2024:#Update - The site above has failed its second appointment due to the engineer being unable to gain access to the site. Security clearance is required to access line plant in the post office. The engineer was told security is handled by Grapevine (03456034004) FAD code 1544349. Allwyn to discuss the above with the retailer and advise if they can arrange access with the security company. _x000D_2/9/2024:#Update - The site above has failed its second appointment due to the engineer being unable to gain access to the site. Security clearance is required to access line plant in the post office. The engineer was told security is handled by Grapevine (03456034004) FAD code 1544349. Allwyn to discuss the above with the retailer and advise if they can arrange access with the security company. _x000D_29/8/2024:#Update - The site above has failed its second appointment due to the engineer being unable to gain access to the site. Security clearance is required to access line plant in the post office. The engineer was told security is handled by Grapevine (03456034004) FAD code 1544349. Allwyn to discuss the above with the retailer and advise if they can arrange access with the security company. _x000D_28/8/2024:#Update - The site above has failed its second appointment due to the engineer being unable to gain access to the site. Security clearance is required to access line plant in the post office. The engineer was told security is handled by Grapevine (03456034004) FAD code 1544349. Allwyn to discuss the above with the retailer and advise if they can arrange access with the security company. _x000D_27/8/2024:#Update - The site above has failed its second appointment due to the engineer being unable to gain access to the site. Security clearance is required to access line plant in the post office. The engineer was told security is handled by Grapevine (03456034004) FAD code 1544349. Allwyn to discuss the above with the retailer and advise if they can arrange access with the security company. _x000D_22/8/2024:#Update - The site above has failed its second appointment due to the engineer being unable to gain access to the site. Security clearance is required to access line plant in the post office. The engineer was told security is handled by Grapevine (03456034004) FAD code 1544349. Allwyn to discuss the above with the retailer and advise if they can arrange access with the security company. _x000D_21/8/2024:#Update - The site above has failed its second appointment due to the engineer being unable to gain access to the site. Security clearance is required to access line plant in the post office. The engineer was told security is handled by Grapevine (03456034004) FAD code 1544349. Allwyn to discuss the above with the retailer and advise if they can arrange access with the security company. _x000D_20/8/2024:#Update - The site above has failed its second appointment due to the engineer being unable to gain access to the site. Security clearance is required to access line plant in the post office. The engineer was told security is handled by Grapevine (03456034004) FAD code 1544349. Allwyn to discuss the above with the retailer and advise if they can arrange access with the security company. _x000D_19/8/2024:#Update - The site above has failed its second appointment due to the engineer being unable to gain access to the site. Security clearance is required to access line plant in the post office. The engineer was told security is handled by Grapevine (03456034004) FAD code 1544349. Allwyn to discuss the above with the retailer and advise if they can arrange access with the security company. _x000D_19/8/2024:01477093 _x000D_16/8/2024:#Update - The site above has failed its second appointment due to the engineer being unable to gain access to the site. Security clearance is required to access line plant in the post office. The engineer was told security is handled by Grapevine (03456034004) FAD code 1544349. Allwyn to discuss the above with the retailer and advise if they can arrange access with the security company. _x000D_15/8/2024:#Update - The site above has failed its second appointment due to the engineer being unable to gain access to the site. Security clearance is required to access line plant in the post office. The engineer was told security is handled by Grapevine (03456034004) FAD code 1544349. Allwyn to discuss the above with the retailer and advise if they can arrange access with the security company. _x000D_14/8/2024:#Update - The site above has failed its second appointment due to the engineer being unable to gain access to the site. Security clearance is required to access line plant in the post office. The engineer was told security is handled by Grapevine (03456034004) FAD code 1544349. Allwyn to discuss the above with the retailer and advise if they can arrange access with the security company. _x000D_13/8/2024:#Update - The site above has failed its second appointment due to the engineer being unable to gain access to the site. Security clearance is required to access line plant in the post office. The engineer was told security is handled by Grapevine (03456034004) FAD code 1544349. Allwyn to discuss the above with the retailer and advise if they can arrange access with the security company. _x000D_12/8/2024:#Update - The site above has failed its second appointment due to the engineer being unable to gain access to the site. Security clearance is required to access line plant in the post office. The engineer was told security is handled by Grapevine (03456034004) FAD code 1544349. Allwyn to discuss the above with the retailer and advise if they can arrange access with the security company. _x000D_9/8/2024:#Update - The site above has failed its second appointment due to the engineer being unable to gain access to the site. Security clearance is required to access line plant in the post office. The engineer was told security is handled by Grapevine (03456034004) FAD code 1544349. Allwyn to discuss the above with the retailer and advise if they can arrange access with the security company. _x000D_8/8/2024:05/08/2024 _x000D_6/8/2024:05/08/2024 _x000D_5/8/2024:05/08/2024 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:19/07/2024 11:54 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - The site above has failed its second appointment due to the engineer being unable to gain access to the site. Security clearance is required to access line plant in the post office. The engineer was told security is handled by Grapevine (03456034004) FAD code 1544349. Allwyn to discuss the above with the retailer and advise if they can arrange access with the security company. _x000D_6/9/2024:#Update - The site above has failed its second appointment due to the engineer being unable to gain access to the site. Security clearance is required to access line plant in the post office. The engineer was told security is handled by Grapevine (03456034004) FAD code 1544349. Allwyn to discuss the above with the retailer and advise if they can arrange access with the security company. _x000D_5/9/2024:#Update - The site above has failed its second appointment due to the engineer being unable to gain access to the site. Security clearance is required to access line plant in the post office. The engineer was told security is handled by Grapevine (03456034004) FAD code 1544349. Allwyn to discuss the above with the retailer and advise if they can arrange access with the security company. _x000D_4/9/2024:#Update - The site above has failed its second appointment due to the engineer being unable to gain access to the site. Security clearance is required to access line plant in the post office. The engineer was told security is handled by Grapevine (03456034004) FAD code 1544349. Allwyn to discuss the above with the retailer and advise if they can arrange access with the security company. _x000D_3/9/2024:#Update - The site above has failed its second appointment due to the engineer being unable to gain access to the site. Security clearance is required to access line plant in the post office. The engineer was told security is handled by Grapevine (03456034004) FAD code 1544349. Allwyn to discuss the above with the retailer and advise if they can arrange access with the security company. _x000D_2/9/2024:#Update - The site above has failed its second appointment due to the engineer being unable to gain access to the site. Security clearance is required to access line plant in the post office. The engineer was told security is handled by Grapevine (03456034004) FAD code 1544349. Allwyn to discuss the above with the retailer and advise if they can arrange access with the security company. _x000D_29/8/2024:#Update - The site above has failed its second appointment due to the engineer being unable to gain access to the site. Security clearance is required to access line plant in the post office. The engineer was told security is handled by Grapevine (03456034004) FAD code 1544349. Allwyn to discuss the above with the retailer and advise if they can arrange access with the security company. _x000D_28/8/2024:#Update - The site above has failed its second appointment due to the engineer being unable to gain access to the site. Security clearance is required to access line plant in the post office. The engineer was told security is handled by Grapevine (03456034004) FAD code 1544349. Allwyn to discuss the above with the retailer and advise if they can arrange access with the security company. _x000D_27/8/2024:#Update - The site above has failed its second appointment due to the engineer being unable to gain access to the site. Security clearance is required to access line plant in the post office. The engineer was told security is handled by Grapevine (03456034004) FAD code 1544349. Allwyn to discuss the above with the retailer and advise if they can arrange access with the security company. _x000D_22/8/2024:#Update - The site above has failed its second appointment due to the engineer being unable to gain access to the site. Security clearance is required to access line plant in the post office. The engineer was told security is handled by Grapevine (03456034004) FAD code 1544349. Allwyn to discuss the above with the retailer and advise if they can arrange access with the security company. _x000D_21/8/2024:#Update - The site above has failed its second appointment due to the engineer being unable to gain access to the site. Security clearance is required to access line plant in the post office. The engineer was told security is handled by Grapevine (03456034004) FAD code 1544349. Allwyn to discuss the above with the retailer and advise if they can arrange access with the security company. _x000D_20/8/2024:#Update - The site above has failed its second appointment due to the engineer being unable to gain access to the site. Security clearance is required to access line plant in the post office. The engineer was told security is handled by Grapevine (03456034004) FAD code 1544349. Allwyn to discuss the above with the retailer and advise if they can arrange access with the security company. _x000D_19/8/2024:#Update - The site above has failed its second appointment due to the engineer being unable to gain access to the site. Security clearance is required to access line plant in the post office. The engineer was told security is handled by Grapevine (03456034004) FAD code 1544349. Allwyn to discuss the above with the retailer and advise if they can arrange access with the security company. _x000D_19/8/2024:01477093 _x000D_16/8/2024:#Update - The site above has failed its second appointment due to the engineer being unable to gain access to the site. Security clearance is required to access line plant in the post office. The engineer was told security is handled by Grapevine (03456034004) FAD code 1544349. Allwyn to discuss the above with the retailer and advise if they can arrange access with the security company. _x000D_15/8/2024:#Update - The site above has failed its second appointment due to the engineer being unable to gain access to the site. Security clearance is required to access line plant in the post office. The engineer was told security is handled by Grapevine (03456034004) FAD code 1544349. Allwyn to discuss the above with the retailer and advise if they can arrange access with the security company. _x000D_14/8/2024:#Update - The site above has failed its second appointment due to the engineer being unable to gain access to the site. Security clearance is required to access line plant in the post office. The engineer was told security is handled by Grapevine (03456034004) FAD code 1544349. Allwyn to discuss the above with the retailer and advise if they can arrange access with the security company. _x000D_13/8/2024:#Update - The site above has failed its second appointment due to the engineer being unable to gain access to the site. Security clearance is required to access line plant in the post office. The engineer was told security is handled by Grapevine (03456034004) FAD code 1544349. Allwyn to discuss the above with the retailer and advise if they can arrange access with the security company. _x000D_12/8/2024:#Update - The site above has failed its second appointment due to the engineer being unable to gain access to the site. Security clearance is required to access line plant in the post office. The engineer was told security is handled by Grapevine (03456034004) FAD code 1544349. Allwyn to discuss the above with the retailer and advise if they can arrange access with the security company. _x000D_9/8/2024:#Update - The site above has failed its second appointment due to the engineer being unable to gain access to the site. Security clearance is required to access line plant in the post office. The engineer was told security is handled by Grapevine (03456034004) FAD code 1544349. Allwyn to discuss the above with the retailer and advise if they can arrange access with the security company. _x000D_8/8/2024:05/08/2024 _x000D_6/8/2024:05/08/2024 _x000D_5/8/2024:05/08/2024 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:19/07/2024 11:54 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update - The site above has failed its second appointment due to the engineer being unable to gain access to the site. Security clearance is required to access line plant in the post office. The engineer was told security is handled by Grapevine (03456034004) FAD code 1544349. Allwyn to discuss the above with the retailer and advise if they can arrange access with the security company. | 2024-06-07 |  |  |  |  | VFS1012929 | 30016493 | 1.Provisioning | AM |  | 2024-07-08 | 2024-08-29 |  | 0 | [11 empty] | 0
1080 | 665874 | 3784 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Chapel Post Office | KIRKCALDY | KY2 6YL |  | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_22/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_21/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_20/8/2024:End User Missed appointment. Action required _x000D_19/8/2024:End User Missed appointment. Action required _x000D_19/8/2024:19/08/2024 09:21 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_22/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_21/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_20/8/2024:End User Missed appointment. Action required _x000D_19/8/2024:End User Missed appointment. Action required _x000D_19/8/2024:19/08/2024 09:21 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | 0 | 2024-06-07 |  |  |  |  | VFS1063826 | 30016401 | 1.Provisioning | AM |  | 2024-07-08 | 2024-08-19 |  | 0 | [11 empty] | 0
1081 | 665502 | 3786 | Batch 5 Jul24 | Type 1 | FTTP | Goodwood Parade Post Office | WATFORD | WD24 5LL |  | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2363378 | 30016354 | 2.Commissioning |  |  | 2024-07-08 | 2024-07-08 | 2024-07-08 | TRUE |  |  |  | 2024-08-05 | [7 empty] | 0
1082 | 651299 | 3789 | Batch 5 Jul24 | Type 1 | SOGEA | Londis | Milton Keynes | MK2 2NQ |  | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1012928 | 30016444 | 6.Failed router install |  |  | 2024-07-08 | 2024-07-08 | 2024-07-08 | TRUE |  |  |  | 2024-08-05 |  |  |  | 2024-08-05 | 242005010974 |  | 2024-08-06 | 1
1083 | 457660 | 3791 | Batch 5 Jul24 | Type 1 | SOGEA | Keystore | ARDROSSAN | KA22 7HS |  | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1012926 | 30016567 | 2.Commissioning |  |  | 2024-07-08 | 2024-07-08 | 2024-07-08 | TRUE |  |  |  | 2024-08-01 | [7 empty] | 0
1084 | 431279 | 3793 | Batch 5 Jul24 | Type 1 | FTTP | Premier | TONBRIDGE | TN10 3HZ |  | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:Your order has been delayed by suppliers due to advanced install type being required with additional charges please check with end user and confirm charges acceptance to proceed this order. _x000D_15/7/2024:Your order has been delayed by suppliers due to advanced install type being required with additional charges please check with end user and confirm charges acceptance to proceed this order. _x000D_12/7/2024:Your order has been delayed by suppliers due to advanced install type being required with additional charges please check with end user and confirm charges acceptance to proceed this order. _x000D_11/7/2024:Your order has been delayed by suppliers due to advanced install type being required with additional charges please check with end user and confirm charges acceptance to proceed this order. _x000D_10/7/2024:Your order has been delayed by suppliers due to advanced install type being required with additional charges please check with end user and confirm charges acceptance to proceed this order. _x000D_9/7/2024:Supplier Delay: KCI-3 (Order Completed) Delayed in Processing. _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:Your order has been delayed by suppliers due to advanced install type being required with additional charges please check with end user and confirm charges acceptance to proceed this order. _x000D_15/7/2024:Your order has been delayed by suppliers due to advanced install type being required with additional charges please check with end user and confirm charges acceptance to proceed this order. _x000D_12/7/2024:Your order has been delayed by suppliers due to advanced install type being required with additional charges please check with end user and confirm charges acceptance to proceed this order. _x000D_11/7/2024:Your order has been delayed by suppliers due to advanced install type being required with additional charges please check with end user and confirm charges acceptance to proceed this order. _x000D_10/7/2024:Your order has been delayed by suppliers due to advanced install type being required with additional charges please check with end user and confirm charges acceptance to proceed this order. _x000D_9/7/2024:Supplier Delay: KCI-3 (Order Completed) Delayed in Processing. _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2363589 | 30016319 | 6.Failed router install |  |  | 2024-07-08 | 2024-07-08 | 2024-07-08 | TRUE |  |  |  | 2024-08-02 |  |  |  | 2024-08-02 | 242005011082 |  | 2024-08-06 | 1
1085 | 457039 | 3794 | Batch 5 Jul24 | Type 3 | FTTP/Mobile | Nisa Local Bell | Kidderminster | DY10 3YT |  | 6/9/2024:﻿#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_5/9/2024:﻿#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_4/9/2024:﻿#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_3/9/2024:﻿#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_2/9/2024:﻿#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_29/8/2024:﻿#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_28/8/2024:﻿#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_27/8/2024:﻿#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_22/8/2024:﻿#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_21/8/2024:﻿#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_20/8/2024:﻿#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_19/8/2024:﻿#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_19/8/2024:01478363 _x000D_16/8/2024:﻿#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_15/8/2024:﻿#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_14/8/2024:﻿#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_13/8/2024:﻿#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_12/8/2024:﻿#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_9/8/2024:﻿#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_8/8/2024:05/08/2024 _x000D_6/8/2024:05/08/2024 _x000D_5/8/2024:05/08/2024 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:﻿#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_6/9/2024:﻿#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_5/9/2024:﻿#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_4/9/2024:﻿#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_3/9/2024:﻿#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_2/9/2024:﻿#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_29/8/2024:﻿#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_28/8/2024:﻿#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_27/8/2024:﻿#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_22/8/2024:﻿#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_21/8/2024:﻿#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_20/8/2024:﻿#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_19/8/2024:﻿#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_19/8/2024:01478363 _x000D_16/8/2024:﻿#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_15/8/2024:﻿#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_14/8/2024:﻿#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_13/8/2024:﻿#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_12/8/2024:﻿#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_9/8/2024:﻿#Update - this site has changed to a site type 3 / mobile only as per customer request _x000D_8/8/2024:05/08/2024 _x000D_6/8/2024:05/08/2024 _x000D_5/8/2024:05/08/2024 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | ﻿#Update - this site has changed to a site type 3 / mobile only as per customer request | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2363588 | 30016327 | 2.Commissioning | AM |  |  |  |  | 0 |  |  |  | 2024-08-27 | [7 empty] | 0
1086 | 462607 | 3795 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | SPAR | DALKEITH | EH22 2BP |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:43 _x000D_26/7/2024:22/07/2024 10:43 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:43 _x000D_26/7/2024:22/07/2024 10:43 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2363587 | 30016333 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
1087 | 666318 | 3796 | Batch 5 Jul24 | Type 1 | SOGEA | Smithies PO Local | Barnsely | S71 3SZ |  | 19/7/2024:#Update - ECC proposal sent to Vodafone on 18/07 _x000D_18/7/2024:#Update - 4 hours of additional work is required to complete the task, full provision needed into middle of shop to get socket near lottery machine. CSL are awaiting for more information from Openreach. _x000D_17/7/2024:#Update - 4 hours of additional work is required to complete the task, full provision needed into middle of shop to get socket near lottery machine. CSL are awaiting for more information from Openreach. _x000D_16/7/2024:#Update - 4 hours of additional work is required to complete the task, full provision needed into middle of shop to get socket near lottery machine. CSL are awaiting for more information from Openreach. _x000D_15/7/2024:#Update - 4 hours of additional work is required to complete the task, full provision needed into middle of shop to get socket near lottery machine. CSL are awaiting for more information from Openreach. _x000D_12/7/2024:#Update - 4 hours of additional work is required to complete the task, full provision needed into middle of shop to get socket near lottery machine. CSL are awaiting for more information from Openreach. _x000D_11/7/2024:#Update - 4 hours of additional work is required to complete the task, full provision needed into middle of shop to get socket near lottery machine. CSL are awaiting for more information from Openreach. _x000D_10/7/2024:#Update - 4 hours of additional work is required to complete the task, full provision needed into middle of shop to get socket near lottery machine. CSL are awaiting for more information from Openreach. _x000D_9/7/2024:#Update - 4 hours of additional work is required to complete the task, full provision needed into middle of shop to get socket near lottery machine. CSL are awaiting for more information from Openreach. _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:#Update - ECC proposal sent to Vodafone on 18/07 _x000D_18/7/2024:#Update - 4 hours of additional work is required to complete the task, full provision needed into middle of shop to get socket near lottery machine. CSL are awaiting for more information from Openreach. _x000D_17/7/2024:#Update - 4 hours of additional work is required to complete the task, full provision needed into middle of shop to get socket near lottery machine. CSL are awaiting for more information from Openreach. _x000D_16/7/2024:#Update - 4 hours of additional work is required to complete the task, full provision needed into middle of shop to get socket near lottery machine. CSL are awaiting for more information from Openreach. _x000D_15/7/2024:#Update - 4 hours of additional work is required to complete the task, full provision needed into middle of shop to get socket near lottery machine. CSL are awaiting for more information from Openreach. _x000D_12/7/2024:#Update - 4 hours of additional work is required to complete the task, full provision needed into middle of shop to get socket near lottery machine. CSL are awaiting for more information from Openreach. _x000D_11/7/2024:#Update - 4 hours of additional work is required to complete the task, full provision needed into middle of shop to get socket near lottery machine. CSL are awaiting for more information from Openreach. _x000D_10/7/2024:#Update - 4 hours of additional work is required to complete the task, full provision needed into middle of shop to get socket near lottery machine. CSL are awaiting for more information from Openreach. _x000D_9/7/2024:#Update - 4 hours of additional work is required to complete the task, full provision needed into middle of shop to get socket near lottery machine. CSL are awaiting for more information from Openreach. _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1012923 | 30016508 | 2.Commissioning |  |  | 2024-07-08 | 2024-07-08 | 2024-07-08 | TRUE |  |  |  | 2024-08-02 | [7 empty] | 0
1088 | 662269 | 3799 | Batch 5 Jul24 | Type 1 | SOGEA | Hiccup Convenience Stores | Hanley | ST1 3QH |  | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_15/7/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_12/7/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_11/7/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_10/7/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 06/06/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_6/6/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 06/06/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_5/6/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 06/06/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_4/6/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 06/06/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_ | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_15/7/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_12/7/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_11/7/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_10/7/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 06/06/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_6/6/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 06/06/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_5/6/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 06/06/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_4/6/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 06/06/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1012921 | 30016524 | 2.Commissioning |  |  | 2024-07-09 | 2024-07-09 | 2024-07-09 | TRUE |  |  |  | 2024-08-13 | [7 empty] | 0
1089 | 612448 | 3800 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Go Local Extra | Manchester | M23 9PS |  | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:EU Missed Appointment. Supplier engineer has been unable to gain access. _x000D_22/8/2024:EU Missed Appointment. Supplier engineer has been unable to gain access. _x000D_21/8/2024:EU Missed Appointment. Supplier engineer has been unable to gain access. _x000D_20/8/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:EU Missed Appointment. Supplier engineer has been unable to gain access. _x000D_22/8/2024:EU Missed Appointment. Supplier engineer has been unable to gain access. _x000D_21/8/2024:EU Missed Appointment. Supplier engineer has been unable to gain access. _x000D_20/8/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | 0 | 2024-06-07 |  |  |  |  | VFS1093817 | 30016551 | 1.Provisioning | AM |  | 2024-07-09 | 2024-08-19 |  | 0 | [11 empty] | 0
1090 | 434332 | 3801 | Batch 5 Jul24 | Type 1 | FTTP | G & As Corner Shop | INVERURIE | AB51 4ST |  | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:End User Missed appointment. Action required _x000D_15/7/2024:End User Missed appointment. Action required _x000D_12/7/2024:End User Missed appointment. Action required _x000D_11/7/2024:End User Missed appointment. Action required _x000D_10/7/2024:End User Missed appointment. Action required _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:End User Missed appointment. Action required _x000D_15/7/2024:End User Missed appointment. Action required _x000D_12/7/2024:End User Missed appointment. Action required _x000D_11/7/2024:End User Missed appointment. Action required _x000D_10/7/2024:End User Missed appointment. Action required _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2363586 | 30016208 | 6.Failed router install |  |  | 2024-07-09 | 2024-07-09 | 2024-07-09 | TRUE | [7 empty] | 2024-08-21 | 239004929647 | 239004929647 | 2024-08-22 | 1
1091 | 636176 | 3803 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Go Local | MANCHESTER | M22 0LA |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:22 _x000D_26/7/2024:22/07/2024 10:22 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_15/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_12/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_11/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_10/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:22 _x000D_26/7/2024:22/07/2024 10:22 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_15/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_12/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_11/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_10/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2363583 | 30016286 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
1092 | 645397 | 3804 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Welcome Buckskin | Basingstoke | RG22 5BW |  | 22/8/2024:#Update Awaiting further information from OR _x000D_21/8/2024:#Update Awaiting further information from OR _x000D_20/8/2024:#Update Awaiting further information from OR _x000D_19/8/2024:#Update Awaiting further information from OR _x000D_19/8/2024:01480328 _x000D_16/8/2024:#Update Awaiting further information from OR _x000D_15/8/2024:#Update Awaiting further information from OR _x000D_14/8/2024:#Update Awaiting further information from OR _x000D_13/8/2024:#Update Awaiting further information from OR _x000D_12/8/2024:#Update Awaiting further information from OR _x000D_9/8/2024:#Update Awaiting further information from OR _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update Awaiting further information from OR _x000D_29/7/2024:#Update Awaiting further information from OR _x000D_29/7/2024:01480328 _x000D_26/7/2024:19/07/2024 10:52 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 22/8/2024:#Update Awaiting further information from OR _x000D_21/8/2024:#Update Awaiting further information from OR _x000D_20/8/2024:#Update Awaiting further information from OR _x000D_19/8/2024:#Update Awaiting further information from OR _x000D_19/8/2024:01480328 _x000D_16/8/2024:#Update Awaiting further information from OR _x000D_15/8/2024:#Update Awaiting further information from OR _x000D_14/8/2024:#Update Awaiting further information from OR _x000D_13/8/2024:#Update Awaiting further information from OR _x000D_12/8/2024:#Update Awaiting further information from OR _x000D_9/8/2024:#Update Awaiting further information from OR _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update Awaiting further information from OR _x000D_29/7/2024:#Update Awaiting further information from OR _x000D_29/7/2024:01480328 _x000D_26/7/2024:19/07/2024 10:52 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1012917 | 30016411 | 2.Commissioning | AM |  | 2024-07-09 | 2024-08-20 |  | 0 | [11 empty] | 0
1093 | 621898 | 3806 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | H and S Stores | Dagenham | RM10 8YL |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:24 _x000D_26/7/2024:22/07/2024 10:24 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_12/7/2024:Openreach Delay : Automated testing has identified a potential fault _x000D_11/7/2024:Openreach Delay : Automated testing has identified a potential fault _x000D_10/7/2024:Openreach Delay : Automated testing has identified a potential fault _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:24 _x000D_26/7/2024:22/07/2024 10:24 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_12/7/2024:Openreach Delay : Automated testing has identified a potential fault _x000D_11/7/2024:Openreach Delay : Automated testing has identified a potential fault _x000D_10/7/2024:Openreach Delay : Automated testing has identified a potential fault _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2363582 | 30016217 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
1094 | 656539 | 3808 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Spar | Huntingdon | PE26 1HA |  | 6/9/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_5/9/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_4/9/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_3/9/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_2/9/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_29/8/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_28/8/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_27/8/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_22/8/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_21/8/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_20/8/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_19/8/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_19/8/2024:01478933 _x000D_16/8/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_15/8/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_14/8/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_13/8/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_12/8/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_9/8/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_8/8/2024:10/07/2024 _x000D_6/8/2024:10/07/2024 _x000D_5/8/2024:10/07/2024 _x000D_2/8/2024:10/07/2024 _x000D_1/8/2024:10/07/2024 _x000D_31/7/2024:10/07/2024 _x000D_31/7/2024:10/07/2024 _x000D_30/7/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_29/7/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_29/7/2024:01478933 _x000D_26/7/2024:01478933 _x000D_24/7/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_23/7/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_22/7/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_22/7/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_6/9/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_5/9/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_4/9/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_3/9/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_2/9/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_29/8/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_28/8/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_27/8/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_22/8/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_21/8/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_20/8/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_19/8/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_19/8/2024:01478933 _x000D_16/8/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_15/8/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_14/8/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_13/8/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_12/8/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_9/8/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_8/8/2024:10/07/2024 _x000D_6/8/2024:10/07/2024 _x000D_5/8/2024:10/07/2024 _x000D_2/8/2024:10/07/2024 _x000D_1/8/2024:10/07/2024 _x000D_31/7/2024:10/07/2024 _x000D_31/7/2024:10/07/2024 _x000D_30/7/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_29/7/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_29/7/2024:01478933 _x000D_26/7/2024:01478933 _x000D_24/7/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_23/7/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_22/7/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_22/7/2024:#Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update - Retailer unaware. Reappointed for 29/07 - Action for allwyn - Please confirm new appoint with retailer., | 2024-06-07 |  |  |  |  | VFS1074509 | 30022179 | 1.Provisioning | AM |  | 2024-08-19 | 2024-09-02 |  | 0 | [11 empty] | 0
1095 | 461006 | 3812 | Batch 5 Jul24 | Type 1 | FTTP | AM 2 PM | SLOUGH | SL1 2BE |  | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2363580 | 30016302 | 6.Failed router install |  |  | 2024-07-09 | 2024-07-09 | 2024-07-09 | TRUE |  |  |  | 2024-08-02 |  |  |  | 2024-08-02 | 242005011004 |  | 2024-08-06 | 1
1096 | 479725 | 3819 | Batch 5 Jul24 | Type 1 | SOGEA | Whaplode Convenience | Splading | PE12 6TJ |  | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1012910 | 30016535 | 2.Commissioning |  |  | 2024-07-09 | 2024-07-09 | 2024-07-09 | TRUE |  |  |  | 2024-07-31 | [7 empty] | 0
1097 | 611401 | 3821 | Batch 5 Jul24 | Type 1 | SOGEA | Ink & Candy | Mansfield | NG18 1JY |  | 22/8/2024:#Update - Address reification sent to VF _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 22/8/2024:#Update - Address reification sent to VF _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1012908 | 30016515 | 2.Commissioning |  |  | 2024-07-09 | 2024-07-09 | 2024-07-10 | TRUE |  |  |  | 2024-08-07 | [7 empty] | 0
1098 | 468135 | 3823 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Centra | Belfast | BT2 7HR |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:33 _x000D_26/7/2024:22/07/2024 10:33 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:33 _x000D_26/7/2024:22/07/2024 10:33 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2363575 | 30016282 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
1099 | 264609 | 3825 | Batch 5 Jul24 | Type 1 | FTTP | Express Checkout | PRESTON | PR2 1BU |  | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2363573 | 30016227 | 6.Failed router install |  |  | 2024-07-09 | 2024-07-09 | 2024-07-09 | TRUE |  |  |  | 2024-08-12 |  |  |  | 2024-08-12 | 23A004952833 | 23A004952833 | 2024-08-13 | 1
1100 | 468347 | 3827 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Mini Market | London | SE15 1BA |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:27 _x000D_26/7/2024:22/07/2024 10:27 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:Update: Order Amended _x000D_15/7/2024:Update: Order Amended _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:27 _x000D_26/7/2024:22/07/2024 10:27 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:Update: Order Amended _x000D_15/7/2024:Update: Order Amended _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2363572 | 30016261 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
1101 | 430688 | 3828 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Little Local | LONDON | E8 2HS |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:#Update Retailer happy with new appointment _x000D_21/8/2024:#Update Retailer happy with new appointment _x000D_20/8/2024:#Update Retailer happy with new appointment _x000D_19/8/2024:#Update Retailer happy with new appointment _x000D_19/8/2024:01477701 _x000D_16/8/2024:#Update Retailer happy with new appointment _x000D_15/8/2024:#Update Retailer happy with new appointment _x000D_14/8/2024:#Update Retailer happy with new appointment _x000D_13/8/2024:#Update Retailer happy with new appointment _x000D_12/8/2024:#Update Retailer happy with new appointment _x000D_9/8/2024:#Update Retailer happy with new appointment _x000D_8/8/2024:22/07/2024 _x000D_6/8/2024:22/07/2024 _x000D_5/8/2024:22/07/2024 _x000D_2/8/2024:22/07/2024 _x000D_1/8/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_30/7/2024:#Update Retailer happy with new appointment _x000D_29/7/2024:#Update Retailer happy with new appointment _x000D_29/7/2024:01477701 _x000D_26/7/2024:01477701 _x000D_24/7/2024:#Update Retailer happy with new appointment _x000D_23/7/2024:#Update Retailer happy with new appointment _x000D_22/7/2024:#Update Retailer happy with new appointment _x000D_22/7/2024:0 _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:#Update Retailer happy with new appointment _x000D_21/8/2024:#Update Retailer happy with new appointment _x000D_20/8/2024:#Update Retailer happy with new appointment _x000D_19/8/2024:#Update Retailer happy with new appointment _x000D_19/8/2024:01477701 _x000D_16/8/2024:#Update Retailer happy with new appointment _x000D_15/8/2024:#Update Retailer happy with new appointment _x000D_14/8/2024:#Update Retailer happy with new appointment _x000D_13/8/2024:#Update Retailer happy with new appointment _x000D_12/8/2024:#Update Retailer happy with new appointment _x000D_9/8/2024:#Update Retailer happy with new appointment _x000D_8/8/2024:22/07/2024 _x000D_6/8/2024:22/07/2024 _x000D_5/8/2024:22/07/2024 _x000D_2/8/2024:22/07/2024 _x000D_1/8/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_30/7/2024:#Update Retailer happy with new appointment _x000D_29/7/2024:#Update Retailer happy with new appointment _x000D_29/7/2024:01477701 _x000D_26/7/2024:01477701 _x000D_24/7/2024:#Update Retailer happy with new appointment _x000D_23/7/2024:#Update Retailer happy with new appointment _x000D_22/7/2024:#Update Retailer happy with new appointment _x000D_22/7/2024:0 _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | 0 | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2363574 | 30016202 | 2.Commissioning | AM |  | 2024-07-09 | 2024-08-21 |  | 0 |  |  |  | 2024-09-18 | [7 empty] | 0
1102 | 460586 | 3830 | Batch 5 Jul24 | Type 1 | SOGEA | Costcutter Extra | LOCHGELLY | KY5 8AT |  | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1012905 | 30016539 | 6.Failed router install |  |  | 2024-07-09 | 2024-07-09 | 2024-07-09 | TRUE |  |  |  | 2024-08-01 |  |  |  | 2024-08-01 | 242005008958 |  | 2024-08-02 | 1
1103 | 656708 | 3832 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Budgens | Feltham | TW14 9NJ |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:46 _x000D_26/7/2024:22/07/2024 10:46 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 22/07/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment slot received _x000D_18/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 22/07/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment slot received _x000D_17/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 22/07/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment slot received _x000D_16/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 22/07/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment slot received _x000D_15/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 22/07/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment slot received _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_9/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:46 _x000D_26/7/2024:22/07/2024 10:46 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 22/07/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment slot received _x000D_18/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 22/07/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment slot received _x000D_17/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 22/07/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment slot received _x000D_16/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 22/07/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment slot received _x000D_15/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 22/07/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment slot received _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_9/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2363570 | 30016266 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
1104 | 420650 | 3835 | Batch 5 Jul24 | Type 1 | FTTP | Premier | RYDE | PO33 1EL |  | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2363569 | 30016190 | 2.Commissioning |  |  | 2024-07-09 | 2024-07-09 | 2024-07-09 | TRUE | [11 empty] | 0
1105 | 448421 | 3839 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Deos Shop N Save | TONBRIDGE | TN9 2EA |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:56 _x000D_26/7/2024:22/07/2024 10:56 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:56 _x000D_26/7/2024:22/07/2024 10:56 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2363566 | 30016274 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
1106 | 664575 | 3840 | Batch 5 Jul24 | Type 1 | SOGEA | Parkside Convenience Store | Seaham | SR7 7UQ |  | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1012904 | 30016549 | 2.Commissioning |  |  | 2024-07-09 | 2024-07-09 | 2024-07-09 | TRUE |  |  |  | 2024-07-31 | [7 empty] | 0
1107 | 457909 | 3842 | Batch 5 Jul24 | Type 3 | SoGEA/Mobile | COST CUTTER | LUTON | LU1 3AJ |  | 6/9/2024:#Update - Site type 3 - as req. by allwyn. _x000D_5/9/2024:#Update - Site type 3 - as req. by allwyn. _x000D_4/9/2024:#Update - Site type 3 - as req. by allwyn. _x000D_3/9/2024:#Update - Awaiting feedback from OR about alternative route. _x000D_2/9/2024:#Update - Awaiting feedback from OR about alternative route. _x000D_29/8/2024:#Update - Awaiting feedback from OR about alternative route. _x000D_28/8/2024:#Update - Awaiting feedback from OR about alternative route. _x000D_27/8/2024:#Update - Awaiting feedback from OR about alternative route. _x000D_22/8/2024:#Update - Awaiting feedback from OR about alternative route. _x000D_21/8/2024:#Update - Awaiting feedback from OR about alternative route. _x000D_20/8/2024:#Update - Awaiting feedback from OR about alternative route. _x000D_19/8/2024:#Update - Awaiting feedback from OR about alternative route. _x000D_19/8/2024:01478993 _x000D_16/8/2024:#Update - Awaiting feedback from OR about alternative route. _x000D_15/8/2024:#Update - Awaiting feedback from OR about alternative route. _x000D_14/8/2024:#Update - Awaiting feedback from OR about alternative route. _x000D_13/8/2024:#Update - Awaiting feedback from OR about alternative route. _x000D_12/8/2024:#Update - Awaiting feedback from OR about alternative route. _x000D_9/8/2024:#Update - Awaiting feedback from OR about alternative route. _x000D_8/8/2024:01/08/2024 _x000D_6/8/2024:01/08/2024 _x000D_5/8/2024:01/08/2024 _x000D_2/8/2024:01/08/2024 _x000D_1/8/2024:01/08/2024 _x000D_31/7/2024:30/07/2024 _x000D_31/7/2024:30/07/2024 _x000D_30/7/2024:#Update - Awaiting response from OR regarding alternative Cabling route _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - Site type 3 - as req. by allwyn. _x000D_6/9/2024:#Update - Site type 3 - as req. by allwyn. _x000D_5/9/2024:#Update - Site type 3 - as req. by allwyn. _x000D_4/9/2024:#Update - Site type 3 - as req. by allwyn. _x000D_3/9/2024:#Update - Awaiting feedback from OR about alternative route. _x000D_2/9/2024:#Update - Awaiting feedback from OR about alternative route. _x000D_29/8/2024:#Update - Awaiting feedback from OR about alternative route. _x000D_28/8/2024:#Update - Awaiting feedback from OR about alternative route. _x000D_27/8/2024:#Update - Awaiting feedback from OR about alternative route. _x000D_22/8/2024:#Update - Awaiting feedback from OR about alternative route. _x000D_21/8/2024:#Update - Awaiting feedback from OR about alternative route. _x000D_20/8/2024:#Update - Awaiting feedback from OR about alternative route. _x000D_19/8/2024:#Update - Awaiting feedback from OR about alternative route. _x000D_19/8/2024:01478993 _x000D_16/8/2024:#Update - Awaiting feedback from OR about alternative route. _x000D_15/8/2024:#Update - Awaiting feedback from OR about alternative route. _x000D_14/8/2024:#Update - Awaiting feedback from OR about alternative route. _x000D_13/8/2024:#Update - Awaiting feedback from OR about alternative route. _x000D_12/8/2024:#Update - Awaiting feedback from OR about alternative route. _x000D_9/8/2024:#Update - Awaiting feedback from OR about alternative route. _x000D_8/8/2024:01/08/2024 _x000D_6/8/2024:01/08/2024 _x000D_5/8/2024:01/08/2024 _x000D_2/8/2024:01/08/2024 _x000D_1/8/2024:01/08/2024 _x000D_31/7/2024:30/07/2024 _x000D_31/7/2024:30/07/2024 _x000D_30/7/2024:#Update - Awaiting response from OR regarding alternative Cabling route _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update - Site type 3 - as req. by allwyn. | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1012898 | 30016564 | 2.Commissioning | AM |  | 2024-07-09 | 2024-08-27 |  | 0 |  |  |  | 2024-09-04 | [7 empty] | 0
1108 | 632239 | 3843 | Batch 5 Jul24 | Type 1 | SOGEA | Casterton Convenience Store | STAMFORD | PE9 1BE |  | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1012897 | 30016523 | 2.Commissioning |  |  | 2024-07-09 | 2024-07-09 | 2024-07-09 | TRUE |  |  |  | 2024-08-02 | [7 empty] | 0
1109 | 209939 | 3844 | Batch 5 Jul24 | Type 1 | SOGEA | One Stop | WEST BROMWICH | B71 1AN |  | 19/7/2024:#Update Retailer happy with new appointment, 24/07, AM. _x000D_18/7/2024:#Update Retailer happy with new appointment, 24/07, AM. _x000D_17/7/2024:#Update Retailer happy with new appointment, 24/07, AM. _x000D_16/7/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_15/7/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_12/7/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_11/7/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:#Update Retailer happy with new appointment, 24/07, AM. _x000D_18/7/2024:#Update Retailer happy with new appointment, 24/07, AM. _x000D_17/7/2024:#Update Retailer happy with new appointment, 24/07, AM. _x000D_16/7/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_15/7/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_12/7/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_11/7/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1012895 | 30016484 | 6.Failed router install |  |  | 2024-07-09 | 2024-07-09 | 2024-07-09 | TRUE |  |  |  | 2024-08-12 |  |  |  | 2024-08-12 | 238004926100 | 238004926100 | 2024-08-13 | 1
1110 | 665096 | 3846 | Batch 5 Jul24 | Type 1 | SOGEA | One Stop | Northampton | NN3 8QH |  | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1012892 | 30016532 | 2.Commissioning |  |  | 2024-07-09 | 2024-07-09 | 2024-07-09 | TRUE |  |  |  | 2024-08-05 | [7 empty] | 0
1111 | 634244 | 3848 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | One Stop | Rhyl | LL18 2HB |  | 6/9/2024:#Update Retailer happy with new appointment 28/08, AM. _x000D_5/9/2024:#Update Retailer happy with new appointment 28/08, AM. _x000D_4/9/2024:#Update Retailer happy with new appointment 28/08, AM. _x000D_3/9/2024:#Update Retailer happy with new appointment 28/08, AM. _x000D_2/9/2024:#Update Retailer happy with new appointment 28/08, AM. _x000D_29/8/2024:#Update Retailer happy with new appointment 28/08, AM. _x000D_28/8/2024:#Update Retailer happy with new appointment 28/08, AM. _x000D_27/8/2024:#Update Retailer happy with new appointment 28/08, AM. _x000D_22/8/2024:#Update Retailer happy with new appointment 28/08, AM. _x000D_21/8/2024:#Update Retailer happy with new appointment 28/08, AM. _x000D_20/8/2024:#Update Retailer happy with new appointment 28/08, AM. _x000D_19/8/2024:#Update Retailer happy with new appointment 28/08, AM. _x000D_19/8/2024:01429936 _x000D_16/8/2024:#Update Retailer happy with new appointment 28/08, AM. _x000D_15/8/2024:#Update Retailer happy with new appointment 28/08, AM. _x000D_14/8/2024:#Update Retailer happy with new appointment 28/08, AM. _x000D_13/8/2024:#Update Retailer happy with new appointment 28/08, AM. _x000D_12/8/2024:#Update Retailer happy with new appointment 28/08, AM. _x000D_9/8/2024:#Update Retailer happy with new appointment 28/08, AM. _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update Retailer happy with new appointment 28/08, AM. _x000D_29/7/2024:#Update Retailer happy with new appointment 28/08, AM. _x000D_29/7/2024:01429936 _x000D_26/7/2024:01429936 _x000D_24/7/2024:#Update Retailer happy with new appointment - 11/07,AM _x000D_23/7/2024:#Update Retailer happy with new appointment - 11/07,AM _x000D_22/7/2024:#Update Retailer happy with new appointment - 11/07,AM _x000D_22/7/2024:#Update Retailer happy with new appointment - 11/07,AM _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update Retailer happy with new appointment 28/08, AM. _x000D_6/9/2024:#Update Retailer happy with new appointment 28/08, AM. _x000D_5/9/2024:#Update Retailer happy with new appointment 28/08, AM. _x000D_4/9/2024:#Update Retailer happy with new appointment 28/08, AM. _x000D_3/9/2024:#Update Retailer happy with new appointment 28/08, AM. _x000D_2/9/2024:#Update Retailer happy with new appointment 28/08, AM. _x000D_29/8/2024:#Update Retailer happy with new appointment 28/08, AM. _x000D_28/8/2024:#Update Retailer happy with new appointment 28/08, AM. _x000D_27/8/2024:#Update Retailer happy with new appointment 28/08, AM. _x000D_22/8/2024:#Update Retailer happy with new appointment 28/08, AM. _x000D_21/8/2024:#Update Retailer happy with new appointment 28/08, AM. _x000D_20/8/2024:#Update Retailer happy with new appointment 28/08, AM. _x000D_19/8/2024:#Update Retailer happy with new appointment 28/08, AM. _x000D_19/8/2024:01429936 _x000D_16/8/2024:#Update Retailer happy with new appointment 28/08, AM. _x000D_15/8/2024:#Update Retailer happy with new appointment 28/08, AM. _x000D_14/8/2024:#Update Retailer happy with new appointment 28/08, AM. _x000D_13/8/2024:#Update Retailer happy with new appointment 28/08, AM. _x000D_12/8/2024:#Update Retailer happy with new appointment 28/08, AM. _x000D_9/8/2024:#Update Retailer happy with new appointment 28/08, AM. _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update Retailer happy with new appointment 28/08, AM. _x000D_29/7/2024:#Update Retailer happy with new appointment 28/08, AM. _x000D_29/7/2024:01429936 _x000D_26/7/2024:01429936 _x000D_24/7/2024:#Update Retailer happy with new appointment - 11/07,AM _x000D_23/7/2024:#Update Retailer happy with new appointment - 11/07,AM _x000D_22/7/2024:#Update Retailer happy with new appointment - 11/07,AM _x000D_22/7/2024:#Update Retailer happy with new appointment - 11/07,AM _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update Retailer happy with new appointment 28/08, AM. | 2024-06-07 |  |  |  |  | VFP2430270 | 30016212 | 1.Provisioning | AM |  | 2024-07-09 | 2024-09-06 |  | 0 | [11 empty] | 0
1112 | 467365 | 3850 | Batch 5 Jul24 | Type 1 | SOGEA | One Stop | LIVERPOOL | L12 0NB |  | 22/7/2024:Order Completed _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 22/7/2024:Order Completed _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1012889 | 30016470 | 6.Failed router install |  |  | 2024-07-16 | 2024-07-16 | 2024-07-16 | TRUE |  |  |  | 2024-08-14 |  |  |  | 2024-08-14 | 23A004948666 | 23A004948666 | 2024-08-15 | 1
1113 | 646648 | 3852 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | One Stop | Leicester | LE5 0HL |  | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_15/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_12/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_11/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_10/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_9/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_15/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_12/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_11/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_10/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_9/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | 0 | 2024-06-07 |  |  |  |  | VFP2363562 | 30016375 | 1.Provisioning | AM |  | 2024-07-09 | 2024-09-02 |  | 0 | [11 empty] | 0
1114 | 233246 | 3855 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | One Stop | LEAMINGTON SPA | CV31 3EE |  | 6/9/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_5/9/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_4/9/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_3/9/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_2/9/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_29/8/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_28/8/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_27/8/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_22/8/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_21/8/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_20/8/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_19/8/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_19/8/2024:01480035 _x000D_16/8/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_15/8/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_14/8/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_13/8/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_12/8/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_9/8/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_8/8/2024:10/07/2024 _x000D_6/8/2024:10/07/2024 _x000D_5/8/2024:10/07/2024 _x000D_2/8/2024:10/07/2024 _x000D_1/8/2024:10/07/2024 _x000D_31/7/2024:10/07/2024 _x000D_31/7/2024:10/07/2024 _x000D_30/7/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_29/7/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_29/7/2024:01480035 _x000D_26/7/2024:01480035 _x000D_24/7/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_23/7/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_22/7/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_22/7/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_6/9/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_5/9/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_4/9/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_3/9/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_2/9/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_29/8/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_28/8/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_27/8/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_22/8/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_21/8/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_20/8/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_19/8/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_19/8/2024:01480035 _x000D_16/8/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_15/8/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_14/8/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_13/8/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_12/8/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_9/8/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_8/8/2024:10/07/2024 _x000D_6/8/2024:10/07/2024 _x000D_5/8/2024:10/07/2024 _x000D_2/8/2024:10/07/2024 _x000D_1/8/2024:10/07/2024 _x000D_31/7/2024:10/07/2024 _x000D_31/7/2024:10/07/2024 _x000D_30/7/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_29/7/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_29/7/2024:01480035 _x000D_26/7/2024:01480035 _x000D_24/7/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_23/7/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_22/7/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_22/7/2024:#Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update - Needs a quieter time for internal works to be completed Action for allwyn : Please confirm with the retailer which day and time the engineer can attend. | 2024-06-07 |  |  |  |  | VFS1012885 | 30016469 | 1.Provisioning | AM |  | 2024-07-09 | 2024-09-17 |  | 0 | [11 empty] | 0
1115 | 668422 | 3857 | Batch 5 Jul24 | Type 1 | SOGEA | One Stop | Sutton Coldfield | B72 1YG |  | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Update: Order Completed by Supplier _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Update: Order Completed by Supplier _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1012883 | 30016482 | 6.Failed router install |  |  | 2024-07-09 | 2024-07-09 | 2024-07-09 | TRUE |  |  |  | 2024-08-12 |  |  |  | 2024-08-12 | 238004926102 | 238004926102 | 2024-08-13 | 1
1116 | 618485 | 3858 | Batch 5 Jul24 | Type 1 | SOGEA | One Stop | Liverpool | L3 6LG |  | 19/7/2024:0 _x000D_18/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 29/07/2024.We will continue to provide update as they become available. _x000D_17/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 29/07/2024.We will continue to provide update as they become available. _x000D_16/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 29/07/2024.We will continue to provide update as they become available. _x000D_15/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 29/07/2024.We will continue to provide update as they become available. _x000D_12/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 29/07/2024.We will continue to provide update as they become available. _x000D_11/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 29/07/2024.We will continue to provide update as they become available. _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A4 (ECC) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_17/6/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_14/6/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_13/6/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_12/6/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:0 _x000D_18/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 29/07/2024.We will continue to provide update as they become available. _x000D_17/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 29/07/2024.We will continue to provide update as they become available. _x000D_16/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 29/07/2024.We will continue to provide update as they become available. _x000D_15/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 29/07/2024.We will continue to provide update as they become available. _x000D_12/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 29/07/2024.We will continue to provide update as they become available. _x000D_11/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 29/07/2024.We will continue to provide update as they become available. _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A4 (ECC) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_17/6/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_14/6/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_13/6/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_12/6/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1012882 | 30016431 | 2.Commissioning |  |  | 2024-07-09 | 2024-07-09 | 2024-07-09 | TRUE |  |  |  | 2024-08-13 | [7 empty] | 0
1117 | 632853 | 3859 | Batch 5 Jul24 | Type 1 | SOGEA | One Stop | Denton | M34 3WQ | 2024-07-11 | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Update: Order Completed by Supplier _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Update: Order Completed by Supplier _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1012881 | 30016394 | 2.Commissioning |  |  | 2024-07-10 | 2024-07-10 | 2024-07-10 | TRUE |  |  |  | 2024-08-08 | [7 empty] | 0
1118 | 444355 | 3860 | Batch 5 Jul24 | Type 1 | SOGEA | One Stop | BIRMINGHAM | B45 0JD | 2024-07-11 | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1012880 | 30016478 | 2.Commissioning |  |  | 2024-07-10 | 2024-07-10 | 2024-07-10 | TRUE |  |  |  | 2024-08-08 | [7 empty] | 0
1119 | 639698 | 3861 | Batch 5 Jul24 | Type 1 | FTTP | One Stop Working With Hightown Stor | Wakefield | WF15 8HU | 2024-07-11 | 12/7/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_11/7/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_10/7/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_9/7/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_4/7/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_3/7/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_27/6/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_25/6/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_24/6/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_20/6/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_19/6/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_18/6/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_17/6/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_14/6/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_13/6/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_12/6/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_10/6/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_7/6/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_6/6/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_5/6/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_4/6/2024:#Update- Network records need to be updated. Review 03/06. OR to provide updates as they become available. Will review 03/06 _x000D_ | 12/7/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_11/7/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_10/7/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_9/7/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_4/7/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_3/7/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_27/6/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_25/6/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_24/6/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_20/6/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_19/6/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_18/6/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_17/6/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_14/6/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_13/6/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_12/6/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_10/6/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_7/6/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_6/6/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_5/6/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_4/6/2024:#Update- Network records need to be updated. Review 03/06. OR to provide updates as they become available. Will review 03/06 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFP2363565 | 30016269 | 6.Failed router install |  |  | 2024-07-10 | 2024-07-10 | 2024-07-10 | TRUE |  |  |  | 2024-08-02 |  |  |  | 2024-08-02 | 238004926089 |  | 2024-08-06 | 1
1120 | 661182 | 3862 | Batch 5 Jul24 | Type 1 | SOGEA | One Stop | Guisborough | TS14 6HF | 2024-07-11 | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Update: Order Completed by Supplier _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:Your order has been delayed. Line plant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 14/06/2024.We will continue to provide update as they become available. CSL Note: Invalid appointme _x000D_14/6/2024:Your order has been delayed. Line plant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 14/06/2024.We will continue to provide update as they become available. CSL Note: Invalid appointme _x000D_13/6/2024:Your order has been delayed. Line plant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 14/06/2024.We will continue to provide update as they become available. CSL Note: Invalid appointme _x000D_12/6/2024:Your order has been delayed. Line plant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 14/06/2024.We will continue to provide update as they become available. CSL Note: Invalid appointme _x000D_10/6/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 11/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_7/6/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 11/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/6/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 07/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/6/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 07/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/6/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 07/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Update: Order Completed by Supplier _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:Your order has been delayed. Line plant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 14/06/2024.We will continue to provide update as they become available. CSL Note: Invalid appointme _x000D_14/6/2024:Your order has been delayed. Line plant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 14/06/2024.We will continue to provide update as they become available. CSL Note: Invalid appointme _x000D_13/6/2024:Your order has been delayed. Line plant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 14/06/2024.We will continue to provide update as they become available. CSL Note: Invalid appointme _x000D_12/6/2024:Your order has been delayed. Line plant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 14/06/2024.We will continue to provide update as they become available. CSL Note: Invalid appointme _x000D_10/6/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 11/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_7/6/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 11/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/6/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 07/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/6/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 07/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/6/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 07/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1012879 | 30016418 | 6.Failed router install |  |  | 2024-07-10 | 2024-07-10 | 2024-07-10 | TRUE |  |  |  | 2024-07-31 |  |  |  | 2024-07-31 | 238004926087 |  | 2024-08-01 | 1
1121 | 648282 | 3863 | Batch 5 Jul24 | Type 1 | SOGEA | One Stop | MILFORD HAVEN | SA73 2HA | 2024-07-11 | 19/7/2024:#Update - installation unsuccessful - EU unaware, action with Allwyn to liaise with retailer, rescheduled for 25/07- AM _x000D_18/7/2024:#Update - installation unsuccessful - EU unaware, action with Allwyn to liaise with retailer, rescheduled for 25/07- AM _x000D_17/7/2024:#Update - installation unsuccessful - EU unaware, action with Allwyn to liaise with retailer, rescheduled for 25/07- AM _x000D_16/7/2024:Update: Order Amended _x000D_15/7/2024:Update: Order Amended _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:#Update - installation unsuccessful - EU unaware, action with Allwyn to liaise with retailer, rescheduled for 25/07- AM _x000D_18/7/2024:#Update - installation unsuccessful - EU unaware, action with Allwyn to liaise with retailer, rescheduled for 25/07- AM _x000D_17/7/2024:#Update - installation unsuccessful - EU unaware, action with Allwyn to liaise with retailer, rescheduled for 25/07- AM _x000D_16/7/2024:Update: Order Amended _x000D_15/7/2024:Update: Order Amended _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1012878 | 30016606 | 2.Commissioning |  |  | 2024-07-10 | 2024-07-10 | 2024-07-10 | TRUE |  |  |  | 2024-08-07 | [7 empty] | 0
1122 | 464738 | 3864 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | One Stop Kingsholm | GLOUCESTER | GL1 3AX | 2024-07-11 | 5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:#Update - installation unsuccessful - EU unaware, action with Allwyn to liaise with retailer, rescheduled for 25/07- AM _x000D_9/8/2024:#Update - installation unsuccessful - EU unaware, action with Allwyn to liaise with retailer, rescheduled for 25/07- AM _x000D_8/8/2024:16/07/2024 _x000D_6/8/2024:16/07/2024 _x000D_5/8/2024:16/07/2024 _x000D_2/8/2024:16/07/2024 _x000D_1/8/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_30/7/2024:#Update - installation unsuccessful - EU unaware, action with Allwyn to liaise with retailer, rescheduled for 25/07- AM _x000D_29/7/2024:#Update - installation unsuccessful - EU unaware, action with Allwyn to liaise with retailer, rescheduled for 25/07- AM _x000D_29/7/2024:01481915 _x000D_26/7/2024:01481915 _x000D_24/7/2024:#Update - installation unsuccessful - EU unaware, action with Allwyn to liaise with retailer, rescheduled for 25/07- AM _x000D_23/7/2024:#Update - installation unsuccessful - EU unaware, action with Allwyn to liaise with retailer, rescheduled for 25/07- AM _x000D_22/7/2024:#Update - installation unsuccessful - EU unaware, action with Allwyn to liaise with retailer, rescheduled for 25/07- AM _x000D_22/7/2024:#Update - installation unsuccessful - EU unaware, action with Allwyn to liaise with retailer, rescheduled for 25/07- AM _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:#Update - installation unsuccessful - EU unaware, action with Allwyn to liaise with retailer, rescheduled for 25/07- AM _x000D_9/8/2024:#Update - installation unsuccessful - EU unaware, action with Allwyn to liaise with retailer, rescheduled for 25/07- AM _x000D_8/8/2024:16/07/2024 _x000D_6/8/2024:16/07/2024 _x000D_5/8/2024:16/07/2024 _x000D_2/8/2024:16/07/2024 _x000D_1/8/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_30/7/2024:#Update - installation unsuccessful - EU unaware, action with Allwyn to liaise with retailer, rescheduled for 25/07- AM _x000D_29/7/2024:#Update - installation unsuccessful - EU unaware, action with Allwyn to liaise with retailer, rescheduled for 25/07- AM _x000D_29/7/2024:01481915 _x000D_26/7/2024:01481915 _x000D_24/7/2024:#Update - installation unsuccessful - EU unaware, action with Allwyn to liaise with retailer, rescheduled for 25/07- AM _x000D_23/7/2024:#Update - installation unsuccessful - EU unaware, action with Allwyn to liaise with retailer, rescheduled for 25/07- AM _x000D_22/7/2024:#Update - installation unsuccessful - EU unaware, action with Allwyn to liaise with retailer, rescheduled for 25/07- AM _x000D_22/7/2024:#Update - installation unsuccessful - EU unaware, action with Allwyn to liaise with retailer, rescheduled for 25/07- AM _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1012877 | 30016474 | 3.In life | [9 empty] | 2024-09-04 |  |  |  | 2024-09-04 | 242005010353 | 242005010353 | 2024-09-05 | 1
1123 | 651293 | 3867 | Batch 5 Jul24 | Type 1 | SOGEA | One Stop | Carlisle | CA1 2ES | 2024-07-11 | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1012872 | 30016574 | 2.Commissioning |  |  | 2024-07-10 | 2024-07-10 | 2024-07-10 | TRUE |  |  |  | 2024-07-31 | [7 empty] | 0
1124 | 618765 | 3870 | Batch 5 Jul24 | Type 1 | FTTP | One Stop | Scunthorpe | DN15 8AL | 2024-07-11 | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFP2363559 | 30016325 | 2.Commissioning |  |  | 2024-07-10 | 2024-07-10 | 2024-07-10 | TRUE |  |  |  | 2024-07-31 | [7 empty] | 0
1125 | 645734 | 3871 | Batch 5 Jul24 | Type 1 | FTTP | One Stop Farwells | Wareham | BH20 4AF | 2024-07-11 | 19/7/2024:Update: Order Amended _x000D_18/7/2024:Update: Order Amended _x000D_17/7/2024:Your order has been delayed due to a customer missed appointment as Out of hour appointment is required. Please check with end user and reappoint the order if still required. _x000D_16/7/2024:Your order has been delayed due to a customer missed appointment as Out of hour appointment is required. Please check with end user and reappoint the order if still required. _x000D_15/7/2024:Your order has been delayed due to a customer missed appointment as Out of hour appointment is required. Please check with end user and reappoint the order if still required. _x000D_12/7/2024:Your order has been delayed due to a customer missed appointment as Out of hour appointment is required. Please check with end user and reappoint the order if still required. _x000D_11/7/2024:Your order has been delayed due to a customer missed appointment as Out of hour appointment is required. Please check with end user and reappoint the order if still required. _x000D_10/7/2024:End User Missed appointment. Action required _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:Update: Order Amended _x000D_18/7/2024:Update: Order Amended _x000D_17/7/2024:Your order has been delayed due to a customer missed appointment as Out of hour appointment is required. Please check with end user and reappoint the order if still required. _x000D_16/7/2024:Your order has been delayed due to a customer missed appointment as Out of hour appointment is required. Please check with end user and reappoint the order if still required. _x000D_15/7/2024:Your order has been delayed due to a customer missed appointment as Out of hour appointment is required. Please check with end user and reappoint the order if still required. _x000D_12/7/2024:Your order has been delayed due to a customer missed appointment as Out of hour appointment is required. Please check with end user and reappoint the order if still required. _x000D_11/7/2024:Your order has been delayed due to a customer missed appointment as Out of hour appointment is required. Please check with end user and reappoint the order if still required. _x000D_10/7/2024:End User Missed appointment. Action required _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1012870 | 30016453 | 2.Commissioning |  |  | 2024-07-10 | 2024-07-10 | 2024-07-10 | TRUE |  |  |  | 2024-08-08 | [7 empty] | 0
1126 | 666112 | 3873 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | One Stop Suffield Park Post Office | CROMER | NR27 0AD | 2024-07-11 | 6/9/2024:#Update Upgrade costs sent to VF for approval. _x000D_5/9/2024:#Update Upgrade costs sent to VF for approval. _x000D_4/9/2024:#Update Upgrade costs sent to VF for approval. _x000D_3/9/2024:#Update Upgrade costs sent to VF for approval. _x000D_2/9/2024:#Update Upgrade costs sent to VF for approval. _x000D_29/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_28/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_27/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_22/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_21/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_20/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_19/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_19/8/2024:01481806 _x000D_16/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_15/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_14/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_13/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_12/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_9/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_8/8/2024:24/07/2024 _x000D_6/8/2024:24/07/2024 _x000D_5/8/2024:24/07/2024 _x000D_2/8/2024:24/07/2024 _x000D_1/8/2024:24/07/2024 _x000D_31/7/2024:24/07/2024 _x000D_31/7/2024:24/07/2024 _x000D_30/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_29/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_29/7/2024:01481806 _x000D_26/7/2024:01481806 _x000D_24/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update Upgrade costs sent to VF for approval. _x000D_6/9/2024:#Update Upgrade costs sent to VF for approval. _x000D_5/9/2024:#Update Upgrade costs sent to VF for approval. _x000D_4/9/2024:#Update Upgrade costs sent to VF for approval. _x000D_3/9/2024:#Update Upgrade costs sent to VF for approval. _x000D_2/9/2024:#Update Upgrade costs sent to VF for approval. _x000D_29/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_28/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_27/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_22/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_21/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_20/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_19/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_19/8/2024:01481806 _x000D_16/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_15/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_14/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_13/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_12/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_9/8/2024:#Update Upgrade costs sent to VF for approval. _x000D_8/8/2024:24/07/2024 _x000D_6/8/2024:24/07/2024 _x000D_5/8/2024:24/07/2024 _x000D_2/8/2024:24/07/2024 _x000D_1/8/2024:24/07/2024 _x000D_31/7/2024:24/07/2024 _x000D_31/7/2024:24/07/2024 _x000D_30/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_29/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_29/7/2024:01481806 _x000D_26/7/2024:01481806 _x000D_24/7/2024:#Update Upgrade costs sent to VF for approval. _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update Upgrade costs sent to VF for approval. | 2024-06-07 |  |  |  |  | VFS1012869 | 30016445 | 1.Provisioning | AM |  | 2024-07-10 | 2024-08-30 |  | 0 | [11 empty] | 0
1127 | 231143 | 3874 | Batch 5 Jul24 | Type 1 | SOGEA | One Stop | SHOTTS | ML7 4AB | 2024-07-11 | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1012868 | 30016594 | 2.Commissioning |  |  | 2024-07-10 | 2024-07-10 | 2024-07-10 | TRUE |  |  |  | 2024-08-01 | [7 empty] | 0
1128 | 642065 | 3875 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | One Stop | Prestatyn | LL19 8BA |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:29 _x000D_26/7/2024:22/07/2024 10:29 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:29 _x000D_26/7/2024:22/07/2024 10:29 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2363560 | 30016323 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
1129 | 650674 | 3876 | Batch 5 Jul24 | Type 1 | SOGEA | One Stop | Rugeley | WS15 2DL | 2024-07-11 | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1012867 | 30016569 | 2.Commissioning |  |  | 2024-07-10 | 2024-07-10 | 2024-07-10 | TRUE |  |  |  | 2024-08-12 | [7 empty] | 0
1130 | 616547 | 3882 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | One Stop | Scarborough | YO11 1ET | 2024-07-11 | 6/9/2024:#Update Upgrade costs sent to VF for approval _x000D_5/9/2024:#Update Upgrade costs sent to VF for approval _x000D_4/9/2024:#Update Upgrade costs sent to VF for approval _x000D_3/9/2024:#Update Upgrade costs sent to VF for approval _x000D_2/9/2024:#Update Upgrade costs sent to VF for approval _x000D_29/8/2024:#Update Upgrade costs sent to VF for approval _x000D_28/8/2024:#Update Upgrade costs sent to VF for approval _x000D_27/8/2024:#Update Upgrade costs sent to VF for approval _x000D_22/8/2024:#Update Upgrade costs sent to VF for approval _x000D_21/8/2024:#Update Upgrade costs sent to VF for approval _x000D_20/8/2024:#Update Upgrade costs sent to VF for approval _x000D_19/8/2024:#Update Upgrade costs sent to VF for approval _x000D_19/8/2024:01483010 _x000D_16/8/2024:#Update Upgrade costs sent to VF for approval _x000D_15/8/2024:#Update Upgrade costs sent to VF for approval _x000D_14/8/2024:#Update Upgrade costs sent to VF for approval _x000D_13/8/2024:#Update Upgrade costs sent to VF for approval _x000D_12/8/2024:#Update Upgrade costs sent to VF for approval _x000D_9/8/2024:#Update Upgrade costs sent to VF for approval _x000D_8/8/2024:22/07/2024 _x000D_6/8/2024:22/07/2024 _x000D_5/8/2024:22/07/2024 _x000D_2/8/2024:22/07/2024 _x000D_1/8/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_30/7/2024:#Update Upgrade costs sent to VF for approval _x000D_29/7/2024:#Update Upgrade costs sent to VF for approval _x000D_29/7/2024:01483010 _x000D_26/7/2024:01483010 _x000D_24/7/2024:#Update Upgrade costs sent to VF for approval _x000D_23/7/2024:#Update Upgrade costs sent to VF for approval _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_6/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_5/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_4/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_ | 9/9/2024:#Update Upgrade costs sent to VF for approval _x000D_6/9/2024:#Update Upgrade costs sent to VF for approval _x000D_5/9/2024:#Update Upgrade costs sent to VF for approval _x000D_4/9/2024:#Update Upgrade costs sent to VF for approval _x000D_3/9/2024:#Update Upgrade costs sent to VF for approval _x000D_2/9/2024:#Update Upgrade costs sent to VF for approval _x000D_29/8/2024:#Update Upgrade costs sent to VF for approval _x000D_28/8/2024:#Update Upgrade costs sent to VF for approval _x000D_27/8/2024:#Update Upgrade costs sent to VF for approval _x000D_22/8/2024:#Update Upgrade costs sent to VF for approval _x000D_21/8/2024:#Update Upgrade costs sent to VF for approval _x000D_20/8/2024:#Update Upgrade costs sent to VF for approval _x000D_19/8/2024:#Update Upgrade costs sent to VF for approval _x000D_19/8/2024:01483010 _x000D_16/8/2024:#Update Upgrade costs sent to VF for approval _x000D_15/8/2024:#Update Upgrade costs sent to VF for approval _x000D_14/8/2024:#Update Upgrade costs sent to VF for approval _x000D_13/8/2024:#Update Upgrade costs sent to VF for approval _x000D_12/8/2024:#Update Upgrade costs sent to VF for approval _x000D_9/8/2024:#Update Upgrade costs sent to VF for approval _x000D_8/8/2024:22/07/2024 _x000D_6/8/2024:22/07/2024 _x000D_5/8/2024:22/07/2024 _x000D_2/8/2024:22/07/2024 _x000D_1/8/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_30/7/2024:#Update Upgrade costs sent to VF for approval _x000D_29/7/2024:#Update Upgrade costs sent to VF for approval _x000D_29/7/2024:01483010 _x000D_26/7/2024:01483010 _x000D_24/7/2024:#Update Upgrade costs sent to VF for approval _x000D_23/7/2024:#Update Upgrade costs sent to VF for approval _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_6/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_5/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_4/6/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_ | 0 | #Update Upgrade costs sent to VF for approval | 2024-06-07 |  |  |  |  | VFS1012864 | 30016590 | 1.Provisioning | AM |  | 2024-07-10 | 2024-08-30 |  | 0 | [11 empty] | 0
1131 | 656121 | 3884 | Batch 5 Jul24 | Type 1 | SOGEA | One Stop | Bridlington | YO15 2AL | 2024-07-11 | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1012860 | 30016430 | 2.Commissioning |  |  | 2024-07-10 | 2024-07-10 | 2024-07-10 | TRUE |  |  |  | 2024-07-31 | [7 empty] | 0
1132 | 626061 | 3885 | Batch 5 Jul24 | Type 1 | FTTP | Sellys One Stop | Barry | CF62 6HD | 2024-07-11 | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Update: Order Completed by Supplier _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Update: Order Completed by Supplier _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFP2363557 | 30016321 | 2.Commissioning |  |  | 2024-07-10 | 2024-07-10 | 2024-07-10 | TRUE |  |  |  | 2024-08-02 | [7 empty] | 0
1133 | 413511 | 971 | Batch 3 May24 | Type 1 | SoGEA/Mobile | K P STATIONERS | WALLINGFORD | OX10 0AD | 2024-06-07 | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:Update: Order Amended _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_21/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_20/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_19/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_19/8/2024:16/08/2024 08:19 _x000D_16/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_17/7/2024:#Update order reappointed for 18/06. Shop is being sold, old shop owner did not know about appointment. _x000D_16/7/2024:#Update order reappointed for 18/06. Shop is being sold, old shop owner did not know about appointment. _x000D_15/7/2024:#Update order reappointed for 18/06. Shop is being sold, old shop owner did not know about appointment. _x000D_12/7/2024:#Update order reappointed for 18/06. Shop is being sold, old shop owner did not know about appointment. _x000D_11/7/2024:#Update order reappointed for 18/06. Shop is being sold, old shop owner did not know about appointment. _x000D_10/7/2024:#Update order reappointed for 18/06. Shop is being sold, old shop owner did not know about appointment. _x000D_9/7/2024:#Update order reappointed for 18/06. Shop is being sold, old shop owner did not know about appointment. _x000D_4/7/2024:#Update order reappointed for 18/06. Shop is being sold, old shop owner did not know about appointment. _x000D_3/7/2024:#Update order reappointed for 18/06. Shop is being sold, old shop owner did not know about appointment. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update order reappointed for 18/06. Shop is being sold, old shop owner did not know about appointment. _x000D_27/6/2024:#Update order reappointed for 18/06. Shop is being sold, old shop owner did not know about appointment. _x000D_25/6/2024:#Update order reappointed for 18/06. Shop is being sold, old shop owner did not know about appointment. _x000D_24/6/2024:#Update order reappointed for 18/06. Shop is being sold, old shop owner did not know about appointment. _x000D_20/6/2024:#Update order reappointed for 18/06. Shop is being sold, old shop owner did not know about appointment. _x000D_19/6/2024:#Update order reappointed for 18/06. Shop is being sold, old shop owner did not know about appointment. _x000D_18/6/2024:#Update order reappointed for 18/06. Shop is being sold, old shop owner did not know about appointment. _x000D_17/6/2024:#Update order reappointed for 18/06. Shop is being sold, old shop owner did not know about appointment. _x000D_14/6/2024:#Update order reappointed for 18/06. Shop is being sold, old shop owner did not know about appointment. _x000D_13/6/2024:#Update order reappointed for 18/06. Shop is being sold, old shop owner did not know about appointment. _x000D_12/6/2024:#Update order reappointed for 18/06. Shop is being sold, old shop owner did not know about appointment. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:Update: Order Amended _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_21/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_20/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_19/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_19/8/2024:16/08/2024 08:19 _x000D_16/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_17/7/2024:#Update order reappointed for 18/06. Shop is being sold, old shop owner did not know about appointment. _x000D_16/7/2024:#Update order reappointed for 18/06. Shop is being sold, old shop owner did not know about appointment. _x000D_15/7/2024:#Update order reappointed for 18/06. Shop is being sold, old shop owner did not know about appointment. _x000D_12/7/2024:#Update order reappointed for 18/06. Shop is being sold, old shop owner did not know about appointment. _x000D_11/7/2024:#Update order reappointed for 18/06. Shop is being sold, old shop owner did not know about appointment. _x000D_10/7/2024:#Update order reappointed for 18/06. Shop is being sold, old shop owner did not know about appointment. _x000D_9/7/2024:#Update order reappointed for 18/06. Shop is being sold, old shop owner did not know about appointment. _x000D_4/7/2024:#Update order reappointed for 18/06. Shop is being sold, old shop owner did not know about appointment. _x000D_3/7/2024:#Update order reappointed for 18/06. Shop is being sold, old shop owner did not know about appointment. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update order reappointed for 18/06. Shop is being sold, old shop owner did not know about appointment. _x000D_27/6/2024:#Update order reappointed for 18/06. Shop is being sold, old shop owner did not know about appointment. _x000D_25/6/2024:#Update order reappointed for 18/06. Shop is being sold, old shop owner did not know about appointment. _x000D_24/6/2024:#Update order reappointed for 18/06. Shop is being sold, old shop owner did not know about appointment. _x000D_20/6/2024:#Update order reappointed for 18/06. Shop is being sold, old shop owner did not know about appointment. _x000D_19/6/2024:#Update order reappointed for 18/06. Shop is being sold, old shop owner did not know about appointment. _x000D_18/6/2024:#Update order reappointed for 18/06. Shop is being sold, old shop owner did not know about appointment. _x000D_17/6/2024:#Update order reappointed for 18/06. Shop is being sold, old shop owner did not know about appointment. _x000D_14/6/2024:#Update order reappointed for 18/06. Shop is being sold, old shop owner did not know about appointment. _x000D_13/6/2024:#Update order reappointed for 18/06. Shop is being sold, old shop owner did not know about appointment. _x000D_12/6/2024:#Update order reappointed for 18/06. Shop is being sold, old shop owner did not know about appointment. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFS975422 | 30013861 | 1.Provisioning | AM |  | 2024-05-20 | 2024-08-16 |  | 0 | [11 empty] | 0 |  | 670878
1134 | 659735 | 3695 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Premier Makenzies Convenience Stor | Elgin | IV30 4AH | 2024-07-23 | 6/9/2024:#Update - NFA - Allwyn confirmed date and pre-install prep required by retailer for 04/09 AM _x000D_5/9/2024:#Update - NFA - Allwyn confirmed date and pre-install prep required by retailer for 04/09 AM _x000D_4/9/2024:#Update - NFA - Allwyn confirmed date and pre-install prep required by retailer for 04/09 AM _x000D_3/9/2024:#Update - NFA - Allwyn confirmed date and pre-install prep required by retailer for 04/09 AM _x000D_2/9/2024:#Update - NFA - Allwyn confirmed date and pre-install prep required by retailer for 04/09 AM _x000D_29/8/2024:#Update - NFA - Allwyn confirmed date and pre-install prep required by retailer for 04/09 AM _x000D_28/8/2024:#Update - NFA - Allwyn confirmed date and pre-install prep required by retailer for 04/09 AM _x000D_27/8/2024:#Update - NFA - Allwyn confirmed date and pre-install prep required by retailer for 04/09 AM _x000D_22/8/2024:#Update - NFA - Allwyn confirmed date and pre-install prep required by retailer for 04/09 AM _x000D_21/8/2024:#Update - NFA - Allwyn confirmed date and pre-install prep required by retailer for 04/09 AM _x000D_20/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer 16/08 _x000D_19/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer 16/08 _x000D_19/8/2024:01429921 _x000D_16/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer 16/08 _x000D_15/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer 16/08 _x000D_14/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer 16/08 _x000D_13/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer 16/08 _x000D_12/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer 16/08 _x000D_9/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer 16/08 _x000D_8/8/2024:02/08/2024 _x000D_6/8/2024:02/08/2024 _x000D_5/8/2024:02/08/2024 _x000D_2/8/2024:02/08/2024 _x000D_1/8/2024:Update: Order Amended _x000D_31/7/2024:Update: Order Amended _x000D_31/7/2024:37602 _x000D_30/7/2024:Update: Order Amended _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:26/07/2024 13:55 _x000D_26/7/2024:25/07/2024 11:08 _x000D_24/7/2024:Your order has been delayed by our Suppliers due to Assistance being required to complete the installation. Our suppliers team will contact you to get the available date for installation. We will provide the further updates on 26/07/2024. _x000D_23/7/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_22/7/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:Update: Order Amended _x000D_17/7/2024:Update: Order Amended _x000D_16/7/2024:Your order has been delayed. Civil work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 17/07/2024. We will continue to provide update as they become available. _x000D_15/7/2024:Your order has been delayed. Civil work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 17/07/2024. We will continue to provide update as they become available. _x000D_12/7/2024:Your order has been delayed. Civil work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 17/07/2024. We will continue to provide update as they become available. _x000D_11/7/2024:Your order has been delayed. Civil work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 17/07/2024. We will continue to provide update as they become available. _x000D_10/7/2024:Your order has been delayed. Civil work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 17/07/2024. We will continue to provide update as they become available. _x000D_9/7/2024:Your order has been delayed. Civil work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 17/07/2024. We will continue to provide update as they become available. _x000D_4/7/2024:Your order has been delayed. Civil work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 11/07/2024. We will continue to provide update as they become available. _x000D_3/7/2024:Your order has been delayed. Civil work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 11/07/2024. We will continue to provide update as they become available. _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a estimate completion date of 10/07/2024 and given us a review date of 12/07/2024. We will continue to provide update as they become available. _x000D_18/6/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a estimate completion date of 10/07/2024 and given us a review date of 12/07/2024. We will continue to provide update as they become available. _x000D_17/6/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a estimate completion date of 10/07/2024 and given us a review date of 12/07/2024. We will continue to provide update as they become available. _x000D_14/6/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a estimate completion date of 10/07/2024 and given us a review date of 12/07/2024. We will continue to provide update as they become available. _x000D_13/6/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a estimate completion date of 10/07/2024 and given us a review date of 12/07/2024. We will continue to provide update as they become available. _x000D_12/6/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a estimate completion date of 10/07/2024 and given us a review date of 12/07/2024. We will continue to provide update as they become available. _x000D_10/6/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 12/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_7/6/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 12/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/6/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 12/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/6/2024:Supplier Delay: Issues with provision of the underground network, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 06/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 9/9/2024:#Update - NFA - Allwyn confirmed date and pre-install prep required by retailer for 04/09 AM _x000D_6/9/2024:#Update - NFA - Allwyn confirmed date and pre-install prep required by retailer for 04/09 AM _x000D_5/9/2024:#Update - NFA - Allwyn confirmed date and pre-install prep required by retailer for 04/09 AM _x000D_4/9/2024:#Update - NFA - Allwyn confirmed date and pre-install prep required by retailer for 04/09 AM _x000D_3/9/2024:#Update - NFA - Allwyn confirmed date and pre-install prep required by retailer for 04/09 AM _x000D_2/9/2024:#Update - NFA - Allwyn confirmed date and pre-install prep required by retailer for 04/09 AM _x000D_29/8/2024:#Update - NFA - Allwyn confirmed date and pre-install prep required by retailer for 04/09 AM _x000D_28/8/2024:#Update - NFA - Allwyn confirmed date and pre-install prep required by retailer for 04/09 AM _x000D_27/8/2024:#Update - NFA - Allwyn confirmed date and pre-install prep required by retailer for 04/09 AM _x000D_22/8/2024:#Update - NFA - Allwyn confirmed date and pre-install prep required by retailer for 04/09 AM _x000D_21/8/2024:#Update - NFA - Allwyn confirmed date and pre-install prep required by retailer for 04/09 AM _x000D_20/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer 16/08 _x000D_19/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer 16/08 _x000D_19/8/2024:01429921 _x000D_16/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer 16/08 _x000D_15/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer 16/08 _x000D_14/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer 16/08 _x000D_13/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer 16/08 _x000D_12/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer 16/08 _x000D_9/8/2024:#Update - NFA - Allwyn confirmed new installation date with retailer 16/08 _x000D_8/8/2024:02/08/2024 _x000D_6/8/2024:02/08/2024 _x000D_5/8/2024:02/08/2024 _x000D_2/8/2024:02/08/2024 _x000D_1/8/2024:Update: Order Amended _x000D_31/7/2024:Update: Order Amended _x000D_31/7/2024:37602 _x000D_30/7/2024:Update: Order Amended _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:26/07/2024 13:55 _x000D_26/7/2024:25/07/2024 11:08 _x000D_24/7/2024:Your order has been delayed by our Suppliers due to Assistance being required to complete the installation. Our suppliers team will contact you to get the available date for installation. We will provide the further updates on 26/07/2024. _x000D_23/7/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_22/7/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:Update: Order Amended _x000D_17/7/2024:Update: Order Amended _x000D_16/7/2024:Your order has been delayed. Civil work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 17/07/2024. We will continue to provide update as they become available. _x000D_15/7/2024:Your order has been delayed. Civil work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 17/07/2024. We will continue to provide update as they become available. _x000D_12/7/2024:Your order has been delayed. Civil work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 17/07/2024. We will continue to provide update as they become available. _x000D_11/7/2024:Your order has been delayed. Civil work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 17/07/2024. We will continue to provide update as they become available. _x000D_10/7/2024:Your order has been delayed. Civil work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 17/07/2024. We will continue to provide update as they become available. _x000D_9/7/2024:Your order has been delayed. Civil work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 17/07/2024. We will continue to provide update as they become available. _x000D_4/7/2024:Your order has been delayed. Civil work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 11/07/2024. We will continue to provide update as they become available. _x000D_3/7/2024:Your order has been delayed. Civil work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 11/07/2024. We will continue to provide update as they become available. _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a estimate completion date of 10/07/2024 and given us a review date of 12/07/2024. We will continue to provide update as they become available. _x000D_18/6/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a estimate completion date of 10/07/2024 and given us a review date of 12/07/2024. We will continue to provide update as they become available. _x000D_17/6/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a estimate completion date of 10/07/2024 and given us a review date of 12/07/2024. We will continue to provide update as they become available. _x000D_14/6/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a estimate completion date of 10/07/2024 and given us a review date of 12/07/2024. We will continue to provide update as they become available. _x000D_13/6/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a estimate completion date of 10/07/2024 and given us a review date of 12/07/2024. We will continue to provide update as they become available. _x000D_12/6/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a estimate completion date of 10/07/2024 and given us a review date of 12/07/2024. We will continue to provide update as they become available. _x000D_10/6/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 12/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_7/6/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 12/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/6/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 12/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/6/2024:Supplier Delay: Issues with provision of the underground network, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 06/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | Update: Order Amended | #Update - NFA - Allwyn confirmed date and pre-install prep required by retailer for 04/09 AM | 2024-06-07 |  |  |  |  | VFP2393014 | 30016345 | 1.Provisioning | AM |  | 2024-07-22 | 2024-08-16 |  | 0 | [11 empty] | 0
1135 | 471691 | 3322 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Vishal Newsagents | London | SE15 2LB |  | 6/9/2024:#Update - Dig work required. Our Suppliers have given us a review date of 19/09/2024. _x000D_5/9/2024:#Update - delayed due to wayleave required and our suppliers have given us a review date of 21/08/2024. We will continue to provide update as they become available. _x000D_4/9/2024:#Update - delayed due to wayleave required and our suppliers have given us a review date of 21/08/2024. We will continue to provide update as they become available. _x000D_3/9/2024:#Update - delayed due to wayleave required and our suppliers have given us a review date of 21/08/2024. We will continue to provide update as they become available. _x000D_2/9/2024:#Update - delayed due to wayleave required and our suppliers have given us a review date of 21/08/2024. We will continue to provide update as they become available. _x000D_29/8/2024:#Update - delayed due to wayleave required and our suppliers have given us a review date of 21/08/2024. We will continue to provide update as they become available. _x000D_28/8/2024:#Update - delayed due to wayleave required and our suppliers have given us a review date of 21/08/2024. We will continue to provide update as they become available. _x000D_27/8/2024:#Update - delayed due to wayleave required and our suppliers have given us a review date of 21/08/2024. We will continue to provide update as they become available. _x000D_22/8/2024:#Update - delayed due to wayleave required and our suppliers have given us a review date of 21/08/2024. We will continue to provide update as they become available. _x000D_21/8/2024:#Update - delayed due to wayleave required and our suppliers have given us a review date of 21/08/2024. We will continue to provide update as they become available. _x000D_20/8/2024:#Update - delayed due to wayleave required and our suppliers have given us a review date of 21/08/2024. We will continue to provide update as they become available. _x000D_19/8/2024:#Update - delayed due to wayleave required and our suppliers have given us a review date of 21/08/2024. We will continue to provide update as they become available. _x000D_19/8/2024:01509111 _x000D_16/8/2024:#Update - PTW Applied to the local authority. This may take some time to be granted. On Hold. _x000D_15/8/2024:#Update - PTW Applied to the local authority. This may take some time to be granted. On Hold. _x000D_14/8/2024:#Update - PTW Applied to the local authority. This may take some time to be granted. On Hold. _x000D_13/8/2024:#Update - PTW Applied to the local authority. This may take some time to be granted. On Hold. _x000D_12/8/2024:#Update - PTW Applied to the local authority. This may take some time to be granted. On Hold. _x000D_9/8/2024:#Update - PTW Applied to the local authority. This may take some time to be granted. On Hold. _x000D_8/8/2024:23/07/2024 _x000D_6/8/2024:23/07/2024 _x000D_5/8/2024:23/07/2024 _x000D_2/8/2024:23/07/2024 _x000D_1/8/2024:23/07/2024 _x000D_31/7/2024:23/07/2024 _x000D_31/7/2024:23/07/2024 _x000D_30/7/2024:#Update - PTW Applied to the local authority. This may take some time to be granted. On Hold. _x000D_29/7/2024:#Update - PTW Applied to the local authority. This may take some time to be granted. On Hold. _x000D_29/7/2024:01509111 _x000D_26/7/2024:01509111 _x000D_24/7/2024:#Update - PTW Applied to the local authority. This may take some time to be granted. On Hold. _x000D_23/7/2024:#Update - permit required. Awaiting response from Allwyn to see if this has been signed _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_18/7/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_17/7/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_16/7/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_15/7/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_12/7/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_11/7/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_10/7/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_9/7/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_4/7/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_3/7/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_27/6/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_25/6/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_24/6/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_20/6/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_19/6/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_18/6/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_17/6/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_14/6/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_13/6/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_12/6/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_10/6/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 11/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_7/6/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 11/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/6/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 11/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/6/2024:Supplier Delay: Issues with provision of the underground network, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/6/2024:Supplier Delay: Issues with provision of the underground network, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 9/9/2024:#Update - Dig work required. Our Suppliers have given us a review date of 19/09/2024. _x000D_6/9/2024:#Update - Dig work required. Our Suppliers have given us a review date of 19/09/2024. _x000D_5/9/2024:#Update - delayed due to wayleave required and our suppliers have given us a review date of 21/08/2024. We will continue to provide update as they become available. _x000D_4/9/2024:#Update - delayed due to wayleave required and our suppliers have given us a review date of 21/08/2024. We will continue to provide update as they become available. _x000D_3/9/2024:#Update - delayed due to wayleave required and our suppliers have given us a review date of 21/08/2024. We will continue to provide update as they become available. _x000D_2/9/2024:#Update - delayed due to wayleave required and our suppliers have given us a review date of 21/08/2024. We will continue to provide update as they become available. _x000D_29/8/2024:#Update - delayed due to wayleave required and our suppliers have given us a review date of 21/08/2024. We will continue to provide update as they become available. _x000D_28/8/2024:#Update - delayed due to wayleave required and our suppliers have given us a review date of 21/08/2024. We will continue to provide update as they become available. _x000D_27/8/2024:#Update - delayed due to wayleave required and our suppliers have given us a review date of 21/08/2024. We will continue to provide update as they become available. _x000D_22/8/2024:#Update - delayed due to wayleave required and our suppliers have given us a review date of 21/08/2024. We will continue to provide update as they become available. _x000D_21/8/2024:#Update - delayed due to wayleave required and our suppliers have given us a review date of 21/08/2024. We will continue to provide update as they become available. _x000D_20/8/2024:#Update - delayed due to wayleave required and our suppliers have given us a review date of 21/08/2024. We will continue to provide update as they become available. _x000D_19/8/2024:#Update - delayed due to wayleave required and our suppliers have given us a review date of 21/08/2024. We will continue to provide update as they become available. _x000D_19/8/2024:01509111 _x000D_16/8/2024:#Update - PTW Applied to the local authority. This may take some time to be granted. On Hold. _x000D_15/8/2024:#Update - PTW Applied to the local authority. This may take some time to be granted. On Hold. _x000D_14/8/2024:#Update - PTW Applied to the local authority. This may take some time to be granted. On Hold. _x000D_13/8/2024:#Update - PTW Applied to the local authority. This may take some time to be granted. On Hold. _x000D_12/8/2024:#Update - PTW Applied to the local authority. This may take some time to be granted. On Hold. _x000D_9/8/2024:#Update - PTW Applied to the local authority. This may take some time to be granted. On Hold. _x000D_8/8/2024:23/07/2024 _x000D_6/8/2024:23/07/2024 _x000D_5/8/2024:23/07/2024 _x000D_2/8/2024:23/07/2024 _x000D_1/8/2024:23/07/2024 _x000D_31/7/2024:23/07/2024 _x000D_31/7/2024:23/07/2024 _x000D_30/7/2024:#Update - PTW Applied to the local authority. This may take some time to be granted. On Hold. _x000D_29/7/2024:#Update - PTW Applied to the local authority. This may take some time to be granted. On Hold. _x000D_29/7/2024:01509111 _x000D_26/7/2024:01509111 _x000D_24/7/2024:#Update - PTW Applied to the local authority. This may take some time to be granted. On Hold. _x000D_23/7/2024:#Update - permit required. Awaiting response from Allwyn to see if this has been signed _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_18/7/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_17/7/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_16/7/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_15/7/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_12/7/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_11/7/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_10/7/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_9/7/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_4/7/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_3/7/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_27/6/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_25/6/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_24/6/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_20/6/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_19/6/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_18/6/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_17/6/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_14/6/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_13/6/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_12/6/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_10/6/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 11/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_7/6/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 11/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/6/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 11/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/6/2024:Supplier Delay: Issues with provision of the underground network, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/6/2024:Supplier Delay: Issues with provision of the underground network, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 19/09/2024. We will continue to provide update as they become available. | #Update - Dig work required. Our Suppliers have given us a review date of 19/09/2024. | 2024-06-07 |  |  |  |  | VFP2366081 | 30016615 | 1.Provisioning | AM |  | 2024-07-23 | 2024-08-27 |  | 0 | [11 empty] | 0
1136 | 630185 | 3129 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | N P News | Manchester | M30 0EA |  | 6/9/2024:#Update - Order has been delayed as dig work is required which is awaiting permission from a third party. CSL will update as more information become available. _x000D_5/9/2024:#Update - Order has been delayed as dig work is required which is awaiting permission from a third party. CSL will update as more information become available. _x000D_4/9/2024:#Update - Order has been delayed as dig work is required which is awaiting permission from a third party. CSL will update as more information become available. _x000D_3/9/2024:#Update - Order has been delayed as dig work is required which is awaiting permission from a third party. CSL will update as more information become available. _x000D_2/9/2024:#Update - Order has been delayed as dig work is required which is awaiting permission from a third party. CSL will update as more information become available. _x000D_29/8/2024:#Update - Order has been delayed as dig work is required which is awaiting permission from a third party. CSL will update as more information become available. _x000D_28/8/2024:#Update - Order has been delayed as dig work is required which is awaiting permission from a third party. CSL will update as more information become available. _x000D_27/8/2024:#Update - Order has been delayed as dig work is required which is awaiting permission from a third party. CSL will update as more information become available. _x000D_22/8/2024:#Update - Order has been delayed as dig work is required which is awaiting permission from a third party. CSL will update as more information become available. _x000D_21/8/2024:#Update - Order has been delayed as dig work is required which is awaiting permission from a third party. CSL will update as more information become available. _x000D_20/8/2024:#Update - Order has been delayed as dig work is required which is awaiting permission from a third party. CSL will update as more information become available. _x000D_19/8/2024:#Update - Order has been delayed as dig work is required which is awaiting permission from a third party. CSL will update as more information become available. _x000D_19/8/2024:01437715 _x000D_16/8/2024:#Update - Order has been delayed as dig work is required which is awaiting permission from a third party. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order has been delayed as dig work is required which is awaiting permission from a third party. CSL will update as more information become available. _x000D_14/8/2024:#Update - Order has been delayed as dig work is required which is awaiting permission from a third party. CSL will update as more information become available. _x000D_13/8/2024:#Update - Order has been delayed as dig work is required which is awaiting permission from a third party. CSL will update as more information become available. _x000D_12/8/2024:#Update - Order has been delayed as dig work is required which is awaiting permission from a third party. CSL will update as more information become available. _x000D_9/8/2024:#Update - Order has been delayed as dig work is required which is awaiting permission from a third party. CSL will update as more information become available. _x000D_8/8/2024:05/08/2024 _x000D_6/8/2024:05/08/2024 _x000D_5/8/2024:05/08/2024 _x000D_2/8/2024:31/07/2024 _x000D_1/8/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_30/7/2024:#Update - On Hold - Premises might be being demolished? -JW Chased Alwyn on this - No response from retailer. _x000D_29/7/2024:#Update - On Hold - Premises might be being demolished? -JW Chased Alwyn on this - No response from retailer. _x000D_29/7/2024:01437715 _x000D_26/7/2024:01437715 _x000D_24/7/2024:#Update - On Hold - Premises might be being demolished? -JW Chased Alwyn on this - No response from retailer. _x000D_23/7/2024:#Update - On Hold - Premises might be being demolished? -JW Chased Alwyn on this - No response from retailer. _x000D_22/7/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_22/7/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_19/7/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_18/7/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_17/7/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_16/7/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_15/7/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_12/7/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_11/7/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_10/7/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_9/7/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_4/7/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_3/7/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_27/6/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_25/6/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_24/6/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_20/6/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_19/6/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_18/6/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_17/6/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_14/6/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_13/6/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_12/6/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 9/9/2024:#Update - Order has been delayed as dig work is required which is awaiting permission from a third party. CSL will update as more information become available. _x000D_6/9/2024:#Update - Order has been delayed as dig work is required which is awaiting permission from a third party. CSL will update as more information become available. _x000D_5/9/2024:#Update - Order has been delayed as dig work is required which is awaiting permission from a third party. CSL will update as more information become available. _x000D_4/9/2024:#Update - Order has been delayed as dig work is required which is awaiting permission from a third party. CSL will update as more information become available. _x000D_3/9/2024:#Update - Order has been delayed as dig work is required which is awaiting permission from a third party. CSL will update as more information become available. _x000D_2/9/2024:#Update - Order has been delayed as dig work is required which is awaiting permission from a third party. CSL will update as more information become available. _x000D_29/8/2024:#Update - Order has been delayed as dig work is required which is awaiting permission from a third party. CSL will update as more information become available. _x000D_28/8/2024:#Update - Order has been delayed as dig work is required which is awaiting permission from a third party. CSL will update as more information become available. _x000D_27/8/2024:#Update - Order has been delayed as dig work is required which is awaiting permission from a third party. CSL will update as more information become available. _x000D_22/8/2024:#Update - Order has been delayed as dig work is required which is awaiting permission from a third party. CSL will update as more information become available. _x000D_21/8/2024:#Update - Order has been delayed as dig work is required which is awaiting permission from a third party. CSL will update as more information become available. _x000D_20/8/2024:#Update - Order has been delayed as dig work is required which is awaiting permission from a third party. CSL will update as more information become available. _x000D_19/8/2024:#Update - Order has been delayed as dig work is required which is awaiting permission from a third party. CSL will update as more information become available. _x000D_19/8/2024:01437715 _x000D_16/8/2024:#Update - Order has been delayed as dig work is required which is awaiting permission from a third party. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order has been delayed as dig work is required which is awaiting permission from a third party. CSL will update as more information become available. _x000D_14/8/2024:#Update - Order has been delayed as dig work is required which is awaiting permission from a third party. CSL will update as more information become available. _x000D_13/8/2024:#Update - Order has been delayed as dig work is required which is awaiting permission from a third party. CSL will update as more information become available. _x000D_12/8/2024:#Update - Order has been delayed as dig work is required which is awaiting permission from a third party. CSL will update as more information become available. _x000D_9/8/2024:#Update - Order has been delayed as dig work is required which is awaiting permission from a third party. CSL will update as more information become available. _x000D_8/8/2024:05/08/2024 _x000D_6/8/2024:05/08/2024 _x000D_5/8/2024:05/08/2024 _x000D_2/8/2024:31/07/2024 _x000D_1/8/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_30/7/2024:#Update - On Hold - Premises might be being demolished? -JW Chased Alwyn on this - No response from retailer. _x000D_29/7/2024:#Update - On Hold - Premises might be being demolished? -JW Chased Alwyn on this - No response from retailer. _x000D_29/7/2024:01437715 _x000D_26/7/2024:01437715 _x000D_24/7/2024:#Update - On Hold - Premises might be being demolished? -JW Chased Alwyn on this - No response from retailer. _x000D_23/7/2024:#Update - On Hold - Premises might be being demolished? -JW Chased Alwyn on this - No response from retailer. _x000D_22/7/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_22/7/2024:#Update - Order has been delayed due to dig work required. CSL will update as more information become available. _x000D_19/7/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_18/7/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_17/7/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_16/7/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_15/7/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_12/7/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_11/7/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_10/7/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_9/7/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_4/7/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_3/7/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_27/6/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_25/6/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_24/6/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_20/6/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_19/6/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_18/6/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_17/6/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_14/6/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_13/6/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_12/6/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | Your order has been delayed with civils team to obtain the permission from a third party user. Now there is no response from propertiate to continue the work for service delivery. So please inform end user and re-appoint once permission received. | #Update - Order has been delayed as dig work is required which is awaiting permission from a third party. CSL will update as more information become available. | 2024-06-07 |  |  |  |  | VFP2366119 | 30016623 | 1.Provisioning | AM |  | 2024-07-29 | 2024-07-29 |  | 0 | [11 empty] | 0
1137 | 645074 | 555 | Batch 3 May24 | Type 1 | SoGEA/Mobile | The Strand | Rochdale | OL11 2JG | 2024-08-07 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:#Update - missed appointment - Openreach engineer notes state that no one was aware of the install therefore he was denied access. _x000D_22/8/2024:#Update - missed appointment - Openreach engineer notes state that no one was aware of the install therefore he was denied access. _x000D_21/8/2024:#Update - missed appointment - Openreach engineer notes state that no one was aware of the install therefore he was denied access. _x000D_20/8/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_19/8/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_19/8/2024:01345233 _x000D_16/8/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_15/8/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_14/8/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_13/8/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_12/8/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_9/8/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_8/8/2024:23/05/2024 _x000D_6/8/2024:23/05/2024 _x000D_5/8/2024:23/05/2024 _x000D_2/8/2024:23/05/2024 _x000D_1/8/2024:23/05/2024 _x000D_31/7/2024:23/05/2024 _x000D_31/7/2024:23/05/2024 _x000D_30/7/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_29/7/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_29/7/2024:01345233 _x000D_26/7/2024:01345233 _x000D_24/7/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_23/7/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_22/7/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_22/7/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_19/7/2024:#Update - NFA - Allwyn to confirm with retailer for 09/08, after the shop renovations have been completed, the install can go ahead. _x000D_18/7/2024:#Update - NFA - Allwyn to confirm with retailer for 09/08, after the shop renovations have been completed, the install can go ahead. _x000D_17/7/2024:#Update - NFA - Allwyn to confirm with retailer for 09/08, after the shop renovations have been completed, the install can go ahead. _x000D_16/7/2024:#Update - NFA - Allwyn to confirm with retailer for 09/08, after the shop renovations have been completed, the install can go ahead. _x000D_15/7/2024:#Update - NFA - Allwyn to confirm with retailer for 09/08, after the shop renovations have been completed, the install can go ahead. _x000D_12/7/2024:#Update - NFA - Allwyn to confirm with retailer for 09/08, after the shop renovations have been completed, the install can go ahead. _x000D_11/7/2024:#Update - NFA - Allwyn to confirm with retailer for 09/08, after the shop renovations have been completed, the install can go ahead. _x000D_10/7/2024:#Update - NFA - Allwyn to confirm with retailer for 09/08, after the shop renovations have been completed, the install can go ahead. _x000D_9/7/2024:#Update - NFA - Allwyn to confirm with retailer for 09/08, after the shop renovations have been completed, the install can go ahead. _x000D_4/7/2024:#Update - NFA - Allwyn to confirm with retailer for 09/08, after the shop renovations have been completed, the install can go ahead. _x000D_3/7/2024:#Update - NFA - Allwyn to confirm with retailer for 09/08, after the shop renovations have been completed, the install can go ahead. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - NFA - Allwyn to confirm with retailer for 09/08, after the shop renovations have been completed, the install can go ahead. _x000D_27/6/2024:#Update - NFA - Allwyn to confirm with retailer for 09/08, after the shop renovations have been completed, the install can go ahead. _x000D_25/6/2024:#Update - NFA - Allwyn to confirm with retailer for 09/08, after the shop renovations have been completed, the install can go ahead. _x000D_24/6/2024:#Update - NFA - Allwyn to confirm with retailer for 09/08, after the shop renovations have been completed, the install can go ahead. _x000D_20/6/2024:#Update - NFA - Allwyn to confirm with retailer for 09/08, after the shop renovations have been completed, the install can go ahead. _x000D_19/6/2024:#Update - NFA - Allwyn to confirm with retailer for 09/08, after the shop renovations have been completed, the install can go ahead. _x000D_18/6/2024:#Update - NFA - Allwyn to confirm with retailer for 09/08, after the shop renovations have been completed, the install can go ahead. _x000D_17/6/2024:#Update - NFA - Allwyn to confirm with retailer for 09/08, after the shop renovations have been completed, the install can go ahead. _x000D_14/6/2024:#Update - NFA - Allwyn to confirm with retailer for 09/08, after the shop renovations have been completed, the install can go ahead. _x000D_13/6/2024:#Update - NFA - Allwyn to confirm with retailer for 09/08, after the shop renovations have been completed, the install can go ahead. _x000D_12/6/2024:#Update - NFA - Allwyn to confirm with retailer for 09/08, after the shop renovations have been completed, the install can go ahead. _x000D_11/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_7/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 06/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:#Update - missed appointment - Openreach engineer notes state that no one was aware of the install therefore he was denied access. _x000D_22/8/2024:#Update - missed appointment - Openreach engineer notes state that no one was aware of the install therefore he was denied access. _x000D_21/8/2024:#Update - missed appointment - Openreach engineer notes state that no one was aware of the install therefore he was denied access. _x000D_20/8/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_19/8/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_19/8/2024:01345233 _x000D_16/8/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_15/8/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_14/8/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_13/8/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_12/8/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_9/8/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_8/8/2024:23/05/2024 _x000D_6/8/2024:23/05/2024 _x000D_5/8/2024:23/05/2024 _x000D_2/8/2024:23/05/2024 _x000D_1/8/2024:23/05/2024 _x000D_31/7/2024:23/05/2024 _x000D_31/7/2024:23/05/2024 _x000D_30/7/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_29/7/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_29/7/2024:01345233 _x000D_26/7/2024:01345233 _x000D_24/7/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_23/7/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_22/7/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_22/7/2024:#Update - missed appointment - site closed and looks like it's being renovated/refurb Action on Allwyn to liaise with retailer to understand when the shop will be open and install can be reappointed _x000D_19/7/2024:#Update - NFA - Allwyn to confirm with retailer for 09/08, after the shop renovations have been completed, the install can go ahead. _x000D_18/7/2024:#Update - NFA - Allwyn to confirm with retailer for 09/08, after the shop renovations have been completed, the install can go ahead. _x000D_17/7/2024:#Update - NFA - Allwyn to confirm with retailer for 09/08, after the shop renovations have been completed, the install can go ahead. _x000D_16/7/2024:#Update - NFA - Allwyn to confirm with retailer for 09/08, after the shop renovations have been completed, the install can go ahead. _x000D_15/7/2024:#Update - NFA - Allwyn to confirm with retailer for 09/08, after the shop renovations have been completed, the install can go ahead. _x000D_12/7/2024:#Update - NFA - Allwyn to confirm with retailer for 09/08, after the shop renovations have been completed, the install can go ahead. _x000D_11/7/2024:#Update - NFA - Allwyn to confirm with retailer for 09/08, after the shop renovations have been completed, the install can go ahead. _x000D_10/7/2024:#Update - NFA - Allwyn to confirm with retailer for 09/08, after the shop renovations have been completed, the install can go ahead. _x000D_9/7/2024:#Update - NFA - Allwyn to confirm with retailer for 09/08, after the shop renovations have been completed, the install can go ahead. _x000D_4/7/2024:#Update - NFA - Allwyn to confirm with retailer for 09/08, after the shop renovations have been completed, the install can go ahead. _x000D_3/7/2024:#Update - NFA - Allwyn to confirm with retailer for 09/08, after the shop renovations have been completed, the install can go ahead. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - NFA - Allwyn to confirm with retailer for 09/08, after the shop renovations have been completed, the install can go ahead. _x000D_27/6/2024:#Update - NFA - Allwyn to confirm with retailer for 09/08, after the shop renovations have been completed, the install can go ahead. _x000D_25/6/2024:#Update - NFA - Allwyn to confirm with retailer for 09/08, after the shop renovations have been completed, the install can go ahead. _x000D_24/6/2024:#Update - NFA - Allwyn to confirm with retailer for 09/08, after the shop renovations have been completed, the install can go ahead. _x000D_20/6/2024:#Update - NFA - Allwyn to confirm with retailer for 09/08, after the shop renovations have been completed, the install can go ahead. _x000D_19/6/2024:#Update - NFA - Allwyn to confirm with retailer for 09/08, after the shop renovations have been completed, the install can go ahead. _x000D_18/6/2024:#Update - NFA - Allwyn to confirm with retailer for 09/08, after the shop renovations have been completed, the install can go ahead. _x000D_17/6/2024:#Update - NFA - Allwyn to confirm with retailer for 09/08, after the shop renovations have been completed, the install can go ahead. _x000D_14/6/2024:#Update - NFA - Allwyn to confirm with retailer for 09/08, after the shop renovations have been completed, the install can go ahead. _x000D_13/6/2024:#Update - NFA - Allwyn to confirm with retailer for 09/08, after the shop renovations have been completed, the install can go ahead. _x000D_12/6/2024:#Update - NFA - Allwyn to confirm with retailer for 09/08, after the shop renovations have been completed, the install can go ahead. _x000D_11/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_7/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 06/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2300752 | 30013445 | 2.Commissioning | AM |  | 2024-05-23 | 2024-08-23 |  | 0 | [11 empty] | 0
1138 | 670173 | 1894 | Batch 4 Jun24 | Type 1 | FTTP/Mobile | Palmers | Skegness | PE25 2UB | 2024-06-13 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:Update: Order Amended _x000D_28/8/2024:Update: Order Amended _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_31/05/24: Downgraded from a site type 1 to a site type 3 29/04/2024: 07/03/24 - Advanced upgrade required ( approved ) 22/03/24: Process issue to be resolved before order can be changed and progress. 12/03/24: Abortive charge to be raised for failed visit on the 13/02. OLO order cancelled, there will be order change & cancellation charges tba. 29/02/24: Update from Allwyn retail team, Allwyn would look to another solution as they would not ask the retailer for this type of action. This is process from Allwyn. Alex S will take back into team for further discussion as the DP point (entrance into building) is behind the fridge. CSL have upto 48hrs to cancel order. Installation was not completed as customer line is blocked by a large fridge, which is too heavy to move, and distribution point has power cable running parallel to it and hoist is needed. | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:Update: Order Amended _x000D_28/8/2024:Update: Order Amended _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_31/05/24: Downgraded from a site type 1 to a site type 3 29/04/2024: 07/03/24 - Advanced upgrade required ( approved ) 22/03/24: Process issue to be resolved before order can be changed and progress. 12/03/24: Abortive charge to be raised for failed visit on the 13/02. OLO order cancelled, there will be order change & cancellation charges tba. 29/02/24: Update from Allwyn retail team, Allwyn would look to another solution as they would not ask the retailer for this type of action. This is process from Allwyn. Alex S will take back into team for further discussion as the DP point (entrance into building) is behind the fridge. CSL have upto 48hrs to cancel order. Installation was not completed as customer line is blocked by a large fridge, which is too heavy to move, and distribution point has power cable running parallel to it and hoist is needed. | 0 | 0 | 2024-06-07 |  |  |  | 2.Allwyn to arrange access | VFP2416590 | 30015687 | 1.Provisioning | AM |  | 2024-06-12 | 2024-10-01 |  | 0 | [11 empty] | 0
1139 | 647445 | 14 | Batch 1 Feb24 | Type 3 | SOGEA | Victory News | Broadstairs | CT10 1HQ | 2024-05-31 | 6/9/2024:#Update This order has been cancelled. _x000D_5/9/2024:#Update This order has been cancelled. _x000D_4/9/2024:#Update This order has been cancelled. _x000D_10/5/2024:#Update - Job did not go ahead as a ladder and safety assist is needed for the next visit. Will reappoint and confirm. _x000D_08/04/2024: New order added to report | 9/9/2024:#Update This order has been cancelled. _x000D_6/9/2024:#Update This order has been cancelled. _x000D_5/9/2024:#Update This order has been cancelled. _x000D_4/9/2024:#Update This order has been cancelled. _x000D_10/5/2024:#Update - Job did not go ahead as a ladder and safety assist is needed for the next visit. Will reappoint and confirm. _x000D_08/04/2024: New order added to report | 0 | #Update This order has been cancelled. |  | 07/03/24:Advanced upgrade approved 28/02/24: From meeting agreed that appointment for the 05/03 will be pushed back to the 13/03. Action Allwyn to arrange site access with end user for the 13/02 and also to arrange that fridge is moved to access DP point. 15/02/24: Action Allwyn to discuss with retailer on how to proceed. OR requesting revisit on the 05/03 if Allwyn can arrange site access. | 2024-03-08 | 01/03/24 Allwyn spoken to the retailer, he has agreed the revisit but has advised the fridge is still in situ and cannot be moved 08/03/24: 07/03/24 - Agreed to downgrade to Type3 | 3.Allwyn to arrange rtr install | VFS874905 | 30012229 | 2.Commissioning | AM |  |  |  |  | Not Applicable |  |  |  | 2024-07-25 | [7 empty] | 0
1140 | 458716 | 556 | Batch 3 May24 | Type 1 | FTTP | Costcutter | Whitchurch | SY13 1AG | 2024-06-07 | 10/5/2024:#Update - Delayed appointment from 07/05, Revisiting 08/05 - Engineer Retained works and retailer made aware on site. _x000D_08/05/2024: #Update - Delayed appointment from 07/05, Revisiting 08/05 - Engineer Retained works and retailer made aware on site. 08/04/2024: New order added to report | 10/5/2024:#Update - Delayed appointment from 07/05, Revisiting 08/05 - Engineer Retained works and retailer made aware on site. _x000D_08/05/2024: #Update - Delayed appointment from 07/05, Revisiting 08/05 - Engineer Retained works and retailer made aware on site. 08/04/2024: New order added to report | [6 empty] | 3.Allwyn to arrange rtr install | VFP2300753 | 30013446 | 6.Failed router install |  |  | 2024-05-07 | 2024-07-05 | 2024-05-08 | TRUE | [7 empty] | 2024-06-18 | 242005008891 |  | 2024-07-01 | 1
1141 | 449359 | 659 | Batch 3 May24 | Type 1 | SOGEA | NORTH WEMBLEY NEWS | WEMBLEY | HA9 7PB | 2024-06-07 | 10/5/2024:#Update - Engineer ran out of time on the install, will return 03/05 to complete _x000D_03/05/2024: #Update - Engineer ran out of time on the install, will return 03/05 to complete 08/04/2024: New order added to report | 10/5/2024:#Update - Engineer ran out of time on the install, will return 03/05 to complete _x000D_03/05/2024: #Update - Engineer ran out of time on the install, will return 03/05 to complete 08/04/2024: New order added to report |  |  | 2024-05-08 | 08/05/2024: CSL to provide an update |  |  | 3.Allwyn to arrange rtr install | VFP2300856 | 30013549 | 2.Commissioning |  |  | 2024-05-07 | 2024-07-05 | 2024-05-09 | TRUE |  |  |  | 2024-06-24 | [7 empty] | 0
1142 | 439025 | 739 | Batch 3 May24 | Type 1 | SOGEA | Gedney Newsagents | SPALDING | PE12 9JF | 2024-06-07 | 10/5/2024:#Update - order delayed due to 3rd party supplier - a multiskilled engineer work is required for NCF work, further updates to follow _x000D_03/05/24: Your order has been delayed. Multiskilled engineer work is required for NCF work, Our Suppliers have given us a review date of 10/05/2024. We will continue to provide update as they become available. 08/04/2024: New order added to report | 10/5/2024:#Update - order delayed due to 3rd party supplier - a multiskilled engineer work is required for NCF work, further updates to follow _x000D_03/05/24: Your order has been delayed. Multiskilled engineer work is required for NCF work, Our Suppliers have given us a review date of 10/05/2024. We will continue to provide update as they become available. 08/04/2024: New order added to report |  |  | 2024-05-09 | 09/05/2024: CSL to provide an update |  |  | 3.Allwyn to arrange rtr install | VFP2300936 | 30013629 | 2.Commissioning |  |  | 2024-05-08 | 2024-05-08 | 2024-05-10 | TRUE |  |  |  | 2024-06-17 | [7 empty] | 0
1143 | 458742 | 1817 | Batch 4 Jun24 | Type 1 | SOGEA | MBS News and Off Licence | DUDLEY | DY1 1LP | 2024-06-14 | 17/6/2024:Order Completed _x000D_14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 14/06/2024. We will continue to provide update as they become available. _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 17/6/2024:Order Completed _x000D_14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 14/06/2024. We will continue to provide update as they become available. _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983342 | 30015190 | 2.Commissioning | AM |  | 2024-06-10 | 2024-06-10 | 2024-06-13 | TRUE |  |  |  | 2024-09-04 | [7 empty] | 0
1144 | 661313 | 1883 | Batch 4 Jun24 | Type 1 | SOGEA | Thanet Way Services | Faversham | ME13 9EL | 2024-06-14 | 17/6/2024:Order Completed _x000D_14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 14/06/2024. We will continue to provide update as they become available. _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 17/6/2024:Order Completed _x000D_14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 14/06/2024. We will continue to provide update as they become available. _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983468 | 30015751 | 6.Failed router install | AM |  | 2024-06-10 | 2024-06-10 | 2024-06-13 | TRUE |  |  |  | 2024-07-05 |  |  |  | 2024-07-05 | 242005008597 |  |  | 1
1145 | 669627 | 1876 | Batch 4 Jun24 | Type 1 | SOGEA | Spar Stores | Prestatyn | LL19 9BB | 2024-06-14 | 14/6/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_13/6/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_12/6/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 14/6/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_13/6/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_12/6/2024:#Update - NFA - Allwyn have confirmed reappointed install date with retailer _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996831 | 30016013 | 2.Commissioning | AM |  | 2024-06-10 | 2024-06-10 | 2024-06-13 | TRUE |  |  |  | 2024-07-19 | [7 empty] | 0
1146 | 667838 | 1189 | Batch 3 May24 | Type 1 | SOGEA | D&S Food & Wine | DUNSTABLE | LU5 5ES | 2024-09-02 | 29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-05-29 | 29/05/24: CSL to provide an update |  |  | 3.Allwyn to arrange rtr install | VFP2301386 | 30014079 | 6.Failed router install | AM | [8 empty] | 2024-07-08 |  |  |  | 2024-09-02 | 242005011138 | 242005011138 | 2024-09-02 | 1
1147 | 472505 | 1201 | Batch 3 May24 | Type 1 | FTTP | Londis Supermarket | Minster-on-Sea | ME12 2RW | 2024-06-13 | 14/6/2024:#Update - Order is delayed as step-1 external work is required. CSL to liaise with Openreach and update as necessary. _x000D_13/6/2024:#Update - Order is delayed as step-1 external work is required. CSL to liaise with Openreach and update as necessary. _x000D_12/6/2024:#Update - Order is delayed as step-1 external work is required. CSL to liaise with Openreach and update as necessary. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 14/6/2024:#Update - Order is delayed as step-1 external work is required. CSL to liaise with Openreach and update as necessary. _x000D_13/6/2024:#Update - Order is delayed as step-1 external work is required. CSL to liaise with Openreach and update as necessary. _x000D_12/6/2024:#Update - Order is delayed as step-1 external work is required. CSL to liaise with Openreach and update as necessary. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301398 | 30014091 | 6.Failed router install | AM |  | 2024-05-21 | 2024-06-12 | 2024-06-12 | TRUE |  |  |  | 2024-07-05 |  |  |  | 2024-07-05 | 242005008599 |  |  | 1
1148 | 481374 | 1511 | Batch 4 Jun24 | Type 1 | SOGEA | One O One | Glasgow | G74 1JR | 2024-06-13 | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS985998 | 30015547 | 2.Commissioning | AM |  | 2024-06-12 | 2024-06-12 | 2024-06-12 | TRUE |  |  |  | 2024-07-04 | [7 empty] | 0
1149 | 438116 | 1512 | Batch 4 Jun24 | Type 1 | FTTP | One O One | GLASGOW | G21 4YE | 2024-06-13 | 14/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/05 AM _x000D_13/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/05 AM _x000D_12/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/05 AM _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 14/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/05 AM _x000D_13/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/05 AM _x000D_12/6/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/05 AM _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2338526 | 30015618 | 2.Commissioning | AM |  | 2024-06-12 | 2024-06-12 | 2024-06-12 | TRUE |  |  |  | 2024-07-03 | [7 empty] | 0
1150 | 432511 | 1515 | Batch 4 Jun24 | Type 1 | SOGEA | One O One | GLASGOW | G15 7QR | 2024-06-13 | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984756 | 30015595 | 2.Commissioning | AM |  | 2024-06-12 | 2024-06-12 | 2024-06-12 | TRUE |  |  |  | 2024-09-04 | [7 empty] | 0
1151 | 617389 | 1519 | Batch 4 Jun24 | Type 1 | SOGEA | Bargain Booze | Nottingham | NG5 5PT | 2024-06-13 | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:Order Completed _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS984757 | 30015337 | 6.Failed router install | AM |  | 2024-06-12 | 2024-06-12 | 2024-06-12 | TRUE |  |  |  | 2024-07-05 |  |  |  | 2024-07-11 | 23A004945919 |  | 2024-07-12 | 1
1152 | 405595 | 1831 | Batch 4 Jun24 | Type 1 | SOGEA | Lawrences Budgens | HARLESTON | IP20 9BP | 2024-06-13 | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983355 | 30015188 | 2.Commissioning | AM |  | 2024-06-12 | 2024-06-12 | 2024-06-12 | TRUE |  |  |  | 2024-07-03 | [7 empty] | 0
1153 | 461225 | 1836 | Batch 4 Jun24 | Type 1 | SOGEA | Key Store | RAMSGATE | CT11 9DS | 2024-06-13 | 14/6/2024:Order Completed 13/6/2024:Order Completed 12/6/2024:Update: Order Completed by Supplier 10/6/2024:0 7/6/2024:0 6/6/2024:0 5/6/2024:0 4/6/2024:0 31/5/2024:0 30/5/2024:0 29/5/2024:0 28/5/2024:0 14/05/2024: Retailer changed ( old Id : 461363 ) 10/5/2024:0 02/05/2024: New order added to report | 14/6/2024:Order Completed 13/6/2024:Order Completed 12/6/2024:Update: Order Completed by Supplier 10/6/2024:0 7/6/2024:0 6/6/2024:0 5/6/2024:0 4/6/2024:0 31/5/2024:0 30/5/2024:0 29/5/2024:0 28/5/2024:0 14/05/2024: Retailer changed ( old Id : 461363 ) 10/5/2024:0 02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983360 | 30015285 | 2.Commissioning | AM |  | 2024-06-12 | 2024-06-12 | 2024-06-12 | TRUE |  |  |  | 2024-09-05 | [7 empty] | 0
1154 | 670709 | 1838 | Batch 4 Jun24 | Type 1 | SOGEA | STRACHANS | NAIRN | IV12 4BJ | 2024-06-13 | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983361 | 30015169 | 2.Commissioning | AM |  | 2024-06-12 | 2024-06-12 | 2024-06-12 | TRUE |  |  |  | 2024-07-09 | [7 empty] | 0
1155 | 484274 | 1839 | Batch 4 Jun24 | Type 1 | SOGEA | Llantarnam News | Cwmbran | NP44 3BD | 2024-06-13 | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983362 | 30015242 | 2.Commissioning | AM |  | 2024-06-12 | 2024-06-12 | 2024-06-12 | TRUE |  |  |  | 2024-07-15 | [7 empty] | 0
1156 | 655717 | 1892 | Batch 4 Jun24 | Type 1 | SOGEA | One Stop Working With Gsm Food and | Birmingham | B24 9PJ | 2024-06-13 | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983479 | 30015748 | 2.Commissioning | AM |  | 2024-06-12 | 2024-06-12 | 2024-06-12 | TRUE |  |  |  | 2024-07-04 | [7 empty] | 0
1157 | 669817 | 2396 | Batch 4 Jun24 | Type 1 | SOGEA | Spar Stores | Penrith | CA11 7TA | 2024-06-13 | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 14/6/2024:Order Completed _x000D_13/6/2024:Order Completed _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996875 | 30016101 | 6.Failed router install | AM |  | 2024-06-12 | 2024-06-12 | 2024-06-12 | TRUE |  |  |  | 2024-07-17 |  |  |  | 2024-07-15 | 242005013519 |  | 2024-07-16 | 1
1158 | 666671 | 1159 | Batch 3 May24 | Type 1 | SOGEA | JAMAICA ROAD MSPO | LONDON | SE16 4SN | 2024-06-14 | 17/6/2024:Order Completed _x000D_14/6/2024:Order Completed _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 17/6/2024:Order Completed _x000D_14/6/2024:Order Completed _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-05-22 | 22/05/24: CSL to provide an update |  |  | 3.Allwyn to arrange rtr install | VFP2301356 | 30014049 | 6.Failed router install | AM |  | 2024-05-21 | 2024-06-13 | 2024-06-13 | TRUE |  |  |  | 2024-07-03 |  |  |  | 2024-08-27 | 242005008363 | 242005008363 | 2024-08-28 | 1
1159 | 467482 | 1531 | Batch 4 Jun24 | Type 1 | SOGEA | Spar Gortin Road | OMAGH | BT79 7DH | 2024-06-14 | 17/6/2024:Order Completed _x000D_14/6/2024:Order Completed _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 17/6/2024:Order Completed _x000D_14/6/2024:Order Completed _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2338533 | 30015655 | 6.Failed router install | AM |  | 2024-06-13 | 2024-06-13 | 2024-06-13 | TRUE |  |  |  | 2024-07-11 |  |  |  | 2024-07-11 | 242005010282 |  | 2024-07-12 | 1
1160 | 630516 | 1842 | Batch 4 Jun24 | Type 1 | SOGEA | News Extra | Crewe | CW1 3HE | 2024-06-14 | 17/6/2024:Order Completed _x000D_14/6/2024:Order Completed _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 17/6/2024:Order Completed _x000D_14/6/2024:Order Completed _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983367 | 30015268 | 2.Commissioning | AM |  | 2024-06-13 | 2024-06-13 | 2024-06-13 | TRUE |  |  |  | 2024-07-12 | [7 empty] | 0
1161 | 666866 | 1843 | Batch 4 Jun24 | Type 1 | SOGEA | Post Office | Pontypool | NP4 6XA | 2024-06-14 | 17/6/2024:Order Completed _x000D_14/6/2024:Order Completed _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 17/6/2024:Order Completed _x000D_14/6/2024:Order Completed _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983366 | 30015179 | 2.Commissioning | AM |  | 2024-06-13 | 2024-06-13 | 2024-06-13 | TRUE |  |  |  | 2024-07-15 | [7 empty] | 0
1162 | 668198 | 1846 | Batch 4 Jun24 | Type 1 | SOGEA | Tonypandy Convenience Store | TONYPANDY | CF40 1AL | 2024-06-14 | 17/6/2024:Order Completed _x000D_14/6/2024:Order Completed _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 17/6/2024:Order Completed _x000D_14/6/2024:Order Completed _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983371 | 30015286 | 2.Commissioning | AM |  | 2024-06-13 | 2024-06-13 | 2024-06-13 | TRUE |  |  |  | 2024-07-17 | [7 empty] | 0
1163 | 666617 | 1847 | Batch 4 Jun24 | Type 1 | SOGEA | Costcutter | SOUTHEND-ON-SEA | SS2 4LX | 2024-06-14 | 17/6/2024:#Update Network planning issues, further updates to follow. _x000D_14/6/2024:#Update Network planning issues, further updates to follow. _x000D_13/6/2024:#Update Network planning issues, further updates to follow. _x000D_12/6/2024:#Update Network planning issues, further updates to follow. _x000D_10/6/2024:#Update Network planning issues, further updates to follow. _x000D_7/6/2024:#Update Network planning issues, further updates to follow. _x000D_6/6/2024:#Update Network planning issues, further updates to follow. _x000D_5/6/2024:#Update Network planning issues, further updates to follow. _x000D_4/6/2024:#Update Network planning issues, further updates to follow. _x000D_31/5/2024:#Update Network planning issues, further updates to follow. _x000D_30/5/2024:#Update Network planning issues, further updates to follow. _x000D_29/5/2024:#Update Network planning issues, further updates to follow. _x000D_28/5/2024:#Update Network planning issues, further updates to follow. _x000D_10/5/2024:#Update Network planning issues, further updates to follow. _x000D_02/05/2024: New order added to report | 17/6/2024:#Update Network planning issues, further updates to follow. _x000D_14/6/2024:#Update Network planning issues, further updates to follow. _x000D_13/6/2024:#Update Network planning issues, further updates to follow. _x000D_12/6/2024:#Update Network planning issues, further updates to follow. _x000D_10/6/2024:#Update Network planning issues, further updates to follow. _x000D_7/6/2024:#Update Network planning issues, further updates to follow. _x000D_6/6/2024:#Update Network planning issues, further updates to follow. _x000D_5/6/2024:#Update Network planning issues, further updates to follow. _x000D_4/6/2024:#Update Network planning issues, further updates to follow. _x000D_31/5/2024:#Update Network planning issues, further updates to follow. _x000D_30/5/2024:#Update Network planning issues, further updates to follow. _x000D_29/5/2024:#Update Network planning issues, further updates to follow. _x000D_28/5/2024:#Update Network planning issues, further updates to follow. _x000D_10/5/2024:#Update Network planning issues, further updates to follow. _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983372 | 30015192 | 6.Failed router install | AM |  | 2024-06-13 | 2024-06-13 | 2024-06-13 | TRUE |  |  |  | 2024-07-10 |  |  |  | 2024-07-10 | 242005008573 |  | 2024-07-11 | 1
1164 | 463163 | 1903 | Batch 4 Jun24 | Type 1 | SOGEA | Budgens | INGATESTONE | CM4 9DW | 2024-06-14 | 17/6/2024:Order Completed _x000D_14/6/2024:Order Completed _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 17/6/2024:Order Completed _x000D_14/6/2024:Order Completed _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983487 | 30015743 | 6.Failed router install | AM |  | 2024-06-13 | 2024-06-13 | 2024-06-13 | TRUE |  |  |  | 2024-07-10 |  |  |  | 2024-07-10 | 242005008575 |  | 2024-07-11 | 1
1165 | 478950 | 1904 | Batch 4 Jun24 | Type 1 | SOGEA | Bal | Newcastle | NE15 8DT | 2024-06-14 | 17/6/2024:#Update Site survey is required .This has been sent to the survey engineers and they have given us a review date of 07/05/2024 .We will continue to provide update as they become available. _x000D_14/6/2024:#Update Site survey is required .This has been sent to the survey engineers and they have given us a review date of 07/05/2024 .We will continue to provide update as they become available. _x000D_13/6/2024:#Update Site survey is required .This has been sent to the survey engineers and they have given us a review date of 07/05/2024 .We will continue to provide update as they become available. _x000D_12/6/2024:#Update Site survey is required .This has been sent to the survey engineers and they have given us a review date of 07/05/2024 .We will continue to provide update as they become available. _x000D_10/6/2024:#Update Site survey is required .This has been sent to the survey engineers and they have given us a review date of 07/05/2024 .We will continue to provide update as they become available. _x000D_7/6/2024:#Update Site survey is required .This has been sent to the survey engineers and they have given us a review date of 07/05/2024 .We will continue to provide update as they become available. _x000D_6/6/2024:#Update Site survey is required .This has been sent to the survey engineers and they have given us a review date of 07/05/2024 .We will continue to provide update as they become available. _x000D_5/6/2024:#Update Site survey is required .This has been sent to the survey engineers and they have given us a review date of 07/05/2024 .We will continue to provide update as they become available. _x000D_4/6/2024:#Update Site survey is required .This has been sent to the survey engineers and they have given us a review date of 07/05/2024 .We will continue to provide update as they become available. _x000D_31/5/2024:#Update Site survey is required .This has been sent to the survey engineers and they have given us a review date of 07/05/2024 .We will continue to provide update as they become available. _x000D_30/5/2024:#Update Site survey is required .This has been sent to the survey engineers and they have given us a review date of 07/05/2024 .We will continue to provide update as they become available. _x000D_29/5/2024:#Update Site survey is required .This has been sent to the survey engineers and they have given us a review date of 07/05/2024 .We will continue to provide update as they become available. _x000D_28/5/2024:#Update Site survey is required .This has been sent to the survey engineers and they have given us a review date of 07/05/2024 .We will continue to provide update as they become available. _x000D_10/5/2024:#Update Site survey is required .This has been sent to the survey engineers and they have given us a review date of 07/05/2024 .We will continue to provide update as they become available. _x000D_02/05/2024: New order added to report | 17/6/2024:#Update Site survey is required .This has been sent to the survey engineers and they have given us a review date of 07/05/2024 .We will continue to provide update as they become available. _x000D_14/6/2024:#Update Site survey is required .This has been sent to the survey engineers and they have given us a review date of 07/05/2024 .We will continue to provide update as they become available. _x000D_13/6/2024:#Update Site survey is required .This has been sent to the survey engineers and they have given us a review date of 07/05/2024 .We will continue to provide update as they become available. _x000D_12/6/2024:#Update Site survey is required .This has been sent to the survey engineers and they have given us a review date of 07/05/2024 .We will continue to provide update as they become available. _x000D_10/6/2024:#Update Site survey is required .This has been sent to the survey engineers and they have given us a review date of 07/05/2024 .We will continue to provide update as they become available. _x000D_7/6/2024:#Update Site survey is required .This has been sent to the survey engineers and they have given us a review date of 07/05/2024 .We will continue to provide update as they become available. _x000D_6/6/2024:#Update Site survey is required .This has been sent to the survey engineers and they have given us a review date of 07/05/2024 .We will continue to provide update as they become available. _x000D_5/6/2024:#Update Site survey is required .This has been sent to the survey engineers and they have given us a review date of 07/05/2024 .We will continue to provide update as they become available. _x000D_4/6/2024:#Update Site survey is required .This has been sent to the survey engineers and they have given us a review date of 07/05/2024 .We will continue to provide update as they become available. _x000D_31/5/2024:#Update Site survey is required .This has been sent to the survey engineers and they have given us a review date of 07/05/2024 .We will continue to provide update as they become available. _x000D_30/5/2024:#Update Site survey is required .This has been sent to the survey engineers and they have given us a review date of 07/05/2024 .We will continue to provide update as they become available. _x000D_29/5/2024:#Update Site survey is required .This has been sent to the survey engineers and they have given us a review date of 07/05/2024 .We will continue to provide update as they become available. _x000D_28/5/2024:#Update Site survey is required .This has been sent to the survey engineers and they have given us a review date of 07/05/2024 .We will continue to provide update as they become available. _x000D_10/5/2024:#Update Site survey is required .This has been sent to the survey engineers and they have given us a review date of 07/05/2024 .We will continue to provide update as they become available. _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983488 | 30015720 | 6.Failed router install | AM |  | 2024-06-13 | 2024-06-13 | 2024-06-13 | TRUE |  |  |  | 2024-07-17 |  |  |  | 2024-07-17 | 238004926227 |  | 2024-07-18 | 1
1166 | 251669 | 1907 | Batch 4 Jun24 | Type 1 | FTTP | Londis | CANTERBURY | CT1 1RY | 2024-06-14 | 17/6/2024:Order Completed _x000D_14/6/2024:Order Completed _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 17/6/2024:Order Completed _x000D_14/6/2024:Order Completed _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983490 | 30015726 | 6.Failed router install | AM |  | 2024-06-13 | 2024-06-13 | 2024-06-13 | TRUE | [7 empty] | 2024-07-03 | 242005008594 |  | 2024-07-04 | 1
1167 | 455029 | 1911 | Batch 4 Jun24 | Type 1 | SOGEA | Dike & Son Ltd | Sturminster Newton | DT10 2NB | 2024-06-14 | 17/6/2024:#update - The order has been sent to the survey group; await order status update. _x000D_14/6/2024:#update - The order has been sent to the survey group; await order status update. _x000D_13/6/2024:#update - The order has been sent to the survey group; await order status update. _x000D_12/6/2024:#update - The order has been sent to the survey group; await order status update. _x000D_10/6/2024:#update - The order has been sent to the survey group; await order status update. _x000D_7/6/2024:#update - The order has been sent to the survey group; await order status update. _x000D_6/6/2024:#update - The order has been sent to the survey group; await order status update. _x000D_5/6/2024:#update - The order has been sent to the survey group; await order status update. _x000D_4/6/2024:#update - The order has been sent to the survey group; await order status update. _x000D_31/5/2024:#update - The order has been sent to the survey group; await order status update. _x000D_30/5/2024:#update - The order has been sent to the survey group; await order status update. _x000D_29/5/2024:#update - The order has been sent to the survey group; await order status update. _x000D_28/5/2024:#update - The order has been sent to the survey group; await order status update. _x000D_10/5/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_02/05/2024: New order added to report | 17/6/2024:#update - The order has been sent to the survey group; await order status update. _x000D_14/6/2024:#update - The order has been sent to the survey group; await order status update. _x000D_13/6/2024:#update - The order has been sent to the survey group; await order status update. _x000D_12/6/2024:#update - The order has been sent to the survey group; await order status update. _x000D_10/6/2024:#update - The order has been sent to the survey group; await order status update. _x000D_7/6/2024:#update - The order has been sent to the survey group; await order status update. _x000D_6/6/2024:#update - The order has been sent to the survey group; await order status update. _x000D_5/6/2024:#update - The order has been sent to the survey group; await order status update. _x000D_4/6/2024:#update - The order has been sent to the survey group; await order status update. _x000D_31/5/2024:#update - The order has been sent to the survey group; await order status update. _x000D_30/5/2024:#update - The order has been sent to the survey group; await order status update. _x000D_29/5/2024:#update - The order has been sent to the survey group; await order status update. _x000D_28/5/2024:#update - The order has been sent to the survey group; await order status update. _x000D_10/5/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983495 | 30015739 | 2.Commissioning | AM |  | 2024-06-13 | 2024-06-13 | 2024-06-13 | TRUE |  |  |  | 2024-07-09 | [7 empty] | 0
1168 | 483951 | 1913 | Batch 4 Jun24 | Type 1 | FTTP | Nisa Local | Swansea | SA1 1LN | 2024-06-14 | 17/6/2024:Order Completed _x000D_14/6/2024:Order Completed _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 17/6/2024:Order Completed _x000D_14/6/2024:Order Completed _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2337371 | 30015691 | 6.Failed router install | AM |  | 2024-06-13 | 2024-06-13 | 2024-06-13 | TRUE |  |  |  | 2024-07-16 |  |  |  | 2024-07-16 | 23A004945359 |  | 2024-07-17 | 1
1169 | 487103 | 1914 | Batch 4 Jun24 | Type 1 | SOGEA | Nisa Local | Blackpool | FY3 7RD | 2024-06-14 | 17/6/2024:Order Completed _x000D_14/6/2024:Order Completed _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 17/6/2024:Order Completed _x000D_14/6/2024:Order Completed _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983496 | 30015713 | 6.Failed router install | AM |  | 2024-06-13 | 2024-06-13 | 2024-06-13 | TRUE |  |  |  | 2024-07-16 |  |  |  | 2024-07-16 | 242005013510 |  | 2024-07-17 | 1
1170 | 654229 | 1917 | Batch 4 Jun24 | Type 1 | SOGEA | Nisa Local | Dunstable | LU5 5NS | 2024-06-14 | 17/6/2024:Order Completed _x000D_14/6/2024:Order Completed _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 17/6/2024:Order Completed _x000D_14/6/2024:Order Completed _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983497 | 30015735 | 2.Commissioning | AM |  | 2024-06-13 | 2024-06-13 | 2024-06-13 | TRUE |  |  |  | 2024-07-08 | [7 empty] | 0
1171 | 487430 | 1919 | Batch 4 Jun24 | Type 1 | SoGEA/Mobile | Nisa Local | Fraserburgh | AB43 9JP | 2024-06-14 | 29/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_28/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_27/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_17/6/2024:Openreach Delay : Automated testing has identified a potential fault _x000D_14/6/2024:Openreach Delay : Automated testing has identified a potential fault _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 29/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_28/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_27/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_17/6/2024:Openreach Delay : Automated testing has identified a potential fault _x000D_14/6/2024:Openreach Delay : Automated testing has identified a potential fault _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983498 | 30015707 | 2.Commissioning | AM |  | 2024-08-23 | 2024-08-23 |  | 0 |  |  |  | 2024-07-09 | [7 empty] | 0
1172 | 230908 | 1920 | Batch 4 Jun24 | Type 1 | SOGEA | Keystore | INVERURIE | AB51 0AA | 2024-06-14 | 17/6/2024:Order Completed _x000D_14/6/2024:Order Completed _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 17/6/2024:Order Completed _x000D_14/6/2024:Order Completed _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983499 | 30015715 | 6.Failed router install | AM |  | 2024-06-13 | 2024-06-13 | 2024-06-13 | TRUE |  |  |  | 2024-07-09 |  |  |  | 2024-07-09 | 242005009510 |  |  | 1
1173 | 651335 | 1925 | Batch 4 Jun24 | Type 1 | SOGEA | Nisa Local | Liverpool | L24 2SF | 2024-06-14 | 17/6/2024:Order Completed _x000D_14/6/2024:Order Completed _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 17/6/2024:Order Completed _x000D_14/6/2024:Order Completed _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS983504 | 30015746 | 6.Failed router install | AM |  | 2024-06-13 | 2024-06-13 | 2024-06-13 | TRUE |  |  |  | 2024-07-10 |  |  |  | 2024-07-10 | 242005008784 |  |  | 1
1174 | 442734 | 2483 | Batch 4 Jun24 | Type 1 | SOGEA | Spar Stores | Chesterfield | S41 8QW | 2024-06-14 | 17/6/2024:Order Completed _x000D_14/6/2024:Order Completed _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 17/6/2024:Order Completed _x000D_14/6/2024:Order Completed _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996885 | 30016093 | 2.Commissioning | AM |  | 2024-06-13 | 2024-06-13 | 2024-06-13 | TRUE |  |  |  | 2024-07-15 | [7 empty] | 0
1175 | 670034 | 2502 | Batch 4 Jun24 | Type 1 | SOGEA | Post Office | Southampton | SO45 3PA | 2024-06-14 | 17/6/2024:Order Completed _x000D_14/6/2024:Order Completed _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 17/6/2024:Order Completed _x000D_14/6/2024:Order Completed _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996883 | 30016112 | 2.Commissioning | AM |  | 2024-06-13 | 2024-06-13 | 2024-06-13 | TRUE |  |  |  | 2024-07-04 | [7 empty] | 0
1176 | 669671 | 2513 | Batch 4 Jun24 | Type 1 | SOGEA | Post Office | Scunthorpe | DN16 2AW | 2024-06-14 | 17/6/2024:Order Completed _x000D_14/6/2024:Order Completed _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 17/6/2024:Order Completed _x000D_14/6/2024:Order Completed _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996890 | 30016085 | 2.Commissioning | AM |  | 2024-06-13 | 2024-06-13 | 2024-06-13 | TRUE |  |  |  | 2024-07-12 | [7 empty] | 0
1177 | 665164 | 2662 | Batch 4 Jun24 | Type 1 | SOGEA | Polmont Convenience Store | Falkirk | FK2 0PX | 2024-06-14 | 17/6/2024:Order Completed _x000D_14/6/2024:Order Completed _x000D_13/6/2024:Update: Order Completed by Supplier _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 17/6/2024:Order Completed _x000D_14/6/2024:Order Completed _x000D_13/6/2024:Update: Order Completed by Supplier _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996896 | 30016102 | 2.Commissioning | AM |  | 2024-06-13 | 2024-06-13 | 2024-06-13 | TRUE |  |  |  | 2024-07-08 | [7 empty] | 0
1178 | 411960 | 2721 | Batch 4 Jun24 | Type 1 | SOGEA | Spar Stores | Tywyn | LL36 9AD | 2024-06-14 | 10/5/2024:Update: Order Amended _x000D_08/04/2024: New order added to report | 10/5/2024:Update: Order Amended _x000D_08/04/2024: New order added to report |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS996894 | 30016008 | 2.Commissioning | AM |  | 2024-06-13 | 2024-06-13 | 2024-06-13 | TRUE |  |  |  | 2024-07-19 | [7 empty] | 0
1179 | 458040 | 908 | Batch 3 May24 | Type 1 | SOGEA | Kazs Birley Moor News | SHEFFIELD | S12 4WL | 2024-06-07 | 17/6/2024:#Update - Please be informed the engineer was unable to complete the task as Complex DIG work is required. To progress this further, a DIG activity has been raised. Please allow 7 working days for an update. Review date 07/06/24 _x000D_14/6/2024:#Update - Please be informed the engineer was unable to complete the task as Complex DIG work is required. To progress this further, a DIG activity has been raised. Please allow 7 working days for an update. Review date 07/06/24 _x000D_13/6/2024:#Update - Please be informed the engineer was unable to complete the task as Complex DIG work is required. To progress this further, a DIG activity has been raised. Please allow 7 working days for an update. Review date 07/06/24 _x000D_12/6/2024:#Update - Please be informed the engineer was unable to complete the task as Complex DIG work is required. To progress this further, a DIG activity has been raised. Please allow 7 working days for an update. Review date 07/06/24 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 17/6/2024:#Update - Please be informed the engineer was unable to complete the task as Complex DIG work is required. To progress this further, a DIG activity has been raised. Please allow 7 working days for an update. Review date 07/06/24 _x000D_14/6/2024:#Update - Please be informed the engineer was unable to complete the task as Complex DIG work is required. To progress this further, a DIG activity has been raised. Please allow 7 working days for an update. Review date 07/06/24 _x000D_13/6/2024:#Update - Please be informed the engineer was unable to complete the task as Complex DIG work is required. To progress this further, a DIG activity has been raised. Please allow 7 working days for an update. Review date 07/06/24 _x000D_12/6/2024:#Update - Please be informed the engineer was unable to complete the task as Complex DIG work is required. To progress this further, a DIG activity has been raised. Please allow 7 working days for an update. Review date 07/06/24 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2301105 | 30013798 | 6.Failed router install |  |  | 2024-05-17 | 2024-04-24 | 2024-04-24 | TRUE | [7 empty] | 2024-06-28 | 242005008800 |  | 2024-07-02 | 1
1180 | 641989 | 28 | Batch 2 Apr24 | Type 3 |  | Blackwell Store | ALFRETON | DE55 5JN | 2024-05-31 | 6/9/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_5/9/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_4/9/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_3/9/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_2/9/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_29/8/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_28/8/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_27/8/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_22/8/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_21/8/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_20/8/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_19/8/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_19/8/2024:01361132 _x000D_16/8/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_15/8/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_14/8/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_13/8/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_12/8/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_9/8/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_8/8/2024:29/04/2024 _x000D_6/8/2024:29/04/2024 _x000D_5/8/2024:29/04/2024 _x000D_2/8/2024:29/04/2024 _x000D_1/8/2024:29/04/2024 _x000D_31/7/2024:29/04/2024 _x000D_31/7/2024:29/04/2024 _x000D_30/7/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_29/7/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_29/7/2024:01361132 _x000D_26/7/2024:01361132 _x000D_24/7/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_23/7/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_22/7/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_22/7/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_19/7/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_18/7/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_17/7/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_16/7/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_15/7/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_12/7/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_11/7/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_10/7/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_9/7/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_4/7/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_3/7/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_27/6/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_25/6/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_24/6/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_20/6/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_19/6/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_18/6/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_17/6/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_14/6/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_13/6/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_12/6/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_11/6/2024:0 _x000D_ | 9/9/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_6/9/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_5/9/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_4/9/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_3/9/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_2/9/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_29/8/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_28/8/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_27/8/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_22/8/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_21/8/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_20/8/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_19/8/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_19/8/2024:01361132 _x000D_16/8/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_15/8/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_14/8/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_13/8/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_12/8/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_9/8/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_8/8/2024:29/04/2024 _x000D_6/8/2024:29/04/2024 _x000D_5/8/2024:29/04/2024 _x000D_2/8/2024:29/04/2024 _x000D_1/8/2024:29/04/2024 _x000D_31/7/2024:29/04/2024 _x000D_31/7/2024:29/04/2024 _x000D_30/7/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_29/7/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_29/7/2024:01361132 _x000D_26/7/2024:01361132 _x000D_24/7/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_23/7/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_22/7/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_22/7/2024:#Update - request from Allwyn to change site type 1 to site type 3 mobile only _x000D_19/7/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_18/7/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_17/7/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_16/7/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_15/7/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_12/7/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_11/7/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_10/7/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_9/7/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_4/7/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_3/7/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_27/6/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_25/6/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_24/6/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_20/6/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_19/6/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_18/6/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_17/6/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_14/6/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_13/6/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_12/6/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_11/6/2024:0 _x000D_ | 0 | #Update - request from Allwyn to change site type 1 to site type 3 mobile only | 2024-05-14 | 14/05/2024: Allwyn to approve the charges of the request 03/05/2024: CSL to completed the circut on 13/05 23/04/2024: Allwyn confirmed the new visit date with the retailer. Closed 4/4/2024: Allwyn confirmed the new visit date with the retailer. 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFS939474 | 30013105 | 2.Commissioning | AM | [16 empty] | 0
1181 | 632644 | 190 | Batch 2 Apr24 | Type 3 |  | Yuvraj News & Convenience Store | Leicester | LE5 4DG | 2024-05-31 | 6/9/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_5/9/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_4/9/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_3/9/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_2/9/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_29/8/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_28/8/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_27/8/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_22/8/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_21/8/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_20/8/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_19/8/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_19/8/2024:01348091 _x000D_16/8/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_15/8/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_14/8/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_13/8/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_12/8/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_9/8/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_8/8/2024:15/05/2024 _x000D_6/8/2024:15/05/2024 _x000D_5/8/2024:15/05/2024 _x000D_2/8/2024:15/05/2024 _x000D_1/8/2024:15/05/2024 _x000D_31/7/2024:15/05/2024 _x000D_31/7/2024:15/05/2024 _x000D_30/7/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_29/7/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_29/7/2024:01348091 _x000D_26/7/2024:01348091 _x000D_24/7/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_23/7/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_22/7/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_22/7/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_19/7/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn _x000D_18/7/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn 17/7/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn 16/7/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn 15/7/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn 12/7/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn 11/7/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn 10/7/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn 9/7/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn 4/7/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn 3/7/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn 2/7/2024:A1 (Site access failure) 1/7/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn 27/6/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn 25/6/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn 24/6/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn 20/6/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn 19/6/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn 18/6/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn 17/6/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn 14/6/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn 13/6/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn 12/6/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn 11/6/2024:#Update - Installation unable to go ahead due to a blocked duct. Engineer stated that the cable will have to be fed up the interior pillar and through the ceiling to get behind the counter where the lottery machine is | 9/9/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_6/9/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_5/9/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_4/9/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_3/9/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_2/9/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_29/8/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_28/8/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_27/8/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_22/8/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_21/8/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_20/8/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_19/8/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_19/8/2024:01348091 _x000D_16/8/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_15/8/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_14/8/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_13/8/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_12/8/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_9/8/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_8/8/2024:15/05/2024 _x000D_6/8/2024:15/05/2024 _x000D_5/8/2024:15/05/2024 _x000D_2/8/2024:15/05/2024 _x000D_1/8/2024:15/05/2024 _x000D_31/7/2024:15/05/2024 _x000D_31/7/2024:15/05/2024 _x000D_30/7/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_29/7/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_29/7/2024:01348091 _x000D_26/7/2024:01348091 _x000D_24/7/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_23/7/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_22/7/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_22/7/2024:#Update - Request from Allwyn to change from site type 1 to site type 3 mobile only _x000D_19/7/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn _x000D_18/7/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn 17/7/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn 16/7/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn 15/7/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn 12/7/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn 11/7/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn 10/7/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn 9/7/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn 4/7/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn 3/7/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn 2/7/2024:A1 (Site access failure) 1/7/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn 27/6/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn 25/6/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn 24/6/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn 20/6/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn 19/6/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn 18/6/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn 17/6/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn 14/6/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn 13/6/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn 12/6/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn 11/6/2024:#Update - Installation unable to go ahead due to a blocked duct. Engineer stated that the cable will have to be fed up the interior pillar and through the ceiling to get behind the counter where the lottery machine is | 0 | #Update - Request from Allwyn to change from site type 1 to site type 3 mobile only | 2024-05-07 | 07/05/2024: VF to provide an update on the proposal & Allwyn to approve additional charges 29/04/2024: CSL to cancel the current order and raise a new one- to advise what are the cancellation charges. 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFP2300461 | 30013052 | 2.Commissioning | AM | [8 empty] | 2024-07-26 | [7 empty] | 0
1182 | 632866 | 198 | Batch 2 Apr24 | Type 3 | FTTP/Mobile | Godson Food&Win | Kidderminster | DY11 7JT | 2024-05-30 | 6/9/2024:#Update - Allwyn changed to site type 3 _x000D_5/9/2024:#Update - Allwyn changed to site type 3 _x000D_4/9/2024:#Update - Allwyn changed to site type 3 _x000D_3/9/2024:#Update - Allwyn changed to site type 3 _x000D_2/9/2024:#Update - Allwyn changed to site type 3 _x000D_29/8/2024:#Update - Allwyn changed to site type 3 _x000D_28/8/2024:#Update - Allwyn changed to site type 3 _x000D_27/8/2024:#Update - Allwyn changed to site type 3 _x000D_22/8/2024:#Update - Allwyn changed to site type 3 _x000D_21/8/2024:#Update - Allwyn changed to site type 3 _x000D_20/8/2024:#Update - Allwyn changed to site type 3 _x000D_19/8/2024:#Update - Allwyn changed to site type 3 _x000D_19/8/2024:01347972 _x000D_16/8/2024:#Update - Allwyn changed to site type 3 _x000D_15/8/2024:#Update - Allwyn changed to site type 3 _x000D_14/8/2024:#Update - Allwyn changed to site type 3 _x000D_13/8/2024:#Update - Allwyn changed to site type 3 _x000D_12/8/2024:#Update - Allwyn changed to site type 3 _x000D_9/8/2024:#Update - Allwyn changed to site type 3 _x000D_8/8/2024:06/08/2024 _x000D_6/8/2024:22/05/2024 _x000D_5/8/2024:22/05/2024 _x000D_2/8/2024:22/05/2024 _x000D_1/8/2024:22/05/2024 _x000D_31/7/2024:22/05/2024 _x000D_31/7/2024:22/05/2024 _x000D_30/7/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn _x000D_29/7/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn _x000D_29/7/2024:01347972 _x000D_26/7/2024:01347972 _x000D_24/7/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn _x000D_23/7/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn _x000D_22/7/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn _x000D_22/7/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn _x000D_19/7/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_18/7/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_17/7/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_16/7/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_15/7/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_12/7/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_11/7/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_10/7/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_9/7/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_4/7/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_3/7/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_27/6/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_25/6/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_24/6/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_20/6/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_19/6/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_18/6/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_17/6/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_14/6/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_13/6/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_12/6/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_11/6/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn changed to site type 3 _x000D_6/9/2024:#Update - Allwyn changed to site type 3 _x000D_5/9/2024:#Update - Allwyn changed to site type 3 _x000D_4/9/2024:#Update - Allwyn changed to site type 3 _x000D_3/9/2024:#Update - Allwyn changed to site type 3 _x000D_2/9/2024:#Update - Allwyn changed to site type 3 _x000D_29/8/2024:#Update - Allwyn changed to site type 3 _x000D_28/8/2024:#Update - Allwyn changed to site type 3 _x000D_27/8/2024:#Update - Allwyn changed to site type 3 _x000D_22/8/2024:#Update - Allwyn changed to site type 3 _x000D_21/8/2024:#Update - Allwyn changed to site type 3 _x000D_20/8/2024:#Update - Allwyn changed to site type 3 _x000D_19/8/2024:#Update - Allwyn changed to site type 3 _x000D_19/8/2024:01347972 _x000D_16/8/2024:#Update - Allwyn changed to site type 3 _x000D_15/8/2024:#Update - Allwyn changed to site type 3 _x000D_14/8/2024:#Update - Allwyn changed to site type 3 _x000D_13/8/2024:#Update - Allwyn changed to site type 3 _x000D_12/8/2024:#Update - Allwyn changed to site type 3 _x000D_9/8/2024:#Update - Allwyn changed to site type 3 _x000D_8/8/2024:06/08/2024 _x000D_6/8/2024:22/05/2024 _x000D_5/8/2024:22/05/2024 _x000D_2/8/2024:22/05/2024 _x000D_1/8/2024:22/05/2024 _x000D_31/7/2024:22/05/2024 _x000D_31/7/2024:22/05/2024 _x000D_30/7/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn _x000D_29/7/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn _x000D_29/7/2024:01347972 _x000D_26/7/2024:01347972 _x000D_24/7/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn _x000D_23/7/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn _x000D_22/7/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn _x000D_22/7/2024:#Update - order needs to upgrade to Advanced due to survey required. Email sent to VD for authorisation of upgrade from Allwyn _x000D_19/7/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_18/7/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_17/7/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_16/7/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_15/7/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_12/7/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_11/7/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_10/7/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_9/7/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_4/7/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_3/7/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_27/6/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_25/6/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_24/6/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_20/6/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_19/6/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_18/6/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_17/6/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_14/6/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_13/6/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_12/6/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_11/6/2024:0 _x000D_ | 0 | #Update - Allwyn changed to site type 3 | 2024-04-18 | 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFP2300468 | 30013031 | 2.Commissioning | AM | [8 empty] | 2024-08-27 | [7 empty] | 0
1183 | 648522 | 276 | Batch 2 Apr24 | Type 3 | FTTP | Sam's Of Bourne | Lincolnshire | PE10 9EN | 2024-05-31 | 6/9/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_5/9/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_4/9/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_3/9/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_2/9/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_29/8/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_28/8/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_27/8/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_22/8/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_21/8/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_20/8/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_19/8/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_19/8/2024:01352930 _x000D_16/8/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_15/8/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_14/8/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_13/8/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_12/8/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_9/8/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_8/8/2024:09/05/2024 _x000D_6/8/2024:09/05/2024 _x000D_5/8/2024:09/05/2024 _x000D_2/8/2024:09/05/2024 _x000D_1/8/2024:09/05/2024 _x000D_31/7/2024:09/05/2024 _x000D_31/7/2024:09/05/2024 _x000D_30/7/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_29/7/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_29/7/2024:01352930 _x000D_26/7/2024:01352930 _x000D_24/7/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_23/7/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_22/7/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_22/7/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_6/9/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_5/9/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_4/9/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_3/9/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_2/9/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_29/8/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_28/8/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_27/8/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_22/8/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_21/8/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_20/8/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_19/8/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_19/8/2024:01352930 _x000D_16/8/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_15/8/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_14/8/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_13/8/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_12/8/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_9/8/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_8/8/2024:09/05/2024 _x000D_6/8/2024:09/05/2024 _x000D_5/8/2024:09/05/2024 _x000D_2/8/2024:09/05/2024 _x000D_1/8/2024:09/05/2024 _x000D_31/7/2024:09/05/2024 _x000D_31/7/2024:09/05/2024 _x000D_30/7/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_29/7/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_29/7/2024:01352930 _x000D_26/7/2024:01352930 _x000D_24/7/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_23/7/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_22/7/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_22/7/2024:#Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_ | 0 | #Update - Allwyn advised no internal labour will be carried out by the end user themselves. Action - Openreach to investigate if there are any alternative options for the install - CSL will provide further updates | 2024-04-17 | 17/04/2024: Allwyn to make the retailer aware Confirmed 15/04/2024: CSL to provide updates. 19/03/2024: Allwyn to make retailer aware of visit as per the date in column T |  |  | 3.Allwyn to arrange rtr install | VFP2303026 | 30013523 | 2.Commissioning | AM | [8 empty] | 2024-07-25 | [7 empty] | 0
1184 | 651159 | 335 | Batch 3 May24 | Type 1 | SoGEA/Mobile | Purvis News | Washington | NE37 2AL |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_7/6/2024:#Update - On hold until Allwyn can contact the retailer- Missed appointment from 15.05, and Allwyn have not been able to reach the retailer despite a number of attempts. Will review if contact is made before re-appointing _x000D_6/6/2024:#Update - On hold until Allwyn can contact the retailer- Missed appointment from 15.05, and Allwyn have not been able to reach the retailer despite a number of attempts. Will review if contact is made before re-appointing _x000D_5/6/2024:#Update - On hold until Allwyn can contact the retailer- Missed appointment from 15.05, and Allwyn have not been able to reach the retailer despite a number of attempts. Will review if contact is made before re-appointing _x000D_4/6/2024:#Update - On hold until Allwyn can contact the retailer- Missed appointment from 15.05, and Allwyn have not been able to reach the retailer despite a number of attempts. Will review if contact is made before re-appointing _x000D_31/5/2024:#Update - On hold until Allwyn can contact the retailer- Missed appointment from 15.05, and Allwyn have not been able to reach the retailer despite a number of attempts. Will review if contact is made before re-appointing _x000D_30/5/2024:#Update - On hold until Allwyn can contact the retailer- Missed appointment from 15.05, and Allwyn have not been able to reach the retailer despite a number of attempts. Will review if contact is made before re-appointing _x000D_29/5/2024:#Update - On hold until Allwyn can contact the retailer- Missed appointment from 15.05, and Allwyn have not been able to reach the retailer despite a number of attempts. Will review if contact is made before re-appointing _x000D_28/5/2024:#Update - On hold until Allwyn can contact the retailer- Missed appointment from 15.05, and Allwyn have not been able to reach the retailer despite a number of attempts. Will review if contact is made before re-appointing _x000D_16/5/2024:#Update - On hold until Allwyn can contact the retailer- Missed appointment from 15.05, and Allwyn have not been able to reach the retailer despite a number of attempts. Will review if contact is made before re-appointing 10/5/2024:#Update - Action for Allwyn - Installation has now been amended to 15/05 AM. Please speak with the retailer regarding installation details and confirm to CSL if 15/05 is a suitable date. 02/05/2024: Installation has now been amended to 15/05 AM08/04/2024: New order added to report | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_7/6/2024:#Update - On hold until Allwyn can contact the retailer- Missed appointment from 15.05, and Allwyn have not been able to reach the retailer despite a number of attempts. Will review if contact is made before re-appointing _x000D_6/6/2024:#Update - On hold until Allwyn can contact the retailer- Missed appointment from 15.05, and Allwyn have not been able to reach the retailer despite a number of attempts. Will review if contact is made before re-appointing _x000D_5/6/2024:#Update - On hold until Allwyn can contact the retailer- Missed appointment from 15.05, and Allwyn have not been able to reach the retailer despite a number of attempts. Will review if contact is made before re-appointing _x000D_4/6/2024:#Update - On hold until Allwyn can contact the retailer- Missed appointment from 15.05, and Allwyn have not been able to reach the retailer despite a number of attempts. Will review if contact is made before re-appointing _x000D_31/5/2024:#Update - On hold until Allwyn can contact the retailer- Missed appointment from 15.05, and Allwyn have not been able to reach the retailer despite a number of attempts. Will review if contact is made before re-appointing _x000D_30/5/2024:#Update - On hold until Allwyn can contact the retailer- Missed appointment from 15.05, and Allwyn have not been able to reach the retailer despite a number of attempts. Will review if contact is made before re-appointing _x000D_29/5/2024:#Update - On hold until Allwyn can contact the retailer- Missed appointment from 15.05, and Allwyn have not been able to reach the retailer despite a number of attempts. Will review if contact is made before re-appointing _x000D_28/5/2024:#Update - On hold until Allwyn can contact the retailer- Missed appointment from 15.05, and Allwyn have not been able to reach the retailer despite a number of attempts. Will review if contact is made before re-appointing _x000D_16/5/2024:#Update - On hold until Allwyn can contact the retailer- Missed appointment from 15.05, and Allwyn have not been able to reach the retailer despite a number of attempts. Will review if contact is made before re-appointing 10/5/2024:#Update - Action for Allwyn - Installation has now been amended to 15/05 AM. Please speak with the retailer regarding installation details and confirm to CSL if 15/05 is a suitable date. 02/05/2024: Installation has now been amended to 15/05 AM08/04/2024: New order added to report | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2300532 | 30013225 | 1.Provisioning | AM |  | 2024-05-01 |  |  | 0 | [11 empty] | 0
1185 | 653900 | 505 | Batch 3 May24 | Type 3 | SOGEA | TG Convenience St Katherines | London | E1W 2BN | 2024-05-30 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:Port available but TRFS/CRFS dates is Unknown CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_14/6/2024:Port available but TRFS/CRFS dates is Unknown CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_13/6/2024:Port available but TRFS/CRFS dates is Unknown CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/6/2024:Port available but TRFS/CRFS dates is Unknown CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:Port available but TRFS/CRFS dates is Unknown CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_14/6/2024:Port available but TRFS/CRFS dates is Unknown CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_13/6/2024:Port available but TRFS/CRFS dates is Unknown CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/6/2024:Port available but TRFS/CRFS dates is Unknown CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 0 | 0 |  |  |  |  | 3.Allwyn to arrange rtr install | VFP2300702 | 30013395 | 2.Commissioning | [5 empty] | Not Applicable |  |  |  | 2024-07-10 | [7 empty] | 0
1186 | 479609 | 508 | Batch 3 May24 | Type 1 | SoGEA/Mobile | Londis Otley Road | Bradford | BD2 4QL | 2024-05-31 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_02/05/2024: New order added to report | 0 | 0 | 2024-05-31 | 31/05/24: CSL to provide an update |  |  | 5.CSL | VFS1017448 | 30013398 | 1.Provisioning | AM |  | 2024-05-20 |  |  | 0 | [11 empty] | 0
1187 | 667091 | 544 | Batch 3 May24 | Type 1 | SOGEA | Rosys | SHEFFIELD | S13 8HN | 2024-05-30 | 6/9/2024:#Update order has been reraised for 6/09 AM _x000D_5/9/2024:#Update order has been reraised for 6/09 AM _x000D_4/9/2024:#Update order has been reraised for 6/09 AM _x000D_3/9/2024:#Update order has been reraised for 6/09 AM _x000D_2/9/2024:#Update order has been reraised for 6/09 AM _x000D_29/8/2024:#Update order has been reraised for 6/09 AM _x000D_28/8/2024:#Update order has been reraised for 6/09 AM _x000D_27/8/2024:#Update order has been reraised for 6/09 AM _x000D_22/8/2024:#Update order has been reraised for 6/09 AM _x000D_21/8/2024:#Update order has been reraised for 6/09 AM _x000D_20/8/2024:#Update order has been reraised for 6/09 AM _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 9/9/2024:#Update order has been reraised for 6/09 AM _x000D_6/9/2024:#Update order has been reraised for 6/09 AM _x000D_5/9/2024:#Update order has been reraised for 6/09 AM _x000D_4/9/2024:#Update order has been reraised for 6/09 AM _x000D_3/9/2024:#Update order has been reraised for 6/09 AM _x000D_2/9/2024:#Update order has been reraised for 6/09 AM _x000D_29/8/2024:#Update order has been reraised for 6/09 AM _x000D_28/8/2024:#Update order has been reraised for 6/09 AM _x000D_27/8/2024:#Update order has been reraised for 6/09 AM _x000D_22/8/2024:#Update order has been reraised for 6/09 AM _x000D_21/8/2024:#Update order has been reraised for 6/09 AM _x000D_20/8/2024:#Update order has been reraised for 6/09 AM _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 0 | #Update order has been reraised for 6/09 AM |  |  |  |  | 2.Allwyn to arrange access | VFP2424552 | 30013434 | 1.Provisioning | AM |  | 2024-05-23 | 2024-09-06 |  | 0 | [11 empty] | 0
1188 | 459868 | 624 | Batch 3 May24 | Type 1 | SoGEA/Mobile | Asha General Stores | LEICESTER | LE5 3TP | 2024-06-07 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 23/7/2024:0 22/7/2024:0 22/7/2024:0 19/7/2024:0 18/7/2024:0 17/7/2024:0 16/7/2024:0 5/6/2024 - Allwyn requested to have the retailer ID changed from 660027 to 670706 7/6/2024:0 6/6/2024:0 5/6/2024:0 4/6/2024:0 31/5/2024:Update: Order Amended 30/5/2024:Update: Order Amended 29/5/2024:Update: Order Amended 28/5/2024:Update: Order Amended 20/5/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. 10/5/2024:0 08/04/2024: New order added to report | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 23/7/2024:0 22/7/2024:0 22/7/2024:0 19/7/2024:0 18/7/2024:0 17/7/2024:0 16/7/2024:0 5/6/2024 - Allwyn requested to have the retailer ID changed from 660027 to 670706 7/6/2024:0 6/6/2024:0 5/6/2024:0 4/6/2024:0 31/5/2024:Update: Order Amended 30/5/2024:Update: Order Amended 29/5/2024:Update: Order Amended 28/5/2024:Update: Order Amended 20/5/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. 10/5/2024:0 08/04/2024: New order added to report | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2300821 | 30013514 | 1.Provisioning | AM |  | 2024-05-10 |  |  | 0 | [11 empty] | 0
1189 | 670706 | 921 | Batch 3 May24 | Type 1 | SOGEA | Dunston Convenience Store | Dunston | NE11 9AB | 2024-06-07 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:#Update - Openreach have advised that Socket is in 'No trc banding on job, nte5 in office next to existing socket'. Socket Relocation might be required. _x000D_21/8/2024:#Update - Openreach have advised that Socket is in 'No trc banding on job, nte5 in office next to existing socket'. Socket Relocation might be required. _x000D_20/8/2024:#Update - Openreach have advised that Socket is in 'No trc banding on job, nte5 in office next to existing socket'. Socket Relocation might be required. _x000D_19/8/2024:#Update - Openreach have advised that Socket is in 'No trc banding on job, nte5 in office next to existing socket'. Socket Relocation might be required. _x000D_19/8/2024:01592277 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 23/7/2024:0 22/7/2024:0 22/7/2024:0 19/7/2024:0 18/7/2024:0 17/7/2024:0 16/7/2024:0 15/7/2024:0 12/7/2024:0 11/7/2024:0 10/7/2024:0 9/7/2024:0 4/7/2024:0 3/7/2024:0 2/7/2024:0 1/7/2024:0 27/6/2024:0 25/6/2024:0 24/6/2024:0 20/6/2024:0 19/6/2024:0 18/6/2024:0 17/6/2024:0 14/6/2024:0 13/6/2024:0 12/6/2024:0 11/6/2024:0 10/6/2024:0 7/6/2024:0 6/6/2024:0 5/6/2024 - Allwyn requested to have the retailer ID changed from 660027 to 670706 4/6/2024:0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:#Update - Openreach have advised that Socket is in 'No trc banding on job, nte5 in office next to existing socket'. Socket Relocation might be required. _x000D_21/8/2024:#Update - Openreach have advised that Socket is in 'No trc banding on job, nte5 in office next to existing socket'. Socket Relocation might be required. _x000D_20/8/2024:#Update - Openreach have advised that Socket is in 'No trc banding on job, nte5 in office next to existing socket'. Socket Relocation might be required. _x000D_19/8/2024:#Update - Openreach have advised that Socket is in 'No trc banding on job, nte5 in office next to existing socket'. Socket Relocation might be required. _x000D_19/8/2024:01592277 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 23/7/2024:0 22/7/2024:0 22/7/2024:0 19/7/2024:0 18/7/2024:0 17/7/2024:0 16/7/2024:0 15/7/2024:0 12/7/2024:0 11/7/2024:0 10/7/2024:0 9/7/2024:0 4/7/2024:0 3/7/2024:0 2/7/2024:0 1/7/2024:0 27/6/2024:0 25/6/2024:0 24/6/2024:0 20/6/2024:0 19/6/2024:0 18/6/2024:0 17/6/2024:0 14/6/2024:0 13/6/2024:0 12/6/2024:0 11/6/2024:0 10/6/2024:0 7/6/2024:0 6/6/2024:0 5/6/2024 - Allwyn requested to have the retailer ID changed from 660027 to 670706 4/6/2024:0 | 0 | 0 | 2024-05-20 | 20/05/2024: Allwyn to confirm the new date |  |  | 3.Allwyn to arrange rtr install | VFP2301118 | 30013811 | 2.Commissioning | AM | [8 empty] | 2024-08-16 | [7 empty] | 0
1190 | 654612 | 940 | Batch 3 May24 | Type 1 | SoGEA/Mobile | Jac's News | St. Helens | WA10 1BD | 2024-06-07 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_18/7/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_17/7/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_16/7/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_15/7/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_12/7/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_11/7/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_10/7/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_9/7/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_4/7/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_3/7/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_27/6/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_25/6/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_24/6/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_20/6/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_19/6/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_18/6/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_17/6/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_14/6/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_13/6/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_12/6/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_18/7/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_17/7/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_16/7/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_15/7/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_12/7/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_11/7/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_10/7/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_9/7/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_4/7/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_3/7/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_27/6/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_25/6/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_24/6/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_20/6/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_19/6/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_18/6/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_17/6/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_14/6/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_13/6/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_12/6/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2301137 | 30013830 | 1.Provisioning | AM |  | 2024-05-20 |  |  | 0 | [11 empty] | 0
1191 | 261776 | 958 | Batch 3 May24 | Type 3 |  | RMJ Food and Wine | LONDON | E3 4PH | 2024-06-07 | 6/9/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_5/9/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_4/9/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_3/9/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_2/9/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_29/8/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_28/8/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_27/8/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_22/8/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_21/8/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_20/8/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_19/8/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_19/8/2024:01402920 _x000D_16/8/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_15/8/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_14/8/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_13/8/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_12/8/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_9/8/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_8/8/2024:28/05/2024 _x000D_6/8/2024:28/05/2024 _x000D_5/8/2024:28/05/2024 _x000D_2/8/2024:28/05/2024 _x000D_1/8/2024:28/05/2024 _x000D_31/7/2024:28/05/2024 _x000D_31/7/2024:28/05/2024 _x000D_30/7/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_29/7/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_29/7/2024:01402920 _x000D_26/7/2024:01402920 _x000D_24/7/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_23/7/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_22/7/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_22/7/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_19/7/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_18/7/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_17/7/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_16/7/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_15/7/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_12/7/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_11/7/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_10/7/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_9/7/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_4/7/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_3/7/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_27/6/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_25/6/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_24/6/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_20/6/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_19/6/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_18/6/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_17/6/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_14/6/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_13/6/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_12/6/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_6/9/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_5/9/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_4/9/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_3/9/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_2/9/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_29/8/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_28/8/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_27/8/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_22/8/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_21/8/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_20/8/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_19/8/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_19/8/2024:01402920 _x000D_16/8/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_15/8/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_14/8/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_13/8/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_12/8/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_9/8/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_8/8/2024:28/05/2024 _x000D_6/8/2024:28/05/2024 _x000D_5/8/2024:28/05/2024 _x000D_2/8/2024:28/05/2024 _x000D_1/8/2024:28/05/2024 _x000D_31/7/2024:28/05/2024 _x000D_31/7/2024:28/05/2024 _x000D_30/7/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_29/7/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_29/7/2024:01402920 _x000D_26/7/2024:01402920 _x000D_24/7/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_23/7/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_22/7/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_22/7/2024:#Update - Allwyn have requested a downgrade from site type 1 to site type 3 _x000D_19/7/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_18/7/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_17/7/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_16/7/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_15/7/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_12/7/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_11/7/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_10/7/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_9/7/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_4/7/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_3/7/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_27/6/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_25/6/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_24/6/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_20/6/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_19/6/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_18/6/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_17/6/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_14/6/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_13/6/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_12/6/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update - Allwyn have requested a downgrade from site type 1 to site type 3 | 2024-05-24 | 23/05/2024: Allwyn to procceed with type 3 with SG 22/05/24: Allwyn to review approval for advance upgrade and confirm 21/05/24: CSL to provide an update |  |  | 3.Allwyn to arrange rtr install | VFP2301155 | 30013848 | 2.Commissioning | [9 empty] | 2024-07-10 | [7 empty] | 0
1192 | 665338 | 1086 | Batch 3 May24 | Type 3 | SOGEA | Hendon Central Post Office | LONDON | NW4 3XH | 2024-06-07 | 6/9/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_5/9/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_4/9/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_3/9/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_2/9/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_29/8/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_28/8/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_27/8/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_22/8/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_21/8/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_20/8/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_19/8/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_19/8/2024:01407421 _x000D_16/8/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_15/8/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_14/8/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_13/8/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_12/8/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_9/8/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_8/8/2024:07/06/2024 _x000D_6/8/2024:07/06/2024 _x000D_5/8/2024:07/06/2024 _x000D_2/8/2024:07/06/2024 _x000D_1/8/2024:07/06/2024 _x000D_31/7/2024:07/06/2024 _x000D_31/7/2024:07/06/2024 _x000D_30/7/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_29/7/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_29/7/2024:01407421 _x000D_26/7/2024:01407421 _x000D_24/7/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_23/7/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_22/7/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_22/7/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_19/7/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_18/7/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_17/7/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_16/7/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_15/7/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_12/7/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_11/7/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_10/7/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_9/7/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_4/7/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_3/7/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_27/6/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_25/6/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_24/6/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_20/6/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_19/6/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_18/6/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_17/6/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_14/6/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_13/6/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_12/6/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_6/9/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_5/9/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_4/9/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_3/9/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_2/9/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_29/8/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_28/8/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_27/8/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_22/8/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_21/8/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_20/8/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_19/8/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_19/8/2024:01407421 _x000D_16/8/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_15/8/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_14/8/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_13/8/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_12/8/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_9/8/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_8/8/2024:07/06/2024 _x000D_6/8/2024:07/06/2024 _x000D_5/8/2024:07/06/2024 _x000D_2/8/2024:07/06/2024 _x000D_1/8/2024:07/06/2024 _x000D_31/7/2024:07/06/2024 _x000D_31/7/2024:07/06/2024 _x000D_30/7/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_29/7/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_29/7/2024:01407421 _x000D_26/7/2024:01407421 _x000D_24/7/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_23/7/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_22/7/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_22/7/2024:#Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. _x000D_19/7/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_18/7/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_17/7/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_16/7/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_15/7/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_12/7/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_11/7/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_10/7/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_9/7/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_4/7/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_3/7/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_27/6/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_25/6/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_24/6/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_20/6/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_19/6/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_18/6/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_17/6/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_14/6/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_13/6/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_12/6/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update Site type changed to Type 3 "Mobile-only" solution following decision from Allwyn. |  |  |  |  | 3.Allwyn to arrange rtr install | VFP2301283 | 30013976 | 2.Commissioning | AM | [8 empty] | 2024-08-21 | [7 empty] | 0
1193 | 665201 | 1196 | Batch 3 May24 | Type 3 | FTTP/Mobile | PINNER NEWS & PO | BEDFORD | MK41 8HF | 2024-06-07 | 6/9/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_5/9/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_4/9/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_3/9/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_2/9/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_29/8/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_28/8/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_27/8/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_22/8/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_21/8/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_20/8/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_19/8/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_19/8/2024:01398261 _x000D_16/8/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_15/8/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_14/8/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_13/8/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_12/8/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_9/8/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_8/8/2024:20/05/2024 _x000D_6/8/2024:20/05/2024 _x000D_5/8/2024:20/05/2024 _x000D_2/8/2024:20/05/2024 _x000D_1/8/2024:20/05/2024 _x000D_31/7/2024:20/05/2024 _x000D_31/7/2024:20/05/2024 _x000D_30/7/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_29/7/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_29/7/2024:01398261 _x000D_26/7/2024:01398261 _x000D_24/7/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_23/7/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_22/7/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_22/7/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_6/9/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_5/9/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_4/9/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_3/9/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_2/9/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_29/8/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_28/8/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_27/8/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_22/8/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_21/8/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_20/8/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_19/8/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_19/8/2024:01398261 _x000D_16/8/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_15/8/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_14/8/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_13/8/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_12/8/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_9/8/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_8/8/2024:20/05/2024 _x000D_6/8/2024:20/05/2024 _x000D_5/8/2024:20/05/2024 _x000D_2/8/2024:20/05/2024 _x000D_1/8/2024:20/05/2024 _x000D_31/7/2024:20/05/2024 _x000D_31/7/2024:20/05/2024 _x000D_30/7/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_29/7/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_29/7/2024:01398261 _x000D_26/7/2024:01398261 _x000D_24/7/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_23/7/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_22/7/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_22/7/2024:#Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update- Cancelled Order, Allwyn has requested that the site be downgraded to T3. 20.03 | 2024-05-17 | 17/05/2024: CSL to provide an update |  |  | 3.Allwyn to arrange rtr install | VFP2331703 | 30014086 | 2.Commissioning | AM |  |  |  |  | 0 |  |  |  | 2024-08-15 | [7 empty] | 0
1194 | 266849 | 1233 | Batch 3 May24 | Type 1 | SoGEA/Mobile | Londis | LONDON | E16 4HQ | 2024-06-07 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:20/07/2024 09:01 _x000D_24/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_23/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_18/7/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_17/7/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_16/7/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_15/7/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_12/7/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_11/7/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_10/7/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_9/7/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_4/7/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_3/7/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_27/6/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_25/6/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_24/6/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_20/6/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_19/6/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_18/6/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_17/6/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_14/6/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_13/6/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_12/6/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:20/07/2024 09:01 _x000D_24/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_23/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_18/7/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_17/7/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_16/7/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_15/7/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_12/7/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_11/7/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_10/7/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_9/7/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_4/7/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_3/7/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_2/7/2024:A3 (installation issue) _x000D_1/7/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_27/6/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_25/6/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_24/6/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_20/6/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_19/6/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_18/6/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_17/6/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_14/6/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_13/6/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_12/6/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFS1058504 | 30014123 | 1.Provisioning | AM |  |  |  |  | 0 | [11 empty] | 0