1195 | 605407 | 1280 | Batch 3 May24 | Type 3 | FTTP | Nisa | Ballymena | BT43 5JH | 2024-06-07 | 6/9/2024:#Update Moving to ST3 as cable routing goes through an ATM bank - the engineer requires access behind the cash machine which will need to be decommissioned and emptied before installation. _x000D_5/9/2024:#Update Moving to ST3 as cable routing goes through an ATM bank - the engineer requires access behind the cash machine which will need to be decommissioned and emptied before installation. _x000D_4/9/2024:#Update Moving to ST3 as cable routing goes through an ATM bank - the engineer requires access behind the cash machine which will need to be decommissioned and emptied before installation. _x000D_3/9/2024:#Update Moving to ST3 as cable routing goes through an ATM bank - the engineer requires access behind the cash machine which will need to be decommissioned and emptied before installation. _x000D_2/9/2024:#Update Moving to ST3 as cable routing goes through an ATM bank - the engineer requires access behind the cash machine which will need to be decommissioned and emptied before installation. _x000D_29/8/2024:#Update Moving to ST3 as cable routing goes through an ATM bank - the engineer requires access behind the cash machine which will need to be decommissioned and emptied before installation. _x000D_28/8/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_27/8/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_22/8/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_21/8/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_20/8/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_19/8/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_19/8/2024:01405451 _x000D_16/8/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_15/8/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_14/8/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_13/8/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_12/8/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_9/8/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_8/8/2024:24/05/2024 _x000D_6/8/2024:24/05/2024 _x000D_5/8/2024:24/05/2024 _x000D_2/8/2024:24/05/2024 _x000D_1/8/2024:24/05/2024 _x000D_31/7/2024:24/05/2024 _x000D_31/7/2024:24/05/2024 _x000D_30/7/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_29/7/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_29/7/2024:01405451 _x000D_26/7/2024:01405451 _x000D_24/7/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_23/7/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_22/7/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_22/7/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_19/7/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update Moving to ST3 as cable routing goes through an ATM bank - the engineer requires access behind the cash machine which will need to be decommissioned and emptied before installation. _x000D_6/9/2024:#Update Moving to ST3 as cable routing goes through an ATM bank - the engineer requires access behind the cash machine which will need to be decommissioned and emptied before installation. _x000D_5/9/2024:#Update Moving to ST3 as cable routing goes through an ATM bank - the engineer requires access behind the cash machine which will need to be decommissioned and emptied before installation. _x000D_4/9/2024:#Update Moving to ST3 as cable routing goes through an ATM bank - the engineer requires access behind the cash machine which will need to be decommissioned and emptied before installation. _x000D_3/9/2024:#Update Moving to ST3 as cable routing goes through an ATM bank - the engineer requires access behind the cash machine which will need to be decommissioned and emptied before installation. _x000D_2/9/2024:#Update Moving to ST3 as cable routing goes through an ATM bank - the engineer requires access behind the cash machine which will need to be decommissioned and emptied before installation. _x000D_29/8/2024:#Update Moving to ST3 as cable routing goes through an ATM bank - the engineer requires access behind the cash machine which will need to be decommissioned and emptied before installation. _x000D_28/8/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_27/8/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_22/8/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_21/8/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_20/8/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_19/8/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_19/8/2024:01405451 _x000D_16/8/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_15/8/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_14/8/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_13/8/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_12/8/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_9/8/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_8/8/2024:24/05/2024 _x000D_6/8/2024:24/05/2024 _x000D_5/8/2024:24/05/2024 _x000D_2/8/2024:24/05/2024 _x000D_1/8/2024:24/05/2024 _x000D_31/7/2024:24/05/2024 _x000D_31/7/2024:24/05/2024 _x000D_30/7/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_29/7/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_29/7/2024:01405451 _x000D_26/7/2024:01405451 _x000D_24/7/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_23/7/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_22/7/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_22/7/2024:#Update - Action on Allwyn to agree whether this site requires a advanced upgrade or a change to site type 3. _x000D_19/7/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update Moving to ST3 as cable routing goes through an ATM bank - the engineer requires access behind the cash machine which will need to be decommissioned and emptied before installation. | 2024-05-23 | 23/05/24: Allwyn to arrange access on the new date |  |  | 3.Allwyn to arrange rtr install | VFP2301477 | 30014170 | 2.Commissioning | [9 empty] | 2024-08-27 | [7 empty] | 0
1196 | 469205 | 1281 | Batch 3 May24 | Type 1 | FTTP/Mobile | Nisa Local | LONDONDERRY | BT48 8LB | 2024-06-07 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:Line Identified is not compatible with the requested service _x000D_21/8/2024:Line Identified is not compatible with the requested service _x000D_20/8/2024:Line Identified is not compatible with the requested service _x000D_19/8/2024:Line Identified is not compatible with the requested service _x000D_19/8/2024:15/08/2024 12:01 _x000D_16/8/2024:Line Identified is not compatible with the requested service _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_13/8/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_23/7/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:0 _x000D_10/7/2024:Update: Order progressed to Openreach Network Plan null team for routing confirmation CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_9/7/2024:Update: Order progressed to Openreach Network Plan null team for routing confirmation CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/7/2024:Update: Order progressed to Openreach Network Plan null team for routing confirmation CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_3/7/2024:Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 04/07/2024 for further updates. CSL Note: Invalid appointment _x000D_2/7/2024:0 _x000D_1/7/2024:Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 01/07/2024 for further updates. CSL Note: Invalid appointment _x000D_27/6/2024:Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 01/07/2024 for further updates. CSL Note: Invalid appointment _x000D_25/6/2024:Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 01/07/2024 for further updates. CSL Note: Invalid appointment _x000D_24/6/2024:Your order has been delayed. Dig work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 25/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot recei _x000D_20/6/2024:Your order has been delayed. Dig work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 25/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot recei _x000D_19/6/2024:Your order has been delayed. Dig work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 25/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot recei _x000D_18/6/2024:Your order has been delayed. Dig work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 25/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot recei _x000D_17/6/2024:Supplier Delay: Issues relating to permission to provide the network, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_14/6/2024:Supplier Delay: Issues relating to permission to provide the network, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_13/6/2024:Your order has been delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 24/06/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment slot rec _x000D_12/6/2024:Your order has been delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 24/06/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment slot rec _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:Line Identified is not compatible with the requested service _x000D_21/8/2024:Line Identified is not compatible with the requested service _x000D_20/8/2024:Line Identified is not compatible with the requested service _x000D_19/8/2024:Line Identified is not compatible with the requested service _x000D_19/8/2024:15/08/2024 12:01 _x000D_16/8/2024:Line Identified is not compatible with the requested service _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_13/8/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_23/7/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:0 _x000D_10/7/2024:Update: Order progressed to Openreach Network Plan null team for routing confirmation CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_9/7/2024:Update: Order progressed to Openreach Network Plan null team for routing confirmation CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/7/2024:Update: Order progressed to Openreach Network Plan null team for routing confirmation CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_3/7/2024:Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 04/07/2024 for further updates. CSL Note: Invalid appointment _x000D_2/7/2024:0 _x000D_1/7/2024:Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 01/07/2024 for further updates. CSL Note: Invalid appointment _x000D_27/6/2024:Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 01/07/2024 for further updates. CSL Note: Invalid appointment _x000D_25/6/2024:Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 01/07/2024 for further updates. CSL Note: Invalid appointment _x000D_24/6/2024:Your order has been delayed. Dig work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 25/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot recei _x000D_20/6/2024:Your order has been delayed. Dig work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 25/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot recei _x000D_19/6/2024:Your order has been delayed. Dig work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 25/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot recei _x000D_18/6/2024:Your order has been delayed. Dig work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 25/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot recei _x000D_17/6/2024:Supplier Delay: Issues relating to permission to provide the network, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_14/6/2024:Supplier Delay: Issues relating to permission to provide the network, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_13/6/2024:Your order has been delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 24/06/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment slot rec _x000D_12/6/2024:Your order has been delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 24/06/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment slot rec _x000D_0 | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFS1058527 | 30014171 | 1.Provisioning | AM |  | 2024-08-12 | 2024-08-30 |  | 0 | [11 empty] | 0
1197 | 468980 | 1361 | Batch 4 Jun24 | Type 3 | FTTP/Mobile | Mace | LISBURN | BT27 4NX | 2024-06-07 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_27/6/2024:#Update Delays due to capacity issues - updates to follow _x000D_25/6/2024:#Update Delays due to capacity issues - updates to follow _x000D_24/6/2024:#Update Delays due to capacity issues - updates to follow _x000D_20/6/2024:#Update Delays due to capacity issues - updates to follow _x000D_19/6/2024:#Update Delays due to capacity issues - updates to follow _x000D_18/6/2024:#Update Delays due to capacity issues - updates to follow _x000D_17/6/2024:#Update Delays due to capacity issues - updates to follow _x000D_14/6/2024:#Update Delays due to capacity issues - updates to follow _x000D_13/6/2024:#Update Delays due to capacity issues - updates to follow _x000D_12/6/2024:#Update Delays due to capacity issues - updates to follow _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_27/6/2024:#Update Delays due to capacity issues - updates to follow _x000D_25/6/2024:#Update Delays due to capacity issues - updates to follow _x000D_24/6/2024:#Update Delays due to capacity issues - updates to follow _x000D_20/6/2024:#Update Delays due to capacity issues - updates to follow _x000D_19/6/2024:#Update Delays due to capacity issues - updates to follow _x000D_18/6/2024:#Update Delays due to capacity issues - updates to follow _x000D_17/6/2024:#Update Delays due to capacity issues - updates to follow _x000D_14/6/2024:#Update Delays due to capacity issues - updates to follow _x000D_13/6/2024:#Update Delays due to capacity issues - updates to follow _x000D_12/6/2024:#Update Delays due to capacity issues - updates to follow _x000D_11/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | 0 | 2024-05-31 | 31/05/24: CSL to provide an update |  |  | 3.Allwyn to arrange rtr install | VFP2338486 | 30015563 | 2.Commissioning | AM |  |  |  |  | 0 |  |  |  | 2024-08-19 | [7 empty] | 0
1198 | 487033 | 1618 | Batch 4 Jun24 | Type 1 | FTTP/Mobile | Spar Maxol | Belfast | BT14 7EE | 2024-06-07 | 6/9/2024:#Update order delayed, update 11/07 _x000D_5/9/2024:#Update order delayed, update 11/07 _x000D_4/9/2024:#Update order delayed, update 11/07 _x000D_3/9/2024:#Update order delayed, update 11/07 _x000D_2/9/2024:#Update order delayed, update 11/07 _x000D_29/8/2024:#Update order delayed, update 11/07 _x000D_28/8/2024:#Update order delayed, update 11/07 _x000D_27/8/2024:#Update order delayed, update 11/07 _x000D_22/8/2024:#Update order delayed, update 11/07 _x000D_21/8/2024:#Update order delayed, update 11/07 _x000D_20/8/2024:#Update order delayed, update 11/07 _x000D_19/8/2024:#Update order delayed, update 11/07 _x000D_19/8/2024:01469307 _x000D_16/8/2024:#Update order delayed, update 11/07 _x000D_15/8/2024:#Update order delayed, update 11/07 _x000D_14/8/2024:#Update order delayed, update 11/07 _x000D_13/8/2024:#Update order delayed, update 11/07 _x000D_12/8/2024:#Update order delayed, update 11/07 _x000D_9/8/2024:#Update order delayed, update 11/07 _x000D_8/8/2024:05/07/2024 _x000D_6/8/2024:05/07/2024 _x000D_5/8/2024:05/07/2024 _x000D_2/8/2024:05/07/2024 _x000D_1/8/2024:05/07/2024 _x000D_31/7/2024:05/07/2024 _x000D_31/7/2024:05/07/2024 _x000D_30/7/2024:#Update order delayed, update 11/07 _x000D_29/7/2024:#Update order delayed, update 11/07 _x000D_29/7/2024:01469307 _x000D_26/7/2024:01469307 _x000D_24/7/2024:#Update order delayed, update 11/07 _x000D_23/7/2024:#Update order delayed, update 11/07 _x000D_22/7/2024:#Update order delayed, update 11/07 _x000D_22/7/2024:#Update order delayed, update 11/07 _x000D_4/7/2024:#Update - The appointment has been delayed due to loss of light in fibre, multiskilled engineer required and our Suppliers have given us a review date of 09/07/2024 _x000D_3/7/2024:#Update - The appointment has been delayed due to loss of light in fibre, multiskilled engineer required and our Suppliers have given us a review date of 09/07/2024 _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - The appointment has been delayed due to loss of light in fibre, multiskilled engineer required and our Suppliers have given us a review date of 09/07/2024 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:Planning required – no committed date yet 14/6/2024:0 13/6/2024:0 12/6/2024:0 10/6/2024:0 7/6/2024:0 6/6/2024:0 5/6/2024:0 4/6/2024:Your order has been delayed due to a sales query raised by our supplier. There are several existing line at premises. Please confirm with end user that a new line is required to progress the order further. CSL Note: Invalid appointment slot received CSL N 31/5/2024:Your order has been delayed due to a sales query raised by our supplier. There are several existing line at premises. Please confirm with end user that a new line is required to progress the order further. CSL Note: Invalid appointment slot received CSL N 30/5/2024:Your order has been delayed due to a sales query raised by our supplier. There are several existing line at premises. Please confirm with end user that a new line is required to progress the order further. CSL Note: Invalid appointment slot received CSL N 29/5/2024:Your order has been delayed due to a sales query raised by our supplier. There are several existing line at premises. Please confirm with end user that a new line is required to progress the order further. CSL Note: Invalid appointment slot received CSL N 28/5/2024:0 10/5/2024:0 02/05/2024: New order added to report | 9/9/2024:#Update order delayed, update 11/07 _x000D_6/9/2024:#Update order delayed, update 11/07 _x000D_5/9/2024:#Update order delayed, update 11/07 _x000D_4/9/2024:#Update order delayed, update 11/07 _x000D_3/9/2024:#Update order delayed, update 11/07 _x000D_2/9/2024:#Update order delayed, update 11/07 _x000D_29/8/2024:#Update order delayed, update 11/07 _x000D_28/8/2024:#Update order delayed, update 11/07 _x000D_27/8/2024:#Update order delayed, update 11/07 _x000D_22/8/2024:#Update order delayed, update 11/07 _x000D_21/8/2024:#Update order delayed, update 11/07 _x000D_20/8/2024:#Update order delayed, update 11/07 _x000D_19/8/2024:#Update order delayed, update 11/07 _x000D_19/8/2024:01469307 _x000D_16/8/2024:#Update order delayed, update 11/07 _x000D_15/8/2024:#Update order delayed, update 11/07 _x000D_14/8/2024:#Update order delayed, update 11/07 _x000D_13/8/2024:#Update order delayed, update 11/07 _x000D_12/8/2024:#Update order delayed, update 11/07 _x000D_9/8/2024:#Update order delayed, update 11/07 _x000D_8/8/2024:05/07/2024 _x000D_6/8/2024:05/07/2024 _x000D_5/8/2024:05/07/2024 _x000D_2/8/2024:05/07/2024 _x000D_1/8/2024:05/07/2024 _x000D_31/7/2024:05/07/2024 _x000D_31/7/2024:05/07/2024 _x000D_30/7/2024:#Update order delayed, update 11/07 _x000D_29/7/2024:#Update order delayed, update 11/07 _x000D_29/7/2024:01469307 _x000D_26/7/2024:01469307 _x000D_24/7/2024:#Update order delayed, update 11/07 _x000D_23/7/2024:#Update order delayed, update 11/07 _x000D_22/7/2024:#Update order delayed, update 11/07 _x000D_22/7/2024:#Update order delayed, update 11/07 _x000D_4/7/2024:#Update - The appointment has been delayed due to loss of light in fibre, multiskilled engineer required and our Suppliers have given us a review date of 09/07/2024 _x000D_3/7/2024:#Update - The appointment has been delayed due to loss of light in fibre, multiskilled engineer required and our Suppliers have given us a review date of 09/07/2024 _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - The appointment has been delayed due to loss of light in fibre, multiskilled engineer required and our Suppliers have given us a review date of 09/07/2024 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:Planning required – no committed date yet 14/6/2024:0 13/6/2024:0 12/6/2024:0 10/6/2024:0 7/6/2024:0 6/6/2024:0 5/6/2024:0 4/6/2024:Your order has been delayed due to a sales query raised by our supplier. There are several existing line at premises. Please confirm with end user that a new line is required to progress the order further. CSL Note: Invalid appointment slot received CSL N 31/5/2024:Your order has been delayed due to a sales query raised by our supplier. There are several existing line at premises. Please confirm with end user that a new line is required to progress the order further. CSL Note: Invalid appointment slot received CSL N 30/5/2024:Your order has been delayed due to a sales query raised by our supplier. There are several existing line at premises. Please confirm with end user that a new line is required to progress the order further. CSL Note: Invalid appointment slot received CSL N 29/5/2024:Your order has been delayed due to a sales query raised by our supplier. There are several existing line at premises. Please confirm with end user that a new line is required to progress the order further. CSL Note: Invalid appointment slot received CSL N 28/5/2024:0 10/5/2024:0 02/05/2024: New order added to report | 0 | #Update order delayed, update 11/07 | 2024-06-07 | 31/05/24: CSL to provide an update |  |  | 5.CSL | VFP2338566 | 30015640 | 1.Provisioning | AM |  | 2024-08-15 | 2024-08-15 |  | 0 | [11 empty] | 0
1199 | 670366 | 1721 | Batch 4 Jun24 | Type 3 | FTTP/Mobile | Russells Food & Drink | Crumlin | BT29 4UR | 2024-06-07 | 6/9/2024:#Update - changing to a site type 3 / mobile only _x000D_5/9/2024:#Update - changing to a site type 3 / mobile only _x000D_4/9/2024:#Update - changing to a site type 3 / mobile only _x000D_3/9/2024:#Update - changing to a site type 3 / mobile only _x000D_2/9/2024:#Update - changing to a site type 3 / mobile only _x000D_29/8/2024:#Update - changing to a site type 3 / mobile only _x000D_28/8/2024:#Update - changing to a site type 3 / mobile only _x000D_27/8/2024:#Update - changing to a site type 3 / mobile only _x000D_22/8/2024:#Update - changing to a site type 3 / mobile only _x000D_21/8/2024:#Update - changing to a site type 3 / mobile only _x000D_20/8/2024:#Update - Build work required. Our Suppliers have given us a review date of 23/08/202 _x000D_19/8/2024:#Update - Build work required. Our Suppliers have given us a review date of 23/08/202 _x000D_19/8/2024:01504866 _x000D_16/8/2024:#Update - Build work required. Our Suppliers have given us a review date of 23/08/202 _x000D_15/8/2024:#Update - Build work required. Our Suppliers have given us a review date of 23/08/202 _x000D_14/8/2024:#Update - Supplier Delay - Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_13/8/2024:#Update - Supplier Delay - Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_12/8/2024:#Update - Supplier Delay - Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_9/8/2024:#Update - Supplier Delay - Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_8/8/2024:22/07/2024 _x000D_6/8/2024:22/07/2024 _x000D_5/8/2024:22/07/2024 _x000D_2/8/2024:22/07/2024 _x000D_1/8/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_30/7/2024:#Update - Supplier Delay - Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_29/7/2024:#Update - Supplier Delay - Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_29/7/2024:01504866 _x000D_26/7/2024:01504866 _x000D_24/7/2024:#Update - Supplier Delay - Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_23/7/2024:#Update - Supplier Delay - Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_22/7/2024:#Update - Supplier Delay - Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_22/7/2024:#Update - Reraised, Landlord details passed onwards to OR. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:Your order has been delayed. LinePlant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 10/07/202.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_11/7/2024:Your order has been delayed. LinePlant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 10/07/202.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_10/7/2024:Your order has been delayed. LinePlant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 10/07/202.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_9/7/2024:Your order has been delayed. LinePlant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 10/07/202.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:Your order is still experiencing contractor delay and has been escalated by our supplier. They have given us a review date of 26/06/2024. We will continue to provide updates as they become available. CSL Note: Invalid appointment slot received CSL Note: I _x000D_25/6/2024:Your order is still experiencing contractor delay and has been escalated by our supplier. They have given us a review date of 26/06/2024. We will continue to provide updates as they become available. CSL Note: Invalid appointment slot received CSL Note: I _x000D_24/6/2024:Your order is still experiencing contractor delay and has been escalated by our supplier. They have given us a review date of 26/06/2024. We will continue to provide updates as they become available. CSL Note: Invalid appointment slot received CSL Note: I _x000D_20/6/2024:Your order is still experiencing contractor delay and has been escalated by our supplier. They have given us a review date of 24/06/2024. We will continue to provide updates as they become available. CSL Note: Invalid appointment slot received CSL Note: I _x000D_19/6/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 18/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/6/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 18/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_17/6/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 18/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_14/6/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 18/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_13/6/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 18/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/6/2024:0 _x000D_10/6/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. Please confirm with end user that a second line is required to progress the order further. CSL Note: Invalid appointment slot received CSL Note _x000D_7/6/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. Please confirm with end user that a second line is required to progress the order further. CSL Note: Invalid appointment slot received CSL Note _x000D_6/6/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. Please confirm with end user that a second line is required to progress the order further. CSL Note: Invalid appointment slot received CSL Note _x000D_5/6/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. Please confirm with end user that a second line is required to progress the order further. CSL Note: Invalid appointment slot received CSL Note _x000D_4/6/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. Please confirm with end user that a second line is required to progress the order further. CSL Note: Invalid appointment slot received CSL Note _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 9/9/2024:#Update - changing to a site type 3 / mobile only _x000D_6/9/2024:#Update - changing to a site type 3 / mobile only _x000D_5/9/2024:#Update - changing to a site type 3 / mobile only _x000D_4/9/2024:#Update - changing to a site type 3 / mobile only _x000D_3/9/2024:#Update - changing to a site type 3 / mobile only _x000D_2/9/2024:#Update - changing to a site type 3 / mobile only _x000D_29/8/2024:#Update - changing to a site type 3 / mobile only _x000D_28/8/2024:#Update - changing to a site type 3 / mobile only _x000D_27/8/2024:#Update - changing to a site type 3 / mobile only _x000D_22/8/2024:#Update - changing to a site type 3 / mobile only _x000D_21/8/2024:#Update - changing to a site type 3 / mobile only _x000D_20/8/2024:#Update - Build work required. Our Suppliers have given us a review date of 23/08/202 _x000D_19/8/2024:#Update - Build work required. Our Suppliers have given us a review date of 23/08/202 _x000D_19/8/2024:01504866 _x000D_16/8/2024:#Update - Build work required. Our Suppliers have given us a review date of 23/08/202 _x000D_15/8/2024:#Update - Build work required. Our Suppliers have given us a review date of 23/08/202 _x000D_14/8/2024:#Update - Supplier Delay - Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_13/8/2024:#Update - Supplier Delay - Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_12/8/2024:#Update - Supplier Delay - Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_9/8/2024:#Update - Supplier Delay - Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_8/8/2024:22/07/2024 _x000D_6/8/2024:22/07/2024 _x000D_5/8/2024:22/07/2024 _x000D_2/8/2024:22/07/2024 _x000D_1/8/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_30/7/2024:#Update - Supplier Delay - Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_29/7/2024:#Update - Supplier Delay - Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_29/7/2024:01504866 _x000D_26/7/2024:01504866 _x000D_24/7/2024:#Update - Supplier Delay - Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_23/7/2024:#Update - Supplier Delay - Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_22/7/2024:#Update - Supplier Delay - Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_22/7/2024:#Update - Reraised, Landlord details passed onwards to OR. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:Your order has been delayed. LinePlant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 10/07/202.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_11/7/2024:Your order has been delayed. LinePlant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 10/07/202.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_10/7/2024:Your order has been delayed. LinePlant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 10/07/202.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_9/7/2024:Your order has been delayed. LinePlant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 10/07/202.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:Your order is still experiencing contractor delay and has been escalated by our supplier. They have given us a review date of 26/06/2024. We will continue to provide updates as they become available. CSL Note: Invalid appointment slot received CSL Note: I _x000D_25/6/2024:Your order is still experiencing contractor delay and has been escalated by our supplier. They have given us a review date of 26/06/2024. We will continue to provide updates as they become available. CSL Note: Invalid appointment slot received CSL Note: I _x000D_24/6/2024:Your order is still experiencing contractor delay and has been escalated by our supplier. They have given us a review date of 26/06/2024. We will continue to provide updates as they become available. CSL Note: Invalid appointment slot received CSL Note: I _x000D_20/6/2024:Your order is still experiencing contractor delay and has been escalated by our supplier. They have given us a review date of 24/06/2024. We will continue to provide updates as they become available. CSL Note: Invalid appointment slot received CSL Note: I _x000D_19/6/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 18/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/6/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 18/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_17/6/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 18/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_14/6/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 18/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_13/6/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 18/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/6/2024:0 _x000D_10/6/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. Please confirm with end user that a second line is required to progress the order further. CSL Note: Invalid appointment slot received CSL Note _x000D_7/6/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. Please confirm with end user that a second line is required to progress the order further. CSL Note: Invalid appointment slot received CSL Note _x000D_6/6/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. Please confirm with end user that a second line is required to progress the order further. CSL Note: Invalid appointment slot received CSL Note _x000D_5/6/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. Please confirm with end user that a second line is required to progress the order further. CSL Note: Invalid appointment slot received CSL Note _x000D_4/6/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. Please confirm with end user that a second line is required to progress the order further. CSL Note: Invalid appointment slot received CSL Note _x000D_31/5/2024:0 _x000D_30/5/2024:0 _x000D_29/5/2024:0 _x000D_28/5/2024:0 _x000D_10/5/2024:0 _x000D_10/05/2024: New order added to report | 0 | #Update - changing to a site type 3 / mobile only | 2024-06-07 | 31/05024: Allwyn to provide an update |  |  | 3.Allwyn to arrange rtr install | VFP2424534 | 30015161 | 2.Commissioning | AM |  |  |  |  | 0 |  |  |  | 2024-08-27 | [7 empty] | 0
1200 | 667250 | 2992 | Batch 5 Jul24 | Type 1 | SOGEA | J Evans Newsagents | Bridgend | CF32 0AW |  | 0 | 0 |  |  | 2024-06-07 |  |  |  |  | VFS970492 | 30014483 | 1.Provisioning | [9 empty] | 2024-06-12 | [7 empty] | 0 |  | 665369
1201 | 665369 | 2993 | Batch 5 Jul24 | Type 1 | SOGEA | Green Street Post Office | SOUTH SHIELDS | NE33 5DY |  | 0 | 0 |  |  | 2024-06-07 |  |  |  |  | VFS970476 | 30014583 | 1.Provisioning | [13 empty] | 2024-06-21 | 23A004952678 |  | 2024-07-30 | 1 |  | 670800
1202 | 670800 | 2995 | Batch 5 Jul24 | Type 1 | SOGEA | BP Londis Silverhill S/S | ST. LEONARDS-ON-SEA | TN37 7DA |  | 0 | 0 |  |  | 2024-06-07 |  |  |  |  | VFS970473 | 30014462 | 1.Provisioning | [13 empty] | 2024-06-14 | 23A004948641 |  | 2024-07-30 | 1 |  | 668004
1203 | 668004 | 2996 | Batch 5 Jul24 | Type 1 | SOGEA | 8 Till Late Food & Wine | HOUNSLOW | TW3 1JQ |  | 0 | 0 |  |  | 2024-06-07 |  |  |  |  | VFS970478 | 30014612 | 1.Provisioning | [13 empty] | 2024-07-01 | 242005008668 |  | 2024-07-30 | 1 |  | 664373
1204 | 664373 | 2997 | Batch 5 Jul24 | Type 1 | FTTP | GnR Newsagent | DEESIDE | CH5 4DP |  | 0 | 0 |  |  | 2024-06-07 |  |  |  |  | VFP2325032 | 30014210 | 1.Provisioning | [13 empty] | 2024-06-28 | 242005008903 |  | 2024-07-30 | 1 |  | 664369
1205 | 664369 | 2998 | Batch 5 Jul24 | Type 1 | SOGEA | Springbok Newsagent | LONDON | E12 6RA |  | 0 | 0 |  |  | 2024-06-07 |  |  |  |  | VFS970454 | 30014300 | 1.Provisioning | [13 empty] | 2024-06-10 | 237004907001 |  | 2024-07-30 | 1
1206 | 648528 | 3000 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Kandys News Todays Local | Leicester | LE5 3TA |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:#Update Customer's incorrect details on order. Allwyn to advise _x000D_21/8/2024:#Update Customer's incorrect details on order. Allwyn to advise _x000D_20/8/2024:#Update Customer's incorrect details on order. Allwyn to advise _x000D_19/8/2024:#Update Customer's incorrect details on order. Allwyn to advise _x000D_19/8/2024:01515339 _x000D_16/8/2024:#Update Customer's incorrect details on order. Allwyn to advise _x000D_15/8/2024:#Update Customer's incorrect details on order. Allwyn to advise _x000D_14/8/2024:#Update Customer's incorrect details on order. Allwyn to advise _x000D_13/8/2024:#Update Customer's incorrect details on order. Allwyn to advise _x000D_12/8/2024:#Update Customer's incorrect details on order. Allwyn to advise _x000D_9/8/2024:#Update Customer's incorrect details on order. Allwyn to advise _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update Customer's incorrect details on order. Allwyn to advise _x000D_29/7/2024:#Update Customer's incorrect details on order. Allwyn to advise _x000D_29/7/2024:01515339 _x000D_26/7/2024:24/07/2024 12:56 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:Your order has been delayed. There is an Duplicate order. Please confirm with end user to progress the order further. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/6/2024:Your order has been delayed. There is an Duplicate order. Please confirm with end user to progress the order further. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/6/2024:Your order has been delayed. There is an Duplicate order. Please confirm with end user to progress the order further. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_17/6/2024:Your order has been delayed. There is an Duplicate order. Please confirm with end user to progress the order further. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:Supplier Delay: Delayed in planning. Order completion may be delayed. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/6/2024:Supplier Delay: Delayed in planning. Order completion may be delayed. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/6/2024:Supplier Delay: Delayed in planning. Order completion may be delayed. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:#Update Customer's incorrect details on order. Allwyn to advise _x000D_21/8/2024:#Update Customer's incorrect details on order. Allwyn to advise _x000D_20/8/2024:#Update Customer's incorrect details on order. Allwyn to advise _x000D_19/8/2024:#Update Customer's incorrect details on order. Allwyn to advise _x000D_19/8/2024:01515339 _x000D_16/8/2024:#Update Customer's incorrect details on order. Allwyn to advise _x000D_15/8/2024:#Update Customer's incorrect details on order. Allwyn to advise _x000D_14/8/2024:#Update Customer's incorrect details on order. Allwyn to advise _x000D_13/8/2024:#Update Customer's incorrect details on order. Allwyn to advise _x000D_12/8/2024:#Update Customer's incorrect details on order. Allwyn to advise _x000D_9/8/2024:#Update Customer's incorrect details on order. Allwyn to advise _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update Customer's incorrect details on order. Allwyn to advise _x000D_29/7/2024:#Update Customer's incorrect details on order. Allwyn to advise _x000D_29/7/2024:01515339 _x000D_26/7/2024:24/07/2024 12:56 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_1/7/2024:Order Completed _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:Your order has been delayed. There is an Duplicate order. Please confirm with end user to progress the order further. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/6/2024:Your order has been delayed. There is an Duplicate order. Please confirm with end user to progress the order further. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/6/2024:Your order has been delayed. There is an Duplicate order. Please confirm with end user to progress the order further. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_17/6/2024:Your order has been delayed. There is an Duplicate order. Please confirm with end user to progress the order further. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:Supplier Delay: Delayed in planning. Order completion may be delayed. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/6/2024:Supplier Delay: Delayed in planning. Order completion may be delayed. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/6/2024:Supplier Delay: Delayed in planning. Order completion may be delayed. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 0 | 0 | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2417027 | 30017677 | 2.Commissioning | AM |  | 2024-07-25 | 2024-08-19 |  | 0 |  |  |  | 2024-09-20 | [7 empty] | 0
1207 | 670814 | 3013 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | D & S News | Darlington | DL1 1NT |  | 6/9/2024:#Update - Order has been cancelled as Openreach did not get permission to dig on the land. This will be reraised however please speak to the retailer regarding gaining consent _x000D_5/9/2024:#Update - Order has been cancelled as Openreach did not get permission to dig on the land. This will be reraised however please speak to the retailer regarding gaining consent _x000D_4/9/2024:#Update - Order has been cancelled as Openreach did not get permission to dig on the land. This will be reraised however please speak to the retailer regarding gaining consent _x000D_3/9/2024:#Update - Order has been cancelled as Openreach did not get permission to dig on the land. This will be reraised however please speak to the retailer regarding gaining consent _x000D_2/9/2024:#Update - Order has been cancelled as Openreach did not get permission to dig on the land. This will be reraised however please speak to the retailer regarding gaining consent _x000D_29/8/2024:#Update - Order has been cancelled as Openreach did not get permission to dig on the land. This will be reraised however please speak to the retailer regarding gaining consent _x000D_28/8/2024:#Update - Order has been cancelled as Openreach did not get permission to dig on the land. This will be reraised however please speak to the retailer regarding gaining consent _x000D_27/8/2024:#Update - Order has been cancelled as Openreach did not get permission to dig on the land. This will be reraised however please speak to the retailer regarding gaining consent _x000D_22/8/2024:#Update - Order has been cancelled as Openreach did not get permission to dig on the land. This will be reraised however please speak to the retailer regarding gaining consent _x000D_21/8/2024:#Update - Order has been cancelled as Openreach did not get permission to dig on the land. This will be reraised however please speak to the retailer regarding gaining consent _x000D_20/8/2024:#Update - Order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. CSL will update as more information become available. _x000D_19/8/2024:#Update - Order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. CSL will update as more information become available. _x000D_19/8/2024:01482786 _x000D_16/8/2024:#Update - Order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. CSL will update as more information become available. _x000D_14/8/2024:#Update - Order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. CSL will update as more information become available. _x000D_13/8/2024:#Update - Order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. CSL will update as more information become available. _x000D_12/8/2024:#Update - Order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. CSL will update as more information become available. _x000D_9/8/2024:#Update - Order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. CSL will update as more information become available. _x000D_8/8/2024:18/07/2024 _x000D_6/8/2024:18/07/2024 _x000D_5/8/2024:18/07/2024 _x000D_2/8/2024:18/07/2024 _x000D_1/8/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_30/7/2024:#Update - Order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. CSL will update as more information become available. _x000D_29/7/2024:#Update - Order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. CSL will update as more information become available. _x000D_29/7/2024:01482786 _x000D_26/7/2024:01482786 _x000D_24/7/2024:#Update - Order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. CSL will update as more information become available. _x000D_23/7/2024:#Update - Order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. CSL will update as more information become available. _x000D_22/7/2024:#Update - Order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. CSL will update as more information become available. _x000D_22/7/2024:#Update - Order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. CSL will update as more information become available. _x000D_0 | 9/9/2024:#Update - Order has been cancelled as Openreach did not get permission to dig on the land. This will be reraised however please speak to the retailer regarding gaining consent _x000D_6/9/2024:#Update - Order has been cancelled as Openreach did not get permission to dig on the land. This will be reraised however please speak to the retailer regarding gaining consent _x000D_5/9/2024:#Update - Order has been cancelled as Openreach did not get permission to dig on the land. This will be reraised however please speak to the retailer regarding gaining consent _x000D_4/9/2024:#Update - Order has been cancelled as Openreach did not get permission to dig on the land. This will be reraised however please speak to the retailer regarding gaining consent _x000D_3/9/2024:#Update - Order has been cancelled as Openreach did not get permission to dig on the land. This will be reraised however please speak to the retailer regarding gaining consent _x000D_2/9/2024:#Update - Order has been cancelled as Openreach did not get permission to dig on the land. This will be reraised however please speak to the retailer regarding gaining consent _x000D_29/8/2024:#Update - Order has been cancelled as Openreach did not get permission to dig on the land. This will be reraised however please speak to the retailer regarding gaining consent _x000D_28/8/2024:#Update - Order has been cancelled as Openreach did not get permission to dig on the land. This will be reraised however please speak to the retailer regarding gaining consent _x000D_27/8/2024:#Update - Order has been cancelled as Openreach did not get permission to dig on the land. This will be reraised however please speak to the retailer regarding gaining consent _x000D_22/8/2024:#Update - Order has been cancelled as Openreach did not get permission to dig on the land. This will be reraised however please speak to the retailer regarding gaining consent _x000D_21/8/2024:#Update - Order has been cancelled as Openreach did not get permission to dig on the land. This will be reraised however please speak to the retailer regarding gaining consent _x000D_20/8/2024:#Update - Order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. CSL will update as more information become available. _x000D_19/8/2024:#Update - Order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. CSL will update as more information become available. _x000D_19/8/2024:01482786 _x000D_16/8/2024:#Update - Order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. CSL will update as more information become available. _x000D_14/8/2024:#Update - Order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. CSL will update as more information become available. _x000D_13/8/2024:#Update - Order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. CSL will update as more information become available. _x000D_12/8/2024:#Update - Order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. CSL will update as more information become available. _x000D_9/8/2024:#Update - Order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. CSL will update as more information become available. _x000D_8/8/2024:18/07/2024 _x000D_6/8/2024:18/07/2024 _x000D_5/8/2024:18/07/2024 _x000D_2/8/2024:18/07/2024 _x000D_1/8/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_30/7/2024:#Update - Order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. CSL will update as more information become available. _x000D_29/7/2024:#Update - Order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. CSL will update as more information become available. _x000D_29/7/2024:01482786 _x000D_26/7/2024:01482786 _x000D_24/7/2024:#Update - Order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. CSL will update as more information become available. _x000D_23/7/2024:#Update - Order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. CSL will update as more information become available. _x000D_22/7/2024:#Update - Order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. CSL will update as more information become available. _x000D_22/7/2024:#Update - Order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. CSL will update as more information become available. _x000D_0 | 0 | #Update - Order has been cancelled as Openreach did not get permission to dig on the land. This will be reraised however please speak to the retailer regarding gaining consent | 2024-06-07 |  |  |  |  | VFP2399227 | 30017213 | 1.Provisioning | AM |  | 2024-07-09 | 2024-07-09 |  | 0 | [11 empty] | 0 | 670814
1208 | 668926 | 3021 | Batch 5 Jul24 | Type 1 | SOGEA | Herringthorpe PO & Fiveways Premier | Rotherham | S65 2JY |  | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | Address query | Address query | 1.Provisioning | [17 empty] | 0
1209 | 666783 | 3025 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Daytoday | Glasgow | G22 5JW |  | 6/9/2024:#Update - no capacity, order will need to be replaced in coming weeks _x000D_5/9/2024:#Update - no capacity, order will need to be replaced in coming weeks _x000D_4/9/2024:#Update - no capacity, order will need to be replaced in coming weeks _x000D_3/9/2024:#Update - no capacity, order will need to be replaced in coming weeks _x000D_2/9/2024:#Update - no capacity, order will need to be replaced in coming weeks _x000D_29/8/2024:#Update - no capacity, order will need to be replaced in coming weeks _x000D_28/8/2024:#Update - no capacity, order will need to be replaced in coming weeks _x000D_27/8/2024:#Update - no capacity, order will need to be replaced in coming weeks _x000D_22/8/2024:#Update - no capacity, order will need to be replaced in coming weeks _x000D_21/8/2024:#Update - no capacity, order will need to be replaced in coming weeks _x000D_20/8/2024:#Update - no capacity, order will need to be replaced in coming weeks _x000D_19/8/2024:#Update - no capacity, order will need to be replaced in coming weeks _x000D_19/8/2024:01538971 _x000D_16/8/2024:#Update - no capacity, order will need to be replaced in coming weeks _x000D_15/8/2024:#Update - no capacity, order will need to be replaced in coming weeks _x000D_14/8/2024:#Update - no capacity, order will need to be replaced in coming weeks _x000D_13/8/2024:#Update - no capacity, order will need to be replaced in coming weeks _x000D_12/8/2024:#Update - no capacity, order will need to be replaced in coming weeks _x000D_9/8/2024:#Update - no capacity, order will need to be replaced in coming weeks _x000D_8/8/2024:06/08/2024 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:Port available but TRFS/CRFS dates is Unknown CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_1/8/2024:Port available but TRFS/CRFS dates is Unknown CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:Port available but TRFS/CRFS dates is Unknown CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:37647 _x000D_30/7/2024:Port available but TRFS/CRFS dates is Unknown CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:Port available but TRFS/CRFS dates is Unknown CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:28/07/2024 07:01 _x000D_26/7/2024:26/07/2024 07:02 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:Your order has been delayed. Engineer required access to the end user premises to complete the step -1 work. Please check with the end user and confirm the availablity to proceed further. CSL Note: Invalid appointment slot received CSL Note: Invalid data _x000D_19/6/2024:Your order has been delayed. Engineer required access to the end user premises to complete the step -1 work. Please check with the end user and confirm the availablity to proceed further. CSL Note: Invalid appointment slot received CSL Note: Invalid data _x000D_18/6/2024:Your order has been delayed. Engineer required access to the end user premises to complete the step -1 work. Please check with the end user and confirm the availablity to proceed further. CSL Note: Invalid appointment slot received CSL Note: Invalid data _x000D_17/6/2024:Your order has been delayed. Engineer required access to the end user premises to complete the step -1 work. Please check with the end user and confirm the availablity to proceed further. CSL Note: Invalid appointment slot received CSL Note: Invalid data _x000D_14/6/2024:Your order has been delayed. Engineer required access to the end user premises to complete the step -1 work. Please check with the end user and confirm the availablity to proceed further. CSL Note: Invalid appointment slot received CSL Note: Invalid data _x000D_13/6/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 13/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 13/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 13/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 9/9/2024:#Update - no capacity, order will need to be replaced in coming weeks _x000D_6/9/2024:#Update - no capacity, order will need to be replaced in coming weeks _x000D_5/9/2024:#Update - no capacity, order will need to be replaced in coming weeks _x000D_4/9/2024:#Update - no capacity, order will need to be replaced in coming weeks _x000D_3/9/2024:#Update - no capacity, order will need to be replaced in coming weeks _x000D_2/9/2024:#Update - no capacity, order will need to be replaced in coming weeks _x000D_29/8/2024:#Update - no capacity, order will need to be replaced in coming weeks _x000D_28/8/2024:#Update - no capacity, order will need to be replaced in coming weeks _x000D_27/8/2024:#Update - no capacity, order will need to be replaced in coming weeks _x000D_22/8/2024:#Update - no capacity, order will need to be replaced in coming weeks _x000D_21/8/2024:#Update - no capacity, order will need to be replaced in coming weeks _x000D_20/8/2024:#Update - no capacity, order will need to be replaced in coming weeks _x000D_19/8/2024:#Update - no capacity, order will need to be replaced in coming weeks _x000D_19/8/2024:01538971 _x000D_16/8/2024:#Update - no capacity, order will need to be replaced in coming weeks _x000D_15/8/2024:#Update - no capacity, order will need to be replaced in coming weeks _x000D_14/8/2024:#Update - no capacity, order will need to be replaced in coming weeks _x000D_13/8/2024:#Update - no capacity, order will need to be replaced in coming weeks _x000D_12/8/2024:#Update - no capacity, order will need to be replaced in coming weeks _x000D_9/8/2024:#Update - no capacity, order will need to be replaced in coming weeks _x000D_8/8/2024:06/08/2024 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:Port available but TRFS/CRFS dates is Unknown CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_1/8/2024:Port available but TRFS/CRFS dates is Unknown CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:Port available but TRFS/CRFS dates is Unknown CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:37647 _x000D_30/7/2024:Port available but TRFS/CRFS dates is Unknown CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:Port available but TRFS/CRFS dates is Unknown CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:28/07/2024 07:01 _x000D_26/7/2024:26/07/2024 07:02 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:Your order has been delayed. Engineer required access to the end user premises to complete the step -1 work. Please check with the end user and confirm the availablity to proceed further. CSL Note: Invalid appointment slot received CSL Note: Invalid data _x000D_19/6/2024:Your order has been delayed. Engineer required access to the end user premises to complete the step -1 work. Please check with the end user and confirm the availablity to proceed further. CSL Note: Invalid appointment slot received CSL Note: Invalid data _x000D_18/6/2024:Your order has been delayed. Engineer required access to the end user premises to complete the step -1 work. Please check with the end user and confirm the availablity to proceed further. CSL Note: Invalid appointment slot received CSL Note: Invalid data _x000D_17/6/2024:Your order has been delayed. Engineer required access to the end user premises to complete the step -1 work. Please check with the end user and confirm the availablity to proceed further. CSL Note: Invalid appointment slot received CSL Note: Invalid data _x000D_14/6/2024:Your order has been delayed. Engineer required access to the end user premises to complete the step -1 work. Please check with the end user and confirm the availablity to proceed further. CSL Note: Invalid appointment slot received CSL Note: Invalid data _x000D_13/6/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 13/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 13/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 13/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 0 | #Update - no capacity, order will need to be replaced in coming weeks | 2024-06-07 |  |  |  |  | VFS1065822 | 30016824 | 1.Provisioning | AM |  | 2024-06-20 |  |  | 0 | [11 empty] | 0
1210 | 660242 | 3031 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Nicks News | Wednesbury | WS10 7HD |  | 6/9/2024:#Update - NFA - Allwyn confirmed new install date 12/09 - AM with retailer _x000D_5/9/2024:#Update - NFA - Allwyn confirmed new install date 12/09 - AM with retailer _x000D_4/9/2024:#Update - NFA - Allwyn confirmed new install date 12/09 - AM with retailer _x000D_3/9/2024:#Update - NFA - Allwyn confirmed new install date 12/09 - AM with retailer _x000D_2/9/2024:#Update - NFA - Allwyn confirmed new install date 12/09 - AM with retailer _x000D_29/8/2024:#Update - 21/08 No work has been completed - retailer wants to cancel the order and does not want any work to be done. Action with Allwyn to liaise with retailer to confirm _x000D_28/8/2024:#Update - 21/08 No work has been completed - retailer wants to cancel the order and does not want any work to be done. Action with Allwyn to liaise with retailer to confirm _x000D_Retailer advised they did not want any work to be done. With Allwyn to confirm with retailer - email sent 21/08 and chased 27/08 | 9/9/2024:#Update - NFA - Allwyn confirmed new install date 12/09 - AM with retailer _x000D_6/9/2024:#Update - NFA - Allwyn confirmed new install date 12/09 - AM with retailer _x000D_5/9/2024:#Update - NFA - Allwyn confirmed new install date 12/09 - AM with retailer _x000D_4/9/2024:#Update - NFA - Allwyn confirmed new install date 12/09 - AM with retailer _x000D_3/9/2024:#Update - NFA - Allwyn confirmed new install date 12/09 - AM with retailer _x000D_2/9/2024:#Update - NFA - Allwyn confirmed new install date 12/09 - AM with retailer _x000D_29/8/2024:#Update - 21/08 No work has been completed - retailer wants to cancel the order and does not want any work to be done. Action with Allwyn to liaise with retailer to confirm _x000D_28/8/2024:#Update - 21/08 No work has been completed - retailer wants to cancel the order and does not want any work to be done. Action with Allwyn to liaise with retailer to confirm _x000D_Retailer advised they did not want any work to be done. With Allwyn to confirm with retailer - email sent 21/08 and chased 27/08 | 0 | #Update - NFA - Allwyn confirmed new install date 12/09 - AM with retailer | 2024-06-07 |  |  |  |  | VFP2430107 | 30016928 | 1.Provisioning | AM |  | 2024-06-20 |  |  | 0 | [11 empty] | 0
1211 | 664833 | 3038 | Batch 5 Jul24 | Type 1 | FTTP | Supervalu Newry | NEWRY | BT34 1AF |  | 26/7/2024:01478790 _x000D_24/7/2024:#Update Retailer happy with appointment, 23/07 AM. _x000D_23/7/2024:#Update Retailer happy with appointment, 23/07 AM. _x000D_22/7/2024:#Update Retailer happy with appointment, 23/07 AM. _x000D_22/7/2024:#Update Retailer happy with appointment, 23/07 AM. _x000D_0 | 26/7/2024:01478790 _x000D_24/7/2024:#Update Retailer happy with appointment, 23/07 AM. _x000D_23/7/2024:#Update Retailer happy with appointment, 23/07 AM. _x000D_22/7/2024:#Update Retailer happy with appointment, 23/07 AM. _x000D_22/7/2024:#Update Retailer happy with appointment, 23/07 AM. _x000D_0 |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1050513 | 30016868 | 2.Commissioning |  |  | 2024-07-23 | 2024-07-23 | 2024-07-23 | TRUE |  |  |  | 2024-08-20 | [7 empty] | 0
1212 | 662847 | 3043 | Batch 5 Jul24 | Type 1 | SOGEA | Filco Market | Bridgend | CF32 9NU |  | Address verification issue, email sent to VF - order is cancelled and will be reraised accordingly | Address verification issue, email sent to VF - order is cancelled and will be reraised accordingly |  |  | 2024-06-07 |  |  |  |  | Address query | Address query | 1.Provisioning | [17 empty] | 0
1213 | 665284 | 3048 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Bierley SuperStore & Post Office | BRADFORD | BD4 6AX |  | 6/9/2024:#Update Upgrade / OOH sent to VF for approval. _x000D_5/9/2024:#Update Upgrade / OOH sent to VF for approval. _x000D_4/9/2024:#Update Upgrade / OOH sent to VF for approval. _x000D_3/9/2024:#Update Upgrade / OOH sent to VF for approval. _x000D_2/9/2024:#Update Upgrade / OOH sent to VF for approval. _x000D_29/8/2024:#Update Upgrade / OOH sent to VF for approval. _x000D_28/8/2024:#Update Upgrade / OOH sent to VF for approval. _x000D_27/8/2024:#Update Upgrade / OOH sent to VF for approval. _x000D_22/8/2024:#Update Upgrade / OOH sent to VF for approval. _x000D_21/8/2024:#Update Upgrade / OOH sent to VF for approval. _x000D_20/8/2024:#Update Upgrade / OOH sent to VF for approval. _x000D_19/8/2024:#Update Upgrade / OOH sent to VF for approval. _x000D_19/8/2024:01512714 _x000D_16/8/2024:#Update Upgrade / OOH sent to VF for approval. _x000D_15/8/2024:#Update Upgrade / OOH sent to VF for approval. _x000D_14/8/2024:#Update Upgrade / OOH sent to VF for approval. _x000D_13/8/2024:#Update Upgrade / OOH sent to VF for approval. _x000D_12/8/2024:#Update Upgrade / OOH sent to VF for approval. _x000D_9/8/2024:#Update Upgrade / OOH sent to VF for approval. _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update Upgrade / OOH sent to VF for approval. _x000D_29/7/2024:#Update Upgrade / OOH sent to VF for approval. _x000D_29/7/2024:01512714 _x000D_26/7/2024:24/07/2024 14:42 _x000D_24/7/2024:Our engineer has been unable to complete the task due to the end customer withdrawing access. _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 26/07/2024..We will continue to provide update as they become available. _x000D_17/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 26/07/2024..We will continue to provide update as they become available. _x000D_16/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 26/07/2024..We will continue to provide update as they become available. _x000D_15/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 26/07/2024..We will continue to provide update as they become available. _x000D_12/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 26/07/2024..We will continue to provide update as they become available. _x000D_11/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 26/07/2024..We will continue to provide update as they become available. _x000D_10/7/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_24/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_20/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:#Update Upgrade / OOH sent to VF for approval. _x000D_6/9/2024:#Update Upgrade / OOH sent to VF for approval. _x000D_5/9/2024:#Update Upgrade / OOH sent to VF for approval. _x000D_4/9/2024:#Update Upgrade / OOH sent to VF for approval. _x000D_3/9/2024:#Update Upgrade / OOH sent to VF for approval. _x000D_2/9/2024:#Update Upgrade / OOH sent to VF for approval. _x000D_29/8/2024:#Update Upgrade / OOH sent to VF for approval. _x000D_28/8/2024:#Update Upgrade / OOH sent to VF for approval. _x000D_27/8/2024:#Update Upgrade / OOH sent to VF for approval. _x000D_22/8/2024:#Update Upgrade / OOH sent to VF for approval. _x000D_21/8/2024:#Update Upgrade / OOH sent to VF for approval. _x000D_20/8/2024:#Update Upgrade / OOH sent to VF for approval. _x000D_19/8/2024:#Update Upgrade / OOH sent to VF for approval. _x000D_19/8/2024:01512714 _x000D_16/8/2024:#Update Upgrade / OOH sent to VF for approval. _x000D_15/8/2024:#Update Upgrade / OOH sent to VF for approval. _x000D_14/8/2024:#Update Upgrade / OOH sent to VF for approval. _x000D_13/8/2024:#Update Upgrade / OOH sent to VF for approval. _x000D_12/8/2024:#Update Upgrade / OOH sent to VF for approval. _x000D_9/8/2024:#Update Upgrade / OOH sent to VF for approval. _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update Upgrade / OOH sent to VF for approval. _x000D_29/7/2024:#Update Upgrade / OOH sent to VF for approval. _x000D_29/7/2024:01512714 _x000D_26/7/2024:24/07/2024 14:42 _x000D_24/7/2024:Our engineer has been unable to complete the task due to the end customer withdrawing access. _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 26/07/2024..We will continue to provide update as they become available. _x000D_17/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 26/07/2024..We will continue to provide update as they become available. _x000D_16/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 26/07/2024..We will continue to provide update as they become available. _x000D_15/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 26/07/2024..We will continue to provide update as they become available. _x000D_12/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 26/07/2024..We will continue to provide update as they become available. _x000D_11/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 26/07/2024..We will continue to provide update as they become available. _x000D_10/7/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_24/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_20/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | Update: Order Amended | #Update Upgrade / OOH sent to VF for approval. | 2024-06-07 |  |  |  |  | VFP2416384 | 30016690 | 1.Provisioning | AM |  | 2024-07-23 | 2024-09-10 |  | 0 | [11 empty] | 0
1214 | 433376 | 3052 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Eurospar | BANBRIDGE | BT32 3DA | 2024-07-11 | 6/9/2024:#Update Order delayed due Survey work. It requires permission from management company to proceed the planned works. Our suppliers have given us a review date of 13/09/2024. We will continue to provide update as they become available. _x000D_5/9/2024:#Update Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 02/09/2024.We will continue to provide update as they become available. _x000D_4/9/2024:#Update Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 02/09/2024.We will continue to provide update as they become available. _x000D_3/9/2024:#Update Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 02/09/2024.We will continue to provide update as they become available. _x000D_2/9/2024:#Update Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 02/09/2024.We will continue to provide update as they become available. _x000D_29/8/2024:#Update Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 02/09/2024.We will continue to provide update as they become available. _x000D_28/8/2024:#Update Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 02/09/2024.We will continue to provide update as they become available. _x000D_27/8/2024:#Update Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 02/09/2024.We will continue to provide update as they become available. _x000D_22/8/2024:#Update Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 02/09/2024.We will continue to provide update as they become available. _x000D_21/8/2024:#Update Retailer confirmed new appointment 15/08 _x000D_20/8/2024:#Update Retailer confirmed new appointment 15/08 _x000D_19/8/2024:#Update Retailer confirmed new appointment 15/08 _x000D_19/8/2024:01481996 _x000D_16/8/2024:#Update Retailer confirmed new appointment 15/08 _x000D_15/8/2024:#Update Retailer confirmed new appointment 15/08 _x000D_14/8/2024:#Update Retailer confirmed new appointment 15/08 _x000D_13/8/2024:#Update Retailer confirmed new appointment 15/08 _x000D_12/8/2024:#Update Reappointed 15/08, AM as Allwyn unable to contact retailer _x000D_9/8/2024:#Update Reappointed 15/08, AM as Allwyn unable to contact retailer _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update Reappointed 15/08, AM as Allwyn unable to contact retailer _x000D_29/7/2024:#Update Reappointed 15/08, AM as Allwyn unable to contact retailer _x000D_29/7/2024:01481996 _x000D_26/7/2024:01481996 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:#Update Order delayed due Survey work. It requires permission from management company to proceed the planned works. Our suppliers have given us a review date of 13/09/2024. We will continue to provide update as they become available. _x000D_6/9/2024:#Update Order delayed due Survey work. It requires permission from management company to proceed the planned works. Our suppliers have given us a review date of 13/09/2024. We will continue to provide update as they become available. _x000D_5/9/2024:#Update Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 02/09/2024.We will continue to provide update as they become available. _x000D_4/9/2024:#Update Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 02/09/2024.We will continue to provide update as they become available. _x000D_3/9/2024:#Update Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 02/09/2024.We will continue to provide update as they become available. _x000D_2/9/2024:#Update Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 02/09/2024.We will continue to provide update as they become available. _x000D_29/8/2024:#Update Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 02/09/2024.We will continue to provide update as they become available. _x000D_28/8/2024:#Update Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 02/09/2024.We will continue to provide update as they become available. _x000D_27/8/2024:#Update Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 02/09/2024.We will continue to provide update as they become available. _x000D_22/8/2024:#Update Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 02/09/2024.We will continue to provide update as they become available. _x000D_21/8/2024:#Update Retailer confirmed new appointment 15/08 _x000D_20/8/2024:#Update Retailer confirmed new appointment 15/08 _x000D_19/8/2024:#Update Retailer confirmed new appointment 15/08 _x000D_19/8/2024:01481996 _x000D_16/8/2024:#Update Retailer confirmed new appointment 15/08 _x000D_15/8/2024:#Update Retailer confirmed new appointment 15/08 _x000D_14/8/2024:#Update Retailer confirmed new appointment 15/08 _x000D_13/8/2024:#Update Retailer confirmed new appointment 15/08 _x000D_12/8/2024:#Update Reappointed 15/08, AM as Allwyn unable to contact retailer _x000D_9/8/2024:#Update Reappointed 15/08, AM as Allwyn unable to contact retailer _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update Reappointed 15/08, AM as Allwyn unable to contact retailer _x000D_29/7/2024:#Update Reappointed 15/08, AM as Allwyn unable to contact retailer _x000D_29/7/2024:01481996 _x000D_26/7/2024:01481996 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | Your order has been delayed due Survey work. It requires permission from management company to proceed the planned works. Our suppliers have given us a review date of 13/09/2024. We will continue to provide update as they become available. | #Update Order delayed due Survey work. It requires permission from management company to proceed the planned works. Our suppliers have given us a review date of 13/09/2024. We will continue to provide update as they become available. | 2024-06-07 |  |  |  |  | VFP2393893 | 30017188 | 1.Provisioning | AM |  | 2024-07-10 | 2024-08-15 |  | 0 | [11 empty] | 0
1215 | 652219 | 3069 | Batch 5 Jul24 | Type 1 | FTTP | Spar | Sheffield | S12 4EJ |  | 26/7/2024:23/07/2024 11:24 _x000D_24/7/2024:Order Completed _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_0 | 26/7/2024:23/07/2024 11:24 _x000D_24/7/2024:Order Completed _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_0 |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1050522 | 30016854 | 6.Failed router install |  |  | 2024-07-23 | 2024-07-23 | 2024-07-23 | TRUE |  |  |  | 2024-08-14 |  |  |  | 2024-08-15 | 23A004948460 | 23A004948460 | 2024-08-16 | 1
1216 | 617391 | 3072 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Spar | Northampton | NN1 2LT |  | 6/9/2024:#Update - Address verification issue, email sent to VF - order is cancelled and will be reraised accordingly _x000D_5/9/2024:#Update - Address verification issue, email sent to VF - order is cancelled and will be reraised accordingly _x000D_4/9/2024:#Update - Address verification issue, email sent to VF - order is cancelled and will be reraised accordingly _x000D_3/9/2024:#Update - Address verification issue, email sent to VF - order is cancelled and will be reraised accordingly _x000D_2/9/2024:#Update - Address verification issue, email sent to VF - order is cancelled and will be reraised accordingly _x000D_29/8/2024:#Update - Address verification issue, email sent to VF - order is cancelled and will be reraised accordingly _x000D_28/8/2024:#Update - Address verification issue, email sent to VF - order is cancelled and will be reraised accordingly _x000D_Address verification issue, email sent to VF - order is cancelled and will be reraised accordingly | 9/9/2024:#Update - Address verification issue, email sent to VF - order is cancelled and will be reraised accordingly _x000D_6/9/2024:#Update - Address verification issue, email sent to VF - order is cancelled and will be reraised accordingly _x000D_5/9/2024:#Update - Address verification issue, email sent to VF - order is cancelled and will be reraised accordingly _x000D_4/9/2024:#Update - Address verification issue, email sent to VF - order is cancelled and will be reraised accordingly _x000D_3/9/2024:#Update - Address verification issue, email sent to VF - order is cancelled and will be reraised accordingly _x000D_2/9/2024:#Update - Address verification issue, email sent to VF - order is cancelled and will be reraised accordingly _x000D_29/8/2024:#Update - Address verification issue, email sent to VF - order is cancelled and will be reraised accordingly _x000D_28/8/2024:#Update - Address verification issue, email sent to VF - order is cancelled and will be reraised accordingly _x000D_Address verification issue, email sent to VF - order is cancelled and will be reraised accordingly | 0 | #Update - Address verification issue, email sent to VF - order is cancelled and will be reraised accordingly | 2024-06-07 |  |  |  |  | Address query | 30017226 | 1.Provisioning | AM |  | 2024-07-12 |  |  | 0 | [11 empty] | 0
1217 | 456811 | 3077 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Spar | ACCRINGTON | BB5 4QG |  | 6/9/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_5/9/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_4/9/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_3/9/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_2/9/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_29/8/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_28/8/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_27/8/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_22/8/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_21/8/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_20/8/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_19/8/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_19/8/2024:01431016 _x000D_16/8/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_15/8/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_14/8/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_13/8/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_12/8/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_9/8/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_8/8/2024:28/06/2024 _x000D_6/8/2024:28/06/2024 _x000D_5/8/2024:28/06/2024 _x000D_2/8/2024:28/06/2024 _x000D_1/8/2024:28/06/2024 _x000D_31/7/2024:28/06/2024 _x000D_31/7/2024:28/06/2024 _x000D_30/7/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_29/7/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_29/7/2024:01431016 _x000D_26/7/2024:01431016 _x000D_24/7/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_23/7/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_22/7/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_22/7/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_6/9/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_5/9/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_4/9/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_3/9/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_2/9/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_29/8/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_28/8/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_27/8/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_22/8/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_21/8/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_20/8/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_19/8/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_19/8/2024:01431016 _x000D_16/8/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_15/8/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_14/8/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_13/8/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_12/8/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_9/8/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_8/8/2024:28/06/2024 _x000D_6/8/2024:28/06/2024 _x000D_5/8/2024:28/06/2024 _x000D_2/8/2024:28/06/2024 _x000D_1/8/2024:28/06/2024 _x000D_31/7/2024:28/06/2024 _x000D_31/7/2024:28/06/2024 _x000D_30/7/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_29/7/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_29/7/2024:01431016 _x000D_26/7/2024:01431016 _x000D_24/7/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_23/7/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_22/7/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_22/7/2024:#UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | #UPDATE Order needs to be cancelled and re-raised in August/ September as there are currently no spare pairs available in the DP | 2024-06-07 |  |  |  |  | VFS1015606 | 30016683 | 1.Provisioning | AM |  | 2024-06-20 |  |  | 0 | [11 empty] | 0
1218 | 665342 | 3079 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Spar Parkhall | Antrim | BT41 1AJ |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_Address verification issue, email sent to VF - order is cancelled and will be reraised accordingly | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_Address verification issue, email sent to VF - order is cancelled and will be reraised accordingly | 0 | 0 | 2024-06-07 |  |  |  |  | Address query | 30016867 | 1.Provisioning | AM |  | 2024-06-21 |  |  | 0 | [11 empty] | 0
1219 | 231040 | 3096 | Batch 5 Jul24 | Type 1 | FTTP | Shop Local Archways | GLASGOW | G65 0BD |  | 16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:23/07/2024 10:40 _x000D_24/7/2024:Order Completed _x000D_23/7/2024:Order Completed _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_4/7/2024:#Update - Line plant works delay - Review date 22/06 _x000D_3/7/2024:#Update - Line plant works delay - Review date 22/06 _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Line plant works delay - Review date 22/06 _x000D_27/6/2024:#Update - Line plant works delay - Review date 22/06 _x000D_25/6/2024:#Update - Line plant works delay - Review date 22/06 _x000D_24/6/2024:#Update - Line plant works delay - Review date 22/06 _x000D_20/6/2024:#Update - Line plant works delay - Review date 22/06 _x000D_19/6/2024:#Update - Line plant works delay - Review date 22/06 _x000D_18/6/2024:#Update - Line plant works delay - Review date 22/06 _x000D_17/6/2024:#Update - Supplier delay. Review date of 04/06. Will check HUD when updates become available. _x000D_14/6/2024:#Update - Supplier delay. Review date of 04/06. Will check HUD when updates become available. _x000D_13/6/2024:#Update - Supplier delay. Review date of 04/06. Will check HUD when updates become available. _x000D_12/6/2024:#Update - Supplier delay. Review date of 04/06. Will check HUD when updates become available. _x000D_10/6/2024:#Update - Supplier delay. Review date of 04/06. Will check HUD when updates become available. _x000D_7/6/2024:#Update - Supplier delay. Review date of 04/06. Will check HUD when updates become available. _x000D_6/6/2024:#Update - Supplier delay. Review date of 04/06. Will check HUD when updates become available. _x000D_5/6/2024:#Update - Supplier delay. Review date of 04/06. Will check HUD when updates become available. _x000D_4/6/2024:#Update - Supplier delay. Review date of 04/06. Will check HUD when updates become available. _x000D_ | 16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:23/07/2024 10:40 _x000D_24/7/2024:Order Completed _x000D_23/7/2024:Order Completed _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_4/7/2024:#Update - Line plant works delay - Review date 22/06 _x000D_3/7/2024:#Update - Line plant works delay - Review date 22/06 _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Line plant works delay - Review date 22/06 _x000D_27/6/2024:#Update - Line plant works delay - Review date 22/06 _x000D_25/6/2024:#Update - Line plant works delay - Review date 22/06 _x000D_24/6/2024:#Update - Line plant works delay - Review date 22/06 _x000D_20/6/2024:#Update - Line plant works delay - Review date 22/06 _x000D_19/6/2024:#Update - Line plant works delay - Review date 22/06 _x000D_18/6/2024:#Update - Line plant works delay - Review date 22/06 _x000D_17/6/2024:#Update - Supplier delay. Review date of 04/06. Will check HUD when updates become available. _x000D_14/6/2024:#Update - Supplier delay. Review date of 04/06. Will check HUD when updates become available. _x000D_13/6/2024:#Update - Supplier delay. Review date of 04/06. Will check HUD when updates become available. _x000D_12/6/2024:#Update - Supplier delay. Review date of 04/06. Will check HUD when updates become available. _x000D_10/6/2024:#Update - Supplier delay. Review date of 04/06. Will check HUD when updates become available. _x000D_7/6/2024:#Update - Supplier delay. Review date of 04/06. Will check HUD when updates become available. _x000D_6/6/2024:#Update - Supplier delay. Review date of 04/06. Will check HUD when updates become available. _x000D_5/6/2024:#Update - Supplier delay. Review date of 04/06. Will check HUD when updates become available. _x000D_4/6/2024:#Update - Supplier delay. Review date of 04/06. Will check HUD when updates become available. _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2366131 | 30016856 | 6.Failed router install | [9 empty] | 2024-08-21 |  |  |  | 2024-08-16 | 23A004945396 | 23A004945396 | 2024-08-19 | 1
1220 | 423770 | 3105 | Batch 5 Jul24 | Type 1 | FTTP | SPAR CHAPEL ST LEONARDS | SKEGNESS | PE24 5SJ | 2024-07-11 | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_0 | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_0 |  |  | 2024-06-07 |  |  |  |  | VFP2394934 | 30017141 | 6.Failed router install |  |  | 2024-07-10 | 2024-07-10 | 2024-07-10 | TRUE |  |  |  | 2024-08-02 |  |  |  | 2024-08-02 | 23A004948783 |  | 2024-08-07 | 1
1221 | 466933 | 3112 | Batch 5 Jul24 | Type 1 | SOGEA | Carillon News | LOUGHBOROUGH | LE11 3XA |  | 22/7/2024:Order Completed _x000D_19/7/2024:0 _x000D_18/7/2024:Your order has been delayed due to a customer missed appointment. Customer not received router. Please check with end user and reappoint the order if still required. _x000D_17/7/2024:Your order has been delayed due to a customer missed appointment. Customer not received router. Please check with end user and reappoint the order if still required. _x000D_16/7/2024:Your order has been delayed due to a customer missed appointment. Customer not received router. Please check with end user and reappoint the order if still required. _x000D_15/7/2024:Your order has been delayed due to a customer missed appointment. Customer not received router. Please check with end user and reappoint the order if still required. _x000D_12/7/2024:Your order has been delayed due to a customer missed appointment. Customer not received router. Please check with end user and reappoint the order if still required. _x000D_11/7/2024:Your order has been delayed due to a customer missed appointment. Customer not received router. Please check with end user and reappoint the order if still required. _x000D_10/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 22/7/2024:Order Completed _x000D_19/7/2024:0 _x000D_18/7/2024:Your order has been delayed due to a customer missed appointment. Customer not received router. Please check with end user and reappoint the order if still required. _x000D_17/7/2024:Your order has been delayed due to a customer missed appointment. Customer not received router. Please check with end user and reappoint the order if still required. _x000D_16/7/2024:Your order has been delayed due to a customer missed appointment. Customer not received router. Please check with end user and reappoint the order if still required. _x000D_15/7/2024:Your order has been delayed due to a customer missed appointment. Customer not received router. Please check with end user and reappoint the order if still required. _x000D_12/7/2024:Your order has been delayed due to a customer missed appointment. Customer not received router. Please check with end user and reappoint the order if still required. _x000D_11/7/2024:Your order has been delayed due to a customer missed appointment. Customer not received router. Please check with end user and reappoint the order if still required. _x000D_10/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015492 | 30016861 | 6.Failed router install |  |  | 2024-07-16 | 2024-07-16 | 2024-07-16 | TRUE |  |  |  | 2024-08-07 |  |  |  | 2024-08-07 | 23A004946018 |  | 2024-08-08 | 1
1222 | 671666 | 3116 | Batch 5 Jul24 | Type 3 | SoGEA/Mobile | Spar Min Y Nant Stores | CAERNARFON | LL55 2DF | 2024-07-11 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Update: Order Completed by Supplier _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_0 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Update: Order Completed by Supplier _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_0 |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1069164 | 30017153 | 2.Commissioning | AM |  | 2024-08-14 | 2024-08-14 | 2024-08-14 14:38 | 1 | [11 empty] | 0
1223 | 484687 | 3139 | Batch 5 Jul24 | Type 1 | SOGEA | Nisa Local | Sutton Bridge | PE12 9SG |  | 19/7/2024:Update: Order Amended _x000D_18/7/2024:Update: Order Amended _x000D_17/7/2024:Update: Order Amended _x000D_16/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_15/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_12/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_11/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_10/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_0 | 19/7/2024:Update: Order Amended _x000D_18/7/2024:Update: Order Amended _x000D_17/7/2024:Update: Order Amended _x000D_16/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_15/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_12/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_11/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_10/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_0 |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1039014 | 30017216 | 2.Commissioning |  |  | 2024-07-09 | 2024-07-09 | 2024-07-09 | TRUE |  |  |  | 2024-07-31 | [7 empty] | 0
1224 | 487541 | 3147 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Day Today | Londonderry | BT48 9QH | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | 0 | 2024-06-07 |  |  |  |  | VFS1033697 | 30017199 | 1.Provisioning | AM |  | 2024-07-10 | 2024-09-06 |  | 0 | [11 empty] | 0
1225 | 445937 | 3168 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Spar | FIVEMILETOWN | BT75 0PW |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_Address verification issue, email sent to VF - order is cancelled and will be reraised accordingly | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_Address verification issue, email sent to VF - order is cancelled and will be reraised accordingly | 0 | 0 | 2024-06-07 |  |  |  |  | Address query | 30016750 | 1.Provisioning | AM |  | 2024-06-24 |  |  | 0 | [11 empty] | 0
1226 | 652572 | 3177 | Batch 5 Jul24 | Type 1 | SOGEA | Priyas Mini Market | Newcastle upon Tyne | NE15 6TS |  | 29/7/2024:Order Completed _x000D_29/7/2024:25/07/2024 10:32 _x000D_26/7/2024:25/07/2024 10:32 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_0 | 29/7/2024:Order Completed _x000D_29/7/2024:25/07/2024 10:32 _x000D_26/7/2024:25/07/2024 10:32 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_0 |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2416391 | 30017219 | 2.Commissioning |  |  | 2024-07-25 | 2024-07-25 | 2024-07-25 | TRUE |  |  |  | 2024-08-16 | [7 empty] | 0
1227 | 629565 | 3181 | Batch 5 Jul24 | Type 1 | SOGEA | Dalston Local | Hackney | E8 2PB |  | 19/7/2024:Update: Order Amended _x000D_18/7/2024:Update: Order Amended _x000D_17/7/2024:Update: Order Amended _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_0 | 19/7/2024:Update: Order Amended _x000D_18/7/2024:Update: Order Amended _x000D_17/7/2024:Update: Order Amended _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_0 |  |  | 2024-06-07 |  |  |  |  | Address query | Address query | 1.Provisioning | [17 empty] | 0
1228 | 667451 | 3184 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Spar Ligoniel | Ligoniel | BT14 8PS |  | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 25/07/2024.We will continue to provide update as they become available. _x000D_18/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 25/07/2024.We will continue to provide update as they become available. _x000D_17/7/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Proceed to install - Job can be completed on the day via 1 span from CBT on pole near property. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_3/7/2024:Proceed to install - Job can be completed on the day via 1 span from CBT on pole near property. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_2/7/2024:0 _x000D_1/7/2024:Proceed to install - Job can be completed on the day via 1 span from CBT on pole near property. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_27/6/2024:0 _x000D_25/6/2024:Proceed to install. Engineer to attempt install following existing OH copper route CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_24/6/2024:Proceed to install. Engineer to attempt install following existing OH copper route CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_20/6/2024:Proceed to install. Engineer to attempt install following existing OH copper route CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/6/2024:Proceed to install. Engineer to attempt install following existing OH copper route CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/6/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 25/07/2024.We will continue to provide update as they become available. _x000D_18/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 25/07/2024.We will continue to provide update as they become available. _x000D_17/7/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Proceed to install - Job can be completed on the day via 1 span from CBT on pole near property. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_3/7/2024:Proceed to install - Job can be completed on the day via 1 span from CBT on pole near property. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_2/7/2024:0 _x000D_1/7/2024:Proceed to install - Job can be completed on the day via 1 span from CBT on pole near property. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_27/6/2024:0 _x000D_25/6/2024:Proceed to install. Engineer to attempt install following existing OH copper route CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_24/6/2024:Proceed to install. Engineer to attempt install following existing OH copper route CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_20/6/2024:Proceed to install. Engineer to attempt install following existing OH copper route CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/6/2024:Proceed to install. Engineer to attempt install following existing OH copper route CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/6/2024:0 _x000D_0 | 0 | 0 | 2024-06-07 |  |  |  |  | VFP2416393 | 30017179 | 1.Provisioning | AM |  | 2024-08-27 | 2024-09-06 |  | 0 | [11 empty] | 0
1229 | 486860 | 3186 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Spar | Craigavon | BT62 4BU |  | 6/9/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_5/9/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_4/9/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_3/9/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_2/9/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_29/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_28/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_27/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_22/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_21/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_20/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_19/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_19/8/2024:01456219 _x000D_16/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_15/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_14/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_13/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_12/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_9/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_8/8/2024:31/07/2024 _x000D_6/8/2024:31/07/2024 _x000D_5/8/2024:31/07/2024 _x000D_2/8/2024:31/07/2024 _x000D_1/8/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_30/7/2024:#Update - This has been sent to the survey engineers and they have given us a review date of 31/07/2024. _x000D_29/7/2024:#Update - This has been sent to the survey engineers and they have given us a review date of 31/07/2024. _x000D_29/7/2024:01456219 _x000D_26/7/2024:01456219 _x000D_24/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 25/07/2024.We will continue to provide update as they become available. _x000D_23/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 25/07/2024.We will continue to provide update as they become available. _x000D_22/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 25/07/2024.We will continue to provide update as they become available. _x000D_22/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 25/07/2024.We will continue to provide update as they become available. _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_6/9/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_5/9/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_4/9/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_3/9/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_2/9/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_29/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_28/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_27/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_22/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_21/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_20/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_19/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_19/8/2024:01456219 _x000D_16/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_15/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_14/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_13/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_12/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_9/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. _x000D_8/8/2024:31/07/2024 _x000D_6/8/2024:31/07/2024 _x000D_5/8/2024:31/07/2024 _x000D_2/8/2024:31/07/2024 _x000D_1/8/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_30/7/2024:#Update - This has been sent to the survey engineers and they have given us a review date of 31/07/2024. _x000D_29/7/2024:#Update - This has been sent to the survey engineers and they have given us a review date of 31/07/2024. _x000D_29/7/2024:01456219 _x000D_26/7/2024:01456219 _x000D_24/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 25/07/2024.We will continue to provide update as they become available. _x000D_23/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 25/07/2024.We will continue to provide update as they become available. _x000D_22/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 25/07/2024.We will continue to provide update as they become available. _x000D_22/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 25/07/2024.We will continue to provide update as they become available. _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | #Update - .This has been sent to the survey engineers and they have given us a review date of 01/08/2024.We will continue to provide update as they become available. | 2024-06-07 |  |  |  |  | VFP2403207 | 30017195 | 1.Provisioning | AM |  | 2024-07-10 | 2024-07-16 |  | 0 | [11 empty] | 0
1230 | 486343 | 3208 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | SPAR NEW ROAD | CARDIFF | CF3 3BN |  | 27/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_22/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_21/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_20/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_19/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_19/8/2024:01515735 _x000D_16/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_14/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_13/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_12/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_9/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_29/7/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_29/7/2024:01515735 _x000D_26/7/2024:01515735 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_4/7/2024:#Update - This has been sent to the engineers and they have given us a review date of 26/06/2024. We will continue to provide update as they become available. _x000D_3/7/2024:#Update - This has been sent to the engineers and they have given us a review date of 26/06/2024. We will continue to provide update as they become available. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - This has been sent to the engineers and they have given us a review date of 26/06/2024. We will continue to provide update as they become available. _x000D_27/6/2024:#Update - This has been sent to the engineers and they have given us a review date of 26/06/2024. We will continue to provide update as they become available. _x000D_25/6/2024:#Update - This has been sent to the engineers and they have given us a review date of 26/06/2024. We will continue to provide update as they become available. _x000D_24/6/2024:Your order requires planning validation. We may contact your customer if we need to. You will receive a further update by 11-07-2024. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_20/6/2024:Your order has been delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 24/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot re _x000D_19/6/2024:Your order has been delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 24/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot re _x000D_18/6/2024:Your order has been delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 19/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot re _x000D_17/6/2024:Your order has been delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 19/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot re _x000D_14/6/2024:Your order has been delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 19/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot re _x000D_13/6/2024:Your order has been delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 14/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot re _x000D_12/6/2024:Your order has been delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 14/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot re _x000D_10/6/2024:Your order requires planning validation. We may contact your customer if we need to. You will receive a further update by 28-06-2024. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_7/6/2024:Your order has been delayed due to a sales query raised by our supplier. Customer contact details is required . Please confirm the contact details to progress the order further. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/6/2024:Your order has been delayed due to a sales query raised by our supplier. Customer contact details is required . Please confirm the contact details to progress the order further. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/6/2024:Your order has been delayed due to a sales query raised by our supplier. Customer contact details is required . Please confirm the contact details to progress the order further. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/6/2024:Your order has been delayed due to a sales query raised by our supplier. Customer contact details is required . Please confirm the contact details to progress the order further. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 27/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_22/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_21/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_20/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_19/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_19/8/2024:01515735 _x000D_16/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_14/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_13/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_12/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_9/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_29/7/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_29/7/2024:01515735 _x000D_26/7/2024:01515735 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_4/7/2024:#Update - This has been sent to the engineers and they have given us a review date of 26/06/2024. We will continue to provide update as they become available. _x000D_3/7/2024:#Update - This has been sent to the engineers and they have given us a review date of 26/06/2024. We will continue to provide update as they become available. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - This has been sent to the engineers and they have given us a review date of 26/06/2024. We will continue to provide update as they become available. _x000D_27/6/2024:#Update - This has been sent to the engineers and they have given us a review date of 26/06/2024. We will continue to provide update as they become available. _x000D_25/6/2024:#Update - This has been sent to the engineers and they have given us a review date of 26/06/2024. We will continue to provide update as they become available. _x000D_24/6/2024:Your order requires planning validation. We may contact your customer if we need to. You will receive a further update by 11-07-2024. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_20/6/2024:Your order has been delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 24/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot re _x000D_19/6/2024:Your order has been delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 24/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot re _x000D_18/6/2024:Your order has been delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 19/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot re _x000D_17/6/2024:Your order has been delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 19/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot re _x000D_14/6/2024:Your order has been delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 19/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot re _x000D_13/6/2024:Your order has been delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 14/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot re _x000D_12/6/2024:Your order has been delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 14/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot re _x000D_10/6/2024:Your order requires planning validation. We may contact your customer if we need to. You will receive a further update by 28-06-2024. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_7/6/2024:Your order has been delayed due to a sales query raised by our supplier. Customer contact details is required . Please confirm the contact details to progress the order further. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/6/2024:Your order has been delayed due to a sales query raised by our supplier. Customer contact details is required . Please confirm the contact details to progress the order further. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/6/2024:Your order has been delayed due to a sales query raised by our supplier. Customer contact details is required . Please confirm the contact details to progress the order further. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/6/2024:Your order has been delayed due to a sales query raised by our supplier. Customer contact details is required . Please confirm the contact details to progress the order further. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFP2426909 | 30017140 | 2.Commissioning | AM |  | 2024-08-23 | 2024-08-23 |  | 0 | [11 empty] | 0
1231 | 232322 | 3212 | Batch 5 Jul24 | Type 1 | SOGEA | SPAR SHAWBIRCH | TELFORD | TF5 0LW | 2024-07-03 | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1015471 | 30016765 | 6.Failed router install |  |  | 2024-07-02 | 2024-07-02 | 2024-07-02 | TRUE |  |  |  | 2024-08-02 |  |  |  | 2024-08-02 | 242005008943 |  | 2024-08-06 | 1
1232 | 467489 | 3217 | Batch 5 Jul24 | Type 1 | SOGEA | King Edward Store | Basildon | SS15 6GW | 2024-07-29 | 30/7/2024:Order Completed _x000D_29/7/2024:Order Completed _x000D_29/7/2024:26/07/2024 10:27 _x000D_26/7/2024:26/07/2024 09:55 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:Update: Order Amended _x000D_17/7/2024:Update: Order Amended _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 30/7/2024:Order Completed _x000D_29/7/2024:Order Completed _x000D_29/7/2024:26/07/2024 10:27 _x000D_26/7/2024:26/07/2024 09:55 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:Update: Order Amended _x000D_17/7/2024:Update: Order Amended _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1050671 | 30017217 | 6.Failed router install |  |  | 2024-07-26 | 2024-07-26 | 2024-07-26 | TRUE |  |  |  | 2024-08-16 |  |  |  | 2024-08-16 | 242005008506 | 242005008506 | 2024-08-19 | 1
1233 | 664622 | 3225 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Premier Stores | Swansea | SA2 0UU |  | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_18/7/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_17/7/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_16/7/2024:Update: Order Amended _x000D_15/7/2024:Update: Order Amended _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:Your order has been delayed due to a customer missed appointment. OOH appointment required. Please check with end user and reappoint the order if still required. _x000D_10/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_18/7/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_17/7/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_16/7/2024:Update: Order Amended _x000D_15/7/2024:Update: Order Amended _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:Your order has been delayed due to a customer missed appointment. OOH appointment required. Please check with end user and reappoint the order if still required. _x000D_10/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_0 | 0 | 0 | 2024-06-07 |  |  |  |  | VFP2416407 | 30016846 | 1.Provisioning | AM |  | 2024-08-27 | 2024-09-06 |  | 0 | [11 empty] | 0
1234 | 200383 | 3244 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Moscis Convenience Store | PETERLEE | SR8 4NU | 2024-07-11 | 6/9/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_5/9/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_4/9/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_3/9/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_2/9/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_29/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_28/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_27/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_22/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_21/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_20/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_19/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_19/8/2024:01481865 _x000D_16/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_15/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_14/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_13/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_12/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_9/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_8/8/2024:16/07/2024 _x000D_6/8/2024:16/07/2024 _x000D_5/8/2024:16/07/2024 _x000D_2/8/2024:16/07/2024 _x000D_1/8/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_30/7/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_29/7/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_29/7/2024:01481865 _x000D_26/7/2024:01481865 _x000D_24/7/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_23/7/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_22/7/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_22/7/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_19/7/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_18/7/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_17/7/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_16/7/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_15/7/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_12/7/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_11/7/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_10/7/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_9/7/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_4/7/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_3/7/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_2/7/2024:0 _x000D_1/7/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_27/6/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_25/6/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_24/6/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_20/6/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_19/6/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_18/6/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_17/6/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_14/6/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_13/6/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_12/6/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_10/6/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_7/6/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_6/6/2024:Your order has been delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 07/06/2204.We will continue to provide update as they become available. CSL Note: Invalid appointment slot rec _x000D_5/6/2024:Your order has been delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 07/06/2204.We will continue to provide update as they become available. CSL Note: Invalid appointment slot rec _x000D_4/6/2024:Your order has been delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 07/06/2204.We will continue to provide update as they become available. CSL Note: Invalid appointment slot rec _x000D_ | 9/9/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_6/9/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_5/9/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_4/9/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_3/9/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_2/9/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_29/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_28/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_27/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_22/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_21/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_20/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_19/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_19/8/2024:01481865 _x000D_16/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_15/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_14/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_13/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_12/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_9/8/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_8/8/2024:16/07/2024 _x000D_6/8/2024:16/07/2024 _x000D_5/8/2024:16/07/2024 _x000D_2/8/2024:16/07/2024 _x000D_1/8/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_30/7/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_29/7/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_29/7/2024:01481865 _x000D_26/7/2024:01481865 _x000D_24/7/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_23/7/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_22/7/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_22/7/2024:#Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 _x000D_19/7/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_18/7/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_17/7/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_16/7/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_15/7/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_12/7/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_11/7/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_10/7/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_9/7/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_4/7/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_3/7/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_2/7/2024:0 _x000D_1/7/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_27/6/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_25/6/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_24/6/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_20/6/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_19/6/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_18/6/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_17/6/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_14/6/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_13/6/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_12/6/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_10/6/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_7/6/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_6/6/2024:Your order has been delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 07/06/2204.We will continue to provide update as they become available. CSL Note: Invalid appointment slot rec _x000D_5/6/2024:Your order has been delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 07/06/2204.We will continue to provide update as they become available. CSL Note: Invalid appointment slot rec _x000D_4/6/2024:Your order has been delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 07/06/2204.We will continue to provide update as they become available. CSL Note: Invalid appointment slot rec _x000D_ | 0 | #Update - unsuccessful installation, requires an OOH appointment - OOH proposal sent to VF for review on 15/07 | 2024-06-07 |  |  |  |  | VFS1033694 | 30017182 | 1.Provisioning | AM |  | 2024-07-10 | 2024-08-30 |  | 0 | [11 empty] | 0
1235 | 659781 | 3248 | Batch 5 Jul24 | Type 1 | SOGEA | Kimberley Daily Choice | Nottingham | NG16 2PB |  | 23/7/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_22/7/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_22/7/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:Supplier Delay: Delayed in planning. Order completion may be delayed. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/6/2024:Supplier Delay: Delayed in planning. Order completion may be delayed. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/6/2024:Supplier Delay: Delayed in planning. Order completion may be delayed. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 23/7/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_22/7/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_22/7/2024:#Update Sales query OR want to confirm a 2nd line is needed _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:Supplier Delay: Delayed in planning. Order completion may be delayed. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/6/2024:Supplier Delay: Delayed in planning. Order completion may be delayed. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/6/2024:Supplier Delay: Delayed in planning. Order completion may be delayed. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015561 | 30016918 | 2.Commissioning |  |  | 2024-07-19 | 2024-07-19 | 2024-07-19 | TRUE |  |  |  | 2024-08-07 | [7 empty] | 0
1236 | 486302 | 3253 | Batch 5 Jul24 | Type 1 | SOGEA | SPAR MONKTON | PEMBROKE | SA71 4NA |  | 22/8/2024:#Update - Update from Openreach - Engineer advises NTE is in office as could not put through ceiling as no racks, fire hazard without racks. Shift order required with 2/3 hours TRC banding to move NTE to desired location & Cable trays provided _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 22/8/2024:#Update - Update from Openreach - Engineer advises NTE is in office as could not put through ceiling as no racks, fire hazard without racks. Shift order required with 2/3 hours TRC banding to move NTE to desired location & Cable trays provided _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1015560 | 30016704 | 2.Commissioning |  |  | 2024-07-08 | 2024-07-08 | 2024-07-08 | TRUE |  |  |  | 2024-08-07 | [7 empty] | 0
1237 | 669471 | 3257 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | TOWYN P/O SPAR FOURWAYS | ABERGELE | LL22 9HE |  | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:19/07/2024 12:54 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_16/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_15/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_12/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_11/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_10/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:19/07/2024 12:54 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_16/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_15/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_12/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_11/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_10/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | 0 | 2024-06-07 |  |  |  |  | VFP2416386 | 30016833 | 1.Provisioning | AM |  | 2024-08-09 | 2024-09-06 |  | 0 | [11 empty] | 0
1238 | 446033 | 3264 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Nisa Local | COLNE | BB8 0NQ | 2024-07-11 | 6/9/2024:#Update - Retailer aware of new appointment 16/09 _x000D_5/9/2024:#Update - Retailer aware of new appointment 16/09 _x000D_4/9/2024:#Update - Retailer aware of new appointment 16/09 _x000D_3/9/2024:#Update - Retailer aware of new appointment 16/09 _x000D_2/9/2024:#Update - Retailer aware of new appointment 16/09 _x000D_29/8/2024:#Update - Retailer aware of new appointment 16/09 _x000D_28/8/2024:#Update - Retailer aware of new appointment 16/09 _x000D_27/8/2024:#Update - Retailer aware of new appointment 16/09 _x000D_22/8/2024:#Update - Retailer unaware of appointment. Re-appointed for 16/09 - Am. Action for allwyn: Please contact retailer for confirmation that this appointment is appropriate. _x000D_21/8/2024:#Update - Retailer unaware of appointment. Re-appointed for 16/09 - Am. Action for allwyn: Please contact retailer for confirmation that this appointment is appropriate. _x000D_20/8/2024:#Update - Retailer unaware of appointment. Re-appointed for 16/09 - Am. Action for allwyn: Please contact retailer for confirmation that this appointment is appropriate. _x000D_19/8/2024:#Update - Retailer unaware of appointment. Re-appointed for 16/09 - Am. Action for allwyn: Please contact retailer for confirmation that this appointment is appropriate. _x000D_19/8/2024:01481838 _x000D_16/8/2024:#Update - Retailer unaware of appointment. Re-appointed for 16/09 - Am. Action for allwyn: Please contact retailer for confirmation that this appointment is appropriate. _x000D_15/8/2024:#Update - Retailer unaware of appointment. Re-appointed for 16/09 - Am. Action for allwyn: Please contact retailer for confirmation that this appointment is appropriate. _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_9/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_8/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_6/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:19/07/2024 16:12 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_0 | 9/9/2024:#Update - Retailer aware of new appointment 16/09 _x000D_6/9/2024:#Update - Retailer aware of new appointment 16/09 _x000D_5/9/2024:#Update - Retailer aware of new appointment 16/09 _x000D_4/9/2024:#Update - Retailer aware of new appointment 16/09 _x000D_3/9/2024:#Update - Retailer aware of new appointment 16/09 _x000D_2/9/2024:#Update - Retailer aware of new appointment 16/09 _x000D_29/8/2024:#Update - Retailer aware of new appointment 16/09 _x000D_28/8/2024:#Update - Retailer aware of new appointment 16/09 _x000D_27/8/2024:#Update - Retailer aware of new appointment 16/09 _x000D_22/8/2024:#Update - Retailer unaware of appointment. Re-appointed for 16/09 - Am. Action for allwyn: Please contact retailer for confirmation that this appointment is appropriate. _x000D_21/8/2024:#Update - Retailer unaware of appointment. Re-appointed for 16/09 - Am. Action for allwyn: Please contact retailer for confirmation that this appointment is appropriate. _x000D_20/8/2024:#Update - Retailer unaware of appointment. Re-appointed for 16/09 - Am. Action for allwyn: Please contact retailer for confirmation that this appointment is appropriate. _x000D_19/8/2024:#Update - Retailer unaware of appointment. Re-appointed for 16/09 - Am. Action for allwyn: Please contact retailer for confirmation that this appointment is appropriate. _x000D_19/8/2024:01481838 _x000D_16/8/2024:#Update - Retailer unaware of appointment. Re-appointed for 16/09 - Am. Action for allwyn: Please contact retailer for confirmation that this appointment is appropriate. _x000D_15/8/2024:#Update - Retailer unaware of appointment. Re-appointed for 16/09 - Am. Action for allwyn: Please contact retailer for confirmation that this appointment is appropriate. _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_9/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_8/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_6/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:19/07/2024 16:12 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_0 | 0 | #Update - Retailer aware of new appointment 16/09 | 2024-06-07 |  |  |  |  | VFS1034754 | 30017148 | 1.Provisioning | AM |  | 2024-07-10 | 2024-09-16 |  | 0 | [11 empty] | 0
1239 | 271037 | 3270 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Silverwood Service Station | CRAIGAVON | BT66 6LE |  | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_16/7/2024:Order Completed _x000D_15/7/2024:Order Completed _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Your order has been delayed due to multi skilled engineer work is required, order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 16/07/2024. _x000D_10/7/2024:Supplier Delay: Missed CCD and may require further work as the engineer has retained the job for next day _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_16/7/2024:Order Completed _x000D_15/7/2024:Order Completed _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Your order has been delayed due to multi skilled engineer work is required, order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 16/07/2024. _x000D_10/7/2024:Supplier Delay: Missed CCD and may require further work as the engineer has retained the job for next day _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_6/6/2024:0 _x000D_5/6/2024:0 _x000D_4/6/2024:0 _x000D_ | 0 | 0 | 2024-06-07 |  |  |  |  | VFP2416387 | 30016793 | 1.Provisioning | AM |  | 2024-08-27 | 2024-09-06 |  | 0 | [11 empty] | 0
1240 | 664854 | 3292 | Batch 5 Jul24 | Type 1 | SOGEA | Leverington Stores | Wisbech | PE13 5DB | 2024-07-05 | 19/7/2024:Update: Order Amended _x000D_18/7/2024:Update: Order Amended _x000D_17/7/2024:Update: Order Amended _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_0 | 19/7/2024:Update: Order Amended _x000D_18/7/2024:Update: Order Amended _x000D_17/7/2024:Update: Order Amended _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_0 |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1039013 | 30017221 | 6.Failed router install |  |  | 2024-07-04 | 2024-07-04 | 2024-07-08 | TRUE |  |  |  | 2024-07-31 |  |  |  | 2024-08-27 | 237004907618 | 237004907618 | 2024-08-28 | 1
1241 | 656507 | 3301 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Nisa Local | Derby | DE24 8TD |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:Your order has been delayed. The engineer has now completed all the external work and our suppliers has advised us to reappoint the order. Please check with end user and reappoint for the first available date. _x000D_4/7/2024:Your order has been delayed. The engineer has now completed all the external work and our suppliers has advised us to reappoint the order. Please check with end user and reappoint for the first available date. _x000D_3/7/2024:Your order has been delayed. The engineer has now completed all the external work and our suppliers has advised us to reappoint the order. Please check with end user and reappoint for the first available date. _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 06/07/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment slot received _x000D_25/6/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 06/07/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment slot received _x000D_24/6/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 06/07/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment slot received _x000D_20/6/2024:Supplier Delay: Issues with the line plant, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 14/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_14/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 14/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_13/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 14/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 14/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 08/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_7/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 08/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 08/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 06/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 06/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:Your order has been delayed. The engineer has now completed all the external work and our suppliers has advised us to reappoint the order. Please check with end user and reappoint for the first available date. _x000D_4/7/2024:Your order has been delayed. The engineer has now completed all the external work and our suppliers has advised us to reappoint the order. Please check with end user and reappoint for the first available date. _x000D_3/7/2024:Your order has been delayed. The engineer has now completed all the external work and our suppliers has advised us to reappoint the order. Please check with end user and reappoint for the first available date. _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 06/07/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment slot received _x000D_25/6/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 06/07/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment slot received _x000D_24/6/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 06/07/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment slot received _x000D_20/6/2024:Supplier Delay: Issues with the line plant, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 14/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_14/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 14/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_13/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 14/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 14/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 08/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_7/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 08/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 08/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 06/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 06/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 0 | 0 | 2024-06-07 |  |  |  |  | VFP2416394 | 30017189 | 1.Provisioning | AM |  | 2024-08-27 | 2024-08-27 |  | 0 | [11 empty] | 0
1242 | 484571 | 3318 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Cigs and Paper | Norwich | NR2 1AT |  | 6/9/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_5/9/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_4/9/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_3/9/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_2/9/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_29/8/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_28/8/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_27/8/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_22/8/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_21/8/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_20/8/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_19/8/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_19/8/2024:01458101 _x000D_16/8/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_14/8/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_13/8/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_12/8/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_9/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update with install date after this. _x000D_8/8/2024:05/08/2024 _x000D_6/8/2024:05/08/2024 _x000D_5/8/2024:05/08/2024 _x000D_2/8/2024:29/07/2024 _x000D_1/8/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_30/7/2024:#Update - Order was delayed due to step-1 work required, this has now been booked for 01/08 and CSL will update with install date after this. _x000D_29/7/2024:#Update - Order was delayed due to step-1 work required, this has now been booked for 01/08 and CSL will update with install date after this. _x000D_29/7/2024:01458101 _x000D_26/7/2024:01458101 _x000D_24/7/2024:#Update - Supplier delay- Step-1 work required. Our Suppliers have given us a review date of 29/07/2024. We will continue to provide update as they become available. _x000D_23/7/2024:#Update - Supplier delay- Step-1 work required. Our Suppliers have given us a review date of 29/07/2024. We will continue to provide update as they become available. _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_0 | 9/9/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_6/9/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_5/9/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_4/9/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_3/9/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_2/9/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_29/8/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_28/8/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_27/8/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_22/8/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_21/8/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_20/8/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_19/8/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_19/8/2024:01458101 _x000D_16/8/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_14/8/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_13/8/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_12/8/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_9/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update with install date after this. _x000D_8/8/2024:05/08/2024 _x000D_6/8/2024:05/08/2024 _x000D_5/8/2024:05/08/2024 _x000D_2/8/2024:29/07/2024 _x000D_1/8/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_30/7/2024:#Update - Order was delayed due to step-1 work required, this has now been booked for 01/08 and CSL will update with install date after this. _x000D_29/7/2024:#Update - Order was delayed due to step-1 work required, this has now been booked for 01/08 and CSL will update with install date after this. _x000D_29/7/2024:01458101 _x000D_26/7/2024:01458101 _x000D_24/7/2024:#Update - Supplier delay- Step-1 work required. Our Suppliers have given us a review date of 29/07/2024. We will continue to provide update as they become available. _x000D_23/7/2024:#Update - Supplier delay- Step-1 work required. Our Suppliers have given us a review date of 29/07/2024. We will continue to provide update as they become available. _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_0 | Update: Order Amended | #Update - Order has been delayed as civil work is required. CSL will update as more information become available. | 2024-06-07 |  |  |  |  | VFP2366083 | 30016722 | 1.Provisioning | AM |  | 2024-07-05 | 2024-09-09 |  | 0 | [11 empty] | 0
1243 | 656039 | 3348 | Batch 5 Jul24 | Type 1 | FTTP | Forest Hall Mini Market | Newcastle upon Tyne | NE12 8AR | 2024-07-11 | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1033699 | 30017194 | 6.Failed router install |  |  | 2024-07-10 | 2024-07-10 | 2024-07-10 | TRUE |  |  |  | 2024-07-31 |  |  |  | 2024-07-31 | 238004924270 |  | 2024-08-01 | 1
1244 | 205487 | 3365 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | J Toomey Motors Limited | Basildon | SS15 6RW |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_Address verification issue, email sent to VF - order is cancelled and will be reraised accordingly | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_Address verification issue, email sent to VF - order is cancelled and will be reraised accordingly | 0 | 0 | 2024-06-07 |  |  |  |  | Address query | 30016979 | 1.Provisioning | AM |  | 2024-06-27 |  |  | 0 | [11 empty] | 0
1245 | 608029 | 3377 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Culcheth Newsagents | Culcheth | WA3 4EJ |  | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 09:48 _x000D_26/7/2024:22/07/2024 09:48 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/07 AM _x000D_18/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/07 AM _x000D_17/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/07 AM _x000D_16/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/07 AM _x000D_15/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/07 AM _x000D_12/7/2024:#Update - Action for Allwyn - Installation has now been amended to 23/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 23/07 is a suitable date. _x000D_11/7/2024:#Update - Action for Allwyn - Installation has now been amended to 23/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 23/07 is a suitable date. _x000D_10/7/2024:#Update - Action for Allwyn - Installation has now been amended to 23/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 23/07 is a suitable date. _x000D_9/7/2024:#Update - Action for Allwyn - Installation has now been amended to 23/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 23/07 is a suitable date. _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 09:48 _x000D_26/7/2024:22/07/2024 09:48 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/07 AM _x000D_18/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/07 AM _x000D_17/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/07 AM _x000D_16/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/07 AM _x000D_15/7/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/07 AM _x000D_12/7/2024:#Update - Action for Allwyn - Installation has now been amended to 23/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 23/07 is a suitable date. _x000D_11/7/2024:#Update - Action for Allwyn - Installation has now been amended to 23/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 23/07 is a suitable date. _x000D_10/7/2024:#Update - Action for Allwyn - Installation has now been amended to 23/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 23/07 is a suitable date. _x000D_9/7/2024:#Update - Action for Allwyn - Installation has now been amended to 23/07 AM. Please speak with the retailer regarding installation details and confirm to CSL if 23/07 is a suitable date. _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_0 | 0 | 0 | 2024-06-07 |  |  |  |  | VFP2399224 | 30017214 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
1246 | 629237 | 3394 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Premier Ockerhill Convenience Store | Tipton | DY4 0EU |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_Completd 25/07/2024 10:00:00 however this site has a duplicate address key issue with site 652572, which is the site that is showing as polled -this is currently being resolved | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_Completd 25/07/2024 10:00:00 however this site has a duplicate address key issue with site 652572, which is the site that is showing as polled -this is currently being resolved | 0 | 0 | 2024-06-07 |  |  |  |  | VFP2416392 | 30017220 | 1.Provisioning | AM |  | 2024-07-25 | 2024-07-25 |  | 0 | [11 empty] | 0
1247 | 476372 | 3401 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Premier Round About Stores | Great Yarmouth | NR30 3BQ | 2024-08-12 | 29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:Order Completed _x000D_12/8/2024:Order Completed _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:Update: Order Amended _x000D_31/7/2024:Update: Order Amended _x000D_31/7/2024:37093 _x000D_30/7/2024:Update: Order Amended _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:25/07/2024 14:59 _x000D_26/7/2024:25/07/2024 14:59 _x000D_24/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_23/7/2024:0 _x000D_22/7/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_22/7/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:Order Completed _x000D_12/8/2024:Order Completed _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:Update: Order Amended _x000D_31/7/2024:Update: Order Amended _x000D_31/7/2024:37093 _x000D_30/7/2024:Update: Order Amended _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:25/07/2024 14:59 _x000D_26/7/2024:25/07/2024 14:59 _x000D_24/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_23/7/2024:0 _x000D_22/7/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_22/7/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1050516 | 30016787 | 6.Failed router install | [9 empty] | 2024-08-28 |  |  |  | 2024-08-28 | 242005011095 | 242005011095 | 2024-08-30 | 1
1248 | 646517 | 3407 | Batch 5 Jul24 | Type 1 | FTTP | Newfield Green | Sheffield | S2 2BS |  | 26/7/2024:24/07/2024 09:43 _x000D_24/7/2024:Order Completed _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:Update: Order Amended _x000D_17/7/2024:Update: Order Amended _x000D_16/7/2024:Update: Order Amended _x000D_15/7/2024:Update: Order Amended _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_10/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_9/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 26/7/2024:24/07/2024 09:43 _x000D_24/7/2024:Order Completed _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:Update: Order Amended _x000D_17/7/2024:Update: Order Amended _x000D_16/7/2024:Update: Order Amended _x000D_15/7/2024:Update: Order Amended _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_10/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_9/7/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1050517 | 30016968 | 2.Commissioning |  |  | 2024-07-24 | 2024-07-24 | 2024-07-24 | TRUE |  |  |  | 2024-09-06 | [7 empty] | 0
1249 | 642519 | 3424 | Batch 5 Jul24 | Type 1 | FTTP | Family Shopper | Skegness | PE25 2SA | 2024-07-23 | 26/7/2024:22/07/2024 12:31 _x000D_24/7/2024:Order Completed _x000D_23/7/2024:Order Completed _x000D_22/7/2024:0 _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_0 | 26/7/2024:22/07/2024 12:31 _x000D_24/7/2024:Order Completed _x000D_23/7/2024:Order Completed _x000D_22/7/2024:0 _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_0 |  |  | 2024-06-07 |  |  |  |  | VFP2394932 | 30017167 | 6.Failed router install |  |  | 2024-07-04 | 2024-07-22 | 2024-07-22 | TRUE |  |  |  | 2024-08-07 |  |  |  | 2024-08-07 | 242005008789 |  | 2024-08-08 | 1
1250 | 622853 | 3425 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | CK Supermarkets Ltd | Llanelli | SA16 0BT |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_Address verification issue, email sent to VF - order is cancelled and will be reraised accordingly | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_Address verification issue, email sent to VF - order is cancelled and will be reraised accordingly | 0 | 0 | 2024-06-07 |  |  |  |  | Address query | 30017224 | 1.Provisioning | AM |  | 2024-07-09 |  |  | 0 | [11 empty] | 0
1251 | 485960 | 3447 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | SPAR COALVILLE | Coalville | LE67 3JE |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_Address verification issue, email sent to VF - order is cancelled and will be reraised accordingly | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_Address verification issue, email sent to VF - order is cancelled and will be reraised accordingly | 0 | 0 | 2024-06-07 |  |  |  |  | Address query | 30016361 | 1.Provisioning | AM |  | 2024-07-01 |  |  | 0 | [11 empty] | 0
1252 | 465422 | 3481 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Spar Mount Eagle | BELFAST | BT17 0GY |  | 6/9/2024:#Update OR to advise of next steps, we will update you accordingly _x000D_5/9/2024:#Update OR to advise of next steps, we will update you accordingly _x000D_4/9/2024:#Update OR to advise of next steps, we will update you accordingly _x000D_3/9/2024:#Update OR to advise of next steps, we will update you accordingly _x000D_2/9/2024:#Update OR to advise of next steps, we will update you accordingly _x000D_29/8/2024:#Update OR to advise of next steps, we will update you accordingly _x000D_28/8/2024:#Update OR to advise of next steps, we will update you accordingly _x000D_27/8/2024:#Update OR to advise of next steps, we will update you accordingly _x000D_22/8/2024:#Update OR to advise of next steps, we will update you accordingly _x000D_21/8/2024:#Update OR to advise of next steps, we will update you accordingly _x000D_20/8/2024:#Update OR to advise of next steps, we will update you accordingly _x000D_19/8/2024:#Update OR to advise of next steps, we will update you accordingly _x000D_19/8/2024:01412250 _x000D_16/8/2024:#Update OR to advise of next steps, we will update you accordingly _x000D_15/8/2024:#Update OR to advise of next steps, we will update you accordingly _x000D_14/8/2024:#Update OR to advise of next steps, we will update you accordingly _x000D_13/8/2024:#Update OR to advise of next steps, we will update you accordingly _x000D_12/8/2024:#Update OR to advise of next steps, we will update you accordingly _x000D_9/8/2024:#Update OR to advise of next steps, we will update you accordingly _x000D_8/8/2024:25/07/2024 _x000D_6/8/2024:25/07/2024 _x000D_5/8/2024:25/07/2024 _x000D_2/8/2024:25/07/2024 _x000D_1/8/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_30/7/2024:#Update OR to advise of next steps, we will update you accordingly _x000D_29/7/2024:#Update OR to advise of next steps, we will update you accordingly _x000D_29/7/2024:01412250 _x000D_26/7/2024:01412250 _x000D_24/7/2024:#Update Retailer happy with appointment. 05/07, AM _x000D_23/7/2024:#Update Retailer happy with appointment. 05/07, AM _x000D_22/7/2024:#Update Retailer happy with appointment. 05/07, AM _x000D_22/7/2024:#Update Retailer happy with appointment. 05/07, AM _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update OR to advise of next steps, we will update you accordingly _x000D_6/9/2024:#Update OR to advise of next steps, we will update you accordingly _x000D_5/9/2024:#Update OR to advise of next steps, we will update you accordingly _x000D_4/9/2024:#Update OR to advise of next steps, we will update you accordingly _x000D_3/9/2024:#Update OR to advise of next steps, we will update you accordingly _x000D_2/9/2024:#Update OR to advise of next steps, we will update you accordingly _x000D_29/8/2024:#Update OR to advise of next steps, we will update you accordingly _x000D_28/8/2024:#Update OR to advise of next steps, we will update you accordingly _x000D_27/8/2024:#Update OR to advise of next steps, we will update you accordingly _x000D_22/8/2024:#Update OR to advise of next steps, we will update you accordingly _x000D_21/8/2024:#Update OR to advise of next steps, we will update you accordingly _x000D_20/8/2024:#Update OR to advise of next steps, we will update you accordingly _x000D_19/8/2024:#Update OR to advise of next steps, we will update you accordingly _x000D_19/8/2024:01412250 _x000D_16/8/2024:#Update OR to advise of next steps, we will update you accordingly _x000D_15/8/2024:#Update OR to advise of next steps, we will update you accordingly _x000D_14/8/2024:#Update OR to advise of next steps, we will update you accordingly _x000D_13/8/2024:#Update OR to advise of next steps, we will update you accordingly _x000D_12/8/2024:#Update OR to advise of next steps, we will update you accordingly _x000D_9/8/2024:#Update OR to advise of next steps, we will update you accordingly _x000D_8/8/2024:25/07/2024 _x000D_6/8/2024:25/07/2024 _x000D_5/8/2024:25/07/2024 _x000D_2/8/2024:25/07/2024 _x000D_1/8/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_30/7/2024:#Update OR to advise of next steps, we will update you accordingly _x000D_29/7/2024:#Update OR to advise of next steps, we will update you accordingly _x000D_29/7/2024:01412250 _x000D_26/7/2024:01412250 _x000D_24/7/2024:#Update Retailer happy with appointment. 05/07, AM _x000D_23/7/2024:#Update Retailer happy with appointment. 05/07, AM _x000D_22/7/2024:#Update Retailer happy with appointment. 05/07, AM _x000D_22/7/2024:#Update Retailer happy with appointment. 05/07, AM _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. | #Update OR to advise of next steps, we will update you accordingly | 2024-06-07 |  |  |  |  | VFP2363533 | 30016349 | 1.Provisioning | AM |  | 2024-07-05 | 2024-07-05 |  | 0 | [11 empty] | 0
1253 | 485471 | 3532 | Batch 5 Jul24 | Type 1 | FTTP | Londis Rossendale Road | BURNLEY | BB11 5DB | 2024-07-11 | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_27/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_25/6/2024:Your order has been delayed due to step-1 work required. Our Suppliers contacted Enduser and booked the engineer for 26/06/2024. Kindly review back on 28/06/2024 for more information. CSL Note: Invalid appointment slot received CSL Note: Invalid data rece _x000D_24/6/2024:Your order has been delayed due to step-1 work required. Our Suppliers contacted Enduser and booked the engineer for 26/06/2024. Kindly review back on 28/06/2024 for more information. CSL Note: Invalid appointment slot received CSL Note: Invalid data rece _x000D_20/6/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:Your order has been delayed by the suppliers. Site is not ready for the order. Please check with end user and confirm to progress the order further CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_14/6/2024:Your order has been delayed by the suppliers. Site is not ready for the order. Please check with end user and confirm to progress the order further CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_13/6/2024:Your order has been delayed by the suppliers. Site is not ready for the order. Please check with end user and confirm to progress the order further CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/6/2024:Your order has been delayed by the suppliers. Site is not ready for the order. Please check with end user and confirm to progress the order further CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/6/2024:Your order has been delayed due to step-1 work required. Our Suppliers contacted Enduser and booked the engineer for 07/06/2024. Kindly review back on 11/04/2024 for more information. CSL Note: Invalid appointment slot received CSL Note: Invalid data rece _x000D_7/6/2024:Your order has been delayed due to step-1 work required. Our Suppliers contacted Enduser and booked the engineer for 07/06/2024. Kindly review back on 11/04/2024 for more information. CSL Note: Invalid appointment slot received CSL Note: Invalid data rece _x000D_6/6/2024:Your order has been delayed due to step-1 work required. Our Suppliers contacted Enduser and booked the engineer for 07/06/2024. Kindly review back on 11/04/2024 for more information. CSL Note: Invalid appointment slot received CSL Note: Invalid data rece _x000D_5/6/2024:Your order has been delayed due to step-1 work required. Our Suppliers contacted Enduser and booked the engineer for 07/06/2024. Kindly review back on 11/04/2024 for more information. CSL Note: Invalid appointment slot received CSL Note: Invalid data rece _x000D_4/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 05/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:Update: Order Amended _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_27/6/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_25/6/2024:Your order has been delayed due to step-1 work required. Our Suppliers contacted Enduser and booked the engineer for 26/06/2024. Kindly review back on 28/06/2024 for more information. CSL Note: Invalid appointment slot received CSL Note: Invalid data rece _x000D_24/6/2024:Your order has been delayed due to step-1 work required. Our Suppliers contacted Enduser and booked the engineer for 26/06/2024. Kindly review back on 28/06/2024 for more information. CSL Note: Invalid appointment slot received CSL Note: Invalid data rece _x000D_20/6/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:Your order has been delayed by the suppliers. Site is not ready for the order. Please check with end user and confirm to progress the order further CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_14/6/2024:Your order has been delayed by the suppliers. Site is not ready for the order. Please check with end user and confirm to progress the order further CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_13/6/2024:Your order has been delayed by the suppliers. Site is not ready for the order. Please check with end user and confirm to progress the order further CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/6/2024:Your order has been delayed by the suppliers. Site is not ready for the order. Please check with end user and confirm to progress the order further CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/6/2024:Your order has been delayed due to step-1 work required. Our Suppliers contacted Enduser and booked the engineer for 07/06/2024. Kindly review back on 11/04/2024 for more information. CSL Note: Invalid appointment slot received CSL Note: Invalid data rece _x000D_7/6/2024:Your order has been delayed due to step-1 work required. Our Suppliers contacted Enduser and booked the engineer for 07/06/2024. Kindly review back on 11/04/2024 for more information. CSL Note: Invalid appointment slot received CSL Note: Invalid data rece _x000D_6/6/2024:Your order has been delayed due to step-1 work required. Our Suppliers contacted Enduser and booked the engineer for 07/06/2024. Kindly review back on 11/04/2024 for more information. CSL Note: Invalid appointment slot received CSL Note: Invalid data rece _x000D_5/6/2024:Your order has been delayed due to step-1 work required. Our Suppliers contacted Enduser and booked the engineer for 07/06/2024. Kindly review back on 11/04/2024 for more information. CSL Note: Invalid appointment slot received CSL Note: Invalid data rece _x000D_4/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 05/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFP2393892 | 30017177 | 2.Commissioning |  |  | 2024-07-10 | 2024-07-10 | 2024-07-10 | TRUE |  |  |  | 2024-08-12 | [7 empty] | 0
1254 | 670043 | 3534 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | TARLETON SPSO | PRESTON | PR4 6TU | 2024-07-03 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:Update: Order Amended _x000D_31/7/2024:Update: Order Amended _x000D_31/7/2024:37765 _x000D_30/7/2024:Update: Order Amended _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:19/07/2024 12:05 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:Update: Order Amended _x000D_31/7/2024:Update: Order Amended _x000D_31/7/2024:37765 _x000D_30/7/2024:Update: Order Amended _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:19/07/2024 12:05 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_12/7/2024:Update: Order Amended _x000D_11/7/2024:Update: Order Amended _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2436060 | 30016207 | 1.Provisioning | AM |  | 2024-08-23 | 2024-08-23 |  | 0 | [11 empty] | 0
1255 | 621917 | 3537 | Batch 5 Jul24 | Type 1 | FTTP | Premier Pant Stores | Merthyr Tydfil | CF48 2BY |  | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_0 | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_0 |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2394931 | 30017170 | 6.Failed router install |  |  | 2024-07-08 | 2024-07-08 | 2024-07-08 | TRUE |  |  |  | 2024-08-05 |  |  |  | 2024-08-05 | 239004929412 |  | 2024-08-06 | 1
1256 | 661214 | 3538 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Spar | Ballymena | BT42 1JU |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:08 _x000D_26/7/2024:22/07/2024 10:08 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_0 | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:08 _x000D_26/7/2024:22/07/2024 10:08 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_0 | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2393897 | 30017196 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
1257 | 485572 | 3578 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Baker Street News and Convenience | London | NW1 5RT |  | 6/9/2024:#Update Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 06/09/2024. We will continue to provide update as they become available. _x000D_5/9/2024:#Update Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 06/09/2024. We will continue to provide update as they become available. _x000D_4/9/2024:#Update Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 06/09/2024. We will continue to provide update as they become available. _x000D_3/9/2024:#Update Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 06/09/2024. We will continue to provide update as they become available. _x000D_2/9/2024:#Update Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 06/09/2024. We will continue to provide update as they become available. _x000D_29/8/2024:#Update Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 06/09/2024. We will continue to provide update as they become available. _x000D_28/8/2024:#Update Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 06/09/2024. We will continue to provide update as they become available. _x000D_27/8/2024:#Update - NFA - Allwyn confirmed new installation date 08/08 - AM with retailer _x000D_22/8/2024:#Update - NFA - Allwyn confirmed new installation date 08/08 - AM with retailer _x000D_21/8/2024:#Update - NFA - Allwyn confirmed new installation date 08/08 - AM with retailer _x000D_20/8/2024:#Update - NFA - Allwyn confirmed new installation date 08/08 - AM with retailer _x000D_19/8/2024:#Update - NFA - Allwyn confirmed new installation date 08/08 - AM with retailer _x000D_19/8/2024:01413832 _x000D_16/8/2024:#Update - NFA - Allwyn confirmed new installation date 08/08 - AM with retailer _x000D_15/8/2024:#Update - NFA - Allwyn confirmed new installation date 08/08 - AM with retailer _x000D_14/8/2024:#Update - NFA - Allwyn confirmed new installation date 08/08 - AM with retailer _x000D_13/8/2024:#Update - NFA - Allwyn confirmed new installation date 08/08 - AM with retailer _x000D_12/8/2024:#Update - NFA - Allwyn confirmed new installation date 08/08 - AM with retailer _x000D_9/8/2024:#Update - NFA - Allwyn confirmed new installation date 08/08 - AM with retailer _x000D_8/8/2024:01/08/2024 _x000D_6/8/2024:01/08/2024 _x000D_5/8/2024:01/08/2024 _x000D_2/8/2024:01/08/2024 _x000D_1/8/2024:23/07/2024 _x000D_31/7/2024:23/07/2024 _x000D_31/7/2024:23/07/2024 _x000D_30/7/2024:#Update Reappointed to 08/08, AM. Action on Allwyn - ensure the retailer is aware. _x000D_29/7/2024:#Update Reappointed to 08/08, AM. Action on Allwyn - ensure the retailer is aware. _x000D_29/7/2024:01413832 _x000D_26/7/2024:01413832 _x000D_24/7/2024:#Update Reappointed to 08/08, AM. Action on Allwyn - ensure the retailer is aware. _x000D_23/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 05/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order has been delayed due to step-1 work required. Our Suppliers contacted Enduser and booked the engineer for 17/07/2024. Kindly review back on 19/07/2024 for more information. CSL Note: Invalid appointment slot received CSL Note: Invalid data rece _x000D_22/7/2024:Your order has been delayed due to step-1 work required. Our Suppliers contacted Enduser and booked the engineer for 17/07/2024. Kindly review back on 19/07/2024 for more information. CSL Note: Invalid appointment slot received CSL Note: Invalid data rece _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Update: Order Completed by Supplier _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_0 | 9/9/2024:#Update Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 06/09/2024. We will continue to provide update as they become available. _x000D_6/9/2024:#Update Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 06/09/2024. We will continue to provide update as they become available. _x000D_5/9/2024:#Update Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 06/09/2024. We will continue to provide update as they become available. _x000D_4/9/2024:#Update Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 06/09/2024. We will continue to provide update as they become available. _x000D_3/9/2024:#Update Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 06/09/2024. We will continue to provide update as they become available. _x000D_2/9/2024:#Update Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 06/09/2024. We will continue to provide update as they become available. _x000D_29/8/2024:#Update Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 06/09/2024. We will continue to provide update as they become available. _x000D_28/8/2024:#Update Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 06/09/2024. We will continue to provide update as they become available. _x000D_27/8/2024:#Update - NFA - Allwyn confirmed new installation date 08/08 - AM with retailer _x000D_22/8/2024:#Update - NFA - Allwyn confirmed new installation date 08/08 - AM with retailer _x000D_21/8/2024:#Update - NFA - Allwyn confirmed new installation date 08/08 - AM with retailer _x000D_20/8/2024:#Update - NFA - Allwyn confirmed new installation date 08/08 - AM with retailer _x000D_19/8/2024:#Update - NFA - Allwyn confirmed new installation date 08/08 - AM with retailer _x000D_19/8/2024:01413832 _x000D_16/8/2024:#Update - NFA - Allwyn confirmed new installation date 08/08 - AM with retailer _x000D_15/8/2024:#Update - NFA - Allwyn confirmed new installation date 08/08 - AM with retailer _x000D_14/8/2024:#Update - NFA - Allwyn confirmed new installation date 08/08 - AM with retailer _x000D_13/8/2024:#Update - NFA - Allwyn confirmed new installation date 08/08 - AM with retailer _x000D_12/8/2024:#Update - NFA - Allwyn confirmed new installation date 08/08 - AM with retailer _x000D_9/8/2024:#Update - NFA - Allwyn confirmed new installation date 08/08 - AM with retailer _x000D_8/8/2024:01/08/2024 _x000D_6/8/2024:01/08/2024 _x000D_5/8/2024:01/08/2024 _x000D_2/8/2024:01/08/2024 _x000D_1/8/2024:23/07/2024 _x000D_31/7/2024:23/07/2024 _x000D_31/7/2024:23/07/2024 _x000D_30/7/2024:#Update Reappointed to 08/08, AM. Action on Allwyn - ensure the retailer is aware. _x000D_29/7/2024:#Update Reappointed to 08/08, AM. Action on Allwyn - ensure the retailer is aware. _x000D_29/7/2024:01413832 _x000D_26/7/2024:01413832 _x000D_24/7/2024:#Update Reappointed to 08/08, AM. Action on Allwyn - ensure the retailer is aware. _x000D_23/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 05/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order has been delayed due to step-1 work required. Our Suppliers contacted Enduser and booked the engineer for 17/07/2024. Kindly review back on 19/07/2024 for more information. CSL Note: Invalid appointment slot received CSL Note: Invalid data rece _x000D_22/7/2024:Your order has been delayed due to step-1 work required. Our Suppliers contacted Enduser and booked the engineer for 17/07/2024. Kindly review back on 19/07/2024 for more information. CSL Note: Invalid appointment slot received CSL Note: Invalid data rece _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Update: Order Completed by Supplier _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_0 | Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 11/09/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received | #Update Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 06/09/2024. We will continue to provide update as they become available. | 2024-06-07 |  |  |  |  | VFP2461355 | 30016610 | 1.Provisioning | AM |  | 2024-07-03 | 2024-08-08 |  | 0 | [11 empty] | 0
1258 | 459085 | 3636 | Batch 5 Jul24 | Type 1 | FTTP | One Stop Shop | GLASGOW | G51 4EH | 2024-07-11 | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_0 | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_0 |  |  | 2024-06-07 |  |  |  |  | VFP2393898 | 30017174 | 2.Commissioning |  |  | 2024-07-10 | 2024-07-10 | 2024-07-10 | TRUE |  |  |  | 2024-08-02 | [7 empty] | 0
1259 | 665817 | 3643 | Batch 5 Jul24 | Type 1 | SOGEA | Aughton Post Office | SHEFFIELD | S26 3XH | 2024-07-11 | 19/7/2024:Update: Order Amended _x000D_18/7/2024:Update: Order Amended _x000D_17/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_16/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_15/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_12/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_11/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_10/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_0 | 19/7/2024:Update: Order Amended _x000D_18/7/2024:Update: Order Amended _x000D_17/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_16/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_15/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_12/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_11/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_10/7/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_0 |  |  | 2024-06-07 |  |  |  |  | VFS1033702 | 30017186 | 2.Commissioning |  |  | 2024-07-10 | 2024-07-10 | 2024-07-10 | TRUE |  |  |  | 2024-08-02 | [7 empty] | 0
1260 | 658940 | 3654 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Spar | Tamworth | B77 4EW |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_Order rejected - FTTP and SOGEA rejected, CSL investigating other options 27/08 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_Order rejected - FTTP and SOGEA rejected, CSL investigating other options 27/08 | 0 | 0 | 2024-06-07 |  |  |  |  | Address query | 30017152 | 1.Provisioning | AM |  | 2024-07-08 |  |  | 0 | [11 empty] | 0
1261 | 637612 | 3656 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Nash and Gardners Budgens | East Finchley | N2 8AQ |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_Order rejected due to Openreach issue - order being reraised 28/08 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_Order rejected due to Openreach issue - order being reraised 28/08 | 0 | 0 | 2024-06-07 |  |  |  |  | VFS1038343 | 30017222 | 1.Provisioning | AM |  |  |  |  | 0 | [11 empty] | 0
1262 | 101998 | 3657 | Batch 5 Jul24 | Type 1 | SOGEA | Patel Brothers | TELFORD | TF7 5LZ | 2024-07-11 | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFS1033701 | 30017176 | 2.Commissioning |  |  | 2024-07-10 | 2024-07-10 | 2024-07-10 | TRUE |  |  |  | 2024-08-12 | [7 empty] | 0
1263 | 665268 | 3662 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Parkside Post Office | STOCKPORT | SK7 3LQ |  | 6/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 30/07 _x000D_5/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 30/07 _x000D_4/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 30/07 _x000D_3/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 30/07 _x000D_2/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 30/07 _x000D_29/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 30/07 _x000D_28/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 30/07 _x000D_27/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 30/07 _x000D_22/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 30/07 _x000D_21/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 30/07 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:Update: Order Amended _x000D_31/7/2024:Update: Order Amended _x000D_31/7/2024:37781 _x000D_30/7/2024:Update: Order Amended _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:25/07/2024 15:26 _x000D_26/7/2024:25/07/2024 15:26 _x000D_24/7/2024:Supplier Delay: New Appointment might be required _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_0 | 9/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 30/07 _x000D_6/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 30/07 _x000D_5/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 30/07 _x000D_4/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 30/07 _x000D_3/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 30/07 _x000D_2/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 30/07 _x000D_29/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 30/07 _x000D_28/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 30/07 _x000D_27/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 30/07 _x000D_22/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 30/07 _x000D_21/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 30/07 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:Update: Order Amended _x000D_31/7/2024:Update: Order Amended _x000D_31/7/2024:37781 _x000D_30/7/2024:Update: Order Amended _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:25/07/2024 15:26 _x000D_26/7/2024:25/07/2024 15:26 _x000D_24/7/2024:Supplier Delay: New Appointment might be required _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_0 | 0 | #Update - awaiting ECC approval from customer - proposal sent to VF 30/07 | 2024-06-07 |  |  |  |  | VFS1050519 | 30016230 | 1.Provisioning | AM |  | 2024-07-24 | 2024-08-27 |  | 0 | [11 empty] | 0
1264 | 480403 | 3663 | Batch 5 Jul24 | Type 1 | SOGEA | Premier Cot House Services | Dunoon | PA23 8QT | 2024-07-11 | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_16/7/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_15/7/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_12/7/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_11/7/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_10/7/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_0 | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_16/7/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_15/7/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_12/7/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_11/7/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_10/7/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_0 |  |  | 2024-06-07 |  |  |  |  | VFS1033703 | 30017175 | 2.Commissioning |  |  | 2024-07-10 | 2024-07-10 | 2024-07-10 | TRUE | [11 empty] | 0
1265 | 670381 | 3664 | Batch 5 Jul24 | Type 3 | FTTP/Mobile | COOKSTOWN CFPO & SUPERVALU | COOKSTOWN | BT80 8DJ | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 02/09/2024. We will continue to provide update as they become available. _x000D_20/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 02/09/2024. We will continue to provide update as they become available. _x000D_19/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 02/09/2024. We will continue to provide update as they become available. _x000D_19/8/2024:14/08/2024 09:27 _x000D_16/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 02/09/2024. We will continue to provide update as they become available. _x000D_15/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 02/09/2024. We will continue to provide update as they become available. _x000D_14/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 02/09/2024. We will continue to provide update as they become available. _x000D_13/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 14/08/2024. We will continue to provide update as they become available. _x000D_12/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 14/08/2024. We will continue to provide update as they become available. _x000D_9/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 14/08/2024. We will continue to provide update as they become available. _x000D_8/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 14/08/2024. We will continue to provide update as they become available. _x000D_6/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 07/08/2024. We will continue to provide update as they become available. _x000D_5/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 07/08/2024. We will continue to provide update as they become available. _x000D_2/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 07/08/2024. We will continue to provide update as they become available. _x000D_1/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 07/08/2024. We will continue to provide update as they become available. _x000D_31/7/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 07/08/2024. We will continue to provide update as they become available. _x000D_31/7/2024:37814 _x000D_30/7/2024:Update: Order Amended _x000D_29/7/2024:Your order has been delayed due to a sales query raised by our suppliers. This is due to extra construction charges in supplying a line. please check and confirm charges acceptance to proceed this order. _x000D_29/7/2024:22/07/2024 11:49 _x000D_26/7/2024:22/07/2024 11:49 _x000D_24/7/2024:Your order has been delayed due to a sales query raised by our suppliers. This is due to extra construction charges in supplying a line. please check and confirm charges acceptance to proceed this order. _x000D_23/7/2024:Your order has been delayed due to a sales query raised by our suppliers. This is due to extra construction charges in supplying a line. please check and confirm charges acceptance to proceed this order. _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_17/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_16/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_11/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 02/09/2024. We will continue to provide update as they become available. _x000D_20/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 02/09/2024. We will continue to provide update as they become available. _x000D_19/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 02/09/2024. We will continue to provide update as they become available. _x000D_19/8/2024:14/08/2024 09:27 _x000D_16/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 02/09/2024. We will continue to provide update as they become available. _x000D_15/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 02/09/2024. We will continue to provide update as they become available. _x000D_14/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 02/09/2024. We will continue to provide update as they become available. _x000D_13/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 14/08/2024. We will continue to provide update as they become available. _x000D_12/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 14/08/2024. We will continue to provide update as they become available. _x000D_9/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 14/08/2024. We will continue to provide update as they become available. _x000D_8/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 14/08/2024. We will continue to provide update as they become available. _x000D_6/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 07/08/2024. We will continue to provide update as they become available. _x000D_5/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 07/08/2024. We will continue to provide update as they become available. _x000D_2/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 07/08/2024. We will continue to provide update as they become available. _x000D_1/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 07/08/2024. We will continue to provide update as they become available. _x000D_31/7/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 07/08/2024. We will continue to provide update as they become available. _x000D_31/7/2024:37814 _x000D_30/7/2024:Update: Order Amended _x000D_29/7/2024:Your order has been delayed due to a sales query raised by our suppliers. This is due to extra construction charges in supplying a line. please check and confirm charges acceptance to proceed this order. _x000D_29/7/2024:22/07/2024 11:49 _x000D_26/7/2024:22/07/2024 11:49 _x000D_24/7/2024:Your order has been delayed due to a sales query raised by our suppliers. This is due to extra construction charges in supplying a line. please check and confirm charges acceptance to proceed this order. _x000D_23/7/2024:Your order has been delayed due to a sales query raised by our suppliers. This is due to extra construction charges in supplying a line. please check and confirm charges acceptance to proceed this order. _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_17/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_16/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_11/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | 0 | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2393895 | 30017191 | 2.Commissioning | AM |  | 2024-07-10 | 2024-07-10 |  | 0 |  |  |  | 2024-09-09 | [7 empty] | 0
1266 | 665557 | 3668 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Yardley Costcutter | Birmingham | B27 6LL |  | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 09:44 _x000D_26/7/2024:22/07/2024 09:44 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 09:44 _x000D_26/7/2024:22/07/2024 09:44 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_0 | 0 | 0 | 2024-06-07 |  |  |  |  | VFP2424549 | 30016397 | 1.Provisioning | AM |  | 2024-08-08 | 2024-09-06 |  | 0 | [11 empty] | 0
1267 | 658888 | 3669 | Batch 5 Jul24 | Type 1 | FTTP | Bestone | Inverness | IV3 8HS | 2024-07-11 | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFP2393900 | 30017197 | 6.Failed router install |  |  | 2024-07-10 | 2024-07-10 | 2024-07-10 | TRUE | [7 empty] | 2024-08-21 | 239004929649 | 239004929649 | 2024-08-21 | 1
1268 | 633473 | 3683 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Russells Food & Drink | Belfast | BT6 9DR |  | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:Supplier Delay: Delay due to Frames Complications, please await for further details CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:Supplier Delay: Delay due to Frames Complications, please await for further details CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:Supplier Delay: Delay due to Frames Complications, please await for further details CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:Supplier Delay: Delay due to Frames Complications, please await for further details CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | 0 | 2024-06-07 |  |  |  |  | VFP2416388 | 30016456 | 1.Provisioning | AM |  | 2024-08-27 | 2024-09-06 |  | 0 | [11 empty] | 0
1269 | 469133 | 3719 | Batch 5 Jul24 | Type 1 | FTTP | One O One | Glasgow | G52 4BE | 2024-07-11 | 19/7/2024:#Update - Awaiting address query, Emailed allwyn to confirm. _x000D_18/7/2024:#Update - Awaiting address query, Emailed allwyn to confirm. _x000D_17/7/2024:#Update- Rejected on HUD- Querying with engineer about address, as this apears to be correct via google. Will re-appoint if this is all good to go. _x000D_16/7/2024:#Update- Rejected on HUD- Querying with engineer about address, as this apears to be correct via google. Will re-appoint if this is all good to go. _x000D_15/7/2024:#Update- Rejected on HUD- Querying with engineer about address, as this apears to be correct via google. Will re-appoint if this is all good to go. _x000D_12/7/2024:#Update- Rejected on HUD- Querying with engineer about address, as this apears to be correct via google. Will re-appoint if this is all good to go. _x000D_11/7/2024:#Update- Rejected on HUD- Querying with engineer about address, as this apears to be correct via google. Will re-appoint if this is all good to go. _x000D_10/7/2024:#Update- Rejected on HUD- Querying with engineer about address, as this apears to be correct via google. Will re-appoint if this is all good to go. _x000D_9/7/2024:#Update- Rejected on HUD- Querying with engineer about address, as this apears to be correct via google. Will re-appoint if this is all good to go. _x000D_4/7/2024:#Update- Rejected on HUD- Querying with engineer about address, as this apears to be correct via google. Will re-appoint if this is all good to go. _x000D_3/7/2024:#Update- Rejected on HUD- Querying with engineer about address, as this apears to be correct via google. Will re-appoint if this is all good to go. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update- Rejected on HUD- Querying with engineer about address, as this apears to be correct via google. Will re-appoint if this is all good to go. _x000D_27/6/2024:#Update- Rejected on HUD- Querying with engineer about address, as this apears to be correct via google. Will re-appoint if this is all good to go. _x000D_25/6/2024:#Update- Rejected on HUD- Querying with engineer about address, as this apears to be correct via google. Will re-appoint if this is all good to go. _x000D_24/6/2024:#Update- Rejected on HUD- Querying with engineer about address, as this apears to be correct via google. Will re-appoint if this is all good to go. _x000D_20/6/2024:#Update- Rejected on HUD- Querying with engineer about address, as this apears to be correct via google. Will re-appoint if this is all good to go. _x000D_19/6/2024:#Update- Rejected on HUD- Querying with engineer about address, as this apears to be correct via google. Will re-appoint if this is all good to go. _x000D_18/6/2024:#Update - Supplier delay, Review date 10/06 _x000D_17/6/2024:#Update - Supplier delay, Review date 10/06 _x000D_14/6/2024:#Update - Supplier delay, Review date 10/06 _x000D_13/6/2024:#Update - Supplier delay, Review date 10/06 _x000D_12/6/2024:#Update - Supplier delay, Review date 10/06 _x000D_10/6/2024:#Update - Supplier delay, Review date 10/06 _x000D_7/6/2024:#Update - Supplier delay, Review date 10/06 _x000D_6/6/2024:#Update - Supplier delay, Review date 10/06 _x000D_5/6/2024:#Update - Supplier delay, Review date 10/06 _x000D_4/6/2024:#Update - Supplier delay, Review date 10/06 _x000D_ | 19/7/2024:#Update - Awaiting address query, Emailed allwyn to confirm. _x000D_18/7/2024:#Update - Awaiting address query, Emailed allwyn to confirm. _x000D_17/7/2024:#Update- Rejected on HUD- Querying with engineer about address, as this apears to be correct via google. Will re-appoint if this is all good to go. _x000D_16/7/2024:#Update- Rejected on HUD- Querying with engineer about address, as this apears to be correct via google. Will re-appoint if this is all good to go. _x000D_15/7/2024:#Update- Rejected on HUD- Querying with engineer about address, as this apears to be correct via google. Will re-appoint if this is all good to go. _x000D_12/7/2024:#Update- Rejected on HUD- Querying with engineer about address, as this apears to be correct via google. Will re-appoint if this is all good to go. _x000D_11/7/2024:#Update- Rejected on HUD- Querying with engineer about address, as this apears to be correct via google. Will re-appoint if this is all good to go. _x000D_10/7/2024:#Update- Rejected on HUD- Querying with engineer about address, as this apears to be correct via google. Will re-appoint if this is all good to go. _x000D_9/7/2024:#Update- Rejected on HUD- Querying with engineer about address, as this apears to be correct via google. Will re-appoint if this is all good to go. _x000D_4/7/2024:#Update- Rejected on HUD- Querying with engineer about address, as this apears to be correct via google. Will re-appoint if this is all good to go. _x000D_3/7/2024:#Update- Rejected on HUD- Querying with engineer about address, as this apears to be correct via google. Will re-appoint if this is all good to go. _x000D_2/7/2024:A1 (Site access failure) _x000D_1/7/2024:#Update- Rejected on HUD- Querying with engineer about address, as this apears to be correct via google. Will re-appoint if this is all good to go. _x000D_27/6/2024:#Update- Rejected on HUD- Querying with engineer about address, as this apears to be correct via google. Will re-appoint if this is all good to go. _x000D_25/6/2024:#Update- Rejected on HUD- Querying with engineer about address, as this apears to be correct via google. Will re-appoint if this is all good to go. _x000D_24/6/2024:#Update- Rejected on HUD- Querying with engineer about address, as this apears to be correct via google. Will re-appoint if this is all good to go. _x000D_20/6/2024:#Update- Rejected on HUD- Querying with engineer about address, as this apears to be correct via google. Will re-appoint if this is all good to go. _x000D_19/6/2024:#Update- Rejected on HUD- Querying with engineer about address, as this apears to be correct via google. Will re-appoint if this is all good to go. _x000D_18/6/2024:#Update - Supplier delay, Review date 10/06 _x000D_17/6/2024:#Update - Supplier delay, Review date 10/06 _x000D_14/6/2024:#Update - Supplier delay, Review date 10/06 _x000D_13/6/2024:#Update - Supplier delay, Review date 10/06 _x000D_12/6/2024:#Update - Supplier delay, Review date 10/06 _x000D_10/6/2024:#Update - Supplier delay, Review date 10/06 _x000D_7/6/2024:#Update - Supplier delay, Review date 10/06 _x000D_6/6/2024:#Update - Supplier delay, Review date 10/06 _x000D_5/6/2024:#Update - Supplier delay, Review date 10/06 _x000D_4/6/2024:#Update - Supplier delay, Review date 10/06 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFP2393899 | 30017192 | 6.Failed router install |  |  | 2024-07-10 | 2024-07-10 | 2024-07-10 | TRUE |  |  |  | 2024-08-02 |  |  |  | 2024-08-02 | 242005013370 |  | 2024-08-06 | 1
1270 | 622819 | 3727 | Batch 5 Jul24 | Type 3 | FTTP/Mobile | Day Today Express | Edinburgh | EH16 4UT |  | 6/9/2024:#Update - Customer unaware of visit. The rescheduled install date is 27/08 - AM between 8am-1pm. _x000D_5/9/2024:#Update - Customer unaware of visit. The rescheduled install date is 27/08 - AM between 8am-1pm. _x000D_4/9/2024:#Update - Customer unaware of visit. The rescheduled install date is 27/08 - AM between 8am-1pm. _x000D_3/9/2024:#Update - Customer unaware of visit. The rescheduled install date is 27/08 - AM between 8am-1pm. _x000D_2/9/2024:#Update - Customer unaware of visit. The rescheduled install date is 27/08 - AM between 8am-1pm. _x000D_29/8/2024:#Update - Customer unaware of visit. The rescheduled install date is 27/08 - AM between 8am-1pm. _x000D_28/8/2024:#Update - Customer unaware of visit. The rescheduled install date is 27/08 - AM between 8am-1pm. _x000D_27/8/2024:#Update - Customer unaware of visit. The rescheduled install date is 27/08 - AM between 8am-1pm. _x000D_22/8/2024:#Update - Customer unaware of visit. The rescheduled install date is 27/08 - AM between 8am-1pm. _x000D_21/8/2024:#Update - Customer unaware of visit. The rescheduled install date is 27/08 - AM between 8am-1pm. _x000D_20/8/2024:#Update - Customer unaware of visit. The rescheduled install date is 27/08 - AM between 8am-1pm. _x000D_19/8/2024:#Update - Customer unaware of visit. The rescheduled install date is 27/08 - AM between 8am-1pm. _x000D_19/8/2024:01432236 _x000D_16/8/2024:#Update - Customer unaware of visit. The rescheduled install date is 27/08 - AM between 8am-1pm. _x000D_15/8/2024:#Update - Customer unaware of visit. The rescheduled install date is 27/08 - AM between 8am-1pm. _x000D_14/8/2024:#Update - Customer unaware of visit. The rescheduled install date is 27/08 - AM between 8am-1pm. _x000D_13/8/2024:#Update - Customer unaware of visit. The rescheduled install date is 27/08 - AM between 8am-1pm. _x000D_12/8/2024:#Update - Customer unaware of visit. The rescheduled install date is 27/08 - AM between 8am-1pm. _x000D_9/8/2024:#Update - Customer unaware of visit. The rescheduled install date is 27/08 - AM between 8am-1pm. _x000D_8/8/2024:05/08/2024 _x000D_6/8/2024:05/08/2024 _x000D_5/8/2024:05/08/2024 _x000D_2/8/2024:18/07/2024 _x000D_1/8/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_30/7/2024:#Update - Awaiting address query, Emailed allwyn to confirm. _x000D_29/7/2024:#Update - Awaiting address query, Emailed allwyn to confirm. _x000D_29/7/2024:01432236 _x000D_26/7/2024:01432236 _x000D_24/7/2024:#Update - Awaiting address query, Emailed allwyn to confirm. _x000D_23/7/2024:#Update - Awaiting address query, Emailed allwyn to confirm. _x000D_22/7/2024:#Update - Awaiting address query, Emailed allwyn to confirm. _x000D_22/7/2024:#Update - Awaiting address query, Emailed allwyn to confirm. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:Order Rejected: Service Incompatible for input CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_25/6/2024:Order Rejected: Service Incompatible for input CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_24/6/2024:Order Rejected: Service Incompatible for input CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - Customer unaware of visit. The rescheduled install date is 27/08 - AM between 8am-1pm. _x000D_6/9/2024:#Update - Customer unaware of visit. The rescheduled install date is 27/08 - AM between 8am-1pm. _x000D_5/9/2024:#Update - Customer unaware of visit. The rescheduled install date is 27/08 - AM between 8am-1pm. _x000D_4/9/2024:#Update - Customer unaware of visit. The rescheduled install date is 27/08 - AM between 8am-1pm. _x000D_3/9/2024:#Update - Customer unaware of visit. The rescheduled install date is 27/08 - AM between 8am-1pm. _x000D_2/9/2024:#Update - Customer unaware of visit. The rescheduled install date is 27/08 - AM between 8am-1pm. _x000D_29/8/2024:#Update - Customer unaware of visit. The rescheduled install date is 27/08 - AM between 8am-1pm. _x000D_28/8/2024:#Update - Customer unaware of visit. The rescheduled install date is 27/08 - AM between 8am-1pm. _x000D_27/8/2024:#Update - Customer unaware of visit. The rescheduled install date is 27/08 - AM between 8am-1pm. _x000D_22/8/2024:#Update - Customer unaware of visit. The rescheduled install date is 27/08 - AM between 8am-1pm. _x000D_21/8/2024:#Update - Customer unaware of visit. The rescheduled install date is 27/08 - AM between 8am-1pm. _x000D_20/8/2024:#Update - Customer unaware of visit. The rescheduled install date is 27/08 - AM between 8am-1pm. _x000D_19/8/2024:#Update - Customer unaware of visit. The rescheduled install date is 27/08 - AM between 8am-1pm. _x000D_19/8/2024:01432236 _x000D_16/8/2024:#Update - Customer unaware of visit. The rescheduled install date is 27/08 - AM between 8am-1pm. _x000D_15/8/2024:#Update - Customer unaware of visit. The rescheduled install date is 27/08 - AM between 8am-1pm. _x000D_14/8/2024:#Update - Customer unaware of visit. The rescheduled install date is 27/08 - AM between 8am-1pm. _x000D_13/8/2024:#Update - Customer unaware of visit. The rescheduled install date is 27/08 - AM between 8am-1pm. _x000D_12/8/2024:#Update - Customer unaware of visit. The rescheduled install date is 27/08 - AM between 8am-1pm. _x000D_9/8/2024:#Update - Customer unaware of visit. The rescheduled install date is 27/08 - AM between 8am-1pm. _x000D_8/8/2024:05/08/2024 _x000D_6/8/2024:05/08/2024 _x000D_5/8/2024:05/08/2024 _x000D_2/8/2024:18/07/2024 _x000D_1/8/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_30/7/2024:#Update - Awaiting address query, Emailed allwyn to confirm. _x000D_29/7/2024:#Update - Awaiting address query, Emailed allwyn to confirm. _x000D_29/7/2024:01432236 _x000D_26/7/2024:01432236 _x000D_24/7/2024:#Update - Awaiting address query, Emailed allwyn to confirm. _x000D_23/7/2024:#Update - Awaiting address query, Emailed allwyn to confirm. _x000D_22/7/2024:#Update - Awaiting address query, Emailed allwyn to confirm. _x000D_22/7/2024:#Update - Awaiting address query, Emailed allwyn to confirm. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:Order Rejected: Service Incompatible for input CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_25/6/2024:Order Rejected: Service Incompatible for input CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_24/6/2024:Order Rejected: Service Incompatible for input CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 0 | #Update - Customer unaware of visit. The rescheduled install date is 27/08 - AM between 8am-1pm. | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2440687 | 30016328 | 2.Commissioning | AM |  | 2024-07-05 | 2024-08-27 |  | 0 |  |  |  | 2024-09-18 | [7 empty] | 0
1271 | 655807 | 3756 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Kirkholt Convenience | Rochdale | OL11 2JG |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 09:47 _x000D_26/7/2024:22/07/2024 09:47 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_12/7/2024:#Update - Order has been delayed due to line plant issues. CSL will update as more information become available. _x000D_11/7/2024:#Update - Order has been delayed due to line plant issues. CSL will update as more information become available. _x000D_10/7/2024:#Update - Order has been delayed due to line plant issues. CSL will update as more information become available. _x000D_9/7/2024:#Update - Order has been delayed due to line plant issues. CSL will update as more information become available. _x000D_4/7/2024:#Update - Order has been delayed due to line plant issues. CSL will update as more information become available. _x000D_3/7/2024:#Update - Order has been delayed due to line plant issues. CSL will update as more information become available. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Order has been delayed due to line plant issues. CSL will update as more information become available. _x000D_27/6/2024:#Update - Order has been delayed due to line plant issues. CSL will update as more information become available. _x000D_25/6/2024:#Update - Order has been delayed due to line plant issues. CSL will update as more information become available. _x000D_24/6/2024:#Update - Order has been delayed due to line plant issues. CSL will update as more information become available. _x000D_20/6/2024:#Update - Order has been delayed due to line plant issues. CSL will update as more information become available. _x000D_19/6/2024:#Update - Order has been delayed due to line plant issues. CSL will update as more information become available. _x000D_18/6/2024:#Update - Order has been delayed due to line plant issues. CSL will update as more information become available. _x000D_17/6/2024:#Update - Order has been delayed due to line plant issues. CSL will update as more information become available. _x000D_14/6/2024:#Update - Order has been delayed due to line plant issues. CSL will update as more information become available. _x000D_13/6/2024:#Update - Order has been delayed due to line plant issues. CSL will update as more information become available. _x000D_12/6/2024:#Update - Order has been delayed due to line plant issues. CSL will update as more information become available. _x000D_10/6/2024:#Update - Order has been delayed due to line plant issues. CSL will update as more information become available. _x000D_7/6/2024:#Update - Order has been delayed due to line plant issues. CSL will update as more information become available. _x000D_6/6/2024:#Update - Order has been delayed due to line plant issues. CSL will update as more information become available. _x000D_5/6/2024:#Update - Order has been delayed due to line plant issues. CSL will update as more information become available. _x000D_4/6/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 05/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 09:47 _x000D_26/7/2024:22/07/2024 09:47 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_12/7/2024:#Update - Order has been delayed due to line plant issues. CSL will update as more information become available. _x000D_11/7/2024:#Update - Order has been delayed due to line plant issues. CSL will update as more information become available. _x000D_10/7/2024:#Update - Order has been delayed due to line plant issues. CSL will update as more information become available. _x000D_9/7/2024:#Update - Order has been delayed due to line plant issues. CSL will update as more information become available. _x000D_4/7/2024:#Update - Order has been delayed due to line plant issues. CSL will update as more information become available. _x000D_3/7/2024:#Update - Order has been delayed due to line plant issues. CSL will update as more information become available. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Order has been delayed due to line plant issues. CSL will update as more information become available. _x000D_27/6/2024:#Update - Order has been delayed due to line plant issues. CSL will update as more information become available. _x000D_25/6/2024:#Update - Order has been delayed due to line plant issues. CSL will update as more information become available. _x000D_24/6/2024:#Update - Order has been delayed due to line plant issues. CSL will update as more information become available. _x000D_20/6/2024:#Update - Order has been delayed due to line plant issues. CSL will update as more information become available. _x000D_19/6/2024:#Update - Order has been delayed due to line plant issues. CSL will update as more information become available. _x000D_18/6/2024:#Update - Order has been delayed due to line plant issues. CSL will update as more information become available. _x000D_17/6/2024:#Update - Order has been delayed due to line plant issues. CSL will update as more information become available. _x000D_14/6/2024:#Update - Order has been delayed due to line plant issues. CSL will update as more information become available. _x000D_13/6/2024:#Update - Order has been delayed due to line plant issues. CSL will update as more information become available. _x000D_12/6/2024:#Update - Order has been delayed due to line plant issues. CSL will update as more information become available. _x000D_10/6/2024:#Update - Order has been delayed due to line plant issues. CSL will update as more information become available. _x000D_7/6/2024:#Update - Order has been delayed due to line plant issues. CSL will update as more information become available. _x000D_6/6/2024:#Update - Order has been delayed due to line plant issues. CSL will update as more information become available. _x000D_5/6/2024:#Update - Order has been delayed due to line plant issues. CSL will update as more information become available. _x000D_4/6/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 05/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2398943 | 30016426 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
1272 | 486412 | 3758 | Batch 5 Jul24 | Type 1 | SOGEA | SPAR BRACKLA | BRIDGEND | CF31 2JS |  | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:No matching address found CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/7/2024:No matching address found CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/7/2024:No matching address found CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_11/7/2024:No matching address found CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/7/2024:No matching address found CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_9/7/2024:No matching address found CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:No matching address found CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/7/2024:No matching address found CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/7/2024:No matching address found CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_11/7/2024:No matching address found CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/7/2024:No matching address found CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_9/7/2024:No matching address found CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFS1012943 | 30016512 | 2.Commissioning |  |  | 2024-07-08 | 2024-07-08 | 2024-07-08 | TRUE |  |  |  | 2024-08-02 | [7 empty] | 0
1273 | 664663 | 3759 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Vivo Essentials Ballysillan | Belfast | BT14 8AB |  | 22/8/2024:Order Completed _x000D_21/8/2024:Order Completed _x000D_20/8/2024:Order Completed _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_18/7/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_17/7/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_16/7/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_15/7/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_12/7/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_11/7/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_10/7/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_9/7/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_4/7/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_3/7/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_27/6/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_25/6/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_24/6/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_20/6/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_19/6/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_18/6/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_17/6/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_14/6/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_13/6/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_12/6/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_10/6/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_7/6/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_6/6/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_5/6/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_4/6/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_ | 22/8/2024:Order Completed _x000D_21/8/2024:Order Completed _x000D_20/8/2024:Order Completed _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_18/7/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_17/7/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_16/7/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_15/7/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_12/7/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_11/7/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_10/7/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_9/7/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_4/7/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_3/7/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_2/7/2024:0 _x000D_1/7/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_27/6/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_25/6/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_24/6/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_20/6/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_19/6/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_18/6/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_17/6/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_14/6/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_13/6/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_12/6/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_10/6/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_7/6/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_6/6/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_5/6/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_4/6/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2416468 | 30016362 | 2.Commissioning | AM |  | 2024-07-31 | 2024-08-19 |  | 0 |  |  |  | 2024-09-27 | [7 empty] | 0
1274 | 601644 | 3763 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Texaco Costcutter | Coventry | CV4 9HU |  | 6/9/2024:#Update - Order re-raised. _x000D_5/9/2024:#Update - Order re-raised. _x000D_4/9/2024:#Update - Order re-raised. _x000D_3/9/2024:#Update - Order re-raised. _x000D_2/9/2024:#Update - Order re-raised. _x000D_29/8/2024:#Update - Order re-raised. _x000D_28/8/2024:#Update - Order re-raised. _x000D_27/8/2024:#Update - Order re-raised. _x000D_22/8/2024:#Update - Order re-raised. _x000D_21/8/2024:#Update - Order re-raised. _x000D_20/8/2024:#Update - Order re-raised. _x000D_19/8/2024:#Update - Order re-raised. _x000D_19/8/2024:01431097 _x000D_16/8/2024:#Update - Order re-raised. _x000D_15/8/2024:#Update - Order re-raised. _x000D_14/8/2024:#Update - Order re-raised. _x000D_13/8/2024:#Update - Order re-raised. _x000D_12/8/2024:#Update - Order re-raised. _x000D_9/8/2024:#Update - Order re-raised. _x000D_8/8/2024:24/07/2024 _x000D_6/8/2024:24/07/2024 _x000D_5/8/2024:24/07/2024 _x000D_2/8/2024:24/07/2024 _x000D_1/8/2024:24/07/2024 _x000D_31/7/2024:24/07/2024 _x000D_31/7/2024:24/07/2024 _x000D_30/7/2024:#Update - Order re-raised. _x000D_29/7/2024:#Update - Order re-raised. _x000D_29/7/2024:01431097 _x000D_26/7/2024:01431097 _x000D_24/7/2024:#Update - Order re-raised. _x000D_23/7/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_22/7/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_22/7/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 27/06/2024. We will continue to provide update as they become available. _x000D_25/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 27/06/2024. We will continue to provide update as they become available. _x000D_24/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 27/06/2024. We will continue to provide update as they become available. _x000D_20/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 18/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 18/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 18/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_17/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 18/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_14/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 18/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_13/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 18/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/6/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/6/2024:Your order has been delayed by the suppliers. The provided site contact unaware of the order. Please check with end user and confirm the alternative contact to progress the order further CSL Note: Invalid appointment slot received CSL Note: Invalid data _x000D_7/6/2024:Your order has been delayed by the suppliers. The provided site contact unaware of the order. Please check with end user and confirm the alternative contact to progress the order further CSL Note: Invalid appointment slot received CSL Note: Invalid data _x000D_6/6/2024:Your order has been delayed by the suppliers. The provided site contact unaware of the order. Please check with end user and confirm the alternative contact to progress the order further CSL Note: Invalid appointment slot received CSL Note: Invalid data _x000D_5/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 10/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 10/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 9/9/2024:#Update - Order re-raised. _x000D_6/9/2024:#Update - Order re-raised. _x000D_5/9/2024:#Update - Order re-raised. _x000D_4/9/2024:#Update - Order re-raised. _x000D_3/9/2024:#Update - Order re-raised. _x000D_2/9/2024:#Update - Order re-raised. _x000D_29/8/2024:#Update - Order re-raised. _x000D_28/8/2024:#Update - Order re-raised. _x000D_27/8/2024:#Update - Order re-raised. _x000D_22/8/2024:#Update - Order re-raised. _x000D_21/8/2024:#Update - Order re-raised. _x000D_20/8/2024:#Update - Order re-raised. _x000D_19/8/2024:#Update - Order re-raised. _x000D_19/8/2024:01431097 _x000D_16/8/2024:#Update - Order re-raised. _x000D_15/8/2024:#Update - Order re-raised. _x000D_14/8/2024:#Update - Order re-raised. _x000D_13/8/2024:#Update - Order re-raised. _x000D_12/8/2024:#Update - Order re-raised. _x000D_9/8/2024:#Update - Order re-raised. _x000D_8/8/2024:24/07/2024 _x000D_6/8/2024:24/07/2024 _x000D_5/8/2024:24/07/2024 _x000D_2/8/2024:24/07/2024 _x000D_1/8/2024:24/07/2024 _x000D_31/7/2024:24/07/2024 _x000D_31/7/2024:24/07/2024 _x000D_30/7/2024:#Update - Order re-raised. _x000D_29/7/2024:#Update - Order re-raised. _x000D_29/7/2024:01431097 _x000D_26/7/2024:01431097 _x000D_24/7/2024:#Update - Order re-raised. _x000D_23/7/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_22/7/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_22/7/2024:#Update - Supplier delay, Review date of 10.06. Will review updates for resolution. _x000D_12/7/2024:Order Completed _x000D_11/7/2024:Order Completed _x000D_10/7/2024:Order Completed _x000D_9/7/2024:Order Completed _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 27/06/2024. We will continue to provide update as they become available. _x000D_25/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 27/06/2024. We will continue to provide update as they become available. _x000D_24/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 27/06/2024. We will continue to provide update as they become available. _x000D_20/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 18/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 18/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 18/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_17/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 18/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_14/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 18/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_13/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 18/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/6/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/6/2024:Your order has been delayed by the suppliers. The provided site contact unaware of the order. Please check with end user and confirm the alternative contact to progress the order further CSL Note: Invalid appointment slot received CSL Note: Invalid data _x000D_7/6/2024:Your order has been delayed by the suppliers. The provided site contact unaware of the order. Please check with end user and confirm the alternative contact to progress the order further CSL Note: Invalid appointment slot received CSL Note: Invalid data _x000D_6/6/2024:Your order has been delayed by the suppliers. The provided site contact unaware of the order. Please check with end user and confirm the alternative contact to progress the order further CSL Note: Invalid appointment slot received CSL Note: Invalid data _x000D_5/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 10/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/6/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 10/06/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 0 | #Update - Order re-raised. | 2024-06-07 |  |  |  |  | VFP2363390 | 30016214 | 1.Provisioning | AM |  | 2024-08-19 | 2024-09-06 |  | 0 | [11 empty] | 0
1275 | 435182 | 3772 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | CENTRA | Armagh | BT60 3EW |  | 6/9/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_5/9/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_4/9/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_3/9/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_2/9/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_29/8/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_28/8/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_27/8/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_22/8/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_21/8/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_20/8/2024:#Update - Your order has been delayed. Duct work required. We will continue to provide update as they become available. _x000D_19/8/2024:#Update - Your order has been delayed. Duct work required. We will continue to provide update as they become available. _x000D_19/8/2024:01415585 _x000D_16/8/2024:#Update - Your order has been delayed. Duct work required. We will continue to provide update as they become available. _x000D_15/8/2024:#Update - Your order has been delayed. Duct work required. We will continue to provide update as they become available. _x000D_14/8/2024:#Update - Your order has been delayed. Duct work required. We will continue to provide update as they become available. _x000D_13/8/2024:#Update - Your order has been delayed. Duct work required. We will continue to provide update as they become available. _x000D_12/8/2024:#Update - Your order has been delayed. Duct work required. We will continue to provide update as they become available. _x000D_9/8/2024:#Update - Your order has been delayed. Duct work required. We will continue to provide update as they become available. _x000D_8/8/2024:25/07/2024 _x000D_6/8/2024:25/07/2024 _x000D_5/8/2024:25/07/2024 _x000D_2/8/2024:25/07/2024 _x000D_1/8/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_30/7/2024:#Update - Your order has been delayed. Duct work required. We will continue to provide update as they become available. _x000D_29/7/2024:#Update - Your order has been delayed. Duct work required. We will continue to provide update as they become available. _x000D_29/7/2024:01415585 _x000D_26/7/2024:01415585 _x000D_24/7/2024:#Update - order has been delayed as site survey is required. This has been sent to the survey engineers and we will update accordingly _x000D_23/7/2024:#Update - order has been delayed as site survey is required. This has been sent to the survey engineers and we will update accordingly _x000D_22/7/2024:#Update - order has been delayed as site survey is required. This has been sent to the survey engineers and we will update accordingly _x000D_22/7/2024:#Update - Dig work required which is awaiting permission from a third party. CSL will update as more information become available. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_6/9/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_5/9/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_4/9/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_3/9/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_2/9/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_29/8/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_28/8/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_27/8/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_22/8/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_21/8/2024:#Update - Order has been delayed as civil work is required. CSL will update as more information become available. _x000D_20/8/2024:#Update - Your order has been delayed. Duct work required. We will continue to provide update as they become available. _x000D_19/8/2024:#Update - Your order has been delayed. Duct work required. We will continue to provide update as they become available. _x000D_19/8/2024:01415585 _x000D_16/8/2024:#Update - Your order has been delayed. Duct work required. We will continue to provide update as they become available. _x000D_15/8/2024:#Update - Your order has been delayed. Duct work required. We will continue to provide update as they become available. _x000D_14/8/2024:#Update - Your order has been delayed. Duct work required. We will continue to provide update as they become available. _x000D_13/8/2024:#Update - Your order has been delayed. Duct work required. We will continue to provide update as they become available. _x000D_12/8/2024:#Update - Your order has been delayed. Duct work required. We will continue to provide update as they become available. _x000D_9/8/2024:#Update - Your order has been delayed. Duct work required. We will continue to provide update as they become available. _x000D_8/8/2024:25/07/2024 _x000D_6/8/2024:25/07/2024 _x000D_5/8/2024:25/07/2024 _x000D_2/8/2024:25/07/2024 _x000D_1/8/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_30/7/2024:#Update - Your order has been delayed. Duct work required. We will continue to provide update as they become available. _x000D_29/7/2024:#Update - Your order has been delayed. Duct work required. We will continue to provide update as they become available. _x000D_29/7/2024:01415585 _x000D_26/7/2024:01415585 _x000D_24/7/2024:#Update - order has been delayed as site survey is required. This has been sent to the survey engineers and we will update accordingly _x000D_23/7/2024:#Update - order has been delayed as site survey is required. This has been sent to the survey engineers and we will update accordingly _x000D_22/7/2024:#Update - order has been delayed as site survey is required. This has been sent to the survey engineers and we will update accordingly _x000D_22/7/2024:#Update - Dig work required which is awaiting permission from a third party. CSL will update as more information become available. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Supplier Delay: Issues with provision of the underground network, please await for further details. | #Update - Order has been delayed as civil work is required. CSL will update as more information become available. | 2024-06-07 |  |  |  |  | VFP2363386 | 30016267 | 1.Provisioning | AM |  | 2024-07-08 | 2024-07-08 |  | 0 | [11 empty] | 0
1276 | 456700 | 3780 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Costcutter | TAMWORTH | B78 3JN |  | 22/8/2024:Order Completed _x000D_21/8/2024:Order Completed _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:CP Delay: The HandoverPortServiceId provided is invalid. Amend should be placed within 2 days. Please contact IT Operations. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_17/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 22/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_16/7/2024:Update: Order Completed by Supplier _x000D_15/7/2024:Update: Order Completed by Supplier _x000D_12/7/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_11/7/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/7/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_9/7/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 01/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_3/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 01/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_2/7/2024:0 _x000D_1/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 01/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_27/6/2024:0 _x000D_25/6/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_24/6/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_20/6/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 22/8/2024:Order Completed _x000D_21/8/2024:Order Completed _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:CP Delay: The HandoverPortServiceId provided is invalid. Amend should be placed within 2 days. Please contact IT Operations. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_17/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 22/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_16/7/2024:Update: Order Completed by Supplier _x000D_15/7/2024:Update: Order Completed by Supplier _x000D_12/7/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_11/7/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_10/7/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_9/7/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 01/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_3/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 01/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_2/7/2024:0 _x000D_1/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 01/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_27/6/2024:0 _x000D_25/6/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_24/6/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_20/6/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 3.Allwyn to arrange rtr install | VFP2416390 | 30016513 | 2.Commissioning | AM |  | 2024-07-25 | 2024-07-25 |  | 0 |  |  |  | 2024-09-20 | [7 empty] | 0
1277 | 613814 | 3788 | Batch 5 Jul24 | Type 1 | FTTP | Nisa | Wallsend | NE28 0PS | 2024-07-03 | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:Update: Order Amended _x000D_3/7/2024:Update: Order Amended _x000D_2/7/2024:0 _x000D_1/7/2024:Update: Order Amended _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  | 6.No action | VFP2394930 | 30017132 | 9.Completed |  |  | 2024-07-02 | 2024-07-02 | 2024-07-02 | TRUE |  |  |  | 2024-07-24 |  |  |  | 2024-07-24 | 23A004948659 |  | 2024-07-25 | 1
1278 | 667697 | 3790 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | South Elmsall | Pontefract | WF9 2UP |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:20 _x000D_26/7/2024:22/07/2024 10:20 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:20 _x000D_26/7/2024:22/07/2024 10:20 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | Update: Order Amended | 0 | 2024-06-07 |  |  |  |  | VFP2394927 | 30017143 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
1279 | 486538 | 3805 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Pydar Stores | Truro | TR1 2SW |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_Address verification issue, email sent to VF - order is cancelled and will be reraised accordingly | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_Address verification issue, email sent to VF - order is cancelled and will be reraised accordingly | 0 | 0 | 2024-06-07 |  |  |  |  | Address query | 30017150 | 1.Provisioning | AM |  | 2024-07-03 |  |  | 0 | [11 empty] | 0
1280 | 656307 | 3811 | Batch 5 Jul24 | Type 1 | FTTP/Mobile | Londis Dobshill Service Station | Dobshill | CH5 3LZ | 2024-08-02 | 5/8/2024:Order Completed _x000D_2/8/2024:Order Completed _x000D_1/8/2024:Update: Order Amended _x000D_31/7/2024:Update: Order Amended _x000D_31/7/2024:37783 _x000D_30/7/2024:Update: Order Amended _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:29/07/2024 09:47 _x000D_26/7/2024:24/07/2024 14:34 _x000D_24/7/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_23/7/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_0 | 5/8/2024:Order Completed _x000D_2/8/2024:Order Completed _x000D_1/8/2024:Update: Order Amended _x000D_31/7/2024:Update: Order Amended _x000D_31/7/2024:37783 _x000D_30/7/2024:Update: Order Amended _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:29/07/2024 09:47 _x000D_26/7/2024:24/07/2024 14:34 _x000D_24/7/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_23/7/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_0 |  |  | 2024-06-07 |  |  |  |  | VFP2416512 | 30016240 | 6.Failed router install |  |  | 2024-07-23 | 2024-08-01 | 2024-08-01 | TRUE |  |  |  | 2024-08-21 |  |  |  | 2024-08-21 | 23A004948613 | 23A004948613 | 2024-08-22 | 1
1281 | 659332 | 3815 | Batch 5 Jul24 | Type 1 | SOGEA | SPAR Poole Park Road | Plymouth | PL5 1DJ |  | 19/7/2024:Order Completed _x000D_18/7/2024:Order Completed _x000D_17/7/2024:Order Completed _x000D_16/7/2024:Supplier Delay: Provision of service will be delayed by a scheduled service outage _x000D_15/7/2024:Supplier Delay: Provision of service will be delayed by a scheduled service outage _x000D_12/7/2024:Supplier Delay: Provision of service will be delayed by a scheduled service outage _x000D_11/7/2024:Supplier Delay: Provision of service will be delayed by a scheduled service outage _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 19/07/2024.We will continue to provide update as they become available. _x000D_4/7/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_3/7/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:Order Completed _x000D_18/7/2024:Order Completed _x000D_17/7/2024:Order Completed _x000D_16/7/2024:Supplier Delay: Provision of service will be delayed by a scheduled service outage _x000D_15/7/2024:Supplier Delay: Provision of service will be delayed by a scheduled service outage _x000D_12/7/2024:Supplier Delay: Provision of service will be delayed by a scheduled service outage _x000D_11/7/2024:Supplier Delay: Provision of service will be delayed by a scheduled service outage _x000D_10/7/2024:Update: Order Amended _x000D_9/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 19/07/2024.We will continue to provide update as they become available. _x000D_4/7/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_3/7/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | Address query | Address query | 1.Provisioning | [17 empty] | 0
1282 | 466352 | 3826 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Topshop Convenience Store | Trimdon Station | TS29 6AR |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_Address verification issue, email sent to VF - order is cancelled and will be reraised accordingly | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_Address verification issue, email sent to VF - order is cancelled and will be reraised accordingly | 0 | 0 | 2024-06-07 |  |  |  |  | Address query | 30017225 | 1.Provisioning | AM |  | 2024-07-11 |  |  | 0 | [11 empty] | 0
1283 | 656385 | 3836 | Batch 5 Jul24 | Type 1 | FTTP | Girishs Premier | Glasgow | G21 3ES |  | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_10/7/2024:0 _x000D_9/7/2024:0 _x000D_4/7/2024:0 _x000D_3/7/2024:0 _x000D_2/7/2024:0 _x000D_1/7/2024:0 _x000D_27/6/2024:0 _x000D_25/6/2024:0 _x000D_24/6/2024:0 _x000D_20/6/2024:0 _x000D_19/6/2024:0 _x000D_18/6/2024:0 _x000D_17/6/2024:0 _x000D_14/6/2024:0 _x000D_13/6/2024:0 _x000D_12/6/2024:0 _x000D_10/6/2024:0 _x000D_7/6/2024:0 _x000D_ |  |  | 2024-06-07 |  |  |  |  | VFP2394926 | 30017157 | 6.Failed router install |  |  | 2024-07-05 | 2024-07-05 |  | TRUE |  |  |  | 2024-07-24 |  |  |  | 2024-07-24 | 242005013566 |  | 2024-07-25 | 1
1284 | 616544 | 3872 | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | One Stop | Scarborough | YO11 3LS |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_Address verification issue, email sent to Allwyn deployment to confirm address, further update to follow | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_Address verification issue, email sent to Allwyn deployment to confirm address, further update to follow | 0 | 0 | 2024-06-07 |  |  |  |  | VFS983480 | 30015711 | 1.Provisioning | AM |  |  |  |  | 0 | [11 empty] | 0
1285 | 639713 | 3880 | Batch 5 Jul24 | Type 1 | SOGEA | One Stop | Barnsley | S71 2PX | 2024-07-11 | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_0 | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_0 |  |  | 2024-06-07 |  |  |  |  | VFS1012863 | 30016536 | 2.Commissioning |  |  | 2024-07-10 | 2024-07-10 | 2024-07-10 | TRUE |  |  |  | 2024-08-02 | [7 empty] | 0
1286 | 424051 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Kings Square News | WEST BROMWICH | B70 7NW | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Silver Address Issue | 30021808 | 1.Provisioning | AM |  | 2024-08-05 |  |  | 0 | [11 empty] | 0
1287 | 434059 |  | Batch 6 Aug 24 | Type 1 | KCOM/Mobile | Supernews | HULL | HU7 4EE | 2024-09-02 | 6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_19/8/2024:01583518 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_19/8/2024:01583518 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM |  |  |  |  | 2.Allwyn to arrange access | BUS0004467 | 30017243 | 2.Commissioning | AM | 2024-08-12 | 2024-08-30 | 2024-08-30 |  | 0 | [11 empty] | 0
1288 | 478215 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Whittakers Tobacconist | Oldham | OL1 3BG | 2024-09-02 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:Order Completed _x000D_2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:Order Completed _x000D_2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFS1055220 | 30017764 | 2.Commissioning | AM |  | 2024-08-05 | 2024-08-30 |  | 0 | [11 empty] | 0
1289 | 615908 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Daily News | BARNSLEY | S70 1SB | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Silver Address Issue | 30017446 | 1.Provisioning | AM |  | 2024-08-05 |  |  | 0 | [11 empty] | 0
1290 | 645851 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Bestone | CORBY | NN17 1NU | 2024-07-11 | 12/8/2024:#Update - Install was completed on 08/08 _x000D_9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:Supplier Delay: Missed CCD and may require further work as the engineer has retained the job for next day _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 12/8/2024:#Update - Install was completed on 08/08 _x000D_9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:Supplier Delay: Missed CCD and may require further work as the engineer has retained the job for next day _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFS1055216 | 30017735 | 3.In life |  |  | 2024-08-05 | 2024-08-05 | 2024-08-08 09:18 | TRUE |  |  |  | 2024-08-30 |  |  |  | 2024-08-30 | 237004907611 | 237004907611 | 2024-09-04 | 1
1291 | 458514 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Ganapathy Cash & Carry | WEMBLEY | HA0 4TL | 2024-09-05 | 6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_27/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_22/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:Supplier Delay: New Appointment might be required _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:End User Missed appointment. Action required _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_0 | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_27/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_22/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:Supplier Delay: New Appointment might be required _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:End User Missed appointment. Action required _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_0 | Order Completed | 0 |  |  |  |  | 2.Allwyn to arrange access | VFS1055209 | 30017700 | 2.Commissioning | AM |  | 2024-08-05 | 2024-08-20 |  | 0 | [11 empty] | 0
1292 | 662773 |  | Batch 6 Aug 24 | Type 1 | FTTP | HPC Construction - East Retail | BRIDGWATER | TA6 6FA | 2024-07-11 | 19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | Order On Hold | Order On Hold | 1.Provisioning | [17 empty] | 0
1293 | 431169 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | ARDEN NEWS | KEIGHLEY | BD21 3NR | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Silver Address Issue | 30017721 | 1.Provisioning | AM |  | 2024-08-05 |  |  | 0 | [11 empty] | 0
1294 | 662772 |  | Batch 6 Aug 24 | Type 1 | Exception | HPC Construction - West Retail | BRIDGWATER | TA6 6FA | 2024-07-11 | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_0 | 19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_0 | [6 empty] | 2.Allwyn to arrange access | Order On Hold | Order On Hold | 1.Provisioning | [17 empty] | 0
1295 | 434040 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Super Cigs | HARTLEPOOL | TS24 7RT | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Silver Address Issue | 30021825 | 1.Provisioning | AM |  | 2024-08-05 |  |  | 0 | [11 empty] | 0
1296 | 471461 |  | Batch 6 Aug 24 | Type 1 | SURE/Mobile | Spar | ISLE OF MAN | IM1 2EE | 2024-09-03 | 3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | SURE | 30017236 | 2.Commissioning | AM | 2024-08-09 | 2024-08-09 |  |  | 0 | [11 empty] | 0
1297 | 602159 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | News Factor | BOOTLE | L20 4SP | 2024-07-11 | 22/8/2024:Order Completed _x000D_21/8/2024:Order Completed _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_5/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 22/8/2024:Order Completed _x000D_21/8/2024:Order Completed _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_5/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFS1057022 | 30017412 | 2.Commissioning | AM |  | 2024-08-05 | 2024-08-20 |  | 0 |  |  |  | 2024-09-26 | [7 empty] | 0
1298 | 438061 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Middleton News | MANCHESTER | M24 4EL | 2024-08-07 | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043988 | 30017450 | 2.Commissioning |  |  | 2024-08-06 | 2024-08-06 | 2024-08-06 14:00 | TRUE |  |  |  | 2024-08-28 | [7 empty] | 0
1299 | 607396 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Lesleys News Market Stall | BLACKBURN | BB1 5AF | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Address query | 30017726 | 1.Provisioning | AM |  | 2024-08-05 |  |  | 0 | [11 empty] | 0
1300 | 636081 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Livi News | LIVINGSTON | EH54 6HS | 2024-08-07 | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043990 | 30017420 | 2.Commissioning |  |  | 2024-08-06 | 2024-08-06 | 2024-08-06 14:20 | TRUE |  |  |  | 2024-09-11 | [7 empty] | 0
1301 | 666849 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Post Office | BELFAST | BT11 9JQ | 2024-08-23 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_13/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_12/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_9/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_8/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_6/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_13/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_12/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_9/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_8/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_6/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFS1043986 | 30017422 | 2.Commissioning | AM |  | 2024-08-06 | 2024-08-22 |  | 0 | [11 empty] | 0
1302 | 616535 |  | Batch 6 Aug 24 | Type 1 | KCOM/Mobile | Premier | HULL | HU6 8AQ | 2024-09-04 | 6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 PM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 PM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 PM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 PM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 PM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 PM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 PM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 PM _x000D_19/8/2024:01583456 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 PM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 PM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 PM _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 AM _x000D_6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 PM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 PM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 PM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 PM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 PM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 PM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 PM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 PM _x000D_19/8/2024:01583456 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 PM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 PM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 PM _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - Allwyn confirmed Retailer has agreed to installation on 03/09 AM |  |  |  |  | 2.Allwyn to arrange access | BUS0004491 | 30017253 | 2.Commissioning | PM | 2024-08-09 | 2024-08-29 | 2024-08-29 |  | 0 | [11 empty] | 0
1303 | 434470 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Morans Supervalue | LIMAVADY | BT49 9HS | 2024-08-07 | 22/8/2024:#Update - NFA - Allwyn confirmed new install date 22/08 with retailer _x000D_21/8/2024:#Update - NFA - Allwyn confirmed new install date 22/08 with retailer _x000D_20/8/2024:#Update - NFA - Allwyn confirmed new install date 22/08 with retailer _x000D_19/8/2024:#Update - NFA - Allwyn confirmed new install date 22/08 with retailer _x000D_19/8/2024:01567219 _x000D_16/8/2024:#Update - NFA - Allwyn confirmed new install date 22/08 with retailer _x000D_15/8/2024:#Update - NFA - Allwyn confirmed new install date 22/08 with retailer _x000D_14/8/2024:#Update - NFA - Allwyn confirmed new install date 22/08 with retailer _x000D_13/8/2024:#Update - NFA - Allwyn confirmed new install date 22/08 with retailer _x000D_12/8/2024:#Update - NFA - Allwyn confirmed new install date 22/08 with retailer _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 22/8/2024:#Update - NFA - Allwyn confirmed new install date 22/08 with retailer _x000D_21/8/2024:#Update - NFA - Allwyn confirmed new install date 22/08 with retailer _x000D_20/8/2024:#Update - NFA - Allwyn confirmed new install date 22/08 with retailer _x000D_19/8/2024:#Update - NFA - Allwyn confirmed new install date 22/08 with retailer _x000D_19/8/2024:01567219 _x000D_16/8/2024:#Update - NFA - Allwyn confirmed new install date 22/08 with retailer _x000D_15/8/2024:#Update - NFA - Allwyn confirmed new install date 22/08 with retailer _x000D_14/8/2024:#Update - NFA - Allwyn confirmed new install date 22/08 with retailer _x000D_13/8/2024:#Update - NFA - Allwyn confirmed new install date 22/08 with retailer _x000D_12/8/2024:#Update - NFA - Allwyn confirmed new install date 22/08 with retailer _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFS1043981 | 30017490 | 2.Commissioning | AM |  | 2024-08-06 | 2024-08-22 |  | 0 |  |  |  | 2024-09-27 | [7 empty] | 0
1304 | 423283 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Spar Stores | PETERBOROUGH | PE1 3SY | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:Your order has been delayed by suppliers due to advanced install type being required with additional charges please check with end user and confirm charges acceptance to proceed this order. _x000D_12/8/2024:Your order has been delayed by suppliers due to advanced install type being required with additional charges please check with end user and confirm charges acceptance to proceed this order. _x000D_9/8/2024:Your order has been delayed by suppliers due to advanced install type being required with additional charges please check with end user and confirm charges acceptance to proceed this order. _x000D_8/8/2024:Your order has been delayed by suppliers due to advanced install type being required with additional charges please check with end user and confirm charges acceptance to proceed this order. _x000D_6/8/2024:Supplier Delay: KCI-3 (Order Completed) Delayed in Processing. _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available _x000D_18/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available _x000D_17/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available _x000D_16/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available _x000D_15/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available _x000D_12/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available _x000D_11/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:Your order has been delayed by suppliers due to advanced install type being required with additional charges please check with end user and confirm charges acceptance to proceed this order. _x000D_12/8/2024:Your order has been delayed by suppliers due to advanced install type being required with additional charges please check with end user and confirm charges acceptance to proceed this order. _x000D_9/8/2024:Your order has been delayed by suppliers due to advanced install type being required with additional charges please check with end user and confirm charges acceptance to proceed this order. _x000D_8/8/2024:Your order has been delayed by suppliers due to advanced install type being required with additional charges please check with end user and confirm charges acceptance to proceed this order. _x000D_6/8/2024:Supplier Delay: KCI-3 (Order Completed) Delayed in Processing. _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available _x000D_18/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available _x000D_17/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available _x000D_16/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available _x000D_15/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available _x000D_12/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available _x000D_11/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2422522 | 30017324 | 1.Provisioning | AM |  | 2024-08-05 | 2024-08-05 |  | 0 | [11 empty] | 0
1305 | 659552 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Buckys News | LONDON | N17 6UB | 2024-08-07 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:End User Missed appointment. Action required _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:End User Missed appointment. Action required _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | Update: Order Amended | 0 |  |  |  |  | 2.Allwyn to arrange access | VFS1043975 | 30017424 | 1.Provisioning | AM |  | 2024-08-06 | 2024-09-02 |  | 0 | [11 empty] | 0
1306 | 668075 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Centra | ANTRIM | BT41 2BA | 2024-08-07 | 6/9/2024:#Update - Openreach determined that Centra - Antrim (Belfast Road) requires a site survey to progress and this has now been carried out by the survey group. A survey pack and pictures outlining the work has been sent. This will be automatically cancelled on the 12th of September if the charges have not been approved, therefore please let us know how you wish to proceed as soon as possible. _x000D_5/9/2024:#Update - Openreach determined that Centra - Antrim (Belfast Road) requires a site survey to progress and this has now been carried out by the survey group. A survey pack and pictures outlining the work has been sent. This will be automatically cancelled on the 12th of September if the charges have not been approved, therefore please let us know how you wish to proceed as soon as possible. _x000D_4/9/2024:#Update - Openreach determined that Centra - Antrim (Belfast Road) requires a site survey to progress and this has now been carried out by the survey group. A survey pack and pictures outlining the work has been sent. This will be automatically cancelled on the 12th of September if the charges have not been approved, therefore please let us know how you wish to proceed as soon as possible. _x000D_3/9/2024:#Update - Openreach determined that Centra - Antrim (Belfast Road) requires a site survey to progress and this has now been carried out by the survey group. A survey pack and pictures outlining the work has been sent. This will be automatically cancelled on the 12th of September if the charges have not been approved, therefore please let us know how you wish to proceed as soon as possible. _x000D_2/9/2024:#Update - Openreach determined that Centra - Antrim (Belfast Road) requires a site survey to progress and this has now been carried out by the survey group. A survey pack and pictures outlining the work has been sent. This will be automatically cancelled on the 12th of September if the charges have not been approved, therefore please let us know how you wish to proceed as soon as possible. _x000D_29/8/2024:#Update - Openreach determined that Centra - Antrim (Belfast Road) requires a site survey to progress and this has now been carried out by the survey group. A survey pack and pictures outlining the work has been sent. This will be automatically cancelled on the 12th of September if the charges have not been approved, therefore please let us know how you wish to proceed as soon as possible. _x000D_28/8/2024:#Update - Openreach determined that Centra - Antrim (Belfast Road) requires a site survey to progress and this has now been carried out by the survey group. A survey pack and pictures outlining the work has been sent. This will be automatically cancelled on the 12th of September if the charges have not been approved, therefore please let us know how you wish to proceed as soon as possible. _x000D_27/8/2024:#Update - Openreach determined that Centra - Antrim (Belfast Road) requires a site survey to progress and this has now been carried out by the survey group. A survey pack and pictures outlining the work has been sent. This will be automatically cancelled on the 12th of September if the charges have not been approved, therefore please let us know how you wish to proceed as soon as possible. _x000D_22/8/2024:#Update - Openreach determined that Centra - Antrim (Belfast Road) requires a site survey to progress and this has now been carried out by the survey group. A survey pack and pictures outlining the work has been sent. This will be automatically cancelled on the 12th of September if the charges have not been approved, therefore please let us know how you wish to proceed as soon as possible. _x000D_21/8/2024:#Update - Order has been delayed due to network planning. CSL will update as more information become available. _x000D_20/8/2024:#Update - Order has been delayed due to network planning. CSL will update as more information become available. _x000D_19/8/2024:#Update - Order has been delayed due to network planning. CSL will update as more information become available. _x000D_19/8/2024:01563071 _x000D_16/8/2024:#Update - Order has been delayed due to network planning. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order has been delayed due to network planning. CSL will update as more information become available. _x000D_14/8/2024:#Update - Order has been delayed due to network planning. CSL will update as more information become available. _x000D_13/8/2024:#Update - Order has been delayed due to network planning. CSL will update as more information become available. _x000D_12/8/2024:#Update - Order has been delayed due to network planning. CSL will update as more information become available. _x000D_9/8/2024:#Update - Order has been delayed due to network planning. CSL will update as more information become available. _x000D_8/8/2024:06/08/2024 _x000D_6/8/2024:06/08/2024 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Openreach determined that Centra - Antrim (Belfast Road) requires a site survey to progress and this has now been carried out by the survey group. A survey pack and pictures outlining the work has been sent. This will be automatically cancelled on the 12th of September if the charges have not been approved, therefore please let us know how you wish to proceed as soon as possible. _x000D_6/9/2024:#Update - Openreach determined that Centra - Antrim (Belfast Road) requires a site survey to progress and this has now been carried out by the survey group. A survey pack and pictures outlining the work has been sent. This will be automatically cancelled on the 12th of September if the charges have not been approved, therefore please let us know how you wish to proceed as soon as possible. _x000D_5/9/2024:#Update - Openreach determined that Centra - Antrim (Belfast Road) requires a site survey to progress and this has now been carried out by the survey group. A survey pack and pictures outlining the work has been sent. This will be automatically cancelled on the 12th of September if the charges have not been approved, therefore please let us know how you wish to proceed as soon as possible. _x000D_4/9/2024:#Update - Openreach determined that Centra - Antrim (Belfast Road) requires a site survey to progress and this has now been carried out by the survey group. A survey pack and pictures outlining the work has been sent. This will be automatically cancelled on the 12th of September if the charges have not been approved, therefore please let us know how you wish to proceed as soon as possible. _x000D_3/9/2024:#Update - Openreach determined that Centra - Antrim (Belfast Road) requires a site survey to progress and this has now been carried out by the survey group. A survey pack and pictures outlining the work has been sent. This will be automatically cancelled on the 12th of September if the charges have not been approved, therefore please let us know how you wish to proceed as soon as possible. _x000D_2/9/2024:#Update - Openreach determined that Centra - Antrim (Belfast Road) requires a site survey to progress and this has now been carried out by the survey group. A survey pack and pictures outlining the work has been sent. This will be automatically cancelled on the 12th of September if the charges have not been approved, therefore please let us know how you wish to proceed as soon as possible. _x000D_29/8/2024:#Update - Openreach determined that Centra - Antrim (Belfast Road) requires a site survey to progress and this has now been carried out by the survey group. A survey pack and pictures outlining the work has been sent. This will be automatically cancelled on the 12th of September if the charges have not been approved, therefore please let us know how you wish to proceed as soon as possible. _x000D_28/8/2024:#Update - Openreach determined that Centra - Antrim (Belfast Road) requires a site survey to progress and this has now been carried out by the survey group. A survey pack and pictures outlining the work has been sent. This will be automatically cancelled on the 12th of September if the charges have not been approved, therefore please let us know how you wish to proceed as soon as possible. _x000D_27/8/2024:#Update - Openreach determined that Centra - Antrim (Belfast Road) requires a site survey to progress and this has now been carried out by the survey group. A survey pack and pictures outlining the work has been sent. This will be automatically cancelled on the 12th of September if the charges have not been approved, therefore please let us know how you wish to proceed as soon as possible. _x000D_22/8/2024:#Update - Openreach determined that Centra - Antrim (Belfast Road) requires a site survey to progress and this has now been carried out by the survey group. A survey pack and pictures outlining the work has been sent. This will be automatically cancelled on the 12th of September if the charges have not been approved, therefore please let us know how you wish to proceed as soon as possible. _x000D_21/8/2024:#Update - Order has been delayed due to network planning. CSL will update as more information become available. _x000D_20/8/2024:#Update - Order has been delayed due to network planning. CSL will update as more information become available. _x000D_19/8/2024:#Update - Order has been delayed due to network planning. CSL will update as more information become available. _x000D_19/8/2024:01563071 _x000D_16/8/2024:#Update - Order has been delayed due to network planning. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order has been delayed due to network planning. CSL will update as more information become available. _x000D_14/8/2024:#Update - Order has been delayed due to network planning. CSL will update as more information become available. _x000D_13/8/2024:#Update - Order has been delayed due to network planning. CSL will update as more information become available. _x000D_12/8/2024:#Update - Order has been delayed due to network planning. CSL will update as more information become available. _x000D_9/8/2024:#Update - Order has been delayed due to network planning. CSL will update as more information become available. _x000D_8/8/2024:06/08/2024 _x000D_6/8/2024:06/08/2024 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - Openreach determined that Centra - Antrim (Belfast Road) requires a site survey to progress and this has now been carried out by the survey group. A survey pack and pictures outlining the work has been sent. This will be automatically cancelled on the 12th of September if the charges have not been approved, therefore please let us know how you wish to proceed as soon as possible. |  |  |  |  | 2.Allwyn to arrange access | VFP2422519 | 30017402 | 1.Provisioning | AM |  | 2024-08-06 | 2024-08-06 |  | 0 | [11 empty] | 0
1307 | 653797 |  | Batch 6 Aug 24 | Type 1 | KCOM/Mobile | Village News | HESSLE | HU13 0AA | 2024-07-11 | 6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 AM _x000D_22/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 23/08 PM. Please speak with the retailer regarding installation details and confirm to CSL if 23/08 is a suitable date. _x000D_21/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 23/08 PM. Please speak with the retailer regarding installation details and confirm to CSL if 23/08 is a suitable date. _x000D_20/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 23/08 PM. Please speak with the retailer regarding installation details and confirm to CSL if 23/08 is a suitable date. _x000D_19/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 23/08 PM. Please speak with the retailer regarding installation details and confirm to CSL if 23/08 is a suitable date. _x000D_19/8/2024:01579283 _x000D_16/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 23/08 PM. Please speak with the retailer regarding installation details and confirm to CSL if 23/08 is a suitable date. _x000D_15/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 23/08 PM. Please speak with the retailer regarding installation details and confirm to CSL if 23/08 is a suitable date. _x000D_14/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 23/08 PM. Please speak with the retailer regarding installation details and confirm to CSL if 23/08 is a suitable date. _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 AM _x000D_6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 AM _x000D_22/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 23/08 PM. Please speak with the retailer regarding installation details and confirm to CSL if 23/08 is a suitable date. _x000D_21/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 23/08 PM. Please speak with the retailer regarding installation details and confirm to CSL if 23/08 is a suitable date. _x000D_20/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 23/08 PM. Please speak with the retailer regarding installation details and confirm to CSL if 23/08 is a suitable date. _x000D_19/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 23/08 PM. Please speak with the retailer regarding installation details and confirm to CSL if 23/08 is a suitable date. _x000D_19/8/2024:01579283 _x000D_16/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 23/08 PM. Please speak with the retailer regarding installation details and confirm to CSL if 23/08 is a suitable date. _x000D_15/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 23/08 PM. Please speak with the retailer regarding installation details and confirm to CSL if 23/08 is a suitable date. _x000D_14/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 23/08 PM. Please speak with the retailer regarding installation details and confirm to CSL if 23/08 is a suitable date. _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - Allwyn confirmed Retailer has agreed to installation on 09/09 AM |  |  |  |  | 2.Allwyn to arrange access | BUS0004439 | 30021844 | 1.Provisioning | PM | 2024-08-05 | 2024-08-23 | 2024-08-23 |  | 0 | [11 empty] | 0
1308 | 665541 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Lockharts Spar | COLERAINE | BT52 2EH | 2024-08-07 | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFP2422515 | 30017294 | 3.In life |  |  | 2024-08-06 | 2024-08-06 | 2024-08-06 11:59 | TRUE |  |  |  | 2024-09-02 |  |  |  | 2024-09-02 | 23A004952901 | 23A004952901 | 2024-09-03 | 1
1309 | 664935 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Premier Barrys Halton Moor | LEEDS | LS9 0HB | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 15:13 _x000D_26/7/2024:22/07/2024 15:13 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 15:13 _x000D_26/7/2024:22/07/2024 15:13 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2422514 | 30017419 | 1.Provisioning | AM |  | 2024-08-09 | 2024-09-06 |  | 0 | [11 empty] | 0
1310 | 657123 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Premier | SUNDERLAND | SR4 6NT | 2024-08-07 | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:Update: Order Completed by Supplier _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:Update: Order Completed by Supplier _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFS1043973 | 30017534 | 2.Commissioning |  |  | 2024-08-06 | 2024-08-06 | 2024-08-06 10:31 | TRUE |  |  |  | 2024-09-06 | [7 empty] | 0
1311 | 426543 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | One O One Off Sales Ltd | GLASGOW | G45 9AA | 2024-08-07 | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043971 | 30017533 | 2.Commissioning |  |  | 2024-08-06 | 2024-08-06 | 2024-08-06 12:28 | TRUE |  |  |  | 2024-09-11 | [7 empty] | 0
1312 | 662204 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Kushan Newsagent | LONDON | N9 7EP | 2024-08-28 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:#Update - NFA - Allwyn confirmed installation date with retailer 27/08 AM _x000D_28/8/2024:#Update - NFA - Allwyn confirmed installation date with retailer 27/08 AM _x000D_27/8/2024:#Update - NFA - Allwyn confirmed installation date with retailer 27/08 AM _x000D_22/8/2024:#Update - NFA - Allwyn confirmed installation date with retailer 27/08 AM _x000D_21/8/2024:#Update - NFA - Allwyn confirmed installation date with retailer 27/08 AM _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_8/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:#Update - NFA - Allwyn confirmed installation date with retailer 27/08 AM _x000D_28/8/2024:#Update - NFA - Allwyn confirmed installation date with retailer 27/08 AM _x000D_27/8/2024:#Update - NFA - Allwyn confirmed installation date with retailer 27/08 AM _x000D_22/8/2024:#Update - NFA - Allwyn confirmed installation date with retailer 27/08 AM _x000D_21/8/2024:#Update - NFA - Allwyn confirmed installation date with retailer 27/08 AM _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_8/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFS1043972 | 30017561 | 2.Commissioning | AM |  | 2024-08-07 | 2024-08-27 |  | 0 | [11 empty] | 0
1313 | 672567 |  | Batch 6 Aug 24 | Type 1 | KCOM/Mobile | Budgens Hessle Road | HULL | HU3 3DU | 2024-07-11 | 12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:An existing issue with the Customer Apparatus has been detected on this line. This may impact the new service. _x000D_18/7/2024:An existing issue with the Customer Apparatus has been detected on this line. This may impact the new service. _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:An existing issue with the Customer Apparatus has been detected on this line. This may impact the new service. _x000D_18/7/2024:An existing issue with the Customer Apparatus has been detected on this line. This may impact the new service. _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | BUS0004447 | 30017241 | 1.Provisioning | [17 empty] | 0 | 672567
1314 | 429774 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Frances Street Service Station | NEWTOWNARDS | BT23 7DX | 2024-09-03 | 6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_29/8/2024:#Update - The engineer was unable to locate the internal DP within the premise, the retailer is responsible for investigating where this is located before the next appointment. _x000D_28/8/2024:#Update - The engineer was unable to locate the internal DP within the premise, the retailer is responsible for investigating where this is located before the next appointment. _x000D_27/8/2024:#Update - The engineer was unable to locate the internal DP within the premise, the retailer is responsible for investigating where this is located before the next appointment. _x000D_22/8/2024:#Update - The engineer was unable to locate the internal DP within the premise, the retailer is responsible for investigating where this is located before the next appointment. _x000D_21/8/2024:#Update - The engineer was unable to locate the internal DP within the premise, the retailer is responsible for investigating where this is located before the next appointment. _x000D_20/8/2024:#Update - The engineer was unable to locate the internal DP within the premise, the retailer is responsible for investigating where this is located before the next appointment. _x000D_19/8/2024:#Update - The engineer was unable to locate the internal DP within the premise, the retailer is responsible for investigating where this is located before the next appointment. _x000D_19/8/2024:01563966 _x000D_16/8/2024:#Update - The engineer was unable to locate the internal DP within the premise, the retailer is responsible for investigating where this is located before the next appointment. _x000D_15/8/2024:#Update - The engineer was unable to locate the internal DP within the premise, the retailer is responsible for investigating where this is located before the next appointment. _x000D_14/8/2024:#Update - The engineer was unable to locate the internal DP within the premise, the retailer is responsible for investigating where this is located before the next appointment. _x000D_13/8/2024:#Update - The engineer was unable to locate the internal DP within the premise, the retailer is responsible for investigating where this is located before the next appointment. _x000D_12/8/2024:#Update - The engineer was unable to locate the internal DP within the premise, the retailer is responsible for investigating where this is located before the next appointment. _x000D_9/8/2024:#Update - The engineer was unable to locate the internal DP within the premise, the retailer is responsible for investigating where this is located before the next appointment. _x000D_8/8/2024:07/08/2024 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:An existing issue with the Customer Apparatus has been detected on this line. This may impact the new service. _x000D_23/7/2024:An existing issue with the Customer Apparatus has been detected on this line. This may impact the new service. _x000D_22/7/2024:An existing issue with the Customer Apparatus has been detected on this line. This may impact the new service. _x000D_22/7/2024:An existing issue with the Customer Apparatus has been detected on this line. This may impact the new service. _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_29/8/2024:#Update - The engineer was unable to locate the internal DP within the premise, the retailer is responsible for investigating where this is located before the next appointment. _x000D_28/8/2024:#Update - The engineer was unable to locate the internal DP within the premise, the retailer is responsible for investigating where this is located before the next appointment. _x000D_27/8/2024:#Update - The engineer was unable to locate the internal DP within the premise, the retailer is responsible for investigating where this is located before the next appointment. _x000D_22/8/2024:#Update - The engineer was unable to locate the internal DP within the premise, the retailer is responsible for investigating where this is located before the next appointment. _x000D_21/8/2024:#Update - The engineer was unable to locate the internal DP within the premise, the retailer is responsible for investigating where this is located before the next appointment. _x000D_20/8/2024:#Update - The engineer was unable to locate the internal DP within the premise, the retailer is responsible for investigating where this is located before the next appointment. _x000D_19/8/2024:#Update - The engineer was unable to locate the internal DP within the premise, the retailer is responsible for investigating where this is located before the next appointment. _x000D_19/8/2024:01563966 _x000D_16/8/2024:#Update - The engineer was unable to locate the internal DP within the premise, the retailer is responsible for investigating where this is located before the next appointment. _x000D_15/8/2024:#Update - The engineer was unable to locate the internal DP within the premise, the retailer is responsible for investigating where this is located before the next appointment. _x000D_14/8/2024:#Update - The engineer was unable to locate the internal DP within the premise, the retailer is responsible for investigating where this is located before the next appointment. _x000D_13/8/2024:#Update - The engineer was unable to locate the internal DP within the premise, the retailer is responsible for investigating where this is located before the next appointment. _x000D_12/8/2024:#Update - The engineer was unable to locate the internal DP within the premise, the retailer is responsible for investigating where this is located before the next appointment. _x000D_9/8/2024:#Update - The engineer was unable to locate the internal DP within the premise, the retailer is responsible for investigating where this is located before the next appointment. _x000D_8/8/2024:07/08/2024 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:An existing issue with the Customer Apparatus has been detected on this line. This may impact the new service. _x000D_23/7/2024:An existing issue with the Customer Apparatus has been detected on this line. This may impact the new service. _x000D_22/7/2024:An existing issue with the Customer Apparatus has been detected on this line. This may impact the new service. _x000D_22/7/2024:An existing issue with the Customer Apparatus has been detected on this line. This may impact the new service. _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | Order Completed | #Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM |  |  |  |  | 2.Allwyn to arrange access | VFS1056989 | 30017339 | 2.Commissioning | AM |  | 2024-08-06 | 2024-09-02 |  | 0 | [11 empty] | 0
1315 | 655005 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Watsons Newagents | EASTBOURNE | BN21 3NW | 2024-07-11 | 6/9/2024:#Update missed appointment due to blocked lineplant. Rescheduled for 19/09 AM _x000D_5/9/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:Update: Order Amended _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:End User Missed appointment. Action required _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update missed appointment due to blocked lineplant. Rescheduled for 19/09 AM _x000D_6/9/2024:#Update missed appointment due to blocked lineplant. Rescheduled for 19/09 AM _x000D_5/9/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:Update: Order Amended _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:End User Missed appointment. Action required _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | Update: Order Amended | #Update missed appointment due to blocked lineplant. Rescheduled for 19/09 AM |  |  |  |  | 2.Allwyn to arrange access | VFS1043970 | 30017569 | 1.Provisioning | AM |  | 2024-08-07 | 2024-08-23 |  | 0 | [11 empty] | 0
1316 | 666928 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Post Office | BELFAST | BT11 9AE | 2024-08-08 | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:#Update - Supplier delay - review date of 22/07/2024. We will continue to provide update as they become available. _x000D_18/7/2024:#Update - Supplier delay - review date of 22/07/2024. We will continue to provide update as they become available. _x000D_17/7/2024:#Update - Supplier delay - review date of 22/07/2024. We will continue to provide update as they become available. _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:#Update - Supplier delay - review date of 22/07/2024. We will continue to provide update as they become available. _x000D_18/7/2024:#Update - Supplier delay - review date of 22/07/2024. We will continue to provide update as they become available. _x000D_17/7/2024:#Update - Supplier delay - review date of 22/07/2024. We will continue to provide update as they become available. _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043969 | 30017474 | 3.In life |  |  | 2024-08-07 | 2024-08-07 | 2024-08-07 14:44 | TRUE |  |  |  | 2024-09-03 |  |  |  | 2024-09-03 | 23A004952897 | 23A004952897 | 2024-09-04 | 1
1317 | 652480 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Supersaver | WEMBLEY | HA0 1SL | 2024-08-07 | 9/8/2024:#Update - Supplier delay - review date of 22/07/2024. We will continue to provide update as they become available. _x000D_8/8/2024:16/07/2024 _x000D_6/8/2024:16/07/2024 _x000D_5/8/2024:16/07/2024 _x000D_2/8/2024:16/07/2024 _x000D_1/8/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_30/7/2024:#Update - Supplier delay - review date of 22/07/2024. We will continue to provide update as they become available. _x000D_29/7/2024:#Update - Supplier delay - review date of 22/07/2024. We will continue to provide update as they become available. _x000D_29/7/2024:01495506 _x000D_26/7/2024:01495506 _x000D_24/7/2024:#Update - Supplier delay - review date of 22/07/2024. We will continue to provide update as they become available. _x000D_23/7/2024:#Update - Supplier delay - review date of 22/07/2024. We will continue to provide update as they become available. _x000D_22/7/2024:#Update - Supplier delay - review date of 22/07/2024. We will continue to provide update as they become available. _x000D_22/7/2024:#Update - Supplier delay - review date of 22/07/2024. We will continue to provide update as they become available. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/8/2024:#Update - Supplier delay - review date of 22/07/2024. We will continue to provide update as they become available. _x000D_8/8/2024:16/07/2024 _x000D_6/8/2024:16/07/2024 _x000D_5/8/2024:16/07/2024 _x000D_2/8/2024:16/07/2024 _x000D_1/8/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_30/7/2024:#Update - Supplier delay - review date of 22/07/2024. We will continue to provide update as they become available. _x000D_29/7/2024:#Update - Supplier delay - review date of 22/07/2024. We will continue to provide update as they become available. _x000D_29/7/2024:01495506 _x000D_26/7/2024:01495506 _x000D_24/7/2024:#Update - Supplier delay - review date of 22/07/2024. We will continue to provide update as they become available. _x000D_23/7/2024:#Update - Supplier delay - review date of 22/07/2024. We will continue to provide update as they become available. _x000D_22/7/2024:#Update - Supplier delay - review date of 22/07/2024. We will continue to provide update as they become available. _x000D_22/7/2024:#Update - Supplier delay - review date of 22/07/2024. We will continue to provide update as they become available. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1055188 | 30017770 | 2.Commissioning |  |  | 2024-08-06 | 2024-08-06 | 2024-08-06 14:28 | TRUE |  |  |  | 2024-08-28 | [7 empty] | 0
1318 | 430290 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Vivo | NEWTOWNABBEY | BT36 5ED | 2024-08-08 | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFP2422511 | 30017331 | 3.In life |  |  | 2024-08-07 | 2024-08-07 | 2024-08-07 12:51 | TRUE |  |  |  | 2024-09-03 |  |  |  | 2024-09-03 | 23A004952898 | 23A004952898 | 2024-09-04 | 1
1319 | 429708 |  | Batch 6 Aug 24 | Type 1 | SURE/Mobile | Convenience Shopping Centre | ISLE OF MAN | IM1 3JX | 2024-08-13 | 13/8/2024:#Update Retailer happy with appointment 09/08, AM. _x000D_12/8/2024:#Update Retailer happy with appointment 09/08, AM. _x000D_9/8/2024:#Update Retailer happy with appointment 09/08, AM. _x000D_8/8/2024:22/07/2024 _x000D_6/8/2024:22/07/2024 _x000D_5/8/2024:22/07/2024 _x000D_2/8/2024:22/07/2024 _x000D_1/8/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_30/7/2024:#Update Retailer happy with appointment 09/08, AM. _x000D_29/7/2024:#Update Retailer happy with appointment 09/08, AM. _x000D_29/7/2024:01501619 _x000D_26/7/2024:01501619 _x000D_24/7/2024:#Update Retailer happy with appointment 09/08, AM. _x000D_23/7/2024:#Update Retailer happy with appointment 09/08, AM. _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_0 | 13/8/2024:#Update Retailer happy with appointment 09/08, AM. _x000D_12/8/2024:#Update Retailer happy with appointment 09/08, AM. _x000D_9/8/2024:#Update Retailer happy with appointment 09/08, AM. _x000D_8/8/2024:22/07/2024 _x000D_6/8/2024:22/07/2024 _x000D_5/8/2024:22/07/2024 _x000D_2/8/2024:22/07/2024 _x000D_1/8/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_30/7/2024:#Update Retailer happy with appointment 09/08, AM. _x000D_29/7/2024:#Update Retailer happy with appointment 09/08, AM. _x000D_29/7/2024:01501619 _x000D_26/7/2024:01501619 _x000D_24/7/2024:#Update Retailer happy with appointment 09/08, AM. _x000D_23/7/2024:#Update Retailer happy with appointment 09/08, AM. _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_0 | [6 empty] | 2.Allwyn to arrange access | 1624894119 | 30017245 | 2.Commissioning |  |  | 2024-08-09 | 2024-08-09 | 2024-08-09 12:00 | TRUE | [11 empty] | 0
1320 | 646080 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Frenchgate News & Food | DONCASTER | DN1 1SR | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Silver Address Issue | 30021798 | 1.Provisioning | AM |  | 2024-08-07 |  |  | 0 | [11 empty] | 0
1321 | 636748 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Go Local Convenience Store | MANCHESTER | M40 7WE | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Silver Address Issue | 30017776 | 1.Provisioning | AM |  | 2024-08-07 |  |  | 0 | [11 empty] | 0
1322 | 418769 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Nisa Local | OLDBURY | B68 9LW | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 09:56 _x000D_26/7/2024:22/07/2024 09:56 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 09:56 _x000D_26/7/2024:22/07/2024 09:56 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2422508 | 30017417 | 1.Provisioning | AM |  | 2024-08-07 | 2024-09-06 |  | 0 | [11 empty] | 0
1323 | 461818 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | SPAR | COLERAINE | BT52 2JB | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Address query | 30017694 | 1.Provisioning | AM |  | 2024-08-07 |  |  | 0 | [11 empty] | 0
1324 | 664766 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Penny Cards At Cardarama | BOOTLE | L30 5QA | 2024-08-08 | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFP2423429 | 30017501 | 6.Failed router install |  |  | 2024-08-07 | 2024-08-07 | 2024-08-07 11:09 | TRUE |  |  |  | 2024-08-29 |  |  |  | 2024-08-29 | 23A004948663 | 23A004948663 | 2024-08-30 | 1
1325 | 651840 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Supervalu Supermarket | LISBURN | BT28 2EA | 2024-08-28 | 29/8/2024:#Update - The issue has now been resolved and the installation has a committed date 27/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/08 is a suitable date. _x000D_28/8/2024:#Update - The issue has now been resolved and the installation has a committed date 27/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/08 is a suitable date. _x000D_27/8/2024:#Update - The issue has now been resolved and the installation has a committed date 27/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/08 is a suitable date. _x000D_22/8/2024:#Update - The issue has now been resolved and the installation has a committed date 27/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/08 is a suitable date. _x000D_21/8/2024:#Update - The issue has now been resolved and the installation has a committed date 27/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/08 is a suitable date. _x000D_20/8/2024:#Update - The issue has now been resolved and the installation has a committed date 27/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/08 is a suitable date. _x000D_19/8/2024:#Update - The issue has now been resolved and the installation has a committed date 27/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/08 is a suitable date. _x000D_19/8/2024:01566272 _x000D_16/8/2024:#Update - The issue has now been resolved and the installation has a committed date 27/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/08 is a suitable date. _x000D_15/8/2024:#Update - The issue has now been resolved and the installation has a committed date 27/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/08 is a suitable date. _x000D_14/8/2024:#Update - The issue has now been resolved and the installation has a committed date 27/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/08 is a suitable date. _x000D_13/8/2024:#Update - The issue has now been resolved and the installation has a committed date 27/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/08 is a suitable date. _x000D_12/8/2024:#Update - The issue has now been resolved and the installation has a committed date 27/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/08 is a suitable date. _x000D_9/8/2024:#Update - The issue has now been resolved and the installation has a committed date 27/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/08 is a suitable date. _x000D_8/8/2024:07/08/2024 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 29/8/2024:#Update - The issue has now been resolved and the installation has a committed date 27/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/08 is a suitable date. _x000D_28/8/2024:#Update - The issue has now been resolved and the installation has a committed date 27/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/08 is a suitable date. _x000D_27/8/2024:#Update - The issue has now been resolved and the installation has a committed date 27/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/08 is a suitable date. _x000D_22/8/2024:#Update - The issue has now been resolved and the installation has a committed date 27/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/08 is a suitable date. _x000D_21/8/2024:#Update - The issue has now been resolved and the installation has a committed date 27/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/08 is a suitable date. _x000D_20/8/2024:#Update - The issue has now been resolved and the installation has a committed date 27/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/08 is a suitable date. _x000D_19/8/2024:#Update - The issue has now been resolved and the installation has a committed date 27/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/08 is a suitable date. _x000D_19/8/2024:01566272 _x000D_16/8/2024:#Update - The issue has now been resolved and the installation has a committed date 27/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/08 is a suitable date. _x000D_15/8/2024:#Update - The issue has now been resolved and the installation has a committed date 27/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/08 is a suitable date. _x000D_14/8/2024:#Update - The issue has now been resolved and the installation has a committed date 27/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/08 is a suitable date. _x000D_13/8/2024:#Update - The issue has now been resolved and the installation has a committed date 27/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/08 is a suitable date. _x000D_12/8/2024:#Update - The issue has now been resolved and the installation has a committed date 27/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/08 is a suitable date. _x000D_9/8/2024:#Update - The issue has now been resolved and the installation has a committed date 27/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 27/08 is a suitable date. _x000D_8/8/2024:07/08/2024 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1078860 | 30017583 | 2.Commissioning | AM |  | 2024-08-07 | 2024-08-27 |  | 0 | [11 empty] | 0
1326 | 470855 |  | Batch 6 Aug 24 | Type 1 | KCOM/Mobile | Wharfedale Premier | HULL | HU9 3UA | 2024-07-11 | 6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 11/09 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 11/09 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 11/09 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 11/09 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 11/09 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 11/09 AM _x000D_28/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 11/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 11/09 is a suitable date. _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 11/09 AM _x000D_6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 11/09 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 11/09 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 11/09 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 11/09 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 11/09 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 11/09 AM _x000D_28/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 11/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 11/09 is a suitable date. _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - Allwyn confirmed Retailer has agreed to installation on 11/09 AM |  |  |  |  | 2.Allwyn to arrange access | BUS0004486 | 30017268 | 1.Provisioning | AM | 2024-08-15 | 2024-08-15 |  |  | 0 | [11 empty] | 0
1327 | 470992 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Piccadilly Card & News | LONDON | W1S 4RR | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_18/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_18/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Silver Address Issue | 30017689 | 1.Provisioning | AM |  | 2024-08-07 |  |  | 0 | [11 empty] | 0
1328 | 670825 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Post Office | MILFORD HAVEN | SA73 2AA | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:Update: Order Amended _x000D_19/8/2024:Update: Order Amended _x000D_19/8/2024:13/08/2024 10:19 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Your order has been delayed due to a routing issue at our suppliers. Now backend team confirmed that new routings has been updated, Please check with end user and reappoint the order. _x000D_9/8/2024:Your order has been delayed due to a routing issue at our suppliers. The order has now been passed to a backend team to update. They have given us a review date of 12/08/2024. Once routing update we will progress the order. _x000D_8/8/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_23/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_22/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_22/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:Update: Order Amended _x000D_19/8/2024:Update: Order Amended _x000D_19/8/2024:13/08/2024 10:19 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Your order has been delayed due to a routing issue at our suppliers. Now backend team confirmed that new routings has been updated, Please check with end user and reappoint the order. _x000D_9/8/2024:Your order has been delayed due to a routing issue at our suppliers. The order has now been passed to a backend team to update. They have given us a review date of 12/08/2024. Once routing update we will progress the order. _x000D_8/8/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_23/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_22/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_22/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFS1055177 | 30017731 | 1.Provisioning | AM |  | 2024-08-07 | 2024-09-06 |  | 0 | [11 empty] | 0
1329 | 427934 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Strelley Supermarket | NOTTINGHAM | NG8 6LR | 2024-07-11 | 6/9/2024:#Update Missed appointment. Customer requested out of hours due to safety, engineer was unable to work because of step ladders as customers and staff are within the facility. OOH being discussed _x000D_5/9/2024:#Update Missed appointment. Customer requested out of hours due to safety, engineer was unable to work because of step ladders as customers and staff are within the facility. OOH being discussed _x000D_4/9/2024:#Update Missed appointment. Customer requested out of hours due to safety, engineer was unable to work because of step ladders as customers and staff are within the facility. OOH being discussed _x000D_3/9/2024:#Update Missed appointment. Customer requested out of hours due to safety, engineer was unable to work because of step ladders as customers and staff are within the facility. OOH being discussed _x000D_2/9/2024:#Update Missed appointment. Customer requested out of hours due to safety, engineer was unable to work because of step ladders as customers and staff are within the facility. OOH being discussed _x000D_29/8/2024:#Update Missed appointment. Customer requested out of hours due to safety, engineer was unable to work because of step ladders as customers and staff are within the facility. OOH being discussed _x000D_28/8/2024:#Update Missed appointment. Customer requested out of hours due to safety, engineer was unable to work because of step ladders as customers and staff are within the facility. OOH being discussed _x000D_27/8/2024:#Update Missed appointment. Customer requested out of hours due to safety, engineer was unable to work because of step ladders as customers and staff are within the facility. OOH being discussed _x000D_22/8/2024:#Update Missed appointment. Customer requested out of hours due to safety, engineer was unable to work because of step ladders as customers and staff are within the facility. OOH being discussed _x000D_21/8/2024:#Update Missed appointment. Customer requested out of hours due to safety, engineer was unable to work because of step ladders as customers and staff are within the facility. OOH being discussed _x000D_20/8/2024:#Update Missed appointment. Customer requested out of hours due to safety, engineer was unable to work because of step ladders as customers and staff are within the facility. OOH being discussed _x000D_19/8/2024:#Update Missed appointment. Customer requested out of hours due to safety, engineer was unable to work because of step ladders as customers and staff are within the facility. OOH being discussed _x000D_19/8/2024:01566615 _x000D_16/8/2024:#Update Missed appointment. Customer requested out of hours due to safety, engineer was unable to work because of step ladders as customers and staff are within the facility. OOH being discussed _x000D_15/8/2024:#Update Missed appointment. Customer requested out of hours due to safety, engineer was unable to work because of step ladders as customers and staff are within the facility. OOH being discussed _x000D_14/8/2024:#Update Missed appointment. Customer requested out of hours due to safety, engineer was unable to work because of step ladders as customers and staff are within the facility. OOH being discussed _x000D_13/8/2024:#Update Missed appointment. Customer requested out of hours due to safety, engineer was unable to work because of step ladders as customers and staff are within the facility. OOH being discussed _x000D_12/8/2024:#Update Missed appointment. Customer requested out of hours due to safety, engineer was unable to work because of step ladders as customers and staff are within the facility. OOH being discussed _x000D_9/8/2024:#Update Missed appointment. Customer requested out of hours due to safety, engineer was unable to work because of step ladders as customers and staff are within the facility. OOH being discussed _x000D_8/8/2024:07/08/2024 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update Missed appointment. Customer requested out of hours due to safety, engineer was unable to work because of step ladders as customers and staff are within the facility. OOH being discussed _x000D_6/9/2024:#Update Missed appointment. Customer requested out of hours due to safety, engineer was unable to work because of step ladders as customers and staff are within the facility. OOH being discussed _x000D_5/9/2024:#Update Missed appointment. Customer requested out of hours due to safety, engineer was unable to work because of step ladders as customers and staff are within the facility. OOH being discussed _x000D_4/9/2024:#Update Missed appointment. Customer requested out of hours due to safety, engineer was unable to work because of step ladders as customers and staff are within the facility. OOH being discussed _x000D_3/9/2024:#Update Missed appointment. Customer requested out of hours due to safety, engineer was unable to work because of step ladders as customers and staff are within the facility. OOH being discussed _x000D_2/9/2024:#Update Missed appointment. Customer requested out of hours due to safety, engineer was unable to work because of step ladders as customers and staff are within the facility. OOH being discussed _x000D_29/8/2024:#Update Missed appointment. Customer requested out of hours due to safety, engineer was unable to work because of step ladders as customers and staff are within the facility. OOH being discussed _x000D_28/8/2024:#Update Missed appointment. Customer requested out of hours due to safety, engineer was unable to work because of step ladders as customers and staff are within the facility. OOH being discussed _x000D_27/8/2024:#Update Missed appointment. Customer requested out of hours due to safety, engineer was unable to work because of step ladders as customers and staff are within the facility. OOH being discussed _x000D_22/8/2024:#Update Missed appointment. Customer requested out of hours due to safety, engineer was unable to work because of step ladders as customers and staff are within the facility. OOH being discussed _x000D_21/8/2024:#Update Missed appointment. Customer requested out of hours due to safety, engineer was unable to work because of step ladders as customers and staff are within the facility. OOH being discussed _x000D_20/8/2024:#Update Missed appointment. Customer requested out of hours due to safety, engineer was unable to work because of step ladders as customers and staff are within the facility. OOH being discussed _x000D_19/8/2024:#Update Missed appointment. Customer requested out of hours due to safety, engineer was unable to work because of step ladders as customers and staff are within the facility. OOH being discussed _x000D_19/8/2024:01566615 _x000D_16/8/2024:#Update Missed appointment. Customer requested out of hours due to safety, engineer was unable to work because of step ladders as customers and staff are within the facility. OOH being discussed _x000D_15/8/2024:#Update Missed appointment. Customer requested out of hours due to safety, engineer was unable to work because of step ladders as customers and staff are within the facility. OOH being discussed _x000D_14/8/2024:#Update Missed appointment. Customer requested out of hours due to safety, engineer was unable to work because of step ladders as customers and staff are within the facility. OOH being discussed _x000D_13/8/2024:#Update Missed appointment. Customer requested out of hours due to safety, engineer was unable to work because of step ladders as customers and staff are within the facility. OOH being discussed _x000D_12/8/2024:#Update Missed appointment. Customer requested out of hours due to safety, engineer was unable to work because of step ladders as customers and staff are within the facility. OOH being discussed _x000D_9/8/2024:#Update Missed appointment. Customer requested out of hours due to safety, engineer was unable to work because of step ladders as customers and staff are within the facility. OOH being discussed _x000D_8/8/2024:07/08/2024 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | Update: Order Amended | #Update Missed appointment. Customer requested out of hours due to safety, engineer was unable to work because of step ladders as customers and staff are within the facility. OOH being discussed |  |  |  |  | 2.Allwyn to arrange access | VFS1043967 | 30017469 | 1.Provisioning | AM |  | 2024-08-07 | 2024-09-04 |  | 0 | [11 empty] | 0
1330 | 438473 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Interchange News Ltd | GATESHEAD | NE8 1BH | 2024-08-08 | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043963 | 30017449 | 6.Failed router install |  |  | 2024-08-07 | 2024-08-07 | 2024-08-07 08:53 | TRUE |  |  |  | 2024-08-29 |  |  |  | 2024-08-29 | 242005008921 | 242005008921 | 2024-08-30 | 1
1331 | 644754 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Spar Stores | HARTLEPOOL | TS24 8NA | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 19/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_9/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 19/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_8/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 19/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 19/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 06/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_2/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 06/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_1/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 06/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:Supplier Delay: Issues with provision of the underground network, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:37800 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_23/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 19/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_9/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 19/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_8/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 19/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 19/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 06/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_2/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 06/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_1/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 06/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:Supplier Delay: Issues with provision of the underground network, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:37800 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_23/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2422506 | 30017418 | 1.Provisioning | AM |  | 2024-08-07 |  |  | 0 | [11 empty] | 0
1332 | 646342 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Dannys | SWINDON | SN3 2GD | 2024-08-08 | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1057062 | 30017343 | 3.In life |  |  | 2024-08-07 | 2024-08-07 | 2024-08-07 12:58 | TRUE |  |  |  | 2024-09-05 |  |  |  | 2024-09-05 | 242005011035 | 242005011035 | 2024-09-06 | 1
1333 | 665119 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Post Office | HEBBURN | NE31 1AA | 2024-07-11 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:Update: Order Amended _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:Update: Order Amended _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | Update: Order Amended | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2421299 | 30017707 | 1.Provisioning | AM |  | 2024-08-07 | 2024-08-21 |  | 0 | [11 empty] | 0
1334 | 458658 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Spar Stores | LLANGEFNI | LL77 7LT | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:Your order has been delayed. The engineer has now completed all the external work and our suppliers has advised us to reappoint the order. Please check with end user and reappoint for the first available date. _x000D_19/8/2024:Your order has been delayed. The engineer has now completed all the external work and our suppliers has advised us to reappoint the order. Please check with end user and reappoint for the first available date. _x000D_19/8/2024:15/08/2024 10:11 _x000D_16/8/2024:Your order has been delayed. The engineer has now completed all the external work and our suppliers has advised us to reappoint the order. Please check with end user and reappoint for the first available date. _x000D_15/8/2024:Your order has been delayed. The engineer has now completed all the external work and our suppliers has advised us to reappoint the order. Please check with end user and reappoint for the first available date. _x000D_14/8/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_13/8/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_12/8/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_9/8/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_8/8/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:Your order has been delayed. The engineer has now completed all the external work and our suppliers has advised us to reappoint the order. Please check with end user and reappoint for the first available date. _x000D_19/8/2024:Your order has been delayed. The engineer has now completed all the external work and our suppliers has advised us to reappoint the order. Please check with end user and reappoint for the first available date. _x000D_19/8/2024:15/08/2024 10:11 _x000D_16/8/2024:Your order has been delayed. The engineer has now completed all the external work and our suppliers has advised us to reappoint the order. Please check with end user and reappoint for the first available date. _x000D_15/8/2024:Your order has been delayed. The engineer has now completed all the external work and our suppliers has advised us to reappoint the order. Please check with end user and reappoint for the first available date. _x000D_14/8/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_13/8/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_12/8/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_9/8/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_8/8/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFS1055171 | 30017732 | 1.Provisioning | AM |  | 2024-08-07 | 2024-08-07 |  | 0 | [11 empty] | 0
1335 | 666687 |  | Batch 6 Aug 24 | Type 1 | KCOM/Mobile | Jackpot Wines | HULL | HU8 8HP | 2024-09-03 | 6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_19/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 02/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 02/09 is a suitable date. _x000D_19/8/2024:01592306 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_18/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_17/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_19/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 02/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 02/09 is a suitable date. _x000D_19/8/2024:01592306 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_18/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_17/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM |  |  |  |  | 2.Allwyn to arrange access | BUS0004472 | 30017242 | 2.Commissioning | AM | 2024-08-13 | 2024-08-13 |  |  | 0 | [11 empty] | 0
1336 | 473498 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Loco | GRIMSBY | DN32 7LH | 2024-08-08 | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_22/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_22/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_22/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_22/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1055167 | 30017766 | 6.Failed router install |  |  | 2024-08-07 | 2024-08-07 | 2024-08-07 11:37 | TRUE |  |  |  | 2024-08-28 |  |  |  | 2024-08-28 | 23A004948595 | 23A004948595 | 2024-08-29 | 1
1337 | 620353 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | T & B News | HARROW | HA3 8DQ | 2024-09-04 | 6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:Order Completed _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:Update: Order Amended _x000D_19/8/2024:Update: Order Amended _x000D_19/8/2024:14/08/2024 09:46 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_9/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:Order Completed _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:Update: Order Amended _x000D_19/8/2024:Update: Order Amended _x000D_19/8/2024:14/08/2024 09:46 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_9/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | Order Completed | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2422505 | 30017314 | 2.Commissioning | AM |  | 2024-08-07 | 2024-09-03 |  | 0 | [11 empty] | 0
1338 | 664864 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Kandola Food Stores | STEVENAGE | SG2 8LU | 2024-08-08 | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043964 | 30017551 | 6.Failed router install |  |  | 2024-08-07 | 2024-08-07 | 2024-08-07 12:24 | TRUE |  |  |  | 2024-08-28 |  |  |  | 2024-08-30 | 23A004945993 | 23A004945993 | 2024-09-05 | 1
1339 | 608463 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Centra Balloo | BANGOR | BT19 7PG | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 09:52 _x000D_26/7/2024:22/07/2024 09:52 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 09:52 _x000D_26/7/2024:22/07/2024 09:52 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2422502 | 30017392 | 1.Provisioning | AM |  | 2024-08-07 | 2024-09-06 |  | 0 | [11 empty] | 0
1340 | 462317 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Spar | BELFAST | BT5 5DS | 2024-09-04 | 6/9/2024:#Update - missed appointment, manager not on site, the office was locked and only the manager has the key _x000D_5/9/2024:#Update - missed appointment, manager not on site, the office was locked and only the manager has the key _x000D_4/9/2024:#Update - missed appointment, manager not on site, the office was locked and only the manager has the key _x000D_3/9/2024:#Update - missed appointment, manager not on site, the office was locked and only the manager has the key _x000D_2/9/2024:#Update - missed appointment, manager not on site, the office was locked and only the manager has the key _x000D_29/8/2024:#Update - missed appointment, manager not on site, the office was locked and only the manager has the key _x000D_28/8/2024:#Update - missed appointment, manager not on site, the office was locked and only the manager has the key _x000D_27/8/2024:#Update - missed appointment, manager not on site, the office was locked and only the manager has the key _x000D_22/8/2024:#Update - missed appointment, manager not on site, the office was locked and only the manager has the key _x000D_21/8/2024:#Update - missed appointment, manager not on site, the office was locked and only the manager has the key _x000D_20/8/2024:Update: Order Amended _x000D_19/8/2024:Update: Order Amended _x000D_19/8/2024:14/08/2024 09:34 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point within customer premise to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_12/8/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point within customer premise to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_9/8/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point within customer premise to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_8/8/2024:End User Missed appointment. Action required _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - missed appointment, manager not on site, the office was locked and only the manager has the key _x000D_6/9/2024:#Update - missed appointment, manager not on site, the office was locked and only the manager has the key _x000D_5/9/2024:#Update - missed appointment, manager not on site, the office was locked and only the manager has the key _x000D_4/9/2024:#Update - missed appointment, manager not on site, the office was locked and only the manager has the key _x000D_3/9/2024:#Update - missed appointment, manager not on site, the office was locked and only the manager has the key _x000D_2/9/2024:#Update - missed appointment, manager not on site, the office was locked and only the manager has the key _x000D_29/8/2024:#Update - missed appointment, manager not on site, the office was locked and only the manager has the key _x000D_28/8/2024:#Update - missed appointment, manager not on site, the office was locked and only the manager has the key _x000D_27/8/2024:#Update - missed appointment, manager not on site, the office was locked and only the manager has the key _x000D_22/8/2024:#Update - missed appointment, manager not on site, the office was locked and only the manager has the key _x000D_21/8/2024:#Update - missed appointment, manager not on site, the office was locked and only the manager has the key _x000D_20/8/2024:Update: Order Amended _x000D_19/8/2024:Update: Order Amended _x000D_19/8/2024:14/08/2024 09:34 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point within customer premise to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_12/8/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point within customer premise to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_9/8/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point within customer premise to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_8/8/2024:End User Missed appointment. Action required _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | Order Completed | #Update - missed appointment, manager not on site, the office was locked and only the manager has the key |  |  |  |  | 2.Allwyn to arrange access | VFS1057010 | 30017318 | 2.Commissioning | AM |  | 2024-08-07 | 2024-09-03 |  | 0 | [11 empty] | 0
1341 | 473075 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Craigs | LONDONDERRY | BT47 5AB | 2024-09-02 | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043962 | 30017444 | 6.Failed router install |  |  | 2024-08-07 | 2024-08-07 | 2024-08-07 11:19 | TRUE |  |  |  | 2024-09-02 |  |  |  | 2024-09-02 | 23A004952911 | 23A004952911 | 2024-09-02 | 1
1342 | 450743 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Jempsons Supermarket | RYE | TN31 7AX | 2024-07-11 | 6/9/2024:#Update - OOH appointment required, raised with VF, awaiting feedback. _x000D_5/9/2024:#Update - OOH appointment required, raised with VF, awaiting feedback. _x000D_4/9/2024:#Update - OOH appointment required, raised with VF, awaiting feedback. _x000D_3/9/2024:#Update - OOH appointment required, raised with VF, awaiting feedback. _x000D_2/9/2024:#Update - OOH appointment required, raised with VF, awaiting feedback. _x000D_29/8/2024:#Update - OOH appointment required, raised with VF, awaiting feedback. _x000D_28/8/2024:#Update - OOH appointment required, raised with VF, awaiting feedback. _x000D_27/8/2024:#Update - OOH appointment required, raised with VF, awaiting feedback. _x000D_22/8/2024:#Update - OOH appointment required, raised with VF, awaiting feedback. _x000D_21/8/2024:#Update - OOH appointment required, raised with VF, awaiting feedback. _x000D_20/8/2024:#Update - OOH appointment required, raised with VF, awaiting feedback. _x000D_19/8/2024:#Update - OOH appointment required, raised with VF, awaiting feedback. _x000D_19/8/2024:01566292 _x000D_16/8/2024:#Update - OOH appointment required, raised with VF, awaiting feedback. _x000D_15/8/2024:#Update - OOH appointment required, raised with VF, awaiting feedback. _x000D_14/8/2024:#Update - OOH appointment required, raised with VF, awaiting feedback. _x000D_13/8/2024:#Update - OOH appointment required, raised with VF, awaiting feedback. _x000D_12/8/2024:#Update - OOH appointment required, raised with VF, awaiting feedback. _x000D_9/8/2024:#Update - OOH appointment required, raised with VF, awaiting feedback. _x000D_8/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - OOH appointment required, raised with VF, awaiting feedback. _x000D_6/9/2024:#Update - OOH appointment required, raised with VF, awaiting feedback. _x000D_5/9/2024:#Update - OOH appointment required, raised with VF, awaiting feedback. _x000D_4/9/2024:#Update - OOH appointment required, raised with VF, awaiting feedback. _x000D_3/9/2024:#Update - OOH appointment required, raised with VF, awaiting feedback. _x000D_2/9/2024:#Update - OOH appointment required, raised with VF, awaiting feedback. _x000D_29/8/2024:#Update - OOH appointment required, raised with VF, awaiting feedback. _x000D_28/8/2024:#Update - OOH appointment required, raised with VF, awaiting feedback. _x000D_27/8/2024:#Update - OOH appointment required, raised with VF, awaiting feedback. _x000D_22/8/2024:#Update - OOH appointment required, raised with VF, awaiting feedback. _x000D_21/8/2024:#Update - OOH appointment required, raised with VF, awaiting feedback. _x000D_20/8/2024:#Update - OOH appointment required, raised with VF, awaiting feedback. _x000D_19/8/2024:#Update - OOH appointment required, raised with VF, awaiting feedback. _x000D_19/8/2024:01566292 _x000D_16/8/2024:#Update - OOH appointment required, raised with VF, awaiting feedback. _x000D_15/8/2024:#Update - OOH appointment required, raised with VF, awaiting feedback. _x000D_14/8/2024:#Update - OOH appointment required, raised with VF, awaiting feedback. _x000D_13/8/2024:#Update - OOH appointment required, raised with VF, awaiting feedback. _x000D_12/8/2024:#Update - OOH appointment required, raised with VF, awaiting feedback. _x000D_9/8/2024:#Update - OOH appointment required, raised with VF, awaiting feedback. _x000D_8/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - OOH appointment required, raised with VF, awaiting feedback. |  |  |  |  | 2.Allwyn to arrange access | VFS1043961 | 30017473 | 1.Provisioning | AM |  | 2024-08-07 | 2024-09-13 |  | 0 | [11 empty] | 0
1343 | 668921 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Post Office | CANNOCK | WS11 5DD | 2024-08-08 | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043960 | 30017507 | 6.Failed router install |  |  | 2024-08-07 | 2024-08-07 | 2024-08-07 08:49 | TRUE |  |  |  | 2024-08-28 |  |  |  | 2024-08-28 | 23A004948720 | 23A004948720 | 2024-08-29 | 1
1344 | 486408 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | SPAR ST FAGANS ROAD | CARDIFF | CF5 3BA | 2024-08-08 | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043959 | 30017546 | 2.Commissioning |  |  | 2024-08-07 | 2024-08-07 | 2024-08-07 11:10 | TRUE |  |  |  | 2024-08-28 | [7 empty] | 0
1345 | 626291 |  | Batch 6 Aug 24 | Type 1 | KCOM/Mobile | Nisa | HULL | HU3 2HA | 2024-08-28 | 6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 AM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 AM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 AM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 AM _x000D_19/8/2024:01579358 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 AM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 AM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 AM _x000D_13/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 AM _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 AM _x000D_6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 AM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 AM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 AM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 AM _x000D_19/8/2024:01579358 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 AM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 AM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 AM _x000D_13/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 AM _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - Allwyn confirmed Retailer has agreed to installation on 27/08 AM |  |  |  |  | 2.Allwyn to arrange access | BUS0004444 | 30017251 | 2.Commissioning | AM | 2024-08-06 | 2024-08-27 | 2024-08-27 |  | 0 | [11 empty] | 0
1346 | 664846 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Nisa Local Overton Road | KIRKCALDY | KY1 2DY | 2024-08-08 | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043958 | 30017526 | 2.Commissioning |  |  | 2024-08-07 | 2024-08-07 | 2024-08-07 09:34 | TRUE |  |  |  | 2024-09-11 | [7 empty] | 0
1347 | 633162 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Post Office | LIVERPOOL | L25 2RQ | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 26/07/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment slot received _x000D_18/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 19-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_17/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 19-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 26/07/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment slot received _x000D_18/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 19-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_17/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 19-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Silver Address Issue | 30017692 | 1.Provisioning | AM |  | 2024-08-08 |  |  | 0 | [11 empty] | 0
1348 | 670370 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Post Office | PLYMOUTH | PL1 3HP | 2024-07-11 | 6/9/2024:#Update - access denied - store manager unaware of order and would not let engineer start work _x000D_5/9/2024:#Update - access denied - store manager unaware of order and would not let engineer start work _x000D_4/9/2024:#Update - access denied - store manager unaware of order and would not let engineer start work _x000D_3/9/2024:#Update - access denied - store manager unaware of order and would not let engineer start work _x000D_2/9/2024:#Update - access denied - store manager unaware of order and would not let engineer start work _x000D_29/8/2024:#Update - access denied - store manager unaware of order and would not let engineer start work _x000D_28/8/2024:#Update - access denied - store manager unaware of order and would not let engineer start work _x000D_27/8/2024:#Update - missed appointment - engineer arrived on site and not permitted to work because no one on site was aware of the visit _x000D_22/8/2024:#Update - missed appointment - engineer arrived on site and not permitted to work because no one on site was aware of the visit _x000D_21/8/2024:#Update - missed appointment - engineer arrived on site and not permitted to work because no one on site was aware of the visit _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 26/07/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment slot received _x000D_23/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 26/07/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment slot received _x000D_22/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 26/07/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment slot received _x000D_22/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 26/07/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment slot received _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - access denied - store manager unaware of order and would not let engineer start work _x000D_6/9/2024:#Update - access denied - store manager unaware of order and would not let engineer start work _x000D_5/9/2024:#Update - access denied - store manager unaware of order and would not let engineer start work _x000D_4/9/2024:#Update - access denied - store manager unaware of order and would not let engineer start work _x000D_3/9/2024:#Update - access denied - store manager unaware of order and would not let engineer start work _x000D_2/9/2024:#Update - access denied - store manager unaware of order and would not let engineer start work _x000D_29/8/2024:#Update - access denied - store manager unaware of order and would not let engineer start work _x000D_28/8/2024:#Update - access denied - store manager unaware of order and would not let engineer start work _x000D_27/8/2024:#Update - missed appointment - engineer arrived on site and not permitted to work because no one on site was aware of the visit _x000D_22/8/2024:#Update - missed appointment - engineer arrived on site and not permitted to work because no one on site was aware of the visit _x000D_21/8/2024:#Update - missed appointment - engineer arrived on site and not permitted to work because no one on site was aware of the visit _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 26/07/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment slot received _x000D_23/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 26/07/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment slot received _x000D_22/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 26/07/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment slot received _x000D_22/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 26/07/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment slot received _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - access denied - store manager unaware of order and would not let engineer start work |  |  |  |  | 2.Allwyn to arrange access | VFS1057140 | 30017358 | 1.Provisioning | AM |  | 2024-08-08 | 2024-08-23 |  | 0 | [11 empty] | 0
1349 | 231287 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | SPAR | LIMAVADY | BT49 9AA | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Address query | 30017693 | 1.Provisioning | AM |  | 2024-08-08 |  |  | 0 | [11 empty] | 0
1350 | 657788 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Early Noon & Night | SPENNYMOOR | DL16 6DJ | 2024-08-08 | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:Your order is currently being processed. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:Your order is currently being processed. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_17/7/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_16/7/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/7/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:Your order is currently being processed. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:Your order is currently being processed. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_17/7/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_16/7/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/7/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043956 | 30017541 | 6.Failed router install |  |  | 2024-08-07 | 2024-08-07 | 2024-08-07 13:38 | TRUE |  |  |  | 2024-08-28 |  |  |  | 2024-08-28 | 242005008928 | 242005008928 | 2024-08-29 | 1
1351 | 467203 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Kearneys Supermarket | ANTRIM | BT41 3AB | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:Update: Order Amended _x000D_19/8/2024:12/08/2024 15:15 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:Update: Order Amended _x000D_19/8/2024:12/08/2024 15:15 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2422499 | 30017328 | 1.Provisioning | AM |  | 2024-08-08 | 2024-10-11 |  | 0 | [11 empty] | 0
1352 | 434911 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Londis Supermarket | NORTHAMPTON | NN5 7LQ | 2024-07-11 | 12/8/2024:#Update - Order has been delayed due to a supplier system delay. CSL will update as more information becomes available. _x000D_9/8/2024:#Update - Order has been delayed due to a supplier system delay. CSL will update as more information becomes available. _x000D_8/8/2024:18/07/2024 _x000D_6/8/2024:18/07/2024 _x000D_5/8/2024:18/07/2024 _x000D_2/8/2024:18/07/2024 _x000D_1/8/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_30/7/2024:#Update - Order has been delayed due to a supplier system delay. CSL will update as more information becomes available. _x000D_29/7/2024:#Update - Order has been delayed due to a supplier system delay. CSL will update as more information becomes available. _x000D_29/7/2024:01499150 _x000D_26/7/2024:01499150 _x000D_24/7/2024:#Update - Order has been delayed due to a supplier system delay. CSL will update as more information becomes available. _x000D_23/7/2024:#Update - Order has been delayed due to a supplier system delay. CSL will update as more information becomes available. _x000D_22/7/2024:#Update - Order has been delayed due to a supplier system delay. CSL will update as more information becomes available. _x000D_22/7/2024:#Update - Order has been delayed due to a supplier system delay. CSL will update as more information becomes available. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 12/8/2024:#Update - Order has been delayed due to a supplier system delay. CSL will update as more information becomes available. _x000D_9/8/2024:#Update - Order has been delayed due to a supplier system delay. CSL will update as more information becomes available. _x000D_8/8/2024:18/07/2024 _x000D_6/8/2024:18/07/2024 _x000D_5/8/2024:18/07/2024 _x000D_2/8/2024:18/07/2024 _x000D_1/8/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_30/7/2024:#Update - Order has been delayed due to a supplier system delay. CSL will update as more information becomes available. _x000D_29/7/2024:#Update - Order has been delayed due to a supplier system delay. CSL will update as more information becomes available. _x000D_29/7/2024:01499150 _x000D_26/7/2024:01499150 _x000D_24/7/2024:#Update - Order has been delayed due to a supplier system delay. CSL will update as more information becomes available. _x000D_23/7/2024:#Update - Order has been delayed due to a supplier system delay. CSL will update as more information becomes available. _x000D_22/7/2024:#Update - Order has been delayed due to a supplier system delay. CSL will update as more information becomes available. _x000D_22/7/2024:#Update - Order has been delayed due to a supplier system delay. CSL will update as more information becomes available. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFS1055068 | 30017684 | 2.Commissioning |  |  | 2024-08-08 | 2024-08-08 | 2024-08-08 11:27 | TRUE |  |  |  | 2024-08-30 | [7 empty] | 0
1353 | 656174 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Spar | BELFAST | BT14 6AD | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Silver Address Issue | 30017713 | 1.Provisioning | AM |  | 2024-08-08 |  |  | 0 | [11 empty] | 0
1354 | 646237 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Moss Lane News | LIVERPOOL | L9 8AQ | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:Order Completed _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:Order Completed _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_0 | 0 | 0 |  |  |  |  | 3.Allwyn to arrange rtr install | VFS1043953 | 30017451 | 2.Commissioning | AM |  | 2024-08-07 | 2024-08-21 |  | 0 |  |  |  | 2024-09-26 | [7 empty] | 0
1355 | 201441 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | S S Sidhu | WOLVERHAMPTON | WV2 2AB | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Supplier Delay: Delay encountered during automated test of new service _x000D_18/7/2024:Supplier Delay: Delay encountered during automated test of new service _x000D_17/7/2024:Supplier Delay: Delay encountered during automated test of new service _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Supplier Delay: Delay encountered during automated test of new service _x000D_18/7/2024:Supplier Delay: Delay encountered during automated test of new service _x000D_17/7/2024:Supplier Delay: Delay encountered during automated test of new service _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Silver Address Issue | 30021837 | 1.Provisioning | AM |  | 2024-08-08 |  |  | 0 | [11 empty] | 0
1356 | 467416 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Spar Stores | OMAGH | BT79 7ET | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:10 _x000D_26/7/2024:22/07/2024 10:10 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Supplier Delay: Delay encountered during automated test of new service _x000D_19/7/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_17/7/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_16/7/2024:Delay : Sales Query CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/7/2024:Delay : Sales Query CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/7/2024:Your order has been delayed. LinePlant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 17/07/2024.We will continue to provide update as they become available. CSL Note: Invalid appointmen _x000D_11/7/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 15/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:10 _x000D_26/7/2024:22/07/2024 10:10 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Supplier Delay: Delay encountered during automated test of new service _x000D_19/7/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_17/7/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_16/7/2024:Delay : Sales Query CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/7/2024:Delay : Sales Query CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/7/2024:Your order has been delayed. LinePlant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 17/07/2024.We will continue to provide update as they become available. CSL Note: Invalid appointmen _x000D_11/7/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 15/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2421578 | 30017741 | 1.Provisioning | AM |  | 2024-08-08 | 2024-09-06 |  | 0 | [11 empty] | 0
1357 | 466673 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | K N G | STROUD | GL5 1AF | 2024-07-11 | 6/9/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 30/07/2024. _x000D_5/9/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 30/07/2024. _x000D_4/9/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 30/07/2024. _x000D_3/9/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 30/07/2024. _x000D_2/9/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 30/07/2024. _x000D_29/8/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 30/07/2024. _x000D_28/8/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 30/07/2024. _x000D_27/8/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 30/07/2024. _x000D_22/8/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 30/07/2024. _x000D_21/8/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 30/07/2024. _x000D_20/8/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 30/07/2024. _x000D_19/8/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 30/07/2024. _x000D_19/8/2024:01461988 _x000D_16/8/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 30/07/2024. _x000D_15/8/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 30/07/2024. _x000D_14/8/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 30/07/2024. _x000D_13/8/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 30/07/2024. _x000D_12/8/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 30/07/2024. _x000D_9/8/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 30/07/2024. _x000D_8/8/2024:25/07/2024 _x000D_6/8/2024:25/07/2024 _x000D_5/8/2024:25/07/2024 _x000D_2/8/2024:25/07/2024 _x000D_1/8/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_30/7/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 30/07/2024. _x000D_29/7/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 30/07/2024. _x000D_29/7/2024:01461988 _x000D_26/7/2024:01461988 _x000D_24/7/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 25/07/2024 _x000D_23/7/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 25/07/2024 _x000D_22/7/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 25/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 30/07/2024. _x000D_6/9/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 30/07/2024. _x000D_5/9/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 30/07/2024. _x000D_4/9/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 30/07/2024. _x000D_3/9/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 30/07/2024. _x000D_2/9/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 30/07/2024. _x000D_29/8/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 30/07/2024. _x000D_28/8/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 30/07/2024. _x000D_27/8/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 30/07/2024. _x000D_22/8/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 30/07/2024. _x000D_21/8/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 30/07/2024. _x000D_20/8/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 30/07/2024. _x000D_19/8/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 30/07/2024. _x000D_19/8/2024:01461988 _x000D_16/8/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 30/07/2024. _x000D_15/8/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 30/07/2024. _x000D_14/8/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 30/07/2024. _x000D_13/8/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 30/07/2024. _x000D_12/8/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 30/07/2024. _x000D_9/8/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 30/07/2024. _x000D_8/8/2024:25/07/2024 _x000D_6/8/2024:25/07/2024 _x000D_5/8/2024:25/07/2024 _x000D_2/8/2024:25/07/2024 _x000D_1/8/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_31/7/2024:25/07/2024 _x000D_30/7/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 30/07/2024. _x000D_29/7/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 30/07/2024. _x000D_29/7/2024:01461988 _x000D_26/7/2024:01461988 _x000D_24/7/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 25/07/2024 _x000D_23/7/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 25/07/2024 _x000D_22/7/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 25/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - Pair divert work required. Our Suppliers have given us a review date of 30/07/2024. |  |  |  |  | 2.Allwyn to arrange access | VFS1053737 | 30017427 | 1.Provisioning | AM |  | 2024-08-27 | 2024-08-27 |  | 0 | [11 empty] | 0
1358 | 670361 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Post Office | BELFAST | BT8 7SW | 2024-07-11 | 12/8/2024:Order Completed _x000D_9/8/2024:Order Completed _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 12/8/2024:Order Completed _x000D_9/8/2024:Order Completed _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2422498 | 30017365 | 3.In life |  |  | 2024-08-08 | 2024-08-08 | 2024-08-08 13:15 | TRUE |  |  |  | 2024-09-03 |  |  |  | 2024-09-03 | 23A004952896 | 23A004952896 | 2024-09-04 | 1
1359 | 446092 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Budgens Stores Ltd | ABINGDON | OX14 2QA | 2024-08-08 | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:Your order has been delayed due to a sales query raised by our supplier. We have now confirmed to supplier that a second line is required and progressed sales query. Review on 18/07/2024. _x000D_18/7/2024:Your order has been delayed due to a sales query raised by our supplier. We have now confirmed to supplier that a second line is required and progressed sales query. Review on 18/07/2024. _x000D_17/7/2024:Your order has been delayed due to a sales query raised by our supplier. We have now confirmed to supplier that a second line is required and progressed sales query. Review on 18/07/2024. _x000D_16/7/2024:Delay : Sales Query CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/7/2024:Delay : Sales Query CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/7/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_11/7/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:Your order has been delayed due to a sales query raised by our supplier. We have now confirmed to supplier that a second line is required and progressed sales query. Review on 18/07/2024. _x000D_18/7/2024:Your order has been delayed due to a sales query raised by our supplier. We have now confirmed to supplier that a second line is required and progressed sales query. Review on 18/07/2024. _x000D_17/7/2024:Your order has been delayed due to a sales query raised by our supplier. We have now confirmed to supplier that a second line is required and progressed sales query. Review on 18/07/2024. _x000D_16/7/2024:Delay : Sales Query CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/7/2024:Delay : Sales Query CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/7/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_11/7/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043949 | 30017443 | 3.In life |  |  | 2024-08-07 | 2024-08-07 | 2024-08-07 11:19 | TRUE |  |  |  | 2024-09-05 |  |  |  | 2024-09-05 | 242005011018 | 242005011018 | 2024-09-06 | 1
1360 | 621479 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Eurospar | BALLYCASTLE | BT54 6EG | 2024-07-11 | 12/8/2024:Order Completed _x000D_9/8/2024:Order Completed _x000D_8/8/2024:Update: Order Completed by Supplier _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:Your order has been delayed due to a sales query raised by our supplier. We have now confirmed to supplier that a second line is required and progressed sales query. Review on 18/07/2024. _x000D_22/7/2024:Your order has been delayed due to a sales query raised by our supplier. We have now confirmed to supplier that a second line is required and progressed sales query. Review on 18/07/2024. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 12/8/2024:Order Completed _x000D_9/8/2024:Order Completed _x000D_8/8/2024:Update: Order Completed by Supplier _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:Your order has been delayed due to a sales query raised by our supplier. We have now confirmed to supplier that a second line is required and progressed sales query. Review on 18/07/2024. _x000D_22/7/2024:Your order has been delayed due to a sales query raised by our supplier. We have now confirmed to supplier that a second line is required and progressed sales query. Review on 18/07/2024. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFS1053739 | 30017582 | 3.In life |  |  | 2024-08-08 | 2024-08-08 | 2024-08-08 10:19 | TRUE |  |  |  | 2024-09-02 |  |  |  | 2024-09-02 | 242005010393 | 242005010393 | 2024-09-03 | 1
1361 | 409975 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Costcutter | LIMAVADY | BT49 9DB | 2024-08-12 | 13/8/2024:Order Completed _x000D_12/8/2024:Order Completed _x000D_9/8/2024:Order Completed _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_0 | 13/8/2024:Order Completed _x000D_12/8/2024:Order Completed _x000D_9/8/2024:Order Completed _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_0 | [6 empty] | 3.Allwyn to arrange rtr install | VFS1055049 | 30017715 | 3.In life |  |  | 2024-08-09 | 2024-08-09 | 2024-08-09 09:20 | TRUE |  |  |  | 2024-09-02 |  |  |  | 2024-09-02 | 23A004952913 | 23A004952913 | 2024-09-03 | 1
1362 | 617410 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | G T News | STOCKPORT | SK6 1RJ | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Silver Address Issue | 30021835 | 1.Provisioning | AM |  | 2024-08-09 |  |  | 0 | [11 empty] | 0
1363 | 659304 |  | Batch 6 Aug 24 | Type 1 | KCOM/Mobile | Londis | HULL | HU4 6PJ | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | BUS0004456 | 30017282 | 1.Provisioning | AM | 2024-08-08 | 2024-08-08 |  |  | 0 | [11 empty] | 0
1364 | 105037 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Spar Stores | WREXHAM | LL14 1AH | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:Update: Order Amended _x000D_19/8/2024:Update: Order Amended _x000D_19/8/2024:19/08/2024 10:01 _x000D_16/8/2024:Your order has been delayed. The appointment has been delayed due to a Hazard owned by end user. Please check with end user and reappoint the order if still required. _x000D_15/8/2024:Your order has been delayed. The appointment has been delayed due to a Hazard owned by end user. Please check with end user and reappoint the order if still required. _x000D_14/8/2024:Your order has been delayed. The appointment has been delayed due to a Hazard owned by end user. Please check with end user and reappoint the order if still required. _x000D_13/8/2024:Your order has been delayed. The appointment has been delayed due to a Hazard owned by end user. Please check with end user and reappoint the order if still required. _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:Update: Order Amended _x000D_19/8/2024:Update: Order Amended _x000D_19/8/2024:19/08/2024 10:01 _x000D_16/8/2024:Your order has been delayed. The appointment has been delayed due to a Hazard owned by end user. Please check with end user and reappoint the order if still required. _x000D_15/8/2024:Your order has been delayed. The appointment has been delayed due to a Hazard owned by end user. Please check with end user and reappoint the order if still required. _x000D_14/8/2024:Your order has been delayed. The appointment has been delayed due to a Hazard owned by end user. Please check with end user and reappoint the order if still required. _x000D_13/8/2024:Your order has been delayed. The appointment has been delayed due to a Hazard owned by end user. Please check with end user and reappoint the order if still required. _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2422495 | 30017368 | 1.Provisioning | AM |  | 2024-08-09 | 2024-08-09 |  | 0 | [11 empty] | 0
1365 | 653831 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Kahlon cash and carry | LEICESTER | LE4 5AS | 2024-07-11 | 6/9/2024:#Update - The engineer arrived around 8:30AM and all shutters were down, no one was around and when calling the number they got no answer. _x000D_5/9/2024:#Update - The engineer arrived around 8:30AM and all shutters were down, no one was around and when calling the number they got no answer. _x000D_4/9/2024:#Update - The engineer arrived around 8:30AM and all shutters were down, no one was around and when calling the number they got no answer. _x000D_3/9/2024:#Update - The engineer arrived around 8:30AM and all shutters were down, no one was around and when calling the number they got no answer. _x000D_2/9/2024:#Update - The engineer arrived around 8:30AM and all shutters were down, no one was around and when calling the number they got no answer. _x000D_29/8/2024:#Update - The engineer arrived around 8:30AM and all shutters were down, no one was around and when calling the number they got no answer. _x000D_28/8/2024:#Update - The engineer arrived around 8:30AM and all shutters were down, no one was around and when calling the number they got no answer. _x000D_27/8/2024:#Update - The engineer arrived around 8:30AM and all shutters were down, no one was around and when calling the number they got no answer. _x000D_22/8/2024:#Update - The engineer arrived around 8:30AM and all shutters were down, no one was around and when calling the number they got no answer. _x000D_21/8/2024:#Update - The engineer arrived around 8:30AM and all shutters were down, no one was around and when calling the number they got no answer. _x000D_20/8/2024:#Update - The engineer arrived around 8:30AM and all shutters were down, no one was around and when calling the number they got no answer. _x000D_19/8/2024:#Update - The engineer arrived around 8:30AM and all shutters were down, no one was around and when calling the number they got no answer. _x000D_19/8/2024:01574495 _x000D_16/8/2024:#Update - The engineer arrived around 8:30AM and all shutters were down, no one was around and when calling the number they got no answer. _x000D_15/8/2024:#Update - The engineer arrived around 8:30AM and all shutters were down, no one was around and when calling the number they got no answer. _x000D_14/8/2024:#Update - The engineer arrived around 8:30AM and all shutters were down, no one was around and when calling the number they got no answer. _x000D_13/8/2024:#Update - The engineer arrived around 8:30AM and all shutters were down, no one was around and when calling the number they got no answer. _x000D_12/8/2024:End User Missed appointment. Action required _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - The engineer arrived around 8:30AM and all shutters were down, no one was around and when calling the number they got no answer. _x000D_6/9/2024:#Update - The engineer arrived around 8:30AM and all shutters were down, no one was around and when calling the number they got no answer. _x000D_5/9/2024:#Update - The engineer arrived around 8:30AM and all shutters were down, no one was around and when calling the number they got no answer. _x000D_4/9/2024:#Update - The engineer arrived around 8:30AM and all shutters were down, no one was around and when calling the number they got no answer. _x000D_3/9/2024:#Update - The engineer arrived around 8:30AM and all shutters were down, no one was around and when calling the number they got no answer. _x000D_2/9/2024:#Update - The engineer arrived around 8:30AM and all shutters were down, no one was around and when calling the number they got no answer. _x000D_29/8/2024:#Update - The engineer arrived around 8:30AM and all shutters were down, no one was around and when calling the number they got no answer. _x000D_28/8/2024:#Update - The engineer arrived around 8:30AM and all shutters were down, no one was around and when calling the number they got no answer. _x000D_27/8/2024:#Update - The engineer arrived around 8:30AM and all shutters were down, no one was around and when calling the number they got no answer. _x000D_22/8/2024:#Update - The engineer arrived around 8:30AM and all shutters were down, no one was around and when calling the number they got no answer. _x000D_21/8/2024:#Update - The engineer arrived around 8:30AM and all shutters were down, no one was around and when calling the number they got no answer. _x000D_20/8/2024:#Update - The engineer arrived around 8:30AM and all shutters were down, no one was around and when calling the number they got no answer. _x000D_19/8/2024:#Update - The engineer arrived around 8:30AM and all shutters were down, no one was around and when calling the number they got no answer. _x000D_19/8/2024:01574495 _x000D_16/8/2024:#Update - The engineer arrived around 8:30AM and all shutters were down, no one was around and when calling the number they got no answer. _x000D_15/8/2024:#Update - The engineer arrived around 8:30AM and all shutters were down, no one was around and when calling the number they got no answer. _x000D_14/8/2024:#Update - The engineer arrived around 8:30AM and all shutters were down, no one was around and when calling the number they got no answer. _x000D_13/8/2024:#Update - The engineer arrived around 8:30AM and all shutters were down, no one was around and when calling the number they got no answer. _x000D_12/8/2024:End User Missed appointment. Action required _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - The engineer arrived around 8:30AM and all shutters were down, no one was around and when calling the number they got no answer. |  |  |  |  | 2.Allwyn to arrange access | VFS1055045 | 30017739 | 1.Provisioning | AM |  | 2024-08-09 | 2024-09-03 |  | 0 | [11 empty] | 0
1366 | 662623 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Premier Fresh & Local | WATERLOOVILLE | PO8 8LH | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:Update: Order Amended _x000D_19/8/2024:Update: Order Amended _x000D_19/8/2024:15/08/2024 10:03 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point within customer premise to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_13/8/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point within customer premise to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_12/8/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point within customer premise to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_9/8/2024:End User Missed appointment. Action required _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:Update: Order Amended _x000D_19/8/2024:Update: Order Amended _x000D_19/8/2024:15/08/2024 10:03 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point within customer premise to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_13/8/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point within customer premise to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_12/8/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point within customer premise to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_9/8/2024:End User Missed appointment. Action required _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFS1043943 | 30017454 | 1.Provisioning | AM |  | 2024-08-08 | 2024-10-25 |  | 0 | [11 empty] | 0
1367 | 632909 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Nisa Local | BARNSLEY | S71 3NB | 2024-07-11 | 12/8/2024:Order Completed _x000D_9/8/2024:Order Completed _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 12/8/2024:Order Completed _x000D_9/8/2024:Order Completed _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFS1043942 | 30017536 | 6.Failed router install |  |  | 2024-08-08 | 2024-08-08 | 2024-08-08 13:27 | TRUE |  |  |  | 2024-08-29 |  |  |  | 2024-08-29 | 23A004948597 | 23A004948597 | 2024-08-30 | 1
1368 | 630402 |  | Batch 6 Aug 24 | Type 1 | KCOM/Mobile | Jag's Orchard Stores | HULL | HU6 9BX | 2024-07-11 | 6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_19/8/2024:01583491 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_19/8/2024:01583491 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM |  |  |  |  | 2.Allwyn to arrange access | BUS0004463 | 30017234 | 1.Provisioning | AM | 2024-08-09 | 2024-08-29 | 2024-08-29 |  | 0 | [11 empty] | 0
1369 | 448317 |  | Batch 6 Aug 24 | Type 1 | KCOM/Mobile | Nisa | HULL | HU7 4ND | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | BUS0004468 | 30017283 | 1.Provisioning | AM | 2024-08-12 | 2024-08-12 |  |  | 0 | [11 empty] | 0
1370 | 666927 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Spar Stores | WREXHAM | LL11 4NT | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Silver Address Issue | 30017393 | 1.Provisioning | AM |  | 2024-08-09 |  |  | 0 | [11 empty] | 0
1371 | 664925 |  | Batch 6 Aug 24 | Type 1 | KCOM/Mobile | Turnbull's Convenience Store | HULL | HU5 5JW | 2024-08-29 | 6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_19/8/2024:01579424 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_13/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_19/8/2024:01579424 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_13/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM |  |  |  |  | 2.Allwyn to arrange access | BUS0004457 | 30017261 | 2.Commissioning | AM | 2024-08-08 | 2024-08-28 | 2024-08-28 |  | 0 | [11 empty] | 0
1372 | 469355 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Rosehill Newsagents | OXFORD | OX4 4SE | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 02/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 02/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Silver Address Issue | 30017740 | 1.Provisioning | AM |  | 2024-08-09 |  |  | 0 | [11 empty] | 0
1373 | 665123 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Bp Service Station | LEEDS | LS27 9NU | 2024-08-12 | 13/8/2024:Order Completed _x000D_12/8/2024:Order Completed _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:22/07/2024 09:53 _x000D_26/7/2024:22/07/2024 09:53 _x000D_24/7/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_23/7/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 02/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 13/8/2024:Order Completed _x000D_12/8/2024:Order Completed _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:22/07/2024 09:53 _x000D_26/7/2024:22/07/2024 09:53 _x000D_24/7/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_23/7/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 02/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFP2422492 | 30017325 | 2.Commissioning |  |  | 2024-08-09 | 2024-08-09 | 2024-08-09 10:37 | TRUE |  |  |  | 2024-08-29 | [7 empty] | 0
1374 | 670840 |  | Batch 6 Aug 24 | Type 1 | SURE/Mobile | Tesco Express. | ISLE OF MAN | IM8 2LL | 2024-07-11 | 6/9/2024:#Update - Awaiting site contract from allwyn as the number provided was an out of service line. _x000D_5/9/2024:#Update - Awaiting site contract from allwyn as the number provided was an out of service line. _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Awaiting site contract from allwyn as the number provided was an out of service line. _x000D_6/9/2024:#Update - Awaiting site contract from allwyn as the number provided was an out of service line. _x000D_5/9/2024:#Update - Awaiting site contract from allwyn as the number provided was an out of service line. _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - Awaiting site contract from allwyn as the number provided was an out of service line. |  |  |  |  | 2.Allwyn to arrange access | FPSU001812 | 30017233 | 1.Provisioning | AM |  | 2024-07-26 |  |  | 0 | [11 empty] | 0 | 670840
1375 | 665131 |  | Batch 6 Aug 24 | Type 1 | KCOM/Mobile | Marfleet Bargain Centre | HULL | HU9 5AQ | 2024-09-06 | 6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_19/8/2024:01592345 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_0 | 9/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_19/8/2024:01592345 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_0 | 0 | #Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM |  |  |  |  | 2.Allwyn to arrange access | BUS0004487 | 30017272 | 2.Commissioning | AM | 2024-08-15 | 2024-08-15 |  |  | 0 | [11 empty] | 0
1376 | 663084 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Convenience Pointe | MANCHESTER | M11 2AS | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Silver Address Issue | 30021830 | 1.Provisioning | AM |  | 2024-08-09 |  |  | 0 | [11 empty] | 0
1377 | 485783 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Premier Stores | TILBURY | RM18 8AD | 2024-09-05 | 6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:End User Missed appointment. Action required _x000D_8/8/2024:End User Missed appointment. Action required _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:19/07/2024 13:49 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:End User Missed appointment. Action required _x000D_8/8/2024:End User Missed appointment. Action required _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:19/07/2024 13:49 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | Order Completed | 0 |  |  |  |  | 2.Allwyn to arrange access | VFS1043934 | 30017482 | 2.Commissioning | AM |  | 2024-08-08 | 2024-09-04 |  | 0 | [11 empty] | 0
1378 | 465238 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Londis Supermarket | FOLKESTONE | CT20 1NS | 2024-07-11 | 12/8/2024:Order Completed _x000D_9/8/2024:Order Completed _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:19/07/2024 13:49 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 12/8/2024:Order Completed _x000D_9/8/2024:Order Completed _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:19/07/2024 13:49 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFS1043936 | 30017587 | 3.In life |  |  | 2024-08-08 | 2024-08-08 | 2024-08-08 11:15 | TRUE |  |  |  | 2024-09-05 |  |  |  | 2024-09-05 | 242005008589 | 242005008589 | 2024-09-06 | 1
1379 | 668419 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Brownsover Community Hut | RUGBY | CV21 1LT | 2024-07-11 | 6/9/2024:#Update Retailer confirmed 09/09, AM. _x000D_5/9/2024:#Update Retailer confirmed 09/09, AM. _x000D_4/9/2024:#Update Retailer confirmed 09/09, AM. _x000D_3/9/2024:#Update Retailer confirmed 09/09, AM. _x000D_2/9/2024:#Update Retailer confirmed 09/09, AM. _x000D_29/8/2024:#Update Retailer confirmed 09/09, AM. _x000D_28/8/2024:#Update Retailer confirmed 09/09, AM. _x000D_27/8/2024:#Update Retailer confirmed 09/09, AM. _x000D_22/8/2024:#Update Retailer confirmed 09/09, AM. _x000D_21/8/2024:#Update Retailer confirmed 09/09, AM. _x000D_20/8/2024:Update: Order Amended _x000D_19/8/2024:Your order has been delayed due to a routing issue at our suppliers. The order has now been passed to a backend team to update. They have given us a review date of 16/08/2024. _x000D_19/8/2024:13/08/2024 16:03 _x000D_16/8/2024:Your order has been delayed due to a routing issue at our suppliers. The order has now been passed to a backend team to update. They have given us a review date of 16/08/2024. _x000D_15/8/2024:Your order has been delayed due to a routing issue at our suppliers. The order has now been passed to a backend team to update. They have given us a review date of 16/08/2024. _x000D_14/8/2024:Your order has been delayed due to a routing issue at our suppliers. The order has now been passed to a backend team to update. They have given us a review date of 16/08/2024. _x000D_13/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_12/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:19/07/2024 13:49 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update Retailer confirmed 09/09, AM. _x000D_6/9/2024:#Update Retailer confirmed 09/09, AM. _x000D_5/9/2024:#Update Retailer confirmed 09/09, AM. _x000D_4/9/2024:#Update Retailer confirmed 09/09, AM. _x000D_3/9/2024:#Update Retailer confirmed 09/09, AM. _x000D_2/9/2024:#Update Retailer confirmed 09/09, AM. _x000D_29/8/2024:#Update Retailer confirmed 09/09, AM. _x000D_28/8/2024:#Update Retailer confirmed 09/09, AM. _x000D_27/8/2024:#Update Retailer confirmed 09/09, AM. _x000D_22/8/2024:#Update Retailer confirmed 09/09, AM. _x000D_21/8/2024:#Update Retailer confirmed 09/09, AM. _x000D_20/8/2024:Update: Order Amended _x000D_19/8/2024:Your order has been delayed due to a routing issue at our suppliers. The order has now been passed to a backend team to update. They have given us a review date of 16/08/2024. _x000D_19/8/2024:13/08/2024 16:03 _x000D_16/8/2024:Your order has been delayed due to a routing issue at our suppliers. The order has now been passed to a backend team to update. They have given us a review date of 16/08/2024. _x000D_15/8/2024:Your order has been delayed due to a routing issue at our suppliers. The order has now been passed to a backend team to update. They have given us a review date of 16/08/2024. _x000D_14/8/2024:Your order has been delayed due to a routing issue at our suppliers. The order has now been passed to a backend team to update. They have given us a review date of 16/08/2024. _x000D_13/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_12/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:19/07/2024 13:49 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update Retailer confirmed 09/09, AM. |  |  |  |  | 2.Allwyn to arrange access | VFS1043930 | 30017457 | 1.Provisioning | AM |  | 2024-08-12 | 2024-08-12 |  | 0 | [11 empty] | 0
1380 | 429548 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Urban Fresh | Belfast | BT1 6GE | 2024-07-11 | 6/9/2024:#Update Retailer confirmed 19/09, AM. _x000D_5/9/2024:#Update Retailer confirmed 19/09, AM. _x000D_4/9/2024:#Update Retailer confirmed 19/09, AM. _x000D_3/9/2024:#Update Retailer confirmed 19/09, AM. _x000D_2/9/2024:#Update Retailer confirmed 19/09, AM. _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:Your order has been delayed. Engineer required access to the end user premises to complete the external works . Please check with the end user and book a new appointment. _x000D_22/8/2024:Your order has been delayed. Engineer required access to the end user premises to complete the external works . Please check with the end user and book a new appointment. _x000D_21/8/2024:Your order has been delayed. Engineer required access to the end user premises to complete the external works . Please check with the end user and book a new appointment. _x000D_20/8/2024:Supplier Delay: Network Planning issues. Please await for further updates _x000D_19/8/2024:Supplier Delay: Network Planning issues. Please await for further updates _x000D_19/8/2024:15/08/2024 14:18 _x000D_16/8/2024:Supplier Delay: Network Planning issues. Please await for further updates _x000D_15/8/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 21/08/2024.We will continue to provide update as they become available. _x000D_14/8/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 21/08/2024.We will continue to provide update as they become available. _x000D_13/8/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update Retailer confirmed 19/09, AM. _x000D_6/9/2024:#Update Retailer confirmed 19/09, AM. _x000D_5/9/2024:#Update Retailer confirmed 19/09, AM. _x000D_4/9/2024:#Update Retailer confirmed 19/09, AM. _x000D_3/9/2024:#Update Retailer confirmed 19/09, AM. _x000D_2/9/2024:#Update Retailer confirmed 19/09, AM. _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:Your order has been delayed. Engineer required access to the end user premises to complete the external works . Please check with the end user and book a new appointment. _x000D_22/8/2024:Your order has been delayed. Engineer required access to the end user premises to complete the external works . Please check with the end user and book a new appointment. _x000D_21/8/2024:Your order has been delayed. Engineer required access to the end user premises to complete the external works . Please check with the end user and book a new appointment. _x000D_20/8/2024:Supplier Delay: Network Planning issues. Please await for further updates _x000D_19/8/2024:Supplier Delay: Network Planning issues. Please await for further updates _x000D_19/8/2024:15/08/2024 14:18 _x000D_16/8/2024:Supplier Delay: Network Planning issues. Please await for further updates _x000D_15/8/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 21/08/2024.We will continue to provide update as they become available. _x000D_14/8/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 21/08/2024.We will continue to provide update as they become available. _x000D_13/8/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update Retailer confirmed 19/09, AM. |  |  |  |  | 2.Allwyn to arrange access | VFP2422491 | 30017334 | 1.Provisioning | AM |  | 2024-08-12 | 2024-08-12 |  | 0 | [11 empty] | 0
1381 | 635776 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Edmonton Green News | LONDON | N9 9DX | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:Your order has been delayed due to our suppliers being unable to complete the job in required time frame. Please check with the end user and book a new appointment. _x000D_19/8/2024:Your order has been delayed due to our suppliers being unable to complete the job in required time frame. Please check with the end user and book a new appointment. _x000D_19/8/2024:13/08/2024 14:35 _x000D_16/8/2024:Your order has been delayed due to our suppliers being unable to complete the job in required time frame. Please check with the end user and book a new appointment. _x000D_15/8/2024:Your order has been delayed due to our suppliers being unable to complete the job in required time frame. Please check with the end user and book a new appointment. _x000D_14/8/2024:Your order has been delayed due to our suppliers being unable to complete the job in required time frame. Please check with the end user and book a new appointment. _x000D_13/8/2024:Supplier Delay: Missed CCD and may require further work as the engineer has retained the job for next day _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:Your order has been delayed due to our suppliers being unable to complete the job in required time frame. Please check with the end user and book a new appointment. _x000D_19/8/2024:Your order has been delayed due to our suppliers being unable to complete the job in required time frame. Please check with the end user and book a new appointment. _x000D_19/8/2024:13/08/2024 14:35 _x000D_16/8/2024:Your order has been delayed due to our suppliers being unable to complete the job in required time frame. Please check with the end user and book a new appointment. _x000D_15/8/2024:Your order has been delayed due to our suppliers being unable to complete the job in required time frame. Please check with the end user and book a new appointment. _x000D_14/8/2024:Your order has been delayed due to our suppliers being unable to complete the job in required time frame. Please check with the end user and book a new appointment. _x000D_13/8/2024:Supplier Delay: Missed CCD and may require further work as the engineer has retained the job for next day _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFS1057051 | 30017379 | 1.Provisioning | AM |  | 2024-08-12 | 2024-08-12 |  | 0 | [11 empty] | 0
1382 | 487140 |  | Batch 6 Aug 24 | Type 1 | KCOM/Mobile | Premier Express | HULL | HU3 3BE | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | BUS0004446 | 30017246 | 1.Provisioning | AM | 2024-08-06 | 2024-08-06 |  |  | 0 | [11 empty] | 0
1383 | 469680 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Nisa | SALE | M33 5JS | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_16/7/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_15/7/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_12/7/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_11/7/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_16/7/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_15/7/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_12/7/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_11/7/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Silver Address Issue | 30017697 | 1.Provisioning | AM |  | 2024-08-12 |  |  | 0 | [11 empty] | 0
1384 | 482474 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | News on the Wharf | LONDON | E14 5NY | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Address query | 30017357 | 1.Provisioning | AM |  | 2024-08-12 |  |  | 0 | [11 empty] | 0
1385 | 653845 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Chertsey Local | CHERTSEY | KT16 9AG | 2024-07-11 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:Order Completed _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Supplier Delay: Delayed in planning. Order completion may be delayed. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 29/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment slot received _x000D_17/7/2024:Update: Order progressed to Openreach Network Plan null team for routing confirmation CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:Order Completed _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Supplier Delay: Delayed in planning. Order completion may be delayed. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 29/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment slot received _x000D_17/7/2024:Update: Order progressed to Openreach Network Plan null team for routing confirmation CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFP2422489 | 30017347 | 6.Failed router install | AM |  | 2024-08-12 | 2024-08-12 | 2024-08-12 12:52 | 1 |  |  |  | 2024-08-29 |  |  |  | 2024-08-29 | 242005011145 | 242005011145 | 2024-08-30 | 1
1386 | 483255 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Bay View Convenience Store | CARDIFF | CF10 5AD | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 04/09/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment slot received _x000D_4/9/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 04/09/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment slot received _x000D_3/9/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 04/09/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment slot received _x000D_2/9/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 04/09/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment slot received _x000D_29/8/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 04/09/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment slot received _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Supplier Delay: Delayed in planning. Order completion may be delayed. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_23/7/2024:Supplier Delay: Delayed in planning. Order completion may be delayed. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Supplier Delay: Delayed in planning. Order completion may be delayed. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Supplier Delay: Delayed in planning. Order completion may be delayed. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 04/09/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment slot received _x000D_4/9/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 04/09/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment slot received _x000D_3/9/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 04/09/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment slot received _x000D_2/9/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 04/09/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment slot received _x000D_29/8/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 04/09/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment slot received _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Supplier Delay: Delayed in planning. Order completion may be delayed. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_23/7/2024:Supplier Delay: Delayed in planning. Order completion may be delayed. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Supplier Delay: Delayed in planning. Order completion may be delayed. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Supplier Delay: Delayed in planning. Order completion may be delayed. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2422488 | 30017335 | 1.Provisioning | AM |  | 2024-08-12 |  |  | 0 | [11 empty] | 0
1387 | 466470 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Spar Stores | STRABANE | BT82 8LD | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2422487 | 30017364 | 1.Provisioning | AM |  | 2024-08-12 | 2024-09-06 |  | 0 | [11 empty] | 0
1388 | 646144 |  | Batch 6 Aug 24 | Type 1 | KCOM/Mobile | Budgens Stores Ltd | HULL | HU3 6AS | 2024-08-29 | 6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_19/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 28/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 28/08 is a suitable date. _x000D_19/8/2024:01596879 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM _x000D_19/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 28/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 28/08 is a suitable date. _x000D_19/8/2024:01596879 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - Allwyn confirmed Retailer has agreed to installation on 28/08 AM |  |  |  |  | 2.Allwyn to arrange access | BUS0004448 | 30017249 | 2.Commissioning | AM | 2024-08-07 | 2024-08-07 |  |  | 0 | [11 empty] | 0
1389 | 273502 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Spar Stores | LANCASTER | LA1 2RP | 2024-08-14 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:Supplier Delay: Missed CCD and may require further work as the engineer has retained the job for next day _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_0 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:Supplier Delay: Missed CCD and may require further work as the engineer has retained the job for next day _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_0 | [6 empty] | 2.Allwyn to arrange access | VFP2422486 | 30017313 | 2.Commissioning | AM |  | 2024-08-12 | 2024-08-12 | 2024-08-13 11:56 | 1 |  |  |  | 2024-09-09 | [7 empty] | 0
1390 | 657866 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Nisa Local | FELTHAM | TW13 4AU | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 18/07/2024. We will continue to provide update as they become available _x000D_18/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 18/07/2024. We will continue to provide update as they become available _x000D_17/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 18/07/2024. We will continue to provide update as they become available _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 18/07/2024. We will continue to provide update as they become available _x000D_18/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 18/07/2024. We will continue to provide update as they become available _x000D_17/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 18/07/2024. We will continue to provide update as they become available _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Silver Address Issue | 30021809 | 1.Provisioning | AM |  | 2024-08-12 |  |  | 0 | [11 empty] | 0
1391 | 435160 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Nearby Shop | NEWTOWNABBEY | BT36 4FS | 2024-07-11 | 6/9/2024:#Update - Order re-raised. _x000D_5/9/2024:#Update - Order re-raised. _x000D_4/9/2024:#Update - Order re-raised. _x000D_3/9/2024:#Update - Order re-raised. _x000D_2/9/2024:#Update - Order re-raised. _x000D_29/8/2024:#Update - Order re-raised. _x000D_28/8/2024:#Update - Order re-raised. _x000D_27/8/2024:#Update - Order re-raised. _x000D_22/8/2024:#Update - Order re-raised. _x000D_21/8/2024:#Update - Order re-raised. _x000D_20/8/2024:#Update - Order re-raised. _x000D_19/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 18/07/2024. We will continue to provide update as they become available _x000D_19/8/2024:01496085 _x000D_16/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 18/07/2024. We will continue to provide update as they become available _x000D_15/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 18/07/2024. We will continue to provide update as they become available _x000D_14/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 18/07/2024. We will continue to provide update as they become available _x000D_13/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 18/07/2024. We will continue to provide update as they become available _x000D_12/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 18/07/2024. We will continue to provide update as they become available _x000D_9/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 18/07/2024. We will continue to provide update as they become available _x000D_8/8/2024:16/07/2024 _x000D_6/8/2024:16/07/2024 _x000D_5/8/2024:16/07/2024 _x000D_2/8/2024:16/07/2024 _x000D_1/8/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_30/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 18/07/2024. We will continue to provide update as they become available _x000D_29/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 18/07/2024. We will continue to provide update as they become available _x000D_29/7/2024:01496085 _x000D_26/7/2024:01496085 _x000D_24/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 18/07/2024. We will continue to provide update as they become available _x000D_23/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 18/07/2024. We will continue to provide update as they become available _x000D_22/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 18/07/2024. We will continue to provide update as they become available _x000D_22/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 18/07/2024. We will continue to provide update as they become available _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Order re-raised. _x000D_6/9/2024:#Update - Order re-raised. _x000D_5/9/2024:#Update - Order re-raised. _x000D_4/9/2024:#Update - Order re-raised. _x000D_3/9/2024:#Update - Order re-raised. _x000D_2/9/2024:#Update - Order re-raised. _x000D_29/8/2024:#Update - Order re-raised. _x000D_28/8/2024:#Update - Order re-raised. _x000D_27/8/2024:#Update - Order re-raised. _x000D_22/8/2024:#Update - Order re-raised. _x000D_21/8/2024:#Update - Order re-raised. _x000D_20/8/2024:#Update - Order re-raised. _x000D_19/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 18/07/2024. We will continue to provide update as they become available _x000D_19/8/2024:01496085 _x000D_16/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 18/07/2024. We will continue to provide update as they become available _x000D_15/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 18/07/2024. We will continue to provide update as they become available _x000D_14/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 18/07/2024. We will continue to provide update as they become available _x000D_13/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 18/07/2024. We will continue to provide update as they become available _x000D_12/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 18/07/2024. We will continue to provide update as they become available _x000D_9/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 18/07/2024. We will continue to provide update as they become available _x000D_8/8/2024:16/07/2024 _x000D_6/8/2024:16/07/2024 _x000D_5/8/2024:16/07/2024 _x000D_2/8/2024:16/07/2024 _x000D_1/8/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_30/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 18/07/2024. We will continue to provide update as they become available _x000D_29/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 18/07/2024. We will continue to provide update as they become available _x000D_29/7/2024:01496085 _x000D_26/7/2024:01496085 _x000D_24/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 18/07/2024. We will continue to provide update as they become available _x000D_23/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 18/07/2024. We will continue to provide update as they become available _x000D_22/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 18/07/2024. We will continue to provide update as they become available _x000D_22/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 18/07/2024. We will continue to provide update as they become available _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - Order re-raised. |  |  |  |  | 2.Allwyn to arrange access | VFS1055366 | 30017749 | 1.Provisioning | AM |  | 2024-08-12 | 2024-08-12 |  | 0 | [11 empty] | 0
1392 | 636599 |  | Batch 6 Aug 24 | Type 1 | KCOM/Mobile | Go Local Extra | HULL | HU9 4UY | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 09/08/2024 _x000D_18/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 09/08/2024 _x000D_17/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 09/08/2024 _x000D_16/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 09/08/2024 _x000D_18/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 09/08/2024 _x000D_17/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 09/08/2024 _x000D_16/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_0 | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | BUS0004483 | 30017278 | 1.Provisioning | AM | 2024-08-15 | 2024-08-15 |  |  | 0 | [11 empty] | 0
1393 | 664306 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Spar Stores | LONDONDERRY | BT47 3QG | 2024-08-16 | 19/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_19/8/2024:01496449 _x000D_16/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_14/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_13/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_12/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_9/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_8/8/2024:16/07/2024 _x000D_6/8/2024:16/07/2024 _x000D_5/8/2024:16/07/2024 _x000D_2/8/2024:16/07/2024 _x000D_1/8/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_30/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_29/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_29/7/2024:01496449 _x000D_26/7/2024:01496449 _x000D_24/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_23/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_22/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_22/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_0 | 19/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_19/8/2024:01496449 _x000D_16/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_14/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_13/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_12/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_9/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_8/8/2024:16/07/2024 _x000D_6/8/2024:16/07/2024 _x000D_5/8/2024:16/07/2024 _x000D_2/8/2024:16/07/2024 _x000D_1/8/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_30/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_29/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_29/7/2024:01496449 _x000D_26/7/2024:01496449 _x000D_24/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_23/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_22/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_22/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_0 | [6 empty] | 2.Allwyn to arrange access | VFP2422484 | 30017305 | 2.Commissioning | AM |  | 2024-08-15 | 2024-08-15 |  | 0 |  |  |  | 2024-09-09 | [7 empty] | 0
1394 | 448612 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Ryans | LEEDS | LS1 6PU | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Silver Address Issue | 30021806 | 1.Provisioning | AM |  | 2024-08-12 |  |  | 0 | [11 empty] | 0
1395 | 461499 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Spar Stores | HEMEL HEMPSTEAD | HP3 8QG | 2024-07-11 | 6/9/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_5/9/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_4/9/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_3/9/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_2/9/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_29/8/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_28/8/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_27/8/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_22/8/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_21/8/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_20/8/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_19/8/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_19/8/2024:01579340 _x000D_16/8/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_15/8/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_14/8/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_13/8/2024:End User Missed appointment. Action required _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_6/9/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_5/9/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_4/9/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_3/9/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_2/9/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_29/8/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_28/8/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_27/8/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_22/8/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_21/8/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_20/8/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_19/8/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_19/8/2024:01579340 _x000D_16/8/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_15/8/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_14/8/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_13/8/2024:End User Missed appointment. Action required _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update Allwyn to advise how they'd like to proceed. |  |  |  |  | 2.Allwyn to arrange access | VFS1057007 | 30017394 | 1.Provisioning | AM |  | 2024-08-12 | 2024-08-12 |  | 0 | [11 empty] | 0
1396 | 664947 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Post Office | BLACKBURN | BB2 3EP | 2024-08-14 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:Order Completed _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:Order Completed _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1057090 | 30017323 | 2.Commissioning | AM |  | 2024-08-13 | 2024-08-13 | 2024-08-13 09:24 | 1 |  |  |  | 2024-09-06 | [7 empty] | 0
1397 | 467063 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Premier Store | BODORGAN | LL62 5NE | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFS1098729 | 30017754 | 1.Provisioning | AM |  | 2024-08-13 |  |  | 0 | [11 empty] | 0
1398 | 466413 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Tainsh Grocers Ltd | PERTH | PH1 2DF | 2024-08-14 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1055353 | 30017744 | 3.In life | AM |  | 2024-08-13 | 2024-08-13 | 2024-08-13 11:11 | 1 |  |  |  | 2024-09-05 |  |  |  | 2024-09-05 | 23A004952706 | 23A004952706 | 2024-09-06 | 1
1399 | 465875 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Bargain Booze | DARLINGTON | DL3 9RU | 2024-08-14 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:Order Completed _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:Order Completed _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1055346 | 30017750 | 2.Commissioning | AM |  | 2024-08-13 | 2024-08-13 | 2024-08-13 09:43 | 1 |  |  |  | 2024-09-13 | [7 empty] | 0
1400 | 464960 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Londis Supermarket | WEYMOUTH | DT4 8NU | 2024-07-11 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:Order Completed _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:19/07/2024 13:55 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:Order Completed _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:19/07/2024 13:55 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043926 | 30017488 | 3.In life | AM |  | 2024-08-12 | 2024-08-12 | 2024-08-12 12:34 | 1 |  |  |  | 2024-09-04 |  |  |  | 2024-09-04 | 242005011040 | 242005011040 | 2024-09-05 | 1
1401 | 656629 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Morrisons Daily | REDCAR | TS10 4NY | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2422480 | 30017359 | 1.Provisioning | AM |  | 2024-08-13 | 2024-09-06 |  | 0 | [11 empty] | 0
1402 | 471067 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Post Office | GLASGOW | G20 7QB | 2024-08-14 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:Order Completed _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:Order Completed _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1055345 | 30017737 | 3.In life | AM |  | 2024-08-13 | 2024-08-13 | 2024-08-13 09:31 | 1 |  |  |  | 2024-09-04 |  |  |  | 2024-09-04 | 23A004952705 | 23A004952705 | 2024-09-05 | 1
1403 | 424253 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | G101 Off Sales Ltd | GLASGOW | G75 0BH | 2024-07-11 | 6/9/2024:#Update Retailer confirmed 29/08. _x000D_5/9/2024:#Update Retailer confirmed 29/08. _x000D_4/9/2024:#Update Retailer confirmed 29/08. _x000D_3/9/2024:#Update Retailer confirmed 29/08. _x000D_2/9/2024:#Update Retailer confirmed 29/08. _x000D_29/8/2024:#Update Retailer confirmed 29/08. _x000D_28/8/2024:#Update Retailer confirmed 29/08. _x000D_27/8/2024:#Update Retailer confirmed 29/08. _x000D_22/8/2024:#Update Retailer confirmed 29/08. _x000D_21/8/2024:#Update Retailer confirmed 29/08. _x000D_20/8/2024:#Update Retailer confirmed 29/08. _x000D_19/8/2024:#Update Retailer confirmed 29/08. _x000D_19/8/2024:01581474 _x000D_16/8/2024:Your order has been delayed. The supplier appointment failed due lack of resource, the order needs to be re-appointed. Please check with the end user and book a new appointment. _x000D_15/8/2024:Your order has been delayed. The supplier appointment failed due lack of resource, the order needs to be re-appointed. Please check with the end user and book a new appointment. _x000D_14/8/2024:Your order has been delayed. The supplier appointment failed due lack of resource, the order needs to be re-appointed. Please check with the end user and book a new appointment. _x000D_13/8/2024:Supplier Delay: Unable to complete work in the allocated appointment slot, please await further details. _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:19/07/2024 13:57 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update Retailer confirmed 29/08. _x000D_6/9/2024:#Update Retailer confirmed 29/08. _x000D_5/9/2024:#Update Retailer confirmed 29/08. _x000D_4/9/2024:#Update Retailer confirmed 29/08. _x000D_3/9/2024:#Update Retailer confirmed 29/08. _x000D_2/9/2024:#Update Retailer confirmed 29/08. _x000D_29/8/2024:#Update Retailer confirmed 29/08. _x000D_28/8/2024:#Update Retailer confirmed 29/08. _x000D_27/8/2024:#Update Retailer confirmed 29/08. _x000D_22/8/2024:#Update Retailer confirmed 29/08. _x000D_21/8/2024:#Update Retailer confirmed 29/08. _x000D_20/8/2024:#Update Retailer confirmed 29/08. _x000D_19/8/2024:#Update Retailer confirmed 29/08. _x000D_19/8/2024:01581474 _x000D_16/8/2024:Your order has been delayed. The supplier appointment failed due lack of resource, the order needs to be re-appointed. Please check with the end user and book a new appointment. _x000D_15/8/2024:Your order has been delayed. The supplier appointment failed due lack of resource, the order needs to be re-appointed. Please check with the end user and book a new appointment. _x000D_14/8/2024:Your order has been delayed. The supplier appointment failed due lack of resource, the order needs to be re-appointed. Please check with the end user and book a new appointment. _x000D_13/8/2024:Supplier Delay: Unable to complete work in the allocated appointment slot, please await further details. _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:19/07/2024 13:57 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | Your order has been delayed due to a customer missed appointment. Incorrect CRD Please check with end user and reappoint the order if still required. | #Update Retailer confirmed 29/08. |  |  |  |  | 2.Allwyn to arrange access | VFS1043925 | 30017576 | 1.Provisioning | AM |  | 2024-08-12 | 2024-08-12 |  | 0 | [11 empty] | 0
1404 | 617388 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Select Convenience | MANSFIELD | NG18 1LP | 2024-08-14 | 16/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 19/07/2024. _x000D_15/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 19/07/2024. _x000D_14/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 19/07/2024. _x000D_13/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 19/07/2024. _x000D_12/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 19/07/2024. _x000D_9/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 19/07/2024. _x000D_8/8/2024:16/07/2024 _x000D_6/8/2024:16/07/2024 _x000D_5/8/2024:16/07/2024 _x000D_2/8/2024:16/07/2024 _x000D_1/8/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_30/7/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 19/07/2024. _x000D_29/7/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 19/07/2024. _x000D_29/7/2024:01495498 _x000D_26/7/2024:01495498 _x000D_24/7/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 19/07/2024. _x000D_23/7/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 19/07/2024. _x000D_22/7/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 19/07/2024. _x000D_22/7/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 19/07/2024. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 19/07/2024. _x000D_15/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 19/07/2024. _x000D_14/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 19/07/2024. _x000D_13/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 19/07/2024. _x000D_12/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 19/07/2024. _x000D_9/8/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 19/07/2024. _x000D_8/8/2024:16/07/2024 _x000D_6/8/2024:16/07/2024 _x000D_5/8/2024:16/07/2024 _x000D_2/8/2024:16/07/2024 _x000D_1/8/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_30/7/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 19/07/2024. _x000D_29/7/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 19/07/2024. _x000D_29/7/2024:01495498 _x000D_26/7/2024:01495498 _x000D_24/7/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 19/07/2024. _x000D_23/7/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 19/07/2024. _x000D_22/7/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 19/07/2024. _x000D_22/7/2024:#Update - .This has been sent to the survey engineers and they have given us a review date of 19/07/2024. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1055342 | 30017781 | 2.Commissioning | AM |  | 2024-08-13 | 2024-08-13 | 2024-08-13 09:52 | 1 |  |  |  | 2024-09-06 | [7 empty] | 0
1405 | 422545 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Canary Wharf Contractors (Crossrail) Ltd | LONDON | E14 5AB | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Address query | 30017706 | 1.Provisioning | AM |  | 2024-08-13 |  |  | 0 | [11 empty] | 0
1406 | 641295 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Spar Bishops Waltham | SOUTHAMPTON | SO32 1BJ | 2024-08-28 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:#Update - Retailer confirmed appoiintment date. _x000D_28/8/2024:#Update - Retailer confirmed appoiintment date. _x000D_27/8/2024:#Update - Retailer confirmed appoiintment date. _x000D_22/8/2024:#Update - Retailer confirmed appoiintment date. _x000D_21/8/2024:#Update - Retailer confirmed appoiintment date. _x000D_20/8/2024:#Update - Retailer confirmed appoiintment date. _x000D_19/8/2024:#Update - Retailer confirmed appoiintment date. _x000D_19/8/2024:01579556 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:19/07/2024 13:59 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:#Update - Retailer confirmed appoiintment date. _x000D_28/8/2024:#Update - Retailer confirmed appoiintment date. _x000D_27/8/2024:#Update - Retailer confirmed appoiintment date. _x000D_22/8/2024:#Update - Retailer confirmed appoiintment date. _x000D_21/8/2024:#Update - Retailer confirmed appoiintment date. _x000D_20/8/2024:#Update - Retailer confirmed appoiintment date. _x000D_19/8/2024:#Update - Retailer confirmed appoiintment date. _x000D_19/8/2024:01579556 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:19/07/2024 13:59 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_0 | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFS1043921 | 30017531 | 2.Commissioning | AM |  | 2024-08-12 | 2024-08-27 |  | 0 | [11 empty] | 0
1407 | 666632 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Best One | WASHINGTON | NE38 9AH | 2024-08-28 | 29/8/2024:#Update - address verification issues - two stores with the same name next to each other - neither store manager knows anything about the installation, not received any emails, telephone calls _x000D_28/8/2024:#Update - address verification issues - two stores with the same name next to each other - neither store manager knows anything about the installation, not received any emails, telephone calls _x000D_27/8/2024:#Update - address verification issues - two stores with the same name next to each other - neither store manager knows anything about the installation, not received any emails, telephone calls _x000D_22/8/2024:#Update - address verification issues - two stores with the same name next to each other - neither store manager knows anything about the installation, not received any emails, telephone calls _x000D_21/8/2024:#Update - address verification issues - two stores with the same name next to each other - neither store manager knows anything about the installation, not received any emails, telephone calls _x000D_20/8/2024:0 _x000D_19/8/2024:Update: Order Amended _x000D_19/8/2024:12/08/2024 10:38 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 16:10 _x000D_26/7/2024:22/07/2024 16:10 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 29/8/2024:#Update - address verification issues - two stores with the same name next to each other - neither store manager knows anything about the installation, not received any emails, telephone calls _x000D_28/8/2024:#Update - address verification issues - two stores with the same name next to each other - neither store manager knows anything about the installation, not received any emails, telephone calls _x000D_27/8/2024:#Update - address verification issues - two stores with the same name next to each other - neither store manager knows anything about the installation, not received any emails, telephone calls _x000D_22/8/2024:#Update - address verification issues - two stores with the same name next to each other - neither store manager knows anything about the installation, not received any emails, telephone calls _x000D_21/8/2024:#Update - address verification issues - two stores with the same name next to each other - neither store manager knows anything about the installation, not received any emails, telephone calls _x000D_20/8/2024:0 _x000D_19/8/2024:Update: Order Amended _x000D_19/8/2024:12/08/2024 10:38 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 16:10 _x000D_26/7/2024:22/07/2024 16:10 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043920 | 30017433 | 2.Commissioning | AM |  | 2024-08-12 | 2024-08-27 |  | 0 | [11 empty] | 0
1408 | 617408 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | G T News | SHEFFIELD | S9 1EP | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Order has been delayed as step one work is required. CSL will update as more information become available. _x000D_18/7/2024:#Update - Order has been delayed as step one work is required. CSL will update as more information become available. _x000D_17/7/2024:A network engineering task is required to provision this order. The order will now follow the KCI2 Assure process. KCI2 with a confirmed end customer appointment will be sent once the task has completed. CSL Note: Invalid appointment slot received CSL Not _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Order has been delayed as step one work is required. CSL will update as more information become available. _x000D_18/7/2024:#Update - Order has been delayed as step one work is required. CSL will update as more information become available. _x000D_17/7/2024:A network engineering task is required to provision this order. The order will now follow the KCI2 Assure process. KCI2 with a confirmed end customer appointment will be sent once the task has completed. CSL Note: Invalid appointment slot received CSL Not _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Address query | 30017736 | 1.Provisioning | AM |  | 2024-08-13 |  |  | 0 | [11 empty] | 0
1409 | 664305 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | LIFESTYLE STORES | TREDEGAR | NP22 5DJ | 2024-09-05 | 6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM - Retailed has arranged access to next doors gate _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM - Retailed has arranged access to next doors gate _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM - Retailed has arranged access to next doors gate _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM - Retailed has arranged access to next doors gate _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_22/8/2024:#Update - Action for Allwyn - Installation has now been amended to 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_21/8/2024:#Update - Action for Allwyn - Installation has now been amended to 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_20/8/2024:#Update - Action for Allwyn - Installation has now been amended to 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_19/8/2024:#Update - Action for Allwyn - Installation has now been amended to 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_19/8/2024:01499166 _x000D_16/8/2024:#Update - Action for Allwyn - Installation has now been amended to 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_15/8/2024:#Update - Action for Allwyn - Installation has now been amended to 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_14/8/2024:#Update - Action for Allwyn - Installation has now been amended to 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_13/8/2024:#Update - Action for Allwyn - Installation has now been amended to 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_12/8/2024:#Update - Order has been delayed as step one work is required. CSL will update as more information become available. _x000D_9/8/2024:#Update - Order has been delayed as step one work is required. CSL will update as more information become available. _x000D_8/8/2024:17/07/2024 _x000D_6/8/2024:17/07/2024 _x000D_5/8/2024:17/07/2024 _x000D_2/8/2024:17/07/2024 _x000D_1/8/2024:17/07/2024 _x000D_31/7/2024:17/07/2024 _x000D_31/7/2024:17/07/2024 _x000D_30/7/2024:#Update - Order has been delayed as step one work is required. CSL will update as more information become available. _x000D_29/7/2024:#Update - Order has been delayed as step one work is required. CSL will update as more information become available. _x000D_29/7/2024:01499166 _x000D_26/7/2024:01499166 _x000D_24/7/2024:#Update - Order has been delayed as step one work is required. CSL will update as more information become available. _x000D_23/7/2024:#Update - Order has been delayed as step one work is required. CSL will update as more information become available. _x000D_22/7/2024:#Update - Order has been delayed as step one work is required. CSL will update as more information become available. _x000D_22/7/2024:#Update - Order has been delayed as step one work is required. CSL will update as more information become available. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM - Retailed has arranged access to next doors gate _x000D_6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM - Retailed has arranged access to next doors gate _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM - Retailed has arranged access to next doors gate _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM - Retailed has arranged access to next doors gate _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM - Retailed has arranged access to next doors gate _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_22/8/2024:#Update - Action for Allwyn - Installation has now been amended to 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_21/8/2024:#Update - Action for Allwyn - Installation has now been amended to 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_20/8/2024:#Update - Action for Allwyn - Installation has now been amended to 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_19/8/2024:#Update - Action for Allwyn - Installation has now been amended to 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_19/8/2024:01499166 _x000D_16/8/2024:#Update - Action for Allwyn - Installation has now been amended to 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_15/8/2024:#Update - Action for Allwyn - Installation has now been amended to 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_14/8/2024:#Update - Action for Allwyn - Installation has now been amended to 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_13/8/2024:#Update - Action for Allwyn - Installation has now been amended to 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_12/8/2024:#Update - Order has been delayed as step one work is required. CSL will update as more information become available. _x000D_9/8/2024:#Update - Order has been delayed as step one work is required. CSL will update as more information become available. _x000D_8/8/2024:17/07/2024 _x000D_6/8/2024:17/07/2024 _x000D_5/8/2024:17/07/2024 _x000D_2/8/2024:17/07/2024 _x000D_1/8/2024:17/07/2024 _x000D_31/7/2024:17/07/2024 _x000D_31/7/2024:17/07/2024 _x000D_30/7/2024:#Update - Order has been delayed as step one work is required. CSL will update as more information become available. _x000D_29/7/2024:#Update - Order has been delayed as step one work is required. CSL will update as more information become available. _x000D_29/7/2024:01499166 _x000D_26/7/2024:01499166 _x000D_24/7/2024:#Update - Order has been delayed as step one work is required. CSL will update as more information become available. _x000D_23/7/2024:#Update - Order has been delayed as step one work is required. CSL will update as more information become available. _x000D_22/7/2024:#Update - Order has been delayed as step one work is required. CSL will update as more information become available. _x000D_22/7/2024:#Update - Order has been delayed as step one work is required. CSL will update as more information become available. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | Order Completed | #Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM - Retailed has arranged access to next doors gate |  |  |  |  | 2.Allwyn to arrange access | VFP2422477 | 30017382 | 2.Commissioning | AM |  | 2024-08-13 | 2024-08-29 |  | 0 | [11 empty] | 0
1410 | 466452 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | P Carey Newsagency | GATESHEAD | NE10 0LW | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_17/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_17/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Silver Address Issue | 30017758 | 1.Provisioning | AM |  | 2024-08-13 |  |  | 0 | [11 empty] | 0
1411 | 109504 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Sheehys | COOKSTOWN | BT80 8NB | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_23/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_23/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFS1055334 | 30017717 | 1.Provisioning | AM |  | 2024-08-13 | 2024-09-06 |  | 0 | [11 empty] | 0
1412 | 671600 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Y Farchnad Fach Ltd | LLANELLI | SA14 6HY | 2024-08-15 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFP2422476 | 30017289 | 2.Commissioning | AM |  | 2024-08-13 | 2024-08-13 | 2024-08-14 09:25 | 1 |  |  |  | 2024-09-05 | [7 empty] | 0
1413 | 637586 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Ambleside News | WORCESTER | WR4 9DA | 2024-07-11 | 2/8/2024:Order Completed _x000D_1/8/2024:Order Completed _x000D_31/7/2024:Order Completed _x000D_31/7/2024:37775 _x000D_30/7/2024:Order Completed _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 2/8/2024:Order Completed _x000D_1/8/2024:Order Completed _x000D_31/7/2024:Order Completed _x000D_31/7/2024:37775 _x000D_30/7/2024:Order Completed _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFS1043918 | 30017506 | 6.Failed router install |  |  | 2024-07-30 | 2024-07-30 | 2024-07-30 | TRUE |  |  |  | 2024-08-26 |  |  |  | 2024-09-03 | 23A004945863 | 23A004945863 | 2024-09-04 | 1
1414 | 659729 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | McKenzies Shop | ELGIN | IV30 6YA | 2024-07-11 | 6/9/2024:#Update - An Engineer was on site for Step-1 works w/c 05/08 and the retailer advised them that they wish to cancel the order. Action - Allwyn to liaise with retailer and feedback to CSL _x000D_5/9/2024:#Update - An Engineer was on site for Step-1 works w/c 05/08 and the retailer advised them that they wish to cancel the order. Action - Allwyn to liaise with retailer and feedback to CSL _x000D_4/9/2024:#Update - An Engineer was on site for Step-1 works w/c 05/08 and the retailer advised them that they wish to cancel the order. Action - Allwyn to liaise with retailer and feedback to CSL _x000D_3/9/2024:#Update - An Engineer was on site for Step-1 works w/c 05/08 and the retailer advised them that they wish to cancel the order. Action - Allwyn to liaise with retailer and feedback to CSL _x000D_2/9/2024:#Update - An Engineer was on site for Step-1 works w/c 05/08 and the retailer advised them that they wish to cancel the order. Action - Allwyn to liaise with retailer and feedback to CSL _x000D_29/8/2024:#Update - An Engineer was on site for Step-1 works w/c 05/08 and the retailer advised them that they wish to cancel the order. Action - Allwyn to liaise with retailer and feedback to CSL _x000D_28/8/2024:#Update - An Engineer was on site for Step-1 works w/c 05/08 and the retailer advised them that they wish to cancel the order. Action - Allwyn to liaise with retailer and feedback to CSL _x000D_27/8/2024:#Update - An Engineer was on site for Step-1 works w/c 05/08 and the retailer advised them that they wish to cancel the order. Action - Allwyn to liaise with retailer and feedback to CSL _x000D_22/8/2024:#Update - An Engineer was on site for Step-1 works w/c 05/08 and the retailer advised them that they wish to cancel the order. Action - Allwyn to liaise with retailer and feedback to CSL _x000D_21/8/2024:#Update - An Engineer was on site for Step-1 works w/c 05/08 and the retailer advised them that they wish to cancel the order. Action - Allwyn to liaise with retailer and feedback to CSL _x000D_20/8/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/8/2024:Your order has been delayed. Engineer required access to the end user premises to complete the step -1 work. Please check with the end user and confirm the availablity to proceed further. CSL Note: Invalid appointment slot received CSL Note: Invalid data _x000D_19/8/2024:16/08/2024 19:10 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 16/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_13/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 16/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 16/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_9/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 16/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_8/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 16/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 08/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 06/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_2/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 06/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_1/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 06/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:37729 _x000D_30/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_23/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - An Engineer was on site for Step-1 works w/c 05/08 and the retailer advised them that they wish to cancel the order. Action - Allwyn to liaise with retailer and feedback to CSL _x000D_6/9/2024:#Update - An Engineer was on site for Step-1 works w/c 05/08 and the retailer advised them that they wish to cancel the order. Action - Allwyn to liaise with retailer and feedback to CSL _x000D_5/9/2024:#Update - An Engineer was on site for Step-1 works w/c 05/08 and the retailer advised them that they wish to cancel the order. Action - Allwyn to liaise with retailer and feedback to CSL _x000D_4/9/2024:#Update - An Engineer was on site for Step-1 works w/c 05/08 and the retailer advised them that they wish to cancel the order. Action - Allwyn to liaise with retailer and feedback to CSL _x000D_3/9/2024:#Update - An Engineer was on site for Step-1 works w/c 05/08 and the retailer advised them that they wish to cancel the order. Action - Allwyn to liaise with retailer and feedback to CSL _x000D_2/9/2024:#Update - An Engineer was on site for Step-1 works w/c 05/08 and the retailer advised them that they wish to cancel the order. Action - Allwyn to liaise with retailer and feedback to CSL _x000D_29/8/2024:#Update - An Engineer was on site for Step-1 works w/c 05/08 and the retailer advised them that they wish to cancel the order. Action - Allwyn to liaise with retailer and feedback to CSL _x000D_28/8/2024:#Update - An Engineer was on site for Step-1 works w/c 05/08 and the retailer advised them that they wish to cancel the order. Action - Allwyn to liaise with retailer and feedback to CSL _x000D_27/8/2024:#Update - An Engineer was on site for Step-1 works w/c 05/08 and the retailer advised them that they wish to cancel the order. Action - Allwyn to liaise with retailer and feedback to CSL _x000D_22/8/2024:#Update - An Engineer was on site for Step-1 works w/c 05/08 and the retailer advised them that they wish to cancel the order. Action - Allwyn to liaise with retailer and feedback to CSL _x000D_21/8/2024:#Update - An Engineer was on site for Step-1 works w/c 05/08 and the retailer advised them that they wish to cancel the order. Action - Allwyn to liaise with retailer and feedback to CSL _x000D_20/8/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/8/2024:Your order has been delayed. Engineer required access to the end user premises to complete the step -1 work. Please check with the end user and confirm the availablity to proceed further. CSL Note: Invalid appointment slot received CSL Note: Invalid data _x000D_19/8/2024:16/08/2024 19:10 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 16/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_13/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 16/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 16/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_9/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 16/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_8/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 16/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 08/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 06/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_2/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 06/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_1/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 06/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:37729 _x000D_30/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_23/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - An Engineer was on site for Step-1 works w/c 05/08 and the retailer advised them that they wish to cancel the order. Action - Allwyn to liaise with retailer and feedback to CSL |  |  |  |  | 2.Allwyn to arrange access | VFP2422474 | 30017405 | 1.Provisioning | AM |  | 2024-08-13 |  |  | 0 | [11 empty] | 0
1415 | 663257 |  | Batch 6 Aug 24 | Type 1 | KCOM/Mobile | Todays Extra | HULL | HU9 3TN | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | BUS0004479 | 30017237 | 1.Provisioning | AM | 2024-08-14 | 2024-08-14 |  |  | 0 | [11 empty] | 0
1416 | 670734 |  | Batch 6 Aug 24 | Type 1 | SURE/Mobile | Shoprite Ltd | ISLE OF MAN | IM9 6AL | 2024-07-11 | 6/9/2024:#Update - Awaiting site contract from allwyn as the number provided was an out of service line. _x000D_5/9/2024:#Update - Awaiting site contract from allwyn as the number provided was an out of service line. _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Awaiting site contract from allwyn as the number provided was an out of service line. _x000D_6/9/2024:#Update - Awaiting site contract from allwyn as the number provided was an out of service line. _x000D_5/9/2024:#Update - Awaiting site contract from allwyn as the number provided was an out of service line. _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - Awaiting site contract from allwyn as the number provided was an out of service line. |  |  |  |  | 2.Allwyn to arrange access | FPSU010388 | 30017274 | 1.Provisioning | AM | 2024-08-13 | 2024-08-13 |  |  | 0 | [11 empty] | 0
1417 | 471454 |  | Batch 6 Aug 24 | Type 1 | SURE/Mobile | SPAR | ISLE OF MAN | IM2 2BZ | 2024-07-11 | 22/8/2024:#Update Allwyn to speak to retailer regarding appointment and advise if it's suitable. _x000D_21/8/2024:#Update Allwyn to speak to retailer regarding appointment and advise if it's suitable. _x000D_20/8/2024:#Update Allwyn to speak to retailer regarding appointment and advise if it's suitable. _x000D_19/8/2024:#Update Allwyn to speak to retailer regarding appointment and advise if it's suitable. _x000D_19/8/2024:01508371 _x000D_16/8/2024:#Update Allwyn to speak to retailer regarding appointment and advise if it's suitable. _x000D_15/8/2024:#Update Allwyn to speak to retailer regarding appointment and advise if it's suitable. _x000D_14/8/2024:#Update Allwyn to speak to retailer regarding appointment and advise if it's suitable. _x000D_13/8/2024:#Update Allwyn to speak to retailer regarding appointment and advise if it's suitable. _x000D_12/8/2024:#Update Allwyn to speak to retailer regarding appointment and advise if it's suitable. _x000D_9/8/2024:#Update Allwyn to speak to retailer regarding appointment and advise if it's suitable. _x000D_8/8/2024:22/07/2024 _x000D_6/8/2024:22/07/2024 _x000D_5/8/2024:22/07/2024 _x000D_2/8/2024:22/07/2024 _x000D_1/8/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_30/7/2024:#Update Allwyn to speak to retailer regarding appointment and advise if it's suitable. _x000D_29/7/2024:#Update Allwyn to speak to retailer regarding appointment and advise if it's suitable. _x000D_29/7/2024:01508371 _x000D_26/7/2024:01508371 _x000D_24/7/2024:#Update Allwyn to speak to retailer regarding appointment and advise if it's suitable. _x000D_23/7/2024:#Update Allwyn to speak to retailer regarding appointment and advise if it's suitable. _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_18/7/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_0 | 22/8/2024:#Update Allwyn to speak to retailer regarding appointment and advise if it's suitable. _x000D_21/8/2024:#Update Allwyn to speak to retailer regarding appointment and advise if it's suitable. _x000D_20/8/2024:#Update Allwyn to speak to retailer regarding appointment and advise if it's suitable. _x000D_19/8/2024:#Update Allwyn to speak to retailer regarding appointment and advise if it's suitable. _x000D_19/8/2024:01508371 _x000D_16/8/2024:#Update Allwyn to speak to retailer regarding appointment and advise if it's suitable. _x000D_15/8/2024:#Update Allwyn to speak to retailer regarding appointment and advise if it's suitable. _x000D_14/8/2024:#Update Allwyn to speak to retailer regarding appointment and advise if it's suitable. _x000D_13/8/2024:#Update Allwyn to speak to retailer regarding appointment and advise if it's suitable. _x000D_12/8/2024:#Update Allwyn to speak to retailer regarding appointment and advise if it's suitable. _x000D_9/8/2024:#Update Allwyn to speak to retailer regarding appointment and advise if it's suitable. _x000D_8/8/2024:22/07/2024 _x000D_6/8/2024:22/07/2024 _x000D_5/8/2024:22/07/2024 _x000D_2/8/2024:22/07/2024 _x000D_1/8/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_30/7/2024:#Update Allwyn to speak to retailer regarding appointment and advise if it's suitable. _x000D_29/7/2024:#Update Allwyn to speak to retailer regarding appointment and advise if it's suitable. _x000D_29/7/2024:01508371 _x000D_26/7/2024:01508371 _x000D_24/7/2024:#Update Allwyn to speak to retailer regarding appointment and advise if it's suitable. _x000D_23/7/2024:#Update Allwyn to speak to retailer regarding appointment and advise if it's suitable. _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_18/7/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_0 | [6 empty] | 3.Allwyn to arrange rtr install | SURE | 30017281 | 2.Commissioning | AM |  | 2024-08-16 | 2024-08-16 |  | 0 | [11 empty] | 0
1418 | 647407 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Spar Stores | BLACKPOOL | FY2 0HF | 2024-07-11 | 6/9/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_5/9/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_4/9/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_3/9/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_2/9/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_29/8/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_28/8/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_27/8/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_22/8/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_21/8/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_20/8/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_19/8/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_19/8/2024:01499161 _x000D_16/8/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_15/8/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_14/8/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_13/8/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_12/8/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_9/8/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_8/8/2024:18/07/2024 _x000D_6/8/2024:18/07/2024 _x000D_5/8/2024:18/07/2024 _x000D_2/8/2024:18/07/2024 _x000D_1/8/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_30/7/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_29/7/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_29/7/2024:01499161 _x000D_26/7/2024:01499161 _x000D_24/7/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_23/7/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_22/7/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_22/7/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_0 | 9/9/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_6/9/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_5/9/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_4/9/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_3/9/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_2/9/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_29/8/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_28/8/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_27/8/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_22/8/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_21/8/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_20/8/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_19/8/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_19/8/2024:01499161 _x000D_16/8/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_15/8/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_14/8/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_13/8/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_12/8/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_9/8/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_8/8/2024:18/07/2024 _x000D_6/8/2024:18/07/2024 _x000D_5/8/2024:18/07/2024 _x000D_2/8/2024:18/07/2024 _x000D_1/8/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_30/7/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_29/7/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_29/7/2024:01499161 _x000D_26/7/2024:01499161 _x000D_24/7/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_23/7/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_22/7/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_22/7/2024:#Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_0 | 0 | #Update - Order has been delayed as TAM pair allocation is required. CSL will update as more information becomes available. |  |  |  |  | 2.Allwyn to arrange access | VFS1054834 | 30021812 | 1.Provisioning | AM |  | 2024-08-14 | 2024-08-14 |  | 0 | [11 empty] | 0
1419 | 477938 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Randlay Superstore | TELFORD | TF3 2LH | 2024-08-15 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1056396 | 30021826 | 3.In life | AM |  | 2024-08-14 | 2024-08-14 | 2024-08-14 14:27 | 1 |  |  |  | 2024-09-04 |  |  |  | 2024-09-04 | 238004926065 | 238004926065 | 2024-09-05 | 1
1420 | 652582 |  | Batch 6 Aug 24 | Type 1 | KCOM/Mobile | Turnbulls Newsagents | COTTINGHAM | HU16 5QF | 2024-07-11 | 6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_19/8/2024:01579333 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_14/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 23/08 PM. Please speak with the retailer regarding installation details and confirm to CSL if 23/08 is a suitable date. _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_19/8/2024:01579333 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_14/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 23/08 PM. Please speak with the retailer regarding installation details and confirm to CSL if 23/08 is a suitable date. _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM |  |  |  |  | 2.Allwyn to arrange access | BUS0004441 | 30021843 | 2.Commissioning | PM | 2024-08-05 | 2024-08-23 | 2024-08-23 |  | 0 | [11 empty] | 0
1421 | 612493 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Falcon News | PORTSMOUTH | PO1 4EZ | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_0 | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Silver Address Issue | 30017691 | 1.Provisioning | AM |  | 2024-08-14 |  |  | 0 | [11 empty] | 0
1422 | 646269 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Frenchgate News & Food Ltd | DONCASTER | DN1 1LB | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Silver Address Issue | 30021800 | 1.Provisioning | AM |  | 2024-08-14 |  |  | 0 | [11 empty] | 0
1423 | 664047 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | One Stop | BIRMINGHAM | B33 8BA | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2422475 | 30017416 | 1.Provisioning | AM |  | 2024-08-14 | 2024-09-06 |  | 0 | [11 empty] | 0
1424 | 231828 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Premier | BOLTON | BL2 1AD | 2024-07-11 | 6/9/2024:#Update Address query, with VF to advise _x000D_5/9/2024:#Update Address query, with VF to advise _x000D_4/9/2024:#Update Address query, with VF to advise _x000D_3/9/2024:#Update Address query, with VF to advise _x000D_2/9/2024:#Update Address query, with VF to advise _x000D_29/8/2024:#Update Address query, with VF to advise _x000D_28/8/2024:#Update Address query, with VF to advise _x000D_27/8/2024:#Update Address query, with VF to advise _x000D_22/8/2024:#Update Address query, with VF to advise _x000D_21/8/2024:#Update Address query, with VF to advise _x000D_20/8/2024:Your order has been delayed due to a customer missed appointment. Incorrect Address Please check with end user and reappoint the order if still required. _x000D_19/8/2024:Your order has been delayed due to a customer missed appointment. Incorrect Address Please check with end user and reappoint the order if still required. _x000D_19/8/2024:15/08/2024 14:46 _x000D_16/8/2024:Your order has been delayed due to a customer missed appointment. Incorrect Address Please check with end user and reappoint the order if still required. _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_0 | 9/9/2024:#Update Address query, with VF to advise _x000D_6/9/2024:#Update Address query, with VF to advise _x000D_5/9/2024:#Update Address query, with VF to advise _x000D_4/9/2024:#Update Address query, with VF to advise _x000D_3/9/2024:#Update Address query, with VF to advise _x000D_2/9/2024:#Update Address query, with VF to advise _x000D_29/8/2024:#Update Address query, with VF to advise _x000D_28/8/2024:#Update Address query, with VF to advise _x000D_27/8/2024:#Update Address query, with VF to advise _x000D_22/8/2024:#Update Address query, with VF to advise _x000D_21/8/2024:#Update Address query, with VF to advise _x000D_20/8/2024:Your order has been delayed due to a customer missed appointment. Incorrect Address Please check with end user and reappoint the order if still required. _x000D_19/8/2024:Your order has been delayed due to a customer missed appointment. Incorrect Address Please check with end user and reappoint the order if still required. _x000D_19/8/2024:15/08/2024 14:46 _x000D_16/8/2024:Your order has been delayed due to a customer missed appointment. Incorrect Address Please check with end user and reappoint the order if still required. _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_0 | 0 | #Update Address query, with VF to advise |  |  |  |  | 2.Allwyn to arrange access | VFP2422473 | 30017389 | 1.Provisioning | AM |  | 2024-08-14 | 2024-08-14 |  | 0 | [11 empty] | 0
1425 | 103885 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Maqsood Newsagent | LONDON | N4 1AL | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Silver Address Issue | 30021803 | 1.Provisioning | AM |  | 2024-08-14 |  |  | 0 | [11 empty] | 0
1426 | 665269 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Premier Arrowe Stores | WIRRAL | CH49 5LZ | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2422472 | 30017300 | 1.Provisioning | AM |  | 2024-08-14 | 2024-09-06 |  | 0 | [11 empty] | 0
1427 | 455944 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Spar Stores | DURHAM | DH1 1AR | 2024-08-15 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFP2422470 | 30017407 | 2.Commissioning | AM |  | 2024-08-14 | 2024-08-14 | 2024-08-14 13:01 | 1 |  |  |  | 2024-09-13 | [7 empty] | 0
1428 | 479787 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Spar Stores | WOLVERHAMPTON | WV5 9JD | 2024-08-14 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 16:15 _x000D_26/7/2024:22/07/2024 16:15 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 16:15 _x000D_26/7/2024:22/07/2024 16:15 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043917 | 30017439 | 3.In life | AM |  | 2024-08-13 | 2024-08-13 | 2024-08-13 14:33 | 1 |  |  |  | 2024-09-04 |  |  |  | 2024-09-04 | 238004926067 | 238004926067 | 2024-09-05 | 1
1429 | 656221 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Spar | CARMARTHEN | SA31 3AE | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2422469 | 30017321 | 1.Provisioning | AM |  | 2024-08-14 | 2024-09-06 |  | 0 | [11 empty] | 0
1430 | 646673 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Nisa Local | SALFORD | M7 1US | 2024-07-11 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1055327 | 30017751 | 6.Failed router install | AM |  | 2024-08-14 | 2024-08-14 |  | 1 |  |  |  | 2024-09-04 |  |  |  | 2024-09-04 | 238004926185 | 238004926185 | 2024-09-05 | 1
1431 | 481364 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Family Shopper | NORTHAMPTON | NN3 2PU | 2024-07-11 | 6/9/2024:#Update - missed appointment, customer unaware of appointment. Store manager absent on holiday _x000D_5/9/2024:#Update - missed appointment, customer unaware of appointment. Store manager absent on holiday _x000D_4/9/2024:#Update - missed appointment, customer unaware of appointment. Store manager absent on holiday _x000D_3/9/2024:#Update - missed appointment, customer unaware of appointment. Store manager absent on holiday _x000D_2/9/2024:#Update - missed appointment, customer unaware of appointment. Store manager absent on holiday _x000D_29/8/2024:#Update - missed appointment, customer unaware of appointment. Store manager absent on holiday _x000D_28/8/2024:#Update - missed appointment, customer unaware of appointment. Store manager absent on holiday _x000D_27/8/2024:#Update - missed appointment, customer unaware of appointment. Store manager absent on holiday _x000D_22/8/2024:#Update - missed appointment, customer unaware of appointment. Store manager absent on holiday _x000D_21/8/2024:#Update - missed appointment, customer unaware of appointment. Store manager absent on holiday _x000D_20/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_19/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_19/8/2024:14/08/2024 13:18 _x000D_16/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_15/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_14/8/2024:End User Missed appointment. Action required _x000D_13/8/2024:End User Missed appointment. Action required _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 16:18 _x000D_26/7/2024:22/07/2024 16:18 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - missed appointment, customer unaware of appointment. Store manager absent on holiday _x000D_6/9/2024:#Update - missed appointment, customer unaware of appointment. Store manager absent on holiday _x000D_5/9/2024:#Update - missed appointment, customer unaware of appointment. Store manager absent on holiday _x000D_4/9/2024:#Update - missed appointment, customer unaware of appointment. Store manager absent on holiday _x000D_3/9/2024:#Update - missed appointment, customer unaware of appointment. Store manager absent on holiday _x000D_2/9/2024:#Update - missed appointment, customer unaware of appointment. Store manager absent on holiday _x000D_29/8/2024:#Update - missed appointment, customer unaware of appointment. Store manager absent on holiday _x000D_28/8/2024:#Update - missed appointment, customer unaware of appointment. Store manager absent on holiday _x000D_27/8/2024:#Update - missed appointment, customer unaware of appointment. Store manager absent on holiday _x000D_22/8/2024:#Update - missed appointment, customer unaware of appointment. Store manager absent on holiday _x000D_21/8/2024:#Update - missed appointment, customer unaware of appointment. Store manager absent on holiday _x000D_20/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_19/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_19/8/2024:14/08/2024 13:18 _x000D_16/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_15/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_14/8/2024:End User Missed appointment. Action required _x000D_13/8/2024:End User Missed appointment. Action required _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 16:18 _x000D_26/7/2024:22/07/2024 16:18 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - missed appointment, customer unaware of appointment. Store manager absent on holiday |  |  |  |  | 2.Allwyn to arrange access | VFS1043914 | 30017535 | 1.Provisioning | AM |  | 2024-08-13 | 2024-08-13 |  | 0 | [11 empty] | 0
1432 | 462623 |  | Batch 6 Aug 24 | Type 1 | KCOM/Mobile | Maybury Village Service Station | HULL | HU9 3LA | 2024-07-11 | 6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 11/09 AM _x000D_5/9/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 11/09 PM. Please speak with the retailer regarding installation details and confirm to CSL if 11/09 is a suitable date. _x000D_4/9/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 11/09 PM. Please speak with the retailer regarding installation details and confirm to CSL if 11/09 is a suitable date. _x000D_3/9/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 11/09 PM. Please speak with the retailer regarding installation details and confirm to CSL if 11/09 is a suitable date. _x000D_2/9/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 11/09 PM. Please speak with the retailer regarding installation details and confirm to CSL if 11/09 is a suitable date. _x000D_29/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 11/09 PM. Please speak with the retailer regarding installation details and confirm to CSL if 11/09 is a suitable date. _x000D_28/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 11/09 PM. Please speak with the retailer regarding installation details and confirm to CSL if 11/09 is a suitable date. _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 11/09 AM _x000D_6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 11/09 AM _x000D_5/9/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 11/09 PM. Please speak with the retailer regarding installation details and confirm to CSL if 11/09 is a suitable date. _x000D_4/9/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 11/09 PM. Please speak with the retailer regarding installation details and confirm to CSL if 11/09 is a suitable date. _x000D_3/9/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 11/09 PM. Please speak with the retailer regarding installation details and confirm to CSL if 11/09 is a suitable date. _x000D_2/9/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 11/09 PM. Please speak with the retailer regarding installation details and confirm to CSL if 11/09 is a suitable date. _x000D_29/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 11/09 PM. Please speak with the retailer regarding installation details and confirm to CSL if 11/09 is a suitable date. _x000D_28/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 11/09 PM. Please speak with the retailer regarding installation details and confirm to CSL if 11/09 is a suitable date. _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - Allwyn confirmed Retailer has agreed to installation on 11/09 AM |  |  |  |  | 2.Allwyn to arrange access | BUS0004480 | 30017252 | 1.Provisioning | AM | 2024-08-14 | 2024-08-14 |  |  | 0 | [11 empty] | 0
1433 | 477390 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Jafars Licensed Grocer | GLASGOW | G78 2JD | 2024-08-14 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 16:20 _x000D_26/7/2024:22/07/2024 16:20 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 16:20 _x000D_26/7/2024:22/07/2024 16:20 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043915 | 30017497 | 2.Commissioning | AM |  | 2024-08-13 | 2024-08-13 | 2024-08-13 10:53 | 1 |  |  |  | 2024-09-04 | [7 empty] | 0
1434 | 470822 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Candy Box | LONDON | SE6 4DT | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2422467 | 30017337 | 1.Provisioning | AM |  | 2024-08-14 | 2024-09-06 |  | 0 | [11 empty] | 0
1435 | 472783 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Spar | STRABANE | BT82 8JG | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Address query | 30017428 | 1.Provisioning | AM |  | 2024-08-14 |  |  | 0 | [11 empty] | 0
1436 | 616251 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Premier Southfield Store | BRADFORD | BD5 9HQ | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:Update: Order Amended _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. _x000D_19/8/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. _x000D_19/8/2024:14/08/2024 13:28 _x000D_16/8/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. _x000D_15/8/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. _x000D_14/8/2024:End User Missed appointment. Action required _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 16:33 _x000D_26/7/2024:22/07/2024 16:33 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:Update: Order Amended _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. _x000D_19/8/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. _x000D_19/8/2024:14/08/2024 13:28 _x000D_16/8/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. _x000D_15/8/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. _x000D_14/8/2024:End User Missed appointment. Action required _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 16:33 _x000D_26/7/2024:22/07/2024 16:33 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFS1043911 | 30017528 | 1.Provisioning | AM |  | 2024-08-13 | 2024-08-13 |  | 0 | [11 empty] | 0
1437 | 620630 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Am News | BLACKPOOL | FY1 4HU | 2024-08-15 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_0 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_0 | [6 empty] | 2.Allwyn to arrange access | VFS1057039 | 30017408 | 3.In life | AM |  | 2024-08-14 | 2024-08-14 | 2024-08-14 12:23 | 1 |  |  |  | 2024-09-05 |  |  |  | 2024-09-05 | 23A004948592 | 23A004948592 | 2024-09-06 | 1
1438 | 242430 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Londis Supermarket | HAVERFORDWEST | SA61 1QX | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Silver Address Issue | 30021827 | 1.Provisioning | AM |  | 2024-08-15 |  |  | 0 | [11 empty] | 0
1439 | 112767 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Spar Stores | ABERDEEN | AB16 5PY | 2024-08-16 | 19/8/2024:Order Completed _x000D_19/8/2024:15/08/2024 12:29 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 19/8/2024:Order Completed _x000D_19/8/2024:15/08/2024 12:29 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFP2422464 | 30017356 | 3.In life | AM |  | 2024-08-15 | 2024-08-15 |  | 0 |  |  |  | 2024-09-04 |  |  |  | 2024-09-04 | 23A004952704 | 23A004952704 | 2024-09-05 | 1
1440 | 231994 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Diamonds Newsagents | BALLYMENA | BT43 6EE | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_18/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_18/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2422466 | 30017363 | 1.Provisioning | AM |  | 2024-08-15 | 2024-09-06 |  | 0 | [11 empty] | 0
1441 | 464182 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Family Shopper | NOTTINGHAM | NG2 2JD | 2024-08-16 | 19/8/2024:Order Completed _x000D_19/8/2024:15/08/2024 11:30 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_23/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_22/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_22/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 19/8/2024:Order Completed _x000D_19/8/2024:15/08/2024 11:30 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_23/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_22/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_22/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1055324 | 30017768 | 2.Commissioning | AM |  | 2024-08-15 | 2024-08-15 |  | 0 |  |  |  | 2024-09-06 | [7 empty] | 0
1442 | 651231 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | River Food & Wine | ENFIELD | EN1 1YY | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2422463 | 30017397 | 1.Provisioning | AM |  | 2024-08-15 | 2024-09-06 |  | 0 | [11 empty] | 0
1443 | 672608 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Spar Stores | SOUTH MOLTON | EX36 3AB | 2024-07-11 | 13/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. _x000D_12/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. _x000D_9/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. _x000D_8/8/2024:16/07/2024 _x000D_6/8/2024:16/07/2024 _x000D_5/8/2024:16/07/2024 _x000D_2/8/2024:16/07/2024 _x000D_1/8/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_30/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. _x000D_29/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. _x000D_29/7/2024:01496173 _x000D_26/7/2024:01496173 _x000D_24/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. _x000D_23/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. _x000D_22/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. _x000D_22/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 13/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. _x000D_12/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. _x000D_9/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. _x000D_8/8/2024:16/07/2024 _x000D_6/8/2024:16/07/2024 _x000D_5/8/2024:16/07/2024 _x000D_2/8/2024:16/07/2024 _x000D_1/8/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_30/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. _x000D_29/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. _x000D_29/7/2024:01496173 _x000D_26/7/2024:01496173 _x000D_24/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. _x000D_23/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. _x000D_22/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. _x000D_22/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1055322 | 30017773 | 1.Provisioning |  |  | 2024-08-15 | 2024-08-15 |  | 0 | [11 empty] | 0
1444 | 643348 |  | Batch 6 Aug 24 | Type 1 | KCOM/Mobile | Nisa Convenience Store | HULL | HU7 4HE | 2024-09-02 | 6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_19/8/2024:01583531 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_19/8/2024:01583531 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - Allwyn confirmed Retailer has agreed to installation on 30/08 AM |  |  |  |  | 2.Allwyn to arrange access | BUS0004469 | 30017248 | 2.Commissioning | AM | 2024-08-12 | 2024-08-30 | 2024-08-30 |  | 0 | [11 empty] | 0
1445 | 633437 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Bayswater Corner Shop | LEEDS | LS8 5NF | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Address query | 30017760 | 1.Provisioning | AM |  | 2024-08-15 |  |  | 0 | [11 empty] | 0
1446 | 668395 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Grangetown Convenience Stores | MIDDLESBROUGH | TS6 7HX | 2024-08-14 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 16:24 _x000D_26/7/2024:22/07/2024 16:24 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 16:24 _x000D_26/7/2024:22/07/2024 16:24 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043910 | 30017489 | 2.Commissioning | AM |  | 2024-08-13 | 2024-08-13 | 2024-08-13 12:49 | 1 |  |  |  | 2024-09-13 | [7 empty] | 0
1447 | 655969 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Spar | LONDONDERRY | BT47 3DY | 2024-08-14 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 16:26 _x000D_26/7/2024:22/07/2024 16:26 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 16:26 _x000D_26/7/2024:22/07/2024 16:26 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043908 | 30017468 | 2.Commissioning | AM |  | 2024-08-13 | 2024-08-13 | 2024-08-13 11:29 | 1 |  |  |  | 2024-09-09 | [7 empty] | 0
1448 | 615670 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | The Lanes News | CARLISLE | CA3 8NX | 2024-08-14 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 16:26 _x000D_26/7/2024:22/07/2024 16:26 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 16:26 _x000D_26/7/2024:22/07/2024 16:26 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043906 | 30017573 | 2.Commissioning | AM |  | 2024-08-13 | 2024-08-13 | 2024-08-13 11:42 | 1 |  |  |  | 2024-09-09 | [7 empty] | 0
1449 | 655342 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | VP New Express | BASILDON | SS13 3DU | 2024-08-14 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:Order Completed _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 16:29 _x000D_26/7/2024:22/07/2024 16:29 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:Order Completed _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 16:29 _x000D_26/7/2024:22/07/2024 16:29 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043905 | 30017568 | 2.Commissioning | AM |  | 2024-08-13 | 2024-08-13 | 2024-08-13 08:55 | 1 |  |  |  | 2024-09-06 | [7 empty] | 0
1450 | 665101 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Streethouse Junior & Infant School | PONTEFRACT | WF7 6DJ | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Supplier delay - Awaiting further updates _x000D_18/7/2024:#Update - Supplier delay - Awaiting further updates _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Supplier delay - Awaiting further updates _x000D_18/7/2024:#Update - Supplier delay - Awaiting further updates _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Address query | 30017369 | 1.Provisioning | AM |  | 2024-08-15 |  |  | 0 | [11 empty] | 0
1451 | 629636 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Spar Stores | WALSALL | WS9 8BD | 2024-07-11 | 6/9/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 22/08/202 _x000D_5/9/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 22/08/202 _x000D_4/9/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 22/08/202 _x000D_3/9/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 22/08/202 _x000D_2/9/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 22/08/202 _x000D_29/8/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 22/08/202 _x000D_28/8/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 22/08/202 _x000D_27/8/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 22/08/202 _x000D_22/8/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 22/08/202 _x000D_21/8/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 22/08/202 _x000D_20/8/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 22/08/202 _x000D_19/8/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 22/08/202 _x000D_19/8/2024:01500486 _x000D_16/8/2024:#Update - Supplier delay - Awaiting further updates _x000D_15/8/2024:#Update - Supplier delay - Awaiting further updates _x000D_14/8/2024:#Update - Supplier delay - Awaiting further updates _x000D_13/8/2024:#Update - Supplier delay - Awaiting further updates _x000D_12/8/2024:#Update - Supplier delay - Awaiting further updates _x000D_9/8/2024:#Update - Supplier delay - Awaiting further updates _x000D_8/8/2024:18/07/2024 _x000D_6/8/2024:18/07/2024 _x000D_5/8/2024:18/07/2024 _x000D_2/8/2024:18/07/2024 _x000D_1/8/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_30/7/2024:#Update - Supplier delay - Awaiting further updates _x000D_29/7/2024:#Update - Supplier delay - Awaiting further updates _x000D_29/7/2024:01500486 _x000D_26/7/2024:01500486 _x000D_24/7/2024:#Update - Supplier delay - Awaiting further updates _x000D_23/7/2024:#Update - Supplier delay - Awaiting further updates _x000D_22/7/2024:#Update - Supplier delay - Awaiting further updates _x000D_22/7/2024:#Update - Supplier delay - Awaiting further updates _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_0 | 9/9/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 22/08/202 _x000D_6/9/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 22/08/202 _x000D_5/9/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 22/08/202 _x000D_4/9/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 22/08/202 _x000D_3/9/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 22/08/202 _x000D_2/9/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 22/08/202 _x000D_29/8/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 22/08/202 _x000D_28/8/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 22/08/202 _x000D_27/8/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 22/08/202 _x000D_22/8/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 22/08/202 _x000D_21/8/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 22/08/202 _x000D_20/8/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 22/08/202 _x000D_19/8/2024:#Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 22/08/202 _x000D_19/8/2024:01500486 _x000D_16/8/2024:#Update - Supplier delay - Awaiting further updates _x000D_15/8/2024:#Update - Supplier delay - Awaiting further updates _x000D_14/8/2024:#Update - Supplier delay - Awaiting further updates _x000D_13/8/2024:#Update - Supplier delay - Awaiting further updates _x000D_12/8/2024:#Update - Supplier delay - Awaiting further updates _x000D_9/8/2024:#Update - Supplier delay - Awaiting further updates _x000D_8/8/2024:18/07/2024 _x000D_6/8/2024:18/07/2024 _x000D_5/8/2024:18/07/2024 _x000D_2/8/2024:18/07/2024 _x000D_1/8/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_30/7/2024:#Update - Supplier delay - Awaiting further updates _x000D_29/7/2024:#Update - Supplier delay - Awaiting further updates _x000D_29/7/2024:01500486 _x000D_26/7/2024:01500486 _x000D_24/7/2024:#Update - Supplier delay - Awaiting further updates _x000D_23/7/2024:#Update - Supplier delay - Awaiting further updates _x000D_22/7/2024:#Update - Supplier delay - Awaiting further updates _x000D_22/7/2024:#Update - Supplier delay - Awaiting further updates _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_0 | 0 | #Update - delayed as line plant planning work is required. This has been sent to the engineers and they have given us a review date of 22/08/202 |  |  |  |  | 2.Allwyn to arrange access | VFP2422462 | 30017299 | 1.Provisioning | AM |  | 2024-08-15 | 2024-09-13 |  | 0 | [11 empty] | 0
1452 | 435238 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Spar Stores | BURNLEY | BB11 4LF | 2024-08-16 | 19/8/2024:Order Completed _x000D_19/8/2024:15/08/2024 09:17 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 19/8/2024:Order Completed _x000D_19/8/2024:15/08/2024 09:17 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1054879 | 30021802 | 2.Commissioning | AM |  | 2024-08-15 | 2024-08-15 | 2024-08-15 08:43 | 1 |  |  |  | 2024-09-06 | [7 empty] | 0
1453 | 210066 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Travel Time & News Ltd | SHREWSBURY | SY1 1PL | 2024-08-14 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:Order Completed _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 16:29 _x000D_26/7/2024:22/07/2024 16:29 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:Order Completed _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 16:29 _x000D_26/7/2024:22/07/2024 16:29 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043904 | 30017565 | 3.In life | AM |  | 2024-08-13 | 2024-08-13 | 2024-08-13 08:57 | 1 |  |  |  | 2024-09-04 |  |  |  | 2024-09-04 | 238004926064 | 238004926064 | 2024-09-05 | 1
1454 | 412205 |  | Batch 6 Aug 24 | Type 1 | SURE/Mobile | Station Garage | ISLE OF MAN | IM9 1EE | 2024-07-11 | 6/9/2024:#Update Retailer confirmed 26/09 _x000D_5/9/2024:#Update Retailer confirmed 26/09 _x000D_4/9/2024:#Update Retailer confirmed 26/09 _x000D_3/9/2024:#Update Retailer confirmed 26/09 _x000D_2/9/2024:#Update Retailer confirmed 26/09 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Supplier delay - next update 14/08/2024 _x000D_18/7/2024:#Update - Supplier delay - next update 14/08/2024 _x000D_17/7/2024:#Update - Supplier delay - next update 14/08/2024 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update Retailer confirmed 26/09 _x000D_6/9/2024:#Update Retailer confirmed 26/09 _x000D_5/9/2024:#Update Retailer confirmed 26/09 _x000D_4/9/2024:#Update Retailer confirmed 26/09 _x000D_3/9/2024:#Update Retailer confirmed 26/09 _x000D_2/9/2024:#Update Retailer confirmed 26/09 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Supplier delay - next update 14/08/2024 _x000D_18/7/2024:#Update - Supplier delay - next update 14/08/2024 _x000D_17/7/2024:#Update - Supplier delay - next update 14/08/2024 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update Retailer confirmed 26/09 |  |  |  |  | 2.Allwyn to arrange access | FPSU010510 | 30017240 | 1.Provisioning | AM | 2024-08-13 | 2024-08-13 |  |  | 0 | [11 empty] | 0
1455 | 111592 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Bishopston Stores | CARDIFF | CF5 5DX | 2024-08-16 | 19/8/2024:#Update - Supplier delay - next update 14/08/2024 _x000D_19/8/2024:01495500 _x000D_16/8/2024:#Update - Supplier delay - next update 14/08/2024 _x000D_15/8/2024:#Update - Supplier delay - next update 14/08/2024 _x000D_14/8/2024:#Update - Supplier delay - next update 14/08/2024 _x000D_13/8/2024:#Update - Supplier delay - next update 14/08/2024 _x000D_12/8/2024:#Update - Supplier delay - next update 14/08/2024 _x000D_9/8/2024:#Update - Supplier delay - next update 14/08/2024 _x000D_8/8/2024:16/07/2024 _x000D_6/8/2024:16/07/2024 _x000D_5/8/2024:16/07/2024 _x000D_2/8/2024:16/07/2024 _x000D_1/8/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_30/7/2024:#Update - Supplier delay - next update 14/08/2024 _x000D_29/7/2024:#Update - Supplier delay - next update 14/08/2024 _x000D_29/7/2024:01495500 _x000D_26/7/2024:01495500 _x000D_24/7/2024:#Update - Supplier delay - next update 14/08/2024 _x000D_23/7/2024:#Update - Supplier delay - next update 14/08/2024 _x000D_22/7/2024:#Update - Supplier delay - next update 14/08/2024 _x000D_22/7/2024:#Update - Supplier delay - next update 14/08/2024 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 19/8/2024:#Update - Supplier delay - next update 14/08/2024 _x000D_19/8/2024:01495500 _x000D_16/8/2024:#Update - Supplier delay - next update 14/08/2024 _x000D_15/8/2024:#Update - Supplier delay - next update 14/08/2024 _x000D_14/8/2024:#Update - Supplier delay - next update 14/08/2024 _x000D_13/8/2024:#Update - Supplier delay - next update 14/08/2024 _x000D_12/8/2024:#Update - Supplier delay - next update 14/08/2024 _x000D_9/8/2024:#Update - Supplier delay - next update 14/08/2024 _x000D_8/8/2024:16/07/2024 _x000D_6/8/2024:16/07/2024 _x000D_5/8/2024:16/07/2024 _x000D_2/8/2024:16/07/2024 _x000D_1/8/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_30/7/2024:#Update - Supplier delay - next update 14/08/2024 _x000D_29/7/2024:#Update - Supplier delay - next update 14/08/2024 _x000D_29/7/2024:01495500 _x000D_26/7/2024:01495500 _x000D_24/7/2024:#Update - Supplier delay - next update 14/08/2024 _x000D_23/7/2024:#Update - Supplier delay - next update 14/08/2024 _x000D_22/7/2024:#Update - Supplier delay - next update 14/08/2024 _x000D_22/7/2024:#Update - Supplier delay - next update 14/08/2024 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1055316 | 30017769 | 3.In life | AM |  | 2024-08-15 | 2024-08-15 | 2024-08-15 10:41 | 1 |  |  |  | 2024-09-04 |  |  |  | 2024-09-04 | 242005010356 | 242005010356 | 2024-09-05 | 1
1456 | 649822 |  | Batch 6 Aug 24 | Type 1 | KCOM/Mobile | Premier | HULL | HU7 5BZ | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | BUS0004473 | 30017263 | 1.Provisioning | AM | 2024-08-13 | 2024-08-13 |  |  | 0 | [11 empty] | 0
1457 | 656628 |  | Batch 6 Aug 24 | Type 1 | KCOM/Mobile | Sainsburys Local | HULL | HU1 3JF | 2024-07-11 | 27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | BUS0004438 | 30017270 | 2.Commissioning | AM | 2024-08-05 | 2024-08-23 | 2024-08-23 |  | 0 | [11 empty] | 0
1458 | 472018 |  | Batch 6 Aug 24 | Type 1 | KCOM/Mobile | St. Georges News | HULL | HU3 3PX | 2024-08-29 | 6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_19/8/2024:01596927 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_18/7/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_17/7/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_16/7/2024:Delay : Sales Query CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/7/2024:Delay : Sales Query CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/7/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 25/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_11/7/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 25/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 9/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_19/8/2024:01596927 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_18/7/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_17/7/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_16/7/2024:Delay : Sales Query CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/7/2024:Delay : Sales Query CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/7/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 25/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_11/7/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 25/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 0 | #Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM |  |  |  |  | 2.Allwyn to arrange access | BUS0004452 | 30017284 | 2.Commissioning | AM | 2024-08-07 | 2024-08-07 |  |  | 0 | [11 empty] | 0
1459 | 433264 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Glenshane Tourist Services | MAGHERA | BT46 5JZ | 2024-07-11 | 6/9/2024:#Update Order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 05/09/2024. We will continue to provide update as they become available. _x000D_5/9/2024:#Update Order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 05/09/2024. We will continue to provide update as they become available. _x000D_4/9/2024:#Update Order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 05/09/2024. We will continue to provide update as they become available. _x000D_3/9/2024:#Update Order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 05/09/2024. We will continue to provide update as they become available. _x000D_2/9/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_29/8/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_28/8/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_27/8/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_22/8/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_21/8/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_20/8/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_19/8/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_19/8/2024:01484740 _x000D_16/8/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_15/8/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_14/8/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_13/8/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_12/8/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_9/8/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_8/8/2024:15/07/2024 _x000D_6/8/2024:15/07/2024 _x000D_5/8/2024:15/07/2024 _x000D_2/8/2024:15/07/2024 _x000D_1/8/2024:15/07/2024 _x000D_31/7/2024:15/07/2024 _x000D_31/7/2024:15/07/2024 _x000D_30/7/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_29/7/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_29/7/2024:01484740 _x000D_26/7/2024:01484740 _x000D_24/7/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_23/7/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_22/7/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_22/7/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update Order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 05/09/2024. We will continue to provide update as they become available. _x000D_6/9/2024:#Update Order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 05/09/2024. We will continue to provide update as they become available. _x000D_5/9/2024:#Update Order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 05/09/2024. We will continue to provide update as they become available. _x000D_4/9/2024:#Update Order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 05/09/2024. We will continue to provide update as they become available. _x000D_3/9/2024:#Update Order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 05/09/2024. We will continue to provide update as they become available. _x000D_2/9/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_29/8/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_28/8/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_27/8/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_22/8/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_21/8/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_20/8/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_19/8/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_19/8/2024:01484740 _x000D_16/8/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_15/8/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_14/8/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_13/8/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_12/8/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_9/8/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_8/8/2024:15/07/2024 _x000D_6/8/2024:15/07/2024 _x000D_5/8/2024:15/07/2024 _x000D_2/8/2024:15/07/2024 _x000D_1/8/2024:15/07/2024 _x000D_31/7/2024:15/07/2024 _x000D_31/7/2024:15/07/2024 _x000D_30/7/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_29/7/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_29/7/2024:01484740 _x000D_26/7/2024:01484740 _x000D_24/7/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_23/7/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_22/7/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_22/7/2024:#Update Order delayed due to pair divert works. We will provide updates as they become available. _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 09/09/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received | #Update Order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 05/09/2024. We will continue to provide update as they become available. |  |  |  |  | 2.Allwyn to arrange access | VFS1053727 | 30017578 | 1.Provisioning | AM |  | 2024-08-15 |  |  | 0 | [11 empty] | 0
1460 | 485330 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Station Food & Wine | LONDON | N16 6XZ | 2024-08-14 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043901 | 30017479 | 2.Commissioning | AM |  | 2024-08-13 | 2024-08-13 | 2024-08-13 13:54 | 1 |  |  |  | 2024-09-06 | [7 empty] | 0
1461 | 435450 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Raja Bros | ASHTON-UNDER-LYNE | OL7 0LH | 2024-07-11 | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 09:12 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Supplier Delay: Issues with provision of the underground network, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 09:12 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Supplier Delay: Issues with provision of the underground network, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFS1055472 | 30017695 | 2.Commissioning | AM |  | 2024-08-16 | 2024-08-16 |  | 0 |  |  |  | 2024-09-18 | [7 empty] | 0
1462 | 668930 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Premier Inns Court Stores | BRISTOL | BS4 1TR | 2024-07-11 | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 09:00 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:Informational - External visit has been completed _x000D_2/8/2024:Informational - External visit has been completed _x000D_1/8/2024:Informational - External visit has been completed _x000D_31/7/2024:Informational - External visit has been completed _x000D_31/7/2024:37661 _x000D_30/7/2024:Informational - External visit has been completed _x000D_29/7/2024:Informational - External visit has been completed _x000D_29/7/2024:29/07/2024 09:17 _x000D_26/7/2024:19/07/2024 03:58 _x000D_24/7/2024:Supplier Delay: Issues with provision of the underground network, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_23/7/2024:Supplier Delay: Issues with provision of the underground network, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Supplier Delay: Issues with provision of the underground network, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Supplier Delay: Issues with provision of the underground network, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 09:00 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:Informational - External visit has been completed _x000D_2/8/2024:Informational - External visit has been completed _x000D_1/8/2024:Informational - External visit has been completed _x000D_31/7/2024:Informational - External visit has been completed _x000D_31/7/2024:37661 _x000D_30/7/2024:Informational - External visit has been completed _x000D_29/7/2024:Informational - External visit has been completed _x000D_29/7/2024:29/07/2024 09:17 _x000D_26/7/2024:19/07/2024 03:58 _x000D_24/7/2024:Supplier Delay: Issues with provision of the underground network, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_23/7/2024:Supplier Delay: Issues with provision of the underground network, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Supplier Delay: Issues with provision of the underground network, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Supplier Delay: Issues with provision of the underground network, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2422461 | 30017317 | 2.Commissioning | AM |  | 2024-08-16 | 2024-08-16 |  | 0 |  |  |  | 2024-09-18 | [7 empty] | 0
1463 | 654782 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Jassal Mini Store | GRAVESEND | DA12 5DZ | 2024-07-11 | 6/9/2024:#Update Upgrade & OOH sent to VF for approval _x000D_5/9/2024:#Update Upgrade & OOH sent to VF for approval _x000D_4/9/2024:#Update Upgrade & OOH sent to VF for approval _x000D_3/9/2024:#Update Upgrade & OOH sent to VF for approval _x000D_2/9/2024:#Update Upgrade & OOH sent to VF for approval _x000D_29/8/2024:#Update Upgrade & OOH sent to VF for approval _x000D_28/8/2024:#Update Upgrade & OOH sent to VF for approval _x000D_27/8/2024:#Update Upgrade & OOH sent to VF for approval _x000D_22/8/2024:Your order has been delayed due to a customer missed appointment. Out of hour appointment required. Please check with end user and reappoint the order if still required. _x000D_21/8/2024:Your order has been delayed due to a customer missed appointment. Out of hour appointment required. Please check with end user and reappoint the order if still required. _x000D_20/8/2024:Your order has been delayed due to a customer missed appointment. Out of hour appointment required. Please check with end user and reappoint the order if still required. _x000D_19/8/2024:End User Missed appointment. Action required _x000D_19/8/2024:16/08/2024 12:20 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:19/07/2024 19:17 _x000D_24/7/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 30/07/2024.We will continue to provide update as they become available. _x000D_23/7/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 30/07/2024.We will continue to provide update as they become available. _x000D_22/7/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 30/07/2024.We will continue to provide update as they become available. _x000D_22/7/2024:0 _x000D_19/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_17/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update Upgrade & OOH sent to VF for approval _x000D_6/9/2024:#Update Upgrade & OOH sent to VF for approval _x000D_5/9/2024:#Update Upgrade & OOH sent to VF for approval _x000D_4/9/2024:#Update Upgrade & OOH sent to VF for approval _x000D_3/9/2024:#Update Upgrade & OOH sent to VF for approval _x000D_2/9/2024:#Update Upgrade & OOH sent to VF for approval _x000D_29/8/2024:#Update Upgrade & OOH sent to VF for approval _x000D_28/8/2024:#Update Upgrade & OOH sent to VF for approval _x000D_27/8/2024:#Update Upgrade & OOH sent to VF for approval _x000D_22/8/2024:Your order has been delayed due to a customer missed appointment. Out of hour appointment required. Please check with end user and reappoint the order if still required. _x000D_21/8/2024:Your order has been delayed due to a customer missed appointment. Out of hour appointment required. Please check with end user and reappoint the order if still required. _x000D_20/8/2024:Your order has been delayed due to a customer missed appointment. Out of hour appointment required. Please check with end user and reappoint the order if still required. _x000D_19/8/2024:End User Missed appointment. Action required _x000D_19/8/2024:16/08/2024 12:20 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:19/07/2024 19:17 _x000D_24/7/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 30/07/2024.We will continue to provide update as they become available. _x000D_23/7/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 30/07/2024.We will continue to provide update as they become available. _x000D_22/7/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 30/07/2024.We will continue to provide update as they become available. _x000D_22/7/2024:0 _x000D_19/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_17/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update Upgrade & OOH sent to VF for approval |  |  |  |  | 2.Allwyn to arrange access | VFS1057082 | 30017316 | 1.Provisioning | AM |  | 2024-08-16 | 2024-08-16 |  | 0 | [11 empty] | 0
1464 | 487018 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Continental Food Centre | DAGENHAM | RM10 9HX | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_23/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_23/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Line Identified is not compatible with the requested service CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFS1055310 | 30017727 | 1.Provisioning | AM |  | 2024-08-16 |  |  | 0 | [11 empty] | 0
1465 | 641518 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Budgens Stores Ltd | BRIGHTON | BN2 1JN | 2024-08-14 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043898 | 30017556 | 3.In life | AM |  | 2024-08-13 | 2024-08-13 | 2024-08-13 14:00 | 1 |  |  |  | 2024-09-04 |  |  |  | 2024-09-04 | 242005011012 | 242005011012 | 2024-09-05 | 1
1466 | 659386 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Nisa | LEEDS | LS12 1QQ | 2024-08-14 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:Order Completed _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:Order Completed _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043896 | 30017463 | 2.Commissioning | AM |  | 2024-08-13 | 2024-08-13 | 2024-08-13 09:20 | 1 |  |  |  | 2024-09-13 | [7 empty] | 0
1467 | 659854 |  | Batch 6 Aug 24 | Type 1 | KCOM/Mobile | Braim Newsagents | HULL | HU9 2JX | 2024-07-11 | 6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 10/09 AM _x000D_5/9/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 05/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 05/09 is a suitable date. _x000D_4/9/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 05/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 05/09 is a suitable date. _x000D_3/9/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 05/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 05/09 is a suitable date. _x000D_2/9/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 05/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 05/09 is a suitable date. _x000D_29/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 05/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 05/09 is a suitable date. _x000D_28/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 05/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 05/09 is a suitable date. _x000D_27/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 05/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 05/09 is a suitable date. _x000D_22/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 05/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 05/09 is a suitable date. _x000D_21/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 05/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 05/09 is a suitable date. _x000D_20/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 05/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 05/09 is a suitable date. _x000D_19/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 05/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 05/09 is a suitable date. _x000D_19/8/2024:01592378 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 10/09 AM _x000D_6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 10/09 AM _x000D_5/9/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 05/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 05/09 is a suitable date. _x000D_4/9/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 05/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 05/09 is a suitable date. _x000D_3/9/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 05/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 05/09 is a suitable date. _x000D_2/9/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 05/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 05/09 is a suitable date. _x000D_29/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 05/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 05/09 is a suitable date. _x000D_28/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 05/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 05/09 is a suitable date. _x000D_27/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 05/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 05/09 is a suitable date. _x000D_22/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 05/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 05/09 is a suitable date. _x000D_21/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 05/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 05/09 is a suitable date. _x000D_20/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 05/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 05/09 is a suitable date. _x000D_19/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 05/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 05/09 is a suitable date. _x000D_19/8/2024:01592378 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - Allwyn confirmed Retailer has agreed to installation on 10/09 AM |  |  |  |  | 2.Allwyn to arrange access | BUS0004481 | 30017250 | 1.Provisioning | AM |  | 2024-08-02 |  |  | 0 | [11 empty] | 0
1468 | 662747 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Todays Express | CLEETHORPES | DN35 7RN | 2024-07-11 | 6/9/2024:#Update Retailer confirmed 10/09, AM. _x000D_5/9/2024:#Update Retailer confirmed 10/09, AM. _x000D_4/9/2024:#Update Retailer confirmed 10/09, AM. _x000D_3/9/2024:#Update Retailer confirmed 10/09, AM. _x000D_2/9/2024:#Update Retailer confirmed 10/09, AM. _x000D_29/8/2024:#Update Retailer confirmed 10/09, AM. _x000D_28/8/2024:#Update Retailer confirmed 10/09, AM. _x000D_27/8/2024:#Update Retailer confirmed 10/09, AM. _x000D_22/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_21/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_20/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update Retailer confirmed 10/09, AM. _x000D_6/9/2024:#Update Retailer confirmed 10/09, AM. _x000D_5/9/2024:#Update Retailer confirmed 10/09, AM. _x000D_4/9/2024:#Update Retailer confirmed 10/09, AM. _x000D_3/9/2024:#Update Retailer confirmed 10/09, AM. _x000D_2/9/2024:#Update Retailer confirmed 10/09, AM. _x000D_29/8/2024:#Update Retailer confirmed 10/09, AM. _x000D_28/8/2024:#Update Retailer confirmed 10/09, AM. _x000D_27/8/2024:#Update Retailer confirmed 10/09, AM. _x000D_22/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_21/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_20/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update Retailer confirmed 10/09, AM. |  |  |  |  | 2.Allwyn to arrange access | VFP2422460 | 30017367 | 1.Provisioning | AM |  | 2024-08-16 | 2024-08-16 |  | 0 | [11 empty] | 0
1469 | 438171 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Balvi Superstore | LEICESTER | LE3 9NH | 2024-08-14 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043897 | 30017464 | 2.Commissioning | AM |  | 2024-08-13 | 2024-08-13 | 2024-08-13 12:37 | 1 |  |  |  | 2024-09-06 | [7 empty] | 0
1470 | 469260 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Spar Stores | DUNDEE | DD4 8NU | 2024-07-11 | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 11:38 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_23/7/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 11:38 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_23/7/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2422459 | 30017401 | 2.Commissioning | AM |  | 2024-08-16 | 2024-08-16 |  | 0 |  |  |  | 2024-09-18 | [7 empty] | 0
1471 | 614182 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Everydayz | LIVERPOOL | L36 7TU | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2422457 | 30017403 | 1.Provisioning | AM |  | 2024-08-16 | 2024-09-06 |  | 0 | [11 empty] | 0
1472 | 471453 |  | Batch 6 Aug 24 | Type 1 | SURE/Mobile | Spar Stores | ISLE OF MAN | IM8 1AS | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_0 | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | FPSU010508 | 30017244 | 1.Provisioning | AM |  | 2024-08-20 | 2024-08-20 |  | 0 | [11 empty] | 0
1473 | 424297 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Hamilton News | COVENTRY | CV1 5RX | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Silver Address Issue | 30021813 | 1.Provisioning | AM |  | 2024-08-16 |  |  | 0 | [11 empty] | 0
1474 | 657901 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Greene Fayre Ltd | CRAIGAVON | BT66 8PR | 2024-07-11 | 6/9/2024:#Update Delayed due to an exception on the order which has now been cleared. Reappointed for 25/11, AM. Action on Allwyn - ensure the retailer is aware. _x000D_5/9/2024:#Update Delayed due to an exception on the order which has now been cleared. Reappointed for 25/11, AM. Action on Allwyn - ensure the retailer is aware. _x000D_4/9/2024:#Update Delayed due to an exception on the order which has now been cleared. Reappointed for 25/11, AM. Action on Allwyn - ensure the retailer is aware. _x000D_3/9/2024:#Update Delayed due to an exception on the order which has now been cleared. Reappointed for 25/11, AM. Action on Allwyn - ensure the retailer is aware. _x000D_2/9/2024:#Update Delayed due to an exception on the order which has now been cleared. Reappointed for 25/11, AM. Action on Allwyn - ensure the retailer is aware. _x000D_29/8/2024:#Update Order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 30/08/2024. We will continue to provide update as they become available. _x000D_28/8/2024:#Update Order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 30/08/2024. We will continue to provide update as they become available. _x000D_27/8/2024:#Update Order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 30/08/2024. We will continue to provide update as they become available. _x000D_22/8/2024:#Update Order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 30/08/2024. We will continue to provide update as they become available. _x000D_21/8/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_20/8/2024:Your order has been delayed due to Pole work is required, order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 22/08/2024. _x000D_19/8/2024:Supplier Delay: KCI-3 (Order Completed) Delayed in Processing. _x000D_19/8/2024:16/08/2024 23:04 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update Delayed due to an exception on the order which has now been cleared. Reappointed for 25/11, AM. Action on Allwyn - ensure the retailer is aware. _x000D_6/9/2024:#Update Delayed due to an exception on the order which has now been cleared. Reappointed for 25/11, AM. Action on Allwyn - ensure the retailer is aware. _x000D_5/9/2024:#Update Delayed due to an exception on the order which has now been cleared. Reappointed for 25/11, AM. Action on Allwyn - ensure the retailer is aware. _x000D_4/9/2024:#Update Delayed due to an exception on the order which has now been cleared. Reappointed for 25/11, AM. Action on Allwyn - ensure the retailer is aware. _x000D_3/9/2024:#Update Delayed due to an exception on the order which has now been cleared. Reappointed for 25/11, AM. Action on Allwyn - ensure the retailer is aware. _x000D_2/9/2024:#Update Delayed due to an exception on the order which has now been cleared. Reappointed for 25/11, AM. Action on Allwyn - ensure the retailer is aware. _x000D_29/8/2024:#Update Order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 30/08/2024. We will continue to provide update as they become available. _x000D_28/8/2024:#Update Order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 30/08/2024. We will continue to provide update as they become available. _x000D_27/8/2024:#Update Order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 30/08/2024. We will continue to provide update as they become available. _x000D_22/8/2024:#Update Order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 30/08/2024. We will continue to provide update as they become available. _x000D_21/8/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_20/8/2024:Your order has been delayed due to Pole work is required, order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 22/08/2024. _x000D_19/8/2024:Supplier Delay: KCI-3 (Order Completed) Delayed in Processing. _x000D_19/8/2024:16/08/2024 23:04 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update Delayed due to an exception on the order which has now been cleared. Reappointed for 25/11, AM. Action on Allwyn - ensure the retailer is aware. |  |  |  |  | 2.Allwyn to arrange access | VFP2422456 | 30017372 | 1.Provisioning | AM |  | 2024-08-16 | 2024-08-16 |  | 0 | [11 empty] | 0
1475 | 654998 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | LIFESTYLE EXPRESS | WALLSEND | NE28 7RX | 2024-07-11 | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 13:37 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_0 | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 13:37 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_0 | [6 empty] | 3.Allwyn to arrange rtr install | VFP2422455 | 30017293 | 2.Commissioning | AM |  | 2024-08-16 | 2024-08-16 |  | 0 |  |  |  | 2024-09-27 | [7 empty] | 0
1476 | 654490 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | J S Convenience Stores Ltd | WORCESTER | WR4 9QN | 2024-07-11 | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 16:16 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 16:16 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2422329 | 30021838 | 2.Commissioning | AM |  | 2024-08-16 | 2024-08-16 |  | 0 |  |  |  | 2024-09-18 | [7 empty] | 0
1477 | 455147 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | S & D Enterprise Ltd | LEICESTER | LE2 9PE | 2024-07-11 | 6/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 15/07 _x000D_5/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 15/07 _x000D_4/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 15/07 _x000D_3/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 15/07 _x000D_2/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 15/07 _x000D_29/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 15/07 _x000D_28/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 15/07 _x000D_27/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 15/07 _x000D_22/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 15/07 _x000D_21/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 15/07 _x000D_20/8/2024:Update: Order Amended _x000D_19/8/2024:Update: Order Amended _x000D_19/8/2024:15/08/2024 11:45 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Your order has been delayed due to a sales query raised by our supplier, additional time related charges are not covered, please inform end user and amend the order. _x000D_14/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_13/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 15/07 _x000D_6/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 15/07 _x000D_5/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 15/07 _x000D_4/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 15/07 _x000D_3/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 15/07 _x000D_2/9/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 15/07 _x000D_29/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 15/07 _x000D_28/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 15/07 _x000D_27/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 15/07 _x000D_22/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 15/07 _x000D_21/8/2024:#Update - awaiting ECC approval from customer - proposal sent to VF 15/07 _x000D_20/8/2024:Update: Order Amended _x000D_19/8/2024:Update: Order Amended _x000D_19/8/2024:15/08/2024 11:45 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Your order has been delayed due to a sales query raised by our supplier, additional time related charges are not covered, please inform end user and amend the order. _x000D_14/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_13/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - awaiting ECC approval from customer - proposal sent to VF 15/07 |  |  |  |  | 2.Allwyn to arrange access | VFS1043894 | 30017524 | 1.Provisioning | AM |  | 2024-08-13 | 2024-08-13 |  | 0 | [11 empty] | 0
1478 | 467653 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Go Local | NORTHWICH | CW8 2NS | 2024-07-11 | 6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 AM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 AM _x000D_21/8/2024:#Update - The external work has been completed however there are shelves/stock on the wall which prohibited the engineer from drilling out the exterior wall. _x000D_20/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 AM _x000D_6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 AM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 AM _x000D_21/8/2024:#Update - The external work has been completed however there are shelves/stock on the wall which prohibited the engineer from drilling out the exterior wall. _x000D_20/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - Allwyn confirmed Retailer has agreed to installation on 09/09 AM |  |  |  |  | 2.Allwyn to arrange access | VFP2422046 | 30017772 | 1.Provisioning | AM |  | 2024-08-16 | 2024-08-16 |  | 0 | [11 empty] | 0
1479 | 435411 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Spar Stores | CAERNARFON | LL55 2NN | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:Your order has been delayed. Engineer required access to the end user premises to complete the step -1 work. Please check with the end user and confirm the availablity to proceed further. CSL Note: Invalid appointment slot received CSL Note: Invalid data _x000D_19/8/2024:Your order has been delayed. Engineer required access to the end user premises to complete the step -1 work. Please check with the end user and confirm the availablity to proceed further. CSL Note: Invalid appointment slot received CSL Note: Invalid data _x000D_19/8/2024:13/08/2024 16:17 _x000D_16/8/2024:Your order has been delayed. Engineer required access to the end user premises to complete the step -1 work. Please check with the end user and confirm the availablity to proceed further. CSL Note: Invalid appointment slot received CSL Note: Invalid data _x000D_15/8/2024:Your order has been delayed. Engineer required access to the end user premises to complete the step -1 work. Please check with the end user and confirm the availablity to proceed further. CSL Note: Invalid appointment slot received CSL Note: Invalid data _x000D_14/8/2024:Your order has been delayed. Engineer required access to the end user premises to complete the step -1 work. Please check with the end user and confirm the availablity to proceed further. CSL Note: Invalid appointment slot received CSL Note: Invalid data _x000D_13/8/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/8/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 11/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 11/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_2/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 11/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_1/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 11/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_23/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:Your order has been delayed. Engineer required access to the end user premises to complete the step -1 work. Please check with the end user and confirm the availablity to proceed further. CSL Note: Invalid appointment slot received CSL Note: Invalid data _x000D_19/8/2024:Your order has been delayed. Engineer required access to the end user premises to complete the step -1 work. Please check with the end user and confirm the availablity to proceed further. CSL Note: Invalid appointment slot received CSL Note: Invalid data _x000D_19/8/2024:13/08/2024 16:17 _x000D_16/8/2024:Your order has been delayed. Engineer required access to the end user premises to complete the step -1 work. Please check with the end user and confirm the availablity to proceed further. CSL Note: Invalid appointment slot received CSL Note: Invalid data _x000D_15/8/2024:Your order has been delayed. Engineer required access to the end user premises to complete the step -1 work. Please check with the end user and confirm the availablity to proceed further. CSL Note: Invalid appointment slot received CSL Note: Invalid data _x000D_14/8/2024:Your order has been delayed. Engineer required access to the end user premises to complete the step -1 work. Please check with the end user and confirm the availablity to proceed further. CSL Note: Invalid appointment slot received CSL Note: Invalid data _x000D_13/8/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/8/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 11/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 11/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_2/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 11/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_1/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 11/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_23/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2422451 | 30017413 | 1.Provisioning | AM |  | 2024-08-16 |  |  | 0 | [11 empty] | 0
1480 | 667673 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Londis | NEWPORT | NP20 7DB | 2024-07-11 | 6/9/2024:#Update Potential SSRAMS visit wanted, details with Allwyn to advise if they would like to proceed. _x000D_5/9/2024:#Update Potential SSRAMS visit wanted, details with Allwyn to advise if they would like to proceed. _x000D_4/9/2024:#Update Potential SSRAMS visit wanted, details with Allwyn to advise if they would like to proceed. _x000D_3/9/2024:#Update The retailer unaware of the order, and reappointed for 05/09, AM. Action on Allwyn - ensure the retailer is aware. _x000D_2/9/2024:#Update The retailer unaware of the order, and reappointed for 05/09, AM. Action on Allwyn - ensure the retailer is aware. _x000D_29/8/2024:#Update The retailer unaware of the order, and reappointed for 05/09, AM. Action on Allwyn - ensure the retailer is aware. _x000D_28/8/2024:#Update The retailer unaware of the order, and reappointed for 05/09, AM. Action on Allwyn - ensure the retailer is aware. _x000D_27/8/2024:#Update The retailer unaware of the order, and reappointed for 05/09, AM. Action on Allwyn - ensure the retailer is aware. _x000D_22/8/2024:#Update The retailer unaware of the order, and reappointed for 05/09, AM. Action on Allwyn - ensure the retailer is aware. _x000D_21/8/2024:#Update The retailer unaware of the order, and reappointed for 05/09, AM. Action on Allwyn - ensure the retailer is aware. _x000D_20/8/2024:#Update The retailer unaware of the order, and reappointed for 05/09, AM. Action on Allwyn - ensure the retailer is aware. _x000D_19/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_19/8/2024:16/08/2024 08:57 _x000D_16/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update Potential SSRAMS visit wanted, details with Allwyn to advise if they would like to proceed. _x000D_6/9/2024:#Update Potential SSRAMS visit wanted, details with Allwyn to advise if they would like to proceed. _x000D_5/9/2024:#Update Potential SSRAMS visit wanted, details with Allwyn to advise if they would like to proceed. _x000D_4/9/2024:#Update Potential SSRAMS visit wanted, details with Allwyn to advise if they would like to proceed. _x000D_3/9/2024:#Update The retailer unaware of the order, and reappointed for 05/09, AM. Action on Allwyn - ensure the retailer is aware. _x000D_2/9/2024:#Update The retailer unaware of the order, and reappointed for 05/09, AM. Action on Allwyn - ensure the retailer is aware. _x000D_29/8/2024:#Update The retailer unaware of the order, and reappointed for 05/09, AM. Action on Allwyn - ensure the retailer is aware. _x000D_28/8/2024:#Update The retailer unaware of the order, and reappointed for 05/09, AM. Action on Allwyn - ensure the retailer is aware. _x000D_27/8/2024:#Update The retailer unaware of the order, and reappointed for 05/09, AM. Action on Allwyn - ensure the retailer is aware. _x000D_22/8/2024:#Update The retailer unaware of the order, and reappointed for 05/09, AM. Action on Allwyn - ensure the retailer is aware. _x000D_21/8/2024:#Update The retailer unaware of the order, and reappointed for 05/09, AM. Action on Allwyn - ensure the retailer is aware. _x000D_20/8/2024:#Update The retailer unaware of the order, and reappointed for 05/09, AM. Action on Allwyn - ensure the retailer is aware. _x000D_19/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_19/8/2024:16/08/2024 08:57 _x000D_16/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | Update: Order Amended | #Update Potential SSRAMS visit wanted, details with Allwyn to advise if they would like to proceed. |  |  |  |  | 2.Allwyn to arrange access | VFS1055306 | 30017696 | 1.Provisioning | AM |  | 2024-08-16 | 2024-08-16 |  | 0 | [11 empty] | 0
1481 | 671366 |  | Batch 6 Aug 24 | Type 1 | SURE/Mobile | Tesco Express. | ISLE OF MAN | IM5 1HP | 2024-07-11 | 6/9/2024:#Update - Awaiting site contract from allwyn as the number provided was an out of service line. _x000D_5/9/2024:#Update - Awaiting site contract from allwyn as the number provided was an out of service line. _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Awaiting site contract from allwyn as the number provided was an out of service line. _x000D_6/9/2024:#Update - Awaiting site contract from allwyn as the number provided was an out of service line. _x000D_5/9/2024:#Update - Awaiting site contract from allwyn as the number provided was an out of service line. _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - Awaiting site contract from allwyn as the number provided was an out of service line. |  |  |  |  | 2.Allwyn to arrange access | FPSU012783 | 30017239 | 1.Provisioning | AM |  | 2024-08-02 |  |  | 0 | [11 empty] | 0 | 671366
1482 | 664863 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Post Office | BURY ST. EDMUNDS | IP32 6HZ | 2024-07-11 | 6/9/2024:#Update - NFA, Allwyn confirmed new installation date with retailer 09/09 AM _x000D_5/9/2024:#Update - NFA, Allwyn confirmed new installation date with retailer 09/09 AM _x000D_4/9/2024:#Update - NFA, Allwyn confirmed new installation date with retailer 09/09 AM _x000D_3/9/2024:#Update - NFA, Allwyn confirmed new installation date with retailer 09/09 AM _x000D_2/9/2024:#Update - NFA, Allwyn confirmed new installation date with retailer 09/09 AM _x000D_29/8/2024:#Update - NFA, Allwyn confirmed new installation date with retailer 09/09 AM _x000D_28/8/2024:#Update - NFA, Allwyn confirmed new installation date with retailer 09/09 AM _x000D_27/8/2024:#Update - NFA, Allwyn confirmed new installation date with retailer 09/09 AM _x000D_22/8/2024:#Update - NFA, Allwyn confirmed new installation date with retailer 09/09 AM _x000D_21/8/2024:#Update - NFA, Allwyn confirmed new installation date with retailer 09/09 AM _x000D_20/8/2024:#Update - NFA, Allwyn confirmed new installation date with retailer 09/09 AM _x000D_19/8/2024:#Update - NFA, Allwyn confirmed new installation date with retailer 09/09 AM _x000D_19/8/2024:01553599 _x000D_16/8/2024:#Update - NFA, Allwyn confirmed new installation date with retailer 09/09 AM _x000D_15/8/2024:#Update - NFA, Allwyn confirmed new installation date with retailer 09/09 AM _x000D_14/8/2024:#Update - NFA, Allwyn confirmed new installation date with retailer 09/09 AM _x000D_13/8/2024:#Update - NFA, Allwyn confirmed new installation date with retailer 09/09 AM _x000D_12/8/2024:#Update - NFA, Allwyn confirmed new installation date with retailer 09/09 AM _x000D_9/8/2024:#Update - NFA, Allwyn confirmed new installation date with retailer 09/09 AM _x000D_8/8/2024:05/08/2024 _x000D_6/8/2024:05/08/2024 _x000D_5/8/2024:05/08/2024 _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 31/07/2024. _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - NFA, Allwyn confirmed new installation date with retailer 09/09 AM _x000D_6/9/2024:#Update - NFA, Allwyn confirmed new installation date with retailer 09/09 AM _x000D_5/9/2024:#Update - NFA, Allwyn confirmed new installation date with retailer 09/09 AM _x000D_4/9/2024:#Update - NFA, Allwyn confirmed new installation date with retailer 09/09 AM _x000D_3/9/2024:#Update - NFA, Allwyn confirmed new installation date with retailer 09/09 AM _x000D_2/9/2024:#Update - NFA, Allwyn confirmed new installation date with retailer 09/09 AM _x000D_29/8/2024:#Update - NFA, Allwyn confirmed new installation date with retailer 09/09 AM _x000D_28/8/2024:#Update - NFA, Allwyn confirmed new installation date with retailer 09/09 AM _x000D_27/8/2024:#Update - NFA, Allwyn confirmed new installation date with retailer 09/09 AM _x000D_22/8/2024:#Update - NFA, Allwyn confirmed new installation date with retailer 09/09 AM _x000D_21/8/2024:#Update - NFA, Allwyn confirmed new installation date with retailer 09/09 AM _x000D_20/8/2024:#Update - NFA, Allwyn confirmed new installation date with retailer 09/09 AM _x000D_19/8/2024:#Update - NFA, Allwyn confirmed new installation date with retailer 09/09 AM _x000D_19/8/2024:01553599 _x000D_16/8/2024:#Update - NFA, Allwyn confirmed new installation date with retailer 09/09 AM _x000D_15/8/2024:#Update - NFA, Allwyn confirmed new installation date with retailer 09/09 AM _x000D_14/8/2024:#Update - NFA, Allwyn confirmed new installation date with retailer 09/09 AM _x000D_13/8/2024:#Update - NFA, Allwyn confirmed new installation date with retailer 09/09 AM _x000D_12/8/2024:#Update - NFA, Allwyn confirmed new installation date with retailer 09/09 AM _x000D_9/8/2024:#Update - NFA, Allwyn confirmed new installation date with retailer 09/09 AM _x000D_8/8/2024:05/08/2024 _x000D_6/8/2024:05/08/2024 _x000D_5/8/2024:05/08/2024 _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 31/07/2024. _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - NFA, Allwyn confirmed new installation date with retailer 09/09 AM |  |  |  |  | 2.Allwyn to arrange access | VFP2422452 | 30017398 | 1.Provisioning | AM |  | 2024-08-16 | 2024-09-09 |  | 0 | [11 empty] | 0
1483 | 443122 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Supervalue | CRAIGAVON | BT62 2JU | 2024-07-11 | 6/9/2024:#Update Network Planning issues. Please await for further updates _x000D_5/9/2024:#Update Network Planning issues. Please await for further updates _x000D_4/9/2024:#Update Network Planning issues. Please await for further updates _x000D_3/9/2024:#Update Network Planning issues. Please await for further updates _x000D_2/9/2024:#Update Network Planning issues. Please await for further updates _x000D_29/8/2024:#Update Network Planning issues. Please await for further updates _x000D_28/8/2024:#Update Network Planning issues. Please await for further updates _x000D_27/8/2024:#Update Network Planning issues. Please await for further updates _x000D_22/8/2024:#Update Network Planning issues. Please await for further updates _x000D_21/8/2024:#Update Network Planning issues. Please await for further updates _x000D_20/8/2024:#Update Network Planning issues. Please await for further updates _x000D_19/8/2024:#Update Network Planning issues. Please await for further updates _x000D_19/8/2024:01535319 _x000D_16/8/2024:#Update Network Planning issues. Please await for further updates _x000D_15/8/2024:#Update Network Planning issues. Please await for further updates _x000D_14/8/2024:#Update Network Planning issues. Please await for further updates _x000D_13/8/2024:#Update Network Planning issues. Please await for further updates _x000D_12/8/2024:#Update Network Planning issues. Please await for further updates _x000D_9/8/2024:#Update Network Planning issues. Please await for further updates _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update Network Planning issues. Please await for further updates _x000D_29/7/2024:#Update Network Planning issues. Please await for further updates _x000D_29/7/2024:01535319 _x000D_26/7/2024:01535319 _x000D_24/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 31/07/2024. _x000D_23/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 31/07/2024. _x000D_22/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 31/07/2024. _x000D_22/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 31/07/2024. _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update Network Planning issues. Please await for further updates _x000D_6/9/2024:#Update Network Planning issues. Please await for further updates _x000D_5/9/2024:#Update Network Planning issues. Please await for further updates _x000D_4/9/2024:#Update Network Planning issues. Please await for further updates _x000D_3/9/2024:#Update Network Planning issues. Please await for further updates _x000D_2/9/2024:#Update Network Planning issues. Please await for further updates _x000D_29/8/2024:#Update Network Planning issues. Please await for further updates _x000D_28/8/2024:#Update Network Planning issues. Please await for further updates _x000D_27/8/2024:#Update Network Planning issues. Please await for further updates _x000D_22/8/2024:#Update Network Planning issues. Please await for further updates _x000D_21/8/2024:#Update Network Planning issues. Please await for further updates _x000D_20/8/2024:#Update Network Planning issues. Please await for further updates _x000D_19/8/2024:#Update Network Planning issues. Please await for further updates _x000D_19/8/2024:01535319 _x000D_16/8/2024:#Update Network Planning issues. Please await for further updates _x000D_15/8/2024:#Update Network Planning issues. Please await for further updates _x000D_14/8/2024:#Update Network Planning issues. Please await for further updates _x000D_13/8/2024:#Update Network Planning issues. Please await for further updates _x000D_12/8/2024:#Update Network Planning issues. Please await for further updates _x000D_9/8/2024:#Update Network Planning issues. Please await for further updates _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update Network Planning issues. Please await for further updates _x000D_29/7/2024:#Update Network Planning issues. Please await for further updates _x000D_29/7/2024:01535319 _x000D_26/7/2024:01535319 _x000D_24/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 31/07/2024. _x000D_23/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 31/07/2024. _x000D_22/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 31/07/2024. _x000D_22/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 31/07/2024. _x000D_19/7/2024:Update: Order Amended _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update Network Planning issues. Please await for further updates |  |  |  |  | 2.Allwyn to arrange access | VFP2422448 | 30017399 | 1.Provisioning | AM |  | 2024-08-16 |  |  | 0 | [11 empty] | 0
1484 | 664472 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Eurospar | BALLYMENA | BT44 8HS | 2024-08-14 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:Order Completed _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:Order Completed _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043895 | 30017555 | 2.Commissioning | AM |  | 2024-08-13 | 2024-08-13 | 2024-08-13 09:21 | 1 |  |  |  | 2024-09-09 | [7 empty] | 0
1485 | 606666 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Park Lane News | CONSETT | DH8 5SD | 2024-07-11 | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 11:14 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Supplier delay - Awaiting new updates, _x000D_18/7/2024:#Update - Supplier delay - Awaiting new updates, _x000D_17/7/2024:#Update - Supplier delay - Awaiting new updates, _x000D_0 | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 11:14 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Supplier delay - Awaiting new updates, _x000D_18/7/2024:#Update - Supplier delay - Awaiting new updates, _x000D_17/7/2024:#Update - Supplier delay - Awaiting new updates, _x000D_0 | [6 empty] | 3.Allwyn to arrange rtr install | VFS1057024 | 30017374 | 2.Commissioning | AM |  | 2024-08-16 | 2024-08-16 |  | 0 |  |  |  | 2024-09-27 | [7 empty] | 0
1486 | 483296 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Spar Stores | GAINSBOROUGH | DN21 1FT | 2024-07-11 | 6/9/2024:#Update - NFA - Allwyn confirmed installation date 06/09 with retailer _x000D_5/9/2024:#Update - NFA - Allwyn confirmed installation date 06/09 with retailer _x000D_4/9/2024:#Update - NFA - Allwyn confirmed installation date 06/09 with retailer _x000D_3/9/2024:#Update - NFA - Allwyn confirmed installation date 06/09 with retailer _x000D_2/9/2024:#Update - NFA - Allwyn confirmed installation date 06/09 with retailer _x000D_29/8/2024:#Update - NFA - Allwyn confirmed installation date 06/09 with retailer _x000D_28/8/2024:#Update - NFA - Allwyn confirmed installation date 06/09 with retailer _x000D_27/8/2024:#Update - NFA - Allwyn confirmed installation date 06/09 with retailer _x000D_22/8/2024:#Update - NFA - Allwyn confirmed installation date 06/09 with retailer _x000D_21/8/2024:#Update - NFA - Allwyn confirmed installation date 06/09 with retailer _x000D_20/8/2024:#Update - NFA - Allwyn confirmed installation date 06/09 with retailer _x000D_19/8/2024:#Update - NFA - Allwyn confirmed installation date 06/09 with retailer _x000D_19/8/2024:01560681 _x000D_16/8/2024:#Update - NFA - Allwyn confirmed installation date 06/09 with retailer _x000D_15/8/2024:#Update - NFA - Allwyn confirmed installation date 06/09 with retailer _x000D_14/8/2024:#Update - NFA - Allwyn confirmed installation date 06/09 with retailer _x000D_13/8/2024:#Update - NFA - Allwyn confirmed installation date 06/09 with retailer _x000D_12/8/2024:#Update - NFA - Allwyn confirmed installation date 06/09 with retailer _x000D_9/8/2024:#Update - NFA - Allwyn confirmed installation date 06/09 with retailer _x000D_8/8/2024:17/07/2024 _x000D_6/8/2024:17/07/2024 _x000D_5/8/2024:17/07/2024 _x000D_2/8/2024:17/07/2024 _x000D_1/8/2024:17/07/2024 _x000D_31/7/2024:17/07/2024 _x000D_31/7/2024:17/07/2024 _x000D_30/7/2024:#Update - Supplier delay - Awaiting new updates, _x000D_29/7/2024:#Update - Supplier delay - Awaiting new updates, _x000D_29/7/2024:01496750 _x000D_26/7/2024:01496750 _x000D_24/7/2024:#Update - Supplier delay - Awaiting new updates, _x000D_23/7/2024:#Update - Supplier delay - Awaiting new updates, _x000D_22/7/2024:#Update - Supplier delay - Awaiting new updates, _x000D_22/7/2024:#Update - Supplier delay - Awaiting new updates, _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_0 | 9/9/2024:#Update - NFA - Allwyn confirmed installation date 06/09 with retailer _x000D_6/9/2024:#Update - NFA - Allwyn confirmed installation date 06/09 with retailer _x000D_5/9/2024:#Update - NFA - Allwyn confirmed installation date 06/09 with retailer _x000D_4/9/2024:#Update - NFA - Allwyn confirmed installation date 06/09 with retailer _x000D_3/9/2024:#Update - NFA - Allwyn confirmed installation date 06/09 with retailer _x000D_2/9/2024:#Update - NFA - Allwyn confirmed installation date 06/09 with retailer _x000D_29/8/2024:#Update - NFA - Allwyn confirmed installation date 06/09 with retailer _x000D_28/8/2024:#Update - NFA - Allwyn confirmed installation date 06/09 with retailer _x000D_27/8/2024:#Update - NFA - Allwyn confirmed installation date 06/09 with retailer _x000D_22/8/2024:#Update - NFA - Allwyn confirmed installation date 06/09 with retailer _x000D_21/8/2024:#Update - NFA - Allwyn confirmed installation date 06/09 with retailer _x000D_20/8/2024:#Update - NFA - Allwyn confirmed installation date 06/09 with retailer _x000D_19/8/2024:#Update - NFA - Allwyn confirmed installation date 06/09 with retailer _x000D_19/8/2024:01560681 _x000D_16/8/2024:#Update - NFA - Allwyn confirmed installation date 06/09 with retailer _x000D_15/8/2024:#Update - NFA - Allwyn confirmed installation date 06/09 with retailer _x000D_14/8/2024:#Update - NFA - Allwyn confirmed installation date 06/09 with retailer _x000D_13/8/2024:#Update - NFA - Allwyn confirmed installation date 06/09 with retailer _x000D_12/8/2024:#Update - NFA - Allwyn confirmed installation date 06/09 with retailer _x000D_9/8/2024:#Update - NFA - Allwyn confirmed installation date 06/09 with retailer _x000D_8/8/2024:17/07/2024 _x000D_6/8/2024:17/07/2024 _x000D_5/8/2024:17/07/2024 _x000D_2/8/2024:17/07/2024 _x000D_1/8/2024:17/07/2024 _x000D_31/7/2024:17/07/2024 _x000D_31/7/2024:17/07/2024 _x000D_30/7/2024:#Update - Supplier delay - Awaiting new updates, _x000D_29/7/2024:#Update - Supplier delay - Awaiting new updates, _x000D_29/7/2024:01496750 _x000D_26/7/2024:01496750 _x000D_24/7/2024:#Update - Supplier delay - Awaiting new updates, _x000D_23/7/2024:#Update - Supplier delay - Awaiting new updates, _x000D_22/7/2024:#Update - Supplier delay - Awaiting new updates, _x000D_22/7/2024:#Update - Supplier delay - Awaiting new updates, _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_0 | 0 | #Update - NFA - Allwyn confirmed installation date 06/09 with retailer |  |  |  |  | 2.Allwyn to arrange access | VFP2422352 | 30021823 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
1487 | 108800 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Nisa Extra | GAERWEN | LL60 6BW | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Silver Address Issue | 30021804 | 1.Provisioning | AM |  | 2024-08-05 |  |  | 0 | [11 empty] | 0
1488 | 111078 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Spar Stores | HOLYHEAD | LL65 3EB | 2024-07-11 | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:Openreach Delay : Automated testing has identified a potential fault _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:Openreach Delay : Automated testing has identified a potential fault _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2422449 | 30017411 | 3.In life |  |  | 2024-08-05 | 2024-08-05 | 2024-08-05 12:29 | TRUE | [7 empty] | 2024-09-02 | 23A004948579 | 23A004948579 | 2024-09-03 | 1
1489 | 457383 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | SPAR Newhouse Road | GRANGEMOUTH | FK3 8LL | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Your order has been delayed. TAM pair allocation required. Our Suppliers have given us a review date of 02/08/2024. We will continue to provide update as they become available. _x000D_18/7/2024:Your order has been delayed. TAM pair allocation required. Our Suppliers have given us a review date of 02/08/2024. We will continue to provide update as they become available. _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Your order has been delayed. TAM pair allocation required. Our Suppliers have given us a review date of 02/08/2024. We will continue to provide update as they become available. _x000D_18/7/2024:Your order has been delayed. TAM pair allocation required. Our Suppliers have given us a review date of 02/08/2024. We will continue to provide update as they become available. _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Address query | 30017771 | 1.Provisioning | AM |  | 2024-08-05 |  |  | 0 | [11 empty] | 0
1490 | 430371 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | NISA LOCAL | BURTON-ON-TRENT | DE13 0SW | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:Update: Order Amended _x000D_19/8/2024:Update: Order Amended _x000D_19/8/2024:13/08/2024 09:23 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_9/8/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_8/8/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_6/8/2024:End User Missed appointment. Action required _x000D_5/8/2024:End User Missed appointment. Action required _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_17/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_16/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:Update: Order Amended _x000D_19/8/2024:Update: Order Amended _x000D_19/8/2024:13/08/2024 09:23 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_9/8/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_8/8/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_6/8/2024:End User Missed appointment. Action required _x000D_5/8/2024:End User Missed appointment. Action required _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_17/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_16/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_0 | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFS1043891 | 30017467 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-16 |  | 0 | [11 empty] | 0
1491 | 631929 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Premier | LEICESTER | LE2 6QT | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/08 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/08 AM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/08 AM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/08 AM _x000D_19/8/2024:01561202 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/08 AM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/08 AM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/08 AM _x000D_13/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/08 AM _x000D_12/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/08 AM _x000D_9/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/08 AM _x000D_8/8/2024:06/08/2024 _x000D_6/8/2024:05/08/2024 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/08 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/08 AM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/08 AM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/08 AM _x000D_19/8/2024:01561202 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/08 AM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/08 AM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/08 AM _x000D_13/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/08 AM _x000D_12/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/08 AM _x000D_9/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 22/08 AM _x000D_8/8/2024:06/08/2024 _x000D_6/8/2024:05/08/2024 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 3.Allwyn to arrange rtr install | VFS1054862 | 30021797 | 2.Commissioning | AM |  | 2024-08-05 | 2024-08-22 |  | 0 |  |  |  | 2024-09-20 | [7 empty] | 0
1492 | 427173 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Spar Stores | PWLLHELI | LL53 5HA | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. _x000D_12/8/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. _x000D_9/8/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. _x000D_8/8/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. _x000D_12/8/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. _x000D_9/8/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. _x000D_8/8/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2422447 | 30017377 | 1.Provisioning | AM |  | 2024-08-05 | 2024-08-05 |  | 0 | [11 empty] | 0
1493 | 439386 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Spar | BALLYMONEY | BT53 6LE | 2024-07-11 | 6/9/2024:#Update Order delayed due to a supplier system delay. _x000D_5/9/2024:#Update Order delayed due to a supplier system delay. _x000D_4/9/2024:#Update Order delayed due to a supplier system delay. _x000D_3/9/2024:#Update Order delayed due to a supplier system delay. _x000D_2/9/2024:#Update Order delayed due to a supplier system delay. _x000D_29/8/2024:#Update Order delayed due to a supplier system delay. _x000D_28/8/2024:#Update Order delayed due to a supplier system delay. _x000D_27/8/2024:#Update Order delayed due to a supplier system delay. _x000D_22/8/2024:#Update Order delayed due to a supplier system delay. _x000D_21/8/2024:#Update Order delayed due to a supplier system delay. _x000D_20/8/2024:#Update delay due to cable wires being required - update on 15/08 _x000D_19/8/2024:#Update delay due to cable wires being required - update on 15/08 _x000D_19/8/2024:01561052 _x000D_16/8/2024:#Update delay due to cable wires being required - update on 15/08 _x000D_15/8/2024:#Update delay due to cable wires being required - update on 15/08 _x000D_14/8/2024:#Update delay due to cable wires being required - update on 15/08 _x000D_13/8/2024:#Update Engineer unable to complete installation due to line plant survey needed. Internal cabling is required before order can progress. Will update as they come in. _x000D_12/8/2024:#Update Engineer unable to complete installation due to line plant survey needed. Internal cabling is required before order can progress. Will update as they come in. _x000D_9/8/2024:#Update Engineer unable to complete installation due to line plant survey needed. Internal cabling is required before order can progress. Will update as they come in. _x000D_8/8/2024:07/08/2024 _x000D_6/8/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update Order delayed due to a supplier system delay. _x000D_6/9/2024:#Update Order delayed due to a supplier system delay. _x000D_5/9/2024:#Update Order delayed due to a supplier system delay. _x000D_4/9/2024:#Update Order delayed due to a supplier system delay. _x000D_3/9/2024:#Update Order delayed due to a supplier system delay. _x000D_2/9/2024:#Update Order delayed due to a supplier system delay. _x000D_29/8/2024:#Update Order delayed due to a supplier system delay. _x000D_28/8/2024:#Update Order delayed due to a supplier system delay. _x000D_27/8/2024:#Update Order delayed due to a supplier system delay. _x000D_22/8/2024:#Update Order delayed due to a supplier system delay. _x000D_21/8/2024:#Update Order delayed due to a supplier system delay. _x000D_20/8/2024:#Update delay due to cable wires being required - update on 15/08 _x000D_19/8/2024:#Update delay due to cable wires being required - update on 15/08 _x000D_19/8/2024:01561052 _x000D_16/8/2024:#Update delay due to cable wires being required - update on 15/08 _x000D_15/8/2024:#Update delay due to cable wires being required - update on 15/08 _x000D_14/8/2024:#Update delay due to cable wires being required - update on 15/08 _x000D_13/8/2024:#Update Engineer unable to complete installation due to line plant survey needed. Internal cabling is required before order can progress. Will update as they come in. _x000D_12/8/2024:#Update Engineer unable to complete installation due to line plant survey needed. Internal cabling is required before order can progress. Will update as they come in. _x000D_9/8/2024:#Update Engineer unable to complete installation due to line plant survey needed. Internal cabling is required before order can progress. Will update as they come in. _x000D_8/8/2024:07/08/2024 _x000D_6/8/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | Your order has been delayed. Multiskilled engineer work is required for NCF work, Our Suppliers have given us a review date of 10/09/2024. We will continue to provide update as they become available. | #Update Order delayed due to a supplier system delay. |  |  |  |  | 2.Allwyn to arrange access | VFS1043889 | 30017543 | 1.Provisioning | AM |  | 2024-08-05 | 2024-08-05 |  | 0 | [11 empty] | 0
1494 | 667361 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Post Office | BIRMINGHAM | B7 5DT | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Silver Address Issue | 30017685 | 1.Provisioning | AM |  | 2024-08-05 |  |  | 0 | [11 empty] | 0
1495 | 459768 |  | Batch 6 Aug 24 | Type 1 | KCOM/Mobile | Sutton Service Station | HULL | HU8 9XL | 2024-09-04 | 6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_19/8/2024:01592400 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_19/8/2024:01592400 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM |  |  |  |  | 2.Allwyn to arrange access | BUS0004482 | 30017273 | 2.Commissioning | AM | 2024-08-14 | 2024-08-14 |  |  | 0 | [11 empty] | 0
1496 | 467483 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Spar 24Hr | ENNISKILLEN | BT74 7JR | 2024-07-11 | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:Order Completed _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:Supplier Delay: Delay encountered during automated test of new service _x000D_22/7/2024:Supplier Delay: Delay encountered during automated test of new service _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:Order Completed _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:Supplier Delay: Delay encountered during automated test of new service _x000D_22/7/2024:Supplier Delay: Delay encountered during automated test of new service _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2421155 | 30017746 | 6.Failed router install |  |  | 2024-08-05 | 2024-08-05 | 2024-08-05 18:13 | TRUE |  |  |  | 2024-08-21 |  |  |  | 2024-08-21 | 23A004952955 | 23A004952955 | 2024-08-22 | 1
1497 | 656909 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | JJs Premier | Alperton | HA0 1UE | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2422010 | 30017682 | 1.Provisioning | AM |  | 2024-08-05 | 2024-08-30 |  | 0 | [11 empty] | 0
1498 | 470388 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | North Street Garage | HAVERHILL | CB9 0EP | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:01 _x000D_26/7/2024:22/07/2024 10:01 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:01 _x000D_26/7/2024:22/07/2024 10:01 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2422446 | 30017329 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
1499 | 472541 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Nearby | BALLYMENA | BT42 1BW | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 09:57 _x000D_26/7/2024:22/07/2024 09:57 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 09:57 _x000D_26/7/2024:22/07/2024 09:57 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2422444 | 30017290 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
1500 | 461760 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Texaco Spar | ROTHERHAM | S63 9AE | 2024-07-11 | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:Order Completed _x000D_5/8/2024:Order Completed _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:Order Completed _x000D_5/8/2024:Order Completed _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2422443 | 30017354 | 2.Commissioning |  |  | 2024-08-05 | 2024-08-05 | 2024-08-05 | TRUE |  |  |  | 2024-08-23 | [7 empty] | 0
1501 | 654025 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Boaler Street Convenience Store | LIVERPOOL | L6 6AD | 2024-07-11 | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:Order Completed _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:Order Completed _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2422445 | 30017376 | 2.Commissioning |  |  | 2024-08-05 | 2024-08-05 | 2024-08-05 11:40 | TRUE |  |  |  | 2024-08-22 | [7 empty] | 0
1502 | 646521 |  | Batch 6 Aug 24 | Type 3 | SURE/Mobile | EVF Todays Express | ISLE OF MAN | IM8 2LN | 2024-07-11 | 4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | FPSU010396 | 30017271 | 2.Commissioning | AM |  | 2024-08-05 |  |  | 0 | [11 empty] | 0
1503 | 668162 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Spar | NEWRY | BT34 4TJ | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 09:59 _x000D_26/7/2024:22/07/2024 09:59 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 09:59 _x000D_26/7/2024:22/07/2024 09:59 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2422442 | 30017366 | 1.Provisioning | AM |  | 2024-08-05 | 2024-09-06 |  | 0 | [11 empty] | 0
1504 | 485148 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Anvil Stores | MANCHESTER | M44 5AN | 2024-08-07 | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043882 | 30017553 | 2.Commissioning |  |  | 2024-08-06 | 2024-08-06 | 2024-08-06 11:00 | TRUE |  |  |  | 2024-08-28 | [7 empty] | 0
1505 | 632820 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Tolworth News | SURBITON | KT6 7HT | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Silver Address Issue | 30017708 | 1.Provisioning | AM |  | 2024-08-06 |  |  | 0 | [11 empty] | 0
1506 | 469817 |  | Batch 6 Aug 24 | Type 1 | KCOM/Mobile | Todays Local | HULL | HU8 9QA | 2024-09-03 | 6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 PM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 PM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 PM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 PM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 PM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 PM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 PM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 PM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 PM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 PM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 PM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 PM _x000D_19/8/2024:01592322 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 PM _x000D_6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 PM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 PM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 PM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 PM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 PM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 PM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 PM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 PM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 PM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 PM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 PM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 PM _x000D_19/8/2024:01592322 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - Allwyn confirmed Retailer has agreed to installation on 02/09 PM |  |  |  |  | 2.Allwyn to arrange access | BUS0004474 | 30017254 | 2.Commissioning | AM | 2024-08-13 | 2024-08-13 |  |  | 0 | [11 empty] | 0
1507 | 641159 |  | Batch 6 Aug 24 | Type 1 | KCOM/Mobile | Booze Blitz | HULL | HU6 8AG | 2024-07-11 | 6/9/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_5/9/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_4/9/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_3/9/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_2/9/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_29/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_28/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_27/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_22/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_21/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_20/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_19/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_19/8/2024:01583504 _x000D_16/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_15/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_14/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_0 | 9/9/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_6/9/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_5/9/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_4/9/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_3/9/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_2/9/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_29/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_28/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_27/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_22/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_21/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_20/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_19/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_19/8/2024:01583504 _x000D_16/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_15/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_14/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_0 | 0 | #Update - Action for Allwyn - Installation has been committed by KCOM for 29/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 29/08 is a suitable date. |  |  |  |  | 2.Allwyn to arrange access | BUS0004464 | 30017285 | 1.Provisioning | AM | 2024-08-09 | 2024-08-29 | 2024-08-29 |  | 0 | [11 empty] | 0
1508 | 482377 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Spar Stores | LIVERPOOL | L37 7DJ | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:31 _x000D_26/7/2024:22/07/2024 10:31 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:31 _x000D_26/7/2024:22/07/2024 10:31 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2422346 | 30021840 | 1.Provisioning | AM |  | 2024-08-06 | 2024-09-06 |  | 0 | [11 empty] | 0
1509 | 656407 |  | Batch 6 Aug 24 | Type 1 | KCOM/Mobile | Riversdale Convenience Store | HULL | HU6 7EY | 2024-07-11 | 6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/09 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/09 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/09 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/09 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/09 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/09 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/09 AM _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/09 AM _x000D_6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/09 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/09 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/09 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/09 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/09 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/09 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 12/09 AM _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - Allwyn confirmed Retailer has agreed to installation on 12/09 AM |  |  |  |  | 2.Allwyn to arrange access | BUS0004465 | 30017247 | 1.Provisioning | AM | 2024-08-09 | 2024-08-09 |  |  | 0 | [11 empty] | 0
1510 | 481045 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Londis Supermarket | FELTHAM | TW13 4HT | 2024-09-05 | 6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:Update: Order Amended _x000D_28/8/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the order. Please check with end user and reappoint the order if still required. _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 19-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 19-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_17/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 19-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:Update: Order Amended _x000D_28/8/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the order. Please check with end user and reappoint the order if still required. _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 19-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 19-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_17/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 19-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | Order Completed | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2422441 | 30017355 | 2.Commissioning | AM |  | 2024-08-06 | 2024-08-27 |  | 0 | [11 empty] | 0
1511 | 424602 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Budgens | FAIRFORD | GL7 4AH | 2024-08-07 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:End User Missed appointment. Action required _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 19-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_23/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 19-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 19-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 19-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:End User Missed appointment. Action required _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 19-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_23/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 19-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 19-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 19-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_0 | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFS1056985 | 30017327 | 1.Provisioning | AM |  | 2024-08-06 | 2024-09-23 |  | 0 | [11 empty] | 0
1512 | 635386 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Iriana Convenience Store | NEWCASTLE UPON TYNE | NE4 7EH | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:03 _x000D_26/7/2024:22/07/2024 10:03 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:03 _x000D_26/7/2024:22/07/2024 10:03 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2422440 | 30017336 | 1.Provisioning | AM |  | 2024-08-06 | 2024-09-06 |  | 0 | [11 empty] | 0
1513 | 660505 |  | Batch 6 Aug 24 | Type 1 | KCOM/Mobile | Bargain Beers | HULL | HU6 9QA | 2024-09-06 | 6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_19/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 04/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 04/09 is a suitable date. _x000D_19/8/2024:01592287 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM _x000D_19/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 04/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 04/09 is a suitable date. _x000D_19/8/2024:01592287 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - Allwyn confirmed Retailer has agreed to installation on 04/09 AM |  |  |  |  | 2.Allwyn to arrange access | BUS0004470 | 30017256 | 2.Commissioning | AM | 2024-08-12 | 2024-08-12 |  |  | 0 | [11 empty] | 0
1514 | 467137 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Lucky Supermarket | LEICESTER | LE3 0RA | 2024-08-07 | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:Update: Order Completed by Supplier _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:Update: Order Completed by Supplier _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2422439 | 30017302 | 6.Failed router install |  |  | 2024-08-06 | 2024-08-06 | 2024-08-06 10:09 | TRUE |  |  |  | 2024-08-23 |  |  |  | 2024-08-23 | 237004907560 | 237004907560 | 2024-08-27 | 1
1515 | 264758 |  | Batch 6 Aug 24 | Type 1 | KCOM/Mobile | Rispins Foodmarket | HULL | HU5 5RS | 2024-07-11 | 6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 13/09 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 13/09 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 13/09 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 13/09 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 13/09 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 13/09 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 13/09 AM _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 13/09 AM _x000D_6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 13/09 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 13/09 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 13/09 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 13/09 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 13/09 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 13/09 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 13/09 AM _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - Allwyn confirmed Retailer has agreed to installation on 13/09 AM |  |  |  |  | 2.Allwyn to arrange access | BUS0004466 | 30017255 | 1.Provisioning | AM | 2024-08-09 | 2024-08-09 |  |  | 0 | [11 empty] | 0
1516 | 632863 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | News Brunels Food | HAVANT | PO9 1QD | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Silver Address Issue | 30021811 | 1.Provisioning | AM |  | 2024-08-06 |  |  | 0 | [11 empty] | 0
1517 | 444562 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Centra Farm & Tackle Shop | NEWTOWNARDS | BT22 1HR | 2024-08-07 | 6/9/2024:#Update - The order has now been cancelled as the site survey charge was not approved in time. Please confirm if/when you wish to re-raise and the charge has been accepted. _x000D_5/9/2024:#Update - The order has now been cancelled as the site survey charge was not approved in time. Please confirm if/when you wish to re-raise and the charge has been accepted. _x000D_4/9/2024:#Update - The order has now been cancelled as the site survey charge was not approved in time. Please confirm if/when you wish to re-raise and the charge has been accepted. _x000D_3/9/2024:#Update - The order has now been cancelled as the site survey charge was not approved in time. Please confirm if/when you wish to re-raise and the charge has been accepted. _x000D_2/9/2024:#Update - The order has now been cancelled as the site survey charge was not approved in time. Please confirm if/when you wish to re-raise and the charge has been accepted. _x000D_29/8/2024:#Update - The order has now been cancelled as the site survey charge was not approved in time. Please confirm if/when you wish to re-raise and the charge has been accepted. _x000D_28/8/2024:#Update - The order has now been cancelled as the site survey charge was not approved in time. Please confirm if/when you wish to re-raise and the charge has been accepted. _x000D_27/8/2024:#Update - The order has now been cancelled as the site survey charge was not approved in time. Please confirm if/when you wish to re-raise and the charge has been accepted. _x000D_22/8/2024:#Update - Order has been delayed due to network planning. CSL will update as more information become available. _x000D_21/8/2024:#Update - Order has been delayed due to network planning. CSL will update as more information become available. _x000D_20/8/2024:#Update - Order has been delayed due to network planning. CSL will update as more information become available. _x000D_19/8/2024:#Update - Order has been delayed due to network planning. CSL will update as more information become available. _x000D_19/8/2024:01563907 _x000D_16/8/2024:#Update - Order has been delayed due to network planning. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order has been delayed due to network planning. CSL will update as more information become available. _x000D_14/8/2024:#Update - Order has been delayed due to network planning. CSL will update as more information become available. _x000D_13/8/2024:#Update - Order has been delayed due to network planning. CSL will update as more information become available. _x000D_12/8/2024:#Update - Order has been delayed due to network planning. CSL will update as more information become available. _x000D_9/8/2024:#Update - Order has been delayed due to network planning. CSL will update as more information become available. _x000D_8/8/2024:06/08/2024 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - The order has now been cancelled as the site survey charge was not approved in time. Please confirm if/when you wish to re-raise and the charge has been accepted. _x000D_6/9/2024:#Update - The order has now been cancelled as the site survey charge was not approved in time. Please confirm if/when you wish to re-raise and the charge has been accepted. _x000D_5/9/2024:#Update - The order has now been cancelled as the site survey charge was not approved in time. Please confirm if/when you wish to re-raise and the charge has been accepted. _x000D_4/9/2024:#Update - The order has now been cancelled as the site survey charge was not approved in time. Please confirm if/when you wish to re-raise and the charge has been accepted. _x000D_3/9/2024:#Update - The order has now been cancelled as the site survey charge was not approved in time. Please confirm if/when you wish to re-raise and the charge has been accepted. _x000D_2/9/2024:#Update - The order has now been cancelled as the site survey charge was not approved in time. Please confirm if/when you wish to re-raise and the charge has been accepted. _x000D_29/8/2024:#Update - The order has now been cancelled as the site survey charge was not approved in time. Please confirm if/when you wish to re-raise and the charge has been accepted. _x000D_28/8/2024:#Update - The order has now been cancelled as the site survey charge was not approved in time. Please confirm if/when you wish to re-raise and the charge has been accepted. _x000D_27/8/2024:#Update - The order has now been cancelled as the site survey charge was not approved in time. Please confirm if/when you wish to re-raise and the charge has been accepted. _x000D_22/8/2024:#Update - Order has been delayed due to network planning. CSL will update as more information become available. _x000D_21/8/2024:#Update - Order has been delayed due to network planning. CSL will update as more information become available. _x000D_20/8/2024:#Update - Order has been delayed due to network planning. CSL will update as more information become available. _x000D_19/8/2024:#Update - Order has been delayed due to network planning. CSL will update as more information become available. _x000D_19/8/2024:01563907 _x000D_16/8/2024:#Update - Order has been delayed due to network planning. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order has been delayed due to network planning. CSL will update as more information become available. _x000D_14/8/2024:#Update - Order has been delayed due to network planning. CSL will update as more information become available. _x000D_13/8/2024:#Update - Order has been delayed due to network planning. CSL will update as more information become available. _x000D_12/8/2024:#Update - Order has been delayed due to network planning. CSL will update as more information become available. _x000D_9/8/2024:#Update - Order has been delayed due to network planning. CSL will update as more information become available. _x000D_8/8/2024:06/08/2024 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - The order has now been cancelled as the site survey charge was not approved in time. Please confirm if/when you wish to re-raise and the charge has been accepted. |  |  |  |  | 2.Allwyn to arrange access | VFP2423334 | 30017494 | 1.Provisioning | AM |  | 2024-08-06 | 2024-08-06 |  | 0 | [11 empty] | 0
1518 | 630196 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Costcutter Supermarket | LONDON | SE16 2BE | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:24 _x000D_26/7/2024:22/07/2024 10:24 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:24 _x000D_26/7/2024:22/07/2024 10:24 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2421557 | 30017774 | 1.Provisioning | AM |  | 2024-08-08 | 2024-09-06 |  | 0 | [11 empty] | 0
1519 | 655539 |  | Batch 6 Aug 24 | Type 1 | KCOM/Mobile | Stepney News | HULL | HU3 1UP | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | bus0004443 | 30017279 | 1.Provisioning | AM | 2024-08-06 | 2024-08-06 |  |  | 0 | [11 empty] | 0
1520 | 665300 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Post Office | SOUTHAMPTON | SO30 4QU | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:Order Completed _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:End User Missed appointment. Action required _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:Order Completed _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:End User Missed appointment. Action required _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 3.Allwyn to arrange rtr install | VFS1043872 | 30017477 | 2.Commissioning | AM |  | 2024-08-07 | 2024-08-22 |  | 0 | [11 empty] | 0
1521 | 632480 |  | Batch 6 Aug 24 | Type 1 | KCOM/Mobile | M & M's | HULL | HU9 2RD | 2024-09-05 | 6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 AM _x000D_29/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 03/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 03/09 is a suitable date. _x000D_28/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 03/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 03/09 is a suitable date. _x000D_27/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 03/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 03/09 is a suitable date. _x000D_22/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 03/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 03/09 is a suitable date. _x000D_21/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 03/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 03/09 is a suitable date. _x000D_20/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 03/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 03/09 is a suitable date. _x000D_19/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 03/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 03/09 is a suitable date. _x000D_19/8/2024:01592422 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 AM _x000D_6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 AM _x000D_29/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 03/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 03/09 is a suitable date. _x000D_28/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 03/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 03/09 is a suitable date. _x000D_27/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 03/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 03/09 is a suitable date. _x000D_22/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 03/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 03/09 is a suitable date. _x000D_21/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 03/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 03/09 is a suitable date. _x000D_20/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 03/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 03/09 is a suitable date. _x000D_19/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 03/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 03/09 is a suitable date. _x000D_19/8/2024:01592422 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - Allwyn confirmed Retailer has agreed to installation on 03/09 AM |  |  |  |  | 2.Allwyn to arrange access | BUS0004485 | 30017260 | 2.Commissioning | AM | 2024-08-14 | 2024-08-14 |  |  | 0 | [11 empty] | 0
1522 | 425886 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Premier | CREWE | CW2 7EZ | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_14/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_13/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_12/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_9/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_8/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_14/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_13/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_12/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_9/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_8/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFS1043874 | 30017487 | 1.Provisioning | AM |  | 2024-08-07 | 2024-09-19 |  | 0 | [11 empty] | 0
1523 | 632647 |  | Batch 6 Aug 24 | Type 1 | KCOM/Mobile | Nisa | HULL | HU3 3DN | 2024-07-11 | 6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 PM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 PM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 PM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 PM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 PM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 PM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 PM _x000D_27/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 27/08 PM. Please speak with the retailer regarding installation details and confirm to CSL if 27/08 is a suitable date. _x000D_22/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 27/08 PM. Please speak with the retailer regarding installation details and confirm to CSL if 27/08 is a suitable date. _x000D_21/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 27/08 PM. Please speak with the retailer regarding installation details and confirm to CSL if 27/08 is a suitable date. _x000D_20/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 27/08 PM. Please speak with the retailer regarding installation details and confirm to CSL if 27/08 is a suitable date. _x000D_19/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 27/08 PM. Please speak with the retailer regarding installation details and confirm to CSL if 27/08 is a suitable date. _x000D_19/8/2024:01579371 _x000D_16/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 27/08 PM. Please speak with the retailer regarding installation details and confirm to CSL if 27/08 is a suitable date. _x000D_15/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 27/08 PM. Please speak with the retailer regarding installation details and confirm to CSL if 27/08 is a suitable date. _x000D_14/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 27/08 PM. Please speak with the retailer regarding installation details and confirm to CSL if 27/08 is a suitable date. _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 PM _x000D_6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 PM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 PM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 PM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 PM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 PM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 PM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 09/09 PM _x000D_27/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 27/08 PM. Please speak with the retailer regarding installation details and confirm to CSL if 27/08 is a suitable date. _x000D_22/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 27/08 PM. Please speak with the retailer regarding installation details and confirm to CSL if 27/08 is a suitable date. _x000D_21/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 27/08 PM. Please speak with the retailer regarding installation details and confirm to CSL if 27/08 is a suitable date. _x000D_20/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 27/08 PM. Please speak with the retailer regarding installation details and confirm to CSL if 27/08 is a suitable date. _x000D_19/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 27/08 PM. Please speak with the retailer regarding installation details and confirm to CSL if 27/08 is a suitable date. _x000D_19/8/2024:01579371 _x000D_16/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 27/08 PM. Please speak with the retailer regarding installation details and confirm to CSL if 27/08 is a suitable date. _x000D_15/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 27/08 PM. Please speak with the retailer regarding installation details and confirm to CSL if 27/08 is a suitable date. _x000D_14/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 27/08 PM. Please speak with the retailer regarding installation details and confirm to CSL if 27/08 is a suitable date. _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - Allwyn confirmed Retailer has agreed to installation on 09/09 PM |  |  |  |  | 2.Allwyn to arrange access | BUS0004501 | 30017265 | 1.Provisioning | PM | 2024-08-06 | 2024-08-27 | 2024-08-27 |  | 0 | [11 empty] | 0
1524 | 666819 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Post Office | WOLVERHAMPTON | WV6 8AE | 2024-08-08 | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043871 | 30017478 | 2.Commissioning |  |  | 2024-08-07 | 2024-08-07 | 2024-08-07 09:57 | TRUE |  |  |  | 2024-08-28 | [7 empty] | 0
1525 | 601890 |  | Batch 6 Aug 24 | Type 1 | SURE/Mobile | Spar | ISLE OF MAN | IM1 3AF | 2024-07-11 | 6/9/2024:#Update Retailer confirmed 04/09 _x000D_5/9/2024:#Update Retailer confirmed 04/09 _x000D_4/9/2024:#Update Retailer confirmed 04/09 _x000D_3/9/2024:#Update Retailer confirmed 04/09 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update Retailer confirmed 04/09 _x000D_6/9/2024:#Update Retailer confirmed 04/09 _x000D_5/9/2024:#Update Retailer confirmed 04/09 _x000D_4/9/2024:#Update Retailer confirmed 04/09 _x000D_3/9/2024:#Update Retailer confirmed 04/09 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update Retailer confirmed 04/09 |  |  |  |  | 2.Allwyn to arrange access | FPSU010360 | 30017262 | 1.Provisioning | AM |  | 2024-08-07 |  |  | 0 | [11 empty] | 0
1526 | 647032 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Standard News Newsagents and Off Li | COVENTRY | CV6 5FJ | 2024-07-11 | 6/9/2024:#Update - NFA - Allwyn confirmed rescheduled install date of 06/09 and scaffolding will be down by this date _x000D_5/9/2024:#Update - NFA - Allwyn confirmed rescheduled install date of 06/09 and scaffolding will be down by this date _x000D_4/9/2024:#Update - NFA - Allwyn confirmed rescheduled install date of 06/09 and scaffolding will be down by this date _x000D_3/9/2024:#Update - NFA - Allwyn confirmed rescheduled install date of 06/09 and scaffolding will be down by this date _x000D_2/9/2024:#Update - NFA - Allwyn confirmed rescheduled install date of 06/09 and scaffolding will be down by this date _x000D_29/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date of 06/09 and scaffolding will be down by this date _x000D_28/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date of 06/09 and scaffolding will be down by this date _x000D_27/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date of 06/09 and scaffolding will be down by this date _x000D_22/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date of 06/09 and scaffolding will be down by this date _x000D_21/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date of 06/09 and scaffolding will be down by this date _x000D_20/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date of 06/09 and scaffolding will be down by this date _x000D_19/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date of 06/09 and scaffolding will be down by this date _x000D_19/8/2024:01566038 _x000D_16/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date of 06/09 and scaffolding will be down by this date _x000D_15/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date of 06/09 and scaffolding will be down by this date _x000D_14/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date of 06/09 and scaffolding will be down by this date _x000D_13/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date of 06/09 and scaffolding will be down by this date _x000D_12/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date of 06/09 and scaffolding will be down by this date _x000D_9/8/2024:#Update - unsuccessful install due to scaffolding hazard around building _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - NFA - Allwyn confirmed rescheduled install date of 06/09 and scaffolding will be down by this date _x000D_6/9/2024:#Update - NFA - Allwyn confirmed rescheduled install date of 06/09 and scaffolding will be down by this date _x000D_5/9/2024:#Update - NFA - Allwyn confirmed rescheduled install date of 06/09 and scaffolding will be down by this date _x000D_4/9/2024:#Update - NFA - Allwyn confirmed rescheduled install date of 06/09 and scaffolding will be down by this date _x000D_3/9/2024:#Update - NFA - Allwyn confirmed rescheduled install date of 06/09 and scaffolding will be down by this date _x000D_2/9/2024:#Update - NFA - Allwyn confirmed rescheduled install date of 06/09 and scaffolding will be down by this date _x000D_29/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date of 06/09 and scaffolding will be down by this date _x000D_28/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date of 06/09 and scaffolding will be down by this date _x000D_27/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date of 06/09 and scaffolding will be down by this date _x000D_22/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date of 06/09 and scaffolding will be down by this date _x000D_21/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date of 06/09 and scaffolding will be down by this date _x000D_20/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date of 06/09 and scaffolding will be down by this date _x000D_19/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date of 06/09 and scaffolding will be down by this date _x000D_19/8/2024:01566038 _x000D_16/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date of 06/09 and scaffolding will be down by this date _x000D_15/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date of 06/09 and scaffolding will be down by this date _x000D_14/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date of 06/09 and scaffolding will be down by this date _x000D_13/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date of 06/09 and scaffolding will be down by this date _x000D_12/8/2024:#Update - NFA - Allwyn confirmed rescheduled install date of 06/09 and scaffolding will be down by this date _x000D_9/8/2024:#Update - unsuccessful install due to scaffolding hazard around building _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - NFA - Allwyn confirmed rescheduled install date of 06/09 and scaffolding will be down by this date |  |  |  |  | 2.Allwyn to arrange access | VFP2422436 | 30017362 | 1.Provisioning | AM |  | 2024-08-07 | 2024-09-06 |  | 0 | [11 empty] | 0
1527 | 646008 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Fags & Mags | UPMINSTER | RM14 1DZ | 2024-08-08 | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043867 | 30017547 | 6.Failed router install |  |  | 2024-08-07 | 2024-08-07 | 2024-08-07 11:04 | TRUE |  |  |  | 2024-08-28 |  |  |  | 2024-08-28 | 242005011096 | 242005011096 | 2024-08-29 | 1
1528 | 472069 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Premier Stores | PONTEFRACT | WF9 3AB | 2024-07-11 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_14/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_13/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_12/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_9/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_0 | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_14/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_13/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_12/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_9/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_0 | Update: Order Amended | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2422004 | 30017722 | 1.Provisioning | AM |  | 2024-08-07 | 2024-09-05 |  | 0 | [11 empty] | 0
1529 | 426847 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | One O One Wine Merchant | GLASGOW | G3 6TH | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Silver Address Issue | 30021810 | 1.Provisioning | AM |  | 2024-08-07 |  |  | 0 | [11 empty] | 0
1530 | 607614 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Nisa Local | LEVEN | KY8 4EU | 2024-08-08 | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1057028 | 30017373 | 2.Commissioning |  |  | 2024-08-07 | 2024-08-07 | 2024-08-07 09:30 | TRUE |  |  |  | 2024-09-11 | [7 empty] | 0
1531 | 644177 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Beaconsfield Convenience Store | NEWCASTLE UPON TYNE | NE4 5JN | 2024-08-08 | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFP2422435 | 30017292 | 6.Failed router install |  |  | 2024-08-07 | 2024-08-07 | 2024-08-07 13:08 | TRUE |  |  |  | 2024-08-29 |  |  |  | 2024-08-29 | 242005008923 | 242005008923 | 2024-08-30 | 1
1532 | 455050 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Spar Stores | COLERAINE | BT51 3AS | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Silver Address Issue | 30017683 | 1.Provisioning | AM |  | 2024-08-07 |  |  | 0 | [11 empty] | 0
1533 | 637693 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Muxton Price Point | TELFORD | TF2 8JQ | 2024-08-08 | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1057053 | 30017344 | 6.Failed router install |  |  | 2024-08-07 | 2024-08-07 | 2024-08-07 14:50 | TRUE |  |  |  | 2024-08-28 |  |  |  | 2024-08-28 | 23A004948717 | 23A004948717 | 2024-08-29 | 1
1534 | 663268 |  | Batch 6 Aug 24 | Type 1 | KCOM/Mobile | Nisa | HULL | HU8 8TY | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | BUS0004475 | 30017235 | 1.Provisioning | AM | 2024-08-13 | 2024-08-13 |  |  | 0 | [11 empty] | 0
1535 | 660571 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Go Local Extra M & S Superstore | SALFORD | M6 8DA | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:Update: Order Amended _x000D_28/8/2024:Update: Order Amended _x000D_27/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_14/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_13/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_12/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_9/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:Update: Order Amended _x000D_28/8/2024:Update: Order Amended _x000D_27/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_14/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_13/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_12/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_9/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2422434 | 30017320 | 1.Provisioning | AM |  | 2024-08-07 | 2024-08-22 |  | 0 | [11 empty] | 0
1536 | 644101 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Spar | FOCHABERS | IV32 7JS | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Address query | 30017711 | 1.Provisioning | AM |  | 2024-08-07 |  |  | 0 | [11 empty] | 0
1537 | 609175 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | High Oaks News | ST. ALBANS | AL3 6DL | 2024-08-08 | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/8/2024:Order Completed _x000D_8/8/2024:Order Completed _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043868 | 30017572 | 2.Commissioning |  |  | 2024-08-07 | 2024-08-07 | 2024-08-07 08:32 | TRUE |  |  |  | 2024-08-30 | [7 empty] | 0
1538 | 654481 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Nisa Local | GLASGOW | G72 7HB | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Silver Address Issue | 30017724 | 1.Provisioning | AM |  | 2024-08-07 |  |  | 0 | [11 empty] | 0
1539 | 448266 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Best One | LIVERPOOL | L19 8EJ | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:25 _x000D_26/7/2024:22/07/2024 10:25 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:25 _x000D_26/7/2024:22/07/2024 10:25 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2421531 | 30017701 | 1.Provisioning | AM |  | 2024-09-06 | 2024-09-06 |  | 0 | [11 empty] | 0
1540 | 646143 |  | Batch 6 Aug 24 | Type 1 | KCOM/Mobile | Budgens Supermarket | HULL | HU3 1BH | 2024-07-11 | 6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_19/8/2024:01579236 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_18/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_19/8/2024:01579236 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_18/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - Allwyn confirmed Retailer has agreed to installation on 23/08 AM |  |  |  |  | 2.Allwyn to arrange access | BUS0004442 | 30017231 | 2.Commissioning | AM | 2024-08-05 | 2024-08-23 | 2024-08-23 |  | 0 | [11 empty] | 0
1541 | 629619 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Rishins | LONDON | N10 1LR | 2024-07-11 | 6/9/2024:#Update - NFA - retailer confirmed new installation date 27/09 with retailer _x000D_5/9/2024:#Update - NFA - retailer confirmed new installation date 27/09 with retailer _x000D_4/9/2024:#Update - NFA - retailer confirmed new installation date 27/09 with retailer _x000D_3/9/2024:#Update - NFA - retailer confirmed new installation date 27/09 with retailer _x000D_2/9/2024:#Update - NFA - retailer confirmed new installation date 27/09 with retailer _x000D_29/8/2024:#Update - NFA - retailer confirmed new installation date 27/09 with retailer _x000D_28/8/2024:#Update - NFA - retailer confirmed new installation date 27/09 with retailer _x000D_27/8/2024:#Update - NFA - retailer confirmed new installation date 27/09 with retailer _x000D_22/8/2024:#Update - NFA - retailer confirmed new installation date 27/09 with retailer _x000D_21/8/2024:#Update - NFA - retailer confirmed new installation date 27/09 with retailer _x000D_20/8/2024:#Update - NFA - retailer confirmed new installation date 27/09 with retailer _x000D_19/8/2024:#Update - NFA - retailer confirmed new installation date 27/09 with retailer _x000D_19/8/2024:01569557 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_8/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_23/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_22/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_22/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - NFA - retailer confirmed new installation date 27/09 with retailer _x000D_6/9/2024:#Update - NFA - retailer confirmed new installation date 27/09 with retailer _x000D_5/9/2024:#Update - NFA - retailer confirmed new installation date 27/09 with retailer _x000D_4/9/2024:#Update - NFA - retailer confirmed new installation date 27/09 with retailer _x000D_3/9/2024:#Update - NFA - retailer confirmed new installation date 27/09 with retailer _x000D_2/9/2024:#Update - NFA - retailer confirmed new installation date 27/09 with retailer _x000D_29/8/2024:#Update - NFA - retailer confirmed new installation date 27/09 with retailer _x000D_28/8/2024:#Update - NFA - retailer confirmed new installation date 27/09 with retailer _x000D_27/8/2024:#Update - NFA - retailer confirmed new installation date 27/09 with retailer _x000D_22/8/2024:#Update - NFA - retailer confirmed new installation date 27/09 with retailer _x000D_21/8/2024:#Update - NFA - retailer confirmed new installation date 27/09 with retailer _x000D_20/8/2024:#Update - NFA - retailer confirmed new installation date 27/09 with retailer _x000D_19/8/2024:#Update - NFA - retailer confirmed new installation date 27/09 with retailer _x000D_19/8/2024:01569557 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_8/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_23/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_22/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_22/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - NFA - retailer confirmed new installation date 27/09 with retailer |  |  |  |  | 2.Allwyn to arrange access | VFS1054988 | 30017729 | 1.Provisioning | AM |  | 2024-08-08 | 2024-08-27 |  | 0 | [11 empty] | 0
1542 | 601652 |  | Batch 6 Aug 24 | Type 1 | SURE/Mobile | Ellan Vannin Fuels | ISLE OF MAN | IM2 3QL | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | FPSU012771 | 30017258 | 1.Provisioning | AM |  | 2024-08-08 |  |  | 0 | [11 empty] | 0
1543 | 200338 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Premier Lower Darwen | DARWEN | BB3 0QE | 2024-07-11 | 6/9/2024:#Update - installation unsuccessful, unable to get access to Openreach network due to drink machines in the way. Awaiting further update from OR - may require upgrade and OOH due to busy shop, will need 2 Engineers _x000D_5/9/2024:#Update - installation unsuccessful, unable to get access to Openreach network due to drink machines in the way. Awaiting further update from OR - may require upgrade and OOH due to busy shop, will need 2 Engineers _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - installation unsuccessful, unable to get access to Openreach network due to drink machines in the way. Awaiting further update from OR - may require upgrade and OOH due to busy shop, will need 2 Engineers _x000D_6/9/2024:#Update - installation unsuccessful, unable to get access to Openreach network due to drink machines in the way. Awaiting further update from OR - may require upgrade and OOH due to busy shop, will need 2 Engineers _x000D_5/9/2024:#Update - installation unsuccessful, unable to get access to Openreach network due to drink machines in the way. Awaiting further update from OR - may require upgrade and OOH due to busy shop, will need 2 Engineers _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - installation unsuccessful, unable to get access to Openreach network due to drink machines in the way. Awaiting further update from OR - may require upgrade and OOH due to busy shop, will need 2 Engineers |  |  |  |  | 2.Allwyn to arrange access | VFS1054984 | 30017784 | 1.Provisioning | AM |  | 2024-08-08 | 2024-09-20 |  | 0 | [11 empty] | 0
1544 | 645619 |  | Batch 6 Aug 24 | Type 1 | KCOM/Mobile | Premier | HULL | HU7 4NP | 2024-09-02 | 6/9/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 30/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 30/08 is a suitable date. _x000D_5/9/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 30/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 30/08 is a suitable date. _x000D_4/9/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 30/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 30/08 is a suitable date. _x000D_3/9/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 30/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 30/08 is a suitable date. _x000D_2/9/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 30/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 30/08 is a suitable date. _x000D_29/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 30/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 30/08 is a suitable date. _x000D_28/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 30/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 30/08 is a suitable date. _x000D_27/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 30/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 30/08 is a suitable date. _x000D_22/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 30/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 30/08 is a suitable date. _x000D_21/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 30/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 30/08 is a suitable date. _x000D_20/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 30/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 30/08 is a suitable date. _x000D_19/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 30/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 30/08 is a suitable date. _x000D_19/8/2024:01583541 _x000D_16/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 30/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 30/08 is a suitable date. _x000D_15/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 30/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 30/08 is a suitable date. _x000D_14/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 30/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 30/08 is a suitable date. _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 30/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 30/08 is a suitable date. _x000D_6/9/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 30/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 30/08 is a suitable date. _x000D_5/9/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 30/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 30/08 is a suitable date. _x000D_4/9/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 30/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 30/08 is a suitable date. _x000D_3/9/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 30/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 30/08 is a suitable date. _x000D_2/9/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 30/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 30/08 is a suitable date. _x000D_29/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 30/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 30/08 is a suitable date. _x000D_28/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 30/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 30/08 is a suitable date. _x000D_27/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 30/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 30/08 is a suitable date. _x000D_22/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 30/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 30/08 is a suitable date. _x000D_21/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 30/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 30/08 is a suitable date. _x000D_20/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 30/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 30/08 is a suitable date. _x000D_19/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 30/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 30/08 is a suitable date. _x000D_19/8/2024:01583541 _x000D_16/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 30/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 30/08 is a suitable date. _x000D_15/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 30/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 30/08 is a suitable date. _x000D_14/8/2024:#Update - Action for Allwyn - Installation has been committed by KCOM for 30/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 30/08 is a suitable date. _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - Action for Allwyn - Installation has been committed by KCOM for 30/08 AM. Please speak with the retailer regarding installation details and confirm to CSL if 30/08 is a suitable date. |  |  |  |  | 2.Allwyn to arrange access | BUS0004492 | 30017238 | 2.Commissioning | AM | 2024-08-12 | 2024-08-30 | 2024-08-30 |  | 0 | [11 empty] | 0
1545 | 667273 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | A M Grieve Newsagents | MOFFAT | DG10 9HF | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Silver Address Issue | 30017705 | 1.Provisioning | AM |  | 2024-08-08 |  |  | 0 | [11 empty] | 0
1546 | 669597 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Spar Stores | RHYL | LL18 5WS | 2024-07-11 | 6/9/2024:#Update Still with Allwyn to advise. _x000D_5/9/2024:#Update Still with Allwyn to advise. _x000D_4/9/2024:#Update Still with Allwyn to advise. _x000D_3/9/2024:#Update Address query sent to VF. _x000D_2/9/2024:#Update Address query sent to VF. _x000D_29/8/2024:#Update Address query sent to VF. _x000D_28/8/2024:#Update Address query sent to VF. _x000D_27/8/2024:#Update Address query sent to VF. _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:Order Rejected: Service Incompatible for input CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Order Rejected: Service Incompatible for input CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update Still with Allwyn to advise. _x000D_6/9/2024:#Update Still with Allwyn to advise. _x000D_5/9/2024:#Update Still with Allwyn to advise. _x000D_4/9/2024:#Update Still with Allwyn to advise. _x000D_3/9/2024:#Update Address query sent to VF. _x000D_2/9/2024:#Update Address query sent to VF. _x000D_29/8/2024:#Update Address query sent to VF. _x000D_28/8/2024:#Update Address query sent to VF. _x000D_27/8/2024:#Update Address query sent to VF. _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:Order Rejected: Service Incompatible for input CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Order Rejected: Service Incompatible for input CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update Still with Allwyn to advise. |  |  |  |  | 2.Allwyn to arrange access | VFS1055429 | 30017748 | 1.Provisioning | AM |  | 2024-08-08 |  |  | 0 | [11 empty] | 0
1547 | 665832 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Post Office | PONTEFRACT | WF7 6BB | 2024-07-11 | 6/9/2024:#Update - this site is changing to a site type 3 / mobile only as per instruction from Allwyn _x000D_5/9/2024:#Update - this site is changing to a site type 3 / mobile only as per instruction from Allwyn _x000D_4/9/2024:#Update - this site is changing to a site type 3 / mobile only as per instruction from Allwyn _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - this site is changing to a site type 3 / mobile only as per instruction from Allwyn _x000D_6/9/2024:#Update - this site is changing to a site type 3 / mobile only as per instruction from Allwyn _x000D_5/9/2024:#Update - this site is changing to a site type 3 / mobile only as per instruction from Allwyn _x000D_4/9/2024:#Update - this site is changing to a site type 3 / mobile only as per instruction from Allwyn _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - this site is changing to a site type 3 / mobile only as per instruction from Allwyn |  |  |  |  | 2.Allwyn to arrange access | VFP2422428 | 30017304 | 1.Provisioning | AM |  | 2024-08-08 | 2024-09-09 |  | 0 | [11 empty] | 0
1548 | 635568 |  | Batch 6 Aug 24 | Type 1 | KCOM/Mobile | Sangha News | HULL | HU5 2TX | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_0 | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | BUS0004458 | 30017280 | 1.Provisioning | AM | 2024-08-08 | 2024-08-08 |  |  | 0 | [11 empty] | 0
1549 | 632154 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Londis Supermarket | LIVERPOOL | L11 1EQ | 2024-07-11 | 12/8/2024:Order Completed _x000D_9/8/2024:Order Completed _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 12/8/2024:Order Completed _x000D_9/8/2024:Order Completed _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFS1056378 | 30021831 | 6.Failed router install |  |  | 2024-08-08 | 2024-08-08 | 2024-08-08 11:07 | TRUE |  |  |  | 2024-08-29 |  |  |  | 2024-08-29 | 23A004948664 | 23A004948664 | 2024-08-30 | 1
1550 | 450046 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Eldon Lane W M C | BISHOP AUCKLAND | DL14 8TL | 2024-07-11 | 6/9/2024:Your order has been delayed due to a customer missed appointment. Incorrect Address Please check with end user and reappoint the order if still required. _x000D_5/9/2024:Your order has been delayed due to a customer missed appointment. Incorrect Address Please check with end user and reappoint the order if still required. _x000D_4/9/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_3/9/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_8/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_0 | 9/9/2024:Your order has been delayed due to a customer missed appointment. Incorrect Address Please check with end user and reappoint the order if still required. _x000D_6/9/2024:Your order has been delayed due to a customer missed appointment. Incorrect Address Please check with end user and reappoint the order if still required. _x000D_5/9/2024:Your order has been delayed due to a customer missed appointment. Incorrect Address Please check with end user and reappoint the order if still required. _x000D_4/9/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_3/9/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_8/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_0 | Your order has been delayed due to a customer missed appointment. Incorrect Address Please check with end user and reappoint the order if still required. | 0 |  |  |  |  | 2.Allwyn to arrange access | VFS1057001 | 30017338 | 1.Provisioning | AM |  | 2024-08-08 | 2024-09-03 |  | 0 | [11 empty] | 0
1551 | 660079 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Stars News Shops Ltd | BIRMINGHAM | B23 6SR | 2024-07-11 | 6/9/2024:#Update - Your order has been delayed. Dig work required. Further updates to follow _x000D_5/9/2024:#Update - Your order has been delayed. Dig work required. Further updates to follow _x000D_4/9/2024:#Update - Your order has been delayed. Dig work required. Further updates to follow _x000D_3/9/2024:#Update - Your order has been delayed. Dig work required. Further updates to follow _x000D_2/9/2024:#Update - Your order has been delayed. Dig work required. Further updates to follow _x000D_29/8/2024:#Update - Your order has been delayed. Dig work required. Further updates to follow _x000D_28/8/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 02/09/2024. We will continue to provide update as they become available. _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:Update: Order Amended _x000D_19/8/2024:Update: Order Amended _x000D_19/8/2024:16/08/2024 06:29 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Informational - External visit has been completed _x000D_14/8/2024:Informational - External visit has been completed _x000D_13/8/2024:Informational - External visit has been completed _x000D_12/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 03/09/2024. We will continue to provide update as they become available. _x000D_9/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 03/09/2024. We will continue to provide update as they become available. _x000D_8/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 03/09/2024. We will continue to provide update as they become available. _x000D_6/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 08/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 08/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_2/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 08/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_1/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 08/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 08/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:37870 _x000D_30/7/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 31/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 31/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:25/07/2024 15:45 _x000D_26/7/2024:25/07/2024 15:45 _x000D_24/7/2024:Supplier Delay: Issues with provision of the underground network, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_23/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:Your order has been delayed. TAM pair allocation required. Our Suppliers have given us a review date of 08/08/2024. We will continue to provide update as they become available. _x000D_18/7/2024:Your order has been delayed. TAM pair allocation required. Our Suppliers have given us a review date of 08/08/2024. We will continue to provide update as they become available. _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Your order has been delayed. Dig work required. Further updates to follow _x000D_6/9/2024:#Update - Your order has been delayed. Dig work required. Further updates to follow _x000D_5/9/2024:#Update - Your order has been delayed. Dig work required. Further updates to follow _x000D_4/9/2024:#Update - Your order has been delayed. Dig work required. Further updates to follow _x000D_3/9/2024:#Update - Your order has been delayed. Dig work required. Further updates to follow _x000D_2/9/2024:#Update - Your order has been delayed. Dig work required. Further updates to follow _x000D_29/8/2024:#Update - Your order has been delayed. Dig work required. Further updates to follow _x000D_28/8/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 02/09/2024. We will continue to provide update as they become available. _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:Update: Order Amended _x000D_19/8/2024:Update: Order Amended _x000D_19/8/2024:16/08/2024 06:29 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Informational - External visit has been completed _x000D_14/8/2024:Informational - External visit has been completed _x000D_13/8/2024:Informational - External visit has been completed _x000D_12/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 03/09/2024. We will continue to provide update as they become available. _x000D_9/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 03/09/2024. We will continue to provide update as they become available. _x000D_8/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 03/09/2024. We will continue to provide update as they become available. _x000D_6/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 08/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 08/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_2/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 08/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_1/8/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 08/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:Your order has been delayed. Civil work required. Our Suppliers have given us a review date of 08/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:37870 _x000D_30/7/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 31/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 31/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:25/07/2024 15:45 _x000D_26/7/2024:25/07/2024 15:45 _x000D_24/7/2024:Supplier Delay: Issues with provision of the underground network, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_23/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:Your order has been delayed. TAM pair allocation required. Our Suppliers have given us a review date of 08/08/2024. We will continue to provide update as they become available. _x000D_18/7/2024:Your order has been delayed. TAM pair allocation required. Our Suppliers have given us a review date of 08/08/2024. We will continue to provide update as they become available. _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 09/09/2024. We will continue to provide update as they become available. | #Update - Your order has been delayed. Dig work required. Further updates to follow |  |  |  |  | 2.Allwyn to arrange access | VFP2422326 | 30021841 | 1.Provisioning | AM |  | 2024-09-16 | 2024-09-16 |  | 0 | [11 empty] | 0
1552 | 635783 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | The Corner Shop | PLYMOUTH | PL1 4AW | 2024-07-11 | 12/8/2024:Order Completed _x000D_9/8/2024:Order Completed _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Your order has been delayed. TAM pair allocation required. Our Suppliers have given us a review date of 08/08/2024. We will continue to provide update as they become available. _x000D_23/7/2024:Your order has been delayed. TAM pair allocation required. Our Suppliers have given us a review date of 08/08/2024. We will continue to provide update as they become available. _x000D_22/7/2024:Your order has been delayed. TAM pair allocation required. Our Suppliers have given us a review date of 08/08/2024. We will continue to provide update as they become available. _x000D_22/7/2024:Your order has been delayed. TAM pair allocation required. Our Suppliers have given us a review date of 08/08/2024. We will continue to provide update as they become available. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 12/8/2024:Order Completed _x000D_9/8/2024:Order Completed _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Your order has been delayed. TAM pair allocation required. Our Suppliers have given us a review date of 08/08/2024. We will continue to provide update as they become available. _x000D_23/7/2024:Your order has been delayed. TAM pair allocation required. Our Suppliers have given us a review date of 08/08/2024. We will continue to provide update as they become available. _x000D_22/7/2024:Your order has been delayed. TAM pair allocation required. Our Suppliers have given us a review date of 08/08/2024. We will continue to provide update as they become available. _x000D_22/7/2024:Your order has been delayed. TAM pair allocation required. Our Suppliers have given us a review date of 08/08/2024. We will continue to provide update as they become available. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFS1054973 | 30017687 | 2.Commissioning |  |  | 2024-08-08 | 2024-08-08 | 2024-08-08 11:54 | TRUE |  |  |  | 2024-09-04 | [7 empty] | 0
1553 | 624886 |  | Batch 6 Aug 24 | Type 1 | KCOM/Mobile | Premier | HULL | HU3 6RE | 2024-08-28 | 6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 PM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 PM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 PM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 PM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 PM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 PM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 PM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 PM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 PM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 PM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 PM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 PM _x000D_19/8/2024:01579402 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 PM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 PM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 PM _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 PM _x000D_6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 PM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 PM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 PM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 PM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 PM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 PM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 PM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 PM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 PM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 PM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 PM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 PM _x000D_19/8/2024:01579402 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 PM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 PM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 27/08 PM _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - Allwyn confirmed Retailer has agreed to installation on 27/08 PM |  |  |  |  | 2.Allwyn to arrange access | BUS0004454 | 30017257 | 2.Commissioning | PM | 2024-08-07 | 2024-08-27 | 2024-08-27 |  | 0 | [11 empty] | 0
1554 | 460062 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Wilsons | LEICESTER | LE7 7NL | 2024-07-11 | 6/9/2024:#Update - order is delayed as line plant planning work is required. This has been sent to the engineers to review. We will continue to provide update as they become available. _x000D_5/9/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_8/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:Informational: The survey phase is now complete. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:Informational: The survey phase is now complete. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:23/07/2024 07:18 _x000D_26/7/2024:23/07/2024 07:18 _x000D_24/7/2024:Informational: The survey phase is now complete. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_23/7/2024:Informational: The survey phase is now complete. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Informational: The survey phase is now complete. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 22/07/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment slot received _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - order is delayed as line plant planning work is required. This has been sent to the engineers to review. We will continue to provide update as they become available. _x000D_6/9/2024:#Update - order is delayed as line plant planning work is required. This has been sent to the engineers to review. We will continue to provide update as they become available. _x000D_5/9/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_8/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:Informational: The survey phase is now complete. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:Informational: The survey phase is now complete. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:23/07/2024 07:18 _x000D_26/7/2024:23/07/2024 07:18 _x000D_24/7/2024:Informational: The survey phase is now complete. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_23/7/2024:Informational: The survey phase is now complete. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Informational: The survey phase is now complete. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 22/07/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment slot received _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | Informational: The survey phase is now complete. | #Update - order is delayed as line plant planning work is required. This has been sent to the engineers to review. We will continue to provide update as they become available. |  |  |  |  | 2.Allwyn to arrange access | VFS1054811 | 30021814 | 1.Provisioning | AM |  | 2024-08-08 | 2024-09-04 |  | 0 | [11 empty] | 0
1555 | 437565 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | PREMIER FESTIVAL STORES | SHIPLEY | BD18 2HX | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:01 _x000D_26/7/2024:22/07/2024 10:01 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:Update: Order Amended _x000D_29/7/2024:22/07/2024 10:01 _x000D_26/7/2024:22/07/2024 10:01 _x000D_24/7/2024:Update: Order Amended _x000D_23/7/2024:Update: Order Amended _x000D_22/7/2024:Update: Order Amended _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2422427 | 30017361 | 1.Provisioning | AM |  | 2024-08-08 | 2024-09-06 |  | 0 | [11 empty] | 0
1556 | 456568 |  | Batch 6 Aug 24 | Type 1 | KCOM/Mobile | Chanterlands Service Station | HULL | HU5 4DH | 2024-08-29 | 6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_19/8/2024:01579438 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_13/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_19/8/2024:01579438 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_13/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - Allwyn confirmed Retailer has agreed to installation on 28/08 PM |  |  |  |  | 2.Allwyn to arrange access | BUS0004460 | 30017275 | 2.Commissioning | PM | 2024-08-08 | 2024-08-28 | 2024-08-28 |  | 0 | [11 empty] | 0
1557 | 485105 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Metro C21 | BARNSLEY | S72 8UT | 2024-07-11 | 12/8/2024:Order Completed _x000D_9/8/2024:Order Completed _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 12/8/2024:Order Completed _x000D_9/8/2024:Order Completed _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFS1043866 | 30017441 | 2.Commissioning |  |  | 2024-08-08 | 2024-08-08 | 2024-08-08 15:24 | TRUE |  |  |  | 2024-08-29 | [7 empty] | 0
1558 | 625853 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Spar | WREXHAM | LL11 3UE | 2024-07-11 | 6/9/2024:#Update - ECC proposal sent to Vodafone on 09/08 _x000D_5/9/2024:#Update - ECC proposal sent to Vodafone on 09/08 _x000D_4/9/2024:#Update - ECC proposal sent to Vodafone on 09/08 _x000D_3/9/2024:#Update - ECC proposal sent to Vodafone on 09/08 _x000D_2/9/2024:#Update - ECC proposal sent to Vodafone on 09/08 _x000D_29/8/2024:#Update - ECC proposal sent to Vodafone on 09/08 _x000D_28/8/2024:#Update - ECC proposal sent to Vodafone on 09/08 _x000D_27/8/2024:#Update - ECC proposal sent to Vodafone on 09/08 _x000D_22/8/2024:#Update - ECC proposal sent to Vodafone on 09/08 _x000D_21/8/2024:#Update - ECC proposal sent to Vodafone on 09/08 _x000D_20/8/2024:#Update - ECC proposal sent to Vodafone on 09/08 _x000D_19/8/2024:#Update - ECC proposal sent to Vodafone on 09/08 _x000D_19/8/2024:01492347 _x000D_16/8/2024:#Update - ECC proposal sent to Vodafone on 09/08 _x000D_15/8/2024:#Update - ECC proposal sent to Vodafone on 09/08 _x000D_14/8/2024:#Update - ECC proposal sent to Vodafone on 09/08 _x000D_13/8/2024:#Update - ECC proposal sent to Vodafone on 09/08 _x000D_12/8/2024:#Update - ECC proposal sent to Vodafone on 09/08 _x000D_9/8/2024:#Update - ECC proposal sent to Vodafone on 09/08 _x000D_8/8/2024:15/07/2024 _x000D_6/8/2024:15/07/2024 _x000D_5/8/2024:15/07/2024 _x000D_2/8/2024:15/07/2024 _x000D_1/8/2024:15/07/2024 _x000D_31/7/2024:15/07/2024 _x000D_31/7/2024:15/07/2024 _x000D_30/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_29/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_29/7/2024:01492347 _x000D_26/7/2024:01492347 _x000D_24/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_23/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_22/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_22/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - ECC proposal sent to Vodafone on 09/08 _x000D_6/9/2024:#Update - ECC proposal sent to Vodafone on 09/08 _x000D_5/9/2024:#Update - ECC proposal sent to Vodafone on 09/08 _x000D_4/9/2024:#Update - ECC proposal sent to Vodafone on 09/08 _x000D_3/9/2024:#Update - ECC proposal sent to Vodafone on 09/08 _x000D_2/9/2024:#Update - ECC proposal sent to Vodafone on 09/08 _x000D_29/8/2024:#Update - ECC proposal sent to Vodafone on 09/08 _x000D_28/8/2024:#Update - ECC proposal sent to Vodafone on 09/08 _x000D_27/8/2024:#Update - ECC proposal sent to Vodafone on 09/08 _x000D_22/8/2024:#Update - ECC proposal sent to Vodafone on 09/08 _x000D_21/8/2024:#Update - ECC proposal sent to Vodafone on 09/08 _x000D_20/8/2024:#Update - ECC proposal sent to Vodafone on 09/08 _x000D_19/8/2024:#Update - ECC proposal sent to Vodafone on 09/08 _x000D_19/8/2024:01492347 _x000D_16/8/2024:#Update - ECC proposal sent to Vodafone on 09/08 _x000D_15/8/2024:#Update - ECC proposal sent to Vodafone on 09/08 _x000D_14/8/2024:#Update - ECC proposal sent to Vodafone on 09/08 _x000D_13/8/2024:#Update - ECC proposal sent to Vodafone on 09/08 _x000D_12/8/2024:#Update - ECC proposal sent to Vodafone on 09/08 _x000D_9/8/2024:#Update - ECC proposal sent to Vodafone on 09/08 _x000D_8/8/2024:15/07/2024 _x000D_6/8/2024:15/07/2024 _x000D_5/8/2024:15/07/2024 _x000D_2/8/2024:15/07/2024 _x000D_1/8/2024:15/07/2024 _x000D_31/7/2024:15/07/2024 _x000D_31/7/2024:15/07/2024 _x000D_30/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_29/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_29/7/2024:01492347 _x000D_26/7/2024:01492347 _x000D_24/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_23/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_22/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_22/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | Update: Order Amended | #Update - ECC proposal sent to Vodafone on 09/08 |  |  |  |  | 2.Allwyn to arrange access | VFS1054948 | 30017714 | 1.Provisioning | AM |  | 2024-08-08 | 2024-09-09 |  | 0 | [11 empty] | 0
1559 | 471456 |  | Batch 6 Aug 24 | Type 1 | SURE/Mobile | SPAR STORES | ISLE OF MAN | IM2 6LX | 2024-07-11 | 6/9/2024:#Update - Awaiting VF decision on low bandwidth speeds. Upspeed is 1-1.5Mb. _x000D_5/9/2024:#Update - Awaiting VF decision on low bandwidth speeds. Upspeed is 1-1.5Mb. _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Awaiting VF decision on low bandwidth speeds. Upspeed is 1-1.5Mb. _x000D_6/9/2024:#Update - Awaiting VF decision on low bandwidth speeds. Upspeed is 1-1.5Mb. _x000D_5/9/2024:#Update - Awaiting VF decision on low bandwidth speeds. Upspeed is 1-1.5Mb. _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - Awaiting VF decision on low bandwidth speeds. Upspeed is 1-1.5Mb. |  |  |  |  | 2.Allwyn to arrange access | SURE | 30017259 | 1.Provisioning | AM |  | 2024-08-08 |  |  | 0 | [11 empty] | 0
1560 | 422316 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Nisa | ALTRINCHAM | WA15 6SB | 2024-08-12 | 13/8/2024:Order Completed _x000D_12/8/2024:Order Completed _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 13/8/2024:Order Completed _x000D_12/8/2024:Order Completed _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFP2421518 | 30017755 | 2.Commissioning |  |  | 2024-08-09 | 2024-08-09 | 2024-08-09 11:48 | TRUE |  |  |  | 2024-08-28 | [7 empty] | 0
1561 | 670874 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Crescent Food Hall | BOURNEMOUTH | BH1 4AE | 2024-08-12 | 13/8/2024:Order Completed _x000D_12/8/2024:Order Completed _x000D_9/8/2024:Order Completed _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_18/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_17/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 18/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 13/8/2024:Order Completed _x000D_12/8/2024:Order Completed _x000D_9/8/2024:Order Completed _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_18/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_17/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 18/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFS1043865 | 30017520 | 3.In life |  |  | 2024-08-09 | 2024-08-09 | 2024-08-09 09:37 | TRUE |  |  |  | 2024-09-04 |  |  |  | 2024-09-04 | 242005011039 | 242005011039 | 2024-09-05 | 1
1562 | 664409 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Nisa Local Otterbourne Foodmarket | WINCHESTER | SO21 2EE | 2024-07-11 | 6/9/2024:#Update Premium costs with VF to approve _x000D_5/9/2024:#Update Premium costs with VF to approve _x000D_4/9/2024:#Update Premium costs with VF to approve _x000D_3/9/2024:#Update Premium costs with VF to approve _x000D_2/9/2024:#Update Premium costs with VF to approve _x000D_29/8/2024:#Update Premium costs with VF to approve _x000D_28/8/2024:#Update Premium costs with VF to approve _x000D_27/8/2024:#Update Premium costs with VF to approve _x000D_22/8/2024:#Update Premium costs with VF to approve _x000D_21/8/2024:#Update Premium costs with VF to approve _x000D_20/8/2024:#Update Premium costs with VF to approve _x000D_19/8/2024:#Update Premium costs with VF to approve _x000D_19/8/2024:01496381 _x000D_16/8/2024:Your order has been delayed due to a customer missed appointment. Incorrect Product, Please check with end user and reappoint the order if still required. _x000D_15/8/2024:Your order has been delayed due to a customer missed appointment. Incorrect Product, Please check with end user and reappoint the order if still required. _x000D_14/8/2024:Your order has been delayed due to a customer missed appointment. Incorrect Product, Please check with end user and reappoint the order if still required. _x000D_13/8/2024:Your order has been delayed due to a customer missed appointment. Incorrect Product, Please check with end user and reappoint the order if still required. _x000D_12/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_9/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_23/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_22/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_22/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update Premium costs with VF to approve _x000D_6/9/2024:#Update Premium costs with VF to approve _x000D_5/9/2024:#Update Premium costs with VF to approve _x000D_4/9/2024:#Update Premium costs with VF to approve _x000D_3/9/2024:#Update Premium costs with VF to approve _x000D_2/9/2024:#Update Premium costs with VF to approve _x000D_29/8/2024:#Update Premium costs with VF to approve _x000D_28/8/2024:#Update Premium costs with VF to approve _x000D_27/8/2024:#Update Premium costs with VF to approve _x000D_22/8/2024:#Update Premium costs with VF to approve _x000D_21/8/2024:#Update Premium costs with VF to approve _x000D_20/8/2024:#Update Premium costs with VF to approve _x000D_19/8/2024:#Update Premium costs with VF to approve _x000D_19/8/2024:01496381 _x000D_16/8/2024:Your order has been delayed due to a customer missed appointment. Incorrect Product, Please check with end user and reappoint the order if still required. _x000D_15/8/2024:Your order has been delayed due to a customer missed appointment. Incorrect Product, Please check with end user and reappoint the order if still required. _x000D_14/8/2024:Your order has been delayed due to a customer missed appointment. Incorrect Product, Please check with end user and reappoint the order if still required. _x000D_13/8/2024:Your order has been delayed due to a customer missed appointment. Incorrect Product, Please check with end user and reappoint the order if still required. _x000D_12/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_9/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_23/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_22/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_22/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update Premium costs with VF to approve |  |  |  |  | 2.Allwyn to arrange access | VFS1054941 | 30017699 | 1.Provisioning | AM |  | 2024-08-09 | 2024-08-09 |  | 0 | [11 empty] | 0
1563 | 433717 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Spar Stores | IRVINE | KA11 2DH | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:Your order has been delayed. The supplier appointment failed due lack of resource, the order needs to be re-appointed. Please check with the end user and book a new appointment. CSL Note: Invalid appointment slot received _x000D_19/8/2024:Your order has been delayed. The supplier appointment failed due lack of resource, the order needs to be re-appointed. Please check with the end user and book a new appointment. CSL Note: Invalid appointment slot received _x000D_19/8/2024:13/08/2024 11:47 _x000D_16/8/2024:Your order has been delayed. The supplier appointment failed due lack of resource, the order needs to be re-appointed. Please check with the end user and book a new appointment. CSL Note: Invalid appointment slot received _x000D_15/8/2024:Your order has been delayed. The supplier appointment failed due lack of resource, the order needs to be re-appointed. Please check with the end user and book a new appointment. CSL Note: Invalid appointment slot received _x000D_14/8/2024:Your order has been delayed. The supplier appointment failed due lack of resource, the order needs to be re-appointed. Please check with the end user and book a new appointment. CSL Note: Invalid appointment slot received _x000D_13/8/2024:Update: Order Amended CSL Note: Invalid appointment slot received _x000D_12/8/2024:Update: Order Amended CSL Note: Invalid appointment slot received _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:Your order has been delayed. The supplier appointment failed due lack of resource, the order needs to be re-appointed. Please check with the end user and book a new appointment. CSL Note: Invalid appointment slot received _x000D_19/8/2024:Your order has been delayed. The supplier appointment failed due lack of resource, the order needs to be re-appointed. Please check with the end user and book a new appointment. CSL Note: Invalid appointment slot received _x000D_19/8/2024:13/08/2024 11:47 _x000D_16/8/2024:Your order has been delayed. The supplier appointment failed due lack of resource, the order needs to be re-appointed. Please check with the end user and book a new appointment. CSL Note: Invalid appointment slot received _x000D_15/8/2024:Your order has been delayed. The supplier appointment failed due lack of resource, the order needs to be re-appointed. Please check with the end user and book a new appointment. CSL Note: Invalid appointment slot received _x000D_14/8/2024:Your order has been delayed. The supplier appointment failed due lack of resource, the order needs to be re-appointed. Please check with the end user and book a new appointment. CSL Note: Invalid appointment slot received _x000D_13/8/2024:Update: Order Amended CSL Note: Invalid appointment slot received _x000D_12/8/2024:Update: Order Amended CSL Note: Invalid appointment slot received _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFS1043862 | 30017496 | 1.Provisioning | AM |  | 2024-08-09 | 2024-08-12 |  | 0 | [11 empty] | 0
1564 | 477094 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | The Card Shop | CLEATOR MOOR | CA25 5BD | 2024-08-12 | 13/8/2024:Order Completed _x000D_12/8/2024:Order Completed _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 13/8/2024:Order Completed _x000D_12/8/2024:Order Completed _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1054934 | 30017702 | 2.Commissioning |  |  | 2024-08-09 | 2024-08-09 | 2024-08-09 11:10 | TRUE |  |  |  | 2024-08-28 | [7 empty] | 0
1565 | 615689 |  | Batch 6 Aug 24 | Type 1 | KCOM/Mobile | Premier | HULL | HU5 5PH | 2024-07-11 | 6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_19/8/2024:01583430 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_17/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_16/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_19/8/2024:01583430 _x000D_16/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_15/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_14/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_17/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_16/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - Allwyn confirmed Retailer has agreed to installation on 29/08 AM |  |  |  |  | 2.Allwyn to arrange access | BUS0004461 | 30017264 | 1.Provisioning | AM | 2024-08-08 | 2024-08-29 | 2024-08-29 |  | 0 | [11 empty] | 0
1566 | 666438 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Nisa Local | CAERPHILLY | CF83 4DH | 2024-07-11 | 6/9/2024:#Update - awaiting ECC approval - proposal sent to VF 14/07 _x000D_5/9/2024:#Update - awaiting ECC approval - proposal sent to VF 14/07 _x000D_4/9/2024:#Update - awaiting ECC approval - proposal sent to VF 14/07 _x000D_3/9/2024:#Update - awaiting ECC approval - proposal sent to VF 14/07 _x000D_2/9/2024:#Update - awaiting ECC approval - proposal sent to VF 14/07 _x000D_29/8/2024:#Update - awaiting ECC approval - proposal sent to VF 14/07 _x000D_28/8/2024:#Update - awaiting ECC approval - proposal sent to VF 14/07 _x000D_27/8/2024:#Update - awaiting ECC approval - proposal sent to VF 14/07 _x000D_22/8/2024:#Update - awaiting ECC approval - proposal sent to VF 14/07 _x000D_21/8/2024:#Update - awaiting ECC approval - proposal sent to VF 14/07 _x000D_20/8/2024:Update: Order Amended _x000D_19/8/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point within customer premise to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_19/8/2024:12/08/2024 10:54 _x000D_16/8/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point within customer premise to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_15/8/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point within customer premise to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_14/8/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point within customer premise to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_13/8/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point within customer premise to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_12/8/2024:End User Missed appointment. Action required _x000D_9/8/2024:End User Missed appointment. Action required _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_0 | 9/9/2024:#Update - awaiting ECC approval - proposal sent to VF 14/07 _x000D_6/9/2024:#Update - awaiting ECC approval - proposal sent to VF 14/07 _x000D_5/9/2024:#Update - awaiting ECC approval - proposal sent to VF 14/07 _x000D_4/9/2024:#Update - awaiting ECC approval - proposal sent to VF 14/07 _x000D_3/9/2024:#Update - awaiting ECC approval - proposal sent to VF 14/07 _x000D_2/9/2024:#Update - awaiting ECC approval - proposal sent to VF 14/07 _x000D_29/8/2024:#Update - awaiting ECC approval - proposal sent to VF 14/07 _x000D_28/8/2024:#Update - awaiting ECC approval - proposal sent to VF 14/07 _x000D_27/8/2024:#Update - awaiting ECC approval - proposal sent to VF 14/07 _x000D_22/8/2024:#Update - awaiting ECC approval - proposal sent to VF 14/07 _x000D_21/8/2024:#Update - awaiting ECC approval - proposal sent to VF 14/07 _x000D_20/8/2024:Update: Order Amended _x000D_19/8/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point within customer premise to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_19/8/2024:12/08/2024 10:54 _x000D_16/8/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point within customer premise to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_15/8/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point within customer premise to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_14/8/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point within customer premise to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_13/8/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point within customer premise to complete the install. Please check with end user and re-appoint order for earliest date. _x000D_12/8/2024:End User Missed appointment. Action required _x000D_9/8/2024:End User Missed appointment. Action required _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_0 | 0 | #Update - awaiting ECC approval - proposal sent to VF 14/07 |  |  |  |  | 2.Allwyn to arrange access | VFS1057102 | 30017378 | 1.Provisioning | AM |  | 2024-08-09 | 2024-08-09 |  | 0 | [11 empty] | 0
1567 | 614971 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Nevinson Convenience Store | SOUTH SHIELDS | NE34 8ND | 2024-08-29 | 29/8/2024:#Update Retailer confirmed 28/08, AM. _x000D_28/8/2024:#Update Retailer confirmed 28/08, AM. _x000D_27/8/2024:#Update Retailer confirmed 28/08, AM. _x000D_22/8/2024:#Update Retailer confirmed 28/08, AM. _x000D_21/8/2024:#Update Retailer confirmed 28/08, AM. _x000D_20/8/2024:#Update Retailer confirmed 28/08, AM. _x000D_19/8/2024:#Update Retailer confirmed 28/08, AM. _x000D_19/8/2024:01574348 _x000D_16/8/2024:#Update Reappointed for 28/08, AM. Action on Allwyn - ensure the retailer is aware. _x000D_15/8/2024:#Update Reappointed for 28/08, AM. Action on Allwyn - ensure the retailer is aware. _x000D_14/8/2024:#Update Reappointed for 28/08, AM. Action on Allwyn - ensure the retailer is aware. _x000D_13/8/2024:Your order has been delayed by our Suppliers due to Assistance being required to complete the installation. Please check with end user and re-appoint order for earliest date. _x000D_12/8/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Supplier delay - Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 22/07/2024 _x000D_18/7/2024:#Update - Supplier delay - Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 22/07/2024 _x000D_17/7/2024:#Update - Supplier delay - Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 22/07/2024 _x000D_16/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 29/8/2024:#Update Retailer confirmed 28/08, AM. _x000D_28/8/2024:#Update Retailer confirmed 28/08, AM. _x000D_27/8/2024:#Update Retailer confirmed 28/08, AM. _x000D_22/8/2024:#Update Retailer confirmed 28/08, AM. _x000D_21/8/2024:#Update Retailer confirmed 28/08, AM. _x000D_20/8/2024:#Update Retailer confirmed 28/08, AM. _x000D_19/8/2024:#Update Retailer confirmed 28/08, AM. _x000D_19/8/2024:01574348 _x000D_16/8/2024:#Update Reappointed for 28/08, AM. Action on Allwyn - ensure the retailer is aware. _x000D_15/8/2024:#Update Reappointed for 28/08, AM. Action on Allwyn - ensure the retailer is aware. _x000D_14/8/2024:#Update Reappointed for 28/08, AM. Action on Allwyn - ensure the retailer is aware. _x000D_13/8/2024:Your order has been delayed by our Suppliers due to Assistance being required to complete the installation. Please check with end user and re-appoint order for earliest date. _x000D_12/8/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Supplier delay - Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 22/07/2024 _x000D_18/7/2024:#Update - Supplier delay - Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 22/07/2024 _x000D_17/7/2024:#Update - Supplier delay - Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 22/07/2024 _x000D_16/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFP2422322 | 30021829 | 2.Commissioning | AM |  | 2024-08-09 | 2024-08-28 |  | 0 | [11 empty] | 0
1568 | 433800 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Spar | LLANGEFNI | LL77 7FE | 2024-09-02 | 13/8/2024:#Update - Supplier delay - Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 22/07/2024 _x000D_12/8/2024:#Update - Supplier delay - Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 22/07/2024 _x000D_9/8/2024:#Update - Supplier delay - Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 22/07/2024 _x000D_8/8/2024:17/07/2024 _x000D_6/8/2024:17/07/2024 _x000D_5/8/2024:17/07/2024 _x000D_2/8/2024:17/07/2024 _x000D_1/8/2024:17/07/2024 _x000D_31/7/2024:17/07/2024 _x000D_31/7/2024:17/07/2024 _x000D_30/7/2024:#Update - Supplier delay - Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 22/07/2024 _x000D_29/7/2024:#Update - Supplier delay - Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 22/07/2024 _x000D_29/7/2024:01496396 _x000D_26/7/2024:01496396 _x000D_24/7/2024:#Update - Supplier delay - Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 22/07/2024 _x000D_23/7/2024:#Update - Supplier delay - Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 22/07/2024 _x000D_22/7/2024:#Update - Supplier delay - Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 22/07/2024 _x000D_22/7/2024:#Update - Supplier delay - Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 22/07/2024 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 13/8/2024:#Update - Supplier delay - Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 22/07/2024 _x000D_12/8/2024:#Update - Supplier delay - Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 22/07/2024 _x000D_9/8/2024:#Update - Supplier delay - Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 22/07/2024 _x000D_8/8/2024:17/07/2024 _x000D_6/8/2024:17/07/2024 _x000D_5/8/2024:17/07/2024 _x000D_2/8/2024:17/07/2024 _x000D_1/8/2024:17/07/2024 _x000D_31/7/2024:17/07/2024 _x000D_31/7/2024:17/07/2024 _x000D_30/7/2024:#Update - Supplier delay - Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 22/07/2024 _x000D_29/7/2024:#Update - Supplier delay - Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 22/07/2024 _x000D_29/7/2024:01496396 _x000D_26/7/2024:01496396 _x000D_24/7/2024:#Update - Supplier delay - Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 22/07/2024 _x000D_23/7/2024:#Update - Supplier delay - Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 22/07/2024 _x000D_22/7/2024:#Update - Supplier delay - Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 22/07/2024 _x000D_22/7/2024:#Update - Supplier delay - Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 22/07/2024 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFS1054909 | 30017786 | 6.Failed router install |  |  | 2024-08-09 | 2024-08-09 | 2024-08-09 09:24 | TRUE |  |  |  | 2024-09-02 |  |  |  | 2024-09-02 | 23A004948577 | 23A004948577 | 2024-09-02 | 1
1569 | 432427 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | K C News | LONDON | SW2 3BU | 2024-08-12 | 13/8/2024:Order Completed _x000D_12/8/2024:Order Completed _x000D_9/8/2024:Order Completed _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 13/8/2024:Order Completed _x000D_12/8/2024:Order Completed _x000D_9/8/2024:Order Completed _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFS1043863 | 30017539 | 6.Failed router install |  |  | 2024-08-09 | 2024-08-09 | 2024-08-09 09:48 | TRUE |  |  |  | 2024-08-29 |  |  |  | 2024-09-02 | 242005010998 | 242005010998 | 2024-09-03 | 1
1570 | 478008 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | McKellars Grocers | CAMPBELTOWN | PA28 6AD | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Silver Address Issue | 30017763 | 1.Provisioning | AM |  | 2024-08-09 |  |  | 0 | [11 empty] | 0
1571 | 642573 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Hollands | RICKMANSWORTH | WD3 1EE | 2024-08-12 | 13/8/2024:Order Completed _x000D_12/8/2024:Order Completed _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 13/8/2024:Order Completed _x000D_12/8/2024:Order Completed _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043859 | 30017511 | 2.Commissioning |  |  | 2024-08-09 | 2024-08-09 | 2024-08-09 17:53 | TRUE |  |  |  | 2024-08-30 | [7 empty] | 0
1572 | 660390 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Macaris | ARMAGH | BT61 7LJ | 2024-08-12 | 13/8/2024:Order Completed _x000D_12/8/2024:Order Completed _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 13/8/2024:Order Completed _x000D_12/8/2024:Order Completed _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFP2422543 | 30017380 | 6.Failed router install |  |  | 2024-08-09 | 2024-08-09 | 2024-08-09 12:11 | TRUE |  |  |  | 2024-08-28 |  |  |  | 2024-08-28 | 238004925808 | 238004925808 | 2024-08-29 | 1
1573 | 458353 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Sids News | DEWSBURY | WF12 8QS | 2024-08-12 | 13/8/2024:Order Completed _x000D_12/8/2024:Order Completed _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 13/8/2024:Order Completed _x000D_12/8/2024:Order Completed _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043860 | 30017537 | 6.Failed router install |  |  | 2024-08-09 | 2024-08-09 | 2024-08-09 14:21 | TRUE |  |  |  | 2024-08-29 |  |  |  | 2024-08-29 | 238004923989 | 238004923989 | 2024-08-30 | 1
1574 | 664981 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Post Office | HOLYHEAD | LL65 3EB | 2024-07-11 | 6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 11/09 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 11/09 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 11/09 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 11/09 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 11/09 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 11/09 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 11/09 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 11/09 AM _x000D_22/8/2024:#Update - Action for Allwyn - Installation has now been amended to 11/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 11/09 is a suitable date. _x000D_21/8/2024:Supplier Delay: Unable to complete work in the allocated appointment slot, please await further details. _x000D_20/8/2024:Supplier Delay: Unable to complete work in the allocated appointment slot, please await further details. _x000D_19/8/2024:Supplier Delay: Unable to complete work in the allocated appointment slot, please await further details. _x000D_19/8/2024:14/08/2024 04:02 _x000D_16/8/2024:Supplier Delay: Unable to complete work in the allocated appointment slot, please await further details. _x000D_15/8/2024:Supplier Delay: Unable to complete work in the allocated appointment slot, please await further details. _x000D_14/8/2024:Supplier Delay: Unable to complete work in the allocated appointment slot, please await further details. _x000D_13/8/2024:Your order has been delayed due to further Assistance is required, order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 15/08/2024 _x000D_12/8/2024:Supplier Delay: KCI-3 (Order Completed) Delayed in Processing. _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 11/09 AM _x000D_6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 11/09 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 11/09 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 11/09 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 11/09 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 11/09 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 11/09 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 11/09 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 11/09 AM _x000D_22/8/2024:#Update - Action for Allwyn - Installation has now been amended to 11/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 11/09 is a suitable date. _x000D_21/8/2024:Supplier Delay: Unable to complete work in the allocated appointment slot, please await further details. _x000D_20/8/2024:Supplier Delay: Unable to complete work in the allocated appointment slot, please await further details. _x000D_19/8/2024:Supplier Delay: Unable to complete work in the allocated appointment slot, please await further details. _x000D_19/8/2024:14/08/2024 04:02 _x000D_16/8/2024:Supplier Delay: Unable to complete work in the allocated appointment slot, please await further details. _x000D_15/8/2024:Supplier Delay: Unable to complete work in the allocated appointment slot, please await further details. _x000D_14/8/2024:Supplier Delay: Unable to complete work in the allocated appointment slot, please await further details. _x000D_13/8/2024:Your order has been delayed due to further Assistance is required, order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 15/08/2024 _x000D_12/8/2024:Supplier Delay: KCI-3 (Order Completed) Delayed in Processing. _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - Allwyn confirmed Retailer has agreed to installation on 11/09 AM |  |  |  |  | 2.Allwyn to arrange access | VFS1054895 | 30017759 | 1.Provisioning | AM |  | 2024-08-09 | 2024-08-09 |  | 0 | [11 empty] | 0
1575 | 461847 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | SPAR | COLERAINE | BT51 3QB | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_0 | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Silver Address Issue | 30017458 | 1.Provisioning | AM |  | 2024-08-09 |  |  | 0 | [11 empty] | 0
1576 | 669670 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Spar Stores | CLEETHORPES | DN35 0DW | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Silver Address Issue | 30021832 | 1.Provisioning | AM |  | 2024-08-09 |  |  | 0 | [11 empty] | 0
1577 | 665348 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Post Office | EDGWARE | HA8 5QL | 2024-08-29 | 29/8/2024:#Update Retailer confirmed 28/08, AM. _x000D_28/8/2024:#Update Retailer confirmed 28/08, AM. _x000D_27/8/2024:#Update Retailer confirmed 28/08, AM. _x000D_22/8/2024:#Update Retailer confirmed 28/08, AM. _x000D_21/8/2024:#Update Retailer confirmed 28/08, AM. _x000D_20/8/2024:#Update Retailer confirmed 28/08, AM. _x000D_19/8/2024:#Update Retailer confirmed 28/08, AM. _x000D_19/8/2024:01576062 _x000D_16/8/2024:#Update Reappointed for 28/08, AM. Action on Allwyn - ensure the retailer is aware. _x000D_15/8/2024:#Update Reappointed for 28/08, AM. Action on Allwyn - ensure the retailer is aware. _x000D_14/8/2024:#Update Reappointed for 28/08, AM. Action on Allwyn - ensure the retailer is aware. _x000D_13/8/2024:Your order has been delayed due to our suppliers being unable to complete the job in required time frame. Please check with the end user and book a new appointment. _x000D_12/8/2024:Supplier Delay: Unable to complete work in the allocated appointment slot, please await further details. _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 29/8/2024:#Update Retailer confirmed 28/08, AM. _x000D_28/8/2024:#Update Retailer confirmed 28/08, AM. _x000D_27/8/2024:#Update Retailer confirmed 28/08, AM. _x000D_22/8/2024:#Update Retailer confirmed 28/08, AM. _x000D_21/8/2024:#Update Retailer confirmed 28/08, AM. _x000D_20/8/2024:#Update Retailer confirmed 28/08, AM. _x000D_19/8/2024:#Update Retailer confirmed 28/08, AM. _x000D_19/8/2024:01576062 _x000D_16/8/2024:#Update Reappointed for 28/08, AM. Action on Allwyn - ensure the retailer is aware. _x000D_15/8/2024:#Update Reappointed for 28/08, AM. Action on Allwyn - ensure the retailer is aware. _x000D_14/8/2024:#Update Reappointed for 28/08, AM. Action on Allwyn - ensure the retailer is aware. _x000D_13/8/2024:Your order has been delayed due to our suppliers being unable to complete the job in required time frame. Please check with the end user and book a new appointment. _x000D_12/8/2024:Supplier Delay: Unable to complete work in the allocated appointment slot, please await further details. _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043858 | 30017465 | 2.Commissioning | AM |  | 2024-08-09 | 2024-08-28 |  | 0 | [11 empty] | 0
1578 | 662003 |  | Batch 6 Aug 24 | Type 1 | KCOM/Mobile | C & M News | HULL | HU9 4BU | 2024-09-04 | 6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_19/8/2024:01592166 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_20/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_19/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM _x000D_19/8/2024:01592166 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - Allwyn confirmed Retailer has agreed to installation on 03/09 PM |  |  |  |  | 2.Allwyn to arrange access | BUS0004488 | 30017266 | 2.Commissioning | AM | 2024-08-15 | 2024-08-15 |  |  | 0 | [11 empty] | 0
1579 | 650498 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | QD | GREAT YARMOUTH | NR29 5JE | 2024-07-11 | 6/9/2024:#Update - Allwyn have requested for this site to be downgraded to a site type 3 due to asbestos in the buildings structure _x000D_5/9/2024:#Update - Allwyn have requested for this site to be downgraded to a site type 3 due to asbestos in the buildings structure _x000D_4/9/2024:#Update - Allwyn have requested for this site to be downgraded to a site type 3 due to asbestos in the buildings structure _x000D_3/9/2024:#Update - Allwyn have requested for this site to be downgraded to a site type 3 due to asbestos in the buildings structure _x000D_2/9/2024:#Update – Access to the area above the ceiling tiles and confined loft space is required for the install. The asbestos registry book was present and reported asbestos up in the buildings structure. _x000D_29/8/2024:#Update – Access to the area above the ceiling tiles and confined loft space is required for the install. The asbestos registry book was present and reported asbestos up in the buildings structure. _x000D_28/8/2024:#Update – Access to the area above the ceiling tiles and confined loft space is required for the install. The asbestos registry book was present and reported asbestos up in the buildings structure. _x000D_27/8/2024:#Update – Access to the area above the ceiling tiles and confined loft space is required for the install. The asbestos registry book was present and reported asbestos up in the buildings structure. _x000D_22/8/2024:#Update – Access to the area above the ceiling tiles and confined loft space is required for the install. The asbestos registry book was present and reported asbestos up in the buildings structure. _x000D_21/8/2024:#Update – Access to the area above the ceiling tiles and confined loft space is required for the install. The asbestos registry book was present and reported asbestos up in the buildings structure. _x000D_20/8/2024:#Update – Access to the area above the ceiling tiles and confined loft space is required for the install. The asbestos registry book was present and reported asbestos up in the buildings structure. _x000D_19/8/2024:#Update – Access to the area above the ceiling tiles and confined loft space is required for the install. The asbestos registry book was present and reported asbestos up in the buildings structure. _x000D_19/8/2024:01573294 _x000D_16/8/2024:#Update – Access to the area above the ceiling tiles and confined loft space is required for the install. The asbestos registry book was present and reported asbestos up in the buildings structure. _x000D_15/8/2024:#Update – Access to the area above the ceiling tiles and confined loft space is required for the install. The asbestos registry book was present and reported asbestos up in the buildings structure. _x000D_14/8/2024:#Update – Access to the area above the ceiling tiles and confined loft space is required for the install. The asbestos registry book was present and reported asbestos up in the buildings structure. _x000D_13/8/2024:#Update – Access to the area above the ceiling tiles and confined loft space is required for the install. The asbestos registry book was present and reported asbestos up in the buildings structure. _x000D_12/8/2024:#Update – Access to the area above the ceiling tiles and confined loft space is required for the install. The asbestos registry book was present and reported asbestos up in the buildings structure. _x000D_9/8/2024:Supplier Delay: New Appointment might be required _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn have requested for this site to be downgraded to a site type 3 due to asbestos in the buildings structure _x000D_6/9/2024:#Update - Allwyn have requested for this site to be downgraded to a site type 3 due to asbestos in the buildings structure _x000D_5/9/2024:#Update - Allwyn have requested for this site to be downgraded to a site type 3 due to asbestos in the buildings structure _x000D_4/9/2024:#Update - Allwyn have requested for this site to be downgraded to a site type 3 due to asbestos in the buildings structure _x000D_3/9/2024:#Update - Allwyn have requested for this site to be downgraded to a site type 3 due to asbestos in the buildings structure _x000D_2/9/2024:#Update – Access to the area above the ceiling tiles and confined loft space is required for the install. The asbestos registry book was present and reported asbestos up in the buildings structure. _x000D_29/8/2024:#Update – Access to the area above the ceiling tiles and confined loft space is required for the install. The asbestos registry book was present and reported asbestos up in the buildings structure. _x000D_28/8/2024:#Update – Access to the area above the ceiling tiles and confined loft space is required for the install. The asbestos registry book was present and reported asbestos up in the buildings structure. _x000D_27/8/2024:#Update – Access to the area above the ceiling tiles and confined loft space is required for the install. The asbestos registry book was present and reported asbestos up in the buildings structure. _x000D_22/8/2024:#Update – Access to the area above the ceiling tiles and confined loft space is required for the install. The asbestos registry book was present and reported asbestos up in the buildings structure. _x000D_21/8/2024:#Update – Access to the area above the ceiling tiles and confined loft space is required for the install. The asbestos registry book was present and reported asbestos up in the buildings structure. _x000D_20/8/2024:#Update – Access to the area above the ceiling tiles and confined loft space is required for the install. The asbestos registry book was present and reported asbestos up in the buildings structure. _x000D_19/8/2024:#Update – Access to the area above the ceiling tiles and confined loft space is required for the install. The asbestos registry book was present and reported asbestos up in the buildings structure. _x000D_19/8/2024:01573294 _x000D_16/8/2024:#Update – Access to the area above the ceiling tiles and confined loft space is required for the install. The asbestos registry book was present and reported asbestos up in the buildings structure. _x000D_15/8/2024:#Update – Access to the area above the ceiling tiles and confined loft space is required for the install. The asbestos registry book was present and reported asbestos up in the buildings structure. _x000D_14/8/2024:#Update – Access to the area above the ceiling tiles and confined loft space is required for the install. The asbestos registry book was present and reported asbestos up in the buildings structure. _x000D_13/8/2024:#Update – Access to the area above the ceiling tiles and confined loft space is required for the install. The asbestos registry book was present and reported asbestos up in the buildings structure. _x000D_12/8/2024:#Update – Access to the area above the ceiling tiles and confined loft space is required for the install. The asbestos registry book was present and reported asbestos up in the buildings structure. _x000D_9/8/2024:Supplier Delay: New Appointment might be required _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - Allwyn have requested for this site to be downgraded to a site type 3 due to asbestos in the buildings structure |  |  |  |  | 2.Allwyn to arrange access | VFS1043857 | 30017523 | 1.Provisioning | AM |  | 2024-08-09 | 2024-08-09 |  | 0 | [11 empty] | 0
1580 | 486971 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Central Services Agency | BELFAST | BT12 6HU | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Silver Address Issue | 30017688 | 1.Provisioning | AM |  | 2024-08-09 |  |  | 0 | [11 empty] | 0
1581 | 457991 |  | Batch 6 Aug 24 | Type 1 | KCOM/Mobile | Stuarts News | HULL | HU3 6QP | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | BUS0004455 | 30017232 | 1.Provisioning | AM | 2024-08-07 | 2024-08-07 |  |  | 0 | [11 empty] | 0
1582 | 651282 |  | Batch 6 Aug 24 | Type 1 | KCOM/Mobile | Happy News | HULL | HU2 8PN | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | BUS0004508 | 30017269 | 1.Provisioning | AM | 2024-08-05 | 2024-08-05 |  |  | 0 | [11 empty] | 0
1583 | 664481 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Post Office | KIDLINGTON | OX5 1PT | 2024-07-11 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:Order Completed _x000D_12/8/2024:Order Completed _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:Order Completed _x000D_12/8/2024:Order Completed _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043856 | 30017542 | 3.In life | AM |  | 2024-08-12 | 2024-08-12 | 2024-08-12 09:36 | 1 |  |  |  | 2024-09-05 |  |  |  | 2024-09-05 | 242005011000 | 242005011000 | 2024-09-06 | 1
1584 | 426684 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Farchnad Fach | AMMANFORD | SA18 3RY | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2421504 | 30017743 | 1.Provisioning | AM |  | 2024-06-09 | 2024-06-09 |  | 0 | [11 empty] | 0
1585 | 458297 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Nisa | DERBY | DE22 4AT | 2024-09-05 | 6/9/2024:#Update Reappointed for 04/09, AM as store manager to be present. Action on Allwyn - ensure the retailer is aware. _x000D_5/9/2024:#Update Reappointed for 04/09, AM as store manager to be present. Action on Allwyn - ensure the retailer is aware. _x000D_4/9/2024:#Update Reappointed for 04/09, AM as store manager to be present. Action on Allwyn - ensure the retailer is aware. _x000D_3/9/2024:#Update Reappointed for 04/09, AM as store manager to be present. Action on Allwyn - ensure the retailer is aware. _x000D_2/9/2024:#Update Reappointed for 04/09, AM as store manager to be present. Action on Allwyn - ensure the retailer is aware. _x000D_29/8/2024:#Update Reappointed for 04/09, AM as store manager to be present. Action on Allwyn - ensure the retailer is aware. _x000D_28/8/2024:#Update Reappointed for 04/09, AM as store manager to be present. Action on Allwyn - ensure the retailer is aware. _x000D_27/8/2024:#Update Reappointed for 04/09, AM as store manager to be present. Action on Allwyn - ensure the retailer is aware. _x000D_22/8/2024:#Update Reappointed for 04/09, AM as store manager to be present. Action on Allwyn - ensure the retailer is aware. _x000D_21/8/2024:#Update Reappointed for 04/09, AM as store manager to be present. Action on Allwyn - ensure the retailer is aware. _x000D_20/8/2024:#Update Reappointed for 04/09, AM as store manager to be present. Action on Allwyn - ensure the retailer is aware. _x000D_19/8/2024:#Update Reappointed for 04/09, AM as store manager to be present. Action on Allwyn - ensure the retailer is aware. _x000D_19/8/2024:01579675 _x000D_16/8/2024:#Update Reappointed for 04/09, AM as store manager to be present. Action on Allwyn - ensure the retailer is aware. _x000D_15/8/2024:#Update Reappointed for 04/09, AM as store manager to be present. Action on Allwyn - ensure the retailer is aware. _x000D_14/8/2024:#Update Reappointed for 04/09, AM as store manager to be present. Action on Allwyn - ensure the retailer is aware. _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_17/7/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update Reappointed for 04/09, AM as store manager to be present. Action on Allwyn - ensure the retailer is aware. _x000D_6/9/2024:#Update Reappointed for 04/09, AM as store manager to be present. Action on Allwyn - ensure the retailer is aware. _x000D_5/9/2024:#Update Reappointed for 04/09, AM as store manager to be present. Action on Allwyn - ensure the retailer is aware. _x000D_4/9/2024:#Update Reappointed for 04/09, AM as store manager to be present. Action on Allwyn - ensure the retailer is aware. _x000D_3/9/2024:#Update Reappointed for 04/09, AM as store manager to be present. Action on Allwyn - ensure the retailer is aware. _x000D_2/9/2024:#Update Reappointed for 04/09, AM as store manager to be present. Action on Allwyn - ensure the retailer is aware. _x000D_29/8/2024:#Update Reappointed for 04/09, AM as store manager to be present. Action on Allwyn - ensure the retailer is aware. _x000D_28/8/2024:#Update Reappointed for 04/09, AM as store manager to be present. Action on Allwyn - ensure the retailer is aware. _x000D_27/8/2024:#Update Reappointed for 04/09, AM as store manager to be present. Action on Allwyn - ensure the retailer is aware. _x000D_22/8/2024:#Update Reappointed for 04/09, AM as store manager to be present. Action on Allwyn - ensure the retailer is aware. _x000D_21/8/2024:#Update Reappointed for 04/09, AM as store manager to be present. Action on Allwyn - ensure the retailer is aware. _x000D_20/8/2024:#Update Reappointed for 04/09, AM as store manager to be present. Action on Allwyn - ensure the retailer is aware. _x000D_19/8/2024:#Update Reappointed for 04/09, AM as store manager to be present. Action on Allwyn - ensure the retailer is aware. _x000D_19/8/2024:01579675 _x000D_16/8/2024:#Update Reappointed for 04/09, AM as store manager to be present. Action on Allwyn - ensure the retailer is aware. _x000D_15/8/2024:#Update Reappointed for 04/09, AM as store manager to be present. Action on Allwyn - ensure the retailer is aware. _x000D_14/8/2024:#Update Reappointed for 04/09, AM as store manager to be present. Action on Allwyn - ensure the retailer is aware. _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_17/7/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | Order Completed | #Update Reappointed for 04/09, AM as store manager to be present. Action on Allwyn - ensure the retailer is aware. |  |  |  |  | 2.Allwyn to arrange access | VFS1043851 | 30017491 | 2.Commissioning | AM |  | 2024-08-12 | 2024-09-04 |  | 0 | [11 empty] | 0
1586 | 445211 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | SUBRA ENTERPRISES | LONDON | E17 6HE | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2422540 | 30017370 | 1.Provisioning | AM |  | 2024-08-12 | 2024-09-06 |  | 0 | [11 empty] | 0
1587 | 469266 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Eurospar | COLERAINE | BT51 5AA | 2024-07-11 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:Update: Order Completed by Supplier _x000D_12/8/2024:Update: Order Completed by Supplier _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:Update: Order Completed by Supplier _x000D_12/8/2024:Update: Order Completed by Supplier _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043850 | 30017581 | 3.In life | AM |  | 2024-08-12 | 2024-08-12 | 2024-08-12 08:29 | 1 |  |  |  | 2024-09-02 |  |  |  | 2024-09-02 | 23A004952910 | 23A004952910 | 2024-09-03 | 1
1588 | 463940 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Budgens Supermarket | TROWBRIDGE | BA14 7GW | 2024-07-11 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:Order Completed _x000D_12/8/2024:Order Completed _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_1/8/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:37559 _x000D_30/7/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:26/07/2024 10:32 _x000D_26/7/2024:19/07/2024 10:02 _x000D_24/7/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_23/7/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:#Update - Our Suppliers have given us a review date of 18/07/2024. We will continue to provide update as they become available. _x000D_18/7/2024:#Update - Our Suppliers have given us a review date of 18/07/2024. We will continue to provide update as they become available. _x000D_17/7/2024:#Update - Our Suppliers have given us a review date of 18/07/2024. We will continue to provide update as they become available. _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:Order Completed _x000D_12/8/2024:Order Completed _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_1/8/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:37559 _x000D_30/7/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:26/07/2024 10:32 _x000D_26/7/2024:19/07/2024 10:02 _x000D_24/7/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_23/7/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:#Update - Our Suppliers have given us a review date of 18/07/2024. We will continue to provide update as they become available. _x000D_18/7/2024:#Update - Our Suppliers have given us a review date of 18/07/2024. We will continue to provide update as they become available. _x000D_17/7/2024:#Update - Our Suppliers have given us a review date of 18/07/2024. We will continue to provide update as they become available. _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFP2422539 | 30017383 | 2.Commissioning | AM |  | 2024-08-12 | 2024-08-12 | 2024-08-12 08:17 | 1 |  |  |  | 2024-09-05 | [7 empty] | 0
1589 | 651871 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Newstyme | WORKSOP | S80 1JA | 2024-07-11 | 16/8/2024:#Update - Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 31/07/2024.We will continue to provide update as they become available. _x000D_15/8/2024:#Update - Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 31/07/2024.We will continue to provide update as they become available. _x000D_14/8/2024:#Update - Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 31/07/2024.We will continue to provide update as they become available. _x000D_13/8/2024:#Update - Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 31/07/2024.We will continue to provide update as they become available. _x000D_12/8/2024:#Update - Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 31/07/2024.We will continue to provide update as they become available. _x000D_9/8/2024:#Update - Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 31/07/2024.We will continue to provide update as they become available. _x000D_8/8/2024:24/07/2024 _x000D_6/8/2024:24/07/2024 _x000D_5/8/2024:24/07/2024 _x000D_2/8/2024:24/07/2024 _x000D_1/8/2024:24/07/2024 _x000D_31/7/2024:24/07/2024 _x000D_31/7/2024:24/07/2024 _x000D_30/7/2024:#Update - Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 31/07/2024.We will continue to provide update as they become available. _x000D_29/7/2024:#Update - Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 31/07/2024.We will continue to provide update as they become available. _x000D_29/7/2024:01496121 _x000D_26/7/2024:01496121 _x000D_24/7/2024:#Update - Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 31/07/2024.We will continue to provide update as they become available. _x000D_23/7/2024:#Update - Our Suppliers have given us a review date of 24/07/2024. We will continue to provide update as they become available. _x000D_22/7/2024:#Update - Our Suppliers have given us a review date of 24/07/2024. We will continue to provide update as they become available. _x000D_22/7/2024:#Update - Our Suppliers have given us a review date of 18/07/2024. We will continue to provide update as they become available. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:#Update - Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 31/07/2024.We will continue to provide update as they become available. _x000D_15/8/2024:#Update - Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 31/07/2024.We will continue to provide update as they become available. _x000D_14/8/2024:#Update - Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 31/07/2024.We will continue to provide update as they become available. _x000D_13/8/2024:#Update - Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 31/07/2024.We will continue to provide update as they become available. _x000D_12/8/2024:#Update - Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 31/07/2024.We will continue to provide update as they become available. _x000D_9/8/2024:#Update - Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 31/07/2024.We will continue to provide update as they become available. _x000D_8/8/2024:24/07/2024 _x000D_6/8/2024:24/07/2024 _x000D_5/8/2024:24/07/2024 _x000D_2/8/2024:24/07/2024 _x000D_1/8/2024:24/07/2024 _x000D_31/7/2024:24/07/2024 _x000D_31/7/2024:24/07/2024 _x000D_30/7/2024:#Update - Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 31/07/2024.We will continue to provide update as they become available. _x000D_29/7/2024:#Update - Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 31/07/2024.We will continue to provide update as they become available. _x000D_29/7/2024:01496121 _x000D_26/7/2024:01496121 _x000D_24/7/2024:#Update - Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 31/07/2024.We will continue to provide update as they become available. _x000D_23/7/2024:#Update - Our Suppliers have given us a review date of 24/07/2024. We will continue to provide update as they become available. _x000D_22/7/2024:#Update - Our Suppliers have given us a review date of 24/07/2024. We will continue to provide update as they become available. _x000D_22/7/2024:#Update - Our Suppliers have given us a review date of 18/07/2024. We will continue to provide update as they become available. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1055297 | 30017723 | 2.Commissioning | AM |  | 2024-08-12 | 2024-08-12 | 2024-08-12 11:48 | 1 |  |  |  | 2024-08-29 | [7 empty] | 0
1590 | 448293 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Eurofoods | LEEDS | LS12 1LZ | 2024-08-29 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:#Update The retailer was unaware of the appointment, and reappointed for 28/08. Action on Allwyn - please make sure the retailer knows about the new appointment. _x000D_28/8/2024:#Update The retailer was unaware of the appointment, and reappointed for 28/08. Action on Allwyn - please make sure the retailer knows about the new appointment. _x000D_27/8/2024:#Update The retailer was unaware of the appointment, and reappointed for 28/08. Action on Allwyn - please make sure the retailer knows about the new appointment. _x000D_22/8/2024:#Update The retailer was unaware of the appointment, and reappointed for 28/08. Action on Allwyn - please make sure the retailer knows about the new appointment. _x000D_21/8/2024:#Update The retailer was unaware of the appointment, and reappointed for 28/08. Action on Allwyn - please make sure the retailer knows about the new appointment. _x000D_20/8/2024:#Update The retailer was unaware of the appointment, and reappointed for 28/08. Action on Allwyn - please make sure the retailer knows about the new appointment. _x000D_19/8/2024:#Update The retailer was unaware of the appointment, and reappointed for 28/08. Action on Allwyn - please make sure the retailer knows about the new appointment. _x000D_19/8/2024:01578423 _x000D_16/8/2024:#Update The retailer was unaware of the appointment, and reappointed for 28/08. Action on Allwyn - please make sure the retailer knows about the new appointment. _x000D_15/8/2024:#Update The retailer was unaware of the appointment, and reappointed for 28/08. Action on Allwyn - please make sure the retailer knows about the new appointment. _x000D_14/8/2024:#Update The retailer was unaware of the appointment, and reappointed for 28/08. Action on Allwyn - please make sure the retailer knows about the new appointment. _x000D_13/8/2024:#Update The retailer was unaware of the appointment, and reappointed for 28/08. Action on Allwyn - please make sure the retailer knows about the new appointment. _x000D_12/8/2024:End User Missed appointment. Action required _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:#Update The retailer was unaware of the appointment, and reappointed for 28/08. Action on Allwyn - please make sure the retailer knows about the new appointment. _x000D_28/8/2024:#Update The retailer was unaware of the appointment, and reappointed for 28/08. Action on Allwyn - please make sure the retailer knows about the new appointment. _x000D_27/8/2024:#Update The retailer was unaware of the appointment, and reappointed for 28/08. Action on Allwyn - please make sure the retailer knows about the new appointment. _x000D_22/8/2024:#Update The retailer was unaware of the appointment, and reappointed for 28/08. Action on Allwyn - please make sure the retailer knows about the new appointment. _x000D_21/8/2024:#Update The retailer was unaware of the appointment, and reappointed for 28/08. Action on Allwyn - please make sure the retailer knows about the new appointment. _x000D_20/8/2024:#Update The retailer was unaware of the appointment, and reappointed for 28/08. Action on Allwyn - please make sure the retailer knows about the new appointment. _x000D_19/8/2024:#Update The retailer was unaware of the appointment, and reappointed for 28/08. Action on Allwyn - please make sure the retailer knows about the new appointment. _x000D_19/8/2024:01578423 _x000D_16/8/2024:#Update The retailer was unaware of the appointment, and reappointed for 28/08. Action on Allwyn - please make sure the retailer knows about the new appointment. _x000D_15/8/2024:#Update The retailer was unaware of the appointment, and reappointed for 28/08. Action on Allwyn - please make sure the retailer knows about the new appointment. _x000D_14/8/2024:#Update The retailer was unaware of the appointment, and reappointed for 28/08. Action on Allwyn - please make sure the retailer knows about the new appointment. _x000D_13/8/2024:#Update The retailer was unaware of the appointment, and reappointed for 28/08. Action on Allwyn - please make sure the retailer knows about the new appointment. _x000D_12/8/2024:End User Missed appointment. Action required _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_0 | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFS1056998 | 30017386 | 2.Commissioning | AM |  | 2024-08-12 | 2024-08-28 |  | 0 | [11 empty] | 0
1591 | 672250 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Spar | GLASGOW | G62 6PB | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_0 | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | CSL Checking | 30021839 | 1.Provisioning | AM |  | 2024-08-12 |  |  | 0 | [11 empty] | 0 | 672250
1592 | 465662 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Premier Stores | NORTH SHIELDS | NE29 8RW | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Silver Address Issue | 30021836 | 1.Provisioning | AM |  | 2024-08-12 |  |  | 0 | [11 empty] | 0
1593 | 665179 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Nisa | WIMBORNE | BH21 1SQ | 2024-07-11 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:Order Completed _x000D_12/8/2024:Order Completed _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:Order Completed _x000D_12/8/2024:Order Completed _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043852 | 30017440 | 3.In life | AM |  | 2024-08-12 | 2024-08-12 | 2024-08-12 09:19 | 1 |  |  |  | 2024-09-04 |  |  |  | 2024-09-04 | 242005011038 | 242005011038 | 2024-09-05 | 1
1594 | 468894 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Vivo | BALLYMENA | BT42 4JP | 2024-07-11 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:Order Completed _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:Order Completed _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1057015 | 30017307 | 6.Failed router install | AM |  | 2024-08-12 | 2024-08-12 | 2024-08-12 11:40 | 1 |  |  |  | 2024-09-03 |  |  |  | 2024-09-03 | 23A004952895 | 23A004952895 | 2024-09-04 | 1
1595 | 632999 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Davids Kitchen | FALKIRK | FK2 7EG | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Silver Address Issue | 30017756 | 1.Provisioning | AM |  | 2024-08-12 |  |  | 0 | [11 empty] | 0
1596 | 639456 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Gable Stores | WEST DRAYTON | UB7 0AL | 2024-07-11 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:Order Completed _x000D_12/8/2024:Order Completed _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Supplier Delay - Step-1 work required. Our Suppliers have given us a review date of 25/07/2024 _x000D_18/7/2024:#Update - Supplier Delay - Step-1 work required. Our Suppliers have given us a review date of 25/07/2024 _x000D_17/7/2024:A network engineering task is required to provision this order. The order will now follow the KCI2 Assure process. KCI2 with a confirmed end customer appointment will be sent once the task has completed. CSL Note: Invalid appointment slot received CSL Not _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:Order Completed _x000D_12/8/2024:Order Completed _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Supplier Delay - Step-1 work required. Our Suppliers have given us a review date of 25/07/2024 _x000D_18/7/2024:#Update - Supplier Delay - Step-1 work required. Our Suppliers have given us a review date of 25/07/2024 _x000D_17/7/2024:A network engineering task is required to provision this order. The order will now follow the KCI2 Assure process. KCI2 with a confirmed end customer appointment will be sent once the task has completed. CSL Note: Invalid appointment slot received CSL Not _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043849 | 30017484 | 6.Failed router install | AM |  | 2024-08-12 | 2024-08-12 | 2024-08-12 08:54 | 1 |  |  |  | 2024-08-29 |  |  |  | 2024-08-29 | 242005011143 | 242005011143 | 2024-08-30 | 1
1597 | 627908 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Russells Food & Drink | LARNE | BT40 2EF | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2421502 | 30017782 | 1.Provisioning | AM |  | 2024-08-12 | 2024-09-06 |  | 0 | [11 empty] | 0
1598 | 648984 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Budgens | SLOUGH | SL3 0JQ | 2024-08-14 | 16/8/2024:#Update - Multiskilled engineer work is required. Our Suppliers have given us a review date of 19/08/2024 _x000D_15/8/2024:#Update - Multiskilled engineer work is required. Our Suppliers have given us a review date of 19/08/2024 _x000D_14/8/2024:#Update - Multiskilled engineer work is required. Our Suppliers have given us a review date of 19/08/2024 _x000D_13/8/2024:Supplier Delay: KCI-3 (Order Completed) Delayed in Processing. _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:#Update - Multiskilled engineer work is required. Our Suppliers have given us a review date of 19/08/2024 _x000D_15/8/2024:#Update - Multiskilled engineer work is required. Our Suppliers have given us a review date of 19/08/2024 _x000D_14/8/2024:#Update - Multiskilled engineer work is required. Our Suppliers have given us a review date of 19/08/2024 _x000D_13/8/2024:Supplier Delay: KCI-3 (Order Completed) Delayed in Processing. _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1055987 | 30017725 | 2.Commissioning | AM |  | 2024-08-12 | 2024-08-12 | 2024-08-13 15:46 | 1 |  |  |  | 2024-09-05 | [7 empty] | 0
1599 | 486421 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Spar Stores | ROSS-ON-WYE | HR9 7EA | 2024-07-11 | 6/9/2024:#Update - Allwyn advised possible candidate for Site Type 3/mobile only - to be confirmed _x000D_5/9/2024:#Update - Allwyn advised possible candidate for Site Type 3/mobile only - to be confirmed _x000D_4/9/2024:#Update - Allwyn advised possible candidate for Site Type 3/mobile only - to be confirmed _x000D_3/9/2024:#Update - Allwyn advised possible candidate for Site Type 3/mobile only - to be confirmed _x000D_2/9/2024:#Update - NFA - Allwyn confirmed new install date 30/08 with retailer _x000D_29/8/2024:#Update - NFA - Allwyn confirmed new install date 30/08 with retailer _x000D_28/8/2024:#Update - NFA - Allwyn confirmed new install date 30/08 with retailer _x000D_27/8/2024:#Update - Engineer was unable to complete the task because end customer’s IT team are required to fit trunking system for existing internal cabling first. Action - Allwyn to confirm retailer will complete this before reappointing _x000D_22/8/2024:#Update - Engineer was unable to complete the task because end customer’s IT team are required to fit trunking system for existing internal cabling first. Action - Allwyn to confirm retailer will complete this before reappointing _x000D_21/8/2024:#Update - Engineer was unable to complete the task because end customer’s IT team are required to fit trunking system for existing internal cabling first. Action - Allwyn to confirm retailer will complete this before reappointing _x000D_20/8/2024:Your order has been delayed by our Suppliers due to Multiskilled Engineer/ Assistance being required to complete the installation. Order now appointed for 30/08/2024 AM slot. _x000D_19/8/2024:Your order has been delayed by our Suppliers due to Multiskilled Engineer/ Assistance being required to complete the installation. Order now appointed for 30/08/2024 AM slot. _x000D_19/8/2024:13/08/2024 16:01 _x000D_16/8/2024:Your order has been delayed by our Suppliers due to Multiskilled Engineer/ Assistance being required to complete the installation. Order now appointed for 30/08/2024 AM slot. _x000D_15/8/2024:Your order has been delayed by our Suppliers due to Multiskilled Engineer/ Assistance being required to complete the installation. Order now appointed for 30/08/2024 AM slot. _x000D_14/8/2024:Your order has been delayed by our Suppliers due to Multiskilled Engineer/ Assistance being required to complete the installation. Order now appointed for 30/08/2024 AM slot. _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:17/07/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_23/7/2024:17/07/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_22/7/2024:17/07/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_22/7/2024:17/07/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn advised possible candidate for Site Type 3/mobile only - to be confirmed _x000D_6/9/2024:#Update - Allwyn advised possible candidate for Site Type 3/mobile only - to be confirmed _x000D_5/9/2024:#Update - Allwyn advised possible candidate for Site Type 3/mobile only - to be confirmed _x000D_4/9/2024:#Update - Allwyn advised possible candidate for Site Type 3/mobile only - to be confirmed _x000D_3/9/2024:#Update - Allwyn advised possible candidate for Site Type 3/mobile only - to be confirmed _x000D_2/9/2024:#Update - NFA - Allwyn confirmed new install date 30/08 with retailer _x000D_29/8/2024:#Update - NFA - Allwyn confirmed new install date 30/08 with retailer _x000D_28/8/2024:#Update - NFA - Allwyn confirmed new install date 30/08 with retailer _x000D_27/8/2024:#Update - Engineer was unable to complete the task because end customer’s IT team are required to fit trunking system for existing internal cabling first. Action - Allwyn to confirm retailer will complete this before reappointing _x000D_22/8/2024:#Update - Engineer was unable to complete the task because end customer’s IT team are required to fit trunking system for existing internal cabling first. Action - Allwyn to confirm retailer will complete this before reappointing _x000D_21/8/2024:#Update - Engineer was unable to complete the task because end customer’s IT team are required to fit trunking system for existing internal cabling first. Action - Allwyn to confirm retailer will complete this before reappointing _x000D_20/8/2024:Your order has been delayed by our Suppliers due to Multiskilled Engineer/ Assistance being required to complete the installation. Order now appointed for 30/08/2024 AM slot. _x000D_19/8/2024:Your order has been delayed by our Suppliers due to Multiskilled Engineer/ Assistance being required to complete the installation. Order now appointed for 30/08/2024 AM slot. _x000D_19/8/2024:13/08/2024 16:01 _x000D_16/8/2024:Your order has been delayed by our Suppliers due to Multiskilled Engineer/ Assistance being required to complete the installation. Order now appointed for 30/08/2024 AM slot. _x000D_15/8/2024:Your order has been delayed by our Suppliers due to Multiskilled Engineer/ Assistance being required to complete the installation. Order now appointed for 30/08/2024 AM slot. _x000D_14/8/2024:Your order has been delayed by our Suppliers due to Multiskilled Engineer/ Assistance being required to complete the installation. Order now appointed for 30/08/2024 AM slot. _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:17/07/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_23/7/2024:17/07/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_22/7/2024:17/07/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_22/7/2024:17/07/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 23/07/2024. We will continue to provide update as they become available. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | Update: Order Amended | #Update - Allwyn advised possible candidate for Site Type 3/mobile only - to be confirmed |  |  |  |  | 2.Allwyn to arrange access | VFS1055290 | 30017762 | 1.Provisioning | AM |  | 2024-08-12 | 2024-08-30 |  | 0 | [11 empty] | 0
1600 | 413460 |  | Batch 6 Aug 24 | Type 3 | SoGEA/Mobile | Nisa | ARMAGH | BT60 1PJ | 2024-07-11 | 6/9/2024:#Update Moving to site type 3 _x000D_5/9/2024:#Update Moving to site type 3 _x000D_4/9/2024:#Update Moving to site type 3 _x000D_3/9/2024:#Update Moving to site type 3 _x000D_2/9/2024:#Update Moving to site type 3 _x000D_29/8/2024:#Update Moving to site type 3 _x000D_28/8/2024:#Update Moving to site type 3 _x000D_27/8/2024:#Update Moving to site type 3 _x000D_22/8/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_21/8/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_20/8/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_19/8/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_19/8/2024:01578829 _x000D_16/8/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_15/8/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_14/8/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_13/8/2024:End User Missed appointment. Action required _x000D_12/8/2024:End User Missed appointment. Action required _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update Moving to site type 3 _x000D_6/9/2024:#Update Moving to site type 3 _x000D_5/9/2024:#Update Moving to site type 3 _x000D_4/9/2024:#Update Moving to site type 3 _x000D_3/9/2024:#Update Moving to site type 3 _x000D_2/9/2024:#Update Moving to site type 3 _x000D_29/8/2024:#Update Moving to site type 3 _x000D_28/8/2024:#Update Moving to site type 3 _x000D_27/8/2024:#Update Moving to site type 3 _x000D_22/8/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_21/8/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_20/8/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_19/8/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_19/8/2024:01578829 _x000D_16/8/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_15/8/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_14/8/2024:#Update Allwyn to advise how they'd like to proceed. _x000D_13/8/2024:End User Missed appointment. Action required _x000D_12/8/2024:End User Missed appointment. Action required _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update Moving to site type 3 |  |  |  |  | 3.Allwyn to arrange rtr install | VFS1043848 | 30017485 | 2.Commissioning | AM |  | 2024-08-12 | 2024-08-12 |  | 0 |  |  |  | 2024-09-27 | [7 empty] | 0
1601 | 672646 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | SPAR SHOP | ST. AUSTELL | PL26 8PD | 2024-07-11 | 6/9/2024:#Update - Network Planning issues- Awaiting further updates. _x000D_5/9/2024:#Update - Network Planning issues- Awaiting further updates. _x000D_4/9/2024:#Update - Network Planning issues- Awaiting further updates. _x000D_3/9/2024:#Update - Network Planning issues- Awaiting further updates. _x000D_2/9/2024:#Update - Network Planning issues- Awaiting further updates. _x000D_29/8/2024:#Update - Network Planning issues- Awaiting further updates. _x000D_28/8/2024:#Update - Network Planning issues- Awaiting further updates. _x000D_27/8/2024:#Update - Network Planning issues- Awaiting further updates. _x000D_22/8/2024:#Update - Network Planning issues- Awaiting further updates. _x000D_21/8/2024:#Update - Network Planning issues- Awaiting further updates. _x000D_20/8/2024:#Update - Network Planning issues- Awaiting further updates. _x000D_13/8/2024:#Update - Network Planning issues- Awaiting further updates. _x000D_12/8/2024:#Update - Network Planning issues- Awaiting further updates. _x000D_9/8/2024:#Update - Network Planning issues- Awaiting further updates. _x000D_8/8/2024:17/07/2024 _x000D_6/8/2024:17/07/2024 _x000D_5/8/2024:17/07/2024 _x000D_2/8/2024:17/07/2024 _x000D_1/8/2024:17/07/2024 _x000D_31/7/2024:17/07/2024 _x000D_31/7/2024:17/07/2024 _x000D_30/7/2024:#Update - Network Planning issues- Awaiting further updates. _x000D_29/7/2024:#Update - Network Planning issues- Awaiting further updates. _x000D_29/7/2024:01497771 _x000D_26/7/2024:01497771 _x000D_24/7/2024:#Update - Network Planning issues- Awaiting further updates. _x000D_23/7/2024:#Update - Network Planning issues- Awaiting further updates. _x000D_22/7/2024:#Update - Network Planning issues- Awaiting further updates. _x000D_22/7/2024:#Update - Network Planning issues- Awaiting further updates. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Network Planning issues- Awaiting further updates. _x000D_6/9/2024:#Update - Network Planning issues- Awaiting further updates. _x000D_5/9/2024:#Update - Network Planning issues- Awaiting further updates. _x000D_4/9/2024:#Update - Network Planning issues- Awaiting further updates. _x000D_3/9/2024:#Update - Network Planning issues- Awaiting further updates. _x000D_2/9/2024:#Update - Network Planning issues- Awaiting further updates. _x000D_29/8/2024:#Update - Network Planning issues- Awaiting further updates. _x000D_28/8/2024:#Update - Network Planning issues- Awaiting further updates. _x000D_27/8/2024:#Update - Network Planning issues- Awaiting further updates. _x000D_22/8/2024:#Update - Network Planning issues- Awaiting further updates. _x000D_21/8/2024:#Update - Network Planning issues- Awaiting further updates. _x000D_20/8/2024:#Update - Network Planning issues- Awaiting further updates. _x000D_13/8/2024:#Update - Network Planning issues- Awaiting further updates. _x000D_12/8/2024:#Update - Network Planning issues- Awaiting further updates. _x000D_9/8/2024:#Update - Network Planning issues- Awaiting further updates. _x000D_8/8/2024:17/07/2024 _x000D_6/8/2024:17/07/2024 _x000D_5/8/2024:17/07/2024 _x000D_2/8/2024:17/07/2024 _x000D_1/8/2024:17/07/2024 _x000D_31/7/2024:17/07/2024 _x000D_31/7/2024:17/07/2024 _x000D_30/7/2024:#Update - Network Planning issues- Awaiting further updates. _x000D_29/7/2024:#Update - Network Planning issues- Awaiting further updates. _x000D_29/7/2024:01497771 _x000D_26/7/2024:01497771 _x000D_24/7/2024:#Update - Network Planning issues- Awaiting further updates. _x000D_23/7/2024:#Update - Network Planning issues- Awaiting further updates. _x000D_22/7/2024:#Update - Network Planning issues- Awaiting further updates. _x000D_22/7/2024:#Update - Network Planning issues- Awaiting further updates. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | Your order has come off a waiters list and will now be fulfilled. | #Update - Network Planning issues- Awaiting further updates. |  |  |  |  | 2.Allwyn to arrange access | VFS1055288 | 30017704 | 1.Provisioning |  |  | 2024-08-13 |  |  | 0 | [11 empty] | 0
1602 | 648368 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Adidas Flagship Store | LONDON | W1C 2PH | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_17/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_17/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Silver Address Issue | 30017767 | 1.Provisioning | AM |  | 2024-08-13 |  |  | 0 | [11 empty] | 0
1603 | 665148 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Post Office | ISLEWORTH | TW7 4BX | 2024-08-14 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:Order Completed _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:Order Completed _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1055283 | 30017686 | 3.In life | AM |  | 2024-08-13 | 2024-08-13 | 2024-08-13 08:33 | 1 |  |  |  | 2024-09-05 |  |  |  | 2024-09-05 | 242005011015 | 242005011015 | 2024-09-06 | 1
1604 | 617409 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | GT News - Meadowhall Bus Station | SHEFFIELD | S9 1EQ | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Address query | 30017745 | 1.Provisioning | AM |  | 2024-08-13 |  |  | 0 | [11 empty] | 0
1605 | 469204 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Spar | BELFAST | BT15 2GW | 2024-08-14 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFP2421497 | 30017765 | 2.Commissioning | AM |  | 2024-08-13 | 2024-08-13 | 2024-08-13 14:16 | 1 |  |  |  | 2024-09-10 | [7 empty] | 0
1606 | 664448 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Day Today | GLASGOW | G75 8TT | 2024-08-14 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:Update: Order Completed by Supplier _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:Update: Order Completed by Supplier _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1057087 | 30017395 | 3.In life | AM |  | 2024-08-13 | 2024-08-13 | 2024-08-13 10:17 | 1 |  |  |  | 2024-09-04 |  |  |  | 2024-09-04 | 23A004952708 | 23A004952708 | 2024-09-05 | 1
1607 | 657535 |  | Batch 6 Aug 24 | Type 1 | SURE/Mobile | Governors Hill Store | ISLE OF MAN | IM2 7EA | 2024-08-16 | 6/9/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_5/9/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_4/9/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_3/9/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_2/9/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_29/8/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_28/8/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_27/8/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_22/8/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_21/8/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_20/8/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_19/8/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_19/8/2024:01501626 _x000D_16/8/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_15/8/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_14/8/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_13/8/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_12/8/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_9/8/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_8/8/2024:22/07/2024 _x000D_6/8/2024:22/07/2024 _x000D_5/8/2024:22/07/2024 _x000D_2/8/2024:22/07/2024 _x000D_1/8/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_30/7/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_29/7/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_29/7/2024:01501626 _x000D_26/7/2024:01501626 _x000D_24/7/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_23/7/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_6/9/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_5/9/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_4/9/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_3/9/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_2/9/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_29/8/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_28/8/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_27/8/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_22/8/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_21/8/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_20/8/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_19/8/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_19/8/2024:01501626 _x000D_16/8/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_15/8/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_14/8/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_13/8/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_12/8/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_9/8/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_8/8/2024:22/07/2024 _x000D_6/8/2024:22/07/2024 _x000D_5/8/2024:22/07/2024 _x000D_2/8/2024:22/07/2024 _x000D_1/8/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_31/7/2024:22/07/2024 _x000D_30/7/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_29/7/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_29/7/2024:01501626 _x000D_26/7/2024:01501626 _x000D_24/7/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_23/7/2024:#Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update Allwyn to speak to the retailer regarding the appointment and advise if it's suitable. |  |  |  |  | 2.Allwyn to arrange access | SURE | 30017286 | 2.Commissioning | AM |  | 2024-08-12 | 2024-08-15 |  | 0 | [11 empty] | 0
1608 | 664156 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Vivo | CARRICKFERGUS | BT38 7QN | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2422536 | 30017410 | 1.Provisioning | AM |  | 2024-08-13 | 2024-09-06 |  | 0 | [11 empty] | 0
1609 | 475292 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Kim Newsagent | LONDON | N17 7QX | 2024-08-14 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043843 | 30017423 | 2.Commissioning | AM |  | 2024-08-13 | 2024-08-13 | 2024-08-13 13:49 | 1 |  |  |  | 2024-09-06 | [7 empty] | 0
1610 | 610199 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Shell Londis | CAERNARFON | LL55 2SS | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_18/7/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_18/7/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Address query | 30017778 | 1.Provisioning | AM |  | 2024-08-13 |  |  | 0 | [11 empty] | 0
1611 | 668980 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Post Office | CRAIGAVON | BT62 1LH | 2024-08-14 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:Order Completed _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:Order Completed _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043842 | 30017426 | 2.Commissioning | AM |  | 2024-08-13 | 2024-08-13 | 2024-08-13 09:34 | 1 |  |  |  | 2024-09-10 | [7 empty] | 0
1612 | 667624 |  | Batch 6 Aug 24 | Type 1 | KCOM/Mobile | Booze Blitz | HULL | HU8 9PD | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | BUS0004476 | 30017267 | 1.Provisioning | AM | 2024-08-13 | 2024-08-13 |  |  | 0 | [11 empty] | 0
1613 | 437040 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | R M S News & Wine | LIVERPOOL | L19 2JG | 2024-08-14 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFP2422535 | 30017330 | 2.Commissioning | AM |  | 2024-08-13 | 2024-08-13 | 2024-08-13 12:18 | 1 |  |  |  | 2024-09-05 | [7 empty] | 0
1614 | 110285 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Londis Supermarket | PONTEFRACT | WF9 5AJ | 2024-07-11 | 6/9/2024:#Update Retailer happy with new appointment 11/09, AM. _x000D_5/9/2024:#Update Retailer happy with new appointment 11/09, AM. _x000D_4/9/2024:#Update Retailer happy with new appointment 11/09, AM. _x000D_3/9/2024:#Update Retailer happy with new appointment 11/09, AM. _x000D_2/9/2024:#Update Retailer happy with new appointment 11/09, AM. _x000D_29/8/2024:#Update Retailer happy with new appointment 11/09, AM. _x000D_28/8/2024:#Update Retailer happy with new appointment 11/09, AM. _x000D_27/8/2024:#Update Retailer happy with new appointment 11/09, AM. _x000D_22/8/2024:#Update Retailer happy with new appointment 11/09, AM. _x000D_21/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_20/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_19/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_19/8/2024:14/08/2024 13:44 _x000D_16/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_15/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_14/8/2024:End User Missed appointment. Action required _x000D_13/8/2024:End User Missed appointment. Action required _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update Retailer happy with new appointment 11/09, AM. _x000D_6/9/2024:#Update Retailer happy with new appointment 11/09, AM. _x000D_5/9/2024:#Update Retailer happy with new appointment 11/09, AM. _x000D_4/9/2024:#Update Retailer happy with new appointment 11/09, AM. _x000D_3/9/2024:#Update Retailer happy with new appointment 11/09, AM. _x000D_2/9/2024:#Update Retailer happy with new appointment 11/09, AM. _x000D_29/8/2024:#Update Retailer happy with new appointment 11/09, AM. _x000D_28/8/2024:#Update Retailer happy with new appointment 11/09, AM. _x000D_27/8/2024:#Update Retailer happy with new appointment 11/09, AM. _x000D_22/8/2024:#Update Retailer happy with new appointment 11/09, AM. _x000D_21/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_20/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_19/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_19/8/2024:14/08/2024 13:44 _x000D_16/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_15/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_14/8/2024:End User Missed appointment. Action required _x000D_13/8/2024:End User Missed appointment. Action required _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update Retailer happy with new appointment 11/09, AM. |  |  |  |  | 2.Allwyn to arrange access | VFS1043837 | 30017483 | 1.Provisioning | AM |  | 2024-08-13 | 2024-08-13 |  | 0 | [11 empty] | 0
1615 | 665110 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Post Office | LONDONDERRY | BT47 2DT | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Silver Address Issue | 30017341 | 1.Provisioning | AM |  | 2024-08-13 |  |  | 0 | [11 empty] | 0
1616 | 463714 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Premier M&H Stores | SWANSEA | SA1 6SZ | 2024-08-14 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFP2423355 | 30017586 | 2.Commissioning | AM |  | 2024-08-13 | 2024-08-13 | 2024-08-13 11:01 | 1 |  |  |  | 2024-09-05 | [7 empty] | 0
1617 | 473221 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Post Office | NOTTINGHAM | NG8 2DS | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2422534 | 30017390 | 1.Provisioning | AM |  | 2024-08-13 | 2024-09-06 |  | 0 | [11 empty] | 0
1618 | 431009 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Sproats Newsagents | CLEATOR MOOR | CA25 5LL | 2024-08-14 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:Update: Order Completed by Supplier _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:Update: Order Completed by Supplier _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1056991 | 30017340 | 2.Commissioning | AM |  | 2024-08-13 | 2024-08-13 | 2024-08-13 10:10 | 1 |  |  |  | 2024-09-09 | [7 empty] | 0
1619 | 477230 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Dan Gregorys Service Station | NEWRY | BT35 7EE | 2024-07-11 | 6/9/2024:#Update Retailer is getting an extension and moving the lotto machine. She told the engineer that she will not be ready for the installation until end of September. OR cancelled the order based off this feedback. Deployment team will be back in contact once the retailer is ready. Order will need to be reraised. _x000D_5/9/2024:#Update Retailer is getting an extension and moving the lotto machine. She told the engineer that she will not be ready for the installation until end of September. OR cancelled the order based off this feedback. Deployment team will be back in contact once the retailer is ready. Order will need to be reraised. _x000D_4/9/2024:#Update Retailer is getting an extension and moving the lotto machine. She told the engineer that she will not be ready for the installation until end of September. OR cancelled the order based off this feedback. Deployment team will be back in contact once the retailer is ready. Order will need to be reraised. _x000D_3/9/2024:#Update Retailer is getting an extension and moving the lotto machine. She told the engineer that she will not be ready for the installation until end of September. OR cancelled the order based off this feedback. Deployment team will be back in contact once the retailer is ready. Order will need to be reraised. _x000D_2/9/2024:#Update Retailer is getting an extension and moving the lotto machine. She told the engineer that she will not be ready for the installation until end of September. OR cancelled the order based off this feedback. Deployment team will be back in contact once the retailer is ready. Order will need to be reraised. _x000D_29/8/2024:#Update Retailer is getting an extension and moving the lotto machine. She told the engineer that she will not be ready for the installation until end of September. OR cancelled the order based off this feedback. Deployment team will be back in contact once the retailer is ready. Order will need to be reraised. _x000D_28/8/2024:#Update Retailer is getting an extension and moving the lotto machine. She told the engineer that she will not be ready for the installation until end of September. OR cancelled the order based off this feedback. Deployment team will be back in contact once the retailer is ready. Order will need to be reraised. _x000D_27/8/2024:#Update Retailer is getting an extension and moving the lotto machine. She told the engineer that she will not be ready for the installation until end of September. OR cancelled the order based off this feedback. Deployment team will be back in contact once the retailer is ready. Order will need to be reraised. _x000D_22/8/2024:#Update Retailer is getting an extension and moving the lotto machine. She told the engineer that she will not be ready for the installation until end of September. OR cancelled the order based off this feedback. Deployment team will be back in contact once the retailer is ready. Order will need to be reraised. _x000D_21/8/2024:#Update Retailer is getting an extension and moving the lotto machine. She told the engineer that she will not be ready for the installation until end of September. OR cancelled the order based off this feedback. Deployment team will be back in contact once the retailer is ready. Order will need to be reraised. _x000D_20/8/2024:#Update Retailer is getting an extension and moving the lotto machine. She told the engineer that she will not be ready for the installation until end of September. OR cancelled the order based off this feedback. Deployment team will be back in contact once the retailer is ready. Order will need to be reraised. _x000D_19/8/2024:#Update Retailer is getting an extension and moving the lotto machine. She told the engineer that she will not be ready for the installation until end of September. OR cancelled the order based off this feedback. Deployment team will be back in contact once the retailer is ready. Order will need to be reraised. _x000D_19/8/2024:01501449 _x000D_16/8/2024:#Update Retailer is getting an extension and moving the lotto machine. She told the engineer that she will not be ready for the installation until end of September. OR cancelled the order based off this feedback. Deployment team will be back in contact once the retailer is ready. Order will need to be reraised. _x000D_15/8/2024:#Update Retailer is getting an extension and moving the lotto machine. She told the engineer that she will not be ready for the installation until end of September. OR cancelled the order based off this feedback. Deployment team will be back in contact once the retailer is ready. Order will need to be reraised. _x000D_14/8/2024:#Update Retailer is getting an extension and moving the lotto machine. She told the engineer that she will not be ready for the installation until end of September. OR cancelled the order based off this feedback. Deployment team will be back in contact once the retailer is ready. Order will need to be reraised. _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:Your order has been delayed due to FTTP KCI2 Assure KCI-D response Queue Order Management exception. Our Suppliers have given us a review date of 02/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot r _x000D_2/8/2024:Your order has been delayed due to FTTP KCI2 Assure KCI-D response Queue Order Management exception. Our Suppliers have given us a review date of 02/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot r _x000D_1/8/2024:Your order has been delayed due to FTTP KCI2 Assure KCI-D response Queue Order Management exception. Our Suppliers have given us a review date of 02/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot r _x000D_31/7/2024:Your order has been delayed due to FTTP KCI2 Assure KCI-D response Queue Order Management exception. Our Suppliers have given us a review date of 02/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot r _x000D_31/7/2024:37716 _x000D_30/7/2024:Your order has been delayed due to FTTP KCI2 Assure KCI-D response Queue Order Management exception. Our Suppliers have given us a review date of 02/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot r _x000D_29/7/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:24/07/2024 09:18 _x000D_26/7/2024:24/07/2024 09:18 _x000D_24/7/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_23/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update Retailer is getting an extension and moving the lotto machine. She told the engineer that she will not be ready for the installation until end of September. OR cancelled the order based off this feedback. Deployment team will be back in contact once the retailer is ready. Order will need to be reraised. _x000D_6/9/2024:#Update Retailer is getting an extension and moving the lotto machine. She told the engineer that she will not be ready for the installation until end of September. OR cancelled the order based off this feedback. Deployment team will be back in contact once the retailer is ready. Order will need to be reraised. _x000D_5/9/2024:#Update Retailer is getting an extension and moving the lotto machine. She told the engineer that she will not be ready for the installation until end of September. OR cancelled the order based off this feedback. Deployment team will be back in contact once the retailer is ready. Order will need to be reraised. _x000D_4/9/2024:#Update Retailer is getting an extension and moving the lotto machine. She told the engineer that she will not be ready for the installation until end of September. OR cancelled the order based off this feedback. Deployment team will be back in contact once the retailer is ready. Order will need to be reraised. _x000D_3/9/2024:#Update Retailer is getting an extension and moving the lotto machine. She told the engineer that she will not be ready for the installation until end of September. OR cancelled the order based off this feedback. Deployment team will be back in contact once the retailer is ready. Order will need to be reraised. _x000D_2/9/2024:#Update Retailer is getting an extension and moving the lotto machine. She told the engineer that she will not be ready for the installation until end of September. OR cancelled the order based off this feedback. Deployment team will be back in contact once the retailer is ready. Order will need to be reraised. _x000D_29/8/2024:#Update Retailer is getting an extension and moving the lotto machine. She told the engineer that she will not be ready for the installation until end of September. OR cancelled the order based off this feedback. Deployment team will be back in contact once the retailer is ready. Order will need to be reraised. _x000D_28/8/2024:#Update Retailer is getting an extension and moving the lotto machine. She told the engineer that she will not be ready for the installation until end of September. OR cancelled the order based off this feedback. Deployment team will be back in contact once the retailer is ready. Order will need to be reraised. _x000D_27/8/2024:#Update Retailer is getting an extension and moving the lotto machine. She told the engineer that she will not be ready for the installation until end of September. OR cancelled the order based off this feedback. Deployment team will be back in contact once the retailer is ready. Order will need to be reraised. _x000D_22/8/2024:#Update Retailer is getting an extension and moving the lotto machine. She told the engineer that she will not be ready for the installation until end of September. OR cancelled the order based off this feedback. Deployment team will be back in contact once the retailer is ready. Order will need to be reraised. _x000D_21/8/2024:#Update Retailer is getting an extension and moving the lotto machine. She told the engineer that she will not be ready for the installation until end of September. OR cancelled the order based off this feedback. Deployment team will be back in contact once the retailer is ready. Order will need to be reraised. _x000D_20/8/2024:#Update Retailer is getting an extension and moving the lotto machine. She told the engineer that she will not be ready for the installation until end of September. OR cancelled the order based off this feedback. Deployment team will be back in contact once the retailer is ready. Order will need to be reraised. _x000D_19/8/2024:#Update Retailer is getting an extension and moving the lotto machine. She told the engineer that she will not be ready for the installation until end of September. OR cancelled the order based off this feedback. Deployment team will be back in contact once the retailer is ready. Order will need to be reraised. _x000D_19/8/2024:01501449 _x000D_16/8/2024:#Update Retailer is getting an extension and moving the lotto machine. She told the engineer that she will not be ready for the installation until end of September. OR cancelled the order based off this feedback. Deployment team will be back in contact once the retailer is ready. Order will need to be reraised. _x000D_15/8/2024:#Update Retailer is getting an extension and moving the lotto machine. She told the engineer that she will not be ready for the installation until end of September. OR cancelled the order based off this feedback. Deployment team will be back in contact once the retailer is ready. Order will need to be reraised. _x000D_14/8/2024:#Update Retailer is getting an extension and moving the lotto machine. She told the engineer that she will not be ready for the installation until end of September. OR cancelled the order based off this feedback. Deployment team will be back in contact once the retailer is ready. Order will need to be reraised. _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:Your order has been delayed due to FTTP KCI2 Assure KCI-D response Queue Order Management exception. Our Suppliers have given us a review date of 02/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot r _x000D_2/8/2024:Your order has been delayed due to FTTP KCI2 Assure KCI-D response Queue Order Management exception. Our Suppliers have given us a review date of 02/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot r _x000D_1/8/2024:Your order has been delayed due to FTTP KCI2 Assure KCI-D response Queue Order Management exception. Our Suppliers have given us a review date of 02/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot r _x000D_31/7/2024:Your order has been delayed due to FTTP KCI2 Assure KCI-D response Queue Order Management exception. Our Suppliers have given us a review date of 02/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot r _x000D_31/7/2024:37716 _x000D_30/7/2024:Your order has been delayed due to FTTP KCI2 Assure KCI-D response Queue Order Management exception. Our Suppliers have given us a review date of 02/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot r _x000D_29/7/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:24/07/2024 09:18 _x000D_26/7/2024:24/07/2024 09:18 _x000D_24/7/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_23/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update Retailer is getting an extension and moving the lotto machine. She told the engineer that she will not be ready for the installation until end of September. OR cancelled the order based off this feedback. Deployment team will be back in contact once the retailer is ready. Order will need to be reraised. |  |  |  |  | 2.Allwyn to arrange access | VFP2422532 | 30017385 | 1.Provisioning | AM |  | 2024-08-13 |  |  | 0 | [11 empty] | 0
1620 | 261634 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Party Party | LONDON | E8 2NP | 2024-08-14 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. _x000D_18/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. _x000D_17/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:Order Completed _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. _x000D_18/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. _x000D_17/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFP2422531 | 30017388 | 2.Commissioning | AM |  | 2024-08-13 | 2024-08-13 | 2024-08-13 13:39 | 1 |  |  |  | 2024-09-06 | [7 empty] | 0
1621 | 646139 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Spar Stores | ROWLEY REGIS | B65 8EW | 2024-08-14 | 16/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. _x000D_15/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. _x000D_14/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. _x000D_13/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. _x000D_12/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. _x000D_9/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. _x000D_8/8/2024:16/07/2024 _x000D_6/8/2024:16/07/2024 _x000D_5/8/2024:16/07/2024 _x000D_2/8/2024:16/07/2024 _x000D_1/8/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_30/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. _x000D_29/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. _x000D_29/7/2024:01496177 _x000D_26/7/2024:01496177 _x000D_24/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. _x000D_23/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. _x000D_22/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. _x000D_22/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. _x000D_15/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. _x000D_14/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. _x000D_13/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. _x000D_12/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. _x000D_9/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. _x000D_8/8/2024:16/07/2024 _x000D_6/8/2024:16/07/2024 _x000D_5/8/2024:16/07/2024 _x000D_2/8/2024:16/07/2024 _x000D_1/8/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_30/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. _x000D_29/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. _x000D_29/7/2024:01496177 _x000D_26/7/2024:01496177 _x000D_24/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. _x000D_23/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. _x000D_22/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. _x000D_22/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1055269 | 30017733 | 3.In life | AM |  | 2024-08-13 | 2024-08-13 | 2024-08-13 15:14 | 1 |  |  |  | 2024-09-04 |  |  |  | 2024-09-04 | 238004926066 | 238004926066 | 2024-09-05 | 1
1622 | 644652 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | North Road Stores | TIPTON | DY4 0XF | 2024-07-11 | 6/9/2024:#Update Retailer confirmed 25/09, AM. _x000D_5/9/2024:#Update Retailer confirmed 25/09, AM. _x000D_4/9/2024:#Update Retailer confirmed 25/09, AM. _x000D_3/9/2024:#Update Retailer confirmed 25/09, AM. _x000D_2/9/2024:#Update Retailer happy with 29/08, AM. _x000D_29/8/2024:#Update Retailer happy with 29/08, AM. _x000D_28/8/2024:#Update Retailer happy with 29/08, AM. _x000D_27/8/2024:#Update Customer unaware of appointment, reappointed for 29/08, AM. Action on Allwyn - ensure the retailer is aware. _x000D_22/8/2024:#Update Customer unaware of appointment, reappointed for 29/08, AM. Action on Allwyn - ensure the retailer is aware. _x000D_21/8/2024:#Update Customer unaware of appointment, reappointed for 29/08, AM. Action on Allwyn - ensure the retailer is aware. _x000D_20/8/2024:#Update Customer unaware of appointment, reappointed for 29/08, AM. Action on Allwyn - ensure the retailer is aware. _x000D_19/8/2024:#Update Customer unaware of appointment, reappointed for 29/08, AM. Action on Allwyn - ensure the retailer is aware. _x000D_19/8/2024:01581493 _x000D_16/8/2024:#Update Customer unaware of appointment, reappointed for 29/08, AM. Action on Allwyn - ensure the retailer is aware. _x000D_15/8/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024::Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 14/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_ | 9/9/2024:#Update Retailer confirmed 25/09, AM. _x000D_6/9/2024:#Update Retailer confirmed 25/09, AM. _x000D_5/9/2024:#Update Retailer confirmed 25/09, AM. _x000D_4/9/2024:#Update Retailer confirmed 25/09, AM. _x000D_3/9/2024:#Update Retailer confirmed 25/09, AM. _x000D_2/9/2024:#Update Retailer happy with 29/08, AM. _x000D_29/8/2024:#Update Retailer happy with 29/08, AM. _x000D_28/8/2024:#Update Retailer happy with 29/08, AM. _x000D_27/8/2024:#Update Customer unaware of appointment, reappointed for 29/08, AM. Action on Allwyn - ensure the retailer is aware. _x000D_22/8/2024:#Update Customer unaware of appointment, reappointed for 29/08, AM. Action on Allwyn - ensure the retailer is aware. _x000D_21/8/2024:#Update Customer unaware of appointment, reappointed for 29/08, AM. Action on Allwyn - ensure the retailer is aware. _x000D_20/8/2024:#Update Customer unaware of appointment, reappointed for 29/08, AM. Action on Allwyn - ensure the retailer is aware. _x000D_19/8/2024:#Update Customer unaware of appointment, reappointed for 29/08, AM. Action on Allwyn - ensure the retailer is aware. _x000D_19/8/2024:01581493 _x000D_16/8/2024:#Update Customer unaware of appointment, reappointed for 29/08, AM. Action on Allwyn - ensure the retailer is aware. _x000D_15/8/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024::Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 14/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_ | Update: Order Amended | #Update Retailer confirmed 25/09, AM. |  |  |  |  | 2.Allwyn to arrange access | VFP2422530 | 30017349 | 1.Provisioning | AM |  | 2024-08-13 | 2024-08-13 |  | 0 | [11 empty] | 0
1623 | 432478 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Hallglen Convenience Store | FALKIRK | FK1 2RB | 2024-08-15 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043840 | 30017476 | 2.Commissioning | AM |  | 2024-08-14 | 2024-08-14 | 2024-08-14 14:30 | 1 |  |  |  | 2024-09-05 | [7 empty] | 0
1624 | 469269 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Spar Stores | ENNISKILLEN | BT74 7PA | 2024-08-15 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043835 | 30017436 | 3.In life | AM |  | 2024-08-14 | 2024-08-14 | 2024-08-14 13:36 | 1 |  |  |  | 2024-09-04 |  |  |  | 2024-09-04 | 238004925785 | 238004925785 | 2024-09-05 | 1
1625 | 670496 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Post Office | BIRMINGHAM | B30 1RT | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Silver Address Issue | 30017777 | 1.Provisioning | AM |  | 2024-08-14 |  |  | 0 | [11 empty] | 0
1626 | 650433 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Select Convenience | ASHTON-UNDER-LYNE | OL6 6DU | 2024-08-16 | 19/8/2024:Order Completed _x000D_19/8/2024:15/08/2024 13:00 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:Supplier Delay: Missed CCD and may require further work as the engineer has retained the job for next day _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 19/8/2024:Order Completed _x000D_19/8/2024:15/08/2024 13:00 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:Supplier Delay: Missed CCD and may require further work as the engineer has retained the job for next day _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1057074 | 30017297 | 2.Commissioning | AM |  | 2024-08-14 | 2024-08-14 |  | 0 |  |  |  | 2024-09-06 | [7 empty] | 0
1627 | 629980 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Chatterton News Agency | BROMLEY | BR2 9QW | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Silver Address Issue | 30021805 | 1.Provisioning | AM |  | 2024-08-14 |  |  | 0 | [11 empty] | 0
1628 | 664771 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Barton Green Convenience | NOTTINGHAM | NG11 8SG | 2024-07-11 | 6/9/2024:#Update - requires PTW signed by retailer, Allwyn are chasing a status update _x000D_5/9/2024:#Update - requires PTW signed by retailer, Allwyn are chasing a status update _x000D_4/9/2024:#Update - requires PTW signed by retailer, Allwyn are chasing a status update _x000D_3/9/2024:#Update - requires PTW signed by retailer, Allwyn are chasing a status update _x000D_2/9/2024:#Update - requires PTW signed by retailer, Allwyn are chasing a status update _x000D_29/8/2024:#Update - requires PTW signed by retailer, Allwyn are chasing a status update _x000D_28/8/2024:#Update - order has been delayed due to Step-1 work requirement, once this is completed the install date will be generated _x000D_27/8/2024:#Update - order has been delayed due to Step-1 work requirement, once this is completed the install date will be generated _x000D_22/8/2024:#Update - order has been delayed due to Step-1 work requirement, once this is completed the install date will be generated _x000D_21/8/2024:#Update - order has been delayed due to Step-1 work requirement, once this is completed the install date will be generated _x000D_20/8/2024:Your order has been delayed. Civils work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 23/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot re _x000D_19/8/2024:Your order has been delayed. Civils work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 23/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot re _x000D_19/8/2024:16/08/2024 18:52 _x000D_16/8/2024:Supplier Delay: Issues with provision of the underground network, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/8/2024:Supplier Delay: Issues with provision of the underground network, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_14/8/2024:Your order has been delayed due to step-1 work required. Our Suppliers contacted Enduser and booked the engineer for 15/08/2024. Kindly review back on 19/08/2024 for more information. CSL Note: Invalid appointment slot received CSL Note: Invalid data rece _x000D_13/8/2024:Your order has been delayed due to step-1 work required. Our Suppliers contacted Enduser and booked the engineer for 15/08/2024. Kindly review back on 19/08/2024 for more information. CSL Note: Invalid appointment slot received CSL Note: Invalid data rece _x000D_12/8/2024:Your order has been delayed due to step-1 work required. Our Suppliers contacted Enduser and booked the engineer for 15/08/2024. Kindly review back on 19/08/2024 for more information. CSL Note: Invalid appointment slot received CSL Note: Invalid data rece _x000D_9/8/2024:Your order has been delayed due to step-1 work required. Our Suppliers contacted Enduser and booked the engineer for 15/08/2024. Kindly review back on 19/08/2024 for more information. CSL Note: Invalid appointment slot received CSL Note: Invalid data rece _x000D_8/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 09/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 09/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 09/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_2/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 09/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_1/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 02/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:36909 _x000D_30/7/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:24/07/2024 09:20 _x000D_26/7/2024:24/07/2024 09:20 _x000D_24/7/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_23/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - requires PTW signed by retailer, Allwyn are chasing a status update _x000D_6/9/2024:#Update - requires PTW signed by retailer, Allwyn are chasing a status update _x000D_5/9/2024:#Update - requires PTW signed by retailer, Allwyn are chasing a status update _x000D_4/9/2024:#Update - requires PTW signed by retailer, Allwyn are chasing a status update _x000D_3/9/2024:#Update - requires PTW signed by retailer, Allwyn are chasing a status update _x000D_2/9/2024:#Update - requires PTW signed by retailer, Allwyn are chasing a status update _x000D_29/8/2024:#Update - requires PTW signed by retailer, Allwyn are chasing a status update _x000D_28/8/2024:#Update - order has been delayed due to Step-1 work requirement, once this is completed the install date will be generated _x000D_27/8/2024:#Update - order has been delayed due to Step-1 work requirement, once this is completed the install date will be generated _x000D_22/8/2024:#Update - order has been delayed due to Step-1 work requirement, once this is completed the install date will be generated _x000D_21/8/2024:#Update - order has been delayed due to Step-1 work requirement, once this is completed the install date will be generated _x000D_20/8/2024:Your order has been delayed. Civils work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 23/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot re _x000D_19/8/2024:Your order has been delayed. Civils work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 23/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot re _x000D_19/8/2024:16/08/2024 18:52 _x000D_16/8/2024:Supplier Delay: Issues with provision of the underground network, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/8/2024:Supplier Delay: Issues with provision of the underground network, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_14/8/2024:Your order has been delayed due to step-1 work required. Our Suppliers contacted Enduser and booked the engineer for 15/08/2024. Kindly review back on 19/08/2024 for more information. CSL Note: Invalid appointment slot received CSL Note: Invalid data rece _x000D_13/8/2024:Your order has been delayed due to step-1 work required. Our Suppliers contacted Enduser and booked the engineer for 15/08/2024. Kindly review back on 19/08/2024 for more information. CSL Note: Invalid appointment slot received CSL Note: Invalid data rece _x000D_12/8/2024:Your order has been delayed due to step-1 work required. Our Suppliers contacted Enduser and booked the engineer for 15/08/2024. Kindly review back on 19/08/2024 for more information. CSL Note: Invalid appointment slot received CSL Note: Invalid data rece _x000D_9/8/2024:Your order has been delayed due to step-1 work required. Our Suppliers contacted Enduser and booked the engineer for 15/08/2024. Kindly review back on 19/08/2024 for more information. CSL Note: Invalid appointment slot received CSL Note: Invalid data rece _x000D_8/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 09/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 09/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 09/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_2/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 09/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_1/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 02/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:36909 _x000D_30/7/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:24/07/2024 09:20 _x000D_26/7/2024:24/07/2024 09:20 _x000D_24/7/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_23/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - requires PTW signed by retailer, Allwyn are chasing a status update |  |  |  |  | 2.Allwyn to arrange access | VFP2422529 | 30017346 | 1.Provisioning | AM |  | 2024-08-14 |  |  | 0 | [11 empty] | 0
1629 | 436602 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Hambrook | EPPING | CM16 7RE | 2024-08-15 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_0 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_0 | [6 empty] | 2.Allwyn to arrange access | VFS1043833 | 30017493 | 2.Commissioning | AM |  | 2024-08-14 | 2024-08-14 | 2024-08-14 13:16 | 1 |  |  |  | 2024-09-06 | [7 empty] | 0
1630 | 665168 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Nisa Local | LEEDS | LS14 2EH | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Silver Address Issue | 30021833 | 1.Provisioning | AM |  | 2024-08-14 |  |  | 0 | [11 empty] | 0
1631 | 632972 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Vivo Essentials Eden | CARRICKFERGUS | BT38 7NN | 2024-07-11 | 6/9/2024:#Update Your order has been delayed. Pole work required. Our Suppliers have given us a review date of 05/09/2024. We will continue to provide update as they become available. _x000D_5/9/2024:#Update Your order has been delayed. Pole work required. Our Suppliers have given us a review date of 05/09/2024. We will continue to provide update as they become available. _x000D_4/9/2024:#Update Your order has been delayed. Pole work required. Our Suppliers have given us a review date of 05/09/2024. We will continue to provide update as they become available. _x000D_3/9/2024:#Update Your order has been delayed. Pole work required. Our Suppliers have given us a review date of 05/09/2024. We will continue to provide update as they become available. _x000D_2/9/2024:#Update Your order has been delayed. Pole work required. Our Suppliers have given us a review date of 05/09/2024. We will continue to provide update as they become available. _x000D_29/8/2024:#Update Your order has been delayed. Pole work required. Our Suppliers have given us a review date of 05/09/2024. We will continue to provide update as they become available. _x000D_28/8/2024:#Update Your order has been delayed. Pole work required. Our Suppliers have given us a review date of 05/09/2024. We will continue to provide update as they become available. _x000D_27/8/2024:#Update Your order has been delayed. Pole work required. Our Suppliers have given us a review date of 05/09/2024. We will continue to provide update as they become available. _x000D_22/8/2024:#Update Your order has been delayed. Pole work required. Our Suppliers have given us a review date of 05/09/2024. We will continue to provide update as they become available. _x000D_21/8/2024:Your order has been delayed. Pole work required. Our Suppliers have given us a review date of 22/08/2024. We will continue to provide update as they become available. _x000D_20/8/2024:Your order has been delayed. Pole work required. Our Suppliers have given us a review date of 22/08/2024. We will continue to provide update as they become available. _x000D_19/8/2024:Your order has been delayed. Pole work required. Our Suppliers have given us a review date of 22/08/2024. We will continue to provide update as they become available. _x000D_19/8/2024:15/08/2024 14:43 _x000D_16/8/2024:Your order has been delayed. Pole work required. Our Suppliers have given us a review date of 22/08/2024. We will continue to provide update as they become available. _x000D_15/8/2024:I will request asset to ask contractors to bring the date forward due to this live order on our system, as soon as we get an update will update notes. _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update Your order has been delayed. Pole work required. Our Suppliers have given us a review date of 05/09/2024. We will continue to provide update as they become available. _x000D_6/9/2024:#Update Your order has been delayed. Pole work required. Our Suppliers have given us a review date of 05/09/2024. We will continue to provide update as they become available. _x000D_5/9/2024:#Update Your order has been delayed. Pole work required. Our Suppliers have given us a review date of 05/09/2024. We will continue to provide update as they become available. _x000D_4/9/2024:#Update Your order has been delayed. Pole work required. Our Suppliers have given us a review date of 05/09/2024. We will continue to provide update as they become available. _x000D_3/9/2024:#Update Your order has been delayed. Pole work required. Our Suppliers have given us a review date of 05/09/2024. We will continue to provide update as they become available. _x000D_2/9/2024:#Update Your order has been delayed. Pole work required. Our Suppliers have given us a review date of 05/09/2024. We will continue to provide update as they become available. _x000D_29/8/2024:#Update Your order has been delayed. Pole work required. Our Suppliers have given us a review date of 05/09/2024. We will continue to provide update as they become available. _x000D_28/8/2024:#Update Your order has been delayed. Pole work required. Our Suppliers have given us a review date of 05/09/2024. We will continue to provide update as they become available. _x000D_27/8/2024:#Update Your order has been delayed. Pole work required. Our Suppliers have given us a review date of 05/09/2024. We will continue to provide update as they become available. _x000D_22/8/2024:#Update Your order has been delayed. Pole work required. Our Suppliers have given us a review date of 05/09/2024. We will continue to provide update as they become available. _x000D_21/8/2024:Your order has been delayed. Pole work required. Our Suppliers have given us a review date of 22/08/2024. We will continue to provide update as they become available. _x000D_20/8/2024:Your order has been delayed. Pole work required. Our Suppliers have given us a review date of 22/08/2024. We will continue to provide update as they become available. _x000D_19/8/2024:Your order has been delayed. Pole work required. Our Suppliers have given us a review date of 22/08/2024. We will continue to provide update as they become available. _x000D_19/8/2024:15/08/2024 14:43 _x000D_16/8/2024:Your order has been delayed. Pole work required. Our Suppliers have given us a review date of 22/08/2024. We will continue to provide update as they become available. _x000D_15/8/2024:I will request asset to ask contractors to bring the date forward due to this live order on our system, as soon as we get an update will update notes. _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update Your order has been delayed. Pole work required. Our Suppliers have given us a review date of 05/09/2024. We will continue to provide update as they become available. |  |  |  |  | 2.Allwyn to arrange access | VFP2422528 | 30017353 | 1.Provisioning | AM |  | 2024-08-14 | 2024-08-14 |  | 0 | [11 empty] | 0
1632 | 668412 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Spixworth News and Convenience Stor | NORWICH | NR10 3NT | 2024-08-15 | 16/8/2024:Update: Order Completed by Supplier _x000D_15/8/2024:Update: Order Completed by Supplier _x000D_14/8/2024:Update: Order Completed by Supplier _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:Update: Order Completed by Supplier _x000D_15/8/2024:Update: Order Completed by Supplier _x000D_14/8/2024:Update: Order Completed by Supplier _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1055993 | 30017757 | 2.Commissioning | AM |  | 2024-08-14 | 2024-08-14 | 2024-08-14 10:04 | 1 | [11 empty] | 0
1633 | 430712 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Jeeves Budgens | BRISTOL | BS30 5JX | 2024-07-11 | 6/9/2024:#Update- Retailer has confirmed 16/09 -AM appoint. _x000D_5/9/2024:#Update- Retailer has confirmed 16/09 -AM appoint. _x000D_4/9/2024:#Update - Retailer unaware of appointment - Re-appointed for 16/09 - AM. Action for allwyn: Please confirm with retailer that this appoint suits. _x000D_3/9/2024:#Update - Retailer unaware of appointment - Re-appointed for 16/09 - AM. Action for allwyn: Please confirm with retailer that this appoint suits. _x000D_2/9/2024:#Update - Retailer unaware of appointment - Re-appointed for 16/09 - AM. Action for allwyn: Please confirm with retailer that this appoint suits. _x000D_29/8/2024:#Update - Retailer unaware of appointment - Re-appointed for 16/09 - AM. Action for allwyn: Please confirm with retailer that this appoint suits. _x000D_28/8/2024:#Update - Retailer unaware of appointment - Re-appointed for 16/09 - AM. Action for allwyn: Please confirm with retailer that this appoint suits. _x000D_27/8/2024:#Update - Retailer unaware of appointment - Re-appointed for 16/09 - AM. Action for allwyn: Please confirm with retailer that this appoint suits. _x000D_22/8/2024:#Update - Retailer unaware of appointment - Re-appointed for 16/09 - AM. Action for allwyn: Please confirm with retailer that this appoint suits. _x000D_21/8/2024:#Update - Retailer unaware of appointment - Re-appointed for 16/09 - AM. Action for allwyn: Please confirm with retailer that this appoint suits. _x000D_20/8/2024:#Update - Retailer unaware of appointment - Re-appointed for 16/09 - AM. Action for allwyn: Please confirm with retailer that this appoint suits. _x000D_19/8/2024:#Update - Retailer unaware of appointment - Re-appointed for 16/09 - AM. Action for allwyn: Please confirm with retailer that this appoint suits. _x000D_19/8/2024:01585071 _x000D_16/8/2024:#Update - Retailer unaware of appointment - Re-appointed for 16/09 - AM. Action for allwyn: Please confirm with retailer that this appoint suits. _x000D_15/8/2024:#Update - Retailer unaware of appointment - Re-appointed for 16/09 - AM. Action for allwyn: Please confirm with retailer that this appoint suits. _x000D_14/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Supplier Delay - Our Suppliers have given us a review date of 23/07/2024 _x000D_18/7/2024:#Update - Supplier Delay - Our Suppliers have given us a review date of 23/07/2024 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update- Retailer has confirmed 16/09 -AM appoint. _x000D_6/9/2024:#Update- Retailer has confirmed 16/09 -AM appoint. _x000D_5/9/2024:#Update- Retailer has confirmed 16/09 -AM appoint. _x000D_4/9/2024:#Update - Retailer unaware of appointment - Re-appointed for 16/09 - AM. Action for allwyn: Please confirm with retailer that this appoint suits. _x000D_3/9/2024:#Update - Retailer unaware of appointment - Re-appointed for 16/09 - AM. Action for allwyn: Please confirm with retailer that this appoint suits. _x000D_2/9/2024:#Update - Retailer unaware of appointment - Re-appointed for 16/09 - AM. Action for allwyn: Please confirm with retailer that this appoint suits. _x000D_29/8/2024:#Update - Retailer unaware of appointment - Re-appointed for 16/09 - AM. Action for allwyn: Please confirm with retailer that this appoint suits. _x000D_28/8/2024:#Update - Retailer unaware of appointment - Re-appointed for 16/09 - AM. Action for allwyn: Please confirm with retailer that this appoint suits. _x000D_27/8/2024:#Update - Retailer unaware of appointment - Re-appointed for 16/09 - AM. Action for allwyn: Please confirm with retailer that this appoint suits. _x000D_22/8/2024:#Update - Retailer unaware of appointment - Re-appointed for 16/09 - AM. Action for allwyn: Please confirm with retailer that this appoint suits. _x000D_21/8/2024:#Update - Retailer unaware of appointment - Re-appointed for 16/09 - AM. Action for allwyn: Please confirm with retailer that this appoint suits. _x000D_20/8/2024:#Update - Retailer unaware of appointment - Re-appointed for 16/09 - AM. Action for allwyn: Please confirm with retailer that this appoint suits. _x000D_19/8/2024:#Update - Retailer unaware of appointment - Re-appointed for 16/09 - AM. Action for allwyn: Please confirm with retailer that this appoint suits. _x000D_19/8/2024:01585071 _x000D_16/8/2024:#Update - Retailer unaware of appointment - Re-appointed for 16/09 - AM. Action for allwyn: Please confirm with retailer that this appoint suits. _x000D_15/8/2024:#Update - Retailer unaware of appointment - Re-appointed for 16/09 - AM. Action for allwyn: Please confirm with retailer that this appoint suits. _x000D_14/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Supplier Delay - Our Suppliers have given us a review date of 23/07/2024 _x000D_18/7/2024:#Update - Supplier Delay - Our Suppliers have given us a review date of 23/07/2024 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update- Retailer has confirmed 16/09 -AM appoint. |  |  |  |  | 2.Allwyn to arrange access | VFS1055258 | 30017730 | 1.Provisioning | AM |  | 2024-08-14 | 2024-09-16 |  | 0 | [11 empty] | 0
1634 | 471225 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Model Village Convenience Store | MANSFIELD | NG20 8BL | 2024-07-11 | 6/9/2024:#Update - Retailer confirms new appointment date of 25/09 - Proceeding with order _x000D_5/9/2024:#Update - Retailer is relocating this store to another premises. awaiting to be confirmed by allwyn this is the case. then will cancel down. _x000D_4/9/2024:#Update - Retailer is relocating this store to another premises. awaiting to be confirmed by allwyn this is the case. then will cancel down. _x000D_3/9/2024:#Update - Retailer is relocating this store to another premises. awaiting to be confirmed by allwyn this is the case. then will cancel down. _x000D_2/9/2024:#Update - Retailer is relocating this store to another premises. awaiting to be confirmed by allwyn this is the case. then will cancel down. _x000D_29/8/2024:#Update - Retailer is relocating this store to another premises. awaiting to be confirmed by allwyn this is the case. then will cancel down. _x000D_28/8/2024:#Update - Retailer is relocating this store to another premises. awaiting to be confirmed by allwyn this is the case. then will cancel down. _x000D_27/8/2024:#Update - Retailer is relocating this store to another premises. awaiting to be confirmed by allwyn this is the case. then will cancel down. _x000D_22/8/2024:#Update - Retailer is relocating this store to another premises. awaiting to be confirmed by allwyn this is the case. then will cancel down. _x000D_21/8/2024:#Update - Retailer is relocating this store to another premises. awaiting to be confirmed by allwyn this is the case. then will cancel down. _x000D_20/8/2024:#Update - Retailer is relocating this store to another premises. awaiting to be confirmed by allwyn this is the case. then will cancel down. _x000D_19/8/2024:#Update - Retailer is relocating this store to another premises. awaiting to be confirmed by allwyn this is the case. then will cancel down. _x000D_19/8/2024:01499146 _x000D_16/8/2024:#Update - Retailer is relocating this store to another premises. awaiting to be confirmed by allwyn this is the case. then will cancel down. _x000D_15/8/2024:#Update - Retailer is relocating this store to another premises. awaiting to be confirmed by allwyn this is the case. then will cancel down. _x000D_14/8/2024:#Update - Retailer is relocating this store to another premises. awaiting to be confirmed by allwyn this is the case. then will cancel down. _x000D_13/8/2024:#Update - Supplier Delay - Our Suppliers have given us a review date of 23/07/2024 _x000D_12/8/2024:#Update - Supplier Delay - Our Suppliers have given us a review date of 23/07/2024 _x000D_9/8/2024:#Update - Supplier Delay - Our Suppliers have given us a review date of 23/07/2024 _x000D_8/8/2024:18/07/2024 _x000D_6/8/2024:18/07/2024 _x000D_5/8/2024:18/07/2024 _x000D_2/8/2024:18/07/2024 _x000D_1/8/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_30/7/2024:#Update - Supplier Delay - Our Suppliers have given us a review date of 23/07/2024 _x000D_29/7/2024:#Update - Supplier Delay - Our Suppliers have given us a review date of 23/07/2024 _x000D_29/7/2024:01499146 _x000D_26/7/2024:01499146 _x000D_24/7/2024:#Update - Supplier Delay - Our Suppliers have given us a review date of 23/07/2024 _x000D_23/7/2024:#Update - Supplier Delay - Our Suppliers have given us a review date of 23/07/2024 _x000D_22/7/2024:#Update - Supplier Delay - Our Suppliers have given us a review date of 23/07/2024 _x000D_22/7/2024:#Update - Supplier Delay - Our Suppliers have given us a review date of 23/07/2024 _x000D_19/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_17/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Retailer confirms new appointment date of 25/09 - Proceeding with order _x000D_6/9/2024:#Update - Retailer confirms new appointment date of 25/09 - Proceeding with order _x000D_5/9/2024:#Update - Retailer is relocating this store to another premises. awaiting to be confirmed by allwyn this is the case. then will cancel down. _x000D_4/9/2024:#Update - Retailer is relocating this store to another premises. awaiting to be confirmed by allwyn this is the case. then will cancel down. _x000D_3/9/2024:#Update - Retailer is relocating this store to another premises. awaiting to be confirmed by allwyn this is the case. then will cancel down. _x000D_2/9/2024:#Update - Retailer is relocating this store to another premises. awaiting to be confirmed by allwyn this is the case. then will cancel down. _x000D_29/8/2024:#Update - Retailer is relocating this store to another premises. awaiting to be confirmed by allwyn this is the case. then will cancel down. _x000D_28/8/2024:#Update - Retailer is relocating this store to another premises. awaiting to be confirmed by allwyn this is the case. then will cancel down. _x000D_27/8/2024:#Update - Retailer is relocating this store to another premises. awaiting to be confirmed by allwyn this is the case. then will cancel down. _x000D_22/8/2024:#Update - Retailer is relocating this store to another premises. awaiting to be confirmed by allwyn this is the case. then will cancel down. _x000D_21/8/2024:#Update - Retailer is relocating this store to another premises. awaiting to be confirmed by allwyn this is the case. then will cancel down. _x000D_20/8/2024:#Update - Retailer is relocating this store to another premises. awaiting to be confirmed by allwyn this is the case. then will cancel down. _x000D_19/8/2024:#Update - Retailer is relocating this store to another premises. awaiting to be confirmed by allwyn this is the case. then will cancel down. _x000D_19/8/2024:01499146 _x000D_16/8/2024:#Update - Retailer is relocating this store to another premises. awaiting to be confirmed by allwyn this is the case. then will cancel down. _x000D_15/8/2024:#Update - Retailer is relocating this store to another premises. awaiting to be confirmed by allwyn this is the case. then will cancel down. _x000D_14/8/2024:#Update - Retailer is relocating this store to another premises. awaiting to be confirmed by allwyn this is the case. then will cancel down. _x000D_13/8/2024:#Update - Supplier Delay - Our Suppliers have given us a review date of 23/07/2024 _x000D_12/8/2024:#Update - Supplier Delay - Our Suppliers have given us a review date of 23/07/2024 _x000D_9/8/2024:#Update - Supplier Delay - Our Suppliers have given us a review date of 23/07/2024 _x000D_8/8/2024:18/07/2024 _x000D_6/8/2024:18/07/2024 _x000D_5/8/2024:18/07/2024 _x000D_2/8/2024:18/07/2024 _x000D_1/8/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_30/7/2024:#Update - Supplier Delay - Our Suppliers have given us a review date of 23/07/2024 _x000D_29/7/2024:#Update - Supplier Delay - Our Suppliers have given us a review date of 23/07/2024 _x000D_29/7/2024:01499146 _x000D_26/7/2024:01499146 _x000D_24/7/2024:#Update - Supplier Delay - Our Suppliers have given us a review date of 23/07/2024 _x000D_23/7/2024:#Update - Supplier Delay - Our Suppliers have given us a review date of 23/07/2024 _x000D_22/7/2024:#Update - Supplier Delay - Our Suppliers have given us a review date of 23/07/2024 _x000D_22/7/2024:#Update - Supplier Delay - Our Suppliers have given us a review date of 23/07/2024 _x000D_19/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_17/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - Retailer confirms new appointment date of 25/09 - Proceeding with order |  |  |  |  | 2.Allwyn to arrange access | VFS1055252 | 30017720 | 1.Provisioning | AM |  | 2024-08-14 | 2024-08-14 |  | 0 | [11 empty] | 0
1635 | 486299 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Spar Stores | CARDIGAN | SA43 1LS | 2024-08-15 | 16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 17-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1055246 | 30017716 | 2.Commissioning | AM |  | 2024-08-14 | 2024-08-14 | 2024-08-14 12:00 | 1 |  |  |  | 2024-09-09 | [7 empty] | 0
1636 | 481867 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Nisa | NEATH | SA11 1AA | 2024-08-16 | 19/8/2024:Order Completed _x000D_19/8/2024:15/08/2024 11:53 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 19/8/2024:Order Completed _x000D_19/8/2024:15/08/2024 11:53 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043834 | 30017504 | 3.In life | AM |  | 2024-08-14 | 2024-08-14 |  | 0 |  |  |  | 2024-09-05 |  |  |  | 2024-09-05 | 242005010375 | 242005010375 | 2024-09-06 | 1
1637 | 648762 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Londis College Road | BIRMINGHAM | B44 0HL | 2024-08-15 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1057065 | 30017360 | 3.In life | AM |  | 2024-08-14 | 2024-08-14 | 2024-08-14 12:32 | 1 |  |  |  | 2024-09-04 |  |  |  | 2024-09-04 | 238004926069 | 238004926069 | 2024-09-05 | 1
1638 | 462348 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Keystore Stores | GLASGOW | G15 6LU | 2024-08-30 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:#Update Retailer confirmed 29/08, AM. _x000D_29/8/2024:#Update Retailer confirmed 29/08, AM. _x000D_28/8/2024:#Update Retailer confirmed 29/08, AM. _x000D_27/8/2024:#Update Retailer confirmed 29/08, AM. _x000D_22/8/2024:#Update Retailer confirmed 29/08, AM. _x000D_21/8/2024:#Update Customer unaware, reappointed for 29/08, AM. Action on Allwyn - ensure the retailer is aware. _x000D_20/8/2024:#Update Customer unaware, reappointed for 29/08, AM. Action on Allwyn - ensure the retailer is aware. _x000D_19/8/2024:#Update Customer unaware, reappointed for 29/08, AM. Action on Allwyn - ensure the retailer is aware. _x000D_19/8/2024:01585032 _x000D_16/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_15/8/2024:End User Missed appointment. Action required _x000D_14/8/2024:End User Missed appointment. Action required _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:#Update Retailer confirmed 29/08, AM. _x000D_29/8/2024:#Update Retailer confirmed 29/08, AM. _x000D_28/8/2024:#Update Retailer confirmed 29/08, AM. _x000D_27/8/2024:#Update Retailer confirmed 29/08, AM. _x000D_22/8/2024:#Update Retailer confirmed 29/08, AM. _x000D_21/8/2024:#Update Customer unaware, reappointed for 29/08, AM. Action on Allwyn - ensure the retailer is aware. _x000D_20/8/2024:#Update Customer unaware, reappointed for 29/08, AM. Action on Allwyn - ensure the retailer is aware. _x000D_19/8/2024:#Update Customer unaware, reappointed for 29/08, AM. Action on Allwyn - ensure the retailer is aware. _x000D_19/8/2024:01585032 _x000D_16/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_15/8/2024:End User Missed appointment. Action required _x000D_14/8/2024:End User Missed appointment. Action required _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFS1043830 | 30017442 | 2.Commissioning | AM |  | 2024-08-14 | 2024-08-14 |  | 0 | [11 empty] | 0
1639 | 471010 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Co-Operative Retail Services Ltd | SOMERTON | TA11 7PY | 2024-08-15 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1057017 | 30017404 | 2.Commissioning | AM |  | 2024-08-14 | 2024-08-14 | 2024-08-14 13:18 | 1 |  |  |  | 2024-09-05 | [7 empty] | 0
1640 | 627995 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Swain House Off Licence | BRADFORD | BD2 1JN | 2024-08-15 | 16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043831 | 30017460 | 2.Commissioning | AM |  | 2024-08-14 | 2024-08-14 | 2024-08-14 12:00 | 1 |  |  |  | 2024-09-13 | [7 empty] | 0
1641 | 654117 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Co-Operative Retail Services Ltd | NORTHOLT | UB5 5AB | 2024-08-15 | 16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043829 | 30017453 | 2.Commissioning | AM |  | 2024-08-14 | 2024-08-14 | 2024-08-14 12:00 | 1 |  |  |  | 2024-09-05 | [7 empty] | 0
1642 | 670516 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Keystore | KILMARNOCK | KA1 4PS | 2024-07-11 | 16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043828 | 30017522 | 2.Commissioning | AM |  | 2024-08-14 | 2024-08-14 |  | 1 |  |  |  | 2024-09-04 | [7 empty] | 0
1643 | 666861 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Wells Road Convenience Store and Po | BRISTOL | BS4 2QE | 2024-08-15 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_17/7/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_0 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_17/7/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_0 | [6 empty] | 2.Allwyn to arrange access | VFP2422527 | 30017298 | 6.Failed router install | AM |  | 2024-08-14 | 2024-08-14 | 2024-08-14 15:03 | 1 |  |  |  | 2024-09-04 |  |  |  | 2024-09-04 | 242005010358 | 242005010358 | 2024-09-05 | 1
1644 | 632414 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Premier Convenience Store | BRIERLEY HILL | DY5 3TL | 2024-08-15 | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 22/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_18/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_17/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_16/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 17/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_15/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 17/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_12/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 15/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_11/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 15/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_ | 16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 22/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_18/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_17/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 19/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_16/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 17/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_15/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 17/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_12/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 15/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_11/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 15/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043827 | 30017452 | 3.In life | AM |  | 2024-08-14 | 2024-08-14 | 2024-08-14 16:26 | 1 |  |  |  | 2024-09-04 |  |  |  | 2024-09-04 | 238004926068 | 238004926068 | 2024-09-05 | 1
1645 | 647713 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Centra | BANBRIDGE | BT32 4ET | 2024-07-11 | 16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:19/07/2024 20:11 _x000D_24/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 26/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_23/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 26/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_22/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 26/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_22/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 22/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:19/07/2024 20:11 _x000D_24/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 26/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_23/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 26/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_22/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 26/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_22/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 22/07/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043825 | 30017549 | 2.Commissioning | AM |  | 2024-08-14 | 2024-08-14 |  | 1 |  |  |  | 2024-09-10 | [7 empty] | 0
1646 | 670580 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Nisa Local | SWADLINCOTE | DE11 9DA | 2024-08-16 | 19/8/2024:Order Completed _x000D_19/8/2024:15/08/2024 09:19 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 19/8/2024:Order Completed _x000D_19/8/2024:15/08/2024 09:19 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043821 | 30017461 | 2.Commissioning | AM |  | 2024-08-15 | 2024-08-15 | 2024-08-15 08:46 | 1 |  |  |  | 2024-09-06 | [7 empty] | 0
1647 | 461725 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Sava Force (UK) | WALLINGFORD | OX10 7QA | 2024-08-16 | 19/8/2024:Order Completed _x000D_19/8/2024:15/08/2024 12:47 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 19/8/2024:Order Completed _x000D_19/8/2024:15/08/2024 12:47 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043820 | 30017562 | 2.Commissioning | AM |  | 2024-08-15 | 2024-08-15 |  | 0 |  |  |  | 2024-09-05 | [7 empty] | 0
1648 | 424746 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | CENTRA | DUNGANNON | BT70 3ES | 2024-08-16 | 19/8/2024:Order Completed _x000D_19/8/2024:15/08/2024 09:50 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 19/8/2024:Order Completed _x000D_19/8/2024:15/08/2024 09:50 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1056987 | 30017301 | 2.Commissioning | AM |  | 2024-08-15 | 2024-08-15 | 2024-08-15 09:17 | 1 |  |  |  | 2024-09-04 | [7 empty] | 0
1649 | 457688 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Post Office | COATBRIDGE | ML5 3RZ | 2024-08-16 | 19/8/2024:Order Completed _x000D_19/8/2024:15/08/2024 09:27 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 19/8/2024:Order Completed _x000D_19/8/2024:15/08/2024 09:27 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043818 | 30017475 | 3.In life | AM |  | 2024-08-15 | 2024-08-15 | 2024-08-15 08:54 | 1 |  |  |  | 2024-09-05 |  |  |  | 2024-09-05 | 23A004952707 | 23A004952707 | 2024-09-06 | 1
1650 | 651269 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Pace Barrhill Stores | CUMNOCK | KA18 1PW | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2422526 | 30017409 | 1.Provisioning | AM |  | 2024-08-15 | 2024-09-06 |  | 0 | [11 empty] | 0
1651 | 200304 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Dees Newsagents | NEWHAVEN | BN9 9PA | 2024-08-16 | 19/8/2024:Order Completed _x000D_19/8/2024:15/08/2024 14:33 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 19/8/2024:Order Completed _x000D_19/8/2024:15/08/2024 14:33 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043817 | 30017552 | 3.In life | AM |  | 2024-08-15 | 2024-08-15 |  | 0 |  |  |  | 2024-09-04 |  |  |  | 2024-09-04 | 242005011011 | 242005011011 | 2024-09-05 | 1
1652 | 413350 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Dafen Stores | LLANELLI | SA14 8LR | 2024-08-16 | 19/8/2024:Order Completed _x000D_19/8/2024:15/08/2024 10:17 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 19/8/2024:Order Completed _x000D_19/8/2024:15/08/2024 10:17 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFP2421351 | 30017785 | 2.Commissioning | AM |  | 2024-08-15 | 2024-08-15 | 2024-08-15 09:45 | 1 |  |  |  | 2024-09-05 | [7 empty] | 0
1653 | 422238 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Spar Stores | DUNGANNON | BT71 5AX | 2024-08-16 | 19/8/2024:Order Completed _x000D_19/8/2024:15/08/2024 09:51 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 19/8/2024:Order Completed _x000D_19/8/2024:15/08/2024 09:51 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043815 | 30017558 | 2.Commissioning | AM |  | 2024-08-15 | 2024-08-15 | 2024-08-15 09:18 | 1 |  |  |  | 2024-09-04 | [7 empty] | 0
1654 | 449349 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Mace | DINGWALL | IV15 9QF | 2024-08-16 | 20/8/2024:0 _x000D_19/8/2024:Order Completed _x000D_19/8/2024:15/08/2024 10:49 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 20/8/2024:0 _x000D_19/8/2024:Order Completed _x000D_19/8/2024:15/08/2024 10:49 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043814 | 30017435 | 2.Commissioning | AM |  | 2024-08-15 | 2024-08-15 |  | 0 | [11 empty] | 0
1655 | 230604 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Lords | BRENTWOOD | CM13 1BN | 2024-08-16 | 19/8/2024:Order Completed _x000D_19/8/2024:15/08/2024 09:31 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 19/8/2024:Order Completed _x000D_19/8/2024:15/08/2024 09:31 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:Order Completed _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043811 | 30017575 | 2.Commissioning | AM |  | 2024-08-15 | 2024-08-15 | 2024-08-15 09:00 | 1 |  |  |  | 2024-09-06 | [7 empty] | 0
1656 | 655933 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Finchs Spar Millvale | NEWRY | BT35 7NH | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_17/7/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_16/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 15-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 15-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 15-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_11/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 15-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:Update: Order Amended _x000D_5/8/2024:Update: Order Amended _x000D_2/8/2024:Update: Order Amended _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_17/7/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_16/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 15-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 15-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 15-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_11/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 15-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2422525 | 30017322 | 1.Provisioning | AM |  | 2024-08-15 | 2024-09-06 |  | 0 | [11 empty] | 0
1657 | 465121 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Newsplus | LANCASTER | LA1 1NB | 2024-09-04 | 6/9/2024:#Update Order has been delayed due to insufficient capacity at suppliers cabinets. _x000D_5/9/2024:#Update Order has been delayed due to insufficient capacity at suppliers cabinets. _x000D_4/9/2024:#Update Order has been delayed due to insufficient capacity at suppliers cabinets. _x000D_3/9/2024:#Update Order has been delayed due to insufficient capacity at suppliers cabinets. _x000D_2/9/2024:#Update Order has been delayed due to insufficient capacity at suppliers cabinets. _x000D_29/8/2024:#Update Order has been delayed due to insufficient capacity at suppliers cabinets. _x000D_28/8/2024:#Update Order has been delayed due to insufficient capacity at suppliers cabinets. _x000D_27/8/2024:#Update Order has been delayed due to insufficient capacity at suppliers cabinets. _x000D_22/8/2024:#Update Order has been delayed due to insufficient capacity at suppliers cabinets. _x000D_21/8/2024:#Update Order has been delayed due to insufficient capacity at suppliers cabinets. _x000D_20/8/2024:#Update Order has been delayed due to insufficient capacity at suppliers cabinets. _x000D_19/8/2024:#Update Order has been delayed due to insufficient capacity at suppliers cabinets. _x000D_19/8/2024:01496204 _x000D_16/8/2024:#Update Order has been delayed due to insufficient capacity at suppliers cabinets. _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/8/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/8/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_2/8/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_23/7/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_18/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_0 | 9/9/2024:#Update Order has been delayed due to insufficient capacity at suppliers cabinets. _x000D_6/9/2024:#Update Order has been delayed due to insufficient capacity at suppliers cabinets. _x000D_5/9/2024:#Update Order has been delayed due to insufficient capacity at suppliers cabinets. _x000D_4/9/2024:#Update Order has been delayed due to insufficient capacity at suppliers cabinets. _x000D_3/9/2024:#Update Order has been delayed due to insufficient capacity at suppliers cabinets. _x000D_2/9/2024:#Update Order has been delayed due to insufficient capacity at suppliers cabinets. _x000D_29/8/2024:#Update Order has been delayed due to insufficient capacity at suppliers cabinets. _x000D_28/8/2024:#Update Order has been delayed due to insufficient capacity at suppliers cabinets. _x000D_27/8/2024:#Update Order has been delayed due to insufficient capacity at suppliers cabinets. _x000D_22/8/2024:#Update Order has been delayed due to insufficient capacity at suppliers cabinets. _x000D_21/8/2024:#Update Order has been delayed due to insufficient capacity at suppliers cabinets. _x000D_20/8/2024:#Update Order has been delayed due to insufficient capacity at suppliers cabinets. _x000D_19/8/2024:#Update Order has been delayed due to insufficient capacity at suppliers cabinets. _x000D_19/8/2024:01496204 _x000D_16/8/2024:#Update Order has been delayed due to insufficient capacity at suppliers cabinets. _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/8/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/8/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_2/8/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_23/7/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_18/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_0 | Your order has come off a waiters list and will now be fulfilled. | #Update Order has been delayed due to insufficient capacity at suppliers cabinets. |  |  |  |  | 2.Allwyn to arrange access | VFS1052408 | 30017703 | 2.Commissioning | AM |  | 2024-08-15 | 2024-08-15 |  | 0 | [11 empty] | 0
1658 | 477308 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Smokers Paradise | WICKFORD | SS12 9AJ | 2024-07-11 | 6/9/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_5/9/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_4/9/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_3/9/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_2/9/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_29/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_28/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_27/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_22/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_21/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_20/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_19/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_19/8/2024:01499172 _x000D_16/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_15/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_14/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_13/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_12/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_9/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_8/8/2024:18/07/2024 _x000D_6/8/2024:18/07/2024 _x000D_5/8/2024:18/07/2024 _x000D_2/8/2024:18/07/2024 _x000D_1/8/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_30/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_29/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_29/7/2024:01499172 _x000D_26/7/2024:01499172 _x000D_24/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_23/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_22/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_22/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_6/9/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_5/9/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_4/9/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_3/9/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_2/9/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_29/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_28/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_27/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_22/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_21/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_20/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_19/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_19/8/2024:01499172 _x000D_16/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_15/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_14/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_13/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_12/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_9/8/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_8/8/2024:18/07/2024 _x000D_6/8/2024:18/07/2024 _x000D_5/8/2024:18/07/2024 _x000D_2/8/2024:18/07/2024 _x000D_1/8/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_31/7/2024:18/07/2024 _x000D_30/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_29/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_29/7/2024:01499172 _x000D_26/7/2024:01499172 _x000D_24/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_23/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_22/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_22/7/2024:#Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - Supplier delay - Our Suppliers have given us a review date of 24/07/2024 |  |  |  |  | 2.Allwyn to arrange access | VFS1054888 | 30021796 | 1.Provisioning | AM |  |  |  |  | 0 | [11 empty] | 0
1659 | 647389 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Raja Grocers Shop | ASHTON-UNDER-LYNE | OL5 9SB | 2024-08-16 | 19/8/2024:Order Completed _x000D_19/8/2024:15/08/2024 13:16 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 19/8/2024:Order Completed _x000D_19/8/2024:15/08/2024 13:16 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043813 | 30017456 | 2.Commissioning | AM |  | 2024-08-15 | 2024-08-15 |  | 0 |  |  |  | 2024-09-06 | [7 empty] | 0
1660 | 667928 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | O'Loans Talk Express | CRAIGAVON | BT67 9AQ | 2024-07-11 | 6/9/2024:#Update- Retailer has confirmed new appointment date of 09/09 _x000D_5/9/2024:#Update- Retailer has confirmed new appointment date of 09/09 _x000D_4/9/2024:#Update- Retailer has confirmed new appointment date of 09/09 _x000D_3/9/2024:#Update- Retailer has confirmed new appointment date of 09/09 _x000D_2/9/2024:#Update- Retailer has confirmed new appointment date of 09/09 _x000D_29/8/2024:#Update- Retailer has confirmed new appointment date of 09/09 _x000D_28/8/2024:#Update- Retailer has confirmed new appointment date of 09/09 _x000D_27/8/2024:#Update- Retailer has confirmed new appointment date of 09/09 _x000D_22/8/2024:#Update- Retailer has confirmed new appointment date of 09/09 _x000D_21/8/2024:#Update- Retailer has confirmed new appointment date of 09/09 _x000D_20/8/2024:#Update- Retailer has confirmed new appointment date of 09/09 _x000D_19/8/2024:#Update- Retailer has confirmed new appointment date of 09/09 _x000D_19/8/2024:01587721 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update- Retailer has confirmed new appointment date of 09/09 _x000D_6/9/2024:#Update- Retailer has confirmed new appointment date of 09/09 _x000D_5/9/2024:#Update- Retailer has confirmed new appointment date of 09/09 _x000D_4/9/2024:#Update- Retailer has confirmed new appointment date of 09/09 _x000D_3/9/2024:#Update- Retailer has confirmed new appointment date of 09/09 _x000D_2/9/2024:#Update- Retailer has confirmed new appointment date of 09/09 _x000D_29/8/2024:#Update- Retailer has confirmed new appointment date of 09/09 _x000D_28/8/2024:#Update- Retailer has confirmed new appointment date of 09/09 _x000D_27/8/2024:#Update- Retailer has confirmed new appointment date of 09/09 _x000D_22/8/2024:#Update- Retailer has confirmed new appointment date of 09/09 _x000D_21/8/2024:#Update- Retailer has confirmed new appointment date of 09/09 _x000D_20/8/2024:#Update- Retailer has confirmed new appointment date of 09/09 _x000D_19/8/2024:#Update- Retailer has confirmed new appointment date of 09/09 _x000D_19/8/2024:01587721 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update- Retailer has confirmed new appointment date of 09/09 |  |  |  |  | 2.Allwyn to arrange access | VFP2422524 | 30017350 | 1.Provisioning | AM |  | 2024-08-15 | 2024-09-09 |  | 0 | [11 empty] | 0
1661 | 425990 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Spar Stores | BECKENHAM | BR3 3RA | 2024-07-11 | 6/9/2024:#Update - Awaiting further information from OR regarding site - Awaiting ECC approval for Site survey/Advanced upgrade. _x000D_5/9/2024:#Update - Awaiting further information from OR regarding site - Awaiting ECC approval for Site survey/Advanced upgrade. _x000D_4/9/2024:#Update - Awaiting further information from OR regarding site - Awaiting ECC approval for Site survey/Advanced upgrade. _x000D_3/9/2024:#Update - Awaiting further information from OR regarding site - Awaiting ECC approval for Site survey/Advanced upgrade. _x000D_2/9/2024:#Update - Awaiting further information from OR regarding site - Awaiting ECC approval for Site survey/Advanced upgrade. _x000D_29/8/2024:#Update - Awaiting further information from OR regarding site - Awaiting ECC approval for Site survey/Advanced upgrade. _x000D_28/8/2024:#Update - Awaiting further information from OR regarding site - Awaiting ECC approval for Site survey/Advanced upgrade. _x000D_27/8/2024:#Update - Awaiting feedback from OR. _x000D_22/8/2024:#Update - Awaiting feedback from OR. _x000D_21/8/2024:#Update - Awaiting feedback from OR. _x000D_20/8/2024:#Update - Supplier delay - Awaiting further updates _x000D_19/8/2024:#Update - Supplier delay - Awaiting further updates _x000D_19/8/2024:01588953 _x000D_16/8/2024:End User Missed appointment. Action required _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Awaiting further information from OR regarding site - Awaiting ECC approval for Site survey/Advanced upgrade. _x000D_6/9/2024:#Update - Awaiting further information from OR regarding site - Awaiting ECC approval for Site survey/Advanced upgrade. _x000D_5/9/2024:#Update - Awaiting further information from OR regarding site - Awaiting ECC approval for Site survey/Advanced upgrade. _x000D_4/9/2024:#Update - Awaiting further information from OR regarding site - Awaiting ECC approval for Site survey/Advanced upgrade. _x000D_3/9/2024:#Update - Awaiting further information from OR regarding site - Awaiting ECC approval for Site survey/Advanced upgrade. _x000D_2/9/2024:#Update - Awaiting further information from OR regarding site - Awaiting ECC approval for Site survey/Advanced upgrade. _x000D_29/8/2024:#Update - Awaiting further information from OR regarding site - Awaiting ECC approval for Site survey/Advanced upgrade. _x000D_28/8/2024:#Update - Awaiting further information from OR regarding site - Awaiting ECC approval for Site survey/Advanced upgrade. _x000D_27/8/2024:#Update - Awaiting feedback from OR. _x000D_22/8/2024:#Update - Awaiting feedback from OR. _x000D_21/8/2024:#Update - Awaiting feedback from OR. _x000D_20/8/2024:#Update - Supplier delay - Awaiting further updates _x000D_19/8/2024:#Update - Supplier delay - Awaiting further updates _x000D_19/8/2024:01588953 _x000D_16/8/2024:End User Missed appointment. Action required _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - Awaiting further information from OR regarding site - Awaiting ECC approval for Site survey/Advanced upgrade. |  |  |  |  | 2.Allwyn to arrange access | VFS1043810 | 30017559 | 1.Provisioning | AM |  | 2024-08-15 | 2024-08-15 |  | 0 | [11 empty] | 0
1662 | 645703 |  | Batch 6 Aug 24 | Type 1 | KCOM/Mobile | Booze Parade | HULL | HU9 4JU | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | BUS0004490 | 30017276 | 1.Provisioning | AM | 2024-08-15 | 2024-08-15 |  |  | 0 | [11 empty] | 0
1663 | 460183 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Nisa | MANCHESTER | M32 9LD | 2024-08-16 | 19/8/2024:Order Completed _x000D_19/8/2024:15/08/2024 13:25 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_0 | 19/8/2024:Order Completed _x000D_19/8/2024:15/08/2024 13:25 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_0 | [6 empty] | 2.Allwyn to arrange access | VFS1043809 | 30017513 | 3.In life | AM |  | 2024-08-15 | 2024-08-15 |  | 0 |  |  |  | 2024-09-04 |  |  |  | 2024-09-04 | 238004926181 | 238004926181 | 2024-09-05 | 1
1664 | 432729 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Londis Supermarket | ASHFORD | TW15 2PE | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Silver Address Issue | 30021834 | 1.Provisioning | AM |  | 2024-08-15 |  |  | 0 | [11 empty] | 0
1665 | 670827 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Waunarllwydd PO | SWANSEA | SA5 4TQ | 2024-08-16 | 19/8/2024:Order Completed _x000D_19/8/2024:15/08/2024 11:31 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 19/8/2024:Order Completed _x000D_19/8/2024:15/08/2024 11:31 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043805 | 30017580 | 2.Commissioning | AM |  | 2024-08-15 | 2024-08-15 |  | 0 |  |  |  | 2024-09-05 | [7 empty] | 0
1666 | 205231 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Leftleys of Wells Ltd | WELLS-NEXT-THE-SEA | NR23 1AG | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFP2422426 | 30017414 | 1.Provisioning | AM |  | 2024-08-15 | 2024-09-06 |  | 0 | [11 empty] | 0
1667 | 649267 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Grange Road Stores | GILLINGHAM | ME7 2TL | 2024-08-16 | 19/8/2024:Order Completed _x000D_19/8/2024:15/08/2024 12:52 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 19/8/2024:Order Completed _x000D_19/8/2024:15/08/2024 12:52 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043804 | 30017566 | 2.Commissioning | AM |  | 2024-08-15 | 2024-08-15 |  | 0 |  |  |  | 2024-09-06 | [7 empty] | 0
1668 | 630467 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Rosemary Street Service Station | MANSFIELD | NG18 1QX | 2024-08-16 | 19/8/2024:Order Completed _x000D_19/8/2024:15/08/2024 11:37 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 19/8/2024:Order Completed _x000D_19/8/2024:15/08/2024 11:37 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 2.Allwyn to arrange access | VFS1043803 | 30017574 | 2.Commissioning | AM |  | 2024-08-15 | 2024-08-15 |  | 0 |  |  |  | 2024-09-06 | [7 empty] | 0
1669 | 619149 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Cross Keys Garage | SWANSEA | SA4 6SR | 2024-08-16 | 19/8/2024:Order Completed _x000D_19/8/2024:15/08/2024 11:28 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Order was delayed due to a sales query however this has now been resolved. Awaiting a committed install date. _x000D_18/7/2024:#Update - Order was delayed due to a sales query however this has now been resolved. Awaiting a committed install date. _x000D_17/7/2024:#Update - Order was delayed due to a sales query however this has now been resolved. Awaiting a committed install date. _x000D_16/7/2024:Delay : Sales Query CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/7/2024:Delay : Sales Query CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_0 | 19/8/2024:Order Completed _x000D_19/8/2024:15/08/2024 11:28 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update - Order was delayed due to a sales query however this has now been resolved. Awaiting a committed install date. _x000D_18/7/2024:#Update - Order was delayed due to a sales query however this has now been resolved. Awaiting a committed install date. _x000D_17/7/2024:#Update - Order was delayed due to a sales query however this has now been resolved. Awaiting a committed install date. _x000D_16/7/2024:Delay : Sales Query CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/7/2024:Delay : Sales Query CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_0 | [6 empty] | 2.Allwyn to arrange access | VFS1043802 | 30017459 | 2.Commissioning | AM |  | 2024-08-15 | 2024-08-15 |  | 0 |  |  |  | 2024-09-05 | [7 empty] | 0
1670 | 645014 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Go Local British Newsmarket | DURHAM | DH1 2EP | 2024-09-06 | 6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/09 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/09 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/09 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/09 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/09 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/09 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/09 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/09 AM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/09 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/09 AM _x000D_20/8/2024:#Update - Order was delayed due to a sales query however this has now been resolved. Awaiting a committed install date. _x000D_19/8/2024:#Update - Order was delayed due to a sales query however this has now been resolved. Awaiting a committed install date. _x000D_19/8/2024:01495516 _x000D_16/8/2024:#Update - Order was delayed due to a sales query however this has now been resolved. Awaiting a committed install date. _x000D_15/8/2024:#Update - Order was delayed due to a sales query however this has now been resolved. Awaiting a committed install date. _x000D_14/8/2024:#Update - Order was delayed due to a sales query however this has now been resolved. Awaiting a committed install date. _x000D_13/8/2024:#Update - Order was delayed due to a sales query however this has now been resolved. Awaiting a committed install date. _x000D_12/8/2024:#Update - Order was delayed due to a sales query however this has now been resolved. Awaiting a committed install date. _x000D_9/8/2024:#Update - Order was delayed due to a sales query however this has now been resolved. Awaiting a committed install date. _x000D_8/8/2024:16/07/2024 _x000D_6/8/2024:16/07/2024 _x000D_5/8/2024:16/07/2024 _x000D_2/8/2024:16/07/2024 _x000D_1/8/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_30/7/2024:#Update - Order was delayed due to a sales query however this has now been resolved. Awaiting a committed install date. _x000D_29/7/2024:#Update - Order was delayed due to a sales query however this has now been resolved. Awaiting a committed install date. _x000D_29/7/2024:01495516 _x000D_26/7/2024:01495516 _x000D_24/7/2024:#Update - Order was delayed due to a sales query however this has now been resolved. Awaiting a committed install date. _x000D_23/7/2024:#Update - Order was delayed due to a sales query however this has now been resolved. Awaiting a committed install date. _x000D_22/7/2024:#Update - Order was delayed due to a sales query however this has now been resolved. Awaiting a committed install date. _x000D_22/7/2024:#Update - Order was delayed due to a sales query however this has now been resolved. Awaiting a committed install date. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/09 AM _x000D_6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/09 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/09 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/09 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/09 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/09 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/09 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/09 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/09 AM _x000D_22/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/09 AM _x000D_21/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 05/09 AM _x000D_20/8/2024:#Update - Order was delayed due to a sales query however this has now been resolved. Awaiting a committed install date. _x000D_19/8/2024:#Update - Order was delayed due to a sales query however this has now been resolved. Awaiting a committed install date. _x000D_19/8/2024:01495516 _x000D_16/8/2024:#Update - Order was delayed due to a sales query however this has now been resolved. Awaiting a committed install date. _x000D_15/8/2024:#Update - Order was delayed due to a sales query however this has now been resolved. Awaiting a committed install date. _x000D_14/8/2024:#Update - Order was delayed due to a sales query however this has now been resolved. Awaiting a committed install date. _x000D_13/8/2024:#Update - Order was delayed due to a sales query however this has now been resolved. Awaiting a committed install date. _x000D_12/8/2024:#Update - Order was delayed due to a sales query however this has now been resolved. Awaiting a committed install date. _x000D_9/8/2024:#Update - Order was delayed due to a sales query however this has now been resolved. Awaiting a committed install date. _x000D_8/8/2024:16/07/2024 _x000D_6/8/2024:16/07/2024 _x000D_5/8/2024:16/07/2024 _x000D_2/8/2024:16/07/2024 _x000D_1/8/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_31/7/2024:16/07/2024 _x000D_30/7/2024:#Update - Order was delayed due to a sales query however this has now been resolved. Awaiting a committed install date. _x000D_29/7/2024:#Update - Order was delayed due to a sales query however this has now been resolved. Awaiting a committed install date. _x000D_29/7/2024:01495516 _x000D_26/7/2024:01495516 _x000D_24/7/2024:#Update - Order was delayed due to a sales query however this has now been resolved. Awaiting a committed install date. _x000D_23/7/2024:#Update - Order was delayed due to a sales query however this has now been resolved. Awaiting a committed install date. _x000D_22/7/2024:#Update - Order was delayed due to a sales query however this has now been resolved. Awaiting a committed install date. _x000D_22/7/2024:#Update - Order was delayed due to a sales query however this has now been resolved. Awaiting a committed install date. _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | Order Completed | #Update - Allwyn confirmed Retailer has agreed to installation on 05/09 AM |  |  |  |  | 2.Allwyn to arrange access | VFS1054885 | 30021807 | 2.Commissioning | AM |  | 2024-08-16 | 2024-08-16 |  | 0 | [11 empty] | 0
1671 | 441806 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | One O One | GLASGOW | G20 9AA | 2024-07-11 | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 11:38 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 11:38 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFS1055905 | 30017780 | 2.Commissioning | AM |  | 2024-08-16 | 2024-08-16 |  | 0 |  |  |  | 2024-09-18 | [7 empty] | 0
1672 | 421999 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Brocks Supermarket | WELLINGTON | TA21 9BU | 2024-07-11 | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 10:35 _x000D_16/8/2024:Update: Order Completed by Supplier _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 10:35 _x000D_16/8/2024:Update: Order Completed by Supplier _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFS1057182 | 30017518 | 2.Commissioning | AM |  | 2024-08-16 | 2024-08-16 |  | 0 |  |  |  | 2024-09-18 | [7 empty] | 0
1673 | 667226 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Little Hut | LONDON | SE15 5EB | 2024-07-11 | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 09:20 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:Your order requires planning validation. We may contact your customer if we need to. You will receive a further update by 29-07-2024. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/7/2024:Your order requires planning validation. We may contact your customer if we need to. You will receive a further update by 29-07-2024. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/7/2024:Your order requires planning validation. We may contact your customer if we need to. You will receive a further update by 29-07-2024. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_11/7/2024:Your order requires planning validation. We may contact your customer if we need to. You will receive a further update by 29-07-2024. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 09:20 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:Your order requires planning validation. We may contact your customer if we need to. You will receive a further update by 29-07-2024. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/7/2024:Your order requires planning validation. We may contact your customer if we need to. You will receive a further update by 29-07-2024. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/7/2024:Your order requires planning validation. We may contact your customer if we need to. You will receive a further update by 29-07-2024. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_11/7/2024:Your order requires planning validation. We may contact your customer if we need to. You will receive a further update by 29-07-2024. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFS1043801 | 30017545 | 2.Commissioning | AM |  | 2024-08-16 | 2024-08-16 |  | 0 |  |  |  | 2024-09-18 | [7 empty] | 0
1674 | 652566 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Welcome Carshalton | CARSHALTON | SM5 1HA | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:Update: Order Amended _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. _x000D_21/8/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. _x000D_20/8/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. _x000D_19/8/2024:End User Missed appointment. Action required _x000D_19/8/2024:16/08/2024 14:15 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:Update: Order Amended _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. _x000D_21/8/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. _x000D_20/8/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. _x000D_19/8/2024:End User Missed appointment. Action required _x000D_19/8/2024:16/08/2024 14:15 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFS1043799 | 30017432 | 1.Provisioning | AM |  | 2024-08-16 | 2024-08-16 |  | 0 | [11 empty] | 0
1675 | 660617 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Mattu News Ltd | WEDNESBURY | WS10 8PR | 2024-07-11 | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 10:07 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 10:07 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2422425 | 30017391 | 2.Commissioning | AM |  | 2024-08-16 | 2024-08-16 |  | 0 |  |  |  | 2024-09-20 | [7 empty] | 0
1676 | 666845 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Barrys Local | CHATHAM | ME5 7PQ | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Address query | 30017406 | 1.Provisioning | AM |  | 2024-08-16 |  |  | 0 | [11 empty] | 0
1677 | 478057 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Londis | MANCHESTER | M43 7JX | 2024-07-11 | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 10:25 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 10:25 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFS1043800 | 30017554 | 2.Commissioning | AM |  | 2024-08-16 | 2024-08-16 |  | 0 |  |  |  | 2024-09-18 | [7 empty] | 0
1678 | 667251 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Holycross Superstore | WALLSEND | NE28 7EX | 2024-07-11 | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 14:43 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 14:43 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2422423 | 30017308 | 2.Commissioning | AM |  | 2024-08-16 | 2024-08-16 |  | 0 |  |  |  | 2024-09-27 | [7 empty] | 0
1679 | 657741 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | One-O-One | GLASGOW | G45 9AA | 2024-07-11 | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 09:55 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 09:55 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFS1055898 | 30017728 | 2.Commissioning | AM |  | 2024-08-16 | 2024-08-16 |  | 0 |  |  |  | 2024-09-18 | [7 empty] | 0
1680 | 487263 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Lidice Place Newsagents | COVENTRY | CV1 1DX | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | Address query | 30017734 | 1.Provisioning | AM |  | 2024-08-16 |  |  | 0 | [11 empty] | 0
1681 | 650336 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | ARV Onestop | LONDON | SE27 0JD | 2024-07-11 | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 11:28 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 11:28 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFS1057071 | 30017296 | 2.Commissioning | AM |  | 2024-08-16 | 2024-08-16 |  | 0 |  |  |  | 2024-09-18 | [7 empty] | 0
1682 | 670639 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Mohan Food Market | GREENFORD | UB6 7DH | 2024-07-11 | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 11:17 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 11:17 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFS1043798 | 30017560 | 2.Commissioning | AM |  | 2024-08-16 | 2024-08-16 |  | 0 |  |  |  | 2024-09-18 | [7 empty] | 0
1683 | 648725 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Best One Express | MANCHESTER | M9 5AR | 2024-07-11 | 6/9/2024:#Update - Delay on engineer activities. Awaiting further updates. _x000D_5/9/2024:#Update - Delay on engineer activities. Awaiting further updates. _x000D_4/9/2024:#Update - Delay on engineer activities. Awaiting further updates. _x000D_3/9/2024:#Update - Delay on engineer activities. Awaiting further updates. _x000D_2/9/2024:#Update - Delay on engineer activities. Awaiting further updates. _x000D_29/8/2024:#Update - Delay on engineer activities. Awaiting further updates. _x000D_28/8/2024:#Update - Delay on engineer activities. Awaiting further updates. _x000D_27/8/2024:#Update - Delay on engineer activities. Awaiting further updates. _x000D_22/8/2024:#Update - Delay on engineer activities. Awaiting further updates. _x000D_21/8/2024:#Update - Delay on engineer activities. Awaiting further updates. _x000D_20/8/2024:#Update - Delay on engineer activities. Awaiting further updates. _x000D_19/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_19/8/2024:16/08/2024 08:17 _x000D_16/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - Delay on engineer activities. Awaiting further updates. _x000D_6/9/2024:#Update - Delay on engineer activities. Awaiting further updates. _x000D_5/9/2024:#Update - Delay on engineer activities. Awaiting further updates. _x000D_4/9/2024:#Update - Delay on engineer activities. Awaiting further updates. _x000D_3/9/2024:#Update - Delay on engineer activities. Awaiting further updates. _x000D_2/9/2024:#Update - Delay on engineer activities. Awaiting further updates. _x000D_29/8/2024:#Update - Delay on engineer activities. Awaiting further updates. _x000D_28/8/2024:#Update - Delay on engineer activities. Awaiting further updates. _x000D_27/8/2024:#Update - Delay on engineer activities. Awaiting further updates. _x000D_22/8/2024:#Update - Delay on engineer activities. Awaiting further updates. _x000D_21/8/2024:#Update - Delay on engineer activities. Awaiting further updates. _x000D_20/8/2024:#Update - Delay on engineer activities. Awaiting further updates. _x000D_19/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_19/8/2024:16/08/2024 08:17 _x000D_16/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | Update: Order Amended | #Update - Delay on engineer activities. Awaiting further updates. |  |  |  |  | 2.Allwyn to arrange access | VFS1043797 | 30017567 | 1.Provisioning | AM |  | 2024-08-16 | 2024-08-16 |  | 0 | [11 empty] | 0
1684 | 646591 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | Samuel Road Store | SHEFFIELD | S2 3UA | 2024-07-11 | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 14:55 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 14:55 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2422421 | 30017295 | 2.Commissioning | AM |  | 2024-08-16 | 2024-08-16 |  | 0 |  |  |  | 2024-09-19 | [7 empty] | 0
1685 | 644279 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Nisa | SALISBURY | SP4 8EU | 2024-07-11 | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:Update: Order Amended _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:Your order has been delayed. The appointment has been delayed due to a Hazard Asbestos. Please check with end user and reappoint the order if still required. _x000D_21/8/2024:Your order has been delayed. The appointment has been delayed due to a Hazard Asbestos. Please check with end user and reappoint the order if still required. _x000D_20/8/2024:Your order has been delayed. The appointment has been delayed due to a Hazard Asbestos. Please check with end user and reappoint the order if still required. _x000D_19/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_19/8/2024:16/08/2024 10:44 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:Update: Order Amended _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:Your order has been delayed. The appointment has been delayed due to a Hazard Asbestos. Please check with end user and reappoint the order if still required. _x000D_21/8/2024:Your order has been delayed. The appointment has been delayed due to a Hazard Asbestos. Please check with end user and reappoint the order if still required. _x000D_20/8/2024:Your order has been delayed. The appointment has been delayed due to a Hazard Asbestos. Please check with end user and reappoint the order if still required. _x000D_19/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_19/8/2024:16/08/2024 10:44 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | 0 |  |  |  |  | 2.Allwyn to arrange access | VFS1043796 | 30017571 | 1.Provisioning | AM |  | 2024-08-16 | 2024-08-16 |  | 0 | [11 empty] | 0
1686 | 664789 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | One Stop | DARLINGTON | DL1 1XD | 2024-07-11 | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 13:11 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 13:11 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFS1043793 | 30017570 | 2.Commissioning | AM |  | 2024-08-16 | 2024-08-16 |  | 0 |  |  |  | 2024-09-27 | [7 empty] | 0
1687 | 481801 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | One Stop Community Stores Ltd | LEEDS | LS9 9LH | 2024-07-11 | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 14:27 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 14:27 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2422422 | 30017303 | 2.Commissioning | AM |  | 2024-08-16 | 2024-08-16 |  | 0 |  |  |  | 2024-09-19 | [7 empty] | 0
1688 | 615623 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | One Stop Community Stores Ltd | COVENTRY | CV2 1PB | 2024-07-11 | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 12:39 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 12:39 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2422420 | 30017288 | 2.Commissioning | AM |  | 2024-08-16 | 2024-08-16 |  | 0 |  |  |  | 2024-09-20 | [7 empty] | 0
1689 | 470755 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Costcutter Bargain Booze | STOKE-ON-TRENT | ST6 1RU | 2024-07-11 | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 08:50 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 08:50 _x000D_16/8/2024:Order Completed _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFS1043792 | 30017421 | 2.Commissioning | AM |  | 2024-08-16 | 2024-08-16 |  | 0 |  |  |  | 2024-09-20 | [7 empty] | 0
1690 | 656095 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | One Stop | NOTTINGHAM | NG12 5GL | 2024-07-11 | 6/9/2024:#Update Retailer confirmed 12/09, AM. _x000D_5/9/2024:#Update Retailer confirmed 12/09, AM. _x000D_4/9/2024:#Update Retailer confirmed 12/09, AM. _x000D_3/9/2024:#Update Retailer confirmed 12/09, AM. _x000D_2/9/2024:#Update Retailer confirmed 12/09, AM. _x000D_29/8/2024:#Update Retailer confirmed 12/09, AM. _x000D_28/8/2024:#Update Cancelled in error, reappointment for 12/09. Action on allwyn - ensure the retailer is aware. _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update Retailer confirmed 12/09, AM. _x000D_6/9/2024:#Update Retailer confirmed 12/09, AM. _x000D_5/9/2024:#Update Retailer confirmed 12/09, AM. _x000D_4/9/2024:#Update Retailer confirmed 12/09, AM. _x000D_3/9/2024:#Update Retailer confirmed 12/09, AM. _x000D_2/9/2024:#Update Retailer confirmed 12/09, AM. _x000D_29/8/2024:#Update Retailer confirmed 12/09, AM. _x000D_28/8/2024:#Update Cancelled in error, reappointment for 12/09. Action on allwyn - ensure the retailer is aware. _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update Retailer confirmed 12/09, AM. |  |  |  |  | 2.Allwyn to arrange access | VFS1093715 | 30017783 | 1.Provisioning | AM |  | 2024-08-16 | 2024-08-16 |  | 0 | [11 empty] | 0
1691 | 461367 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | One Stop Community Stores Ltd | LEEDS | LS13 3RB | 2024-07-11 | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 10:54 _x000D_16/8/2024:Update: Order Completed by Supplier _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 10:54 _x000D_16/8/2024:Update: Order Completed by Supplier _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2422419 | 30017326 | 2.Commissioning | AM |  | 2024-08-16 | 2024-08-16 |  | 0 |  |  |  | 2024-09-19 | [7 empty] | 0
1692 | 664699 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | One Stop | HEMEL HEMPSTEAD | HP2 5SB | 2024-07-11 | 6/9/2024:#Update - order has been delayed. Dig work required. Our Suppliers will continue to provide update as they become available _x000D_5/9/2024:#Update - order has been delayed. Dig work required. Our Suppliers will continue to provide update as they become available _x000D_4/9/2024:#Update - order has been delayed. Dig work required. Our Suppliers will continue to provide update as they become available _x000D_3/9/2024:#Update - order has been delayed. Dig work required. Our Suppliers will continue to provide update as they become available _x000D_2/9/2024:#Update - order has been delayed. Dig work required. Our Suppliers will continue to provide update as they become available _x000D_29/8/2024:#Update - order has been delayed. Dig work required. Our Suppliers will continue to provide update as they become available _x000D_28/8/2024:#Update - order has been delayed. Dig work required. Our Suppliers will continue to provide update as they become available _x000D_27/8/2024:#Update - order has been delayed. Dig work required. Our Suppliers will continue to provide update as they become available _x000D_22/8/2024:#Update - order has been delayed. Dig work required. Our Suppliers will continue to provide update as they become available _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 22/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/8/2024:12/08/2024 15:17 _x000D_16/8/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 22/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/8/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 22/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_14/8/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 22/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_13/8/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 22/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/8/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 15/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_9/8/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 15/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_8/8/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 15/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/8/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 15/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/8/2024:0 _x000D_2/8/2024:Your order has been delayed. Duct work required. Our Suppliers have given us a review date of 06/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_1/8/2024:Your order has been delayed. Duct work required. Our Suppliers have given us a review date of 06/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:Your order has been delayed. Duct work required. Our Suppliers have given us a review date of 06/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:37635 _x000D_30/7/2024:Your order has been delayed. Duct work required. Our Suppliers have given us a review date of 06/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:Your order has been delayed. Duct work required. Our Suppliers have given us a review date of 06/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:26/07/2024 16:41 _x000D_26/7/2024:25/07/2024 11:51 _x000D_24/7/2024:Supplier Delay: Issues with provision of the underground network, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_23/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 9/9/2024:#Update - order has been delayed. Dig work required. Our Suppliers will continue to provide update as they become available _x000D_6/9/2024:#Update - order has been delayed. Dig work required. Our Suppliers will continue to provide update as they become available _x000D_5/9/2024:#Update - order has been delayed. Dig work required. Our Suppliers will continue to provide update as they become available _x000D_4/9/2024:#Update - order has been delayed. Dig work required. Our Suppliers will continue to provide update as they become available _x000D_3/9/2024:#Update - order has been delayed. Dig work required. Our Suppliers will continue to provide update as they become available _x000D_2/9/2024:#Update - order has been delayed. Dig work required. Our Suppliers will continue to provide update as they become available _x000D_29/8/2024:#Update - order has been delayed. Dig work required. Our Suppliers will continue to provide update as they become available _x000D_28/8/2024:#Update - order has been delayed. Dig work required. Our Suppliers will continue to provide update as they become available _x000D_27/8/2024:#Update - order has been delayed. Dig work required. Our Suppliers will continue to provide update as they become available _x000D_22/8/2024:#Update - order has been delayed. Dig work required. Our Suppliers will continue to provide update as they become available _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 22/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/8/2024:12/08/2024 15:17 _x000D_16/8/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 22/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/8/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 22/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_14/8/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 22/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_13/8/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 22/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/8/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 15/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_9/8/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 15/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_8/8/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 15/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/8/2024:Your order has been delayed. Dig work required. Our Suppliers have given us a review date of 15/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/8/2024:0 _x000D_2/8/2024:Your order has been delayed. Duct work required. Our Suppliers have given us a review date of 06/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_1/8/2024:Your order has been delayed. Duct work required. Our Suppliers have given us a review date of 06/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:Your order has been delayed. Duct work required. Our Suppliers have given us a review date of 06/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:37635 _x000D_30/7/2024:Your order has been delayed. Duct work required. Our Suppliers have given us a review date of 06/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:Your order has been delayed. Duct work required. Our Suppliers have given us a review date of 06/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:26/07/2024 16:41 _x000D_26/7/2024:25/07/2024 11:51 _x000D_24/7/2024:Supplier Delay: Issues with provision of the underground network, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_23/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 0 | #Update - order has been delayed. Dig work required. Our Suppliers will continue to provide update as they become available |  |  |  |  | 2.Allwyn to arrange access | VFP2422418 | 30017342 | 1.Provisioning | AM |  | 2024-08-16 |  |  | 0 | [11 empty] | 0
1693 | 667041 |  | Batch 6 Aug 24 | Type 1 | FTTP/Mobile | One Stop | WEDNESBURY | WS10 8AB | 2024-07-11 | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 14:30 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 14:30 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2423281 | 30017400 | 2.Commissioning | AM |  | 2024-08-16 | 2024-08-16 |  | 0 |  |  |  | 2024-09-20 | [7 empty] | 0
1694 | 666107 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Post Office | DUKINFIELD | SK16 4DB | 2024-07-11 | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 11:46 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 11:46 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFS1043794 | 30017519 | 2.Commissioning | AM |  | 2024-08-16 | 2024-08-16 |  | 0 |  |  |  | 2024-09-18 | [7 empty] | 0
1695 | 666826 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | Tuffley Convenience Store | GLOUCESTER | GL4 0QU | 2024-07-11 | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 12:35 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 12:35 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:0 _x000D_17/7/2024:0 _x000D_16/7/2024:0 _x000D_15/7/2024:0 _x000D_12/7/2024:0 _x000D_11/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFS1043997 | 30017500 | 2.Commissioning | AM |  | 2024-08-16 | 2024-08-16 |  | 0 |  |  |  | 2024-09-18 | [7 empty] | 0
1696 | 460572 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | One Stop | BARROW-IN-FURNESS | LA14 3NT | 2024-07-11 | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 10:46 _x000D_16/8/2024:Update: Order Completed by Supplier _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 15-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_17/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 15-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_16/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 15-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 15-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 15-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_11/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 15-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 10:46 _x000D_16/8/2024:Update: Order Completed by Supplier _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:0 _x000D_18/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 15-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_17/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 15-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_16/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 15-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 15-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 15-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_11/7/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 15-07-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFS1043996 | 30017429 | 2.Commissioning | AM |  | 2024-08-16 | 2024-08-16 |  | 0 | [11 empty] | 0
1697 | 654377 |  | Batch 6 Aug 24 | Type 1 | SoGEA/Mobile | One Stop Supermarket | BARNSLEY | S71 4PX | 2024-07-11 | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 11:49 _x000D_16/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update Allwyn requested this site to be cancelled for now as it is a chain store _x000D_18/7/2024:#Update Allwyn requested this site to be cancelled for now as it is a chain store _x000D_17/7/2024:#Update Allwyn requested this site to be cancelled for now as it is a chain store _x000D_16/7/2024:#Update Allwyn requested this site to be cancelled for now as it is a chain store _x000D_10/5/2024:#update - customer-related - customer to agree on quote provided on additional charges report for out of hours work before we reschedule the appointment. _x000D_23/04/2024: Order booked on 9/5 05/04/2024: Allwyn approved OOH on sunday. 21/02/2024: The appointment has been delayed due to a hazard that makes it unsafe to drill and install cables. The customer wants an OOH appointment. End user missed Appointment. New Appointment required within 15 calendar days to avoid cancellation | 20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:16/08/2024 11:49 _x000D_16/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_24/7/2024:0 _x000D_23/7/2024:0 _x000D_22/7/2024:0 _x000D_22/7/2024:0 _x000D_19/7/2024:#Update Allwyn requested this site to be cancelled for now as it is a chain store _x000D_18/7/2024:#Update Allwyn requested this site to be cancelled for now as it is a chain store _x000D_17/7/2024:#Update Allwyn requested this site to be cancelled for now as it is a chain store _x000D_16/7/2024:#Update Allwyn requested this site to be cancelled for now as it is a chain store _x000D_10/5/2024:#update - customer-related - customer to agree on quote provided on additional charges report for out of hours work before we reschedule the appointment. _x000D_23/04/2024: Order booked on 9/5 05/04/2024: Allwyn approved OOH on sunday. 21/02/2024: The appointment has been delayed due to a hazard that makes it unsafe to drill and install cables. The customer wants an OOH appointment. End user missed Appointment. New Appointment required within 15 calendar days to avoid cancellation | [6 empty] | 3.Allwyn to arrange rtr install | VFS1052413 | 30017698 | 2.Commissioning | AM |  | 2024-08-16 | 2024-08-16 |  | 0 |  |  |  | 2024-09-19 | [7 empty] | 0
1698 | 671651 |  | Batch 5 Jul24 | Type 1 | SoGEA/Mobile | Front Street Superstore | HOUGHTON LE SPRING | DH4 6LP |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_Services order cancelled following instruction from Allwyn to place the site 'on hold' 29/05 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_Services order cancelled following instruction from Allwyn to place the site 'on hold' 29/05 | 0 | 0 | [5 empty] | VFS1013074 | 30016488 | 1.Provisioning | AM |  |  |  |  | 0 | [11 empty] | 0
1699 | 666765 |  | Batch 6 Aug 24 | Type 2 | KCOM/Mobile | Elloughton News | Elloughton | HU15 1JP |  | 6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/09 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to KCOM Site Survey on 03/09 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to KCOM Site Survey on 03/09 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to KCOM Site Survey on 03/09 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to KCOM Site Survey on 03/09 AM _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_0 | 9/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/09 AM _x000D_6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 23/09 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to KCOM Site Survey on 03/09 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to KCOM Site Survey on 03/09 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to KCOM Site Survey on 03/09 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to KCOM Site Survey on 03/09 AM _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_0 | 0 | #Update - Allwyn confirmed Retailer has agreed to installation on 23/09 AM | [5 empty] | CSL Checking | 30022189 | 1.Provisioning | AM |  | 2024-08-19 |  |  | 0 | [11 empty] | 0
1700 | 664557 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Longhope Post Office | LONGHOPE | KW16 3PG |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_0 | 0 | 0 | [5 empty] | ADSL Available | 30022197 | 1.Provisioning | AM |  | 2024-08-19 |  |  | 0 | [11 empty] | 0
1701 | 665537 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Newburgh Post Office | Cupar | KY14 6DA |  | 22/8/2024:Order Completed _x000D_21/8/2024:Order Completed _x000D_20/8/2024:Order Completed _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_0 | 22/8/2024:Order Completed _x000D_21/8/2024:Order Completed _x000D_20/8/2024:Order Completed _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_0 | [6 empty] | 3.Allwyn to arrange rtr install | VFS1070078 | 30022174 | 2.Commissioning | AM |  | 2024-08-19 | 2024-08-19 |  | 0 | [11 empty] | 0
1702 | 666813 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Littleport Convenience Store | ELY | CB6 1PJ |  | 22/8/2024:Order Completed _x000D_21/8/2024:Order Completed _x000D_20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:19/08/2024 10:35 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 22/8/2024:Order Completed _x000D_21/8/2024:Order Completed _x000D_20/8/2024:Order Completed _x000D_19/8/2024:Order Completed _x000D_19/8/2024:19/08/2024 10:35 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFS1065634 | 30021995 | 2.Commissioning | AM |  | 2024-08-19 | 2024-08-19 |  | 0 | [11 empty] | 0
1703 | 450129 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Jubilee Road | Aberdare | CF44 6DD |  | 22/8/2024:Order Completed _x000D_21/8/2024:Order Completed _x000D_20/8/2024:Order Completed _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 22/8/2024:Order Completed _x000D_21/8/2024:Order Completed _x000D_20/8/2024:Order Completed _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFS1065629 | 30022053 | 2.Commissioning | AM |  | 2024-08-19 | 2024-08-19 |  | 0 | [11 empty] | 0
1704 | 668803 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Nisa Cowie | STIRLING | FK7 7BL |  | 6/9/2024:#Update Retailer confirmed 11/09, PM. _x000D_5/9/2024:#Update Retailer confirmed 11/09, PM. _x000D_4/9/2024:#Update Retailer confirmed 11/09, PM. _x000D_3/9/2024:#Update Retailer confirmed 11/09, PM. _x000D_2/9/2024:#Update Retailer confirmed 11/09, PM. _x000D_29/8/2024:#Update Retailer confirmed 11/09, PM. _x000D_28/8/2024:#Update Retailer confirmed 11/09, PM. _x000D_27/8/2024:#Update Retailer confirmed 11/09, PM. _x000D_22/8/2024:Your order has been delayed by our Suppliers due to unable to access distribution point within customer premises. Please check with end user and re-appoint order once access arranged. _x000D_21/8/2024:Your order has been delayed by our Suppliers due to unable to access distribution point within customer premises. Please check with end user and re-appoint order once access arranged. _x000D_20/8/2024:End User Missed appointment. Action required _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:#Update Retailer confirmed 11/09, PM. _x000D_6/9/2024:#Update Retailer confirmed 11/09, PM. _x000D_5/9/2024:#Update Retailer confirmed 11/09, PM. _x000D_4/9/2024:#Update Retailer confirmed 11/09, PM. _x000D_3/9/2024:#Update Retailer confirmed 11/09, PM. _x000D_2/9/2024:#Update Retailer confirmed 11/09, PM. _x000D_29/8/2024:#Update Retailer confirmed 11/09, PM. _x000D_28/8/2024:#Update Retailer confirmed 11/09, PM. _x000D_27/8/2024:#Update Retailer confirmed 11/09, PM. _x000D_22/8/2024:Your order has been delayed by our Suppliers due to unable to access distribution point within customer premises. Please check with end user and re-appoint order once access arranged. _x000D_21/8/2024:Your order has been delayed by our Suppliers due to unable to access distribution point within customer premises. Please check with end user and re-appoint order once access arranged. _x000D_20/8/2024:End User Missed appointment. Action required _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 0 | #Update Retailer confirmed 11/09, PM. | [5 empty] | VFS1065628 | 30022022 | 1.Provisioning | AM |  | 2024-08-19 | 2024-08-19 |  | 0 | [11 empty] | 0
1705 | 670727 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Sandhaven Shoppie | Sandhaven | AB43 7EQ |  | 22/8/2024:Order Completed _x000D_21/8/2024:Order Completed _x000D_20/8/2024:Update: Order Completed by Supplier _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_0 | 22/8/2024:Order Completed _x000D_21/8/2024:Order Completed _x000D_20/8/2024:Update: Order Completed by Supplier _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_0 | [6 empty] | 3.Allwyn to arrange rtr install | VFS1070058 | 30022186 | 2.Commissioning | AM |  | 2024-08-20 | 2024-08-20 |  | 0 | [11 empty] | 0
1706 | 665455 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Thaxted Post Office | Dunmow | CM6 2LA |  | 22/8/2024:Order Completed _x000D_21/8/2024:Order Completed _x000D_20/8/2024:Order Completed _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_0 | 22/8/2024:Order Completed _x000D_21/8/2024:Order Completed _x000D_20/8/2024:Order Completed _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_0 | [6 empty] | 3.Allwyn to arrange rtr install | VFS1070051 | 30022194 | 2.Commissioning | AM |  | 2024-08-20 | 2024-08-20 |  | 0 | [11 empty] | 0
1707 | 632806 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Millbrook Premier Stores | Millbrook | PL10 1BA |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_0 | 0 | 0 | [5 empty] | ADSL Available | 30022182 | 1.Provisioning | AM |  | 2024-08-20 |  |  | 0 | [11 empty] | 0
1708 | 665376 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Cambusbarron PO & Village Store | Stirling | FK7 9JT |  | 6/9/2024:#Update retailer has confirmed new appoint. _x000D_5/9/2024:#Update retailer has confirmed new appoint. _x000D_4/9/2024:#Update retailer has confirmed new appoint. _x000D_3/9/2024:#Update retailer has confirmed new appoint. _x000D_2/9/2024:#Update retailer has confirmed new appoint. _x000D_29/8/2024:#Update retailer has confirmed new appoint. _x000D_28/8/2024:#Update - Retailer unaware - Action for allwyn, Please confirm new appointment for 23/09 - am with the retailer. _x000D_27/8/2024:#Update - Retailer unaware - Action for allwyn, Please confirm new appointment for 23/09 - am with the retailer. _x000D_22/8/2024:#Update - Retailer unaware - Action for allwyn, Please confirm new appointment for 23/09 - am with the retailer. _x000D_21/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_0 | 9/9/2024:#Update retailer has confirmed new appoint. _x000D_6/9/2024:#Update retailer has confirmed new appoint. _x000D_5/9/2024:#Update retailer has confirmed new appoint. _x000D_4/9/2024:#Update retailer has confirmed new appoint. _x000D_3/9/2024:#Update retailer has confirmed new appoint. _x000D_2/9/2024:#Update retailer has confirmed new appoint. _x000D_29/8/2024:#Update retailer has confirmed new appoint. _x000D_28/8/2024:#Update - Retailer unaware - Action for allwyn, Please confirm new appointment for 23/09 - am with the retailer. _x000D_27/8/2024:#Update - Retailer unaware - Action for allwyn, Please confirm new appointment for 23/09 - am with the retailer. _x000D_22/8/2024:#Update - Retailer unaware - Action for allwyn, Please confirm new appointment for 23/09 - am with the retailer. _x000D_21/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_0 | 0 | #Update retailer has confirmed new appoint. | [5 empty] | VFS1070048 | 30022184 | 1.Provisioning | AM |  | 2024-08-20 | 2024-08-20 |  | 0 | [11 empty] | 0
1709 | 659748 |  | Batch 6 Aug 24 | Type 2 | SoGEA | East Kirkby General Store | Spilsby | PE23 4BY |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_0 | 0 | 0 | [5 empty] | Address query | 30022196 | 1.Provisioning | AM |  | 2024-08-20 |  |  | 0 | [11 empty] | 0
1710 | 642187 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Keystore | Macduff | AB44 1TL |  | 22/8/2024:#Update Network Planning issues. Please await for further updates _x000D_21/8/2024:#Update Network Planning issues. Please await for further updates _x000D_20/8/2024:#Update Network Planning issues. Please await for further updates _x000D_19/8/2024:#Update Network Planning issues. Please await for further updates _x000D_19/8/2024:01534319 _x000D_16/8/2024:#Update Network Planning issues. Please await for further updates _x000D_15/8/2024:#Update Network Planning issues. Please await for further updates _x000D_14/8/2024:#Update Network Planning issues. Please await for further updates _x000D_13/8/2024:#Update Network Planning issues. Please await for further updates _x000D_12/8/2024:#Update Network Planning issues. Please await for further updates _x000D_9/8/2024:#Update Network Planning issues. Please await for further updates _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update Network Planning issues. Please await for further updates _x000D_29/7/2024:#Update Network Planning issues. Please await for further updates _x000D_29/7/2024:01534319 _x000D_26/7/2024:25/07/2024 20:28 _x000D_ | 22/8/2024:#Update Network Planning issues. Please await for further updates _x000D_21/8/2024:#Update Network Planning issues. Please await for further updates _x000D_20/8/2024:#Update Network Planning issues. Please await for further updates _x000D_19/8/2024:#Update Network Planning issues. Please await for further updates _x000D_19/8/2024:01534319 _x000D_16/8/2024:#Update Network Planning issues. Please await for further updates _x000D_15/8/2024:#Update Network Planning issues. Please await for further updates _x000D_14/8/2024:#Update Network Planning issues. Please await for further updates _x000D_13/8/2024:#Update Network Planning issues. Please await for further updates _x000D_12/8/2024:#Update Network Planning issues. Please await for further updates _x000D_9/8/2024:#Update Network Planning issues. Please await for further updates _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update Network Planning issues. Please await for further updates _x000D_29/7/2024:#Update Network Planning issues. Please await for further updates _x000D_29/7/2024:01534319 _x000D_26/7/2024:25/07/2024 20:28 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFS1065627 | 30022101 | 2.Commissioning | AM |  | 2024-08-19 | 2024-08-19 |  | 0 | [11 empty] | 0
1711 | 665750 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Hartlebury Store & PO | Kidderminster | DY11 7TA |  | 6/9/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_5/9/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_4/9/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_3/9/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_2/9/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_29/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_28/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_27/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_22/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_21/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_20/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_19/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_19/8/2024:01589245 _x000D_16/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_0 | 9/9/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_6/9/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_5/9/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_4/9/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_3/9/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_2/9/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_29/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_28/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_27/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_22/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_21/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_20/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_19/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_19/8/2024:01589245 _x000D_16/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_0 | Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 06/09/2024. We will continue to provide update as they become available. | #Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. | [5 empty] | VFS1083251 | 30022192 | 1.Provisioning | AM |  | 2024-08-20 |  |  | 0 | [11 empty] | 0
1712 | 478077 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Premier | Aberystwyth | SY23 3AD |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_0 | 0 | 0 | [5 empty] | Address query | 30022178 | 1.Provisioning | AM |  | 2024-08-21 |  |  | 0 | [11 empty] | 0
1713 | 664521 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Goonhavern Bridge Stores & PO | Truro | TR4 9PY |  | 6/9/2024:#Update - installation incomplete - OOH required, CSL awaiting scope of work from Openreach and will progress accordingly _x000D_5/9/2024:#Update - installation incomplete - OOH required, CSL awaiting scope of work from Openreach and will progress accordingly _x000D_4/9/2024:#Update - installation incomplete - OOH required, CSL awaiting scope of work from Openreach and will progress accordingly _x000D_3/9/2024:#Update - installation incomplete - OOH required, CSL awaiting scope of work from Openreach and will progress accordingly _x000D_2/9/2024:#Update - installation incomplete - OOH required, CSL awaiting scope of work from Openreach and will progress accordingly _x000D_29/8/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 30/08/2024. We will continue to provide update as they become available. _x000D_28/8/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 30/08/2024. We will continue to provide update as they become available. _x000D_27/8/2024:Delay on Engineer activities. Supplier will arrange new appointment _x000D_22/8/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_21/8/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_20/8/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/8/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/8/2024:15/08/2024 09:04 _x000D_16/8/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/8/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_14/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 16/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_13/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 09/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 09/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_9/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 09/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_8/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 09/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 09/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 07/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_2/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 07/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_0 | 9/9/2024:#Update - installation incomplete - OOH required, CSL awaiting scope of work from Openreach and will progress accordingly _x000D_6/9/2024:#Update - installation incomplete - OOH required, CSL awaiting scope of work from Openreach and will progress accordingly _x000D_5/9/2024:#Update - installation incomplete - OOH required, CSL awaiting scope of work from Openreach and will progress accordingly _x000D_4/9/2024:#Update - installation incomplete - OOH required, CSL awaiting scope of work from Openreach and will progress accordingly _x000D_3/9/2024:#Update - installation incomplete - OOH required, CSL awaiting scope of work from Openreach and will progress accordingly _x000D_2/9/2024:#Update - installation incomplete - OOH required, CSL awaiting scope of work from Openreach and will progress accordingly _x000D_29/8/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 30/08/2024. We will continue to provide update as they become available. _x000D_28/8/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 30/08/2024. We will continue to provide update as they become available. _x000D_27/8/2024:Delay on Engineer activities. Supplier will arrange new appointment _x000D_22/8/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_21/8/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_20/8/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/8/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/8/2024:15/08/2024 09:04 _x000D_16/8/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/8/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_14/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 16/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_13/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 09/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 09/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_9/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 09/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_8/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 09/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 09/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 07/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_2/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 07/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_0 | Your order has been delayed. Multiskilled engineer work is required. Our Suppliers have given us a review date of 16/09/2024. We will continue to provide update as they become available. | #Update - installation incomplete - OOH required, CSL awaiting scope of work from Openreach and will progress accordingly | [5 empty] | VFS1069700 | 30022188 | 1.Provisioning | AM |  | 2024-08-22 | 2024-08-22 |  | 0 | [11 empty] | 0
1714 | 657751 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Dobsons Convenience Store | Sleaford | NG34 0QD |  | 22/8/2024:Order Completed _x000D_21/8/2024:Order Completed _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_0 | 22/8/2024:Order Completed _x000D_21/8/2024:Order Completed _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_0 | [6 empty] | 3.Allwyn to arrange rtr install | VFS1069692 | 30022200 | 2.Commissioning | AM |  | 2024-08-21 | 2024-08-21 |  | 0 | [11 empty] | 0
1715 | 661782 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Premier Grantown on Spey | Grantown-on-Spey | PH26 3HF |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_0 | 0 | 0 | [5 empty] | Address query | 30022180 | 1.Provisioning | AM |  | 2024-08-21 |  |  | 0 | [11 empty] | 0
1716 | 671864 |  | Batch 6 Aug 24 | Type 2 | FTTP | Weeting Village Store | Weeting | IP27 0QN |  | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 0 | 0 | [5 empty] | VFP2431218 | 30021972 | 1.Provisioning | AM |  | 2024-08-20 | 2024-09-06 |  | 0 | [11 empty] | 0
1717 | 665831 |  | Batch 6 Aug 24 | Type 2 | FTTP | West Harptree Post Office | Bristol | BS40 6EA |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 0 | 0 | [5 empty] | Address query | 30022004 | 1.Provisioning | AM |  | 2024-08-20 |  |  | 0 | [11 empty] | 0
1718 | 654725 |  | Batch 6 Aug 24 | Type 2 | FTTP | Supervalu Portglenone | Ballymena | BT44 8AB |  | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 0 | 0 | [5 empty] | VFP2431220 | 30021967 | 1.Provisioning | AM |  | 2024-08-20 | 2024-09-06 |  | 0 | [11 empty] | 0
1719 | 446995 |  | Batch 6 Aug 24 | Type 2 | FTTP | Family Choice | HORNSEA | HU18 1HU |  | 22/8/2024:Order Completed _x000D_21/8/2024:Order Completed _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 22/8/2024:Order Completed _x000D_21/8/2024:Order Completed _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2431215 | 30022040 | 2.Commissioning | AM |  | 2024-08-20 | 2024-08-20 |  | 0 | [11 empty] | 0
1720 | 665821 |  | Batch 6 Aug 24 | Type 2 | FTTP | Spar Supermarket | NEWRY | BT35 9RD |  | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 0 | 0 | [5 empty] | VFP2431216 | 30021990 | 1.Provisioning | AM |  | 2024-08-20 | 2024-09-06 |  | 0 | [11 empty] | 0
1721 | 644726 |  | Batch 6 Aug 24 | Type 2 | FTTP/Mobile | Spar Stores | TARPORLEY | CW6 0AY |  | 6/9/2024:#Update E- Multiport -Pushed out to August _x000D_5/9/2024:#Update E- Multiport -Pushed out to August _x000D_4/9/2024:#Update E- Multiport -Pushed out to August _x000D_3/9/2024:#Update E- Multiport -Pushed out to August _x000D_2/9/2024:#Update E- Multiport -Pushed out to August _x000D_29/8/2024:#Update E- Multiport -Pushed out to August _x000D_28/8/2024:#Update E- Multiport -Pushed out to August _x000D_27/8/2024:#Update E- Multiport -Pushed out to August _x000D_22/8/2024:#Update E- Multiport -Pushed out to August _x000D_21/8/2024:#Update E- Multiport -Pushed out to August _x000D_20/8/2024:#Update E- Multiport -Pushed out to August _x000D_19/8/2024:#Update E- Multiport -Pushed out to August _x000D_19/8/2024:01459028 _x000D_16/8/2024:#Update E- Multiport -Pushed out to August _x000D_15/8/2024:#Update E- Multiport -Pushed out to August _x000D_14/8/2024:#Update E- Multiport -Pushed out to August _x000D_13/8/2024:#Update E- Multiport -Pushed out to August _x000D_12/8/2024:#Update E- Multiport -Pushed out to August _x000D_9/8/2024:#Update E- Multiport -Pushed out to August _x000D_8/8/2024:10/07/2024 _x000D_6/8/2024:10/07/2024 _x000D_5/8/2024:10/07/2024 _x000D_2/8/2024:10/07/2024 _x000D_1/8/2024:10/07/2024 _x000D_31/7/2024:10/07/2024 _x000D_31/7/2024:10/07/2024 _x000D_30/7/2024:#Update E- Multiport -Pushed out to August _x000D_29/7/2024:#Update E- Multiport -Pushed out to August _x000D_29/7/2024:01459028 _x000D_26/7/2024:01459028 _x000D_ | 9/9/2024:#Update E- Multiport -Pushed out to August _x000D_6/9/2024:#Update E- Multiport -Pushed out to August _x000D_5/9/2024:#Update E- Multiport -Pushed out to August _x000D_4/9/2024:#Update E- Multiport -Pushed out to August _x000D_3/9/2024:#Update E- Multiport -Pushed out to August _x000D_2/9/2024:#Update E- Multiport -Pushed out to August _x000D_29/8/2024:#Update E- Multiport -Pushed out to August _x000D_28/8/2024:#Update E- Multiport -Pushed out to August _x000D_27/8/2024:#Update E- Multiport -Pushed out to August _x000D_22/8/2024:#Update E- Multiport -Pushed out to August _x000D_21/8/2024:#Update E- Multiport -Pushed out to August _x000D_20/8/2024:#Update E- Multiport -Pushed out to August _x000D_19/8/2024:#Update E- Multiport -Pushed out to August _x000D_19/8/2024:01459028 _x000D_16/8/2024:#Update E- Multiport -Pushed out to August _x000D_15/8/2024:#Update E- Multiport -Pushed out to August _x000D_14/8/2024:#Update E- Multiport -Pushed out to August _x000D_13/8/2024:#Update E- Multiport -Pushed out to August _x000D_12/8/2024:#Update E- Multiport -Pushed out to August _x000D_9/8/2024:#Update E- Multiport -Pushed out to August _x000D_8/8/2024:10/07/2024 _x000D_6/8/2024:10/07/2024 _x000D_5/8/2024:10/07/2024 _x000D_2/8/2024:10/07/2024 _x000D_1/8/2024:10/07/2024 _x000D_31/7/2024:10/07/2024 _x000D_31/7/2024:10/07/2024 _x000D_30/7/2024:#Update E- Multiport -Pushed out to August _x000D_29/7/2024:#Update E- Multiport -Pushed out to August _x000D_29/7/2024:01459028 _x000D_26/7/2024:01459028 _x000D_ | 0 | #Update E- Multiport -Pushed out to August | [5 empty] | VFP2403894 | 30016188 | 1.Provisioning | AM |  | 2024-07-25 | 2024-09-06 |  | 0 | [11 empty] | 0
1722 | 444208 |  | Batch 6 Aug 24 | Type 2 | FTTP | Londis | Worcester | WR7 4DB |  | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 0 | 0 | [5 empty] | VFP2431214 | 30022046 | 1.Provisioning | AM |  | 2024-08-20 | 2024-09-06 |  | 0 | [11 empty] | 0
1723 | 652513 |  | Batch 6 Aug 24 | Type 2 | FTTP | Spar | Omagh | BT78 4SD |  | 22/8/2024:Order Completed _x000D_21/8/2024:Order Completed _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 22/8/2024:Order Completed _x000D_21/8/2024:Order Completed _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2431213 | 30022141 | 2.Commissioning | AM |  | 2024-08-20 | 2024-08-20 |  | 0 | [11 empty] | 0
1724 | 655683 |  | Batch 6 Aug 24 | Type 2 | FTTP | Holt Fleet Convenience Store | Worcester | WR6 6NN |  | 6/9/2024:#uPDATE - Traffic management work required. Our Suppliers have given us a review date of 23/08/2024 _x000D_5/9/2024:#uPDATE - Traffic management work required. Our Suppliers have given us a review date of 23/08/2024 _x000D_4/9/2024:#uPDATE - Traffic management work required. Our Suppliers have given us a review date of 23/08/2024 _x000D_3/9/2024:#uPDATE - Traffic management work required. Our Suppliers have given us a review date of 23/08/2024 _x000D_2/9/2024:#uPDATE - Traffic management work required. Our Suppliers have given us a review date of 23/08/2024 _x000D_29/8/2024:#uPDATE - Traffic management work required. Our Suppliers have given us a review date of 23/08/2024 _x000D_28/8/2024:#uPDATE - Traffic management work required. Our Suppliers have given us a review date of 23/08/2024 _x000D_27/8/2024:#uPDATE - Traffic management work required. Our Suppliers have given us a review date of 23/08/2024 _x000D_22/8/2024:#uPDATE - Traffic management work required. Our Suppliers have given us a review date of 23/08/2024 _x000D_21/8/2024:#uPDATE - Traffic management work required. Our Suppliers have given us a review date of 23/08/2024 _x000D_20/8/2024:#uPDATE - Traffic management work required. Our Suppliers have given us a review date of 23/08/2024 _x000D_19/8/2024:#uPDATE - Traffic management work required. Our Suppliers have given us a review date of 23/08/2024 _x000D_19/8/2024:01580302 _x000D_16/8/2024:#uPDATE - Traffic management work required. Our Suppliers have given us a review date of 23/08/2024 _x000D_15/8/2024:#uPDATE - Traffic management work required. Our Suppliers have given us a review date of 23/08/2024 _x000D_14/8/2024:#uPDATE - Traffic management work required. Our Suppliers have given us a review date of 23/08/2024 _x000D_13/8/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 23/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data receive _x000D_12/8/2024:0 _x000D_9/8/2024:Supplier Delay: Issues relating to permission to provide the network, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_8/8/2024:Supplier Delay: Issues relating to permission to provide the network, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/8/2024:Supplier Delay: Issues relating to permission to provide the network, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/8/2024:Supplier Delay: Issues relating to permission to provide the network, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_2/8/2024:A network engineering task is required to provision this order. The order will now follow the KCI2 Assure process. KCI2 with a confirmed end customer appointment will be sent once the task has completed. CSL Note: Invalid appointment slot received CSL Not _x000D_1/8/2024:A network engineering task is required to provision this order. The order will now follow the KCI2 Assure process. KCI2 with a confirmed end customer appointment will be sent once the task has completed. CSL Note: Invalid appointment slot received CSL Not _x000D_31/7/2024:A network engineering task is required to provision this order. The order will now follow the KCI2 Assure process. KCI2 with a confirmed end customer appointment will be sent once the task has completed. CSL Note: Invalid appointment slot received CSL Not _x000D_31/7/2024:37516 _x000D_30/7/2024:A network engineering task is required to provision this order. The order will now follow the KCI2 Assure process. KCI2 with a confirmed end customer appointment will be sent once the task has completed. CSL Note: Invalid appointment slot received CSL Not _x000D_29/7/2024:A network engineering task is required to provision this order. The order will now follow the KCI2 Assure process. KCI2 with a confirmed end customer appointment will be sent once the task has completed. CSL Note: Invalid appointment slot received CSL Not _x000D_29/7/2024:26/07/2024 09:37 _x000D_26/7/2024:26/07/2024 09:37 _x000D_ | 9/9/2024:#uPDATE - Traffic management work required. Our Suppliers have given us a review date of 23/08/2024 _x000D_6/9/2024:#uPDATE - Traffic management work required. Our Suppliers have given us a review date of 23/08/2024 _x000D_5/9/2024:#uPDATE - Traffic management work required. Our Suppliers have given us a review date of 23/08/2024 _x000D_4/9/2024:#uPDATE - Traffic management work required. Our Suppliers have given us a review date of 23/08/2024 _x000D_3/9/2024:#uPDATE - Traffic management work required. Our Suppliers have given us a review date of 23/08/2024 _x000D_2/9/2024:#uPDATE - Traffic management work required. Our Suppliers have given us a review date of 23/08/2024 _x000D_29/8/2024:#uPDATE - Traffic management work required. Our Suppliers have given us a review date of 23/08/2024 _x000D_28/8/2024:#uPDATE - Traffic management work required. Our Suppliers have given us a review date of 23/08/2024 _x000D_27/8/2024:#uPDATE - Traffic management work required. Our Suppliers have given us a review date of 23/08/2024 _x000D_22/8/2024:#uPDATE - Traffic management work required. Our Suppliers have given us a review date of 23/08/2024 _x000D_21/8/2024:#uPDATE - Traffic management work required. Our Suppliers have given us a review date of 23/08/2024 _x000D_20/8/2024:#uPDATE - Traffic management work required. Our Suppliers have given us a review date of 23/08/2024 _x000D_19/8/2024:#uPDATE - Traffic management work required. Our Suppliers have given us a review date of 23/08/2024 _x000D_19/8/2024:01580302 _x000D_16/8/2024:#uPDATE - Traffic management work required. Our Suppliers have given us a review date of 23/08/2024 _x000D_15/8/2024:#uPDATE - Traffic management work required. Our Suppliers have given us a review date of 23/08/2024 _x000D_14/8/2024:#uPDATE - Traffic management work required. Our Suppliers have given us a review date of 23/08/2024 _x000D_13/8/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 23/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data receive _x000D_12/8/2024:0 _x000D_9/8/2024:Supplier Delay: Issues relating to permission to provide the network, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_8/8/2024:Supplier Delay: Issues relating to permission to provide the network, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/8/2024:Supplier Delay: Issues relating to permission to provide the network, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/8/2024:Supplier Delay: Issues relating to permission to provide the network, please await for further details. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_2/8/2024:A network engineering task is required to provision this order. The order will now follow the KCI2 Assure process. KCI2 with a confirmed end customer appointment will be sent once the task has completed. CSL Note: Invalid appointment slot received CSL Not _x000D_1/8/2024:A network engineering task is required to provision this order. The order will now follow the KCI2 Assure process. KCI2 with a confirmed end customer appointment will be sent once the task has completed. CSL Note: Invalid appointment slot received CSL Not _x000D_31/7/2024:A network engineering task is required to provision this order. The order will now follow the KCI2 Assure process. KCI2 with a confirmed end customer appointment will be sent once the task has completed. CSL Note: Invalid appointment slot received CSL Not _x000D_31/7/2024:37516 _x000D_30/7/2024:A network engineering task is required to provision this order. The order will now follow the KCI2 Assure process. KCI2 with a confirmed end customer appointment will be sent once the task has completed. CSL Note: Invalid appointment slot received CSL Not _x000D_29/7/2024:A network engineering task is required to provision this order. The order will now follow the KCI2 Assure process. KCI2 with a confirmed end customer appointment will be sent once the task has completed. CSL Note: Invalid appointment slot received CSL Not _x000D_29/7/2024:26/07/2024 09:37 _x000D_26/7/2024:26/07/2024 09:37 _x000D_ | 0 | #uPDATE - Traffic management work required. Our Suppliers have given us a review date of 23/08/2024 | [5 empty] | VFP2431212 | 30022154 | 1.Provisioning | AM |  | 2024-08-20 |  |  | 0 | [11 empty] | 0
1725 | 672631 |  | Batch 6 Aug 24 | Type 2 | FTTP/Mobile | Spar | Looe | PL13 2EP |  | 6/9/2024:#Update - The retailer was unaware of the order and therefore refused entry. Additionally, the cable will need to run through the ceiling tiles into the back office and will have to be done at a quieter time. _x000D_5/9/2024:#Update - The retailer was unaware of the order and therefore refused entry. Additionally, the cable will need to run through the ceiling tiles into the back office and will have to be done at a quieter time. _x000D_4/9/2024:#Update - The retailer was unaware of the order and therefore refused entry. Additionally, the cable will need to run through the ceiling tiles into the back office and will have to be done at a quieter time. _x000D_3/9/2024:#Update - The retailer was unaware of the order and therefore refused entry. Additionally, the cable will need to run through the ceiling tiles into the back office and will have to be done at a quieter time. _x000D_2/9/2024:#Update - The retailer was unaware of the order and therefore refused entry. Additionally, the cable will need to run through the ceiling tiles into the back office and will have to be done at a quieter time. _x000D_29/8/2024:#Update - The retailer was unaware of the order and therefore refused entry. Additionally, the cable will need to run through the ceiling tiles into the back office and will have to be done at a quieter time. _x000D_28/8/2024:#Update - The retailer was unaware of the order and therefore refused entry. Additionally, the cable will need to run through the ceiling tiles into the back office and will have to be done at a quieter time. _x000D_27/8/2024:#Update - The retailer was unaware of the order and therefore refused entry. Additionally, the cable will need to run through the ceiling tiles into the back office and will have to be done at a quieter time. _x000D_22/8/2024:#Update - The retailer was unaware of the order and therefore refused entry. Additionally, the cable will need to run through the ceiling tiles into the back office and will have to be done at a quieter time. _x000D_21/8/2024:#Update - The retailer was unaware of the order and therefore refused entry. Additionally, the cable will need to run through the ceiling tiles into the back office and will have to be done at a quieter time. _x000D_20/8/2024:#Update - Order has been delayed as step-1 work is requried. CSL will update as more information become available. _x000D_13/8/2024:#Update - Order has been delayed as step-1 work is requried. CSL will update as more information become available. _x000D_12/8/2024:#Update - Order has been delayed as step-1 work is requried. CSL will update as more information become available. _x000D_9/8/2024:#Update - Order has been delayed as step-1 work is requried. CSL will update as more information become available. _x000D_8/8/2024:31/07/2024 _x000D_6/8/2024:31/07/2024 _x000D_5/8/2024:31/07/2024 _x000D_2/8/2024:31/07/2024 _x000D_1/8/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:#Update - The retailer was unaware of the order and therefore refused entry. Additionally, the cable will need to run through the ceiling tiles into the back office and will have to be done at a quieter time. _x000D_6/9/2024:#Update - The retailer was unaware of the order and therefore refused entry. Additionally, the cable will need to run through the ceiling tiles into the back office and will have to be done at a quieter time. _x000D_5/9/2024:#Update - The retailer was unaware of the order and therefore refused entry. Additionally, the cable will need to run through the ceiling tiles into the back office and will have to be done at a quieter time. _x000D_4/9/2024:#Update - The retailer was unaware of the order and therefore refused entry. Additionally, the cable will need to run through the ceiling tiles into the back office and will have to be done at a quieter time. _x000D_3/9/2024:#Update - The retailer was unaware of the order and therefore refused entry. Additionally, the cable will need to run through the ceiling tiles into the back office and will have to be done at a quieter time. _x000D_2/9/2024:#Update - The retailer was unaware of the order and therefore refused entry. Additionally, the cable will need to run through the ceiling tiles into the back office and will have to be done at a quieter time. _x000D_29/8/2024:#Update - The retailer was unaware of the order and therefore refused entry. Additionally, the cable will need to run through the ceiling tiles into the back office and will have to be done at a quieter time. _x000D_28/8/2024:#Update - The retailer was unaware of the order and therefore refused entry. Additionally, the cable will need to run through the ceiling tiles into the back office and will have to be done at a quieter time. _x000D_27/8/2024:#Update - The retailer was unaware of the order and therefore refused entry. Additionally, the cable will need to run through the ceiling tiles into the back office and will have to be done at a quieter time. _x000D_22/8/2024:#Update - The retailer was unaware of the order and therefore refused entry. Additionally, the cable will need to run through the ceiling tiles into the back office and will have to be done at a quieter time. _x000D_21/8/2024:#Update - The retailer was unaware of the order and therefore refused entry. Additionally, the cable will need to run through the ceiling tiles into the back office and will have to be done at a quieter time. _x000D_20/8/2024:#Update - Order has been delayed as step-1 work is requried. CSL will update as more information become available. _x000D_13/8/2024:#Update - Order has been delayed as step-1 work is requried. CSL will update as more information become available. _x000D_12/8/2024:#Update - Order has been delayed as step-1 work is requried. CSL will update as more information become available. _x000D_9/8/2024:#Update - Order has been delayed as step-1 work is requried. CSL will update as more information become available. _x000D_8/8/2024:31/07/2024 _x000D_6/8/2024:31/07/2024 _x000D_5/8/2024:31/07/2024 _x000D_2/8/2024:31/07/2024 _x000D_1/8/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 0 | #Update - The retailer was unaware of the order and therefore refused entry. Additionally, the cable will need to run through the ceiling tiles into the back office and will have to be done at a quieter time. | [5 empty] | VFP2431210 | 30022169 | 1.Provisioning |  |  | 2024-08-20 | 2024-08-20 |  | 0 | [11 empty] | 0
1726 | 651693 |  | Batch 6 Aug 24 | Type 2 | FTTP | Premier Rakegate Convenience | Wolverhampton | WV10 6UX |  | 22/8/2024:Order Completed _x000D_21/8/2024:Order Completed _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 22/8/2024:Order Completed _x000D_21/8/2024:Order Completed _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2431211 | 30022002 | 2.Commissioning | AM |  | 2024-08-20 | 2024-08-20 |  | 0 | [11 empty] | 0
1727 | 666664 |  | Batch 6 Aug 24 | Type 2 | FTTP | Polgooth PO & Store | St Austell | PL26 7BP |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 0 | 0 | [5 empty] | VFP2431209 | 30022089 | 1.Provisioning | AM |  | 2024-08-20 | 2024-08-20 |  | 0 | [11 empty] | 0
1728 | 666027 |  | Batch 6 Aug 24 | Type 2 | FTTP | Pluckley Post Office | Ashford | TN27 0QS |  | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 0 | 0 | [5 empty] | VFP2431208 | 30022069 | 1.Provisioning | AM |  | 2024-08-20 | 2024-09-06 |  | 0 | [11 empty] | 0
1729 | 664857 |  | Batch 6 Aug 24 | Type 2 | FTTP | Denver Post Office | DOWNHAM MARKET | PE38 0DF |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 0 | 0 | [5 empty] | Address query | 30022119 | 1.Provisioning | AM |  | 2024-08-20 |  |  | 0 | [11 empty] | 0
1730 | 630013 |  | Batch 6 Aug 24 | Type 2 | FTTP | Ashley Stores | Newmarket | CB8 9DX |  | 6/9/2024:#Update - missed appointment, retailer unaware of the installation, wants more time to figure out if they want it done or not. _x000D_5/9/2024:#Update - missed appointment, retailer unaware of the installation, wants more time to figure out if they want it done or not. _x000D_4/9/2024:#Update - missed appointment, retailer unaware of the installation, wants more time to figure out if they want it done or not. _x000D_3/9/2024:#Update - missed appointment, retailer unaware of the installation, wants more time to figure out if they want it done or not. _x000D_2/9/2024:#Update - missed appointment, retailer unaware of the installation, wants more time to figure out if they want it done or not. _x000D_29/8/2024:#Update - missed appointment, retailer unaware of the installation, wants more time to figure out if they want it done or not. _x000D_28/8/2024:#Update - missed appointment, retailer unaware of the installation, wants more time to figure out if they want it done or not. _x000D_27/8/2024:#Update - missed appointment, retailer unaware of the installation, wants more time to figure out if they want it done or not. _x000D_22/8/2024:#Update - missed appointment, retailer unaware of the installation, wants more time to figure out if they want it done or not. _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:#Update - missed appointment, retailer unaware of the installation, wants more time to figure out if they want it done or not. _x000D_6/9/2024:#Update - missed appointment, retailer unaware of the installation, wants more time to figure out if they want it done or not. _x000D_5/9/2024:#Update - missed appointment, retailer unaware of the installation, wants more time to figure out if they want it done or not. _x000D_4/9/2024:#Update - missed appointment, retailer unaware of the installation, wants more time to figure out if they want it done or not. _x000D_3/9/2024:#Update - missed appointment, retailer unaware of the installation, wants more time to figure out if they want it done or not. _x000D_2/9/2024:#Update - missed appointment, retailer unaware of the installation, wants more time to figure out if they want it done or not. _x000D_29/8/2024:#Update - missed appointment, retailer unaware of the installation, wants more time to figure out if they want it done or not. _x000D_28/8/2024:#Update - missed appointment, retailer unaware of the installation, wants more time to figure out if they want it done or not. _x000D_27/8/2024:#Update - missed appointment, retailer unaware of the installation, wants more time to figure out if they want it done or not. _x000D_22/8/2024:#Update - missed appointment, retailer unaware of the installation, wants more time to figure out if they want it done or not. _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | Ruggedised ONT cannot be installed due to Incorrect or no power supply present. | #Update - missed appointment, retailer unaware of the installation, wants more time to figure out if they want it done or not. | [5 empty] | VFP2431207 | 30022032 | 1.Provisioning | AM |  | 2024-08-20 | 2024-08-20 |  | 0 | [11 empty] | 0
1731 | 672605 |  | Batch 6 Aug 24 | Type 2 | FTTP/Mobile | Spar Castor Road | BRIXHAM | TQ5 9PY |  | 22/8/2024:Order Completed _x000D_21/8/2024:Order Completed _x000D_20/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 22/8/2024:Order Completed _x000D_21/8/2024:Order Completed _x000D_20/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2431206 | 30022077 | 2.Commissioning |  |  | 2024-08-20 | 2024-08-20 |  | 0 | [11 empty] | 0
1732 | 662356 |  | Batch 6 Aug 24 | Type 2 | SoGEA | The Local Walshaw | Bury | BL8 3AZ |  | 22/8/2024:Order Completed _x000D_21/8/2024:Order Completed _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 22/8/2024:Order Completed _x000D_21/8/2024:Order Completed _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFS1065625 | 30022147 | 2.Commissioning | AM |  | 2024-08-20 | 2024-08-20 |  | 0 | [11 empty] | 0
1733 | 653662 |  | Batch 6 Aug 24 | Type 2 | FTTP | Premier Newry Stores | Caergybi | LL65 1HP |  | 22/8/2024:Order Completed _x000D_21/8/2024:Order Completed _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 22/8/2024:Order Completed _x000D_21/8/2024:Order Completed _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2431203 | 30022047 | 2.Commissioning | AM |  | 2024-08-20 | 2024-08-20 |  | 0 | [11 empty] | 0
1734 | 652622 |  | Batch 6 Aug 24 | Type 2 | FTTP | McGlincheys | Tyrone | BT82 9RP |  | 6/9/2024:#Update Allwyn calling retailer 04/09 to advise of new appointment. _x000D_5/9/2024:#Update Allwyn calling retailer 04/09 to advise of new appointment. _x000D_4/9/2024:#Update Allwyn calling retailer 04/09 to advise of new appointment. _x000D_3/9/2024:#Update Allwyn calling retailer 04/09 to advise of new appointment. _x000D_2/9/2024:#Update Allwyn calling retailer 04/09 to advise of new appointment. _x000D_29/8/2024:0 _x000D_28/8/2024:Your order has been delayed due to a customer missed appointment. Incorrect Address Please check with end user and reappoint the order if still required. _x000D_27/8/2024:Your order has been delayed due to a customer missed appointment. Incorrect Address Please check with end user and reappoint the order if still required. _x000D_22/8/2024:Your order has been delayed due to a customer missed appointment. Incorrect Address Please check with end user and reappoint the order if still required. _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:#Update Allwyn calling retailer 04/09 to advise of new appointment. _x000D_6/9/2024:#Update Allwyn calling retailer 04/09 to advise of new appointment. _x000D_5/9/2024:#Update Allwyn calling retailer 04/09 to advise of new appointment. _x000D_4/9/2024:#Update Allwyn calling retailer 04/09 to advise of new appointment. _x000D_3/9/2024:#Update Allwyn calling retailer 04/09 to advise of new appointment. _x000D_2/9/2024:#Update Allwyn calling retailer 04/09 to advise of new appointment. _x000D_29/8/2024:0 _x000D_28/8/2024:Your order has been delayed due to a customer missed appointment. Incorrect Address Please check with end user and reappoint the order if still required. _x000D_27/8/2024:Your order has been delayed due to a customer missed appointment. Incorrect Address Please check with end user and reappoint the order if still required. _x000D_22/8/2024:Your order has been delayed due to a customer missed appointment. Incorrect Address Please check with end user and reappoint the order if still required. _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 0 | #Update Allwyn calling retailer 04/09 to advise of new appointment. | [5 empty] | VFS1098799 | 30022021 | 1.Provisioning | AM |  | 2024-08-20 | 2024-08-20 |  | 0 | [11 empty] | 0
1735 | 649334 |  | Batch 6 Aug 24 | Type 2 | FTTP | Today Local | ENNISKILLEN | BT94 3LU |  | 22/8/2024:Order Completed _x000D_21/8/2024:Order Completed _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_1/8/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:37642 _x000D_30/7/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:27/07/2024 12:01 _x000D_26/7/2024:0 _x000D_ | 22/8/2024:Order Completed _x000D_21/8/2024:Order Completed _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_1/8/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:37642 _x000D_30/7/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:27/07/2024 12:01 _x000D_26/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2431204 | 30022024 | 2.Commissioning | AM |  | 2024-08-20 | 2024-08-20 |  | 0 | [11 empty] | 0
1736 | 642247 |  | Batch 6 Aug 24 | Type 2 | FTTP | Dans Goods | St Andrews | KY16 0UG |  | 22/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_21/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_20/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_19/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_19/8/2024:01544973 _x000D_16/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_14/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_13/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_12/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_9/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_8/8/2024:31/07/2024 _x000D_6/8/2024:31/07/2024 _x000D_5/8/2024:31/07/2024 _x000D_2/8/2024:31/07/2024 _x000D_1/8/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 22/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_21/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_20/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_19/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_19/8/2024:01544973 _x000D_16/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_14/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_13/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_12/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_9/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_8/8/2024:31/07/2024 _x000D_6/8/2024:31/07/2024 _x000D_5/8/2024:31/07/2024 _x000D_2/8/2024:31/07/2024 _x000D_1/8/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2431202 | 30022008 | 2.Commissioning | AM |  | 2024-08-20 | 2024-08-20 |  | 0 | [11 empty] | 0
1737 | 639239 |  | Batch 6 Aug 24 | Type 2 | FTTP | O'Hares Warrenpoint Ltd | Down | BT34 3PN |  | 22/8/2024:Order Completed _x000D_21/8/2024:Order Completed _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/8/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/8/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_2/8/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_1/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 13/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 13/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:37808 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 22/8/2024:Order Completed _x000D_21/8/2024:Order Completed _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/8/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/8/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_2/8/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_1/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 13/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 13/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:37808 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2431201 | 30022084 | 2.Commissioning | AM |  | 2024-08-20 | 2024-08-20 |  | 0 | [11 empty] | 0
1738 | 638486 |  | Batch 6 Aug 24 | Type 2 | FTTP | Dukes | Armagh | BT63 6HY |  | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 0 | 0 | [5 empty] | VFP2431199 | 30022012 | 1.Provisioning | AM |  | 2024-08-20 | 2024-09-06 |  | 0 | [11 empty] | 0
1739 | 629447 |  | Batch 6 Aug 24 | Type 2 | FTTP | Alderbury Village Stores | Alderbury | SP5 3NY |  | 22/8/2024:Order Completed _x000D_21/8/2024:Order Completed _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 22/8/2024:Order Completed _x000D_21/8/2024:Order Completed _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2431200 | 30021968 | 2.Commissioning | AM |  | 2024-08-20 | 2024-08-20 |  | 0 | [11 empty] | 0
1740 | 604115 |  | Batch 6 Aug 24 | Type 2 | FTTP | Best One | stonehaven | AB39 2HD |  | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 0 | 0 | [5 empty] | VFP2431197 | 30021977 | 1.Provisioning | AM |  | 2024-08-21 | 2024-09-06 |  | 0 | [11 empty] | 0
1741 | 604516 |  | Batch 6 Aug 24 | Type 2 | FTTP | Alexandra Park Convenience Store | Swindon | SN4 0FL | 2024-09-06 | 6/9/2024:#Update - NFA - Allwyn have confirmed new installation date 05/09 AM with retailer _x000D_5/9/2024:#Update - NFA - Allwyn have confirmed new installation date 05/09 AM with retailer _x000D_4/9/2024:#Update - NFA - Allwyn have confirmed new installation date 05/09 AM with retailer _x000D_3/9/2024:#Update - NFA - Allwyn have confirmed new installation date 05/09 AM with retailer _x000D_2/9/2024:#Update - NFA - Allwyn have confirmed new installation date 05/09 AM with retailer _x000D_29/8/2024:#Update - unsuccessful install, retailer unaware the order, Allwyn to liaise with retailer _x000D_28/8/2024:#Update - unsuccessful install, retailer unaware the order, Allwyn to liaise with retailer _x000D_27/8/2024:#Update - unsuccessful install, retailer unaware the order, Allwyn to liaise with retailer _x000D_22/8/2024:#Update - unsuccessful install, retailer unaware the order, Allwyn to liaise with retailer _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:#Update - NFA - Allwyn have confirmed new installation date 05/09 AM with retailer _x000D_6/9/2024:#Update - NFA - Allwyn have confirmed new installation date 05/09 AM with retailer _x000D_5/9/2024:#Update - NFA - Allwyn have confirmed new installation date 05/09 AM with retailer _x000D_4/9/2024:#Update - NFA - Allwyn have confirmed new installation date 05/09 AM with retailer _x000D_3/9/2024:#Update - NFA - Allwyn have confirmed new installation date 05/09 AM with retailer _x000D_2/9/2024:#Update - NFA - Allwyn have confirmed new installation date 05/09 AM with retailer _x000D_29/8/2024:#Update - unsuccessful install, retailer unaware the order, Allwyn to liaise with retailer _x000D_28/8/2024:#Update - unsuccessful install, retailer unaware the order, Allwyn to liaise with retailer _x000D_27/8/2024:#Update - unsuccessful install, retailer unaware the order, Allwyn to liaise with retailer _x000D_22/8/2024:#Update - unsuccessful install, retailer unaware the order, Allwyn to liaise with retailer _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | Order Completed | #Update - NFA - Allwyn have confirmed new installation date 05/09 AM with retailer | [5 empty] | VFP2431198 | 30022045 | 2.Commissioning | AM |  | 2024-08-21 | 2024-08-21 |  | 0 | [11 empty] | 0
1742 | 631895 |  | Batch 6 Aug 24 | Type 2 | FTTP | Nearbuy Orchard Stores | Newry | BT34 1PH | 2024-08-23 | 22/8/2024:Your order has been delayed due to our suppliers being unable to complete the job in required time frame, order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 28/08/2024. _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 22/8/2024:Your order has been delayed due to our suppliers being unable to complete the job in required time frame, order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 28/08/2024. _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFP2431196 | 30022062 | 2.Commissioning | AM |  | 2024-08-21 | 2024-08-21 |  | 0 | [11 empty] | 0
1743 | 485590 |  | Batch 6 Aug 24 | Type 2 | FTTP | Casey's Filling Station | Crossmaglen | BT35 9AB |  | 0 | 0 | [7 empty] | Address query | Address query | 1.Provisioning | [17 empty] | 0
1744 | 633078 |  | Batch 6 Aug 24 | Type 2 | FTTP | Penley Stores | Wrexham | LL13 0LQ |  | 22/8/2024:Order Completed _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 22/8/2024:Order Completed _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2431191 | 30021976 | 2.Commissioning | AM |  | 2024-08-21 | 2024-08-21 |  | 0 | [11 empty] | 0
1745 | 485149 |  | Batch 6 Aug 24 | Type 2 | FTTP | Central Garage | Alford | AB33 8RE |  | 6/9/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_5/9/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_4/9/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_3/9/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_2/9/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_29/8/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_28/8/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_27/8/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_22/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_21/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_20/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_19/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_19/8/2024:01535331 _x000D_16/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_14/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_13/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_12/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_9/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_29/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_29/7/2024:01535331 _x000D_26/7/2024:26/07/2024 09:35 _x000D_ | 9/9/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_6/9/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_5/9/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_4/9/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_3/9/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_2/9/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_29/8/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_28/8/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_27/8/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_22/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_21/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_20/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_19/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_19/8/2024:01535331 _x000D_16/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_14/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_13/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_12/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_9/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_29/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_29/7/2024:01535331 _x000D_26/7/2024:26/07/2024 09:35 _x000D_ | 0 | #Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. | [5 empty] | VFP2431195 | 30022059 | 1.Provisioning | AM |  | 2024-08-21 |  |  | 0 | [11 empty] | 0
1746 | 665736 |  | Batch 6 Aug 24 | Type 2 | FTTP | Drewetts Stores | Badminton | GL9 1DG |  | 22/8/2024:Order Completed _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 22/8/2024:Order Completed _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2431194 | 30022105 | 2.Commissioning | AM |  | 2024-08-21 | 2024-08-21 |  | 0 | [11 empty] | 0
1747 | 664550 |  | Batch 6 Aug 24 | Type 2 | FTTP | Ryburgh Village Store | Fakenham | NR21 0TG |  | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 0 | 0 | [5 empty] | VFP2431190 | 30022124 | 1.Provisioning | AM |  | 2024-08-21 | 2024-09-06 |  | 0 | [11 empty] | 0
1748 | 663417 |  | Batch 6 Aug 24 | Type 2 | FTTP | Bradwell Service Station | Braintree | CM77 8EE |  | 6/9/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/9/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/9/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_3/9/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_2/9/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/8/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_28/8/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_27/8/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/8/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_21/8/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_20/8/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/8/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/8/2024:19/08/2024 05:25 _x000D_16/8/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/8/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_14/8/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_13/8/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/8/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_9/8/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_8/8/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/8/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/8/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_2/8/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_1/8/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:37830 _x000D_30/7/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:29/07/2024 09:45 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/9/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/9/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/9/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_3/9/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_2/9/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/8/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_28/8/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_27/8/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/8/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_21/8/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_20/8/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/8/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/8/2024:19/08/2024 05:25 _x000D_16/8/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/8/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_14/8/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_13/8/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/8/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_9/8/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_8/8/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/8/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/8/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_2/8/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_1/8/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:37830 _x000D_30/7/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:29/07/2024 09:45 _x000D_26/7/2024:0 _x000D_ | Order has been delayed please find the list of Notes CSL Note: Invalid appointment slot received CSL Note: Invalid data received | 0 | [5 empty] | VFP2431189 | 30022099 | 1.Provisioning | AM |  | 2024-08-21 |  |  | 0 | [11 empty] | 0
1749 | 665675 |  | Batch 6 Aug 24 | Type 2 | FTTP | Forbes Spar Brocagh | Dungannon | BT71 5DY |  | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 0 | 0 | [5 empty] | VFP2431188 | 30022149 | 1.Provisioning | AM |  | 2024-08-21 | 2024-09-06 |  | 0 | [11 empty] | 0
1750 | 665655 |  | Batch 6 Aug 24 | Type 2 | FTTP | Aughamullen Post Office | Dungannon | BT71 5DT |  | 22/8/2024:Order Completed _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 22/8/2024:Order Completed _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2431187 | 30022014 | 2.Commissioning | AM |  | 2024-08-21 | 2024-08-21 |  | 0 | [11 empty] | 0
1751 | 668333 |  | Batch 6 Aug 24 | Type 2 | FTTP | Murray's Nearby | Cullyhanna | BT35 0JG |  | 22/8/2024:Order Completed _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 22/8/2024:Order Completed _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2431186 | 30022010 | 2.Commissioning | AM |  | 2024-08-21 | 2024-08-21 |  | 0 | [11 empty] | 0
1752 | 668332 |  | Batch 6 Aug 24 | Type 2 | FTTP | The Dale Stores | Harrogate | HG3 2NF |  | 6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_22/8/2024:Supplier Missed Appointment _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM _x000D_22/8/2024:Supplier Missed Appointment _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | Update: Order Amended | #Update - Allwyn confirmed Retailer has agreed to installation on 02/09 AM | [5 empty] | VFP2431185 | 30022108 | 1.Provisioning | AM |  | 2024-08-21 | 2024-08-21 |  | 0 | [11 empty] | 0
1753 | 477886 |  | Batch 6 Aug 24 | Type 2 | FTTP | Woods Village Shop | Sidmouth | EX10 0LD |  | 22/8/2024:Order Completed _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 22/8/2024:Order Completed _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2431184 | 30022148 | 2.Commissioning | AM |  | 2024-08-21 | 2024-08-21 |  | 0 | [11 empty] | 0
1754 | 483772 |  | Batch 6 Aug 24 | Type 2 | FTTP | Vivo Essentials | Silverbridge | BT35 9LF |  | 22/8/2024:Order Completed _x000D_21/8/2024:Update: Order Completed by Supplier _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 22/8/2024:Order Completed _x000D_21/8/2024:Update: Order Completed by Supplier _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2431182 | 30021994 | 2.Commissioning | AM |  | 2024-08-21 | 2024-08-21 |  | 0 | [11 empty] | 0
1755 | 628281 |  | Batch 6 Aug 24 | Type 2 | FTTP | Porthtowan Village Stores | Truro | TR4 8AD |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 0 | 0 | [5 empty] | VFP2431183 | 30022027 | 1.Provisioning | AM |  | 2024-08-21 | 2024-08-21 |  | 0 | [11 empty] | 0
1756 | 669019 |  | Batch 6 Aug 24 | Type 2 | FTTP | Godreaman PO | Aberdare | CF44 6DD |  | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 0 | 0 | [5 empty] | VFP2431179 | 30022058 | 1.Provisioning | AM |  | 2024-09-06 | 2024-09-06 |  | 0 | [11 empty] | 0
1757 | 663122 |  | Batch 6 Aug 24 | Type 2 | FTTP | Yewtree Stores | Wirral | CH46 9PD |  | 22/8/2024:Order Completed _x000D_21/8/2024:Order Completed _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 22/8/2024:Order Completed _x000D_21/8/2024:Order Completed _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2431181 | 30021987 | 2.Commissioning | AM |  | 2024-08-21 | 2024-08-21 |  | 0 | [11 empty] | 0
1758 | 654789 |  | Batch 6 Aug 24 | Type 2 | FTTP | The Oak Tree Root Best One On Lleig | Manchester | M46 0PW |  | 22/8/2024:Order Completed _x000D_21/8/2024:Order Completed _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 22/8/2024:Order Completed _x000D_21/8/2024:Order Completed _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2431180 | 30022144 | 2.Commissioning | AM |  | 2024-08-21 | 2024-08-21 |  | 0 | [11 empty] | 0
1759 | 647159 |  | Batch 6 Aug 24 | Type 2 | FTTP | Kimmies | Alford | AB33 8QA |  | 22/8/2024:Order Completed _x000D_21/8/2024:Order Completed _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:No matching address found CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_1/8/2024:No matching address found CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:No matching address found CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:37443 _x000D_30/7/2024:No matching address found CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:No matching address found CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:26/07/2024 09:25 _x000D_26/7/2024:26/07/2024 09:25 _x000D_ | 22/8/2024:Order Completed _x000D_21/8/2024:Order Completed _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:No matching address found CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_1/8/2024:No matching address found CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:No matching address found CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:37443 _x000D_30/7/2024:No matching address found CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:No matching address found CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:26/07/2024 09:25 _x000D_26/7/2024:26/07/2024 09:25 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2431176 | 30022018 | 2.Commissioning | AM |  | 2024-08-21 | 2024-08-21 |  | 0 | [11 empty] | 0
1760 | 656105 |  | Batch 6 Aug 24 | Type 2 | FTTP | Holders Spar | Newtownbutler | BT92 8JW |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:Update: Order Amended _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 0 | 0 | [5 empty] | VFP2431177 | 30022056 | 1.Provisioning | AM |  | 2024-08-21 | 2024-08-21 |  | 0 | [11 empty] | 0
1761 | 664470 |  | Batch 6 Aug 24 | Type 2 | FTTP | Spar Augher | Augher | BT77 0BG |  | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Update: Order Amended _x000D_13/8/2024:Update: Order Amended _x000D_12/8/2024:Update: Order Amended _x000D_9/8/2024:Update: Order Amended _x000D_8/8/2024:Update: Order Amended _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 0 | 0 | [5 empty] | VFP2431178 | 30022071 | 1.Provisioning | AM |  | 2024-08-21 | 2024-09-06 |  | 0 | [11 empty] | 0
1762 | 670749 |  | Batch 6 Aug 24 | Type 2 | FTTP/Mobile | Valley Road Convenience Store | SHEFFIELD | S8 9GA |  | 6/9/2024:#Update Retailer confirmed 17/09, at 8AM. _x000D_5/9/2024:#Update Retailer confirmed 17/09, at 8AM. _x000D_4/9/2024:#Update Retailer confirmed 17/09, at 8AM. _x000D_3/9/2024:#Update Retailer confirmed 17/09, at 8AM. _x000D_2/9/2024:#Update Retailer confirmed 17/09, at 8AM. _x000D_29/8/2024:#Update Retailer confirmed 17/09, at 8AM. _x000D_28/8/2024:Your order has been delayed due to a customer missed appointment. Out of Hour appointment required. Please check with end user and reappoint the order if still required. _x000D_27/8/2024:Your order has been delayed due to a customer missed appointment. Out of Hour appointment required. Please check with end user and reappoint the order if still required. _x000D_22/8/2024:Our engineer has been unable to complete the task due to the end customer withdrawing access. _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:#Update Retailer confirmed 17/09, at 8AM. _x000D_6/9/2024:#Update Retailer confirmed 17/09, at 8AM. _x000D_5/9/2024:#Update Retailer confirmed 17/09, at 8AM. _x000D_4/9/2024:#Update Retailer confirmed 17/09, at 8AM. _x000D_3/9/2024:#Update Retailer confirmed 17/09, at 8AM. _x000D_2/9/2024:#Update Retailer confirmed 17/09, at 8AM. _x000D_29/8/2024:#Update Retailer confirmed 17/09, at 8AM. _x000D_28/8/2024:Your order has been delayed due to a customer missed appointment. Out of Hour appointment required. Please check with end user and reappoint the order if still required. _x000D_27/8/2024:Your order has been delayed due to a customer missed appointment. Out of Hour appointment required. Please check with end user and reappoint the order if still required. _x000D_22/8/2024:Our engineer has been unable to complete the task due to the end customer withdrawing access. _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 0 | #Update Retailer confirmed 17/09, at 8AM. | [5 empty] | VFP2431174 | 30022072 | 1.Provisioning |  |  | 2024-08-21 | 2024-08-21 |  | 0 | [11 empty] | 0
1763 | 652500 |  | Batch 6 Aug 24 | Type 2 | FTTP | Premier | Chester Le Street | DH2 3LJ |  | 22/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_21/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_20/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_19/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_19/8/2024:01541262 _x000D_16/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_14/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_13/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_12/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_9/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_8/8/2024:29/07/2024 _x000D_6/8/2024:29/07/2024 _x000D_5/8/2024:29/07/2024 _x000D_2/8/2024:29/07/2024 _x000D_1/8/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_30/7/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_29/7/2024:A network engineering task is required to provision this order. The order will now follow the KCI2 Assure process. KCI2 with a confirmed end customer appointment will be sent once the task has completed. CSL Note: Invalid appointment slot received CSL Not _x000D_29/7/2024:26/07/2024 09:31 _x000D_26/7/2024:26/07/2024 09:31 _x000D_ | 22/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_21/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_20/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_19/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_19/8/2024:01541262 _x000D_16/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_14/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_13/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_12/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_9/8/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_8/8/2024:29/07/2024 _x000D_6/8/2024:29/07/2024 _x000D_5/8/2024:29/07/2024 _x000D_2/8/2024:29/07/2024 _x000D_1/8/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_30/7/2024:#Update - Order has been delayed as step-1 work is required. CSL will update as more information become available. _x000D_29/7/2024:A network engineering task is required to provision this order. The order will now follow the KCI2 Assure process. KCI2 with a confirmed end customer appointment will be sent once the task has completed. CSL Note: Invalid appointment slot received CSL Not _x000D_29/7/2024:26/07/2024 09:31 _x000D_26/7/2024:26/07/2024 09:31 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFP2431172 | 30021998 | 2.Commissioning | AM |  | 2024-08-21 |  |  | 0 | [11 empty] | 0
1764 | 612781 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Premier Valley Stores | Pentre | CF41 7QY |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 0 | 0 | [5 empty] | No Product Available | 30021992 | 1.Provisioning | AM |  | 2024-08-21 |  |  | 0 | [11 empty] | 0
1765 | 109492 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Costcutter | ARMAGH | BT60 4JQ |  | 22/8/2024:Order Completed _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 22/8/2024:Order Completed _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFS1065624 | 30022113 | 2.Commissioning | AM |  | 2024-08-21 | 2024-08-21 |  | 0 | [11 empty] | 0
1766 | 628354 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Londis | Leven | KY9 1LP |  | 6/9/2024:#Update - External works have now been completed and the order has been committed for 24/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 24/09 is a suitable date. _x000D_5/9/2024:#Update - External works have now been completed and the order has been committed for 24/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 24/09 is a suitable date. _x000D_4/9/2024:#Update - External works have now been completed and the order has been committed for 24/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 24/09 is a suitable date. _x000D_3/9/2024:#Update - External works have now been completed and the order has been committed for 24/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 24/09 is a suitable date. _x000D_2/9/2024:#Update - External works have now been completed and the order has been committed for 24/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 24/09 is a suitable date. _x000D_29/8/2024:#Update - External works have now been completed and the order has been committed for 24/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 24/09 is a suitable date. _x000D_28/8/2024:#Update - Order has been delayed as a multiskilled engineer is required, assigned on 22/08 for NCF work. CSL will update as more information become available. _x000D_27/8/2024:#Update - Order has been delayed as a multiskilled engineer is required, assigned on 22/08 for NCF work. CSL will update as more information become available. _x000D_22/8/2024:Your order has been delayed. Multiskilled engineer assigned for 22/08/2024 for NCF work, Our Suppliers have given us a review date of 27/08/2024. We will continue to provide update as they become available. _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:#Update - External works have now been completed and the order has been committed for 24/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 24/09 is a suitable date. _x000D_6/9/2024:#Update - External works have now been completed and the order has been committed for 24/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 24/09 is a suitable date. _x000D_5/9/2024:#Update - External works have now been completed and the order has been committed for 24/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 24/09 is a suitable date. _x000D_4/9/2024:#Update - External works have now been completed and the order has been committed for 24/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 24/09 is a suitable date. _x000D_3/9/2024:#Update - External works have now been completed and the order has been committed for 24/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 24/09 is a suitable date. _x000D_2/9/2024:#Update - External works have now been completed and the order has been committed for 24/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 24/09 is a suitable date. _x000D_29/8/2024:#Update - External works have now been completed and the order has been committed for 24/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 24/09 is a suitable date. _x000D_28/8/2024:#Update - Order has been delayed as a multiskilled engineer is required, assigned on 22/08 for NCF work. CSL will update as more information become available. _x000D_27/8/2024:#Update - Order has been delayed as a multiskilled engineer is required, assigned on 22/08 for NCF work. CSL will update as more information become available. _x000D_22/8/2024:Your order has been delayed. Multiskilled engineer assigned for 22/08/2024 for NCF work, Our Suppliers have given us a review date of 27/08/2024. We will continue to provide update as they become available. _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 0 | #Update - External works have now been completed and the order has been committed for 24/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 24/09 is a suitable date. | [5 empty] | VFS1065623 | 30021969 | 1.Provisioning | AM |  | 2024-08-21 | 2024-08-21 |  | 0 | [11 empty] | 0
1767 | 672658 |  | Batch 6 Aug 24 | Type 2 | SoGEA/Mobile | Gillets | Kingsbridge | TQ7 2AP |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_28/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_27/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_22/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_28/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_27/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_22/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 0 | 0 | [5 empty] | VFS1065622 | 30021966 | 1.Provisioning |  |  | 2024-08-22 | 2024-08-22 |  | 0 | [11 empty] | 0
1768 | 666724 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Kinnerley Stores and Post Office | Oswestry | SY10 8DF |  | 22/8/2024:Order Completed _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 22/8/2024:Order Completed _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFS1065620 | 30022057 | 2.Commissioning | AM |  | 2024-08-22 | 2024-08-22 |  | 0 | [11 empty] | 0
1769 | 462705 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Premier Longside Shop | PETERHEAD | AB42 4XL |  | 22/8/2024:Order Completed _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 22/8/2024:Order Completed _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFS1065621 | 30022143 | 2.Commissioning | AM |  | 2024-08-22 | 2024-08-22 |  | 0 | [11 empty] | 0
1770 | 665939 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Banham Post Office and Village Stor | Norwich | NR16 2AA | 2024-08-23 | 22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065619 | 30022102 | 2.Commissioning | AM |  | 2024-08-22 | 2024-08-22 |  | 0 | [11 empty] | 0
1771 | 667307 |  | Batch 6 Aug 24 | Type 2 | FTTP | Chadwicks Newsagent | Holyhead | LL65 1BW |  | 6/9/2024:Supplier Delay: Provision of service will be delayed by a scheduled service outage _x000D_5/9/2024:Supplier Delay: Provision of service will be delayed by a scheduled service outage _x000D_4/9/2024:Supplier Delay: Provision of service will be delayed by a scheduled service outage _x000D_3/9/2024:Your order has been delayed.Scaffolding work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 05/09/2024. We will continue to provide update as they become available. _x000D_2/9/2024:Your order has been delayed.Scaffolding work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 05/09/2024. We will continue to provide update as they become available. _x000D_29/8/2024:Your order has been delayed. The appointment has been delayed due to Scaffoldings work, multiskilled engineer required and our Suppliers have given us a review date of 02/09/2024. We will continue to provide update as they become available _x000D_28/8/2024:Your order has been delayed. The appointment has been delayed due to Scaffoldings work, multiskilled engineer required and our Suppliers have given us a review date of 02/09/2024. We will continue to provide update as they become available _x000D_27/8/2024:Your order has been delayed. The appointment has been delayed due to Scaffoldings work, multiskilled engineer required and our Suppliers have given us a review date of 02/09/2024. We will continue to provide update as they become available _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:Supplier Delay: Provision of service will be delayed by a scheduled service outage _x000D_6/9/2024:Supplier Delay: Provision of service will be delayed by a scheduled service outage _x000D_5/9/2024:Supplier Delay: Provision of service will be delayed by a scheduled service outage _x000D_4/9/2024:Supplier Delay: Provision of service will be delayed by a scheduled service outage _x000D_3/9/2024:Your order has been delayed.Scaffolding work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 05/09/2024. We will continue to provide update as they become available. _x000D_2/9/2024:Your order has been delayed.Scaffolding work required which is awaiting permission from a third party. Our Suppliers have given us a review date of 05/09/2024. We will continue to provide update as they become available. _x000D_29/8/2024:Your order has been delayed. The appointment has been delayed due to Scaffoldings work, multiskilled engineer required and our Suppliers have given us a review date of 02/09/2024. We will continue to provide update as they become available _x000D_28/8/2024:Your order has been delayed. The appointment has been delayed due to Scaffoldings work, multiskilled engineer required and our Suppliers have given us a review date of 02/09/2024. We will continue to provide update as they become available _x000D_27/8/2024:Your order has been delayed. The appointment has been delayed due to Scaffoldings work, multiskilled engineer required and our Suppliers have given us a review date of 02/09/2024. We will continue to provide update as they become available _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | Supplier Delay: Provision of service will be delayed by a scheduled service outage | 0 | [5 empty] | VFP2431170 | 30021974 | 1.Provisioning | AM |  | 2024-08-22 | 2024-08-22 |  | 0 | [11 empty] | 0
1772 | 655345 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Greens Of Kinross | Kinross | KY13 8AN | 2024-08-23 | 22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065618 | 30022112 | 2.Commissioning | AM |  | 2024-08-22 | 2024-08-22 |  | 0 | [11 empty] | 0
1773 | 633753 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Premier Maryburgh Stores | Dingwall | IV7 8DU | 2024-08-23 | 22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065615 | 30021973 | 2.Commissioning | AM |  | 2024-08-22 | 2024-08-22 |  | 0 | [11 empty] | 0
1774 | 455426 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Willies Newsagent | Burntisland | KY3 0SW |  | 22/8/2024:Update: Order Completed by Supplier _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 22/8/2024:Update: Order Completed by Supplier _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFS1065616 | 30022054 | 2.Commissioning | AM |  | 2024-08-22 | 2024-08-22 |  | 0 | [11 empty] | 0
1775 | 667415 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Swanton Morley Stores | Dereham | NR20 4PP |  | 6/9/2024:#Update - Action for Allwyn - Installation has now been amended to 16/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 16/09 is a suitable date. _x000D_5/9/2024:#Update - Action for Allwyn - Installation has now been amended to 16/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 16/09 is a suitable date. _x000D_4/9/2024:#Update - Action for Allwyn - Installation has now been amended to 16/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 16/09 is a suitable date. _x000D_3/9/2024:#Update - Action for Allwyn - Installation has now been amended to 16/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 16/09 is a suitable date. _x000D_2/9/2024:#Update - Action for Allwyn - Installation has now been amended to 16/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 16/09 is a suitable date. _x000D_29/8/2024:#Update - Action for Allwyn - Installation has now been amended to 16/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 16/09 is a suitable date. _x000D_28/8/2024:#Update - Action for Allwyn - Installation has now been amended to 16/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 16/09 is a suitable date. _x000D_27/8/2024:#Update - Action for Allwyn - Installation has now been amended to 16/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 16/09 is a suitable date. _x000D_22/8/2024:End User Missed appointment. Action required _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:#Update - Action for Allwyn - Installation has now been amended to 16/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 16/09 is a suitable date. _x000D_6/9/2024:#Update - Action for Allwyn - Installation has now been amended to 16/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 16/09 is a suitable date. _x000D_5/9/2024:#Update - Action for Allwyn - Installation has now been amended to 16/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 16/09 is a suitable date. _x000D_4/9/2024:#Update - Action for Allwyn - Installation has now been amended to 16/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 16/09 is a suitable date. _x000D_3/9/2024:#Update - Action for Allwyn - Installation has now been amended to 16/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 16/09 is a suitable date. _x000D_2/9/2024:#Update - Action for Allwyn - Installation has now been amended to 16/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 16/09 is a suitable date. _x000D_29/8/2024:#Update - Action for Allwyn - Installation has now been amended to 16/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 16/09 is a suitable date. _x000D_28/8/2024:#Update - Action for Allwyn - Installation has now been amended to 16/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 16/09 is a suitable date. _x000D_27/8/2024:#Update - Action for Allwyn - Installation has now been amended to 16/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 16/09 is a suitable date. _x000D_22/8/2024:End User Missed appointment. Action required _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 0 | #Update - Action for Allwyn - Installation has now been amended to 16/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 16/09 is a suitable date. | [5 empty] | VFS1065613 | 30022140 | 1.Provisioning | AM |  | 2024-08-22 | 2024-08-22 |  | 0 | [11 empty] | 0
1776 | 446867 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Three Ways Premier | Kings Lynn | PE32 2DR | 2024-08-23 | 22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065614 | 30021985 | 2.Commissioning | AM |  | 2024-08-22 | 2024-08-22 |  | 0 | [11 empty] | 0
1777 | 630255 |  | Batch 6 Aug 24 | Type 2 | SoGEA | A A Stores | Cowie | FK7 7AL | 2024-08-23 | 22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065608 | 30022066 | 2.Commissioning | AM |  | 2024-08-22 | 2024-08-22 |  | 0 | [11 empty] | 0
1778 | 662837 |  | Batch 6 Aug 24 | Type 2 | SoGEA | High Ercall Stores | Telford | TF6 6AG |  | 6/9/2024:#Update Retailer confirmed 18/09, AM. _x000D_5/9/2024:#Update Retailer confirmed 18/09, AM. _x000D_4/9/2024:#Update Retailer confirmed 18/09, AM. _x000D_3/9/2024:#Update Retailer confirmed 18/09, AM. _x000D_2/9/2024:#Update Retailer confirmed 18/09, AM. _x000D_29/8/2024:#Update Retailer confirmed 18/09, AM. _x000D_28/8/2024:#Update Customer unaware of appointment and didn't want install to go ahead. Action on Allwyn - advise if the retailer would like it reappointed. _x000D_27/8/2024:#Update Customer unaware of appointment and didn't want install to go ahead. Action on Allwyn - advise if the retailer would like it reappointed. _x000D_22/8/2024:#Update Network Planning issues. Please await for further updates _x000D_21/8/2024:#Update Network Planning issues. Please await for further updates _x000D_20/8/2024:#Update Network Planning issues. Please await for further updates _x000D_19/8/2024:#Update Network Planning issues. Please await for further updates _x000D_19/8/2024:01534409 _x000D_16/8/2024:#Update Network Planning issues. Please await for further updates _x000D_15/8/2024:#Update Network Planning issues. Please await for further updates _x000D_14/8/2024:#Update Network Planning issues. Please await for further updates _x000D_13/8/2024:#Update Network Planning issues. Please await for further updates _x000D_12/8/2024:#Update Network Planning issues. Please await for further updates _x000D_9/8/2024:#Update Network Planning issues. Please await for further updates _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update Network Planning issues. Please await for further updates _x000D_29/7/2024:#Update Network Planning issues. Please await for further updates _x000D_29/7/2024:01534409 _x000D_26/7/2024:25/07/2024 22:28 _x000D_ | 9/9/2024:#Update Retailer confirmed 18/09, AM. _x000D_6/9/2024:#Update Retailer confirmed 18/09, AM. _x000D_5/9/2024:#Update Retailer confirmed 18/09, AM. _x000D_4/9/2024:#Update Retailer confirmed 18/09, AM. _x000D_3/9/2024:#Update Retailer confirmed 18/09, AM. _x000D_2/9/2024:#Update Retailer confirmed 18/09, AM. _x000D_29/8/2024:#Update Retailer confirmed 18/09, AM. _x000D_28/8/2024:#Update Customer unaware of appointment and didn't want install to go ahead. Action on Allwyn - advise if the retailer would like it reappointed. _x000D_27/8/2024:#Update Customer unaware of appointment and didn't want install to go ahead. Action on Allwyn - advise if the retailer would like it reappointed. _x000D_22/8/2024:#Update Network Planning issues. Please await for further updates _x000D_21/8/2024:#Update Network Planning issues. Please await for further updates _x000D_20/8/2024:#Update Network Planning issues. Please await for further updates _x000D_19/8/2024:#Update Network Planning issues. Please await for further updates _x000D_19/8/2024:01534409 _x000D_16/8/2024:#Update Network Planning issues. Please await for further updates _x000D_15/8/2024:#Update Network Planning issues. Please await for further updates _x000D_14/8/2024:#Update Network Planning issues. Please await for further updates _x000D_13/8/2024:#Update Network Planning issues. Please await for further updates _x000D_12/8/2024:#Update Network Planning issues. Please await for further updates _x000D_9/8/2024:#Update Network Planning issues. Please await for further updates _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update Network Planning issues. Please await for further updates _x000D_29/7/2024:#Update Network Planning issues. Please await for further updates _x000D_29/7/2024:01534409 _x000D_26/7/2024:25/07/2024 22:28 _x000D_ | 0 | #Update Retailer confirmed 18/09, AM. | [5 empty] | VFS1065612 | 30022096 | 1.Provisioning | AM |  | 2024-08-22 | 2024-08-22 |  | 0 | [11 empty] | 0
1779 | 431350 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Palmbush Spar | ENNISKILLEN | BT93 1QX | 2024-08-23 | 22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065610 | 30022037 | 2.Commissioning | AM |  | 2024-08-22 | 2024-08-22 |  | 0 | [11 empty] | 0
1780 | 464647 |  | Batch 6 Aug 24 | Type 2 | SOGEA | Glentham Village Stores | Glentham | LN8 2EQ |  | 0 | 0 | [7 empty] | Address query | Address query | 1.Provisioning | [17 empty] | 0
1781 | 469310 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Premier Three Trees | OSWESTRY | SY11 4DA |  | 6/9/2024:#Update - Advanced upgrade and OOH appointment required, proposal sent to VF 28/08 _x000D_5/9/2024:#Update - Advanced upgrade and OOH appointment required, proposal sent to VF 28/08 _x000D_4/9/2024:#Update - Advanced upgrade and OOH appointment required, proposal sent to VF 28/08 _x000D_3/9/2024:#Update - Advanced upgrade and OOH appointment required, proposal sent to VF 28/08 _x000D_2/9/2024:#Update - Advanced upgrade and OOH appointment required, proposal sent to VF 28/08 _x000D_29/8/2024:#Update - Advanced upgrade and OOH appointment required, proposal sent to VF 28/08 _x000D_28/8/2024:#Update - installation requires OOH and upgrade to advanced for 50+m of cabling. _x000D_27/8/2024:#Update - installation unsuccessful, OOH appointment required, CSL will raise the charge and share proposal to VF accordingly _x000D_22/8/2024:#Update - installation unsuccessful, OOH appointment required, CSL will raise the charge and share proposal to VF accordingly _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:#Update - Advanced upgrade and OOH appointment required, proposal sent to VF 28/08 _x000D_6/9/2024:#Update - Advanced upgrade and OOH appointment required, proposal sent to VF 28/08 _x000D_5/9/2024:#Update - Advanced upgrade and OOH appointment required, proposal sent to VF 28/08 _x000D_4/9/2024:#Update - Advanced upgrade and OOH appointment required, proposal sent to VF 28/08 _x000D_3/9/2024:#Update - Advanced upgrade and OOH appointment required, proposal sent to VF 28/08 _x000D_2/9/2024:#Update - Advanced upgrade and OOH appointment required, proposal sent to VF 28/08 _x000D_29/8/2024:#Update - Advanced upgrade and OOH appointment required, proposal sent to VF 28/08 _x000D_28/8/2024:#Update - installation requires OOH and upgrade to advanced for 50+m of cabling. _x000D_27/8/2024:#Update - installation unsuccessful, OOH appointment required, CSL will raise the charge and share proposal to VF accordingly _x000D_22/8/2024:#Update - installation unsuccessful, OOH appointment required, CSL will raise the charge and share proposal to VF accordingly _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 0 | #Update - Advanced upgrade and OOH appointment required, proposal sent to VF 28/08 | [5 empty] | VFS1065609 | 30022051 | 1.Provisioning | AM |  | 2024-08-22 | 2024-08-22 |  | 0 | [11 empty] | 0
1782 | 666699 |  | Batch 6 Aug 24 | Type 2 | SoGEA | P & I Stores | Radstock | BA3 5JJ |  | 22/8/2024:Update: Order Completed by Supplier _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 22/8/2024:Update: Order Completed by Supplier _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFS1065606 | 30022122 | 2.Commissioning | AM |  | 2024-08-22 | 2024-08-22 |  | 0 | [11 empty] | 0
1783 | 661192 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Stanpit Wines | Christchurch | BH23 3LZ |  | 6/9/2024:#Update - NFA - Allwyn confirmed new installation date 09/09 with retailer _x000D_5/9/2024:#Update - NFA - Allwyn confirmed new installation date 09/09 with retailer _x000D_4/9/2024:#Update - NFA - Allwyn confirmed new installation date 09/09 with retailer _x000D_3/9/2024:#Update - NFA - Allwyn confirmed new installation date 09/09 with retailer _x000D_2/9/2024:#Update - NFA - Allwyn confirmed new installation date 09/09 with retailer _x000D_29/8/2024:#Update - NFA - Allwyn confirmed new installation date 09/09 with retailer _x000D_28/8/2024:#Update - NFA - Allwyn confirmed new installation date 09/09 with retailer _x000D_27/8/2024:#Update - NFA - Allwyn confirmed new installation date 09/09 with retailer _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_2/8/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_1/8/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_31/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_31/7/2024:37745 _x000D_30/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:#Update - NFA - Allwyn confirmed new installation date 09/09 with retailer _x000D_6/9/2024:#Update - NFA - Allwyn confirmed new installation date 09/09 with retailer _x000D_5/9/2024:#Update - NFA - Allwyn confirmed new installation date 09/09 with retailer _x000D_4/9/2024:#Update - NFA - Allwyn confirmed new installation date 09/09 with retailer _x000D_3/9/2024:#Update - NFA - Allwyn confirmed new installation date 09/09 with retailer _x000D_2/9/2024:#Update - NFA - Allwyn confirmed new installation date 09/09 with retailer _x000D_29/8/2024:#Update - NFA - Allwyn confirmed new installation date 09/09 with retailer _x000D_28/8/2024:#Update - NFA - Allwyn confirmed new installation date 09/09 with retailer _x000D_27/8/2024:#Update - NFA - Allwyn confirmed new installation date 09/09 with retailer _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_2/8/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_1/8/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_31/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_31/7/2024:37745 _x000D_30/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 0 | #Update - NFA - Allwyn confirmed new installation date 09/09 with retailer | [5 empty] | VFS1065607 | 30022153 | 1.Provisioning | AM |  | 2024-08-22 | 2024-08-22 |  | 0 | [11 empty] | 0
1784 | 666698 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Sticker Post Office | ST. AUSTELL | PL26 7HD |  | 22/8/2024:Update: Order Completed by Supplier _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_19/8/2024:12/08/2024 12:19 _x000D_16/8/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_15/8/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_14/8/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_13/8/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_12/8/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:37291 _x000D_30/7/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:25/07/2024 20:24 _x000D_26/7/2024:25/07/2024 20:24 _x000D_ | 22/8/2024:Update: Order Completed by Supplier _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_19/8/2024:12/08/2024 12:19 _x000D_16/8/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_15/8/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_14/8/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_13/8/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_12/8/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:37291 _x000D_30/7/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:25/07/2024 20:24 _x000D_26/7/2024:25/07/2024 20:24 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFS1065605 | 30021958 | 2.Commissioning | AM |  | 2024-08-22 | 2024-08-22 |  | 0 | [11 empty] | 0
1785 | 665835 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Otley Village Store & Post Office | IPSWICH | IP6 9NT | 2024-08-23 | 22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065604 | 30022095 | 2.Commissioning | AM |  | 2024-08-22 | 2024-08-22 |  | 0 | [11 empty] | 0
1786 | 666792 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Badwell Ash Post Office And Store | BURY ST. EDMUNDS | IP31 3DG |  | 6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 10/09 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 10/09 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 10/09 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 10/09 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 10/09 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 10/09 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 10/09 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 10/09 AM _x000D_22/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_21/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_20/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_19/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_19/8/2024:01535473 _x000D_16/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_14/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_13/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_12/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_9/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_29/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_29/7/2024:01535473 _x000D_26/7/2024:25/07/2024 20:27 _x000D_ | 9/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 10/09 AM _x000D_6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 10/09 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 10/09 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 10/09 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 10/09 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 10/09 AM _x000D_29/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 10/09 AM _x000D_28/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 10/09 AM _x000D_27/8/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 10/09 AM _x000D_22/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_21/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_20/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_19/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_19/8/2024:01535473 _x000D_16/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_14/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_13/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_12/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_9/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_29/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_29/7/2024:01535473 _x000D_26/7/2024:25/07/2024 20:27 _x000D_ | 0 | #Update - Allwyn confirmed Retailer has agreed to installation on 10/09 AM | [5 empty] | VFS1065602 | 30021959 | 1.Provisioning | AM |  | 2024-08-22 | 2024-08-22 |  | 0 | [11 empty] | 0
1787 | 657606 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Nisa Local | Turriff | AB53 5YJ |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 0 | 0 | [5 empty] | No Product Available | 30021996 | 1.Provisioning | AM |  | 2024-08-22 |  |  | 0 | [11 empty] | 0
1788 | 659155 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Nisa | Borth | SY24 5LJ | 2024-08-23 | 22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065603 | 30022039 | 2.Commissioning | AM |  | 2024-08-22 | 2024-08-22 |  | 0 | [11 empty] | 0
1789 | 446481 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Keystore | ACHARACLE | PH36 4HZ | 2024-08-23 | 22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065599 | 30021999 | 2.Commissioning | AM |  | 2024-08-22 | 2024-08-22 |  | 0 | [11 empty] | 0
1790 | 663659 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Tidings Newsagents | Norwich | NR12 8AA | 2024-08-23 | 22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065600 | 30022139 | 2.Commissioning | AM |  | 2024-08-22 | 2024-08-22 |  | 0 | [11 empty] | 0
1791 | 668799 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Nisa King Street | STIRLING | FK7 7JX | 2024-08-23 | 28/8/2024:#Update - engineer attending 28/08 - AM _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 28/8/2024:#Update - engineer attending 28/08 - AM _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065598 | 30022078 | 2.Commissioning | AM |  | 2024-08-22 | 2024-08-22 |  | 0 | [11 empty] | 0
1792 | 462544 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Costcutter | PURLEY | CR8 4AQ | 2024-08-23 | 22/8/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 20/08/2024 _x000D_21/8/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 20/08/2024 _x000D_20/8/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 20/08/2024 _x000D_19/8/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 20/08/2024 _x000D_19/8/2024:01556163 _x000D_16/8/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 20/08/2024 _x000D_15/8/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 20/08/2024 _x000D_14/8/2024:#Update - Pair divert work required & LinePlant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 15/08/2024 _x000D_13/8/2024:Your order has been delayed. LinePlant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 15/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointmen _x000D_12/8/2024:Your order has been delayed. LinePlant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 15/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointmen _x000D_9/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 08/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_8/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 08/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 08/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 08/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 22/8/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 20/08/2024 _x000D_21/8/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 20/08/2024 _x000D_20/8/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 20/08/2024 _x000D_19/8/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 20/08/2024 _x000D_19/8/2024:01556163 _x000D_16/8/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 20/08/2024 _x000D_15/8/2024:#Update - Pair divert work required. Our Suppliers have given us a review date of 20/08/2024 _x000D_14/8/2024:#Update - Pair divert work required & LinePlant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 15/08/2024 _x000D_13/8/2024:Your order has been delayed. LinePlant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 15/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointmen _x000D_12/8/2024:Your order has been delayed. LinePlant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 15/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointmen _x000D_9/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 08/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_8/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 08/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 08/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 08/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065596 | 30022158 | 2.Commissioning | AM |  | 2024-08-22 |  |  | 0 | [11 empty] | 0
1793 | 233432 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Off Licence | NORWICH | NR11 8AH |  | 22/8/2024:Order Completed _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 22/8/2024:Order Completed _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [6 empty] | 3.Allwyn to arrange rtr install | VFS1065597 | 30022042 | 2.Commissioning | AM |  | 2024-08-22 | 2024-08-22 |  | 0 | [11 empty] | 0
1794 | 231790 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Nisa | NEWRY | BT35 9RL | 2024-08-23 | 22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065595 | 30022060 | 2.Commissioning | AM |  | 2024-08-22 | 2024-08-22 |  | 0 | [11 empty] | 0
1795 | 429331 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Spar Roberts Bow Street | Aberystwyth | SY24 5AX |  | 6/9/2024:Port available but TRFS/CRFS dates is Unknown CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:Port available but TRFS/CRFS dates is Unknown CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:Port available but TRFS/CRFS dates is Unknown CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:37284 _x000D_30/7/2024:Port available but TRFS/CRFS dates is Unknown CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:Port available but TRFS/CRFS dates is Unknown CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:25/07/2024 20:21 _x000D_26/7/2024:25/07/2024 20:21 _x000D_ | 9/9/2024:Port available but TRFS/CRFS dates is Unknown CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/9/2024:Port available but TRFS/CRFS dates is Unknown CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:Port available but TRFS/CRFS dates is Unknown CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:Port available but TRFS/CRFS dates is Unknown CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:37284 _x000D_30/7/2024:Port available but TRFS/CRFS dates is Unknown CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:Port available but TRFS/CRFS dates is Unknown CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:25/07/2024 20:21 _x000D_26/7/2024:25/07/2024 20:21 _x000D_ | Port available but TRFS/CRFS dates is Unknown CSL Note: Invalid appointment slot received CSL Note: Invalid data received | 0 | [5 empty] | VFS1065594 | 30022019 | 1.Provisioning | AM |  | 2024-08-23 |  |  | 0 | [11 empty] | 0
1796 | 231294 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Pybus Newsagents | Boroughbridge | YO51 9AW |  | 27/8/2024:Order Completed _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 27/8/2024:Order Completed _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065593 | 30022152 | 2.Commissioning | AM |  | 2024-08-23 | 2024-08-23 |  | 0 | [11 empty] | 0
1797 | 670514 |  | Batch 6 Aug 24 | Type 2 | SoGEA | The Village Stores And Post Office | Stamford | PE9 4HJ | 2024-09-03 | 6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:Order Completed _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:Order Completed _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | Order Completed | 0 | [5 empty] | VFP2450222 | 30022068 | 2.Commissioning | AM |  | 2024-09-02 | 2024-09-02 |  | 0 | [11 empty] | 0
1798 | 668223 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Burniston News & PO | SCARBOROUGH | YO13 0HH |  | 27/8/2024:Order Completed _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 27/8/2024:Order Completed _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065592 | 30022097 | 2.Commissioning | AM |  | 2024-08-23 | 2024-08-23 |  | 0 | [11 empty] | 0
1799 | 660036 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Landis Far Forest Stores | Kidderminster | DY14 9TF |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:Update: Order Amended _x000D_28/8/2024:Update: Order Amended _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:Update: Order Amended _x000D_28/8/2024:Update: Order Amended _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 0 | 0 | [5 empty] | VFS1065591 | 30021993 | 1.Provisioning | AM |  | 2024-08-23 | 2024-08-23 |  | 0 | [11 empty] | 0
1800 | 417253 |  | Batch 6 Aug 24 | Type 2 | SoGEA | SPAR REEPHAM | NORWICH | NR10 4EJ |  | 27/8/2024:Order Completed _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 27/8/2024:Order Completed _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065589 | 30022025 | 2.Commissioning | AM |  | 2024-08-23 | 2024-08-23 |  | 0 | [11 empty] | 0
1801 | 667748 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Cobble Corner | Marazion | TR17 0AR |  | 27/8/2024:#Update - Order was delayed due to a sales query however this has now been resolved _x000D_22/8/2024:#Update - Order was delayed due to a sales query however this has now been resolved _x000D_21/8/2024:#Update - Order was delayed due to a sales query however this has now been resolved _x000D_20/8/2024:#Update - Order was delayed due to a sales query however this has now been resolved _x000D_19/8/2024:#Update - Order was delayed due to a sales query however this has now been resolved _x000D_19/8/2024:01536622 _x000D_16/8/2024:#Update - Order was delayed due to a sales query however this has now been resolved _x000D_15/8/2024:#Update - Order was delayed due to a sales query however this has now been resolved _x000D_14/8/2024:#Update - Order was delayed due to a sales query however this has now been resolved _x000D_13/8/2024:#Update - Order was delayed due to a sales query however this has now been resolved _x000D_12/8/2024:#Update - Order was delayed due to a sales query however this has now been resolved _x000D_9/8/2024:#Update - Order was delayed due to a sales query however this has now been resolved _x000D_8/8/2024:29/07/2024 _x000D_6/8/2024:29/07/2024 _x000D_5/8/2024:29/07/2024 _x000D_2/8/2024:29/07/2024 _x000D_1/8/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_30/7/2024:#Update - Order was delayed due to a sales query however this has now been resolved _x000D_29/7/2024:#Update - Order was delayed due to a sales query however this has now been resolved _x000D_29/7/2024:01536622 _x000D_26/7/2024:25/07/2024 20:18 _x000D_ | 27/8/2024:#Update - Order was delayed due to a sales query however this has now been resolved _x000D_22/8/2024:#Update - Order was delayed due to a sales query however this has now been resolved _x000D_21/8/2024:#Update - Order was delayed due to a sales query however this has now been resolved _x000D_20/8/2024:#Update - Order was delayed due to a sales query however this has now been resolved _x000D_19/8/2024:#Update - Order was delayed due to a sales query however this has now been resolved _x000D_19/8/2024:01536622 _x000D_16/8/2024:#Update - Order was delayed due to a sales query however this has now been resolved _x000D_15/8/2024:#Update - Order was delayed due to a sales query however this has now been resolved _x000D_14/8/2024:#Update - Order was delayed due to a sales query however this has now been resolved _x000D_13/8/2024:#Update - Order was delayed due to a sales query however this has now been resolved _x000D_12/8/2024:#Update - Order was delayed due to a sales query however this has now been resolved _x000D_9/8/2024:#Update - Order was delayed due to a sales query however this has now been resolved _x000D_8/8/2024:29/07/2024 _x000D_6/8/2024:29/07/2024 _x000D_5/8/2024:29/07/2024 _x000D_2/8/2024:29/07/2024 _x000D_1/8/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_30/7/2024:#Update - Order was delayed due to a sales query however this has now been resolved _x000D_29/7/2024:#Update - Order was delayed due to a sales query however this has now been resolved _x000D_29/7/2024:01536622 _x000D_26/7/2024:25/07/2024 20:18 _x000D_ | [7 empty] | VFS1065588 | 30022165 | 2.Commissioning | AM |  | 2024-08-23 | 2024-08-23 |  | 0 | [11 empty] | 0
1802 | 660194 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Oggs Convenience Stores | Moray | AB38 7AU |  | 27/8/2024:Order Completed _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 27/8/2024:Order Completed _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065587 | 30022038 | 2.Commissioning | AM |  | 2024-08-23 | 2024-08-23 |  | 0 | [11 empty] | 0
1803 | 665020 |  | Batch 6 Aug 24 | Type 2 | SOGEA | Cross Stores | STROUD | GL6 7DP |  | 0 | 0 | [7 empty] | Duplicate Order | Duplicate Order | 1.Provisioning | [17 empty] | 0
1804 | 652321 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Peoples Market | Waterlooville | PO7 4RW |  | 6/9/2024:#Update 3 hour appointment for 2 engineers and upgrade to advanced required _x000D_5/9/2024:#Update 3 hour appointment for 2 engineers and upgrade to advanced required _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_2/9/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_29/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_28/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_27/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:#Update 3 hour appointment for 2 engineers and upgrade to advanced required _x000D_6/9/2024:#Update 3 hour appointment for 2 engineers and upgrade to advanced required _x000D_5/9/2024:#Update 3 hour appointment for 2 engineers and upgrade to advanced required _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_2/9/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_29/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_28/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_27/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | Update: Order Amended | #Update 3 hour appointment for 2 engineers and upgrade to advanced required | [5 empty] | VFS1065586 | 30022031 | 1.Provisioning | AM |  | 2024-08-23 | 2024-08-23 |  | 0 | [11 empty] | 0
1805 | 665016 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Falkland Convenience Store Ltd | Cupar | KY15 7BZ |  | 27/8/2024:Order Completed _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 27/8/2024:Order Completed _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065584 | 30021991 | 2.Commissioning | AM |  | 2024-08-23 | 2024-08-23 |  | 0 | [11 empty] | 0
1806 | 665476 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Slaidburn Central Stores | Clitheroe | BB7 3ER |  | 6/9/2024:#Update - Retailer confirmed new appointment for 16/09 _x000D_5/9/2024:#Update - Retailer confirmed new appointment for 16/09 _x000D_4/9/2024:#Update - Retailer confirmed new appointment for 16/09 _x000D_3/9/2024:#Update - Retailer confirmed new appointment for 16/09 _x000D_2/9/2024:#Update - Retailer confirmed new appointment for 16/09 _x000D_29/8/2024:#Update - Retailer confirmed new appointment for 16/09 _x000D_28/8/2024:#Update - Retailer confirmed new appointment for 16/09 _x000D_27/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:#Update - Retailer confirmed new appointment for 16/09 _x000D_6/9/2024:#Update - Retailer confirmed new appointment for 16/09 _x000D_5/9/2024:#Update - Retailer confirmed new appointment for 16/09 _x000D_4/9/2024:#Update - Retailer confirmed new appointment for 16/09 _x000D_3/9/2024:#Update - Retailer confirmed new appointment for 16/09 _x000D_2/9/2024:#Update - Retailer confirmed new appointment for 16/09 _x000D_29/8/2024:#Update - Retailer confirmed new appointment for 16/09 _x000D_28/8/2024:#Update - Retailer confirmed new appointment for 16/09 _x000D_27/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 0 | #Update - Retailer confirmed new appointment for 16/09 | [5 empty] | VFS1065585 | 30022107 | 1.Provisioning | AM |  | 2024-08-23 | 2024-08-23 |  | 0 | [11 empty] | 0
1807 | 665005 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Fourway Stores | Chippenham | SN15 5EL |  | 27/8/2024:Order Completed _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 27/8/2024:Order Completed _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065582 | 30021970 | 2.Commissioning | AM |  | 2024-08-23 | 2024-08-23 |  | 0 | [11 empty] | 0
1808 | 666667 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Tycroes PO | AMMANFORD | SA18 3QJ |  | 27/8/2024:Order Completed _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 02/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_2/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 02/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_1/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 02/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 02/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:37741 _x000D_30/7/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 02/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 27/8/2024:Order Completed _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 02/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_2/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 02/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_1/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 02/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 02/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:37741 _x000D_30/7/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 02/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065583 | 30022064 | 2.Commissioning | AM |  | 2024-08-23 | 2024-08-23 |  | 0 | [11 empty] | 0
1809 | 668081 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Bishop Sutton PO & Stores | BRISTOL | BS39 5UU |  | 27/8/2024:Order Completed _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 27/8/2024:Order Completed _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065581 | 30022065 | 2.Commissioning | AM |  | 2024-08-23 | 2024-08-23 |  | 0 | [11 empty] | 0
1810 | 487385 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Tremough Premier Stores | Cornwall | TR10 8RF |  | 27/8/2024:Order Completed _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 27/8/2024:Order Completed _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065580 | 30022166 | 2.Commissioning | AM |  | 2024-08-23 | 2024-08-23 |  | 0 | [11 empty] | 0
1811 | 207680 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Hawtree and Sons Riverside | Gillingham | SP8 5RJ |  | 27/8/2024:Order Completed _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 27/8/2024:Order Completed _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065578 | 30021980 | 2.Commissioning | AM |  | 2024-08-23 | 2024-08-23 |  | 0 | [11 empty] | 0
1812 | 626199 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Millbrook News | Millbrook | PL10 1AA |  | 6/9/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_5/9/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_4/9/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_3/9/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_2/9/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_29/8/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_28/8/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_27/8/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_22/8/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_21/8/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_20/8/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_19/8/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_19/8/2024:01541250 _x000D_16/8/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_14/8/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_13/8/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_12/8/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_9/8/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_8/8/2024:02/08/2024 _x000D_6/8/2024:02/08/2024 _x000D_5/8/2024:02/08/2024 _x000D_2/8/2024:02/08/2024 _x000D_1/8/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_30/7/2024:#Update - Order was delayed due to a sales query however this has now been resolved. CSL will update with a install date as it becomes available. _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_6/9/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_5/9/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_4/9/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_3/9/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_2/9/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_29/8/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_28/8/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_27/8/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_22/8/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_21/8/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_20/8/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_19/8/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_19/8/2024:01541250 _x000D_16/8/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_14/8/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_13/8/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_12/8/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_9/8/2024:#Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. _x000D_8/8/2024:02/08/2024 _x000D_6/8/2024:02/08/2024 _x000D_5/8/2024:02/08/2024 _x000D_2/8/2024:02/08/2024 _x000D_1/8/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_31/7/2024:29/07/2024 _x000D_30/7/2024:#Update - Order was delayed due to a sales query however this has now been resolved. CSL will update with a install date as it becomes available. _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 0 | #Update - Order has been delayed due to network records that need updating. CSL will update as more information become available. | [5 empty] | VFS1065579 | 30022090 | 1.Provisioning | AM |  | 2024-08-23 |  |  | 0 | [11 empty] | 0
1813 | 468887 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Enas Newsagents | Anglesey | LL58 8AP |  | 27/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_22/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_21/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_20/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_19/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_19/8/2024:01534496 _x000D_16/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_14/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_13/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_12/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_9/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_29/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_29/7/2024:01534496 _x000D_26/7/2024:26/07/2024 00:21 _x000D_ | 27/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_22/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_21/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_20/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_19/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_19/8/2024:01534496 _x000D_16/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_14/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_13/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_12/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_9/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_29/7/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_29/7/2024:01534496 _x000D_26/7/2024:26/07/2024 00:21 _x000D_ | [7 empty] | VFS1065574 | 30022073 | 2.Commissioning | AM |  | 2024-08-23 | 2024-08-23 |  | 0 | [11 empty] | 0
1814 | 664995 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Premier | TILLICOULTRY | FK13 6JP |  | 27/8/2024:Order Completed _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 27/8/2024:Order Completed _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065572 | 30022160 | 2.Commissioning | AM |  | 2024-08-23 | 2024-08-23 |  | 0 | [11 empty] | 0
1815 | 668406 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Greens Of Ceres | CUPAR | KY15 5NA |  | 27/8/2024:Order Completed _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 27/8/2024:Order Completed _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065570 | 30021964 | 2.Commissioning | AM |  | 2024-08-23 | 2024-08-23 |  | 0 | [11 empty] | 0
1816 | 486298 |  | Batch 6 Aug 24 | Type 2 | SoGEA | SPAR NEWPORT | NEWPORT | SA42 0PH |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_29/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_28/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_27/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_29/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_28/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_27/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | Update: Order Amended | 0 | [5 empty] | VFS1065568 | 30022036 | 1.Provisioning | AM |  | 2024-08-23 | 2024-08-23 |  | 0 | [11 empty] | 0
1817 | 200699 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Crown Store Llandeilo | LLANDEILO | SA19 6DF |  | 27/8/2024:Order Completed _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 27/8/2024:Order Completed _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065567 | 30022079 | 2.Commissioning | AM |  | 2024-08-23 | 2024-08-23 |  | 0 | [11 empty] | 0
1818 | 449988 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Alis Discount Store | Cupar | KY15 4DZ |  | 27/8/2024:Order Completed _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 27/8/2024:Order Completed _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065566 | 30022083 | 2.Commissioning | AM |  | 2024-08-23 | 2024-08-23 |  | 0 | [11 empty] | 0
1819 | 439366 |  | Batch 6 Aug 24 | Type 2 | SoGEA | SPAR | DOUNE | FK16 6BJ |  | 6/9/2024:#Update - Awaiting ECC approval _x000D_5/9/2024:#Update - Awaiting ECC approval _x000D_4/9/2024:#Update - Awaiting ECC approval _x000D_3/9/2024:#Update - Awaiting ECC approval _x000D_2/9/2024:#Update - Awaiting ECC approval _x000D_29/8/2024:#Update - Awaiting ECC approval _x000D_28/8/2024:Supplier Delay: New Appointment might be required _x000D_27/8/2024:Supplier Delay: New Appointment might be required _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:#Update - Awaiting ECC approval _x000D_6/9/2024:#Update - Awaiting ECC approval _x000D_5/9/2024:#Update - Awaiting ECC approval _x000D_4/9/2024:#Update - Awaiting ECC approval _x000D_3/9/2024:#Update - Awaiting ECC approval _x000D_2/9/2024:#Update - Awaiting ECC approval _x000D_29/8/2024:#Update - Awaiting ECC approval _x000D_28/8/2024:Supplier Delay: New Appointment might be required _x000D_27/8/2024:Supplier Delay: New Appointment might be required _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 0 | #Update - Awaiting ECC approval | [5 empty] | VFS1065563 | 30021956 | 1.Provisioning | AM |  | 2024-08-27 | 2024-08-27 |  | 0 | [11 empty] | 0
1820 | 207442 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Spar | HAWES | DL8 3QX |  | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_28/8/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_28/8/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 0 | 0 | [5 empty] | VFS1065565 | 30022007 | 1.Provisioning | AM |  | 2024-08-27 | 2024-08-27 |  | 0 | [11 empty] | 0
1821 | 425041 |  | Batch 6 Aug 24 | Type 2 | SoGEA | (Premier) Painswick Stores | STROUD | GL6 6QG | 2024-08-28 | 29/8/2024:Order Completed _x000D_28/8/2024:Order Completed _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 29/8/2024:Order Completed _x000D_28/8/2024:Order Completed _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065564 | 30022030 | 2.Commissioning | AM |  | 2024-08-27 | 2024-08-27 |  | 0 | [11 empty] | 0
1822 | 646136 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Spar Benview | Golspie | KW10 6SA | 2024-08-28 | 29/8/2024:Order Completed _x000D_28/8/2024:Order Completed _x000D_27/8/2024:Order Completed _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 29/8/2024:Order Completed _x000D_28/8/2024:Order Completed _x000D_27/8/2024:Order Completed _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065562 | 30022104 | 2.Commissioning | AM |  | 2024-08-27 | 2024-08-27 |  | 0 | [11 empty] | 0
1823 | 664931 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Goodwick Post Office | GOODWICK | SA64 0BN |  | 6/9/2024:#update- Retailer Confirmed,16/09 Am _x000D_5/9/2024:#update- Retailer Confirmed,16/09 Am _x000D_4/9/2024:#update- Retailer Confirmed,16/09 Am _x000D_3/9/2024:#update- Retailer Confirmed,16/09 Am _x000D_2/9/2024:#update- Retailer Confirmed,16/09 Am _x000D_29/8/2024:Order has been delayed please find the list of Notes _x000D_28/8/2024:Supplier Delay: KCI-3 (Order Completed) Delayed in Processing. _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:#update- Retailer Confirmed,16/09 Am _x000D_6/9/2024:#update- Retailer Confirmed,16/09 Am _x000D_5/9/2024:#update- Retailer Confirmed,16/09 Am _x000D_4/9/2024:#update- Retailer Confirmed,16/09 Am _x000D_3/9/2024:#update- Retailer Confirmed,16/09 Am _x000D_2/9/2024:#update- Retailer Confirmed,16/09 Am _x000D_29/8/2024:Order has been delayed please find the list of Notes _x000D_28/8/2024:Supplier Delay: KCI-3 (Order Completed) Delayed in Processing. _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | Order has been delayed please find the list of Notes | #update- Retailer Confirmed,16/09 Am | [5 empty] | VFS1065560 | 30022006 | 1.Provisioning | AM |  | 2024-08-27 | 2024-08-27 |  | 0 | [11 empty] | 0
1824 | 664897 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Langtoft Convenience Store | PETERBOROUGH | PE6 9LS | 2024-09-02 | 3/9/2024:Order Completed _x000D_2/9/2024:Order Completed _x000D_29/8/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 02/09/2024.We will continue to provide update as they become available. _x000D_28/8/2024:Your order requires a survey due to a new network solution required. We will only contact your customer if we need to. You will receive a further update by 17-09-2024. _x000D_27/8/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 3/9/2024:Order Completed _x000D_2/9/2024:Order Completed _x000D_29/8/2024:Your order has been delayed as site survey is required .This has been sent to the survey engineers and they have given us a review date of 02/09/2024.We will continue to provide update as they become available. _x000D_28/8/2024:Your order requires a survey due to a new network solution required. We will only contact your customer if we need to. You will receive a further update by 17-09-2024. _x000D_27/8/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065561 | 30022067 | 2.Commissioning | AM |  | 2024-08-27 | 2024-08-27 |  | 0 | [11 empty] | 0
1825 | 666375 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Londis | Attleborough | NR17 1RB |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Now order got re-appointed for 19/09/2024. _x000D_3/9/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Now order got re-appointed for 19/09/2024. _x000D_2/9/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Now order got re-appointed for 19/09/2024. _x000D_29/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Now order got re-appointed for 19/09/2024. _x000D_28/8/2024:Update: Order Amended _x000D_27/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Now order got re-appointed for 19/09/2024. _x000D_3/9/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Now order got re-appointed for 19/09/2024. _x000D_2/9/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Now order got re-appointed for 19/09/2024. _x000D_29/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Now order got re-appointed for 19/09/2024. _x000D_28/8/2024:Update: Order Amended _x000D_27/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 0 | 0 | [5 empty] | VFS1065558 | 30022138 | 1.Provisioning | AM |  | 2024-08-27 | 2024-08-27 |  | 0 | [11 empty] | 0
1826 | 664875 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Orpins Stores & Brabourne Lees PO | ASHFORD | TN25 6QE |  | 6/9/2024:#Update Retailer confirmed 09/09, AM. _x000D_5/9/2024:#Update Retailer confirmed 09/09, AM. _x000D_4/9/2024:#Update Retailer confirmed 09/09, AM. _x000D_3/9/2024:#Update Retailer confirmed 09/09, AM. _x000D_2/9/2024:#Update Retailer confirmed 09/09, AM. _x000D_29/8/2024:#Update Retailer confirmed 09/09, AM. _x000D_28/8/2024:Update: Order Amended _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:#Update Retailer confirmed 09/09, AM. _x000D_6/9/2024:#Update Retailer confirmed 09/09, AM. _x000D_5/9/2024:#Update Retailer confirmed 09/09, AM. _x000D_4/9/2024:#Update Retailer confirmed 09/09, AM. _x000D_3/9/2024:#Update Retailer confirmed 09/09, AM. _x000D_2/9/2024:#Update Retailer confirmed 09/09, AM. _x000D_29/8/2024:#Update Retailer confirmed 09/09, AM. _x000D_28/8/2024:Update: Order Amended _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 0 | #Update Retailer confirmed 09/09, AM. | [5 empty] | VFS1065556 | 30021982 | 1.Provisioning | AM |  | 2024-08-27 | 2024-08-27 |  | 0 | [11 empty] | 0
1827 | 631805 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Premier Mendlesham Bakery & Stores | Mendlesham | IP14 5SA | 2024-08-28 | 29/8/2024:Order Completed _x000D_28/8/2024:Order Completed _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 29/8/2024:Order Completed _x000D_28/8/2024:Order Completed _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065553 | 30022111 | 2.Commissioning | AM |  | 2024-08-27 | 2024-08-27 |  | 0 | [11 empty] | 0
1828 | 616555 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Glandy Cross Spar | Clynderwen | SA66 7XB | 2024-08-28 | 29/8/2024:Order Completed _x000D_28/8/2024:Order Completed _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 29/8/2024:Order Completed _x000D_28/8/2024:Order Completed _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065555 | 30022130 | 2.Commissioning | AM |  | 2024-08-27 | 2024-08-27 |  | 0 | [11 empty] | 0
1829 | 469472 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Conochies Post Office | Shetlands | ZE1 0DL |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Your order has been delayed due to sales query raised by our suppliers. Additional time related charges are not covered, additional cost required. Please check with end user and confirm the acceptance to progress the order further. _x000D_2/9/2024:Your order has been delayed due to sales query raised by our suppliers. Additional time related charges are not covered, additional cost required. Please check with end user and confirm the acceptance to progress the order further. _x000D_29/8/2024:Your order has been delayed due to sales query raised by our suppliers. Additional time related charges are not covered, additional cost required. Please check with end user and confirm the acceptance to progress the order further. _x000D_28/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Your order has been delayed due to sales query raised by our suppliers. Additional time related charges are not covered, additional cost required. Please check with end user and confirm the acceptance to progress the order further. _x000D_2/9/2024:Your order has been delayed due to sales query raised by our suppliers. Additional time related charges are not covered, additional cost required. Please check with end user and confirm the acceptance to progress the order further. _x000D_29/8/2024:Your order has been delayed due to sales query raised by our suppliers. Additional time related charges are not covered, additional cost required. Please check with end user and confirm the acceptance to progress the order further. _x000D_28/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | Update: Order Amended | 0 | [5 empty] | VFS1065554 | 30021979 | 1.Provisioning | AM |  | 2024-08-27 | 2024-08-27 |  | 0 | [11 empty] | 0
1830 | 656576 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Mace | Newry | BT35 7DJ | 2024-08-28 | 29/8/2024:Order Completed _x000D_28/8/2024:Order Completed _x000D_27/8/2024:Order Completed _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 29/8/2024:Order Completed _x000D_28/8/2024:Order Completed _x000D_27/8/2024:Order Completed _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065552 | 30022026 | 2.Commissioning | AM |  | 2024-08-27 | 2024-08-27 |  | 0 | [11 empty] | 0
1831 | 486282 |  | Batch 6 Aug 24 | Type 2 | SOGEA | SPAR ST CLEARS | CARMARTHEN | SA33 4AD |  | 0 | 0 | [7 empty] | Address query | Address query | 1.Provisioning | [17 empty] | 0
1832 | 469378 |  | Batch 6 Aug 24 | Type 2 | SOGEA | Loco | Totland Bay | PO39 0AT |  | 0 | 0 | [7 empty] | Address query | Address query | 1.Provisioning | [17 empty] | 0
1833 | 666994 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Tamerton Village Stores | PLYMOUTH | PL5 4NA |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:#Update - Ceased order from April - Confirmed with VF- Disregard _x000D_3/9/2024:#Update - Ceased order from April - Confirmed with VF- Disregard _x000D_2/9/2024:#Update - Ceased order from April - Confirmed with VF- Disregard _x000D_29/8/2024:#Update - Ceased order from April - Confirmed with VF- Disregard _x000D_28/8/2024:#Update - Ceased order from April - Confirmed with VF- Disregard _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:#Update - Ceased order from April - Confirmed with VF- Disregard _x000D_3/9/2024:#Update - Ceased order from April - Confirmed with VF- Disregard _x000D_2/9/2024:#Update - Ceased order from April - Confirmed with VF- Disregard _x000D_29/8/2024:#Update - Ceased order from April - Confirmed with VF- Disregard _x000D_28/8/2024:#Update - Ceased order from April - Confirmed with VF- Disregard _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | Update: Order Amended | 0 | [5 empty] | VFS1065551 | 30022106 | 1.Provisioning | AM |  | 2024-08-27 | 2024-08-27 |  | 0 | [11 empty] | 0
1834 | 484768 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Burys News Food and Wine | Dorset | BH23 4AS | 2024-08-29 | 29/8/2024:Order Completed _x000D_28/8/2024:Supplier Delay: KCI-3 (Order Completed) Delayed in Processing. _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 29/8/2024:Order Completed _x000D_28/8/2024:Supplier Delay: KCI-3 (Order Completed) Delayed in Processing. _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065549 | 30022034 | 2.Commissioning | AM |  | 2024-08-27 | 2024-08-27 |  | 0 | [11 empty] | 0
1835 | 668382 |  | Batch 6 Aug 24 | Type 2 | SoGEA | East Halton Post Office | Grimsby | DN40 3NL | 2024-08-28 | 29/8/2024:Order Completed _x000D_28/8/2024:Order Completed _x000D_27/8/2024:Order Completed _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 29/8/2024:Order Completed _x000D_28/8/2024:Order Completed _x000D_27/8/2024:Order Completed _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065550 | 30022134 | 2.Commissioning | AM |  | 2024-08-27 | 2024-08-27 |  | 0 | [11 empty] | 0
1836 | 456297 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Brimscombe Stores Premier | Stroud | GL5 2QE | 2024-08-28 | 29/8/2024:Order Completed _x000D_28/8/2024:Order Completed _x000D_27/8/2024:Update: Order Completed by Supplier _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 29/8/2024:Order Completed _x000D_28/8/2024:Order Completed _x000D_27/8/2024:Update: Order Completed by Supplier _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065548 | 30022017 | 2.Commissioning | AM |  | 2024-08-27 | 2024-08-27 |  | 0 | [11 empty] | 0
1837 | 660457 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Nisa Local | Norwich | NR12 9BB |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_3/9/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_2/9/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_29/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_28/8/2024:Supplier Delay: New Appointment might be required _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_3/9/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_2/9/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_29/8/2024:Your order has been delayed due to a customer missed appointment as the site is not ready. Please check with end user and reappoint the order if still required. _x000D_28/8/2024:Supplier Delay: New Appointment might be required _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 0 | 0 | [5 empty] | VFS1065547 | 30021988 | 1.Provisioning | AM |  | 2024-08-27 | 2024-08-27 |  | 0 | [11 empty] | 0
1838 | 659630 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Premier Methwold Convenience | Thetford | IP26 4NT | 2024-08-28 | 29/8/2024:Order Completed _x000D_28/8/2024:Order Completed _x000D_27/8/2024:Update: Order Completed by Supplier _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 29/8/2024:Order Completed _x000D_28/8/2024:Order Completed _x000D_27/8/2024:Update: Order Completed by Supplier _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065546 | 30022110 | 2.Commissioning | AM |  | 2024-08-27 | 2024-08-27 |  | 0 | [11 empty] | 0
1839 | 657728 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Harris Way Express | Colchester | CO2 8WJ |  | 6/9/2024:#Update - Order has been delayed as the line plant records need to be updated by supplier. CSL will update as more information become available. _x000D_5/9/2024:#Update - Order has been delayed as the line plant records need to be updated by supplier. CSL will update as more information become available. _x000D_4/9/2024:#Update - Order has been delayed as the line plant records need to be updated by supplier. CSL will update as more information become available. _x000D_3/9/2024:#Update - Order has been delayed as the line plant records need to be updated by supplier. CSL will update as more information become available. _x000D_2/9/2024:#Update - Order has been delayed as the line plant records need to be updated by supplier. CSL will update as more information become available. _x000D_29/8/2024:#Update - Order has been delayed as the line plant records need to be updated by supplier. CSL will update as more information become available. _x000D_28/8/2024:#Update - Order has been delayed as the line plant records need to be updated by supplier. CSL will update as more information become available. _x000D_27/8/2024:#Update - Order has been delayed as the line plant records need to be updated by supplier. CSL will update as more information become available. _x000D_22/8/2024:#Update - Order has been delayed as the line plant records need to be updated by supplier. CSL will update as more information become available. _x000D_21/8/2024:#Update - Order has been delayed as the line plant records need to be updated by supplier. CSL will update as more information become available. _x000D_20/8/2024:#Update - Order has been delayed as the line plant records need to be updated by supplier. CSL will update as more information become available. _x000D_19/8/2024:#Update - Order has been delayed as the line plant records need to be updated by supplier. CSL will update as more information become available. _x000D_19/8/2024:01534304 _x000D_16/8/2024:#Update - Order has been delayed as the line plant records need to be updated by supplier. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order has been delayed as the line plant records need to be updated by supplier. CSL will update as more information become available. _x000D_14/8/2024:#Update - Order has been delayed as the line plant records need to be updated by supplier. CSL will update as more information become available. _x000D_13/8/2024:#Update - Order has been delayed as the line plant records need to be updated by supplier. CSL will update as more information become available. _x000D_12/8/2024:#Update - Order has been delayed as the line plant records need to be updated by supplier. CSL will update as more information become available. _x000D_9/8/2024:#Update - Order has been delayed as the line plant records need to be updated by supplier. CSL will update as more information become available. _x000D_8/8/2024:31/07/2024 _x000D_6/8/2024:31/07/2024 _x000D_5/8/2024:31/07/2024 _x000D_2/8/2024:31/07/2024 _x000D_1/8/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_30/7/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. We have confirmed with end user that a second line is required to progress the order further. Please review back on 31/07/2024. CSL Note: Inval _x000D_29/7/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. We have confirmed with end user that a second line is required to progress the order further. Please review back on 31/07/2024. CSL Note: Inval _x000D_29/7/2024:26/07/2024 16:23 _x000D_26/7/2024:25/07/2024 20:19 _x000D_ | 9/9/2024:#Update - Order has been delayed as the line plant records need to be updated by supplier. CSL will update as more information become available. _x000D_6/9/2024:#Update - Order has been delayed as the line plant records need to be updated by supplier. CSL will update as more information become available. _x000D_5/9/2024:#Update - Order has been delayed as the line plant records need to be updated by supplier. CSL will update as more information become available. _x000D_4/9/2024:#Update - Order has been delayed as the line plant records need to be updated by supplier. CSL will update as more information become available. _x000D_3/9/2024:#Update - Order has been delayed as the line plant records need to be updated by supplier. CSL will update as more information become available. _x000D_2/9/2024:#Update - Order has been delayed as the line plant records need to be updated by supplier. CSL will update as more information become available. _x000D_29/8/2024:#Update - Order has been delayed as the line plant records need to be updated by supplier. CSL will update as more information become available. _x000D_28/8/2024:#Update - Order has been delayed as the line plant records need to be updated by supplier. CSL will update as more information become available. _x000D_27/8/2024:#Update - Order has been delayed as the line plant records need to be updated by supplier. CSL will update as more information become available. _x000D_22/8/2024:#Update - Order has been delayed as the line plant records need to be updated by supplier. CSL will update as more information become available. _x000D_21/8/2024:#Update - Order has been delayed as the line plant records need to be updated by supplier. CSL will update as more information become available. _x000D_20/8/2024:#Update - Order has been delayed as the line plant records need to be updated by supplier. CSL will update as more information become available. _x000D_19/8/2024:#Update - Order has been delayed as the line plant records need to be updated by supplier. CSL will update as more information become available. _x000D_19/8/2024:01534304 _x000D_16/8/2024:#Update - Order has been delayed as the line plant records need to be updated by supplier. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order has been delayed as the line plant records need to be updated by supplier. CSL will update as more information become available. _x000D_14/8/2024:#Update - Order has been delayed as the line plant records need to be updated by supplier. CSL will update as more information become available. _x000D_13/8/2024:#Update - Order has been delayed as the line plant records need to be updated by supplier. CSL will update as more information become available. _x000D_12/8/2024:#Update - Order has been delayed as the line plant records need to be updated by supplier. CSL will update as more information become available. _x000D_9/8/2024:#Update - Order has been delayed as the line plant records need to be updated by supplier. CSL will update as more information become available. _x000D_8/8/2024:31/07/2024 _x000D_6/8/2024:31/07/2024 _x000D_5/8/2024:31/07/2024 _x000D_2/8/2024:31/07/2024 _x000D_1/8/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_31/7/2024:31/07/2024 _x000D_30/7/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. We have confirmed with end user that a second line is required to progress the order further. Please review back on 31/07/2024. CSL Note: Inval _x000D_29/7/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. We have confirmed with end user that a second line is required to progress the order further. Please review back on 31/07/2024. CSL Note: Inval _x000D_29/7/2024:26/07/2024 16:23 _x000D_26/7/2024:25/07/2024 20:19 _x000D_ | 0 | #Update - Order has been delayed as the line plant records need to be updated by supplier. CSL will update as more information become available. | [5 empty] | VFS1065544 | 30022023 | 1.Provisioning | AM |  | 2024-08-27 |  |  | 0 | [11 empty] | 0
1840 | 656024 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Lifestyle Express | Dyserth | LL18 6AA |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:Your order requires planning validation. We may contact your customer if we need to. You will receive a further update by 16-09-2024. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_2/9/2024:Your order requires planning validation. We may contact your customer if we need to. You will receive a further update by 16-09-2024. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/8/2024:Your order requires planning validation. We may contact your customer if we need to. You will receive a further update by 16-09-2024. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_28/8/2024:Your order requires planning validation. We may contact your customer if we need to. You will receive a further update by 16-09-2024. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_27/8/2024:Your order requires planning validation. We may contact your customer if we need to. You will receive a further update by 16-09-2024. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/8/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 23/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_21/8/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 23/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_20/8/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 23/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_19/8/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 23/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_19/8/2024:16/08/2024 18:44 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 29/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_13/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 29/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 29/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_9/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 29/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_8/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 29/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/8/2024:Your order has been delayed.LinePlant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 07/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_5/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 06/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_2/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 06/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_1/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 02/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 02/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:37897 _x000D_30/7/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. We have confirmed with end user that a second line is required to progress the order further. Please review back on 01/08/2024. CSL Note: Inval _x000D_29/7/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. We have confirmed with end user that a second line is required to progress the order further. Please review back on 01/08/2024. CSL Note: Inval _x000D_29/7/2024:26/07/2024 16:23 _x000D_26/7/2024:25/07/2024 20:12 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:Your order requires planning validation. We may contact your customer if we need to. You will receive a further update by 16-09-2024. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_2/9/2024:Your order requires planning validation. We may contact your customer if we need to. You will receive a further update by 16-09-2024. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/8/2024:Your order requires planning validation. We may contact your customer if we need to. You will receive a further update by 16-09-2024. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_28/8/2024:Your order requires planning validation. We may contact your customer if we need to. You will receive a further update by 16-09-2024. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_27/8/2024:Your order requires planning validation. We may contact your customer if we need to. You will receive a further update by 16-09-2024. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/8/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 23/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_21/8/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 23/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_20/8/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 23/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_19/8/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 23/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_19/8/2024:16/08/2024 18:44 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 29/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_13/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 29/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_12/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 29/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_9/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 29/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_8/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 29/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/8/2024:Your order has been delayed.LinePlant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 07/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_5/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 06/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_2/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 06/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_1/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 02/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 02/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:37897 _x000D_30/7/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. We have confirmed with end user that a second line is required to progress the order further. Please review back on 01/08/2024. CSL Note: Inval _x000D_29/7/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. We have confirmed with end user that a second line is required to progress the order further. Please review back on 01/08/2024. CSL Note: Inval _x000D_29/7/2024:26/07/2024 16:23 _x000D_26/7/2024:25/07/2024 20:12 _x000D_ | 0 | 0 | [5 empty] | VFS1065545 | 30022092 | 1.Provisioning | AM |  | 2024-08-27 |  |  | 0 | [11 empty] | 0
1841 | 655296 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Stonebroom Stores Todays Local | Alfreton | DE55 6LD | 2024-08-28 | 29/8/2024:Order Completed _x000D_28/8/2024:Order Completed _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 29/8/2024:Order Completed _x000D_28/8/2024:Order Completed _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065541 | 30022150 | 2.Commissioning | AM |  | 2024-08-27 | 2024-08-27 |  | 0 | [11 empty] | 0
1842 | 650753 |  | Batch 6 Aug 24 | Type 2 | SOGEA | Sophie's Corner Shop | Hampsthwaite | HG3 2ET |  | 0 | 0 | [7 empty] | Address query | Address query | 1.Provisioning | [17 empty] | 0
1843 | 648776 |  | Batch 6 Aug 24 | Type 2 | SoGEA | The Stores Goldsithney | Penzance | TR20 9HA | 2024-08-28 | 29/8/2024:Order Completed _x000D_28/8/2024:Order Completed _x000D_27/8/2024:Order Completed _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 29/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 29/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 29/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_2/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 29/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_1/8/2024:Your order has been delayed. LinePlant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 02/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointmen _x000D_31/7/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. We have confirmed with end user that a second line is required to progress the order further. Please review back on 01/08/2024. CSL Note: Inval _x000D_31/7/2024:37626 _x000D_30/7/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. We have confirmed with end user that a second line is required to progress the order further. Please review back on 01/08/2024. CSL Note: Inval _x000D_29/7/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. We have confirmed with end user that a second line is required to progress the order further. Please review back on 01/08/2024. CSL Note: Inval _x000D_29/7/2024:26/07/2024 16:24 _x000D_26/7/2024:25/07/2024 20:19 _x000D_ | 29/8/2024:Order Completed _x000D_28/8/2024:Order Completed _x000D_27/8/2024:Order Completed _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 29/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 29/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 29/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_2/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 29/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_1/8/2024:Your order has been delayed. LinePlant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 02/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointmen _x000D_31/7/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. We have confirmed with end user that a second line is required to progress the order further. Please review back on 01/08/2024. CSL Note: Inval _x000D_31/7/2024:37626 _x000D_30/7/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. We have confirmed with end user that a second line is required to progress the order further. Please review back on 01/08/2024. CSL Note: Inval _x000D_29/7/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. We have confirmed with end user that a second line is required to progress the order further. Please review back on 01/08/2024. CSL Note: Inval _x000D_29/7/2024:26/07/2024 16:24 _x000D_26/7/2024:25/07/2024 20:19 _x000D_ | [7 empty] | VFS1065542 | 30022164 | 2.Commissioning | AM |  | 2024-08-27 | 2024-08-27 |  | 0 | [11 empty] | 0
1844 | 666601 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Hegarty's Nearbuy | Dungannon | BT71 7HL | 2024-08-28 | 29/8/2024:Order Completed _x000D_28/8/2024:Order Completed _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 29/8/2024:Order Completed _x000D_28/8/2024:Order Completed _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065540 | 30022091 | 2.Commissioning | AM |  | 2024-08-27 | 2024-08-27 |  | 0 | [11 empty] | 0
1845 | 661430 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Tornagrain Stores | Inverness | IV2 8AL |  | 6/9/2024:#Update Retailer confirmed 17/09,AM. _x000D_5/9/2024:#Update Retailer confirmed 17/09,AM. _x000D_4/9/2024:#Update Retailer confirmed 17/09,AM. _x000D_3/9/2024:#Update Retailer confirmed 17/09,AM. _x000D_2/9/2024:#Update Retailer confirmed 17/09,AM. _x000D_29/8/2024:#Update Retailer confirmed 17/09,AM. _x000D_28/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_27/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:#Update Retailer confirmed 17/09,AM. _x000D_6/9/2024:#Update Retailer confirmed 17/09,AM. _x000D_5/9/2024:#Update Retailer confirmed 17/09,AM. _x000D_4/9/2024:#Update Retailer confirmed 17/09,AM. _x000D_3/9/2024:#Update Retailer confirmed 17/09,AM. _x000D_2/9/2024:#Update Retailer confirmed 17/09,AM. _x000D_29/8/2024:#Update Retailer confirmed 17/09,AM. _x000D_28/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_27/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 0 | #Update Retailer confirmed 17/09,AM. | [5 empty] | VFS1065538 | 30021957 | 1.Provisioning | AM |  | 2024-08-27 | 2024-08-27 |  | 0 | [11 empty] | 0
1846 | 646724 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Spar | Newry | BT35 8JB | 2024-08-28 | 29/8/2024:Order Completed _x000D_28/8/2024:Order Completed _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 29/8/2024:Order Completed _x000D_28/8/2024:Order Completed _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065539 | 30022003 | 2.Commissioning | AM |  | 2024-08-27 | 2024-08-27 |  | 0 | [11 empty] | 0
1847 | 642830 |  | Batch 6 Aug 24 | Type 2 | SoGEA | QD Stores | Saffron Walden | CB10 1AX | 2024-08-29 | 29/8/2024:Order Completed _x000D_28/8/2024:Order Completed _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 29/8/2024:Order Completed _x000D_28/8/2024:Order Completed _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065536 | 30022161 | 2.Commissioning | AM |  | 2024-08-28 | 2024-08-28 |  | 0 | [11 empty] | 0
1848 | 638901 |  | Batch 6 Aug 24 | Type 2 | SoGEA | D C Patrick Newsagents | Woodbridge | IP13 9BA |  | 6/9/2024:#Update - Installation was not completed on 28/08. Awaiting Openreach feedback regarding why and will progress accordingly _x000D_5/9/2024:#Update - Installation was not completed on 28/08. Awaiting Openreach feedback regarding why and will progress accordingly _x000D_4/9/2024:#Update - Installation was not completed on 28/08. Awaiting Openreach feedback regarding why and will progress accordingly _x000D_3/9/2024:#Update - Installation was not completed on 28/08. Awaiting Openreach feedback regarding why and will progress accordingly _x000D_2/9/2024:#Update - Installation was not completed on 28/08. Awaiting Openreach feedback regarding why and will progress accordingly _x000D_29/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:#Update - Installation was not completed on 28/08. Awaiting Openreach feedback regarding why and will progress accordingly _x000D_6/9/2024:#Update - Installation was not completed on 28/08. Awaiting Openreach feedback regarding why and will progress accordingly _x000D_5/9/2024:#Update - Installation was not completed on 28/08. Awaiting Openreach feedback regarding why and will progress accordingly _x000D_4/9/2024:#Update - Installation was not completed on 28/08. Awaiting Openreach feedback regarding why and will progress accordingly _x000D_3/9/2024:#Update - Installation was not completed on 28/08. Awaiting Openreach feedback regarding why and will progress accordingly _x000D_2/9/2024:#Update - Installation was not completed on 28/08. Awaiting Openreach feedback regarding why and will progress accordingly _x000D_29/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 0 | #Update - Installation was not completed on 28/08. Awaiting Openreach feedback regarding why and will progress accordingly | [5 empty] | VFS1065532 | 30022041 | 1.Provisioning | AM |  | 2024-08-28 | 2024-08-28 |  | 0 | [11 empty] | 0
1849 | 637110 |  | Batch 6 Aug 24 | Type 2 | SoGEA | The Braco Shop | Stirlingshire | FK15 9QN | 2024-08-29 | 29/8/2024:Order Completed _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 29/8/2024:Order Completed _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065534 | 30021984 | 2.Commissioning | AM |  | 2024-08-28 | 2024-08-28 |  | 0 | [11 empty] | 0
1850 | 635121 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Londis | Harleston | IP20 9BH | 2024-08-29 | 29/8/2024:Order Completed _x000D_28/8/2024:Update: Order Completed by Supplier _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 29/8/2024:Order Completed _x000D_28/8/2024:Update: Order Completed by Supplier _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065533 | 30022075 | 2.Commissioning | AM |  | 2024-08-28 | 2024-08-28 |  | 0 | [11 empty] | 0
1851 | 633648 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Vivo | Garvagh | BT51 5DS |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 0 | 0 | [5 empty] | Address query | 30022146 | 1.Provisioning | AM |  | 2024-08-28 |  |  | 0 | [11 empty] | 0
1852 | 632115 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Keystore More | Wick | KW1 4AJ | 2024-08-29 | 29/8/2024:Order Completed _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 29/8/2024:Order Completed _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065530 | 30022063 | 2.Commissioning | AM |  | 2024-08-28 | 2024-08-28 |  | 0 | [11 empty] | 0
1853 | 671243 |  | Batch 6 Aug 24 | Type 2 | SoGEA | One Stop Stores | ROTHERHAM | S62 7HX | 2024-08-29 | 29/8/2024:Order Completed _x000D_28/8/2024:Order Completed _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 29/8/2024:Order Completed _x000D_28/8/2024:Order Completed _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065528 | 30022115 | 2.Commissioning | AM |  | 2024-08-28 | 2024-08-28 |  | 0 | [11 empty] | 0
1854 | 618058 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Bestone Wittersham Village Store | Wittersham | TN30 7PD | 2024-08-29 | 29/8/2024:Order Completed _x000D_28/8/2024:Update: Order Completed by Supplier _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 29/8/2024:Order Completed _x000D_28/8/2024:Update: Order Completed by Supplier _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065529 | 30022137 | 2.Commissioning | AM |  | 2024-08-28 | 2024-08-28 |  | 0 | [11 empty] | 0
1855 | 647346 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Over Stores | Over | CB24 5ND |  | 6/9/2024:#Update Retailer confirmed 24/09, AM. _x000D_5/9/2024:#Update Retailer confirmed 24/09, AM. _x000D_4/9/2024:#Update Retailer confirmed 24/09, AM. _x000D_3/9/2024:#Update Retailer confirmed 24/09, AM. _x000D_2/9/2024:Your order has been delayed due to a customer missed appointment. Customer not received router. Please check with end user and reappoint the order if still required. _x000D_29/8/2024:Your order has been delayed due to a customer missed appointment. Customer not received router. Please check with end user and reappoint the order if still required. _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:#Update Retailer confirmed 24/09, AM. _x000D_6/9/2024:#Update Retailer confirmed 24/09, AM. _x000D_5/9/2024:#Update Retailer confirmed 24/09, AM. _x000D_4/9/2024:#Update Retailer confirmed 24/09, AM. _x000D_3/9/2024:#Update Retailer confirmed 24/09, AM. _x000D_2/9/2024:Your order has been delayed due to a customer missed appointment. Customer not received router. Please check with end user and reappoint the order if still required. _x000D_29/8/2024:Your order has been delayed due to a customer missed appointment. Customer not received router. Please check with end user and reappoint the order if still required. _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | Update: Order Amended | #Update Retailer confirmed 24/09, AM. | [5 empty] | VFS1065526 | 30021981 | 1.Provisioning | AM |  | 2024-08-28 | 2024-08-28 |  | 0 | [11 empty] | 0
1856 | 615157 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Londis | Fife | KY8 5JN |  | 6/9/2024:#Update Retailer confirmed 25/09, PM. _x000D_5/9/2024:#Update Retailer confirmed 25/09, PM. _x000D_4/9/2024:#Update Retailer confirmed 25/09, PM. _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:#Update Retailer confirmed 25/09, PM. _x000D_6/9/2024:#Update Retailer confirmed 25/09, PM. _x000D_5/9/2024:#Update Retailer confirmed 25/09, PM. _x000D_4/9/2024:#Update Retailer confirmed 25/09, PM. _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | Update: Order Amended | #Update Retailer confirmed 25/09, PM. | [5 empty] | VFP2450228 | 30022155 | 1.Provisioning | AM |  | 2024-09-02 | 2024-09-02 |  | 0 | [11 empty] | 0
1857 | 608513 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Hovingham Stores | York | YO62 4LF |  | 6/9/2024:#Update - Action for Allwyn - Installation has now been amended to 17/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 17/09 is a suitable date. _x000D_5/9/2024:#Update - Action for Allwyn - Installation has now been amended to 17/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 17/09 is a suitable date. _x000D_4/9/2024:#Update - Action for Allwyn - Installation has now been amended to 17/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 17/09 is a suitable date. _x000D_3/9/2024:#Update - Action for Allwyn - Installation has now been amended to 17/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 17/09 is a suitable date. _x000D_2/9/2024:#Update - Action for Allwyn - Installation has now been amended to 17/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 17/09 is a suitable date. _x000D_29/8/2024:#Update - Action for Allwyn - Installation has now been amended to 17/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 17/09 is a suitable date. _x000D_28/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:#Update - Action for Allwyn - Installation has now been amended to 17/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 17/09 is a suitable date. _x000D_6/9/2024:#Update - Action for Allwyn - Installation has now been amended to 17/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 17/09 is a suitable date. _x000D_5/9/2024:#Update - Action for Allwyn - Installation has now been amended to 17/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 17/09 is a suitable date. _x000D_4/9/2024:#Update - Action for Allwyn - Installation has now been amended to 17/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 17/09 is a suitable date. _x000D_3/9/2024:#Update - Action for Allwyn - Installation has now been amended to 17/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 17/09 is a suitable date. _x000D_2/9/2024:#Update - Action for Allwyn - Installation has now been amended to 17/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 17/09 is a suitable date. _x000D_29/8/2024:#Update - Action for Allwyn - Installation has now been amended to 17/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 17/09 is a suitable date. _x000D_28/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | Update: Order Amended | #Update - Action for Allwyn - Installation has now been amended to 17/09 AM. Please speak with the retailer regarding installation details and confirm to CSL if 17/09 is a suitable date. | [5 empty] | VFS1065522 | 30022129 | 1.Provisioning | AM |  | 2024-08-28 | 2024-08-28 |  | 0 | [11 empty] | 0
1858 | 603871 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Penhaligons News | Lostwithiel | PL22 0BL | 2024-08-29 | 29/8/2024:Order Completed _x000D_28/8/2024:Update: Order Completed by Supplier _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 29/8/2024:Order Completed _x000D_28/8/2024:Update: Order Completed by Supplier _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065525 | 30021989 | 2.Commissioning | AM |  | 2024-08-28 | 2024-08-28 |  | 0 | [11 empty] | 0
1859 | 602003 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Ladybank Supersave | Cupar | KY15 7JS | 2024-08-29 | 29/8/2024:Order Completed _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 29/8/2024:Order Completed _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065523 | 30022016 | 2.Commissioning | AM |  | 2024-08-28 | 2024-08-28 |  | 0 | [11 empty] | 0
1860 | 643171 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Londis Cowie | Stirling | FK7 7BL |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. _x000D_29/8/2024:Supplier Delay: New Appointment might be required _x000D_28/8/2024:Supplier Delay: New Appointment might be required _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. _x000D_29/8/2024:Supplier Delay: New Appointment might be required _x000D_28/8/2024:Supplier Delay: New Appointment might be required _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | Update: Order Amended | 0 | [5 empty] | VFS1065520 | 30022076 | 1.Provisioning | AM |  | 2024-08-28 | 2024-08-28 |  | 0 | [11 empty] | 0
1861 | 619882 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Marston Store | Coventry | CV12 9AD |  | 6/9/2024:#Update Retailer confirmed 12/09, AM. _x000D_5/9/2024:#Update Retailer confirmed 12/09, AM. _x000D_4/9/2024:#Update Retailer confirmed 12/09, AM. _x000D_3/9/2024:#Update Retailer confirmed 12/09, AM. _x000D_2/9/2024:#Update Retailer confirmed 12/09, AM. _x000D_29/8/2024:#Update Retailer unaware and told the engineer he'd cancelled the order. Checking with Allwyn. _x000D_28/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:#Update Retailer confirmed 12/09, AM. _x000D_6/9/2024:#Update Retailer confirmed 12/09, AM. _x000D_5/9/2024:#Update Retailer confirmed 12/09, AM. _x000D_4/9/2024:#Update Retailer confirmed 12/09, AM. _x000D_3/9/2024:#Update Retailer confirmed 12/09, AM. _x000D_2/9/2024:#Update Retailer confirmed 12/09, AM. _x000D_29/8/2024:#Update Retailer unaware and told the engineer he'd cancelled the order. Checking with Allwyn. _x000D_28/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 0 | #Update Retailer confirmed 12/09, AM. | [5 empty] | VFS1065521 | 30021978 | 1.Provisioning | AM |  | 2024-08-28 | 2024-08-28 |  | 0 | [11 empty] | 0
1862 | 616577 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Connaught Food and Wine | Frinton-on-Sea | CO13 9PP | 2024-08-29 | 29/8/2024:Order Completed _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 29/8/2024:Order Completed _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065517 | 30022035 | 2.Commissioning | AM |  | 2024-08-28 | 2024-08-28 |  | 0 | [11 empty] | 0
1863 | 482115 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Avanishan Food And Wine | Ipswich | IP5 2PX |  | 6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 18/09 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 18/09 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 18/09 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 18/09 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 18/09 AM _x000D_29/8/2024:#Update - Missed Appointment - The onsite employee was unaware of order and there was no manager onsite. The engineer is not sure about the cable route and needs to discuss with the manager. _x000D_28/8/2024:End User Missed appointment. Action required _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 18/09 AM _x000D_6/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 18/09 AM _x000D_5/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 18/09 AM _x000D_4/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 18/09 AM _x000D_3/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 18/09 AM _x000D_2/9/2024:#Update - Allwyn confirmed Retailer has agreed to installation on 18/09 AM _x000D_29/8/2024:#Update - Missed Appointment - The onsite employee was unaware of order and there was no manager onsite. The engineer is not sure about the cable route and needs to discuss with the manager. _x000D_28/8/2024:End User Missed appointment. Action required _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | Update: Order Amended | #Update - Allwyn confirmed Retailer has agreed to installation on 18/09 AM | [5 empty] | VFS1065516 | 30022114 | 1.Provisioning | AM |  | 2024-08-28 | 2024-08-28 |  | 0 | [11 empty] | 0
1864 | 659212 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Saline Store | Dunfermline | KY12 9TL | 2024-08-29 | 29/8/2024:Order Completed _x000D_28/8/2024:Order Completed _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 29/8/2024:Order Completed _x000D_28/8/2024:Order Completed _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065519 | 30021960 | 2.Commissioning | AM |  | 2024-08-28 | 2024-08-28 |  | 0 | [11 empty] | 0
1865 | 482778 |  | Batch 6 Aug 24 | Type 2 | SoGEA | The Paper Shop | Tarland | AB34 4YL | 2024-08-29 | 29/8/2024:Order Completed _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 29/8/2024:Order Completed _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065515 | 30022049 | 2.Commissioning | AM |  | 2024-08-28 | 2024-08-28 |  | 0 | [11 empty] | 0
1866 | 664255 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Spar Dyffryn | Dyffryn Ardudwy | LL44 2EN | 2024-08-29 | 29/8/2024:Order Completed _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 29/8/2024:Order Completed _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065513 | 30022020 | 2.Commissioning | AM |  | 2024-08-28 | 2024-08-28 |  | 0 | [11 empty] | 0
1867 | 646893 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Rosehearty Convenience Store | Rosehearty | AB43 7JQ | 2024-08-29 | 29/8/2024:Order Completed _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 29/8/2024:Order Completed _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065514 | 30022011 | 2.Commissioning | AM |  | 2024-08-28 | 2024-08-28 |  | 0 | [11 empty] | 0
1868 | 664614 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Nice Price News & PO | Llandeilo | SA19 6HA | 2024-08-29 | 29/8/2024:Order Completed _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 29/8/2024:Order Completed _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065512 | 30022127 | 2.Commissioning | AM |  | 2024-08-28 | 2024-08-28 |  | 0 | [11 empty] | 0
1869 | 650416 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Jcb s Convenience Store | Filey | YO14 0JR | 2024-08-29 | 29/8/2024:Order Completed _x000D_28/8/2024:Order Completed _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 29/8/2024:Order Completed _x000D_28/8/2024:Order Completed _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065511 | 30022156 | 2.Commissioning | AM |  | 2024-08-28 | 2024-08-28 |  | 0 | [11 empty] | 0
1870 | 643896 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Dans Goods | Fife | KY10 3TD |  | 6/9/2024:#Update Your order has been delayed due to Further Assistance is required, order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 03/09/2024. _x000D_5/9/2024:#Update Your order has been delayed due to Further Assistance is required, order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 03/09/2024. _x000D_4/9/2024:#Update Your order has been delayed due to Further Assistance is required, order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 03/09/2024. _x000D_3/9/2024:#Update Your order has been delayed due to Further Assistance is required, order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 03/09/2024. _x000D_2/9/2024:#Update Your order has been delayed due to Further Assistance is required, order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 03/09/2024. _x000D_29/8/2024:#Update Your order has been delayed due to Further Assistance is required, order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 03/09/2024. _x000D_28/8/2024:#Update Network Planning issues. Please await for further updates _x000D_27/8/2024:#Update Network Planning issues. Please await for further updates _x000D_22/8/2024:#Update Network Planning issues. Please await for further updates _x000D_21/8/2024:#Update Network Planning issues. Please await for further updates _x000D_20/8/2024:#Update Network Planning issues. Please await for further updates _x000D_19/8/2024:#Update Network Planning issues. Please await for further updates _x000D_19/8/2024:01534314 _x000D_16/8/2024:#Update Network Planning issues. Please await for further updates _x000D_15/8/2024:#Update Network Planning issues. Please await for further updates _x000D_14/8/2024:#Update Network Planning issues. Please await for further updates _x000D_13/8/2024:#Update Network Planning issues. Please await for further updates _x000D_12/8/2024:#Update Network Planning issues. Please await for further updates _x000D_9/8/2024:#Update Network Planning issues. Please await for further updates _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update Network Planning issues. Please await for further updates _x000D_29/7/2024:#Update Network Planning issues. Please await for further updates _x000D_29/7/2024:01534314 _x000D_26/7/2024:25/07/2024 20:24 _x000D_ | 9/9/2024:#Update Your order has been delayed due to Further Assistance is required, order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 03/09/2024. _x000D_6/9/2024:#Update Your order has been delayed due to Further Assistance is required, order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 03/09/2024. _x000D_5/9/2024:#Update Your order has been delayed due to Further Assistance is required, order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 03/09/2024. _x000D_4/9/2024:#Update Your order has been delayed due to Further Assistance is required, order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 03/09/2024. _x000D_3/9/2024:#Update Your order has been delayed due to Further Assistance is required, order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 03/09/2024. _x000D_2/9/2024:#Update Your order has been delayed due to Further Assistance is required, order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 03/09/2024. _x000D_29/8/2024:#Update Your order has been delayed due to Further Assistance is required, order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 03/09/2024. _x000D_28/8/2024:#Update Network Planning issues. Please await for further updates _x000D_27/8/2024:#Update Network Planning issues. Please await for further updates _x000D_22/8/2024:#Update Network Planning issues. Please await for further updates _x000D_21/8/2024:#Update Network Planning issues. Please await for further updates _x000D_20/8/2024:#Update Network Planning issues. Please await for further updates _x000D_19/8/2024:#Update Network Planning issues. Please await for further updates _x000D_19/8/2024:01534314 _x000D_16/8/2024:#Update Network Planning issues. Please await for further updates _x000D_15/8/2024:#Update Network Planning issues. Please await for further updates _x000D_14/8/2024:#Update Network Planning issues. Please await for further updates _x000D_13/8/2024:#Update Network Planning issues. Please await for further updates _x000D_12/8/2024:#Update Network Planning issues. Please await for further updates _x000D_9/8/2024:#Update Network Planning issues. Please await for further updates _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update Network Planning issues. Please await for further updates _x000D_29/7/2024:#Update Network Planning issues. Please await for further updates _x000D_29/7/2024:01534314 _x000D_26/7/2024:25/07/2024 20:24 _x000D_ | Your order has been delayed. The engineer has now completed all the external work and our suppliers has advised us to reappoint the order. Please check with end user and reappoint for the first available date. | #Update Your order has been delayed due to Further Assistance is required, order is now with controls team to get the engineer reassigned. Supplier will provide further updates on 03/09/2024. | [5 empty] | VFS1065510 | 30022085 | 1.Provisioning | AM |  | 2024-08-28 | 2024-08-28 |  | 0 | [11 empty] | 0
1871 | 665382 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Drumquin Vivo | Omagh | BT78 4SB | 2024-08-29 | 29/8/2024:Order Completed _x000D_28/8/2024:Order Completed _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 29/8/2024:Order Completed _x000D_28/8/2024:Order Completed _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065508 | 30022109 | 2.Commissioning | AM |  | 2024-08-28 | 2024-08-28 |  | 0 | [11 empty] | 0
1872 | 649759 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Londis | Laceby | DN37 7HY |  | 6/9/2024:0 _x000D_5/9/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_4/9/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_3/9/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_2/9/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_29/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_28/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_4/9/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_3/9/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_2/9/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_29/8/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_28/8/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 0 | 0 | [5 empty] | VFS1065509 | 30022142 | 1.Provisioning | AM |  | 2024-08-28 | 2024-08-28 |  | 0 | [11 empty] | 0
1873 | 667787 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Ditchling Post Office | Hassocks | BN6 8TT | 2024-08-29 | 29/8/2024:Order Completed _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 29/8/2024:Order Completed _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065507 | 30022048 | 2.Commissioning | AM |  | 2024-08-28 | 2024-08-28 |  | 0 | [11 empty] | 0
1874 | 475681 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Castle News | Kidwelly | SA17 4UU | 2024-08-29 | 29/8/2024:Order Completed _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 29/8/2024:Order Completed _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065505 | 30022120 | 2.Commissioning | AM |  | 2024-08-28 | 2024-08-28 |  | 0 | [11 empty] | 0
1875 | 645420 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Nisa Local | Doncaster | DN10 6JE |  | 6/9/2024:#Update Retailer confirmed 23/09, AM. _x000D_5/9/2024:#Update Retailer confirmed 23/09, AM. _x000D_4/9/2024:#Update Retailer confirmed 23/09, AM. _x000D_3/9/2024:#Update Retailer confirmed 23/09, AM. _x000D_2/9/2024:#Update Retailer confirmed 23/09, AM. _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:#Update Retailer confirmed 23/09, AM. _x000D_6/9/2024:#Update Retailer confirmed 23/09, AM. _x000D_5/9/2024:#Update Retailer confirmed 23/09, AM. _x000D_4/9/2024:#Update Retailer confirmed 23/09, AM. _x000D_3/9/2024:#Update Retailer confirmed 23/09, AM. _x000D_2/9/2024:#Update Retailer confirmed 23/09, AM. _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | Update: Order Amended | #Update Retailer confirmed 23/09, AM. | [5 empty] | VFS1065504 | 30022159 | 1.Provisioning | AM |  | 2024-08-29 | 2024-08-29 |  | 0 | [11 empty] | 0
1876 | 655869 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Mc Geough's | Newry | BT35 8HU | 2024-08-30 | 2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 02/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_5/8/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 02/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_2/8/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 02/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_1/8/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 02/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_31/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_31/7/2024:37743 _x000D_30/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 02/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_5/8/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 02/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_2/8/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 02/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_1/8/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 02/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_31/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_31/7/2024:37743 _x000D_30/7/2024:Your order has been delayed due to a supplier system delay which is preventing us from progressing your order. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointm _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065501 | 30022088 | 2.Commissioning | AM |  | 2024-08-29 | 2024-08-29 |  | 0 | [11 empty] | 0
1877 | 638054 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Grimsby Telegraph Glens | Lincolnshire | DN37 7AA | 2024-08-30 | 2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065502 | 30022098 | 2.Commissioning | AM |  | 2024-08-29 | 2024-08-29 |  | 0 | [11 empty] | 0
1878 | 477035 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Gulf | Doune | FK16 6AY | 2024-08-30 | 2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065661 | 30022116 | 2.Commissioning | AM |  | 2024-08-29 | 2024-08-29 |  | 0 | [11 empty] | 0
1879 | 667407 |  | Batch 6 Aug 24 | Type 2 | SoGEA | North Petherton Post Office | Bridgewater | TA6 6SB | 2024-08-30 | 2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065662 | 30022118 | 2.Commissioning | AM |  | 2024-08-29 | 2024-08-29 |  | 0 | [11 empty] | 0
1880 | 662723 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Arlesey Village Store | Arlesey | SG15 6TD | 2024-08-30 | 2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065659 | 30022093 | 2.Commissioning | AM |  | 2024-08-29 | 2024-08-29 |  | 0 | [11 empty] | 0
1881 | 486816 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Llwyn Ifor Stores | Wrexham | LL11 5SY |  | 6/9/2024:Supplier Delay: Unable to complete work please await for further details CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/9/2024:Supplier Delay: Unable to complete work please await for further details CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/9/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 06/09/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 13/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_15/8/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 13/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_14/8/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 13/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_13/8/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 13/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_12/8/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 13/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_9/8/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 13/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_8/8/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 09/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_6/8/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 09/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_5/8/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. We have confirmed with end user that a second line is required to progress the order further. Please review back on 06/08/2024. CSL Note: Inval _x000D_2/8/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. We have confirmed with end user that a second line is required to progress the order further. Please review back on 06/08/2024. CSL Note: Inval _x000D_1/8/2024:Your order has been delayed. LinePlant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 02/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointmen _x000D_31/7/2024:Your order has been delayed. LinePlant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 02/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointmen _x000D_31/7/2024:37894 _x000D_30/7/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:29/07/2024 09:19 _x000D_26/7/2024:25/07/2024 20:27 _x000D_ | 9/9/2024:Supplier Delay: Unable to complete work please await for further details CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_6/9/2024:Supplier Delay: Unable to complete work please await for further details CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_5/9/2024:Supplier Delay: Unable to complete work please await for further details CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_4/9/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 06/09/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 13/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_15/8/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 13/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_14/8/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 13/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_13/8/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 13/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_12/8/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 13/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_9/8/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 13/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_8/8/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 09/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_6/8/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 09/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_5/8/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. We have confirmed with end user that a second line is required to progress the order further. Please review back on 06/08/2024. CSL Note: Inval _x000D_2/8/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. We have confirmed with end user that a second line is required to progress the order further. Please review back on 06/08/2024. CSL Note: Inval _x000D_1/8/2024:Your order has been delayed. LinePlant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 02/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointmen _x000D_31/7/2024:Your order has been delayed. LinePlant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 02/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointmen _x000D_31/7/2024:37894 _x000D_30/7/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 01/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_29/7/2024:29/07/2024 09:19 _x000D_26/7/2024:25/07/2024 20:27 _x000D_ | Supplier Delay: Unable to complete work please await for further details CSL Note: Invalid appointment slot received CSL Note: Invalid data received | 0 | [5 empty] | VFS1065660 | 30022044 | 1.Provisioning | AM |  | 2024-08-29 |  |  | 0 | [11 empty] | 0
1882 | 665724 |  | Batch 6 Aug 24 | Type 2 | SOGEA | The Village Shop | Somerset | TA24 7BF |  | 0 | 0 | [7 empty] | Duplicate Order | Duplicate Order | 1.Provisioning | [17 empty] | 0
1883 | 664551 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Welland PO | Malvern | WR13 6LA | 2024-08-30 | 2/9/2024:Order Completed _x000D_29/8/2024:Update: Order Completed by Supplier _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 2/9/2024:Order Completed _x000D_29/8/2024:Update: Order Completed by Supplier _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065657 | 30022135 | 2.Commissioning | AM |  | 2024-08-29 | 2024-08-29 |  | 0 | [11 empty] | 0
1884 | 665706 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Terling Stores | Chelmsford | CM3 2PG |  | 6/9/2024:#Update - NFA - Allwyn confirmed new installation date 17/09 - PM with retailer _x000D_5/9/2024:#Update - NFA - Allwyn confirmed new installation date 17/09 - PM with retailer _x000D_4/9/2024:#Update - NFA - Allwyn confirmed new installation date 17/09 - PM with retailer _x000D_3/9/2024:#Update - NFA - Allwyn confirmed new installation date 17/09 - PM with retailer _x000D_2/9/2024:#Update - NFA - Allwyn confirmed new installation date 17/09 - PM with retailer _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:#Update - NFA - Allwyn confirmed new installation date 17/09 - PM with retailer _x000D_6/9/2024:#Update - NFA - Allwyn confirmed new installation date 17/09 - PM with retailer _x000D_5/9/2024:#Update - NFA - Allwyn confirmed new installation date 17/09 - PM with retailer _x000D_4/9/2024:#Update - NFA - Allwyn confirmed new installation date 17/09 - PM with retailer _x000D_3/9/2024:#Update - NFA - Allwyn confirmed new installation date 17/09 - PM with retailer _x000D_2/9/2024:#Update - NFA - Allwyn confirmed new installation date 17/09 - PM with retailer _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | Your order has been delayed due to our suppliers being unable to complete the job in required time frame.Now order got re-appointed for 17/09/2024. | #Update - NFA - Allwyn confirmed new installation date 17/09 - PM with retailer | [5 empty] | VFS1065658 | 30021971 | 1.Provisioning | AM |  | 2024-08-29 | 2024-08-29 |  | 0 | [11 empty] | 0
1885 | 665703 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Mileham Village Store | Kings Lynn | PE32 2PS | 2024-08-30 | 2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065656 | 30022029 | 2.Commissioning | AM |  | 2024-08-29 | 2024-08-29 |  | 0 | [11 empty] | 0
1886 | 665702 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Middleton Post Office | Driffield | YO25 9UA |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 02/09/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_27/8/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 02/09/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_22/8/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 02/09/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 27/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_14/8/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 27/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_13/8/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 27/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_12/8/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 27/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_9/8/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 27/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_8/8/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 09/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_6/8/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 07/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_5/8/2024:Your order has been delayed due to sales query raised by our suppliers. Incorrect Product . Please check with end user and confirm the correct Product. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_2/8/2024:Your order has been delayed due to sales query raised by our suppliers. Incorrect Product . Please check with end user and confirm the correct Product. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_1/8/2024:Your order has been delayed due to sales query raised by our suppliers. Incorrect Product . Please check with end user and confirm the correct Product. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:Your order has been delayed due to sales query raised by our suppliers. Incorrect Product . Please check with end user and confirm the correct Product. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:37895 _x000D_30/7/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. We have confirmed with end user that a second line is required to progress the order further. Please review back on 01/08/2024. CSL Note: Inval _x000D_29/7/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. We have confirmed with end user that a second line is required to progress the order further. Please review back on 01/08/2024. CSL Note: Inval _x000D_29/7/2024:26/07/2024 16:15 _x000D_26/7/2024:25/07/2024 20:28 _x000D_ | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 02/09/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_27/8/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 02/09/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_22/8/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 02/09/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 27/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_14/8/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 27/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_13/8/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 27/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_12/8/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 27/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_9/8/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 27/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_8/8/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 09/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_6/8/2024:Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 07/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment _x000D_5/8/2024:Your order has been delayed due to sales query raised by our suppliers. Incorrect Product . Please check with end user and confirm the correct Product. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_2/8/2024:Your order has been delayed due to sales query raised by our suppliers. Incorrect Product . Please check with end user and confirm the correct Product. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_1/8/2024:Your order has been delayed due to sales query raised by our suppliers. Incorrect Product . Please check with end user and confirm the correct Product. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:Your order has been delayed due to sales query raised by our suppliers. Incorrect Product . Please check with end user and confirm the correct Product. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_31/7/2024:37895 _x000D_30/7/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. We have confirmed with end user that a second line is required to progress the order further. Please review back on 01/08/2024. CSL Note: Inval _x000D_29/7/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. We have confirmed with end user that a second line is required to progress the order further. Please review back on 01/08/2024. CSL Note: Inval _x000D_29/7/2024:26/07/2024 16:15 _x000D_26/7/2024:25/07/2024 20:28 _x000D_ | 0 | 0 | [5 empty] | VFS1065653 | 30022100 | 1.Provisioning | AM |  | 2024-08-29 |  |  | 0 | [11 empty] | 0
1887 | 665700 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Great Wilbraham | Cambridge | CB21 5JG |  | 6/9/2024:#Update - unsuccessful installation - no line plant within 3m of lottery machine, upgrade required, waiting for Openreach scope of work _x000D_5/9/2024:#Update - unsuccessful installation - no line plant within 3m of lottery machine, upgrade required, waiting for Openreach scope of work _x000D_4/9/2024:#Update - unsuccessful installation - no line plant within 3m of lottery machine, upgrade required, waiting for Openreach scope of work _x000D_3/9/2024:#Update - unsuccessful installation - no line plant within 3m of lottery machine, upgrade required, waiting for Openreach scope of work _x000D_2/9/2024:#Update - unsuccessful installation - no line plant within 3m of lottery machine, upgrade required, waiting for Openreach scope of work _x000D_29/8/2024:#Update - unsuccessful installation - no line plant within 3m of lottery machine, upgrade required, waiting for Openreach scope of work _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:#Update - unsuccessful installation - no line plant within 3m of lottery machine, upgrade required, waiting for Openreach scope of work _x000D_6/9/2024:#Update - unsuccessful installation - no line plant within 3m of lottery machine, upgrade required, waiting for Openreach scope of work _x000D_5/9/2024:#Update - unsuccessful installation - no line plant within 3m of lottery machine, upgrade required, waiting for Openreach scope of work _x000D_4/9/2024:#Update - unsuccessful installation - no line plant within 3m of lottery machine, upgrade required, waiting for Openreach scope of work _x000D_3/9/2024:#Update - unsuccessful installation - no line plant within 3m of lottery machine, upgrade required, waiting for Openreach scope of work _x000D_2/9/2024:#Update - unsuccessful installation - no line plant within 3m of lottery machine, upgrade required, waiting for Openreach scope of work _x000D_29/8/2024:#Update - unsuccessful installation - no line plant within 3m of lottery machine, upgrade required, waiting for Openreach scope of work _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. | #Update - unsuccessful installation - no line plant within 3m of lottery machine, upgrade required, waiting for Openreach scope of work | [5 empty] | VFS1065655 | 30022167 | 1.Provisioning | AM |  | 2024-08-29 | 2024-08-29 |  | 0 | [11 empty] | 0
1888 | 664548 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Scorton Village Store & Post Office | Richmond | DL10 6DH | 2024-08-30 | 2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065654 | 30022128 | 2.Commissioning | AM |  | 2024-08-29 | 2024-08-29 |  | 0 | [11 empty] | 0
1889 | 666317 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Bunessan Post Office | Isle Of Mull | PA67 6DG |  | 6/9/2024:Your order has been delayed due to a customer missed appointment. Incorrect Address Please check with end user and reappoint the order if still required. _x000D_5/9/2024:Your order has been delayed due to a customer missed appointment. Incorrect Address Please check with end user and reappoint the order if still required. _x000D_4/9/2024:Your order has been delayed due to a customer missed appointment. Incorrect Address Please check with end user and reappoint the order if still required. _x000D_3/9/2024:Your order has been delayed due to a customer missed appointment. Incorrect Address Please check with end user and reappoint the order if still required. _x000D_2/9/2024:Your order has been delayed due to a customer missed appointment. Incorrect Address Please check with end user and reappoint the order if still required. _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:Your order has been delayed due to a customer missed appointment. Incorrect Address Please check with end user and reappoint the order if still required. _x000D_6/9/2024:Your order has been delayed due to a customer missed appointment. Incorrect Address Please check with end user and reappoint the order if still required. _x000D_5/9/2024:Your order has been delayed due to a customer missed appointment. Incorrect Address Please check with end user and reappoint the order if still required. _x000D_4/9/2024:Your order has been delayed due to a customer missed appointment. Incorrect Address Please check with end user and reappoint the order if still required. _x000D_3/9/2024:Your order has been delayed due to a customer missed appointment. Incorrect Address Please check with end user and reappoint the order if still required. _x000D_2/9/2024:Your order has been delayed due to a customer missed appointment. Incorrect Address Please check with end user and reappoint the order if still required. _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | Your order has been delayed due to a customer missed appointment. Incorrect Address Please check with end user and reappoint the order if still required. | 0 | [5 empty] | VFS1083659 | 30022117 | 1.Provisioning | AM |  | 2024-08-29 | 2024-08-29 |  | 0 | [11 empty] | 0
1890 | 666514 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Blairhall Mini Market | Dunfermline | KY12 9PS | 2024-08-30 | 2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065651 | 30022000 | 2.Commissioning | AM |  | 2024-08-29 | 2024-08-29 |  | 0 | [11 empty] | 0
1891 | 661151 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Mace Middletown | Middletown | BT60 4JF | 2024-08-30 | 2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065650 | 30022070 | 2.Commissioning | AM |  | 2024-08-29 | 2024-08-29 |  | 0 | [11 empty] | 0
1892 | 477395 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Ellesmere stores | Shetland | ZE1 0LL | 2024-08-30 | 2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065649 | 30022086 | 2.Commissioning | AM |  | 2024-08-29 | 2024-08-29 |  | 0 | [11 empty] | 0
1893 | 472393 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Gleaner Londis | Aberlour | AB38 9TB |  | 6/9/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 10/09/2024. We will continue to provide update as they become available. _x000D_5/9/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 10/09/2024. We will continue to provide update as they become available. _x000D_4/9/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 10/09/2024. We will continue to provide update as they become available. _x000D_3/9/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 10/09/2024. We will continue to provide update as they become available. _x000D_2/9/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 10/09/2024. We will continue to provide update as they become available. _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 10/09/2024. We will continue to provide update as they become available. _x000D_6/9/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 10/09/2024. We will continue to provide update as they become available. _x000D_5/9/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 10/09/2024. We will continue to provide update as they become available. _x000D_4/9/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 10/09/2024. We will continue to provide update as they become available. _x000D_3/9/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 10/09/2024. We will continue to provide update as they become available. _x000D_2/9/2024:Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 10/09/2024. We will continue to provide update as they become available. _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | Your order has been delayed. Traffic management work required. Our Suppliers have given us a review date of 10/09/2024. We will continue to provide update as they become available. | 0 | [5 empty] | VFS1065648 | 30022103 | 1.Provisioning | AM |  | 2024-08-29 | 2024-08-29 |  | 0 | [11 empty] | 0
1894 | 664533 |  | Batch 6 Aug 24 | Type 2 | SoGEA | West Tanfield Village Shop & PO | Ripon | HG4 5JU |  | 6/9/2024:#Update Network Planning issue, please await for further details. _x000D_5/9/2024:#Update Network Planning issue, please await for further details. _x000D_4/9/2024:#Update Network Planning issue, please await for further details. _x000D_3/9/2024:#Update Network Planning issue, please await for further details. _x000D_2/9/2024:#Update Network Planning issue, please await for further details. _x000D_29/8/2024:#Update Network Planning issue, please await for further details. _x000D_28/8/2024:#Update Network Planning issue, please await for further details. _x000D_27/8/2024:#Update Network Planning issue, please await for further details. _x000D_22/8/2024:#Update Network Planning issue, please await for further details. _x000D_21/8/2024:#Update Network Planning issue, please await for further details. _x000D_20/8/2024:#Update Network Planning issue, please await for further details. _x000D_19/8/2024:#Update Network Planning issue, please await for further details. _x000D_19/8/2024:01535290 _x000D_16/8/2024:#Update Network Planning issue, please await for further details. _x000D_15/8/2024:#Update Network Planning issue, please await for further details. _x000D_14/8/2024:#Update Network Planning issue, please await for further details. _x000D_13/8/2024:#Update Network Planning issue, please await for further details. _x000D_12/8/2024:#Update Network Planning issue, please await for further details. _x000D_9/8/2024:#Update Network Planning issue, please await for further details. _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update Network Planning issue, please await for further details. _x000D_29/7/2024:#Update Network Planning issue, please await for further details. _x000D_29/7/2024:01535290 _x000D_26/7/2024:01535290 _x000D_ | 9/9/2024:#Update Network Planning issue, please await for further details. _x000D_6/9/2024:#Update Network Planning issue, please await for further details. _x000D_5/9/2024:#Update Network Planning issue, please await for further details. _x000D_4/9/2024:#Update Network Planning issue, please await for further details. _x000D_3/9/2024:#Update Network Planning issue, please await for further details. _x000D_2/9/2024:#Update Network Planning issue, please await for further details. _x000D_29/8/2024:#Update Network Planning issue, please await for further details. _x000D_28/8/2024:#Update Network Planning issue, please await for further details. _x000D_27/8/2024:#Update Network Planning issue, please await for further details. _x000D_22/8/2024:#Update Network Planning issue, please await for further details. _x000D_21/8/2024:#Update Network Planning issue, please await for further details. _x000D_20/8/2024:#Update Network Planning issue, please await for further details. _x000D_19/8/2024:#Update Network Planning issue, please await for further details. _x000D_19/8/2024:01535290 _x000D_16/8/2024:#Update Network Planning issue, please await for further details. _x000D_15/8/2024:#Update Network Planning issue, please await for further details. _x000D_14/8/2024:#Update Network Planning issue, please await for further details. _x000D_13/8/2024:#Update Network Planning issue, please await for further details. _x000D_12/8/2024:#Update Network Planning issue, please await for further details. _x000D_9/8/2024:#Update Network Planning issue, please await for further details. _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update Network Planning issue, please await for further details. _x000D_29/7/2024:#Update Network Planning issue, please await for further details. _x000D_29/7/2024:01535290 _x000D_26/7/2024:01535290 _x000D_ | 0 | #Update Network Planning issue, please await for further details. | [5 empty] | VFS1065647 | 30022145 | 1.Provisioning | AM |  | 2024-08-29 |  |  | 0 | [11 empty] | 0
1895 | 664532 |  | Batch 6 Aug 24 | Type 2 | SoGEA | St Weonards Village Store | Hereford | HR2 8NU | 2024-08-30 | 2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065646 | 30022168 | 2.Commissioning | AM |  | 2024-08-29 | 2024-08-29 |  | 0 | [11 empty] | 0
1896 | 665663 |  | Batch 6 Aug 24 | Type 2 | SoGEA | The Trading Post (Orkney) | Orkney | KW17 2SP | 2024-08-30 | 2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. We have confirmed with end user that a second line is required to progress the order further. Please review back on 30/07/2024. _x000D_1/8/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. We have confirmed with end user that a second line is required to progress the order further. Please review back on 30/07/2024. _x000D_31/7/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. We have confirmed with end user that a second line is required to progress the order further. Please review back on 30/07/2024. _x000D_31/7/2024:37620 _x000D_30/7/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. We have confirmed with end user that a second line is required to progress the order further. Please review back on 30/07/2024. _x000D_29/7/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. We have confirmed with end user that a second line is required to progress the order further. Please review back on 30/07/2024. _x000D_29/7/2024:26/07/2024 16:17 _x000D_26/7/2024:25/07/2024 20:24 _x000D_ | 2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. We have confirmed with end user that a second line is required to progress the order further. Please review back on 30/07/2024. _x000D_1/8/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. We have confirmed with end user that a second line is required to progress the order further. Please review back on 30/07/2024. _x000D_31/7/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. We have confirmed with end user that a second line is required to progress the order further. Please review back on 30/07/2024. _x000D_31/7/2024:37620 _x000D_30/7/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. We have confirmed with end user that a second line is required to progress the order further. Please review back on 30/07/2024. _x000D_29/7/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. We have confirmed with end user that a second line is required to progress the order further. Please review back on 30/07/2024. _x000D_29/7/2024:26/07/2024 16:17 _x000D_26/7/2024:25/07/2024 20:24 _x000D_ | [7 empty] | VFS1065643 | 30021963 | 2.Commissioning | AM |  | 2024-08-29 | 2024-08-29 |  | 0 | [11 empty] | 0
1897 | 665662 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Rougham Post Office & Stores | Bury St Edmunds | IP30 9LE | 2024-08-30 | 2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065644 | 30022170 | 2.Commissioning | AM |  | 2024-08-29 | 2024-08-29 |  | 0 | [11 empty] | 0
1898 | 644264 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Vivo Lissan | Cookstown | BT80 9XD | 2024-08-30 | 2/9/2024:Order Completed _x000D_29/8/2024:Update: Order Completed by Supplier _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 2/9/2024:Order Completed _x000D_29/8/2024:Update: Order Completed by Supplier _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065645 | 30022043 | 2.Commissioning | AM |  | 2024-08-29 | 2024-08-29 |  | 0 | [11 empty] | 0
1899 | 665659 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Chirbury Post Office & Store | Montgomery | SY15 6BH | 2024-08-30 | 2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065641 | 30022081 | 2.Commissioning | AM |  | 2024-08-29 | 2024-08-29 |  | 0 | [11 empty] | 0
1900 | 477557 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Spar | Omagh | BT79 9NF | 2024-08-30 | 2/9/2024:Order Completed _x000D_29/8/2024:Update: Order Completed by Supplier _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 2/9/2024:Order Completed _x000D_29/8/2024:Update: Order Completed by Supplier _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065642 | 30022052 | 2.Commissioning | AM |  | 2024-08-29 | 2024-08-29 |  | 0 | [11 empty] | 0
1901 | 475444 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Premier | Tenby | SA70 8LN | 2024-08-30 | 2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065639 | 30022133 | 2.Commissioning | AM |  | 2024-08-29 | 2024-08-29 |  | 0 | [11 empty] | 0
1902 | 477375 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Village Store | Sterling | FK8 3PN | 2024-08-30 | 2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065640 | 30021986 | 2.Commissioning | AM |  | 2024-08-29 | 2024-08-29 |  | 0 | [11 empty] | 0
1903 | 669038 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Christian Malford Post Office | Chippenham | SN15 4BG | 2024-08-30 | 2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065637 | 30022074 | 2.Commissioning | AM |  | 2024-08-29 | 2024-08-29 |  | 0 | [11 empty] | 0
1904 | 476793 |  | Batch 6 Aug 24 | Type 2 | SoGEA | The Dairy | Coleford | GL16 7AG | 2024-09-02 | 3/9/2024:Order Completed _x000D_2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 3/9/2024:Order Completed _x000D_2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065636 | 30021997 | 2.Commissioning | AM |  | 2024-08-30 | 2024-08-30 |  | 0 | [11 empty] | 0
1905 | 472781 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Manifold Stores | Stoke on Trent | ST10 3JS |  | 6/9/2024:#Update Upgrade costs sent to VF for approval. _x000D_5/9/2024:#Update Upgrade costs sent to VF for approval. _x000D_4/9/2024:#Update Upgrade costs sent to VF for approval. _x000D_3/9/2024:#Update Upgrade costs sent to VF for approval. _x000D_2/9/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:#Update Upgrade costs sent to VF for approval. _x000D_6/9/2024:#Update Upgrade costs sent to VF for approval. _x000D_5/9/2024:#Update Upgrade costs sent to VF for approval. _x000D_4/9/2024:#Update Upgrade costs sent to VF for approval. _x000D_3/9/2024:#Update Upgrade costs sent to VF for approval. _x000D_2/9/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | Your order has been delayed due to a customer missed appointment. Incorrect Product Please check with end user and reappoint the order if still required. | #Update Upgrade costs sent to VF for approval. | [5 empty] | VFS1065635 | 30022001 | 1.Provisioning | AM |  | 2024-08-30 | 2024-08-30 |  | 0 | [11 empty] | 0
1906 | 478223 |  | Batch 6 Aug 24 | Type 2 | SOGEA | Ingham Village Minimarket | Lincoln | LN1 2XT |  | 0 | 0 | [7 empty] | Address query | Address query | 1.Provisioning | [17 empty] | 0
1907 | 669031 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Hilton Post Office | Huntingdon | PE28 9NG | 2024-09-02 | 3/9/2024:Order Completed _x000D_2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 3/9/2024:Order Completed _x000D_2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065631 | 30022126 | 2.Commissioning | AM |  | 2024-08-30 | 2024-08-30 |  | 0 | [11 empty] | 0
1908 | 473109 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Delamere Stores | Northwich | CW8 2HU | 2024-09-02 | 3/9/2024:Order Completed _x000D_2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 3/9/2024:Order Completed _x000D_2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065632 | 30022136 | 2.Commissioning | AM |  | 2024-08-30 | 2024-08-30 |  | 0 | [11 empty] | 0
1909 | 478854 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Lifestyle Express | Abergele | LL22 8AW | 2024-09-03 | 6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:Order Completed _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 15-08-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/8/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 15-08-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/8/2024:13/08/2024 14:39 _x000D_16/8/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 15-08-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/8/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 15-08-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_14/8/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 15-08-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_0 | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:Order Completed _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 15-08-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/8/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 15-08-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/8/2024:13/08/2024 14:39 _x000D_16/8/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 15-08-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/8/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 15-08-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_14/8/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 15-08-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_0 | Order Completed | 0 | [5 empty] | VFS1083068 | Silver Address Issue | 2.Commissioning | AM |  | 2024-09-02 | 2024-09-02 |  | 0 | [11 empty] | 0
1910 | 667776 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Enham Post Office & Stores | Andover | SP11 6HH |  | 6/9/2024:#Update - installation unsuccessful, loft space where joint is hazardous for engineer to work in - ECC raised for a site survey to investigate alternative other route 03/09 _x000D_5/9/2024:#Update - installation unsuccessful, loft space where joint is hazardous for engineer to work in - ECC raised for a site survey to investigate alternative other route 03/09 _x000D_4/9/2024:#Update - installation unsuccessful, loft space where joint is hazardous for engineer to work in - ECC raised for a site survey to investigate alternative other route 03/09 _x000D_3/9/2024:#Update - installation incomplete, Engineer unable to access Beyond the DP. Openreach to advise next steps and we will progress order accordingly _x000D_2/9/2024:#Update - installation incomplete, Engineer unable to access Beyond the DP. Openreach to advise next steps and we will progress order accordingly _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:#Update - installation unsuccessful, loft space where joint is hazardous for engineer to work in - ECC raised for a site survey to investigate alternative other route 03/09 _x000D_6/9/2024:#Update - installation unsuccessful, loft space where joint is hazardous for engineer to work in - ECC raised for a site survey to investigate alternative other route 03/09 _x000D_5/9/2024:#Update - installation unsuccessful, loft space where joint is hazardous for engineer to work in - ECC raised for a site survey to investigate alternative other route 03/09 _x000D_4/9/2024:#Update - installation unsuccessful, loft space where joint is hazardous for engineer to work in - ECC raised for a site survey to investigate alternative other route 03/09 _x000D_3/9/2024:#Update - installation incomplete, Engineer unable to access Beyond the DP. Openreach to advise next steps and we will progress order accordingly _x000D_2/9/2024:#Update - installation incomplete, Engineer unable to access Beyond the DP. Openreach to advise next steps and we will progress order accordingly _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | Your order has been delayed by our Suppliers due to unable to access distribution point within customer premises. Please check with end user and re-appoint order once access arranged. | #Update - installation unsuccessful, loft space where joint is hazardous for engineer to work in - ECC raised for a site survey to investigate alternative other route 03/09 | [5 empty] | VFS1065633 | 30022132 | 1.Provisioning | AM |  | 2024-08-30 | 2024-08-30 |  | 0 | [11 empty] | 0
1911 | 664492 |  | Batch 6 Aug 24 | Type 2 | SoGEA | McKays Mini Market Ltd | Buckie | AB56 4LN | 2024-09-02 | 3/9/2024:Order Completed _x000D_2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 3/9/2024:Order Completed _x000D_2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065500 | 30022033 | 2.Commissioning | AM |  | 2024-08-30 | 2024-08-30 |  | 0 | [11 empty] | 0
1912 | 468747 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Strachans | Aboyne | AB34 5HT |  | 6/9/2024:#Update Network Planning issues. Please await for further updates _x000D_5/9/2024:#Update Network Planning issues. Please await for further updates _x000D_4/9/2024:#Update Network Planning issues. Please await for further updates _x000D_3/9/2024:#Update Network Planning issues. Please await for further updates _x000D_2/9/2024:#Update Network Planning issues. Please await for further updates _x000D_29/8/2024:#Update Network Planning issues. Please await for further updates _x000D_28/8/2024:#Update Network Planning issues. Please await for further updates _x000D_27/8/2024:#Update Network Planning issues. Please await for further updates _x000D_22/8/2024:#Update Network Planning issues. Please await for further updates _x000D_21/8/2024:#Update Network Planning issues. Please await for further updates _x000D_20/8/2024:#Update Network Planning issues. Please await for further updates _x000D_19/8/2024:#Update Network Planning issues. Please await for further updates _x000D_19/8/2024:01534490 _x000D_16/8/2024:#Update Network Planning issues. Please await for further updates _x000D_15/8/2024:#Update Network Planning issues. Please await for further updates _x000D_14/8/2024:#Update Network Planning issues. Please await for further updates _x000D_13/8/2024:#Update Network Planning issues. Please await for further updates _x000D_12/8/2024:#Update Network Planning issues. Please await for further updates _x000D_9/8/2024:#Update Network Planning issues. Please await for further updates _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update Network Planning issues. Please await for further updates _x000D_29/7/2024:#Update Network Planning issues. Please await for further updates _x000D_29/7/2024:01534490 _x000D_26/7/2024:26/07/2024 00:15 _x000D_ | 9/9/2024:#Update Network Planning issues. Please await for further updates _x000D_6/9/2024:#Update Network Planning issues. Please await for further updates _x000D_5/9/2024:#Update Network Planning issues. Please await for further updates _x000D_4/9/2024:#Update Network Planning issues. Please await for further updates _x000D_3/9/2024:#Update Network Planning issues. Please await for further updates _x000D_2/9/2024:#Update Network Planning issues. Please await for further updates _x000D_29/8/2024:#Update Network Planning issues. Please await for further updates _x000D_28/8/2024:#Update Network Planning issues. Please await for further updates _x000D_27/8/2024:#Update Network Planning issues. Please await for further updates _x000D_22/8/2024:#Update Network Planning issues. Please await for further updates _x000D_21/8/2024:#Update Network Planning issues. Please await for further updates _x000D_20/8/2024:#Update Network Planning issues. Please await for further updates _x000D_19/8/2024:#Update Network Planning issues. Please await for further updates _x000D_19/8/2024:01534490 _x000D_16/8/2024:#Update Network Planning issues. Please await for further updates _x000D_15/8/2024:#Update Network Planning issues. Please await for further updates _x000D_14/8/2024:#Update Network Planning issues. Please await for further updates _x000D_13/8/2024:#Update Network Planning issues. Please await for further updates _x000D_12/8/2024:#Update Network Planning issues. Please await for further updates _x000D_9/8/2024:#Update Network Planning issues. Please await for further updates _x000D_8/8/2024:26/07/2024 _x000D_6/8/2024:26/07/2024 _x000D_5/8/2024:26/07/2024 _x000D_2/8/2024:26/07/2024 _x000D_1/8/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_31/7/2024:26/07/2024 _x000D_30/7/2024:#Update Network Planning issues. Please await for further updates _x000D_29/7/2024:#Update Network Planning issues. Please await for further updates _x000D_29/7/2024:01534490 _x000D_26/7/2024:26/07/2024 00:15 _x000D_ | Your order has come off a waiters list and will now be fulfilled. | #Update Network Planning issues. Please await for further updates | [5 empty] | VFS1065499 | 30021975 | 1.Provisioning | AM |  | 2024-08-30 |  |  | 0 | [11 empty] | 0
1913 | 467617 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Scoops | Weston-super-Mare | BS23 1SE |  | 6/9/2024:#Update Retailer confirmed 25/09, AM. _x000D_5/9/2024:#Update Retailer confirmed 25/09, AM. _x000D_4/9/2024:#Update Retailer confirmed 25/09, AM. _x000D_3/9/2024:#Update Retailer unaware, reappointed for 25/09, AM. Action on Allwyn - ensure the retailer is aware. _x000D_2/9/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:#Update Retailer confirmed 25/09, AM. _x000D_6/9/2024:#Update Retailer confirmed 25/09, AM. _x000D_5/9/2024:#Update Retailer confirmed 25/09, AM. _x000D_4/9/2024:#Update Retailer confirmed 25/09, AM. _x000D_3/9/2024:#Update Retailer unaware, reappointed for 25/09, AM. Action on Allwyn - ensure the retailer is aware. _x000D_2/9/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | Update: Order Amended | #Update Retailer confirmed 25/09, AM. | [5 empty] | VFS1065497 | 30022080 | 1.Provisioning | AM |  | 2024-08-30 | 2024-08-30 |  | 0 | [11 empty] | 0
1914 | 649904 |  | Batch 6 Aug 24 | Type 2 | FTTP | Red Orange | Norwich | NR5 8AD | 2024-09-02 | 3/9/2024:Order Completed _x000D_2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 3/9/2024:Order Completed _x000D_2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFP2431171 | 30022013 | 2.Commissioning | AM |  | 2024-08-30 | 2024-08-30 |  | 0 | [11 empty] | 0
1915 | 661302 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Springfields S/Stn | Spalding | PE12 6JP | 2024-09-02 | 3/9/2024:Order Completed _x000D_2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 3/9/2024:Order Completed _x000D_2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065495 | 30022055 | 2.Commissioning | AM |  | 2024-08-30 | 2024-08-30 |  | 0 | [11 empty] | 0
1916 | 465841 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Tysoe Village Store | WARWICK | CV35 0SE | 2024-09-02 | 3/9/2024:Order Completed _x000D_2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 3/9/2024:Order Completed _x000D_2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065496 | 30021983 | 2.Commissioning | AM |  | 2024-08-30 | 2024-08-30 |  | 0 | [11 empty] | 0
1917 | 468837 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Patio's Convenience Store | MEXBOROUGH | S64 8SA |  | 6/9/2024:#Update Costs sent to VF for approval. The retailer has requested to have the installation take place on a Saturday as it is the most suitable day for them. _x000D_5/9/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_4/9/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_3/9/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_2/9/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:#Update Costs sent to VF for approval. The retailer has requested to have the installation take place on a Saturday as it is the most suitable day for them. _x000D_6/9/2024:#Update Costs sent to VF for approval. The retailer has requested to have the installation take place on a Saturday as it is the most suitable day for them. _x000D_5/9/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_4/9/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_3/9/2024:Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. _x000D_2/9/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | Your order has been delayed due to a customer missed appointment. Customer unaware of the appointment. Please check with end user and reappoint the order if still required. | #Update Costs sent to VF for approval. The retailer has requested to have the installation take place on a Saturday as it is the most suitable day for them. | [5 empty] | VFS1065494 | 30022157 | 1.Provisioning | AM |  | 2024-08-30 | 2024-08-30 |  | 0 | [11 empty] | 0
1918 | 461769 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Fiveways Convenience Store | ROTHERHAM | S66 7DN |  | 6/9/2024:#Update - NFA - Allwyn confirmed new installation date 18/09 AM with retailer _x000D_5/9/2024:#Update - NFA - Allwyn confirmed new installation date 18/09 AM with retailer _x000D_4/9/2024:#Update - NFA - Allwyn confirmed new installation date 18/09 AM with retailer _x000D_3/9/2024:#Update - NFA - Allwyn confirmed new installation date 18/09 AM with retailer _x000D_2/9/2024:#Update - installation unsuccessful, retailer unaware of appointment or works - rescheduled for 18/09, Allwyn to confirm with retailer _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:#Update - NFA - Allwyn confirmed new installation date 18/09 AM with retailer _x000D_6/9/2024:#Update - NFA - Allwyn confirmed new installation date 18/09 AM with retailer _x000D_5/9/2024:#Update - NFA - Allwyn confirmed new installation date 18/09 AM with retailer _x000D_4/9/2024:#Update - NFA - Allwyn confirmed new installation date 18/09 AM with retailer _x000D_3/9/2024:#Update - NFA - Allwyn confirmed new installation date 18/09 AM with retailer _x000D_2/9/2024:#Update - installation unsuccessful, retailer unaware of appointment or works - rescheduled for 18/09, Allwyn to confirm with retailer _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | Update: Order Amended | #Update - NFA - Allwyn confirmed new installation date 18/09 AM with retailer | [5 empty] | VFS1065492 | 30022131 | 1.Provisioning | AM |  | 2024-08-30 | 2024-08-30 |  | 0 | [11 empty] | 0
1919 | 483417 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Nisa | Newcastle Emlyn | SA38 9JP | 2024-09-02 | 3/9/2024:Order Completed _x000D_2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 3/9/2024:Order Completed _x000D_2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | [7 empty] | VFS1065491 | 30022005 | 2.Commissioning | AM |  | 2024-08-30 | 2024-08-30 |  | 0 | [11 empty] | 0
1920 | 671300 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Talybont Stores | Brecon | LD3 7YJ |  | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:0 _x000D_6/8/2024:0 _x000D_5/8/2024:0 _x000D_2/8/2024:0 _x000D_1/8/2024:0 _x000D_31/7/2024:0 _x000D_31/7/2024:0 _x000D_30/7/2024:0 _x000D_29/7/2024:0 _x000D_29/7/2024:0 _x000D_26/7/2024:0 _x000D_ | Update: Order Amended | 0 | [5 empty] | VFS1065490 | 30022082 | 1.Provisioning | AM |  | 2024-08-30 | 2024-08-30 |  | 0 | [11 empty] | 0
1921 | 668915 |  | Batch 6 Aug 24 | Type 2 | SoGEA | Laleston Post Office & Store | BRIDGEND | CF32 0HP | 2024-09-02 | 3/9/2024:Order Completed _x000D_2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Your order has been delayed. LinePlant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_6/8/2024:Your order has been delayed. LinePlant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_5/8/2024:Your order has been delayed. LinePlant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_2/8/2024:Your order has been delayed. LinePlant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_1/8/2024:Your order has been delayed. LinePlant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 02/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointme _x000D_31/7/2024:Your order has been delayed. LinePlant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 02/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointme _x000D_31/7/2024:37899 _x000D_30/7/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. We have confirmed with end user that a second line is required to progress the order further. Please review back on 01/08/2024. CSL Note: Inval _x000D_29/7/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. We have confirmed with end user that a second line is required to progress the order further. Please review back on 01/08/2024. CSL Note: Inval _x000D_29/7/2024:26/07/2024 16:27 _x000D_26/7/2024:25/07/2024 20:02 _x000D_ | 3/9/2024:Order Completed _x000D_2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_14/8/2024:0 _x000D_13/8/2024:0 _x000D_12/8/2024:0 _x000D_9/8/2024:0 _x000D_8/8/2024:Your order has been delayed. LinePlant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_6/8/2024:Your order has been delayed. LinePlant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_5/8/2024:Your order has been delayed. LinePlant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_2/8/2024:Your order has been delayed. LinePlant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 06/08/2024.We will continue to provide update as they become available. _x000D_1/8/2024:Your order has been delayed. LinePlant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 02/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointme _x000D_31/7/2024:Your order has been delayed. LinePlant records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 02/08/2024.We will continue to provide update as they become available. CSL Note: Invalid appointme _x000D_31/7/2024:37899 _x000D_30/7/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. We have confirmed with end user that a second line is required to progress the order further. Please review back on 01/08/2024. CSL Note: Inval _x000D_29/7/2024:Your order has been delayed due to a sales query raised by our supplier. There is an existing line at premises. We have confirmed with end user that a second line is required to progress the order further. Please review back on 01/08/2024. CSL Note: Inval _x000D_29/7/2024:26/07/2024 16:27 _x000D_26/7/2024:25/07/2024 20:02 _x000D_ | [7 empty] | VFS1065488 | 30022151 | 2.Commissioning | AM |  | 2024-08-30 | 2024-08-30 |  | 0 | [11 empty] | 0
1922 | 669726 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | CO-OP & PO CROOKHORN | WATERLOOVILLE | PO7 5QE | 2024-09-03 | 6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:Order Completed _x000D_2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:Order Completed _x000D_2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Order Completed | 0 | [5 empty] | VFS1076976 | 30022368 | 2.Commissioning | AM |  | 2024-09-02 | 2024-09-02 |  | 0 | [11 empty] | 0
1923 | 449794 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | THE CO-OPERATIVE | HAVANT | PO9 4AB | 2024-09-03 | 6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:Order Completed _x000D_2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:Order Completed _x000D_2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Order Completed | 0 | [5 empty] | VFS1076974 | 30022322 | 2.Commissioning | AM |  | 2024-09-02 | 2024-09-02 |  | 0 | [11 empty] | 0
1924 | 444457 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | THE CO-OPERATIVE | COWES | PO31 7EL | 2024-09-03 | 6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:Order Completed _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:Order Completed _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Order Completed | 0 | [5 empty] | VFS1076975 | 30022418 | 2.Commissioning | AM |  | 2024-09-02 | 2024-09-02 |  | 0 | [11 empty] | 0
1925 | 465159 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | The Co-operative | Portsmouth | PO2 9LU | 2024-09-03 | 6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:Order Completed _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:Order Completed _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Order Completed | 0 | [5 empty] | VFS1076973 | 30022293 | 2.Commissioning | AM |  | 2024-09-02 | 2024-09-02 |  | 0 | [11 empty] | 0
1926 | 251418 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | THE CO-OPERATIVE | NUNEATON | CV11 4LH | 2024-08-14 | 6/9/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. _x000D_5/9/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. _x000D_4/9/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. _x000D_3/9/2024:End User Missed appointment. Action required _x000D_2/9/2024:End User Missed appointment. Action required _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. _x000D_6/9/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. _x000D_5/9/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. _x000D_4/9/2024:Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. _x000D_3/9/2024:End User Missed appointment. Action required _x000D_2/9/2024:End User Missed appointment. Action required _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. | 0 | [5 empty] | VFS1076971 | 30022364 | 1.Provisioning | AM |  | 2024-09-02 | 2024-09-02 |  | 0 | [11 empty] | 0
1927 | 458212 |  | Batch 7 Sep 24 | Type 1 | FTTP/Mobile | THE CO-OPERATIVE | GOSPORT | PO13 0UR | 2024-09-03 | 6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:Order Completed _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:Order Completed _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Order Completed | 0 | [5 empty] | VFP2443438 | 30022325 | 2.Commissioning | AM |  | 2024-09-02 | 2024-09-02 |  | 0 | [11 empty] | 0
1928 | 462696 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | THE CO-OPERATIVE | Nuneaton | CV10 9FB | 2024-09-05 | 6/9/2024:#Update - Order has been delayed as the line plant records need to be updated by the supplier. CSL will update as more information become available. _x000D_5/9/2024:#Update - Order has been delayed as the line plant records need to be updated by the supplier. CSL will update as more information become available. _x000D_4/9/2024:#Update - Order has been delayed as the line plant records need to be updated by the supplier. CSL will update as more information become available. _x000D_3/9/2024:#Update - Order has been delayed as the line plant records need to be updated by the supplier. CSL will update as more information become available. _x000D_2/9/2024:#Update - Order has been delayed as the line plant records need to be updated by the supplier. CSL will update as more information become available. _x000D_29/8/2024:#Update - Order has been delayed as the line plant records need to be updated by the supplier. CSL will update as more information become available. _x000D_28/8/2024:#Update - Order has been delayed as the line plant records need to be updated by the supplier. CSL will update as more information become available. _x000D_27/8/2024:#Update - Order has been delayed as the line plant records need to be updated by the supplier. CSL will update as more information become available. _x000D_22/8/2024:#Update - Order has been delayed as the line plant records need to be updated by the supplier. CSL will update as more information become available. _x000D_21/8/2024:#Update - Order has been delayed as the line plant records need to be updated by the supplier. CSL will update as more information become available. _x000D_20/8/2024:#Update - Order has been delayed as the line plant records need to be updated by the supplier. CSL will update as more information become available. _x000D_19/8/2024:#Update - Order has been delayed as the line plant records need to be updated by the supplier. CSL will update as more information become available. _x000D_19/8/2024:01573843 _x000D_16/8/2024:#Update - Order has been delayed as the line plant records need to be updated by the supplier. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order has been delayed as the line plant records need to be updated by the supplier. CSL will update as more information become available. _x000D_0 | 9/9/2024:#Update - Order has been delayed as the line plant records need to be updated by the supplier. CSL will update as more information become available. _x000D_6/9/2024:#Update - Order has been delayed as the line plant records need to be updated by the supplier. CSL will update as more information become available. _x000D_5/9/2024:#Update - Order has been delayed as the line plant records need to be updated by the supplier. CSL will update as more information become available. _x000D_4/9/2024:#Update - Order has been delayed as the line plant records need to be updated by the supplier. CSL will update as more information become available. _x000D_3/9/2024:#Update - Order has been delayed as the line plant records need to be updated by the supplier. CSL will update as more information become available. _x000D_2/9/2024:#Update - Order has been delayed as the line plant records need to be updated by the supplier. CSL will update as more information become available. _x000D_29/8/2024:#Update - Order has been delayed as the line plant records need to be updated by the supplier. CSL will update as more information become available. _x000D_28/8/2024:#Update - Order has been delayed as the line plant records need to be updated by the supplier. CSL will update as more information become available. _x000D_27/8/2024:#Update - Order has been delayed as the line plant records need to be updated by the supplier. CSL will update as more information become available. _x000D_22/8/2024:#Update - Order has been delayed as the line plant records need to be updated by the supplier. CSL will update as more information become available. _x000D_21/8/2024:#Update - Order has been delayed as the line plant records need to be updated by the supplier. CSL will update as more information become available. _x000D_20/8/2024:#Update - Order has been delayed as the line plant records need to be updated by the supplier. CSL will update as more information become available. _x000D_19/8/2024:#Update - Order has been delayed as the line plant records need to be updated by the supplier. CSL will update as more information become available. _x000D_19/8/2024:01573843 _x000D_16/8/2024:#Update - Order has been delayed as the line plant records need to be updated by the supplier. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order has been delayed as the line plant records need to be updated by the supplier. CSL will update as more information become available. _x000D_0 | Order Completed | #Update - Order has been delayed as the line plant records need to be updated by the supplier. CSL will update as more information become available. | [5 empty] | VFS1076972 | 30022329 | 2.Commissioning | AM |  | 2024-09-02 |  |  | 0 | [11 empty] | 0
1929 | 670004 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | Tamworth PO & Co-op | Tamworth | B79 7DH | 2024-08-14 | 6/9/2024:Your order has been delayed. Engineer required access to the end user premises to complete further works . Please check with the end user and book a new appointment. _x000D_5/9/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_4/9/2024:Supplier Delay: Missed CCD and may require further work as the engineer has retained the job for next day 3/9/2024:Supplier Delay: Missed CCD and may require further work as the engineer has retained the job for next day 2/9/2024:0 29/8/2024:0 28/8/2024:0 27/8/2024:0 22/8/2024:0 21/8/2024:0 20/8/2024:0 19/8/2024:0 19/8/2024:0 16/8/2024:0 15/8/2024:0 0 | 9/9/2024:Your order has been delayed. Engineer required access to the end user premises to complete further works . Please check with the end user and book a new appointment. _x000D_6/9/2024:Your order has been delayed. Engineer required access to the end user premises to complete further works . Please check with the end user and book a new appointment. _x000D_5/9/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_4/9/2024:Supplier Delay: Missed CCD and may require further work as the engineer has retained the job for next day 3/9/2024:Supplier Delay: Missed CCD and may require further work as the engineer has retained the job for next day 2/9/2024:0 29/8/2024:0 28/8/2024:0 27/8/2024:0 22/8/2024:0 21/8/2024:0 20/8/2024:0 19/8/2024:0 19/8/2024:0 16/8/2024:0 15/8/2024:0 0 | Your order has been delayed. Engineer required access to the end user premises to complete further works . Please check with the end user and book a new appointment. | 0 | [5 empty] | VFS1076969 | 30022320 | 1.Provisioning | AM |  | 2024-09-02 | 2024-09-02 |  | 0 | [11 empty] | 0
1930 | 669854 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | Brixlington PO & Budgens | EXMOUTH | EX8 4JS | 2024-09-04 | 6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:Order Completed _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:Order Completed _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Order Completed | 0 | [5 empty] | VFS1076968 | 30022367 | 2.Commissioning | AM |  | 2024-09-03 | 2024-09-03 |  | 0 | [11 empty] | 0
1931 | 423972 |  | Batch 7 Sep 24 | Type 1 | FTTP/Mobile | THE CO-OPERATIVE | ALTON | GU34 1BD | 2024-08-14 | 6/9/2024:Your order has been delayed by our Suppliers due to a Flatroof skill being required to complete the installation. Our suppliers team will contact you to get the available date for installation. We will provide the further updates on 09/09/2024. _x000D_5/9/2024:Your order has been delayed by our Suppliers due to a Flatroof skill being required to complete the installation. Our suppliers team will contact you to get the available date for installation. We will provide the further updates on 09/09/2024. _x000D_4/9/2024:This is a delay message. We are currently unable to complete all engineering activities required to fulfil this order. Further indoor and outdoor work is required. End User presence will be required. _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Your order has been delayed by our Suppliers due to a Flatroof skill being required to complete the installation. Our suppliers team will contact you to get the available date for installation. We will provide the further updates on 09/09/2024. _x000D_6/9/2024:Your order has been delayed by our Suppliers due to a Flatroof skill being required to complete the installation. Our suppliers team will contact you to get the available date for installation. We will provide the further updates on 09/09/2024. _x000D_5/9/2024:Your order has been delayed by our Suppliers due to a Flatroof skill being required to complete the installation. Our suppliers team will contact you to get the available date for installation. We will provide the further updates on 09/09/2024. _x000D_4/9/2024:This is a delay message. We are currently unable to complete all engineering activities required to fulfil this order. Further indoor and outdoor work is required. End User presence will be required. _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Your order has been delayed by our Suppliers due to a Flatroof skill being required to complete the installation. Our suppliers team will contact you to get the available date for installation. We will provide the further updates on 09/09/2024. | 0 | [5 empty] | VFP2443436 | 30022387 | 1.Provisioning | AM |  | 2024-09-03 | 2024-09-03 |  | 0 | [11 empty] | 0
1932 | 413136 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | THE CO-OPERATIVE | Poole | BH17 7XP | 2024-09-04 | 6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:Order Completed _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:Order Completed _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Order Completed | 0 | [5 empty] | VFS1076967 | 30022402 | 2.Commissioning | AM |  | 2024-09-03 | 2024-09-03 |  | 0 | [11 empty] | 0
1933 | 669576 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | PO & CO-OP FLAKLAND COURT | EASTLEIGH | SO53 3GA | 2024-09-04 | 6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:Order Completed _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:Order Completed _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Order Completed | 0 | [5 empty] | VFS1076966 | 30022408 | 2.Commissioning | AM |  | 2024-09-03 | 2024-09-03 |  | 0 | [11 empty] | 0
1934 | 669638 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | CO-OP & PO SHANKLIN | SHANKLIN | PO37 7AA | 2024-09-04 | 6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:Order Completed _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:Order Completed _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Order Completed | 0 | [5 empty] | VFS1076964 | 30022309 | 2.Commissioning | AM |  | 2024-09-03 | 2024-09-03 |  | 0 | [11 empty] | 0
1935 | 456019 |  | Batch 7 Sep 24 | Type 1 | SOGEA | THE CO-OPERATIVE | PORTSMOUTH | PO2 8NR | 2024-08-14 | 6/9/2024:#Update - order delayed due to a supplier system delay. We will continue to provide update as they become available. _x000D_5/9/2024:#Update - order delayed due to a supplier system delay. We will continue to provide update as they become available. _x000D_4/9/2024:#Update - order delayed due to a supplier system delay. We will continue to provide update as they become available. _x000D_3/9/2024:#Update - order delayed due to a supplier system delay. We will continue to provide update as they become available. _x000D_2/9/2024:#Update - order delayed due to a supplier system delay. We will continue to provide update as they become available. _x000D_29/8/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 30-08-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_0 | 9/9/2024:#Update - order delayed due to a supplier system delay. We will continue to provide update as they become available. _x000D_6/9/2024:#Update - order delayed due to a supplier system delay. We will continue to provide update as they become available. _x000D_5/9/2024:#Update - order delayed due to a supplier system delay. We will continue to provide update as they become available. _x000D_4/9/2024:#Update - order delayed due to a supplier system delay. We will continue to provide update as they become available. _x000D_3/9/2024:#Update - order delayed due to a supplier system delay. We will continue to provide update as they become available. _x000D_2/9/2024:#Update - order delayed due to a supplier system delay. We will continue to provide update as they become available. _x000D_29/8/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 30-08-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_0 | 0 | #Update - order delayed due to a supplier system delay. We will continue to provide update as they become available. | [5 empty] | VFS1097771 |  | 1.Provisioning |  |  | 2024-09-19 | 2024-09-19 | [13 empty] | 0
1936 | 484955 |  | Batch 7 Sep 24 | Type 1 | FTTP/Mobile | Welcome | Worthing | BN13 2EL | 2024-09-04 | 6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Order Completed | 0 | [5 empty] | VFP2443434 | 30022302 | 2.Commissioning | AM |  | 2024-09-03 | 2024-09-03 |  | 0 | [11 empty] | 0
1937 | 469413 |  | Batch 7 Sep 24 | Type 1 | FTTP/Mobile | The Co-operative | Bournemouth | BH9 3LD | 2024-08-14 | 6/9/2024:Your order has been delayed due to a customer missed appointment. Out of Hour Appointment required. Please check with end user and reappoint the order if still required. _x000D_5/9/2024:Your order has been delayed due to a customer missed appointment. Out of Hour Appointment required. Please check with end user and reappoint the order if still required. _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Your order has been delayed due to a customer missed appointment. Out of Hour Appointment required. Please check with end user and reappoint the order if still required. _x000D_6/9/2024:Your order has been delayed due to a customer missed appointment. Out of Hour Appointment required. Please check with end user and reappoint the order if still required. _x000D_5/9/2024:Your order has been delayed due to a customer missed appointment. Out of Hour Appointment required. Please check with end user and reappoint the order if still required. _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Your order has been delayed due to a customer missed appointment. Out of Hour Appointment required. Please check with end user and reappoint the order if still required. | 0 | [5 empty] | VFP2443435 | 30022326 | 1.Provisioning | AM |  | 2024-09-03 | 2024-09-03 |  | 0 | [11 empty] | 0
1938 | 613009 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | Welcome Pan Stores | Isle of Wight | PO30 2HW | 2024-09-04 | 6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:Order Completed _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:Order Completed _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Order Completed | 0 | [5 empty] | VFS1076965 | 30022338 | 2.Commissioning | AM |  | 2024-09-03 | 2024-09-03 |  | 0 | [11 empty] | 0
1939 | 429852 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | THE CO-OPERATIVE | HAVANT | PO9 2JR | 2024-09-05 | 6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Order Completed | 0 | [5 empty] | VFS1076962 | 30022327 | 2.Commissioning | AM |  | 2024-09-04 | 2024-09-04 |  | 0 | [11 empty] | 0
1940 | 467944 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | Welcome | ADDLESTONE | KT15 1JH | 2024-08-14 | 6/9/2024:Your order has been delayed due to a customer missed appointment. Additional time related charges are not covered and Out of Office hour appointment required. Please check with end user and reappoint the order if still required. _x000D_5/9/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Your order has been delayed due to a customer missed appointment. Additional time related charges are not covered and Out of Office hour appointment required. Please check with end user and reappoint the order if still required. _x000D_6/9/2024:Your order has been delayed due to a customer missed appointment. Additional time related charges are not covered and Out of Office hour appointment required. Please check with end user and reappoint the order if still required. _x000D_5/9/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Your order has been delayed due to a customer missed appointment. Additional time related charges are not covered and Out of Office hour appointment required. Please check with end user and reappoint the order if still required. | 0 | [5 empty] | VFS1076961 | 30022407 | 1.Provisioning | AM |  | 2024-09-04 | 2024-09-04 |  | 0 | [11 empty] | 0
1941 | 607409 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | The Co-operative | Bournemouth | BH10 5JL | 2024-09-05 | 6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Order Completed | 0 | [5 empty] | VFS1076960 | 30022371 | 2.Commissioning | AM |  | 2024-09-04 | 2024-09-04 |  | 0 | [11 empty] | 0
1942 | 413134 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | THE CO-OPERATIVE | PORTSMOUTH | PO3 5EQ | 2024-09-05 | 6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Order Completed | 0 | [5 empty] | VFS1076959 | 30022363 | 2.Commissioning | AM |  | 2024-09-04 | 2024-09-04 |  | 0 | [11 empty] | 0
1943 | 619028 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | Co-Operative | Tamworth | B77 2AF | 2024-08-14 | 6/9/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_5/9/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_4/9/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_6/9/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_5/9/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_4/9/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Delay on Engineer activities. Wait for further update to confirm re-appointing | 0 | [5 empty] | VFS1076957 | 30022330 | 1.Provisioning | AM |  | 2024-09-04 | 2024-09-04 |  | 0 | [11 empty] | 0
1944 | 669844 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | SELSEY & CO-OP | CHICHESTER | PO20 0QB | 2024-09-05 | 6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Order Completed | 0 | [5 empty] | VFS1076958 | 30022360 | 2.Commissioning | AM |  | 2024-09-04 | 2024-09-04 |  | 0 | [11 empty] | 0
1945 | 435573 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | THE CO-OPERATIVE | Rugby | CV21 2HS | 2024-08-14 | 6/9/2024:#Update OR advised a survey would need to occur due to a complex installation. Details sent to Allwyn, Allwyn to advise. _x000D_5/9/2024:End User Missed appointment. Action required _x000D_4/9/2024:End User Missed appointment. Action required _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:#Update OR advised a survey would need to occur due to a complex installation. Details sent to Allwyn, Allwyn to advise. _x000D_6/9/2024:#Update OR advised a survey would need to occur due to a complex installation. Details sent to Allwyn, Allwyn to advise. _x000D_5/9/2024:End User Missed appointment. Action required _x000D_4/9/2024:End User Missed appointment. Action required _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Your order has been delayed due to a customer missed appointment. No access to the premises. Please check with end user and reappoint the order if still required. | #Update OR advised a survey would need to occur due to a complex installation. Details sent to Allwyn, Allwyn to advise. | [5 empty] | VFS1076955 | 30022432 | 1.Provisioning | AM |  | 2024-09-04 | 2024-09-04 |  | 0 | [11 empty] | 0
1946 | 455457 |  | Batch 7 Sep 24 | Type 1 | FTTP/Mobile | THE CO-OPERATIVE | BASINGSTOKE | RG22 6DJ | 2024-09-05 | 6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Order Completed | 0 | [5 empty] | VFP2443432 | 30022426 | 2.Commissioning | AM |  | 2024-09-04 | 2024-09-04 |  | 0 | [11 empty] | 0
1947 | 626942 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | Co-operative Food | Burnham-on-Sea | TA8 2JQ | 2024-09-05 | 6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Order Completed | 0 | [5 empty] | VFS1076954 | 30022316 | 2.Commissioning | AM |  | 2024-09-04 | 2024-09-04 |  | 0 | [11 empty] | 0
1948 | 481446 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | The Co-operative | Southam | CV47 0EA | 2024-08-14 | 6/9/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point within customer premise. Please check with end user and re-appoint order for earliest date. _x000D_5/9/2024:End User Missed appointment. Action required _x000D_4/9/2024:End User Missed appointment. Action required _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point within customer premise. Please check with end user and re-appoint order for earliest date. _x000D_6/9/2024:Your order has been delayed by our Suppliers as they were unable to access the distribution point within customer premise. Please check with end user and re-appoint order for earliest date. _x000D_5/9/2024:End User Missed appointment. Action required _x000D_4/9/2024:End User Missed appointment. Action required _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Your order has been delayed by our Suppliers as they were unable to access the distribution point within customer premise. Please check with end user and re-appoint order for earliest date. | 0 | [5 empty] | VFS1076953 | 30022422 | 1.Provisioning | AM |  | 2024-09-04 | 2024-09-04 |  | 0 | [11 empty] | 0
1949 | 466395 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | The Co-operative | Bognor Regis | PO21 2UR | 2024-08-14 | 6/9/2024:#Update - Action for Allwyn - Installation has now been amended to 09/10 AM. Please speak with the retailer regarding installation details and confirm to CSL if 09/10 is a suitable date. _x000D_5/9/2024:#Update - Action for Allwyn - Installation has now been amended to 09/10 AM. Please speak with the retailer regarding installation details and confirm to CSL if 09/10 is a suitable date. _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:#Update - Action for Allwyn - Installation has now been amended to 09/10 AM. Please speak with the retailer regarding installation details and confirm to CSL if 09/10 is a suitable date. _x000D_6/9/2024:#Update - Action for Allwyn - Installation has now been amended to 09/10 AM. Please speak with the retailer regarding installation details and confirm to CSL if 09/10 is a suitable date. _x000D_5/9/2024:#Update - Action for Allwyn - Installation has now been amended to 09/10 AM. Please speak with the retailer regarding installation details and confirm to CSL if 09/10 is a suitable date. _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Update: Order Amended | #Update - Action for Allwyn - Installation has now been amended to 09/10 AM. Please speak with the retailer regarding installation details and confirm to CSL if 09/10 is a suitable date. | [5 empty] | VFS1076952 | 30022305 | 1.Provisioning | AM |  | 2024-09-04 | 2024-09-04 |  | 0 | [11 empty] | 0
1950 | 487166 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | CO OP | Bristol | BS39 6TQ | 2024-09-05 | 6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:Update: Order Amended _x000D_0 | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:Update: Order Amended _x000D_0 | Order Completed | 0 | [5 empty] | VFS1076950 | 30022348 | 2.Commissioning | AM |  | 2024-09-04 | 2024-09-04 |  | 0 | [11 empty] | 0
1951 | 434205 |  | Batch 7 Sep 24 | Type 1 | FTTP/Mobile | THE CO-OPERATIVE | COVENTRY | CV4 9DU | 2024-09-05 | 6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Order Completed | 0 | [5 empty] | VFP2443433 | 30022374 | 2.Commissioning | AM |  | 2024-09-04 | 2024-09-04 |  | 0 | [11 empty] | 0
1952 | 483902 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | The Co-operative | Bristol | BS15 1BS | 2024-09-05 | 6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Order Completed | 0 | [5 empty] | VFS1076951 | 30022403 | 2.Commissioning | AM |  | 2024-09-04 | 2024-09-04 |  | 0 | [11 empty] | 0
1953 | 621915 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | Co-Operative Food | Frome | BA11 4LA | 2024-09-05 | 6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:Update: Order Amended _x000D_0 | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:Update: Order Amended _x000D_0 | Order Completed | 0 | [5 empty] | VFS1076949 | 30022358 | 2.Commissioning | AM |  | 2024-09-04 | 2024-09-04 |  | 0 | [11 empty] | 0
1954 | 669208 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | CO-OP & PO | SOUTHAMPTON | SO40 4SF | 2024-08-14 | 6/9/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_6/9/2024:Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Supplier Delay: Further work is required by Openreach to deliver the service, please await further details. | 0 | [5 empty] | VFS1076947 | 30022397 | 1.Provisioning | AM |  | 2024-09-05 | 2024-09-05 |  | 0 | [11 empty] | 0
1955 | 477628 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | The Co-operative | Radstock | BA3 4AX | 2024-09-05 | 6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Order Completed | 0 | [5 empty] | VFS1076948 | 30022351 | 2.Commissioning | AM |  | 2024-09-04 | 2024-09-04 |  | 0 | [11 empty] | 0
1956 | 435724 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | THE CO-OPERATIVE | HAYLING ISLAND | PO11 9EH | 2024-09-06 | 6/9/2024:#Update - Completed - Pole Date 05/09/2024 08:49 _x000D_5/9/2024:Openreach Delay : Automated testing has identified a potential fault _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:#Update - Completed - Pole Date 05/09/2024 08:49 _x000D_6/9/2024:#Update - Completed - Pole Date 05/09/2024 08:49 _x000D_5/9/2024:Openreach Delay : Automated testing has identified a potential fault _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Openreach Delay : Automated testing has identified a potential fault | #Update - Completed - Pole Date 05/09/2024 08:49 | [5 empty] | VFS1076945 | 30022292 | 2.Commissioning | AM |  | 2024-09-05 | 2024-09-05 |  | 0 | [11 empty] | 0
1957 | 627758 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | Southern Co-op | Ramsgate | CT12 4EA | 2024-09-06 | 6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Order Completed | 0 | [5 empty] | VFS1076944 | 30022409 | 2.Commissioning | AM |  | 2024-09-05 | 2024-09-05 |  | 0 | [11 empty] | 0
1958 | 455428 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | THE CO-OPERATIVE | Bournemouth | BH11 9TF | 2024-09-06 | 6/9/2024:Order Completed _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Order Completed | 0 | [5 empty] | VFS1076943 | 30022345 | 2.Commissioning | AM |  | 2024-09-05 | 2024-09-05 |  | 0 | [11 empty] | 0
1959 | 486377 |  | Batch 7 Sep 24 | Type 1 | FTTP/Mobile | The Co-operative | Bridgwater | TA6 6WU | 2024-09-06 | 6/9/2024:Order Completed _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Order Completed | 0 | [5 empty] | VFP2443431 | 30022375 | 2.Commissioning | AM |  | 2024-09-05 | 2024-09-05 |  | 0 | [11 empty] | 0
1960 | 201077 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | THE CO-OPERATIVE | RADSTOCK | BA3 3SX | 2024-09-06 | 6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Order Completed | 0 | [5 empty] | VFS1076942 | 30022343 | 2.Commissioning | AM |  | 2024-09-05 | 2024-09-05 |  | 0 | [11 empty] | 0
1961 | 436534 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | Welcome Bean Hill Co-op | MILTON KEYNES | MK6 4LP | 2024-08-14 | 6/9/2024:End User Missed appointment. Action required _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:End User Missed appointment. Action required _x000D_6/9/2024:End User Missed appointment. Action required _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | End User Missed appointment. Action required | 0 | [5 empty] | VFS1076940 | 30022433 | 1.Provisioning | AM |  | 2024-09-05 | 2024-09-05 |  | 0 | [11 empty] | 0
1962 | 669625 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | CO-OP & PO TANGIER ROAD | PORTSMOUTH | PO3 6JN | 2024-09-06 | 6/9/2024:Order Completed _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Order Completed | 0 | [5 empty] | VFS1076939 | 30022283 | 2.Commissioning | AM |  | 2024-09-05 | 2024-09-05 |  | 0 | [11 empty] | 0
1963 | 625964 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | Southern Co-Operative | Waterlooville | PO7 5LG | 2024-09-06 | 6/9/2024:Order Completed _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Order Completed | 0 | [5 empty] | VFS1076937 | 30022342 | 2.Commissioning | AM |  | 2024-09-05 | 2024-09-05 |  | 0 | [11 empty] | 0
1964 | 471177 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | The Co-operative | Eastleigh | SO53 2FU | 2024-08-14 | 6/9/2024:#Update - Additional work is required to complete the install - awaiting for more information from Openreach _x000D_5/9/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:Update: Order Amended _x000D_19/8/2024:Update: Order Amended _x000D_19/8/2024:13/08/2024 14:54 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_0 | 9/9/2024:#Update - Additional work is required to complete the install - awaiting for more information from Openreach _x000D_6/9/2024:#Update - Additional work is required to complete the install - awaiting for more information from Openreach _x000D_5/9/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:Update: Order Amended _x000D_19/8/2024:Update: Order Amended _x000D_19/8/2024:13/08/2024 14:54 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_0 | Delay on Engineer activities. Wait for further update to confirm re-appointing | #Update - Additional work is required to complete the install - awaiting for more information from Openreach | [5 empty] | VFS1076938 | 30022377 | 1.Provisioning | AM |  | 2024-08-19 | 2024-09-05 |  | 0 | [11 empty] | 0
1965 | 481210 |  | Batch 7 Sep 24 | Type 1 | FTTP/Mobile | The Co-operative | Coventry | CV6 2BQ | 2024-08-14 | 6/9/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_5/9/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_6/9/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_5/9/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. | 0 | [5 empty] | VFP2443428 | 30022384 | 1.Provisioning | AM |  | 2024-09-05 | 2024-09-05 |  | 0 | [11 empty] | 0
1966 | 486705 |  | Batch 7 Sep 24 | Type 1 | FTTP/Mobile | The Co-operative | St Leonards-on-Sea | TN37 7AG | 2024-08-14 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Update: Order Amended | 0 | [5 empty] | VFP2443426 | 30022428 | 1.Provisioning | AM |  | 2024-09-05 | 2024-09-05 |  | 0 | [11 empty] | 0
1967 | 437846 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | THE CO-OPERATIVE | Lichfield | WS13 7QG | 2024-09-06 | 6/9/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_5/9/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_4/9/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_3/9/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_2/9/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_29/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_28/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_27/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_22/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_21/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_20/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_19/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_19/8/2024:01573801 _x000D_16/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_0 | 9/9/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_6/9/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_5/9/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_4/9/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_3/9/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_2/9/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_29/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_28/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_27/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_22/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_21/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_20/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_19/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_19/8/2024:01573801 _x000D_16/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_0 | Order Completed | #Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. | [5 empty] | VFS1076936 | 30022421 | 2.Commissioning | AM |  | 2024-08-21 | 2024-09-05 |  | 0 | [11 empty] | 0
1968 | 413141 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | THE CO-OPERATIVE | SOUTHSEA | PO4 8EA | 2024-09-06 | 6/9/2024:Order Completed _x000D_5/9/2024:Update: Order Completed by Supplier _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:Update: Order Completed by Supplier _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Order Completed | 0 | [5 empty] | VFS1076935 | 30022337 | 2.Commissioning | AM |  | 2024-09-05 | 2024-09-05 |  | 0 | [11 empty] | 0
1969 | 468819 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | Welcome | CANTERBURY | CT3 2EW | 2024-09-06 | 6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Order Completed | 0 | [5 empty] | VFS1076933 | 30022414 | 2.Commissioning | AM |  | 2024-09-05 | 2024-09-05 |  | 0 | [11 empty] | 0
1970 | 479471 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | The Co-operative | Verwood | BH31 7AL | 2024-09-06 | 6/9/2024:Order Completed _x000D_5/9/2024:Update: Order Completed by Supplier _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:Update: Order Completed by Supplier _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Order Completed | 0 | [5 empty] | VFS1076934 | 30022340 | 2.Commissioning | AM |  | 2024-09-05 | 2024-09-05 |  | 0 | [11 empty] | 0
1971 | 463652 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | The Co-operative | Glastonbury | BA6 9DX | 2024-09-06 | 6/9/2024:Order Completed _x000D_5/9/2024:Update: Order Completed by Supplier _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:Update: Order Completed by Supplier _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Order Completed | 0 | [5 empty] | VFS1076931 | 30022404 | 2.Commissioning | AM |  | 2024-09-05 | 2024-09-05 |  | 0 | [11 empty] | 0
1972 | 484613 |  | Batch 7 Sep 24 | Type 1 | SOGEA | The Co-operative | Portsmouth | PO4 9EZ | 2024-08-14 | 0 | 0 | [9 empty] | 1.Provisioning | [17 empty] | 0
1973 | 669639 |  | Batch 7 Sep 24 | Type 1 | Exception | CO-OP & PO WITTERING | Chichester | PO20 8BL | 2024-08-14 | 0 | 0 | [9 empty] | 1.Provisioning | [17 empty] | 0
1974 | 485992 |  | Batch 7 Sep 24 | Type 1 | FTTP/Mobile | The Co-operative | Basingstoke | RG24 9RD | 2024-08-14 | 6/9/2024:#Update - Waiting on Step 1 external works being completed which is appointed for 28/08. Once the external works have been completed, the order will progress and can be re appointed for step 2. _x000D_5/9/2024:#Update - Waiting on Step 1 external works being completed which is appointed for 28/08. Once the external works have been completed, the order will progress and can be re appointed for step 2. _x000D_4/9/2024:#Update - Waiting on Step 1 external works being completed which is appointed for 28/08. Once the external works have been completed, the order will progress and can be re appointed for step 2. _x000D_3/9/2024:#Update - Waiting on Step 1 external works being completed which is appointed for 28/08. Once the external works have been completed, the order will progress and can be re appointed for step 2. _x000D_2/9/2024:#Update - Waiting on Step 1 external works being completed which is appointed for 28/08. Once the external works have been completed, the order will progress and can be re appointed for step 2. _x000D_29/8/2024:#Update - Waiting on Step 1 external works being completed which is appointed for 28/08. Once the external works have been completed, the order will progress and can be re appointed for step 2. _x000D_28/8/2024:#Update - Waiting on Step 1 external works being completed which is appointed for 28/08. Once the external works have been completed, the order will progress and can be re appointed for step 2. _x000D_27/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 29/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/8/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_21/8/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_20/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 27/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 27/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/8/2024:16/08/2024 19:08 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:#Update - Waiting on Step 1 external works being completed which is appointed for 28/08. Once the external works have been completed, the order will progress and can be re appointed for step 2. _x000D_6/9/2024:#Update - Waiting on Step 1 external works being completed which is appointed for 28/08. Once the external works have been completed, the order will progress and can be re appointed for step 2. _x000D_5/9/2024:#Update - Waiting on Step 1 external works being completed which is appointed for 28/08. Once the external works have been completed, the order will progress and can be re appointed for step 2. _x000D_4/9/2024:#Update - Waiting on Step 1 external works being completed which is appointed for 28/08. Once the external works have been completed, the order will progress and can be re appointed for step 2. _x000D_3/9/2024:#Update - Waiting on Step 1 external works being completed which is appointed for 28/08. Once the external works have been completed, the order will progress and can be re appointed for step 2. _x000D_2/9/2024:#Update - Waiting on Step 1 external works being completed which is appointed for 28/08. Once the external works have been completed, the order will progress and can be re appointed for step 2. _x000D_29/8/2024:#Update - Waiting on Step 1 external works being completed which is appointed for 28/08. Once the external works have been completed, the order will progress and can be re appointed for step 2. _x000D_28/8/2024:#Update - Waiting on Step 1 external works being completed which is appointed for 28/08. Once the external works have been completed, the order will progress and can be re appointed for step 2. _x000D_27/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 29/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/8/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_21/8/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_20/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 27/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 27/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/8/2024:16/08/2024 19:08 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Your order has been delayed due to infill and civils work. It requires permission from management company to proceed the planned works. Our suppliers awaiting response and please review this on 12/09/2024 for further updates. CSL Note: Invalid appointment | #Update - Waiting on Step 1 external works being completed which is appointed for 28/08. Once the external works have been completed, the order will progress and can be re appointed for step 2. | [5 empty] | VFP2443425 | 30022346 | 1.Provisioning | AM |  | 2024-09-11 |  |  | 0 | [11 empty] | 0
1975 | 627664 |  | Batch 7 Sep 24 | Type 1 | FTTP/Mobile | Co-op Food | Weymouth | DT4 0RA | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFP2443424 | 30022429 | 1.Provisioning | AM |  | 2024-09-06 | 2024-09-06 |  | 0 | [11 empty] | 0
1976 | 449997 |  | Batch 7 Sep 24 | Type 1 | SOGEA | THE CO-OPERATIVE | SOUTHAMPTON | SO32 1AB | 2024-08-14 | 0 | 0 | [9 empty] | 1.Provisioning | [17 empty] | 0
1977 | 435660 |  | Batch 7 Sep 24 | Type 1 | FTTP | THE CO-OPERATIVE | GOSPORT | PO12 3HW | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_0 | 0 | 0 | [6 empty] | 30022491 | 1.Provisioning |  |  | 2024-09-20 | [14 empty] | 0
1978 | 413125 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | THE CO-OPERATIVE | PORTSMOUTH | PO2 7RJ | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFS1076930 | 30022416 | 1.Provisioning | AM |  | 2024-09-06 | 2024-09-06 |  | 0 | [11 empty] | 0
1979 | 484616 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | The Co-operative | Portsmouth | PO6 2EH | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFS1076929 | 30022350 | 1.Provisioning | AM |  | 2024-09-06 | 2024-09-06 |  | 0 | [11 empty] | 0
1980 | 669260 |  | Batch 7 Sep 24 | Type 1 | Exception | CO-OP & PO YAPTON | ARUNDEL | BN18 0EY | 2024-08-14 | 0 | 0 | [9 empty] | 1.Provisioning | [17 empty] | 0
1981 | 481464 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | The Co-operative | Bournemouth | BH6 3EN | 2024-08-14 | 6/9/2024:Order Completed _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Order Completed | 0 | [5 empty] | VFS1076928 | 30022297 | 1.Provisioning | AM |  | 2024-09-06 | 2024-09-06 |  | 0 | [11 empty] | 0
1982 | 467067 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | The Co-operative | Shaftesbury | SP7 8PT | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFS1076927 | 30022388 | 1.Provisioning | AM |  | 2024-09-06 | 2024-09-06 |  | 0 | [11 empty] | 0
1983 | 632389 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | The Co-op | Bridgewater | TA6 6BD | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFS1076926 | 30022339 | 1.Provisioning | AM |  | 2024-09-06 | 2024-09-06 |  | 0 | [11 empty] | 0
1984 | 464958 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | The Co-operative | Romsey | SO51 8BW | 2024-08-14 | 6/9/2024:End User Missed appointment. Action required _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:End User Missed appointment. Action required _x000D_6/9/2024:End User Missed appointment. Action required _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | End User Missed appointment. Action required | 0 | [5 empty] | VFS1076924 | 30022395 | 1.Provisioning | AM |  | 2024-09-06 | 2024-09-06 |  | 0 | [11 empty] | 0
1985 | 433629 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | THE CO-OPERATIVE | BOGNOR REGIS | PO21 3EQ | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFS1076925 | 30022415 | 1.Provisioning | AM |  | 2024-09-06 | 2024-09-06 |  | 0 | [11 empty] | 0
1986 | 667020 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | Bottishams Coop | CAMBRIDGE | CB25 9DA | 2024-08-14 | 6/9/2024:End User Missed appointment. Action required _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:End User Missed appointment. Action required _x000D_6/9/2024:End User Missed appointment. Action required _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | End User Missed appointment. Action required | 0 | [5 empty] | VFS1076923 | 30022334 | 1.Provisioning | AM |  | 2024-09-06 | 2024-09-06 |  | 0 | [11 empty] | 0
1987 | 669931 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | CO-OP & PO WICOR | FAREHAM | PO16 9AR | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFS1076922 | 30022284 | 1.Provisioning | AM |  | 2024-09-10 | 2024-09-10 |  | 0 | [11 empty] | 0
1988 | 426396 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | THE CO-OPERATIVE | SOUTHAMPTON | SO52 9FN | 2024-08-14 | 6/9/2024:Update: Order Completed by Supplier _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Update: Order Completed by Supplier _x000D_6/9/2024:Update: Order Completed by Supplier _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Update: Order Completed by Supplier | 0 | [5 empty] | VFS1076921 | 30022378 | 1.Provisioning | AM |  | 2024-09-06 | 2024-09-06 |  | 0 | [11 empty] | 0
1989 | 621525 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | Southern Co-Op | Haywards Heath | RH16 4DR | 2024-08-14 | 6/9/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_6/9/2024:Delay on Engineer activities. Wait for further update to confirm re-appointing _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Delay on Engineer activities. Wait for further update to confirm re-appointing | 0 | [5 empty] | VFS1076920 | 30022328 | 1.Provisioning | AM |  | 2024-09-06 | 2024-09-06 |  | 0 | [11 empty] | 0
1990 | 609541 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | The Co-operative | Eastbourne | BN22 0AU | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFS1076919 | 30022430 | 1.Provisioning | AM |  | 2024-09-06 | 2024-09-06 |  | 0 | [11 empty] | 0
1991 | 669964 |  | Batch 7 Sep 24 | Type 1 | Exception | Co-op store | Tamworth | B78 1QE | 2024-08-14 | 0 | 0 | [9 empty] | 1.Provisioning | [17 empty] | 0
1992 | 631990 |  | Batch 7 Sep 24 | Type 1 | SOGEA | The Co-op | Warminster | BA12 8HF | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_0 | 0 | 0 | [6 empty] | 30022492 | 1.Provisioning |  |  | 2024-09-19 | [14 empty] | 0
1993 | 421407 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | THE CO-OPERATIVE | Southsea | PO4 0JJ | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFS1076918 | 30022423 | 1.Provisioning | AM |  | 2024-09-11 | 2024-09-11 |  | 0 | [11 empty] | 0
1994 | 665202 |  | Batch 7 Sep 24 | Type 1 | SOGEA | Bembridge Po & Co-Op | BEMBRIDGE | PO35 5UE | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFS1096837 |  | 1.Provisioning |  |  | 2024-09-18 | 2024-09-18 | [13 empty] | 0
1995 | 110153 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | THE CO-OPERATIVE | TAMWORTH | B78 2HH | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFS1076917 | 30022315 | 1.Provisioning | AM |  | 2024-09-11 | 2024-09-11 |  | 0 | [11 empty] | 0
1996 | 669742 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | QUEEN STREET SPSO | PORTSMOUTH | PO1 3DT | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFS1076916 | 30022317 | 1.Provisioning | AM |  | 2024-09-11 | 2024-09-11 |  | 0 | [11 empty] | 0
1997 | 669807 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | CO-OP & PO COWPLAIN | WATERLOOVILLE | PO8 8XB | 2024-08-14 | 6/9/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_5/9/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_4/9/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_3/9/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_2/9/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_29/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_28/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_27/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_22/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_21/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_20/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_19/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_19/8/2024:01566682 _x000D_16/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_0 | 9/9/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_6/9/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_5/9/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_4/9/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_3/9/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_2/9/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_29/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_28/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_27/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_22/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_21/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_20/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_19/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_19/8/2024:01566682 _x000D_16/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_0 | 0 | #Update - Order has been delayed due to network planning issues. CSL will update as more information become available. | [5 empty] | VFS1076914 | 30022399 | 1.Provisioning | AM |  | 2024-08-27 | 2024-09-11 |  | 0 | [11 empty] | 0
1998 | 486485 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | The Co-operative | Whitstable | CT5 4AX | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFS1076913 | 30022287 | 1.Provisioning | AM |  | 2024-09-11 | 2024-09-11 |  | 0 | [11 empty] | 0
1999 | 480525 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | The Co-operative | Burton upon Trent | DE13 0LB | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFS1076911 | 30022303 | 1.Provisioning | AM |  | 2024-08-13 |  |  | 0 | [11 empty] | 0
2000 | 469489 |  | Batch 7 Sep 24 | Type 1 | SOGEA | One Stop | Leeds | LS12 3BL | 2024-08-14 | 0 | 0 | [9 empty] | 1.Provisioning | [17 empty] | 0
2001 | 455617 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | ONE STOP | CHRISTCHURCH | BH23 3BN | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFS1076910 | 30022333 | 1.Provisioning | AM |  | 2024-09-12 | 2024-09-12 |  | 0 | [11 empty] | 0
2002 | 484188 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | One Stop | Edlington | DN12 1AJ | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFS1076316 | 30015257 | 1.Provisioning | AM |  | 2024-09-12 | 2024-09-12 |  | 0 | [11 empty] | 0
2003 | 626947 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | One Stop | Mansfield | NG19 6AQ | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFS1076909 | 30022362 | 1.Provisioning | AM |  | 2024-09-12 | 2024-09-12 |  | 0 | [11 empty] | 0
2004 | 470143 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | One Stop | Worksop | S80 2PU | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFS1076908 | 30022310 | 1.Provisioning | AM |  | 2024-09-12 | 2024-09-12 |  | 0 | [11 empty] | 0
2005 | 469181 |  | Batch 7 Sep 24 | Type 1 | FTTP/Mobile | One Stop | Doncaster | DN1 2BY | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFP2443423 | 30022424 | 1.Provisioning | AM |  | 2024-09-12 | 2024-09-12 |  | 0 | [11 empty] | 0
2006 | 669356 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | KINGSWAY SPSO & ONE STOP | BOSTON | PE21 0AN | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFS1076907 | 30022386 | 1.Provisioning | AM |  | 2024-09-12 | 2024-09-12 |  | 0 | [11 empty] | 0
2007 | 456706 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | ONE STOP | PRESTON | PR2 6YS | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFS1076906 | 30022332 | 1.Provisioning | AM |  | 2024-09-12 | 2024-09-12 |  | 0 | [11 empty] | 0
2008 | 455819 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | ONE STOP | NEWTON ABBOT | TQ12 1NN | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFS1076905 | 30022289 | 1.Provisioning | AM |  | 2024-09-12 | 2024-09-12 |  | 0 | [11 empty] | 0
2009 | 487287 |  | Batch 7 Sep 24 | Type 1 | FTTP/Mobile | One Stop | Sheffield | S5 6HX | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFP2443422 | 30022355 | 1.Provisioning | AM |  | 2024-09-12 | 2024-09-12 |  | 0 | [11 empty] | 0
2010 | 669192 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | One Stop | PORTSMOUTH | PO6 4HG | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFS1076903 | 30022370 | 1.Provisioning | AM |  | 2024-09-12 | 2024-09-12 |  | 0 | [11 empty] | 0
2011 | 669246 |  | Batch 7 Sep 24 | Type 1 | Exception | ONE STOP & PO | Leatherhead | KT22 7PB | 2024-08-14 | 0 | 0 | [9 empty] | 1.Provisioning | [17 empty] | 0
2012 | 669187 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | One Stop | LOWESTOFT | NR33 0RT | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFS1076899 | 30022313 | 1.Provisioning | AM |  | 2024-09-13 | 2024-09-13 |  | 0 | [11 empty] | 0
2013 | 456167 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | ONE STOP | Porthcawl | CF36 3YE | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFS1076900 | 30022413 | 1.Provisioning | AM |  | 2024-09-13 | 2024-09-13 |  | 0 | [11 empty] | 0
2014 | 484820 |  | Batch 7 Sep 24 | Type 1 | FTTP/Mobile | One Stop | Aberdare | CF44 6PY | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFP2443421 | 30022394 | 1.Provisioning | AM |  | 2024-09-13 | 2024-09-13 |  | 0 | [11 empty] | 0
2015 | 469615 |  | Batch 7 Sep 24 | Type 1 | FTTP/Mobile | One Stop | Harrogate | HG2 7LX | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFP2443419 | 30022401 | 1.Provisioning | AM |  | 2024-09-13 | 2024-09-13 |  | 0 | [11 empty] | 0
2016 | 669368 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | CHESHUNT SPSO | WALTHAM CROSS | EN8 0AH | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFS1076898 | 30022314 | 1.Provisioning | AM |  | 2024-09-13 | 2024-09-13 |  | 0 | [11 empty] | 0
2017 | 669644 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | One Stop | NORWICH | NR15 2XN | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFS1076897 | 30022298 | 1.Provisioning | AM |  | 2024-09-13 | 2024-09-13 |  | 0 | [11 empty] | 0
2018 | 629424 |  | Batch 7 Sep 24 | Type 1 | Exception | One Stop | Brynmawr | NP23 4FD | 2024-08-14 | 0 | 0 | [9 empty] | 1.Provisioning | [17 empty] | 0
2019 | 651950 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | One Stop | Manchester | M19 1EF | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFS1076896 | 30022380 | 1.Provisioning | AM |  | 2024-09-13 | 2024-09-13 |  | 0 | [11 empty] | 0
2020 | 650131 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | One Stop | Spennymoor | DL16 7AP | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFS1076893 | 30022411 | 1.Provisioning | AM |  | 2024-09-13 | 2024-09-13 |  | 0 | [11 empty] | 0
2021 | 669509 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | One Stop and Post Office | COVENTRY | CV7 7FD | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFS1076894 | 30022420 | 1.Provisioning | AM |  | 2024-09-13 | 2024-09-13 |  | 0 | [11 empty] | 0
2022 | 606844 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | One Stop | Oswestry | SY11 2LQ | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:Update: Order Amended _x000D_19/8/2024:Update: Order Amended _x000D_19/8/2024:13/08/2024 08:22 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:Update: Order Amended _x000D_19/8/2024:Update: Order Amended _x000D_19/8/2024:13/08/2024 08:22 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_0 | 0 | 0 | [5 empty] | VFS1076891 | 30022349 | 1.Provisioning | AM |  | 2024-08-19 | 2024-09-16 |  | 0 | [11 empty] | 0
2023 | 469804 |  | Batch 7 Sep 24 | Type 1 | FTTP/Mobile | One Stop | Coventry | CV3 6BP | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFP2443420 | 30022434 | 1.Provisioning | AM |  | 2024-09-16 | 2024-09-16 |  | 0 | [11 empty] | 0
2024 | 469853 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | One Stop | South Shields | NE33 4BT | 2024-09-04 | 6/9/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_5/9/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_4/9/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_3/9/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_2/9/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_29/8/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_28/8/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_27/8/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_22/8/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_21/8/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_20/8/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_19/8/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_19/8/2024:01571481 _x000D_16/8/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_0 | 9/9/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_6/9/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_5/9/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_4/9/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_3/9/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_2/9/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_29/8/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_28/8/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_27/8/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_22/8/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_21/8/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_20/8/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_19/8/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_19/8/2024:01571481 _x000D_16/8/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. _x000D_0 | Order Completed | #Update - Order has been delayed as line plant planning work is required. CSL will update as more information become available. | [5 empty] | VFS1076890 | 30022306 | 2.Commissioning | AM |  | 2024-08-18 |  |  | 0 | [11 empty] | 0
2025 | 670024 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | WELLESBOURNE SPSO | Warwick | CV35 9QP | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFS1076888 | 30022335 | 1.Provisioning | AM |  | 2024-09-16 | 2024-09-16 |  | 0 | [11 empty] | 0
2026 | 669221 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | Post Office Ltd | Paignton | TQ4 6LE | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:Update: Order Amended _x000D_19/8/2024:Update: Order Amended _x000D_19/8/2024:13/08/2024 08:28 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:Update: Order Amended _x000D_19/8/2024:Update: Order Amended _x000D_19/8/2024:13/08/2024 08:28 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_0 | 0 | 0 | [5 empty] | VFS1076889 | 30022290 | 1.Provisioning | AM |  | 2024-08-20 | 2024-09-16 |  | 0 | [11 empty] | 0
2027 | 456231 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | ONE STOP | PENARTH | CF64 5SL | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:Update: Order Amended _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:Update: Order Amended _x000D_0 | 0 | 0 | [5 empty] | VFS1076887 | 30022318 | 1.Provisioning | AM |  | 2024-09-16 | 2024-09-16 |  | 0 | [11 empty] | 0
2028 | 455743 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | ONE STOP | DURSLEY | GL11 6LQ | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFS1076886 | 30022308 | 1.Provisioning | AM |  | 2024-09-16 | 2024-09-16 |  | 0 | [11 empty] | 0
2029 | 639677 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | Trench Lock S/Stn | Telford | TF1 6SZ | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFS1076885 | 30022379 | 1.Provisioning | AM |  | 2024-09-16 | 2024-09-16 |  | 0 | [11 empty] | 0
2030 | 619037 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | Chandos S/Stn | Hockley | SS5 5HA | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFS1076882 | 30022321 | 1.Provisioning | AM |  | 2024-09-16 | 2024-09-16 |  | 0 | [11 empty] | 0
2031 | 470617 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | Collingwood S/Stn | Blackpool | FY3 8BZ | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFS1076326 | 30015213 | 1.Provisioning | AM |  | 2024-09-16 | 2024-09-16 |  | 0 | [11 empty] | 0
2032 | 470486 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | Esso Melksham S/Stn | MELKSHAM | SN12 6DE | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFS1076884 | 30022398 | 1.Provisioning | AM |  | 2024-09-16 | 2024-09-16 |  | 0 | [11 empty] | 0
2033 | 625613 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | Bilston S/Stn | Bilston | WV14 6RN | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFS1076881 | 30022354 | 1.Provisioning | AM |  | 2024-09-17 | 2024-09-16 |  | 0 | [11 empty] | 0
2034 | 617693 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | Langley S/Stn | Slough | SL3 8BB | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFS1076879 | 30022352 | 1.Provisioning | AM |  | 2024-09-17 | 2024-09-17 |  | 0 | [11 empty] | 0
2035 | 620728 |  | Batch 7 Sep 24 | Type 1 | Exception | LEADS ROAD S/Stn | HULL | HU7 0DF | 2024-08-14 | 0 | 0 | [9 empty] | 1.Provisioning | [17 empty] | 0
2036 | 435702 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | THE CO-OPERATIVE | BRAINTREE | CM7 1AN | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFS1076878 | 30022372 | 1.Provisioning | AM |  | 2024-09-17 | 2024-09-17 |  | 0 | [11 empty] | 0
2037 | 421685 |  | Batch 7 Sep 24 | Type 1 | FTTP/Mobile | THE CO-OPERATIVE | CHELMSFORD | CM1 2BB | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFP2443417 | 30022347 | 1.Provisioning | AM |  | 2024-09-17 | 2024-09-17 |  | 0 | [11 empty] | 0
2038 | 422473 |  | Batch 7 Sep 24 | Type 1 | FTTP/Mobile | THE CO-OPERATIVE | SOUTHEND-ON-SEA | SS3 9DT | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFP2443418 | 30022391 | 1.Provisioning | AM |  | 2024-09-17 | 2024-09-17 |  | 0 | [11 empty] | 0
2039 | 421106 |  | Batch 7 Sep 24 | Type 1 | FTTP/Mobile | THE CO-OPERATIVE | BRAINTREE | CM7 3PL | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFP2443414 | 30022406 | 1.Provisioning | AM |  | 2024-09-17 | 2024-09-17 |  | 0 | [11 empty] | 0
2040 | 465690 |  | Batch 7 Sep 24 | Type 1 | Exception | The Co-operative | South Ockendon | RM15 6NH | 2024-08-14 | 0 | 0 | [9 empty] | 1.Provisioning | [17 empty] | 0
2041 | 425660 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | THE CO-OPERATIVE | BENFLEET | SS7 4EN | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_28/8/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_27/8/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_28/8/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_27/8/2024:Supplier Delay: Network Planning issues. Please await for further updates CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFS1076877 | 30022390 | 1.Provisioning | AM |  | 2024-08-20 |  |  | 0 | [11 empty] | 0
2042 | 626099 |  | Batch 7 Sep 24 | Type 1 | FTTP/Mobile | Chelmsford Star Co-Op | Dagenham | RM8 3NH | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFP2443415 | 30022341 | 1.Provisioning | AM |  | 2024-09-17 | 2024-09-17 |  | 0 | [11 empty] | 0
2043 | 466665 |  | Batch 7 Sep 24 | Type 1 | FTTP/Mobile | The Co-operative | Wickford | SS12 0NY | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFP2443412 | 30022365 | 1.Provisioning | AM |  | 2024-09-17 | 2024-09-17 |  | 0 | [11 empty] | 0
2044 | 433912 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | THE CO-OPERATIVE | CHELMSFORD | CM1 6JP | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFS1076876 | 30022410 | 1.Provisioning | AM |  | 2024-09-17 | 2024-09-17 |  | 0 | [11 empty] | 0
2045 | 262170 |  | Batch 7 Sep 24 | Type 1 | Exception | THE CO-OPERATIVE | INGATESTONE | CM4 9EA | 2024-08-14 | 0 | 0 | [9 empty] | 1.Provisioning | [17 empty] | 0
2046 | 265305 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | THE CO-OPERATIVE | CHELMSFORD | CM2 9RP | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFS1076874 | 30022353 | 1.Provisioning | AM |  | 2024-09-18 | 2024-09-18 |  | 0 | [11 empty] | 0
2047 | 669938 |  | Batch 7 Sep 24 | Type 1 | Exception | Parklands & PO | Lincoln | LN6 7ST | 2024-08-14 | 0 | 0 | [9 empty] | 1.Provisioning | [17 empty] | 0
2048 | 669884 |  | Batch 7 Sep 24 | Type 1 | Exception | Riddins PO & Lincoln Co-op | Scunthorpe | DN17 2DJ | 2024-08-14 | 0 | 0 | [9 empty] | 1.Provisioning | [17 empty] | 0
2049 | 623401 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | Lincolnshire Co-Op | Lincolnshire | PE21 8BB | 2024-08-14 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Update: Order Amended | 0 | [5 empty] | VFS1076875 | 30022435 | 1.Provisioning | AM |  | 2024-09-18 | 2024-09-18 |  | 0 | [11 empty] | 0
2050 | 669799 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | THE WILLOWS SPSO | GRIMSBY | DN37 9DR | 2024-08-14 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Update: Order Amended | 0 | [5 empty] | VFS1076871 | 30022319 | 1.Provisioning | AM |  | 2024-09-18 | 2024-09-18 |  | 0 | [11 empty] | 0
2051 | 671943 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | THE CO-OPERATIVE | BOSTON | PE21 8PH | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFS1076870 | 30022286 | 1.Provisioning | AM |  | 2024-09-18 | 2024-09-18 |  | 0 | [11 empty] | 0
2052 | 447933 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | THE CO-OPERATIVE | LINCOLN | LN6 0PY | 2024-09-04 | 6/9/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_5/9/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_4/9/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_3/9/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_2/9/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_29/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_28/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_27/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_22/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_21/8/2024:#Update - Order has been delayed as the line plant records need to be updated by the supplier. CSL will update as more information become available. _x000D_20/8/2024:#Update - Order has been delayed as the line plant records need to be updated by the supplier. CSL will update as more information become available. _x000D_19/8/2024:#Update - Order has been delayed as the line plant records need to be updated by the supplier. CSL will update as more information become available. _x000D_19/8/2024:01573885 _x000D_16/8/2024:#Update - Order has been delayed as the line plant records need to be updated by the supplier. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order has been delayed as the line plant records need to be updated by the supplier. CSL will update as more information become available. _x000D_0 | 9/9/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_6/9/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_5/9/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_4/9/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_3/9/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_2/9/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_29/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_28/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_27/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_22/8/2024:#Update - Order has been delayed due to network planning issues. CSL will update as more information become available. _x000D_21/8/2024:#Update - Order has been delayed as the line plant records need to be updated by the supplier. CSL will update as more information become available. _x000D_20/8/2024:#Update - Order has been delayed as the line plant records need to be updated by the supplier. CSL will update as more information become available. _x000D_19/8/2024:#Update - Order has been delayed as the line plant records need to be updated by the supplier. CSL will update as more information become available. _x000D_19/8/2024:01573885 _x000D_16/8/2024:#Update - Order has been delayed as the line plant records need to be updated by the supplier. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order has been delayed as the line plant records need to be updated by the supplier. CSL will update as more information become available. _x000D_0 | Order Completed | #Update - Order has been delayed due to network planning issues. CSL will update as more information become available. | [5 empty] | VFS1076872 | 30022396 | 2.Commissioning | AM |  | 2024-08-23 |  |  | 0 | [11 empty] | 0
2053 | 644400 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | Lincolnshire Co-op | Lincoln | LN5 7ET | 2024-08-14 | 6/9/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information becomes available. _x000D_5/9/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information becomes available. _x000D_4/9/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information becomes available. _x000D_3/9/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information becomes available. _x000D_2/9/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information becomes available. _x000D_29/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information becomes available. _x000D_28/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information becomes available. _x000D_27/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information becomes available. _x000D_22/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information becomes available. _x000D_21/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information becomes available. _x000D_20/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information becomes available. _x000D_19/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information becomes available. _x000D_19/8/2024:01573909 _x000D_16/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information becomes available. _x000D_15/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information becomes available. _x000D_0 | 9/9/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information becomes available. _x000D_6/9/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information becomes available. _x000D_5/9/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information becomes available. _x000D_4/9/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information becomes available. _x000D_3/9/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information becomes available. _x000D_2/9/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information becomes available. _x000D_29/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information becomes available. _x000D_28/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information becomes available. _x000D_27/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information becomes available. _x000D_22/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information becomes available. _x000D_21/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information becomes available. _x000D_20/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information becomes available. _x000D_19/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information becomes available. _x000D_19/8/2024:01573909 _x000D_16/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information becomes available. _x000D_15/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information becomes available. _x000D_0 | Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 09/09/2024. We will continue to provide update as they become available. | #Update - Order has been delayed as pair divert work is required. CSL will update as more information becomes available. | [5 empty] | VFS1076869 | 30022425 | 1.Provisioning | AM |  | 2024-08-23 |  |  | 0 | [11 empty] | 0
2054 | 442817 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | THE CO-OPERATIVE | GRIMSBY | DN37 9SF | 2024-08-14 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Update: Order Amended | 0 | [5 empty] | VFS1076866 | 30022417 | 1.Provisioning | AM |  | 2024-09-18 | 2024-09-18 |  | 0 | [11 empty] | 0
2055 | 623586 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | Lincolnshire Co-Op | Lincolnshire | PE22 9JT | 2024-08-14 | 6/9/2024:#Update - this order has been delayed. Pair divert work required. We will continue to provide update as they become available. _x000D_5/9/2024:#Update - this order has been delayed. Pair divert work required. We will continue to provide update as they become available. _x000D_4/9/2024:#Update - this order has been delayed. Pair divert work required. We will continue to provide update as they become available. _x000D_3/9/2024:#Update - this order has been delayed. Pair divert work required. We will continue to provide update as they become available. _x000D_2/9/2024:#Update - this order has been delayed. Pair divert work required. We will continue to provide update as they become available. _x000D_29/8/2024:#Update - this order has been delayed. Pair divert work required. We will continue to provide update as they become available. _x000D_28/8/2024:#Update - this order has been delayed. Pair divert work required. We will continue to provide update as they become available. _x000D_27/8/2024:#Update - this order has been delayed. Pair divert work required. We will continue to provide update as they become available. _x000D_22/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 30/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_21/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 20/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_20/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 20/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 20/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/8/2024:14/08/2024 15:29 _x000D_16/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 20/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 20/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_0 | 9/9/2024:#Update - this order has been delayed. Pair divert work required. We will continue to provide update as they become available. _x000D_6/9/2024:#Update - this order has been delayed. Pair divert work required. We will continue to provide update as they become available. _x000D_5/9/2024:#Update - this order has been delayed. Pair divert work required. We will continue to provide update as they become available. _x000D_4/9/2024:#Update - this order has been delayed. Pair divert work required. We will continue to provide update as they become available. _x000D_3/9/2024:#Update - this order has been delayed. Pair divert work required. We will continue to provide update as they become available. _x000D_2/9/2024:#Update - this order has been delayed. Pair divert work required. We will continue to provide update as they become available. _x000D_29/8/2024:#Update - this order has been delayed. Pair divert work required. We will continue to provide update as they become available. _x000D_28/8/2024:#Update - this order has been delayed. Pair divert work required. We will continue to provide update as they become available. _x000D_27/8/2024:#Update - this order has been delayed. Pair divert work required. We will continue to provide update as they become available. _x000D_22/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 30/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_21/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 20/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_20/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 20/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 20/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/8/2024:14/08/2024 15:29 _x000D_16/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 20/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 20/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_0 | Update: Order Amended | #Update - this order has been delayed. Pair divert work required. We will continue to provide update as they become available. | [5 empty] | VFS1076867 | 30022366 | 1.Provisioning | AM |  | 2024-08-24 |  |  | 0 | [11 empty] | 0
2056 | 621900 |  | Batch 7 Sep 24 | Type 1 | FTTP/Mobile | Lincolnshire Co-Op | Lincolnshire | DN21 1SH | 2024-08-14 | 6/9/2024:#Update - site survey is required. This has been sent to the survey engineers. We will continue to provide update as they become available. _x000D_5/9/2024:#Update - site survey is required. This has been sent to the survey engineers. We will continue to provide update as they become available. _x000D_4/9/2024:#Update - site survey is required. This has been sent to the survey engineers. We will continue to provide update as they become available. _x000D_3/9/2024:#Update - site survey is required. This has been sent to the survey engineers. We will continue to provide update as they become available. _x000D_2/9/2024:#Update - site survey is required. This has been sent to the survey engineers. We will continue to provide update as they become available. _x000D_29/8/2024:#Update - order has been delayed. Step-1 work required - we will share further updates accordingly _x000D_28/8/2024:#Update - order has been delayed. Step-1 work required - we will share further updates accordingly _x000D_27/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 28/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/8/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_21/8/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_20/8/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 23/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_0 | 9/9/2024:#Update - site survey is required. This has been sent to the survey engineers. We will continue to provide update as they become available. _x000D_6/9/2024:#Update - site survey is required. This has been sent to the survey engineers. We will continue to provide update as they become available. _x000D_5/9/2024:#Update - site survey is required. This has been sent to the survey engineers. We will continue to provide update as they become available. _x000D_4/9/2024:#Update - site survey is required. This has been sent to the survey engineers. We will continue to provide update as they become available. _x000D_3/9/2024:#Update - site survey is required. This has been sent to the survey engineers. We will continue to provide update as they become available. _x000D_2/9/2024:#Update - site survey is required. This has been sent to the survey engineers. We will continue to provide update as they become available. _x000D_29/8/2024:#Update - order has been delayed. Step-1 work required - we will share further updates accordingly _x000D_28/8/2024:#Update - order has been delayed. Step-1 work required - we will share further updates accordingly _x000D_27/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 28/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_22/8/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_21/8/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_20/8/2024:Update: Order Amended CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 23/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_0 | Update: Order Amended | #Update - site survey is required. This has been sent to the survey engineers. We will continue to provide update as they become available. | [5 empty] | VFP2443413 | 30022304 | 1.Provisioning | AM |  | 2024-08-24 |  |  | 0 | [11 empty] | 0
2057 | 420116 |  | Batch 7 Sep 24 | Type 1 | FTTP/Mobile | THE CO-OPERATIVE | Gainsborough | DN21 3AA | 2024-08-14 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Update: Order Amended | 0 | [5 empty] | VFP2443411 | 30022336 | 1.Provisioning | AM |  | 2024-09-18 | 2024-09-18 |  | 0 | [11 empty] | 0
2058 | 669856 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | WOODSIDE SPSO | Sleaford | NG34 8AD | 2024-08-14 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Update: Order Amended | 0 | [5 empty] | VFS1076862 | 30022373 | 1.Provisioning | AM |  | 2024-09-18 | 2024-09-18 |  | 0 | [11 empty] | 0
2059 | 670019 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | Lowfields Po & Co-op | Lincoln | LN5 9TR | 2024-08-14 | 6/9/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_5/9/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_4/9/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_3/9/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_2/9/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_29/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_28/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_27/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_22/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_21/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_20/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_19/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_19/8/2024:01573917 _x000D_16/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_0 | 9/9/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_6/9/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_5/9/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_4/9/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_3/9/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_2/9/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_29/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_28/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_27/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_22/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_21/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_20/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_19/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_19/8/2024:01573917 _x000D_16/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_15/8/2024:#Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. _x000D_0 | Update: Order Amended | #Update - Order has been delayed as pair divert work is required. CSL will update as more information become available. | [5 empty] | VFS1076864 | 30022385 | 1.Provisioning | AM |  | 2024-08-27 | 2024-09-19 |  | 0 | [11 empty] | 0
2060 | 622102 |  | Batch 7 Sep 24 | Type 1 | FTTP/Mobile | Lincolnshire Co-Op | Newark | NG24 2DP | 2024-08-14 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Update: Order Amended | 0 | [5 empty] | VFP2443410 | 30022307 | 1.Provisioning | AM |  | 2024-09-19 | 2024-09-19 |  | 0 | [11 empty] | 0
2061 | 622100 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | Lincolnshire Co-Op | Boston | PE21 0PH | 2024-08-14 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Update: Order Amended | 0 | [5 empty] | VFS1076861 | 30022359 | 1.Provisioning | AM |  | 2024-09-19 | 2024-09-19 |  | 0 | [11 empty] | 0
2062 | 669998 |  | Batch 7 Sep 24 | Type 1 | FTTP/Mobile | CO-OP & POST OFFICE. | NEWARK | NG24 4ND | 2024-08-14 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Update: Order Amended | 0 | [5 empty] | VFP2443408 | 30022324 | 1.Provisioning | AM |  | 2024-09-19 | 2024-09-19 |  | 0 | [11 empty] | 0
2063 | 622084 |  | Batch 7 Sep 24 | Type 1 | Exception | Lincolnshire Co-Op | Lincolnshire | LN11 0JT | 2024-08-14 | 0 | 0 | [9 empty] | 1.Provisioning | [17 empty] | 0
2064 | 484617 |  | Batch 7 Sep 24 | Type 1 | FTTP/Mobile | The Co-operative | Newark | NG24 4BQ | 2024-08-14 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Update: Order Amended | 0 | [5 empty] | VFP2443409 | 30022419 | 1.Provisioning | AM |  | 2024-09-19 | 2024-09-19 |  | 0 | [11 empty] | 0
2065 | 468196 |  | Batch 7 Sep 24 | Type 1 | Exception | The Co-operative | Caistor | LN7 6QF | 2024-08-14 | 0 | 0 | [9 empty] | 1.Provisioning | [17 empty] | 0
2066 | 622068 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | Lincolnshire Co-Op | Lincolnshire | LN1 3LL | 2024-08-14 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Update: Order Amended | 0 | [5 empty] | VFS1076860 | 30022389 | 1.Provisioning | AM |  | 2024-09-19 | 2024-09-19 |  | 0 | [11 empty] | 0
2067 | 669695 |  | Batch 7 Sep 24 | Type 1 | FTTP/Mobile | CHAPEL ST LEONARDS PO | SKEGNESS | PE24 5TG | 2024-08-14 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Update: Order Amended | 0 | [5 empty] | VFP2443406 | 30022299 | 1.Provisioning | AM |  | 2024-09-19 | 2024-09-19 |  | 0 | [11 empty] | 0
2068 | 616226 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | The Co-Operative | SPALDING | PE12 7AX | 2024-08-14 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Update: Order Amended | 0 | [5 empty] | VFS1076859 | 30022296 | 1.Provisioning | AM |  | 2024-09-19 | 2024-09-19 |  | 0 | [11 empty] | 0
2069 | 669737 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | ST GILES SPSO & CO-OP | Lincoln | LN2 4FN | 2024-08-14 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Update: Order Amended | 0 | [5 empty] | VFS1076858 | 30022382 | 1.Provisioning | AM |  | 2024-09-19 | 2024-09-19 |  | 0 | [11 empty] | 0
2070 | 486762 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | The Co-operative | Scunthorpe | DN17 4LA | 2024-08-14 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Update: Order Amended | 0 | [5 empty] | VFS1076857 | 30022376 | 1.Provisioning | AM |  | 2024-09-20 | 2024-09-20 |  | 0 | [11 empty] | 0
2071 | 459543 |  | Batch 7 Sep 24 | Type 1 | FTTP/Mobile | THE CO-OPERATIVE | SKEGNESS | PE25 1SE | 2024-08-14 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Update: Order Amended | 0 | [5 empty] | VFP2443405 | 30022427 | 1.Provisioning | AM |  | 2024-09-20 | 2024-09-20 |  | 0 | [11 empty] | 0
2072 | 670016 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | HYKEHAM MOOR PO | LINCOLN | LN6 8NH | 2024-08-14 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Update: Order Amended | 0 | [5 empty] | VFS1076856 | 30022282 | 1.Provisioning | AM |  | 2024-09-20 | 2024-09-20 |  | 0 | [11 empty] | 0
2073 | 622096 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | Lincolnshire Co-Op | Lincolnshire | NG34 9RA | 2024-08-14 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Update: Order Amended | 0 | [5 empty] | VFS1076855 | 30022400 | 1.Provisioning | AM |  | 2024-09-20 | 2024-09-20 |  | 0 | [11 empty] | 0
2074 | 459531 |  | Batch 7 Sep 24 | Type 1 | FTTP/Mobile | THE CO-OPERATIVE | Newark | NG24 1RQ | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:Update: Order Amended _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_20/8/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/8/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/8/2024:15/08/2024 16:14 _x000D_16/8/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 22/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:Update: Order Amended _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:Update: Order Amended _x000D_21/8/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_20/8/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/8/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/8/2024:15/08/2024 16:14 _x000D_16/8/2024:Informational - External visit has been completed CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/8/2024:Your order has been delayed. Step-1 work required. Our Suppliers have given us a review date of 22/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_0 | 0 | 0 | [5 empty] | VFP2442811 | 30015157 | 1.Provisioning | AM |  |  |  |  | 0 | [11 empty] | 0
2075 | 485466 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | The Co-operative | Tattershall | LN4 4LJ | 2024-08-14 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Update: Order Amended | 0 | [5 empty] | VFS1076853 | 30022323 | 1.Provisioning | AM |  | 2024-09-20 | 2024-09-20 |  | 0 | [11 empty] | 0
2076 | 429212 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | THE CO-OPERATIVE | SPALDING | PE11 3GD | 2024-08-14 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Update: Order Amended | 0 | [5 empty] | VFS1076852 | 30022301 | 1.Provisioning | AM |  | 2024-09-20 | 2024-09-20 |  | 0 | [11 empty] | 0
2077 | 481206 |  | Batch 7 Sep 24 | Type 1 | SOGEA | The Co-operative | Boston | PE21 6DA | 2024-08-14 | 6/9/2024:#Update - order delayed due to a supplier system delay. We will continue to provide updates as they become available. _x000D_5/9/2024:#Update - order delayed due to a supplier system delay. We will continue to provide updates as they become available. _x000D_4/9/2024:#Update - order delayed due to a supplier system delay. We will continue to provide updates as they become available. _x000D_3/9/2024:#Update - order delayed due to a supplier system delay. We will continue to provide updates as they become available. _x000D_2/9/2024:#Update - order delayed due to a supplier system delay. We will continue to provide updates as they become available. _x000D_29/8/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 30-08-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_28/8/2024:0 _x000D_0 | 9/9/2024:#Update - order delayed due to a supplier system delay. We will continue to provide updates as they become available. _x000D_6/9/2024:#Update - order delayed due to a supplier system delay. We will continue to provide updates as they become available. _x000D_5/9/2024:#Update - order delayed due to a supplier system delay. We will continue to provide updates as they become available. _x000D_4/9/2024:#Update - order delayed due to a supplier system delay. We will continue to provide updates as they become available. _x000D_3/9/2024:#Update - order delayed due to a supplier system delay. We will continue to provide updates as they become available. _x000D_2/9/2024:#Update - order delayed due to a supplier system delay. We will continue to provide updates as they become available. _x000D_29/8/2024:Your order is currently in Address Validation stage.The Address Validation will be completed by 30-08-2024. Next Stage of your order can be Routing or Survey. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_28/8/2024:0 _x000D_0 | 0 | #Update - order delayed due to a supplier system delay. We will continue to provide updates as they become available. | [5 empty] | VFS1097722 |  | 1.Provisioning |  |  | 2024-09-18 | 2024-09-18 | [13 empty] | 0
2078 | 615494 |  | Batch 7 Sep 24 | Type 1 | FTTP/Mobile | The Co-operative | Newark | NG24 4BZ | 2024-08-14 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Update: Order Amended | 0 | [5 empty] | VFP2442828 | 30022436 | 1.Provisioning | AM |  | 2024-09-20 | 2024-09-20 |  | 0 | [11 empty] | 0
2079 | 669659 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | LONG SUTTON SPSO | SPALDING | PE12 9BN | 2024-08-14 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Update: Order Amended | 0 | [5 empty] | VFS1076851 | 30022431 | 1.Provisioning | AM |  | 2024-09-20 | 2024-09-20 |  | 0 | [11 empty] | 0
2080 | 669751 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | CONISTON AVENUE SPSO & CO-OP | GRIMSBY | DN33 3EE | 2024-08-14 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Update: Order Amended | 0 | [5 empty] | VFS1076850 | 30022294 | 1.Provisioning | AM |  | 2024-09-20 | 2024-09-20 |  | 0 | [11 empty] | 0
2081 | 651649 |  | Batch 7 Sep 24 | Type 1 | FTTP | Lincolnshire Co-op | Peterborough | 0 | 2024-08-14 | 0 | 0 | [9 empty] | 1.Provisioning | [17 empty] | 0
2082 | 669719 |  | Batch 7 Sep 24 | Type 1 | FTTP/Mobile | MISTERTON SPSO | DONCASTER | DN10 4BU | 2024-08-14 | 6/9/2024:#Update awaiting for further work to be completed by skilled engineers. Rescheduled for 21/10 _x000D_5/9/2024:#Update awaiting for further work to be completed by skilled engineers. Rescheduled for 21/10 _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_15/8/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_0 | 9/9/2024:#Update awaiting for further work to be completed by skilled engineers. Rescheduled for 21/10 _x000D_6/9/2024:#Update awaiting for further work to be completed by skilled engineers. Rescheduled for 21/10 _x000D_5/9/2024:#Update awaiting for further work to be completed by skilled engineers. Rescheduled for 21/10 _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_15/8/2024:Supplier Delay: Network Planning - The order has been sent to the survey group; await order status update. _x000D_0 | Update: Order Amended | #Update awaiting for further work to be completed by skilled engineers. Rescheduled for 21/10 | [5 empty] | VFP2443404 | 30022300 | 1.Provisioning | AM |  | 2024-09-20 | 2024-09-20 |  | 0 | [11 empty] | 0
2083 | 240596 |  | Batch 7 Sep 24 | Type 1 | Exception | THE CO-OPERATIVE | LINCOLN | LN4 1LH | 2024-08-14 | 0 | 0 | [9 empty] | 1.Provisioning | [17 empty] | 0
2084 | 459534 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | THE CO-OPERATIVE | LINCOLN | LN2 2AD | 2024-08-14 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Update: Order Amended | 0 | [5 empty] | VFS1076849 | 30022369 | 1.Provisioning | AM |  | 2024-09-23 | 2024-09-23 |  | 0 | [11 empty] | 0
2085 | 669731 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | RUSKINGTON SPSO & CO-OP | Sleaford | NG34 9DY | 2024-08-14 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Update: Order Amended | 0 | [5 empty] | VFS1076848 | 30022285 | 1.Provisioning | AM |  | 2024-09-23 | 2024-09-23 |  | 0 | [11 empty] | 0
2086 | 622071 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | Lincolnshire Co-Op | Lincolnshire | LN2 5JP | 2024-08-14 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Update: Order Amended | 0 | [5 empty] | VFS1076847 | 30022331 | 1.Provisioning | AM |  | 2024-09-23 | 2024-09-23 |  | 0 | [11 empty] | 0
2087 | 669264 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | TRELAWNEY POST OFFICE | LINCOLN | LN1 3PA | 2024-08-14 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Update: Order Amended | 0 | [5 empty] | VFS1076846 | 30022393 | 1.Provisioning | AM |  | 2024-09-23 | 2024-09-23 |  | 0 | [11 empty] | 0
2088 | 613530 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | The Co-operative | Dunholme | LN2 3QR | 2024-08-14 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Update: Order Amended | 0 | [5 empty] | VFS1076844 | 30022405 | 1.Provisioning | AM |  | 2024-09-23 | 2024-09-23 |  | 0 | [11 empty] | 0
2089 | 466356 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | The Co-operative | Coninsby | LN4 4SG | 2024-08-14 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:Update: Order Amended _x000D_28/8/2024:Update: Order Amended _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_21/8/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:Update: Order Amended _x000D_28/8/2024:Update: Order Amended _x000D_27/8/2024:Update: Order Amended _x000D_22/8/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_21/8/2024:Your order has come off a waiters list and will now be fulfilled. _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Update: Order Amended | 0 | [5 empty] | VFS1076845 | 30022412 | 1.Provisioning | AM |  | 2024-08-27 |  |  | 0 | [11 empty] | 0
2090 | 613221 |  | Batch 7 Sep 24 | Type 1 | Exception | The Co-operative | Lincoln | LN4 1DQ | 2024-08-14 | 0 | 0 | [9 empty] | 1.Provisioning | [17 empty] | 0
2091 | 240639 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | THE CO-OPERATIVE | LINCOLN | LN3 4JL | 2024-08-14 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Update: Order Amended | 0 | [5 empty] | VFS1076842 | 30022344 | 1.Provisioning | AM |  | 2024-09-23 | 2024-09-23 |  | 0 | [11 empty] | 0
2092 | 661087 |  | Batch 7 Sep 24 | Type 1 | FTTP/Mobile | Lincolnshire Co-op | Lincoln | LN6 0ER | 2024-08-14 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Update: Order Amended | 0 | [5 empty] | VFP2443403 | 30022392 | 1.Provisioning | AM |  | 2024-09-23 | 2024-09-23 |  | 0 | [11 empty] | 0
2093 | 479491 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | The Co-operative | Lincoln | LN1 3SN | 2024-08-14 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Update: Order Amended | 0 | [5 empty] | VFS1076841 | 30022361 | 1.Provisioning | AM |  | 2024-09-23 | 2024-09-23 |  | 0 | [11 empty] | 0
2094 | 642678 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | Lincoln Co-Op PFS | SPALDING | PE12 6TJ | 2024-08-14 | 6/9/2024:#Update Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 28/08/2024. We will continue to provide update as they become available. _x000D_5/9/2024:#Update Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 28/08/2024. We will continue to provide update as they become available. _x000D_4/9/2024:#Update Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 28/08/2024. We will continue to provide update as they become available. _x000D_3/9/2024:#Update Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 28/08/2024. We will continue to provide update as they become available. _x000D_2/9/2024:#Update Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 28/08/2024. We will continue to provide update as they become available. _x000D_29/8/2024:#Update Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 28/08/2024. We will continue to provide update as they become available. _x000D_28/8/2024:#Update Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 28/08/2024. We will continue to provide update as they become available. _x000D_27/8/2024:#Update Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 28/08/2024. We will continue to provide update as they become available. _x000D_22/8/2024:#Update Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 28/08/2024. We will continue to provide update as they become available. _x000D_21/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 22/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_20/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 22/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 22/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/8/2024:16/08/2024 19:07 _x000D_16/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 16/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 16/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_0 | 9/9/2024:#Update Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 28/08/2024. We will continue to provide update as they become available. _x000D_6/9/2024:#Update Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 28/08/2024. We will continue to provide update as they become available. _x000D_5/9/2024:#Update Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 28/08/2024. We will continue to provide update as they become available. _x000D_4/9/2024:#Update Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 28/08/2024. We will continue to provide update as they become available. _x000D_3/9/2024:#Update Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 28/08/2024. We will continue to provide update as they become available. _x000D_2/9/2024:#Update Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 28/08/2024. We will continue to provide update as they become available. _x000D_29/8/2024:#Update Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 28/08/2024. We will continue to provide update as they become available. _x000D_28/8/2024:#Update Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 28/08/2024. We will continue to provide update as they become available. _x000D_27/8/2024:#Update Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 28/08/2024. We will continue to provide update as they become available. _x000D_22/8/2024:#Update Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 28/08/2024. We will continue to provide update as they become available. _x000D_21/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 22/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_20/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 22/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 22/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_19/8/2024:16/08/2024 19:07 _x000D_16/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 16/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_15/8/2024:Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 16/08/2024. We will continue to provide update as they become available. CSL Note: Invalid appointment slot received CSL Note: Invalid data received _x000D_0 | Your order has been delayed. Network records need to be updated by supplier. This has been sent to the engineers and they have given us a review date of 09/09/2024.We will continue to provide update as they become available. CSL Note: Invalid appointment | #Update Your order has been delayed. Pair divert work required. Our Suppliers have given us a review date of 28/08/2024. We will continue to provide update as they become available. | [5 empty] | VFS1076840 | 30022383 | 1.Provisioning | AM |  | 2024-08-30 |  |  | 0 | [11 empty] | 0
2095 | 459264 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | THE CO-OPERATIVE | PETERBOROUGH | PE6 0ED | 2024-08-14 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Update: Order Amended | 0 | [5 empty] | VFS1076839 | 30022357 | 1.Provisioning | AM |  | 2024-09-23 | 2024-09-23 |  | 0 | [11 empty] | 0
2096 | 433315 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | THE CO-OPERATIVE | LINCOLN | LN4 3EA | 2024-08-14 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Update: Order Amended | 0 | [5 empty] | VFS1076838 | 30022381 | 1.Provisioning | AM |  | 2024-09-24 | 2024-09-24 |  | 0 | [11 empty] | 0
2097 | 480536 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | The Co-operative | Horncastle | LN9 5HP | 2024-08-14 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Update: Order Amended | 0 | [5 empty] | VFS1076837 | 30022295 | 1.Provisioning | AM |  | 2024-09-24 | 2024-09-24 |  | 0 | [11 empty] | 0
2098 | 670018 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | NETTLEHAM PO | LINCOLN | LN2 2NR | 2024-08-14 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Update: Order Amended | 0 | [5 empty] | VFS1076836 | 30022312 | 1.Provisioning | AM |  | 2024-09-24 | 2024-09-24 |  | 0 | [11 empty] | 0
2099 | 446576 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | THE CO-OPERATIVE | SPALDING | PE12 9UA | 2024-08-14 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_0 | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:Update: Order Amended _x000D_15/8/2024:Update: Order Amended _x000D_0 | Update: Order Amended | 0 | [5 empty] | VFS1076335 | 30015211 | 1.Provisioning | AM |  | 2024-10-24 | 2024-09-24 |  | 0 | [11 empty] | 0
2100 | 435846 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | THE CO-OPERATIVE | LINCOLN | LN1 2HG | 2024-08-14 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Update: Order Amended | 0 | [5 empty] | VFS1076977 | 30022311 | 1.Provisioning | AM |  | 2024-09-24 | 2024-09-24 |  | 0 | [11 empty] | 0
2101 | 479557 |  | Batch 7 Sep 24 | Type 1 | FTTP/Mobile | The Co-operative | Woodhall Spa | LN10 6TZ | 2024-08-14 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Update: Order Amended | 0 | [5 empty] | VFP2443402 | 30022288 | 1.Provisioning | AM |  | 2024-09-24 | 2024-09-24 |  | 0 | [11 empty] | 0
2102 | 479489 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | The Co-operative | Lincoln | LN4 4RQ | 2024-08-14 | 6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:Update: Order Amended _x000D_6/9/2024:Update: Order Amended _x000D_5/9/2024:Update: Order Amended _x000D_4/9/2024:Update: Order Amended _x000D_3/9/2024:Update: Order Amended _x000D_2/9/2024:Update: Order Amended _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | Update: Order Amended | 0 | [5 empty] | VFS1076835 | 30022356 | 1.Provisioning | AM |  | 2024-09-24 | 2024-09-24 |  | 0 | [11 empty] | 0
2103 | 483052 |  | Batch 7 Sep 24 | Type 1 | SOGEA | The Co-operative | Clydebank | G81 1EA | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_0 | 0 | 0 | [6 empty] | 30022488 | 1.Provisioning |  |  | 2024-09-19 | [14 empty] | 0
2104 | 240594 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | THE CO-OPERATIVE | CLYDEBANK | G81 4BQ | 2024-08-14 | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_15/8/2024:0 _x000D_0 | 0 | 0 | [5 empty] | VFS1076834 | 30022291 | 1.Provisioning | AM |  | 2024-09-24 | 2024-09-24 |  | 0 | [11 empty] | 0
2105 | 243109 |  | Batch 7 Sep 24 | Type 1 | Exception | THE CO-OPERATIVE | CLYDEBANK | G81 3NQ | 2024-08-14 | 0 | 0 | [9 empty] | 1.Provisioning | [17 empty] | 0
2106 | 461942 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | Tesco Express | WALSALL | WS9 0BP | 2024-09-03 | 6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:Order Completed _x000D_2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_0 | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:Order Completed _x000D_2/9/2024:Order Completed _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_0 | Order Completed | 0 | [5 empty] | VFS1086441 | 30022474 | 2.Commissioning |  |  | 2024-09-02 | 2024-09-02 | 2024-09-02 10:22 | TRUE | [11 empty] | 0
2107 | 429444 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | Tesco Stores Ltd | GLASGOW | G32 7JE | 2024-09-03 | 6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:Order Completed _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_0 | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:Order Completed _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_0 | Order Completed | 0 | [5 empty] | VFS1086442 | 30022476 | 2.Commissioning |  |  | 2024-09-02 | 2024-09-02 | 2024-09-02 13:11 | TRUE | [11 empty] | 0
2108 | 251130 |  | Batch 7 Sep 24 | Type 1 | FTTP/Mobile | Tesco Stores Ltd | Blackpool | FY4 4UJ |  | 6/9/2024:#Update - ECCS submitted. Awaiting approval, _x000D_5/9/2024:Your order has been delayed due to a customer missed appointment. Incorrect Product Please check with end user and reappoint the order if still required. _x000D_4/9/2024:Supplier Delay: KCI-3 (Order Completed) Delayed in Processing. _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:Supplier Delay: Delay encountered during automated test of new service _x000D_21/8/2024:Supplier Delay: Delay encountered during automated test of new service _x000D_20/8/2024:Supplier Delay: Delay encountered during automated test of new service _x000D_19/8/2024:Supplier Delay: Delay encountered during automated test of new service _x000D_19/8/2024:16/08/2024 15:12 _x000D_16/8/2024:0 _x000D_0 | 9/9/2024:#Update - ECCS submitted. Awaiting approval, _x000D_6/9/2024:#Update - ECCS submitted. Awaiting approval, _x000D_5/9/2024:Your order has been delayed due to a customer missed appointment. Incorrect Product Please check with end user and reappoint the order if still required. _x000D_4/9/2024:Supplier Delay: KCI-3 (Order Completed) Delayed in Processing. _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:Supplier Delay: Delay encountered during automated test of new service _x000D_21/8/2024:Supplier Delay: Delay encountered during automated test of new service _x000D_20/8/2024:Supplier Delay: Delay encountered during automated test of new service _x000D_19/8/2024:Supplier Delay: Delay encountered during automated test of new service _x000D_19/8/2024:16/08/2024 15:12 _x000D_16/8/2024:0 _x000D_0 | Update: Order Amended | #Update - ECCS submitted. Awaiting approval, | [5 empty] | VFP2454082 | 30022470 | 1.Provisioning |  |  | 2024-09-03 | 2024-09-30 | [13 empty] | 0
2109 | 107959 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | Tesco Stores Ltd | Sunbury-on-Thames | TW16 7BB | 2024-09-04 | 6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_0 | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_0 | Order Completed | 0 | [5 empty] | VFS1086443 | 30022477 | 2.Commissioning |  |  | 2024-09-03 | 2024-09-03 | 2024-09-03 11:53 | TRUE | [11 empty] | 0
2110 | 463338 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | Tesco Stores Ltd | OLDHAM | OL4 2GA |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_0 | 0 | 0 | [6 empty] | 30022475 | 1.Provisioning |  |  | 2024-09-04 | [14 empty] | 0
2111 | 464115 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | Tesco Ltd | Haverhill | CB9 0BQ | 2024-09-05 | 6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_0 | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:Order Completed _x000D_4/9/2024:Order Completed _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_0 | Order Completed | 0 | [5 empty] | VFS1086440 | 30022468 | 2.Commissioning |  |  | 2024-09-04 | 2024-09-04 | 2024-09-04 09:40 | TRUE | [11 empty] | 0
2112 | 415785 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | Tesco Stores Ltd | BATHGATE | EH48 2ES | 2024-09-06 | 6/9/2024:Order Completed _x000D_5/9/2024:Update: Order Completed by Supplier _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_0 | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:Update: Order Completed by Supplier _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_0 | Order Completed | 0 | [5 empty] | VFS1086439 | 30022471 | 2.Commissioning |  |  | 2024-09-05 | 2024-09-05 | 2024-09-05 10:30 | TRUE | [11 empty] | 0
2113 | 233542 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | Tesco | LONDON | NW2 1LZ |  | 6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_0 | 9/9/2024:0 _x000D_6/9/2024:0 _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_0 | 0 | 0 | [6 empty] | 30022473 | 1.Provisioning |  |  | 2024-09-06 | [14 empty] | 0
2114 | 425033 |  | Batch 7 Sep 24 | Type 1 | SoGEA/Mobile | Tesco Stores Ltd | Peterborough | PE6 8UD |  | 6/9/2024:Order Completed _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_0 | 9/9/2024:Order Completed _x000D_6/9/2024:Order Completed _x000D_5/9/2024:0 _x000D_4/9/2024:0 _x000D_3/9/2024:0 _x000D_2/9/2024:0 _x000D_29/8/2024:0 _x000D_28/8/2024:0 _x000D_27/8/2024:0 _x000D_22/8/2024:0 _x000D_21/8/2024:0 _x000D_20/8/2024:0 _x000D_19/8/2024:0 _x000D_19/8/2024:0 _x000D_16/8/2024:0 _x000D_0 | Order Completed | 0 | [5 empty] | VFS1086438 | 30022469 | 1.Provisioning |  |  | 2024-09-06 | 2024-09-06 | [13 empty] | 0